DFID Southern Africa

South African Partnership for Effective Development Cooperation

Full Business Case

August 2012
Intervention Summary
## South African Partnership for Effective Development Cooperation

What support will the UK provide?
The UK will provide £5,000,000 over the period from August 2012 to March 2015.

Why is UK support required?
What need are we trying to address? / South Africa has the potential to play a transformative role in reducing poverty on the African continent. As part of this role, the Government of South Africa (GoSA) has long engaged in some form of international development cooperation beyond its borders. Though precise figures are elusive, one 2006 estimate of total development assistance was between $363m and $475m. But the potential importance of South Africa as a development partner goes beyond its financial contribution. As an African country, South Africa can bring regional expertise and influence to development partnerships which OECD donors cannot. Its recent history lends it unique legitimacy in working on issues of conflict mediation and transitional justice. Its experience of HIV/AIDS and tuberculosis epidemics has left an unparalleled depth of knowledge on aspects of clinical research. / South African development cooperation is at a moment of transition. The priority given to a strengthened contribution to African development is set out in a range of policy statements and actions. At a continental level, a new South African Development Partnership Agency is being established. At a global level, South Africa is deepening cooperation with other “southern” powers – primarily Brazil, India, China and Russia, through the IBSA group and increasingly through BRICS. Although in many ways South Africa is still finding its feet as a fully engaged member of the international community, its position as sub-Saharan Africa’s leading economy and as an emerging development actor gives it an increasing voice in global development policy discussions. / However, there remain constraints on the effectiveness of these new development partnerships. The lack of an overarching development agency has limited South Africa’s ability to coordinate assistance strategically, to ensure that resources are allocated where the need is greatest, or to judge whether specific investments represent the best way to achieve results. South Africa lacks dedicated professional expertise in development management. And there is very little independent analysis or public discussion of South Africa’s regional development policy, including the channels through which it can achieve the greatest results or the specific roles its institutions and policies can best play within the range of existing actors. / What will we do to tackle the problem? / DFID will provide funding and expertise for three areas of activities: / i. Sharing models of organisational development, financial management, oversight and accountability, between the UK and South Africa. / ii. Facilitating dialogue between South Africa and others including the UK, on international development policy, programme design, research and evidence in targeted sectors. / iii. Enhancing evidence and facilitating debate on the potential impact of South African development cooperation. / Who will be implementing the support we provide? / We will work directly with the Department of International Relations and Cooperation to provide support as required for the institutional establishment of the new SA Development Partnerships Agency. We will also work through academia, think tanks, civil society and commercial service providers to commission new research and facilitate broader debate on the future of South Africa’s development cooperation.

What are the expected results?
What will change as a result of our support? / This programme will increase the transformational impact of South African development cooperation on poverty, under-development and marginalisation in Africa. We will contribute to this change by working with South African partners to put in place the institutions, skills and knowledge needed to implement successful development programmes and policies. / An indirect, but significant result of the intervention will be to strengthen the working partnership between the UK and South Africa on international development issues. We expect this to increase the results we can achieve together through collaborative work on policies and programmes in future. / What are the planned outputs attributable to UK support? / The programme will lead to four outputs: / i. The new South African Development Partnerships Agency is able to draw on international best practice / ii. South Africa has the skills needed to manage development policy and programmes professionally / iii. Programme design and resource allocation are based on sound evidence and policy knowledge / iv. South African engagement on global development policy issues is informed by high-quality independent analysis / How will we know whether the results have been achieved? / Indicators of the outputs, outcome and impact of this programme will be monitored routinely by DFIDSA. Through annual reviews of the programme we will assess how far the UK’s support has contributed to more effective South African development cooperation in Africa, and identify lessons for the UK’s future work with emerging development actors in future.

Contents

List of abbreviations	5

1 STRATEGIC CASE
A Context and need for DFID intervention	6
B Impact and outcome	11

2 APPRAISAL CASE
A Feasible options and theory of change	12
B Evidence base	16
C Costs and benefits of options	19
D Value for money measures	23
E Value for money statement	24

3 COMMERCIAL CASE	25

4 FINANCIAL CASE
A How much will it cost?	28
B How will it be funded?	28
C How will funds be paid out?	28
D What is the financial and fraud risk?	28
E How will expenditure be monitored and accounted for?	29

5 MANAGEMENT CASE
A Management arrangements	30
B Risks and management	30
C Conditionality	31
D Monitoring and evaluation	31

Activity approval proforma	Annex 1

Logical Framework	Annex 2

List of abbreviations

ARF	African Renaissance Fund
AU	African Union
BRICS	Brazil, Russia, India, China and South Africa
DBSA	Development Bank of Southern Africa
DFID	UK Department for International Development
DFIDSA	DFID Southern Africa
DIRCO	Department for International Relations and Cooperation
DST	South African Department for Science and Technology
G20	Group of 20 most industrialised nations
GDP	Gross Domestic Product
GNI	Gross National Income
GoSA	Government of South Africa
IBSA	India, Brazil and South Africa
IDC	Industrial Development Corporation
IMF	International Monetary Fund
MDGs	Millennium Development Goals
NEPAD	New Partnership for African Development
OECD	Organisation for Economic Cooperation and Development
SA	South Africa
SADC	Southern African Development Community
SADPA	South African Development Partnerships Agency
UK	United Kingdom

Strategic Case

A. Context and need for a DFID intervention / The context: South Africa and international development cooperation[1] / South Africa has the potential to play a transformative role in reducing poverty on the African continent. The South African economy dominates sub-Saharan Africa. It accounts for a third of Sub-Saharan African GDP. The country remains a gateway for private investment into Africa, including regional headquarters for African and multinational business and banking. It is the only African country represented in global forums such as the G20. And South Africa has a unique role in global development policy as a bridge between international poles: between ‘north’ and ‘south’; developing and developed world; ‘old world’ and ‘new world’ orders. / As part of this continental influence, the Government of South Africa (GoSA) has long engaged in some form of international development cooperation beyond its borders. Before 1994, this consisted of efforts to bolster support in a few African countries to overcome diplomatic isolation. But since the advent of democracy, South Africa has evolved a range of policies and instruments designed to promote economic and social development among its neighbours, both through national mechanisms and through hosting regional institutions such as the New Partnership for African Development (NEPAD), the African Peer Review Mechanism and the Pan-African Parliament. / The most visible component of this cooperation since 2000 has been the African Renaissance Fund (ARF), which aims to enhance cooperation within Africa (recipients include Zimbabwe and the Democratic Republic of Congo). The amount of funding disbursed, and the numbers of projects approved annually, has grown from six projects worth around £30m in 2007, to fifteen projects worth around £38m approved in 2011.[2] Funds are used in a range of sectors covering humanitarian assistance, electoral support, conflict prevention and resolution, debt relief, and private sector development. / But in financial terms, the ARF takes up only a small proportion of South Africa’s overall cooperation – around 3.8% in 2002 and 3.3% in 2004. Many government departments manage a variety of international projects funded from departmental budgets. And South Africa hosts a wide range of research for development, largely structured under the Department of Science and Technology (DST) and related institutions, and generally held in high regard internationally. / Two of South Africa’s domestic development finance institutions also have units responsible for regional development. The mandate of the Development Bank of Southern Africa (DBSA) was expanded in 1997 to include funding projects in SADC – about a third of funding is now for projects outside South Africa, largely in infrastructure. The Industrial Development Corporation (IDC) also had its mandate extended in 2001 to support the “African Renaissance”, largely through investment in mining, agro-processing, infrastructure and manufacturing. / Finally, South Africa is a significant contributor to regional and global multilateral development institutions. In the last replenishment cycles this included contributions of $11.2m to the African Development Bank; $10.3m to the Global Fund to Fight AIDS, Tuberculosis and Malaria; and $31.5m to the International Development Association of the World Bank.[3] These contributions are managed by DIRCO. At the June 2012 G20 summit South Africa announced that it would make $2bn available as a loan to the IMF to tackle financial instability in the Eurozone should these resources be required. / Though precise figures are elusive, one 2006 estimate of total bilateral development assistance was between $363m and $475m. South Africa has committed to increasing development assistance levels to between 0.2% and 0.5% of GNI, though no target date has been set.[4] But the potential importance of South Africa as a development partner goes beyond its financial contribution. As an African country, South Africa can bring regional expertise and influence to development partnerships which OECD donors cannot. Its recent history lends it unique legitimacy in working on issues of conflict mediation and transitional justice.[5] Its experience of HIV/AIDS and tuberculosis epidemics has left an unparalleled depth of knowledge on aspects of clinical research.[6] Amongst developing nations, South Africa is also one of the global leaders on social protection research, policy and programming. / New opportunities? Institutional changes and future strategy / South African development cooperation is at a moment of transition. The priority given to a continued and strengthened contribution to African development is clearly set out in current policy statements. The Presidency’s Medium Term Strategic Framework includes the objective to “create a better South Africa and contribute to a better and safer Africa and world”.[7] The National Planning Commission’s “Vision for 2030” notes that “the shift of global power towards developing countries provides South Africa with an opportunity to maximise its regional and international influence over the next 20 to 30 years”.[8] The successful effort to secure the Chair of the African Union Commission for Nkosazana Dlamini-Zuma in July 2012 is a further signal of the priority afforded to issues of regional security and development. / At a continental level, the DIRCO strategic plan for 2010-13 formalised as a priority “the establishment of a South African Development Partnership Agency (SADPA) to promote development partnerships with other countries on the continent”.[9] SADPA’s aim will be “to use development cooperation as a tool to advance South Africa’s foreign policy goals which seek to address issues of poverty, under-development and marginalisation on the African continent and the global South”. Programmes will “respond to the challenges of peace and security, infrastructure, building institutional capacity and deepening democratic governance”.[10] The agency will be established during 2012 within DIRCO, consisting of around 35-40 permanent staff under a Chief Executive Officer reporting directly to the Foreign Minister. It will subsume the activities of the African Renaissance Fund, though responsibility for development policy (as opposed to programme spend) will remain with DIRCO’s multilateral policy departments. / At a global level, South Africa is deepening cooperation with other “southern” powers – primarily Brazil, India, China and Russia, through the IBSA group and increasingly through BRICS, which it joined in 2011.[11] Though the ability of these groups to produce concrete outcomes has varied, development cooperation is one area where progress has been visible. An IBSA Trust Fund was created in 2004, and a BRICS Development Bank was agreed in principle at the BRICS summit in 2012. As host of the 2013 summit, South Africa will be instrumental in turning this agreement into a functional institutional framework. Both BRICS and IBSA have focused in their annual statements on the reform of global multilateral institutions, including the World Bank and International Monetary Fund – issues which are central to the future of global development architecture. / Although in many ways South Africa is still finding its feet as a fully engaged member of the international community, its position as sub-Saharan Africa’s leading economy and as an emerging development actor gives it an increasing voice in global development policy discussions. South Africa co-chairs the G20 Development Working Group; at the 2011 High Level Forum on Aid Effectiveness in Busan, it was a committed supporter of the principles around south-south cooperation; and has since been an engaged member of the Post-Busan Implementation Group.[12] In July 2012, the University of Pretoria hosted African civil society consultations on the future of the Millennium Development Goals after 2015. / The need: constraints to more successful development cooperation / The opportunity for South Africa to increase the impact of its development cooperation in Africa is significant. However, three potential constraints exist: / First, the lack of an overarching development agency has limited South Africa’s ability to coordinate assistance strategically, to ensure that resources are allocated where the need is greatest, or to judge whether specific investments represent the best way to achieve results. Outward development expenditure has been very difficult to track accurately, limiting the ability of both government and non-governmental organisations to hold departments to account for spend or the results achieved. The ARF has been heavily criticised by parliament for its lack of means to monitor expenditure and for ineffective resource allocation.[13] / Second, in addition to these institutional challenges, South Africa lacks dedicated professional expertise in development management. The ARF has been managed by DIRCO rather than by a separate unit; the administration lacks experience of the challenges of allocating development funds, managing them efficiently, applying procurement processes appropriately, managing programmes for results, evaluating the impact of interventions and applying lessons where relevant. South Africa has limited professional experience in designing and implementing development policy in specific sectors – including those where SADPA is likely to be most active, such as conflict prevention and in working with the private sector for pro-poor growth. / Third, there is very little systematic independent analysis or public discussion of South Africa’s regional development role, including the channels through which South Africa can achieve development results on the continent or how its institutions and policies can best complement the efforts of existing development actors.[14] This includes the relative value and the specific challenges of bilateral programming, trilateral cooperation, new ways of working within groups such as BRICS or IBSA, and contributions to multilateral agencies.[15] It also includes potential South African engagement with broader global policy debates such as the future of the Millennium Development Goals. / The evidence which underpins the analysis of need in this area is judged to be of medium strength, though it is largely qualitative in nature. There is good recent institutional analysis of South Africa’s development cooperation mechanisms, referred to where relevant above. However, given the fragmented nature of funding, reporting of development spend and results is extremely limited: no clear picture of South Africa’s development efforts exists. It is expected that the formation of SADPA, and the additional independent research generated in part through this programme, will go some way to improving this gap. / Why should the UK intervene? / DFID is committed to working with emerging powers to achieve regional and global development outcomes. In February 2011 the Secretary of State for International Development stated that “if the first dimension of our changing relationship is about working with emerging powers to tackle their own poverty, the next is to work with them to reduce poverty in other developing countries”.[16] The 2011 Busan Partnership for Effective Development Cooperation both recognises explicitly the valuable role of emerging economies as “important providers of South-South development cooperation”, and emphasises that as a means of achieving sustainable development results “lessons should be shared by all who participate in development cooperation”. Given South Africa’s potentially transformative influence on development in Africa, a constructive partnership is a priority for the UK’s objectives on international development. / The UK is in a position to share extensive experience of managing development cooperation, dating in various forms from the 1960s and in its present form since the establishment of the Department for International Development (DFID) in May 2007. DFID has been independently recognised as providing “global leadership on development issues”, based both on its commitments to continue increasing development assistance to meet the UN’s target of 0.7% of GNI by 2015 despite broader budgetary challenges, and its championing of policies to improve aid effectiveness.[17] Though the UK model of development cooperation differs greatly from that envisaged by South Africa in scale and in geographical reach, this accrued experience of development programme strategy and management, and of policy leadership, represents a valuable resource on which new South African institutions could draw more systematically. / Such a partnership would bring benefits for both sides. South Africa has unique experience, as set out above, in areas of development policy including conflict mediation, social protection and clinical research, and regional political relationships founded on a very different basis from those of the UK. DFID has previously supported South Africa to share its experience on social protection with other countries in Africa, Middle East and South Asia. In the slightly longer term, the UK’s model of development cooperation will need to evolve over coming years to take account of new actors and new global needs: on current trends, the dynamics of south-south cooperation will rapidly overtake “aid” as a driver of growth and poverty reduction in low income countries.[18] A comprehensive understanding of the emerging priorities and policies of new partners including South Africa will be critical to this evolution. / UK and South African foreign ministers agreed in June 2011 a shared strategy for cooperation across a range of policy issues. This included an explicit commitment towards “effective cooperation between SADPA and DFID, contributing to growth, development, stability and peace” across the region. DFID’s 2010-15 Operational Plan for its work in South Africa specifies that “we will help South Africa become a key provider of development cooperation across the region, including through the establishment of its development agency”. / This commitment has underpinned a constructive bilateral relationship on development issues over recent years. Senior officials from DIRCO and South African Members of Parliament visited London in May 2010 and March 2012 to study UK institutional structures for development policy and for public and parliamentary oversight of development financing systems. At the country level, DFID has hosted DIRCO and National Treasury officials to discuss the needs of the new agency in light of UK experience. / As a result of these shared discussions, in June 2012 the Director General of DIRCO confirmed a request to DFID for further support in a number of areas for SADPA, as part of on-going joint efforts to improve development cooperation in the region. This programme represents DFID’s response to that request.
B. Impact and Outcome that we expect to achieve / This programme will contribute to South African regional development cooperation having a transformative impact on poverty, under-development and marginalisation in Africa. This will be measured through proxy indicators of African development in areas that we expect SADPA to prioritise: economic growth and participatory governance. / The outcome of the programme will be that South African regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice. This will be measured through an increase in the proportion of outgoing development cooperation managed or coordinated by SADPA, and through South Africa’s participation in the multilateral processes to enhance development effectiveness agreed at Busan in 2011. / The outputs of the programme will focus on addressing the constraints identified here to more effective development cooperation: a functioning SA Development Partnerships Agency, evidence-based allocation of resources and design of programmes, professional implementation of policy and programmes, and informed engagement on global development policy issues. / An indirect, but significant result of the intervention will be to strengthen the working partnership between the UK and South Africa on international development issues. We expect this to increase the results achievable at regional, continently and global levels, through collaborative work on policies and programmes in future. Such opportunities may include: / Opportunities for trilateral cooperation on specific country-level development programmes between DFID and SADPA, once systems and skills are in place and priorities have been identified. This would contribute directly to DFID’s ability to achieve results in priority countries, and to the Structural Reform Plan commitment to “maintain momentum on actions to achieve the Millennium Development Goals with a focus on services for poor people”. / Closer policy collaboration in international and regional fora and processes on issues of global development, such as the role and structure of international financial institutions, the future of the global development agenda after 2015, and the implementation of Busan principles. This will contribute to DFID’s Structural Reform Plan commitment on “leading international thinking on development”.
[1] This section draws substantially on Sidiropoulos, South Africa: Development, International Cooperation and Soft Power, in Development Cooperation and Emerging Powers, London, 2012; Braude, Thandrayan, Sidiropoulos, Emerging Donors in International Development Assistance: The South Africa Case, International Development Research Centre, Ottawa, 2008; and Kragelund, The Potential Role of Non-Traditional Donors’ Aid in Africa, International Centre for Trade & Sustainable Development, Geneva, 2010.
[2] Figures are from Sidiropolous, 2012, quoting National Treasury Estimates of National Expenditure 2011.
[3] DATA Report 2011, ONE, www.one.org/data/
[4] DATA Report 2011
[5] Sherman, Gleason, Sidhu, Jones; Engagement on Development and Security: New Actors, New Debates, New York University, September 2011
[6] Shifting Paradign: How the BRICS are reshaping global health and development, Global Health Strategies Initiatives, New York, 2012
[7] Delivery Agreement: Creating a Better South Africa and Contributing to A Better and Safer Africa in a Better World, www.thepresidency.gov.za/pebble.asp?relid=4081
[8] Government of South Africa, National Planning Commission, National Development Plan: Vision for 2030, p.215
[9] Department for International Relations and Cooperation, Strategic Plan 2010-2013, www.dirco.gov.za
[10] http://www.pmg.org.za/report/20110803-department-international-relations-co-operation-legislation-establish
[11] Emerging Powers: India, Brazil and South Africa and the Future of South-South Cooperation, Woodrow Wilson Center, 2009
[12] See e.g. Glennie, Busan has been an expression of shifting geopolitical realities, The Guardian, London, 2 December 2011
[13] Parliamentary Monitoring Group, Briefing by Department of International Relations & Co-operation on legislation for establishment of SADPA, 2 Aug 2011. http://www.pmg.org.za/report/20110803-department-international-relations-co-operation-legislation-establish
[14] Yanacopolos, Public Perceptions of Development Cooperation: Summary Paper 5, South Africa, University of Cambridge, 2011, http://www.geog.cam.ac.uk/research/projects/foreignaidperceptions
[15] There have been some exceptions to this generally limited civil society engagement which indicate the level of future potential: see for example CIVICUS Submission to the International Consultative Seminar of South African Legislature, March 2011, on advancing MDG8 through a South African Development Partnership Agency
[16] Emerging Powers and the International Development Agenda, Andrew Mitchell MP, Chatham House, 15 February 2011
[17] DATA Report 2011, ONE. OECD-DAC Peer Review of the UK, 2010, http://www.oecd.org/dataoecd/49/20/45519815.pdf
[18] See for example Kharas and Rogerson, Horizon 2025: Creative Destruction in the Aid Industry, ODI, London, July 2012

Appraisal Case

A. What are the feasible options that address the need set out in the strategic case? / This section sets out the logic by which this programme is expected to contribute to more effective South African development cooperation in Africa, and considers options for the management of the intervention. / A theory of change / The theory of change for this programme is set out diagrammatically in figure 1 below. The key elements of this are as follows. / The problem identified in the strategic case is that the potential contribution of South African development cooperation to transformation in Africa is currently constrained: by fragmented institutional structures, by a lack of processes and skills to allocate and manage resources for greatest impact, and by limited analysis within and beyond government of how that influence can best be channelled through bilateral, trilateral and multilateral mechanisms. An opportunity exists with the establishment of SADPA for the UK and South Africa to work in partnership to address those constraints. / The desired impact for the programme, in line with the South African government’s aspirations for SADPA, is that South African development cooperation has the greatest possible impact on transforming poverty, under-development and marginalisation in Africa. In turn, that will contribute to enhancing South Africa’s overall positive influence on development in Africa. / To contribute to this impact, DFID will provide financial inputs and expertise to facilitate three sets of activities: sharing international institutional experience on the successful management of development cooperation; increasing dialogue between South Africa and other development actors on policy and programming in selected sectors; and conducting independent research to strengthen the evidence base on South Africa’s regional development cooperation. / Together these will drive a combination of processes to achieve change: working directly with those in the Government of South Africa responsible for the management of development cooperation; and working indirectly through other actors in academia, think tanks, civil society, Parliament and the media who will shape future South African development policy. / These processes will result in a set of outputs which, taken together, will enable South Africa to develop a stronger set of institutions, skills and knowledge to design and implement development policy for results in Africa. This reflects two assumptions: / First, that sharing the experience and operating models of the UK and others for managing development cooperation can help to enhance the potential impact of South African institutions, including SADPA, for development results. / Second, that closer collaboration on development policy in priority sectors will help shape programme design for greater impact. / The evidence base for these is set out in Section B below. / Finally, we recognise that South African development cooperation is only one component of the country’s overall influence in Africa. The contribution of South Africa’s broader role on development policy in regional, continent and global fora such as the G20 is another critical element (addressed in parallel through the complementary DFID programme on Global Economic Governance). The impact of private South African investment on poverty in Africa is a third element which is not addressed by this programme and which could have potentially even greater implications for continental pro-poor growth. / Figure 1: theory of change / Feasible options for the intervention / Based on this theory of change, we have identified three feasible options for a UK intervention, which are set out below. / 1. Do nothing (continue providing non-financial institutional support). / This option represents a continuation of “business as usual”. DFIDSA could maintain ad hoc support to DIRCO on technical issues linked to the establishment of SADPA, though without a dedicated funding channel for this work. There would be no formal measurement of the outcome and impact of this cooperation. / Other development partners (including Canadian and Norwegian development agencies) would continue to provide a range of technical expertise to SADPA on the establishment of systems and policies. / DFIDSA would not have in place any mechanism to commission new research on South African development cooperation, though we could use existing staff time (and, to a limited extent, DFID’s research helpdesk facilities) to conduct simple studies and evidence-gathering exercises on critical issues. / 2. A flexible partnership on institutional and policy development / This option would take a flexible and responsive approach, managed within DFIDSA alongside DIRCO and other partners, to achieving the four outputs set out in the strategic case. It would involve agreeing the results expected at output, outcome and impact level, and an initial set of activities to deliver those. / Given the changing institutional and political context in South Africa, DFID would need to be ready to appraise and (if appropriate) support additional activities throughout the life of the programme. The portfolio of activities would be reviewed on a regular basis by a programme steering committee to monitor progress and agree the range of interventions funded under the programme. / Specifically, for each area of activity: / i. Sharing international models of organisational development, financial management, oversight and accountability. / What results would we achieve? A range of initial areas for technical institutional cooperation have already been identified in correspondence with DIRCO. [19] These include the following, though we would be ready to alter these based on changing requirements: / Organisational development: the roles and structures needed to manage development cooperation / Establishment of public oversight and accountability mechanisms for official development spending / Sharing expertise on Parliamentary and non-governmental roles in overseeing development cooperation / Communications for development: building public awareness of and support for international development / Information technology systems for managing development cooperation / Monitoring and evaluation systems to manage programmes for results and incorporate evidence into future interventions. / How would we work to achieve these? Primarily these areas would be addressed through an institutional partnership between DFID and SADPA, sharing expertise and experience in order to provide the Government of South Africa with a possible model for its development cooperation. Beyond this, DFID would engage other organisations – within the UK Government (e.g. the National Audit Office), within the broader public sector (e.g. Parliamentary Committees), and in the private sector (e.g. independent consultancy services in particular areas) as required by DIRCO to meet specific needs and to achieve best value for money. / ii. Facilitating dialogue between South Africa and other development actors, including the UK, on development policy, research and evidence in targeted sectors. / What results would we achieve? We would focus initially on two areas of development policy identified through discussions with DIRCO for closer cooperation with the UK: working with the private sector, and development and stabilisation in post-conflict environments. / These are areas in which DIRCO has already expressed an interest and are a core focus of DFID’s 2011-15 Structural Reform Plan, which includes commitments to “collaborate more closely with the private sector on development” and to “improve the effectiveness of DFID investments in fragile and conflict-affected countries” in line with agreements made at Busan. / How would we work to achieve these? Under this option, results would be achieved through three channels: / Structured bilateral dialogue directly between DFID officials and those working on related issues in GoSA. For example DIRCO have expressed interest in a visit by officials to the UK Stabilisation Unit. / Engagement of academia, think tanks and civil society in South Africa, the UK or elsewhere to build understanding around current and potential South African engagement in these areas, and to provide non-governmental fora for dialogue on development policy. This could include engaging the Institute of Security Studies to review and facilitate policy discussion on the potential role of conflict-related development cooperation. / South-South cooperation in international development policy. The programme could facilitate links between government departments, academia, think tanks and other civil society organisations in South Africa and other emerging providers of development cooperation to share expertise on development policy issues. / iii. Enhancing local and international evidence on the current and potential impact of South African development cooperation to guide policy decisions. / What results would we achieve? We would initially address three broad areas of research to help build a better shared understanding of the role and impact of South African development cooperation policy and programmes, and specifically on how best to focus UK/SA partnerships on development. This would include three broad areas of enquiry: / How can South African bilateral development cooperation best achieve results for transformation in Africa, including in partnership with others? What is the contribution of South African cooperation compared to other existing actors in Africa? / What opportunities exist for South Africa to enhance its development impact through multilateral fora including the BRICS, IBSA, the G20 and the post-Busan implementation process, and how can existing development actors such as the UK best support this engagement? / What are South African interests in broader global debates on international development policy – such as the future of the Millennium Development Goals – and how can South Africa best engage in these processes? / How would we work to achieve these? Under this option DFIDSA would build evidence on these issues in two ways. Activities would be selected to complement DFID’s centrally-commissioned research on emerging powers, with a specific focus on South African development policy and instruments. / Through selected research proposals from South African and UK institutions, based on an appraisal of relevance and value for money. The Institute for Global Dialogue have proposed a research programme on South African development diplomacy which would address the first and second issues above. The South African Institute for International Affairs has proposed work on South Africa’s role in BRICS and its impact on development engagement in Africa; / Through competitive procurement of research to fill knowledge gaps, where these are not covered by the first two options. / Subcontract institutional support for DIRCO in establishing SADPA / The third option considered would be to procure independent services to achieve the results discussed above under a single contract managed by DFID. / This would target results in the same areas set out above under option 2. DFID would formulate terms of reference which specify the outputs required and broad areas of activity. A service provider or consortium would be expected to: / Work closely with DIRCO and other GoSA departments to provide technical support on organisational development, oversight structure, and skills development, drawing on international best practice; / Facilitate informed policy dialogue on the areas of development policy described above, convening governmental and non-governmental experts from the UK, South Africa and elsewhere to enhance understanding of development policy on all sides; / Conduct or commission research on effective South African development interventions to address the areas of enquiry set out above.
B. Assessing the strength of the evidence base for each feasible option / This section considers evidence around two questions which are critical to the theory of change set out above, and to the potential effectiveness of the proposed options 2 and 3. / Can sharing the UK’s operating model make South African institutions more effective? / DFID recently reviewed evidence on the most successful methods for donors to support institutional strengthening for parastatal and similar organisations.[20] This is directly relevant given options being considered here around different forms of institutional support to SADPA. The review concluded that robust evidence in this area is weak, given the lack of rigorous evaluations that have sought to compare different intervention strategies rather than the outcomes of specific projects. / The review found that longer-term twinning arrangements between institutions are the preferred option to develop sustainable organisational capacity. It is important that such arrangements be viewed by both sides as organisational cooperation, with twinned organisations carrying equal responsibility for progress.[21] Providing technical assistance at the individual level is unlikely to lead to enhanced organisational performance: focusing on the structure of organisations and systems is more likely to achieve results.[22] Finally, consistency of support is a frequent weakness of interventions. Institutional gains are often lost through staff turnover, particularly if interventions do not address demand for improved public sector performance as well as the supply of skilled personnel.[23] / Can closer collaboration on development policy increase the results of interventions? / The debate on the determinants of successful development interventions is extensive. However, robust analysis on the role of evidence in improving policy outcomes is sparse. The few available studies on the evidence-policy link are largely based on sector specific policies such as health and agriculture. One 1998 World Bank study derives a benefit:cost ratio in the range of 4:1 to 8:1 for the efficacy of sector analysis in delivering development impact in developing countries;[24] however, the paper is based specifically on the World Bank’s economic and sector work between 1991-94, and such findings have not been corroborated by any other notable studies, hence should be treated with caution. / The absence of credible benefit:cost ratios does not detract from the theoretical literature, largely from health and agriculture, which shows that good and timely evidence can play a crucial role in the design of policies. A separate World Bank study in 2004 assessed the importance of development agency incentives and processes on aid quality, and concluded that “design is an essential component of aid quality […] aid is not donor-neutral and its quality is not exclusively determined by the characteristics of its recipients”. [25] Overall evidence suggests that, provided that policymakers’ intentions are aligned with positive development objectives, quality research and evidence can improve the effectiveness of policies by addressing information failures. The benefits are likely to be greater the earlier they are addressed in an institution’s development. [26] / Table 1: summary of evidence for options / Option Evidence rating / 1: no new intervention Limited. We have very limited evidence either on the past impact of South African development cooperation, or to predict its future evolution. From current examples of UK/SA cooperation on development issues, and from DFID’s work with emerging donors in China and Brazil, we have anecdotal evidence that such partnerships can help improve bilateral relationships and lead to new opportunities for collaboration on policy and programmes. These would be missed if no new intervention was put in place. / 2: flexible institutional partnership Medium. Some evidence as above that partnerships between institutions are more effective than technical assistance in bringing about improvements in performance. Evidence suggests that better knowledge on programme design is an important determinant of more effective development interventions, but questions exist around how best to make sure that knowledge is put into use. / 3: subcontracted institutional support Medium. Evidence suggests external technical assistance faces challenges as a means of bringing about institutional improvements. Evidence on improving programme design is as for option 2. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Any potential negative impact on the climate and environment under options 2 and 3 can be managed in such a way as to be negligible. All options including the counterfactual present opportunities for positive impact where South Africa delivers sustainable development interventions, drawing on international best practice for climate change and environmental management (through enhancing knowledge, evidence base and systems). Opportunities under options 2 and 3 would provide a platform to share evolving DFID “best development practice” on climate change responses and environmental management, should this be required or requested by DIRCO. / Any future impact from South Africa’s bilateral development policy, programmes and plans should be delivered in such a way as to mitigate negative impacts and enhance positive opportunities for the environment. The nature of this programme could support this process. / South Africa’s engagement in international development fora also has the potential to influence for positive climate and environment outcomes at a continental or global level. / South Africa is well resourced in term of specialist climate and environment expertise. Opportunities may exist to share south African best practice with the UK, within Africa and globally. / Table 2: summary of climate change and environment opportunities and risks / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1: no new intervention C (low risk) C (low opportunity) / 2: flexible institutional partnership C (low risk) B (medium opportunity) / 3: subcontracted institutional support C (low risk) B (medium opportunity)
C. What are the costs and benefits of each feasible option? / Resource costs / The total resource costs to DFID will be the programme funds available for activities, plus the cost of managing the programme. / We have estimated that total programme funds of £5,000,000 will be required to generate the results set out in this business case. This estimate takes into account discussions with DIRCO on institutional support required, and analysis of the costs of suppliers. The total requirement for programme funds will be monitored by the programme steering committee as set out in the management case below, and revised if necessary as part of the annual review process. / Management costs will differ for options 2 and 3. These have been estimated through a cost-effectiveness analysis as set out in the table below. This is based on available estimates of the total resource cost of HMG staff time for option 2; and on consultancy fee benchmarks for option 3. It assumes that tasks would take HMG staff and consultants the same amount of time. The costs of HMG staff are quantified here as opportunity costs rather than as new financial costs to DFID. / We estimate that the programme will require 5% of an A1 DFID staff member; 15% of an A2; 5% of a B1; and 5% of a C1. These reflect assumptions about the proportion of DFIDSA staff time required to manage this work. Similar time proportions have been applied to equivalent levels of consultancy staff for comparison. / The resulting analysis shows that in present value terms, it would cost around £73,500 for HMG staff to manage the programme compared with £108,400 for consultants. Thus the in-house option (option 2) is around 70% of the cost of subcontracting services. / Table 3: analysis of management costs for options / Option 2 Option 3 / Year 0 £28,105 £42,130 / Year 1 £23,768 £34,700 / Year 2 £21,607 £31,545 / Total £73,481 £108,375 / Economic benefits / Although the analysis above suggests that option 2 is the most cost effective, it provides no evidence of whether the programme itself generates net economic benefits. To answer this question, a basic cost-benefit analysis has been conducted for option 2. This is based on four assumptions: / The costs used in this analysis are comprised of the financial programme costs of £5 million, plus imputed administrative costs of £73,500. / The total resources available for South African development cooperation are based on an estimate of 0.18% of South African GDP: around current levels, and at the bottom end of the range targeted by the Government of South Africa. This results in a total of £480m annually, which is held static over the period to further reduce any optimism bias. / We assume here that SADPA will disburse or coordinate two-thirds of those resources by the third year of the programme, and that this intervention can potentially affect the impact of that proportion. / Costs and benefits are discounted at 10% over the programme’s lifespan. / Although we would expect effectiveness gains to continue after the 3 year programme, the approach adopted here ignores post-programme benefits. This reflects the increasing difficulty of making any plausible assumptions around attribution after the programme has ended. / Using these assumptions we have calculated the economic benefits of an increase in the effectiveness of South African development cooperation of 1%, 2% and 4%. A 2% increase in effectiveness would mean, for example, that every R1m spent produced an additional R20,000 of economic benefits. This is presented as a simple, indicative means of judging the potential economic benefits of the programme, given the lack of more robust evidence discussed above and the difficulty of attributing improvements directly to UK interventions. / Table 4: present value and net present value of benefits / Program year Scenario 1- low effectiveness gains, ~1% Scenario 2- mid level effectiveness gains, ~2% Scenario 3- high effectiveness gains, ~4% / PV of benefits NPV[27] PV of benefits NPV PV of benefits NPV / Year 0 0 -£528,105 0 -£528,105 0 -£528,105 / Year 1 £2,927,742 -£722,155 £5,855,484 £3,649,897 £11,710,967 £9,505,381 / Year 2 £1,330,792 -£426,353 £3,992,375 £2,235,231 £7,984,750 £6,227,606 / Total £4,258,534 -£232,302 £9,847,859 £5,357,023 £19,695,718 £15,204,882 / Table 5: Benefit-cost ratios for 3 scenarios / Effectiveness scenarios Benefit:Cost Ratios / Scenario 1- low effectiveness gains 0.94 / Scenario 2- medium effectiveness gains 2.16 / Scenario 3- high effectiveness gains 4.33 / Based on the assumptions made here, under the medium to high end scenarios, the programme could generate significant net benefits. The low end scenario represents a situation where only very low levels of gains in effectiveness result from the programme: for example because assumptions about the ability of activities to generate improvements in development effectiveness prove inaccurate. Under this situation, costs would exceed benefits over this period by approximately £232,000. / Thus, the programme is considered to offer positive economic returns over three years if we judge that the UK’s contribution would generate an improvement in effectiveness of South African development cooperation of at least 2%. Over a longer time period, much smaller sustained economic benefits would represent a positive return. / Social benefits / Sub-Saharan Africa has 12% of the world’s population and is home to just under a third of the world’s poor. Africa needs economic growth to reduce poverty, but its economic and political geography presents some significant challenges that will never be overcome through working at country level alone.[28] This programme design has the potential to build long-term capacity and relationships to increase the impact of South African development assistance for transforming poverty, under-development and marginalisation in Africa, as well as to increase African voice on global agendas for poverty reduction. / South Africa’s experience of democratisation, conflict resolution and poverty reduction (particularly in social protection) promises useful lessons for other developing countries in Africa. South Africa is well placed to share its experience, given its progressive Constitution. The Ibrahim Index of African Governance places South Africa at number 5 in the Continent. The international advocacy group, Human Rights Watch states in its 2011 World Report: “South Africa's pro-human rights constitution, stable government, democratic institutions, independent judiciary, and strong economy mean it has great potential to become a global human rights leader”. South Africa’s enabling legal and operating framework for civil society has much to offer in good practice, in the context of declining space for civil society across many African countries. It has been a strong voice in the development of SADC and AU Social Policy and gender mainstreaming. / Option 1: Doing nothing means the opportunity is missed for more coherent and strategic support to SADPA, for more effective and measurable results and partnerships for poverty reduction. / Option 2: Coherent and flexible support to a new South African Development Partnership Agency offers significant potential for the advancement of MDG 8 (joining government, the business sector and civil society to forge a ‘Global Partnership for Development’) and Outcome 11 of the South African Presidency’s Development Outcomes Framework. Setting up such an agency will help institutionalise as well as make visible South Africa’s development cooperation efforts in Africa and beyond.[29] As identified in civil society consultations, it will be critical that decision makers carve a unique niche for SADPA that focuses on South Africa’s recognised strengths and evidence-based development policy and interventions for poverty reduction. / Option 3: Less opportunity for direct relationship building and exchange of experience with SADPA officials and civil society organisations. / Political risks and benefits / The most significant risk to this intervention is around the level of political commitment to the successful establishment of SADPA on the part of the Government of South Africa, and to working in partnership with the UK. Evidence in this area in the recent past has been mixed. On one hand, as set out in the strategic case above, statements of policy point to an opportunity around the new agency and pan-African ambition. On the other, progress on the details of enabling legislation has been slow, and other development partners have struggled to initiate plans for trilateral programming with DIRCO. This affects the options under consideration in different ways: / “Doing nothing” would limit DFID’s exposure to this risk; however it would offer no opportunities to help advance the process of establishing development institutions, and therefore risks losing future opportunities for more concrete cooperation on policies and programmes. / Option 2 would enable DFID, working with the British High Commission in Pretoria and Cape Town, to monitor political views on this issue closely and respond in a graduated way to help maintain momentum as far as possible. This could include high-level official or Ministerial contact to reaffirm the importance the UK attaches to this agenda. / Option 3 would carry the highest risk in this area: the value of outsourced technical assistance would be highly vulnerable to a lack of political buy-in, and DFID would have less ongoing visibility of any increase or decrease in support for the development agenda within GoSA. / Table 6: summary of costs and benefits of all options / Option 1: no new intervention Option 2: flexible partnership Option 3: support contract / Resource costs No additional resource costs Programme costs: £5,000,000 / Opportunity costs of management by DFID: / £73,481 Programme costs: £5,000,000 / Financial cost of subcontracting management: around £108,375 / Estimated economic benefits No new economic benefits Between £4.3m and £19.7m over three years As for option 2 / Other unquantified benefits and risks Missed opportunities for deeper institutional partnership / Political risks to delivery avoided; but no new opportunity to support political commitment to development results Maximum opportunities to strengthen institutional links between DFID and SADPA / Political risks to delivery; but can be closely monitored and responded to. Limited opportunity for stronger institutional partnership / Most vulnerable to any decline in political commitment / Estimated benefit:cost ratio Costs would equal benefits (both zero). Estimated between 0.94 (low scenario) and 4.33 (high scenario) Marginally lower than option 2 given additional management costs / Based on this analysis, option 2 is judged to represent the best balance of costs and benefits for the implementation of this programme.
D. What measures can be used to assess value for money for the intervention? / Effectiveness / The programme logframe includes a range of quantitative and qualitative indicators to ensure that activities are achieving the planned outputs. / The ability of the programme to achieve quantifiable economic benefits through improving the effectiveness of South African development cooperation, in a way which is attributable to DFID, will be very challenging to monitor objectively. DFID will assess evidence about the links between activities, outputs and outcomes through annual reviews. / Efficiency / The efficiency with which the programme turns inputs into agreed outputs and outcomes will be determined largely by its ability to respond flexibly to changing needs and to evidence on which components are performing well. The option appraisal set out above provides assurance that management costs have been minimised. The quarterly steering group meeting will review activities under this programme, monitor progress against outputs and outcomes, and determine any required changes in the range of activities. / Economy / Economy of programme inputs will be assured at the level of individual activities under this programme. Through the approval process set out in the management case, DFID will scrutinise budgets and payments to project implementers. We will for example expect to see evidence that administrative costs remain within 10% of programme spend, in line with DFID guidance; that all travel costs have been minimised through the use of the cheapest routes and classes; and that any subcontracts represent the best possible value for money through good procurement practice.
E. Summary Value for Money Statement for the preferred option / There is a strong value for money justification for the intervention overall. In purely economic terms, an increase in the effectiveness of South African development cooperation of 2% or more, attributable to this programme, would result in positive economic benefits over the life of the programme. A smaller increase in effectiveness would demonstrate positive returns over a longer period. / However the non-quantifiable benefits of the programme will be equally significant in providing value for UK investment. These include a stronger institutional partnership between the UK and South Africa on international development issues, which we expect to create future opportunities for joint programmes in third countries and to facilitate closer cooperation on priority issues of global development policy. / The case for the specific option identified here is also strong: it minimises management costs for DFID, while simultaneously providing the best opportunities to develop close institutional links with South African partners and enabling DFID to monitor political risks to the programme and respond accordingly.
[19] Letter from Head of DFIDSA to Director General DIRCO, 14th March 2012
[20] DFID Human Development Resource Centre, Helpdesk Report #86, Institutional Strengthening of Parastatal Organisations, January 2011
[21] E.g. Jones, Twinning as a Tool for Sustainable Organisational Capacity Building, Capacity.org Issue 6, 2000; Nwamuo, Partnership – An Instrument for Capacity Building, Capacity,org, Issue 6, 2000
[22] E.g. Capacity Development in Africa: An OED Evaluation of World Bank Support, WB Evaluations Department, 2005
[23] E.g. PNG Cluster Evaluation of three institutional strengthening projects, AusAID Evaluation www.ausaid.gov.au/publications/pdf/qas03.pdf
[24] Deininger, Squire, Basu; Does Economic Analysis Improve the Quality of Foreign Assistance?, World Bank Economic Review, Volume 12 Number 3, 1998
[25] The Quality of Foreign Aid: Country Selectivity or Donor Incentives? World Bank Policy Research Working Paper 3325, June 2004
[26] Kennerley & Mason, The Use of Information in Decision Making: Literature Review for the Audit Commission, Cranfield School of Management, 2004; Moynihan, Dangerous Discrepancies between Experts and Evidence, 2004 www.milbank.org/reports/2004Moynihan/040330Moynihan.html
[27] NPV is derived simply by subtracting the PV of costs from the PV of benefits
[28] DFID Africa Regional Operational Plan 2010-15.
[29] CIVICUS Submission to the International Consultative Seminar of South African Legislatures 2011

Commercial Case

A. Clearly state the procurement/commercial requirements for intervention / The programme will be managed in-house by DFID South Africa, for the reasons set out in the appraisal case above. At the overall programme level, there are no procurement implications (i.e. DFID will not outsource its management to a third party). However, there will be a range of procurement implications (both direct and indirect) for individual activities. These will broadly fall into three categories: / Activities managed and implemented by DFID or UK government partners. This will include sharing expertise directly with DIRCO on areas of development cooperation such as programme cycle management and communications; and working through UK public bodies including Parliament and the National Audit Office to share expertise in areas such as public oversight and accountability. / Activities implemented through non-governmental partners in South Africa or the UK, procured indirectly through grant arrangements. This mechanism will be used where partners are not-for-profit organisations who have proposed work which contributes directly to one or more of the outputs of this programme, and where DFID assesses that such an organisation is best placed to do such work in a way which represents best possible value for money. / Activities procured competitively from commercial suppliers. This mechanism will be used where DFID or other UK government partners cannot provide required services directly for reasons of expertise or capacity, and where needs are not met by work proposed independently by organisations (or where such proposals are not of sufficient quality). This could include the provision of professional services to DIRCO on issues such as organisational development, or commissioning focused research on the impact of particular development policies. / The approval process for activities within this programme, which is described in the management case below, will include consideration of the commercial implications at the activity level. This will follow DFID compliance requirements. DFIDSA has adequate specialised procurement expertise to provide case-by-case advice.
B. How does the intervention design use competition to drive commercial advantage for DFID? / Competitive procurement will be used where a need for services is identified by DFID or DIRCO. Outcome- or output-based terms of reference for any such services will be agreed by the programme steering committee and either sourced through existing competitively tendered frameworks or published for new bids according to normal DFID procurement processes. Advice from the DFIDSA procurement team on a case-by-case basis will ensure that the agreed process achieves maximum value for money for DFID resources. / A stated subsidiary aim of this programme is to enhance the partnership between the UK and South Africa on global development issues. Though all competitive tenders will be open to international competition according to normal DFID procedure, bidders will be expected to demonstrate how they would contribute to this aim as part of the terms of reference.
C. How do we expect the market place will respond to this opportunity? / We judge that there is a moderately wide range of organisations within South Africa who have the expertise, competence and interest to engage more substantively on issues of South African development cooperation. For example, the Institute for Global Dialogue have a stated ambition to be a “centre of expertise on South African development cooperation”. The SA Institute for International Affairs are developing a new strand of work on African development and the BRICS. The Institute for Security Studies have identified opportunities to conduct analysis of peacebuilding and security interventions to inform future development policy. All are internationally recognised research organisations with the potential to make a significant contribution to these agendas. / This programme is also intended in part to stimulate new and wider debate and understanding around South African’s development policy and programmes. We expect that a wider range of local organisations will consider working in this area, as a consequence of DFID support being made available for work which contributes towards the outcome of this programme. This also creates a mechanism to engage a wider range of international institutions (primarily but not exclusively from the UK, such as ODI and Chatham House) in collaborative work on South African development cooperation where this can add value. / Finally, the programme will create an incentive and a mechanism for DIRCO to specify more clearly its own expectations and requirements of non-governmental and commercial partners in establishing structures for development cooperation and improving policymaking in this area. We expect this to help focus market opportunities on those which are of most direct benefit for public policy and for development outcomes.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The financial costs of this programme will primarily be for the time of external experts conducting research and providing direct policy advice, for flights and other transport, and for accommodation and meeting facilities. All costs will be clearly set out by implementing partners prior to activity approval by DFID. These will be assessed at the activity level, and through the programme’s annual review, to ensure they are in line with cost benchmarks established through other DFIDSA programme activity.
E. What is the intended procurement process to support contract award? / A range of procurement processes may be used according to the type of award envisaged under “commercial requirements” above: / For activities managed and implemented by DFID or UK partners, in most cases no procurement process will be required. Should UK government departments incur additional costs which cannot be met from existing budgets, DFID will put in place a standard Memorandum of Understanding to reimburse costs from this programme. / For activities implemented through non-governmental partners in South Africa or the UK, in most cases accountable grant arrangements will be put in place. The process will follow DFID compliance requirements to ensure that partners have satisfactory systems for management and reporting of UK funds. For grants under £1m we will consider using an exchange of letters rather than a formal accountable grant, where this would be a more proportionate solution. Such letters will set out in full payment, monitoring and audit requirements as set out in DFID’s compliance guidelines. / For activities procured through competition, commercial contracts will be put in place. Where possible we will use existing framework contracts to source services, where these ensure that competitive rates have already been agreed. If this is not possible we will use new commercial tender process appropriate to the level of the contract (including OJEU processes if the value exceeds the OJEU threshold).
F. How will contract & supplier performance be managed through the life of the intervention? / Results of each activity, which contribute explicitly to the outputs and outcomes in the logframe attached to this business case, will be agreed with each implementing partner under this programme. For activities costing over £250,000 a full embedded logframe will be agreed with the partner. For activities below this threshold a clear set of expected results will be agreed in an appropriate and proportionate format. / These agreed results will be used to manage the performance of all implementing partners, including through contractual outcome- and output-based agreements where these are in place, or through quarterly grant reporting to trigger financial disbursements where relevant. / Formal monitoring and reporting arrangements will be agreed with individual implementing partners on a case-by-case basis and approved by the programme steering committee.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total financial cost of the programme is £5,000,000 over the period from 20 August 2012 to 31 March 2015, covering the three financial years 2012/13, 2013/14 and 2014/15. / This is based on an initial estimate of need for the three areas of programme activity as set out below. Financial allocations, forecasts and future needs will be revised by the programme’s steering committee on a quarterly basis, with any changes to overall budget agreed as part of the programme’s annual review process. / Table 7: financial costs of programme activities / Year 0 / 2012/13 Year 1 / 2013/14 Year 2 / 2014/15 Total / Institutional support to SADPA £100,000 £200,000 £200,000 £500,000 / Facilitating policy dialogue £250,000 £500,000 £1,750,000 £2,500,000 / Building evidence on SA development cooperation £150,000 £350,000 £1,500,000 £2,000,000 / Total £500,000 £1,050,000 £3,450,000 £5,000,000
B. How will it be funded: capital/programme/admin? / The intervention will be funded from DFID’s Global Development Partnerships Programme (GDPP). An indicative allocation of GDPP funds for DFID Southern Africa was made in May 2011 of £19m over 2011-15.
C. How will funds be paid out? / Payment mechanisms will differ for the activities funded under this programme, as set out in the commercial case above. / Details of payment mechanisms for each implementing partner will be agreed through the approval process outlined in the management case.
D. What is the assessment of financial risk and fraud? / We assess that the financial and fraud risk for this intervention is low. / All funds paid on the basis of accountable grants, contracts, or exchanges of letters, will be subject to formal detailed financial reporting agreed with implementing partners in line with DFID compliance tasks. This will greatly reduce the risk of funds not being used for their intended purpose. / Any specific financial risks linked to individual activities will be identified through the activity approval process set out in the management case, along with any mitigation strategy required. / We do not currently envisage direct transfers of funding to the Government of South Africa under this programme. However we note that according to routine DFID fiduciary risk analysis the risk for central government operations is judged to be low, and there are sufficient controls in place around the National Treasury’s receipt of donor funds. These include annual audits which are available to the public.
E. How will expenditure be monitored, reported, and accounted for? / Individual activities will include discrete monitoring and reporting arrangements, agreed through the approval process in the management case. / The programme’s steering committee will review overall programme expenditure and requirements on a quarterly basis. / The overall programme will be subject to annual review in August 2013 and August 2014, and a programme completion report in April 2015, which will include a review of spend against forecasts and an assessment of value for money.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The programme forms part of DFID’s engagement with emerging powers through its Global Development Partnership Programme (GDPP). Strategic direction for DFID’s work in this area is provided by the National Security Council, by the Secretary of State and Ministers for International Development, and by the Emerging Powers Directors’ Group, chaired by the Director General, Policy and International. / The programme will be overseen by a steering committee chaired by the Head of Global Development Partnerships in DFIDSA, and consisting of: / The Deputy Head of DFIDSA, who will ensure that activities and results contribute to broader DFIDSA objectives, and who will provide assurance (within her delegated authority of up to £5m) that approved activities meet DFID compliance requirements. / The 2nd Secretary (Political Internal) from the British High Commission, who will advise on the political feasibility of proposed activities and the complementarity with other work funded from BHC programme funds; / The Global Partnerships Policy Adviser from DFID London, who will advise on lessons from GDPP work in other emerging powers and contribution to corporate objectives around development effectiveness (including Busan follow-up); / A representative of SADPA has been invited to attend once suitable capacity is in place within DIRCO. The SADPA structure is expected to include a “Policy and Learning Team” from which an attendee could be identified. / The steering team will meet on a quarterly basis or more often if required, in order to: / Consider and approve activities to be funded through this programme to achieve the results set out in this business case. A proforma setting out the relevance of proposed activities, the value for money and commercial implications, and results-based management processes for each activity, is attached to this business case at annex 1 and will be the basis for decisions. / Review results achieved by the programme and agree any additional actions necessary (such as commissioning further work in slow-moving areas). / Review spend and forecasts for the programme. / Agree formal monitoring processes including annual reviews. / The DFIDSA Head of Global Development Partnerships will be responsible for overall management of the programme as well as for work planning, quality assurance, monitoring and dissemination activities.
B. What are the risks and how these will be managed? / Risks associated with specific interventions, alongside appropriate management strategies, will be captured at the intervention level and scrutinised by the steering committee. / The highest level strategic risk associated with the programme is that South African development cooperation, however professionally implemented and efficiently allocated, will fail to achieve maximum impact due to a decline in the economic and political influence of South African public policy on the continent overall. We judge that this is unlikely in the medium term, as set out in the strategic case. In the longer term this will be a critical determinant of how far the UK should continue to dedicate resources to working through this form of partnership with South Africa (compared to, for example, dedicating a greater level of effort to working with South African private investors in Africa). / Operational risks affecting the implementation of the programme are as follows: / Description Residual probability Impact Mitigation / Lack of commitment by GoSA to establish SADPA Medium High DFID will monitor political developments closely. The UK will continue to voice support for South Africa’s regional development role at all levels. / GoSA chooses not to work with UK on development issues Medium High This intervention will itself help to position the UK as a partner of South Africa on development issues. However external factors and other foreign policy issues may affect our ability to work together in general and on specific sectoral issues; we will monitor this closely and address challenges through a coordinated approach to the relationship. / Activities do not contribute fully to DIRCO/SADPA priorities for development cooperation Medium Medium All proposed activities will need to demonstrate contribution and show evidence of agreement with DIRCO or other GoSA counterparts. SADPA have been invited to participate in the programme’s steering committee once capacity is in place. / Insufficient local capacity to implement activities Low Medium Initial market scoping indicates low probability – a range of SA organisations in academia and civil society are already planning work on emerging development policy. This intervention will help develop this capacity further. / Rapidly changing context and demands affect accuracy of financial planning and forecasting Medium Low The flexible, responsive nature of this programme is likely to make long-term financial forecasting more of a challenge. Though the impact on achieving programme results is judged to be low, we recognise that the level of risk we need to tolerate for financial reporting processes may be more significant.
C. What conditions apply (for financial aid only)? / There is no direct financial aid arrangement involved in this intervention.
D. How will progress and results be monitored, measured and evaluated? / Measuring the success of this intervention on achieving more effective South African development cooperation will be challenging for DFID. The approach described here draws heavily on recent guidance on monitoring and evaluating policy influencing interventions.[30] / Monitoring progress at the programme level / The logical framework attached at annex 2 will be the principal tool to measure progress against this intervention’s theory of change. It includes: / Indicators of the programme’s impact, consisting of socio-economic improvements in African development which are in line with the anticipated priorities of SADPA; / Indicators at outcome level of the proportion of South African development cooperation coordinated by SADPA and commitment to participation in forums on multilateral development effectiveness; / A mixture of indicators of process and of behaviour at output level, which reflect changes in institutions (both within and outside GoSA) and in their relationship with the UK. / These provide the basis for the measurement of progress at the overall programme level by the steering committee and through routine annual reviews. Given the evolving political and institutional context for this programme, it is expected that indicators and outputs may need to be revised at the programme’s annual review point. / Monitoring progress of individual activities / In addition, activity-level monitoring will be carried out by individual implementing partners and reported to DFID on at least a quarterly basis for each activity. For activities costing over £250,000 a full embedded logframe (with a clear and explicit contribution to the overall programme logframe) will be agreed with the partner. For activities below this threshold a clear set of expected results will be agreed in an appropriate and proportionate format. / Evaluation / Given the moderate overall financial value of this programme, and the challenges of assessing the impact of UK-funded activities on broader South African policy issues, we do not judge that an external evaluation of this programme would be appropriate. / However annual reviews will need to include detailed judgements of any developments in the evidence linking activities to outcomes, and will include an assessment of DFID’s contribution towards progress made.
Logframe / Quest No of logframe for this intervention:
[30] DRAFT: Monitoring and Evaluation of Policy influencing interventions, Enrique Mendizabal and Jeremy Clarke, ODI, London

ANNEX 1:

SOUTH AFRICAN PARTNERSHIP FOR EFFECTIVE DEVELOPMENT COOPERATION: FUNDING PROFORMA

(This should be proportionate to the specific proposal: Max 3 sides for a proposal of less than £500,000, Max 6 sides for a larger proposal)

In addition to this proforma, a proportionate Logframe should be completed for any proposal greater than £250,000.

Title of Proposal:

Start Date:	End Date:

What is the proposal: (Describe and explain the proposal, set out its outputs and the tangible results that it will deliver. Specifically, what will DFID funds pay for? Are the results self-contained to the proposal, or do they also rely on external factors?) / Why is this a priority for funding? (How does it relate to the priorities of the Government of South Africa and to DFID’s objectives? Are we confident, and with what justification, that the intervention will be successful?). / How will the proposal be delivered? (Who is implementing? What is the role of DFID staff? Are there any other partners? What are we expecting other partners to contribute? What type of funding mechanism?) / How will the proposal be monitored? / What are the costs to DFID? Detailed costing breakdown, over time. Set out the procurement/commercial requirements.

Budget Total:

DFID Southern Africa Lead:

DFIDSA Approval:	Date: