Type of Review: Annual Review

Project Title: Technical Assistance for non-aided ‘At Risk’ Caribbean Overseas Territories (202083)

Date started: 19 August 2010
Date review undertaken: 16 August 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Up to £5,750,000 to fund expertise to help deliver more effective financial management in four non-aided Caribbean Overseas Territories (OTs): Turks and Caicos Islands (TCI), Anguilla, British Virgin Islands (BVI), and Cayman islands. The Territories have deficient financial management and reporting systems and our support is needed to make up for this deficiency in the Territories’ ability to carry out its financial governance responsibilities. / In TCI, where the FCO has installed a Governor-led Interim Government (IG) and DFID is guaranteeing commercial bank lending of up to £160m, expertise will help to strengthen public financial management and administration capacity and systems, and implement budget measures which will lead to the achievement of a fiscal surplus in the current financial year ending March 2013. / In Anguilla, BVI, and Cayman Islands, expertise will enhance monitoring in order to provide HMG with a more detailed understanding of the fiduciary risk in each territory and the extent of actual and contingent liabilities.

What are the expected results?
Outcome: More effective financial management in 4 non-aided ‘At Risk’ Caribbean Overseas Territories / Outcome Indicators Baselines Expected Results / TCI budget deficit/surplus before capital, debt repayments (deficits bracketed) 2010/11: (US$59.4m) / (£39.6m) 2014/15: US$17.2m / £11.5m / DFID involvement in other ‘At Risk’ Territories averted by action taken as a result of monitoring 2010/11: DFID only involved in TCI 2014/15: DFID still only involved in TCI

What is the context in which UK support is provided?
The UK Government (HMG) is committed to meeting the reasonable assistance needs of the OTs as a first call on the aid budget. One of the priorities recorded in the operational plan of DFID’s Overseas Territories Department (OTD) is “To manage HMG’s financial liability for non-aided ‘At Risk’ Caribbean OTs”. This project responds directly to this priority. / TCI has the most serious financial problems, hence the need for a DFID loan guarantee. The other three OTs are each spending more than they earn, all have substantial debt, and all are in breach of FCO borrowing guidelines. / Government financial insolvency in any of the ‘At Risk’ Caribbean OTs would present DFID with a major problem. The OTs are not members of the IMF and have no access to financial support should they experience difficulties in paying the salaries of civil servants or for the provision of public services. Enhanced monitoring and oversight is therefore necessary to prevent their public finances deteriorating further. Of these four OTs only Anguilla is eligible for Overseas Development Assistance (oda). / The cost of this intervention is much less that the potential costs associated with DFID’s loan guarantee in TCI being called or if the fiscal situations in either (or all) of the three other territories deteriorate to the extent DFID is required to provide some form of financial support.

## Section A: Detailed Output Scoring

Output 1: Strengthened public financial management and administration capacity and systems in the Turks and Caicos Islands
Output 1 score and performance description: A+
Progress against expected results: / There has been significant progress against the two indicators for this output: - / TCI public financial management improved [baseline: weak PFM systems, procedures and controls] / % reduction in TCI public administration [baseline: approx. 2,200 staff currently] / On the first indicator, the UK Government, through the deployment of a DFID-funded Chief Financial Officer (CFO), continues to retain direct control of the public finances. The CFO, with support from a range of finance and revenue expertise (also funded by the project), has been critical to all progress that has been made. The main achievements this past year are: - / Budget measures have been implemented in order to stay on track to achieve a fiscal surplus in the financial year ending March 2013 / A new PFM law and a new CFO ordinance have all been enacted and a Statement of Governance Principles agreed. / Robust controls and accurate payroll records have been established / Revenue collection and approval of all expenditure over $5000 has been centralised / More rigorous and realistic budgeting has been introduced, with more regular oversight of departmental budgets, including quarterly expenditure forecast updates and weekly cash flow positions, and corrective interventions taken if expenditures become too high or fail to be controlled / Reports on the state of public finances are being published quarterly / The historic backlog of financial statements have been fully addressed / New financial control procedures and upgrading of financial management skills in the Ministry of Finance are being implemented / The role of permanent secretaries as accounting officers has been strengthened. / On the second indicator, the UK Government, through the deployment of an FCO-funded Chief Executive Officer (CEO), continues to retain direct control over the public service. The CEO, with support from a range of public sector expertise (some of which funded by the project), has been critical to all progress that has been made. The main achievements this past year are: - / The reconfiguration of ministries into five, more integrated structures and the recruitment of a new generation of permanent secretaries with an emphasis on leadership, strategy and financial management capabilities / Implementation of a voluntary severance scheme which reduced the public service workforce by approximately 400 (18-20%) / Introduced changes in working methods to focus on the efficient delivery of government services / A new transparent approach to recording senior staff remuneration and a strengthened Integrity Commission to investigate malpractice are being introduced / General Orders are being revised and simplified and legally enforceable codes of conduct on public servants and future ministers are being put in place / The number of statutory bodies has been reduced and reforms to several statutory bodies, police, emergency services and prison service are underway / Recommendations: / Continue to monitor financial management in the run up to and following elections in November. / Impact Weighting (%): 50 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: HMG has better understanding and control of fiscal health of non-aided Caribbean OTs
Output 2 score and performance description: B
Progress against expected results: / Progress against the two indicators for this output has been mixed: - / No. of annual monitoring missions which include PFM and/or PSR expertise [baseline: current FCO economic missions don’t provide a comprehensive picture of each OTs strengths, weaknesses, risks] / % of recommendations from previous years monitoring missions implemented [baseline: at present there is no mechanism or commitment by OTs to act on findings of current assessments] / On the first indicator, HMG has in the last year gained a more comprehensive understanding of the situation in the At Risk OTs. In that time DFID staff have joined 4 FCO-led missions:- / Month Month Reason for visit / August 2011 Anguilla Discuss measures to get 2011 budget back on track / January 2012 British Virgin Islands Economic update mission / February 2012 Anguilla Discuss 2012 budget performance monitoring process / June 2012 Anguilla Economic update mission / Notes: / DFID did not join the FCO mission to Cayman in July 2012 and FCO has not carried out an economic update visit to the Cayman Islands since June 2011. / DFID also funded PSR expertise to assist Anguilla with a civil service review (May -Sept 2011), and PFM expertise to assist Anguilla with fiscal risk management and budget performance monitoring (April 2012 - ongoing). / Despite the UK having a better understanding of the fiscal health of these OTs and what needs to be done to mitigate the financial risks, there has been very little progress against indicator 2. There is no evidence that the recommendations contained in the economic update reports of FCO-led missions to BVI (January 2011), Anguilla (May 2011) and Cayman (July 2011) have been implemented by the respective governments. / In Anguilla, where the government has formally committed to balancing its budget by the end of 2012 and where DFID has provided advisory and monitoring TA to help them do so, there has been some uptake of revenue recommendations made by tax expertise but not much if anything has been done yet to address experts’ recommendations on the civil service or the health sector. / Recommendations: / DFID will work with FCO and HM Treasury on how to give recommendations that reduce major financial risks to the governments of these OTs and the UK more teeth. / Impact Weighting (%): 50 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money

1. Progress and results
Has the logframe been updated since last review? Y/N / No / 1.2 Overall Output Score and Description: / 1.3 Direct feedback from beneficiaries / The main beneficiary of the project to date is the Governor-led TCI Interim Administration since the majority of the expertise funded by the project is helping to strengthen TCI’s capacity to implement budget measures to generate fiscal surpluses and reduce debt. This support is considered to be making a positive contribution. to i) strengthening PFM systems and capacity in TCI and ii) helping HMG better understand the fiscal health of Anguilla, BVI and Cayman.
1.4 Summary of overall progress / The critical success criteria for the project is: - / TCI implements budget measures which will lead to it generating a fiscal surplus and reducing its debt beginning in the financial year ending March 2013 / DFID’s loan guarantee to TCI is not called / TCI public financial management and administration capacity and systems are strengthened / Fiscal positions of Anguilla, BVI and Cayman Islands are improved / Overall, there is clear progress to date on 1, 2 & 3. There has been no improvement in 4.
1.5 Key challenges / The key challenge in TCI will be to ensure that the return to an elected government does not reverse the substantial progress made. We will ensure our technical assistance is focussed on reducing this risk. / In Anguilla, BVI and the Cayman Islands, the challenge is to use the influence at our disposal effectively so that their public finances begin to improve.
1.6 Annual Outcome Assessment / Outcome: More effective financial management in 4 non-aided ‘At Risk’ Caribbean Overseas Territories / Outcome Indicators Baselines Expected Results 2012/13 Milestones / TCI budget deficit/surplus before capital, debt repayments (deficits bracketed) 2010/11: (US$59.4m) / (£39.6m) 2014/15: US$17.2m / £11.5m US$3.7m / £2.5m / DFID involvement in other ‘At Risk’ Territories averted by action taken as a result of monitoring 2010/11: DFID only involved in TCI 2014/15: DFID still only involved in TCI Anguilla budget surplus: EC$4.8m / £1.1m / Forecasts suggest that the 2012/13 milestone for the first outcome indicator will be met: as at the end of June 2012 (quarter 1) the forecast suggests the surplus could be as high as US$11.8m. / Forecasts suggest that the 2012/13 milestone for ther second outcome indicator will not be met: as at the end of June 2012 (quarter 2) the forecast suggest a deficit of at least EC$5m.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / Yes / 2.2 Key cost drivers / The main cost driver is consultancy fee rates. / 2.3 Is the project on-track against original timescale: Y/N / Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The results in Anguilla, BVI and the Cayman Islands have been disappointing as none has managed yet to improve the state of their public finances. In Anguilla our technical assistance has not been used effectively and therefore we will focus now on improving the incentives for these OTs to take the necessary actions. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation is not planned.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium / 4.2 Assessment of the risk level / The risks identified in the business case remain relevant. These are shown below, as are the mitigating measures which have been updated. / Turks and Caicos Islands / Risks Impact Probability Mitigating measures / Financial control handed back too quickly before adequate systems and protections are in place. High Medium New constitution enables HMG to retain adequate financial management powers to ensure that this does not happen. New Chief Financial Officer ordinance reinforces this. / Insufficient capacity in TCIG to implement the necessary reforms. High Medium Range of Technical Assistance aimed at improving public financial management and transforming public sector into an affordable and effective service. / TCIG budget deficit larger than forecast resulting in higher debt profile; guarantee is called and new funding is required. High Low Chief Financial Officer has sufficient powers to ensure forecasts are met. / With $60m headroom from the Revolving Credit Facility that is part of the lending guaranteed by DFID it is unlikely TCI would need more borrowing. / Revenue exceeds expectations. Surplus cash either incurs a penalty repaying bonds early, or risks being ‘squandered’ or misappropriated. High Low To mitigate this DFID/TCIG can assess the relative benefits of a) repaying debt, b) building up the new Sinking Fund for debt repayment, or c) DFID holding the cash as collateral against the guarantee. / A ‘force majeure’ such as a hurricane hits TCI and causes major damage limiting TCIG ability to service debt. Medium Medium Insurance held against hurricane damage and hurricane relief support available. / Experience of Hurricane Ike suggests damage to tourist industry likely to be short-term. / Anguilla, BVI and Cayman Islands / Risk Probability Impact Mitigating measures / Territory Government’s do not act on early warnings Medium High HMG will establish means to ensure territory Government’s take corrective action to avoid excessive indebtedness or insolvency. / HMG is unable (or disinclined) to respond to the scale of financial problems Low High Project team will work with FCO to leverage more financial and technical support from regional and multilateral institutions (i.e. CDB and EC)
Risk of funds not being used as intended / Project funds are used entirely to pay for contracted expertise and therefore the risk that these funds are not being used as intended is low. / 4.4 Climate and Environment Risk / Not relevant

5. Value for Money
5.1 Performance on VfM measures / The main VfM measures are: - / For TCI, good value will have been achieved if we can partially or fully withdraw technical assistance at the end of 2013 / For the other “At Risk” OTs, VfM will be achieved if there are significant new trends towards meeting FCO borrowing guidelines / On i) it is unlikely that DFID will be able to fully withdraw technical assistance while the guarantee is in play. However we are on track to reduce the number of technical experts involved and would expect this to have come down significantly by the end of 2013 (assuming TCI’s positive direction of travel is not negatively impacted by the return to elected government). / On ii) none of the three territories have made any progress to improve their borrowing status as per the FCO guidelines. / 5.2 Commercial Improvement and Value for Money / The project inputs are entirely contracted technical assistance. Competitive recruitment processes have been undertaken for the large majority of contract awards to ensure not only that the most suitable expertise is selected but also that the fee rates paid to consultants are in line with the market. / 5.3 Role of project partners / Not relevant / 5.4 Does the project still represent Value for Money : Y/N / Overall, yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / There are no conditions attached to this project.

7. Conclusions and actions
Overall, project inputs are contributing to ensuring HMG's financial liability for non-aided 'At Risk' Caribbean OTs is managed effectively. / In TCI, where there has been direct rule by the Governor-led Interim Administration, the technical assistance has in many cases assumed executive positions with direct authority over the management of public finances. This has resulted in significant progress to put TCI on a path to substantially reduce its budget deficit. The key challenge will be to make sure that this progress is not reversed when elected government returns (scheduled for the end of 2012). / Project funded participation (by the project team as well as contracted experts) in monitoring visits to Anguilla, BVI and Cayman Islands has meant FCO and DFID have a much clearer sense of what needs to be done to mitigate the financial risks in these territories. However, the situation in all three territories continues to be a concern. The respective governments have shown little interest to act on advice and no desire to take the tough decisions required to improve their public finances. / The key recommendations for the project team are: - / To link the assessment (to be done in the first half of 2013) of whether to extend the project budget and timeline beyond end 2013, to an assessment of the newly elected government’s conformity (or otherwise) to the various measures and safeguards put in place to ensure PFM and PSR progress is sustained. / In line with the 2012 White Paper on the Overseas Territories, to take a close interest with FCO and HM Treasury officials in the sustainable management of the public finances in Anguilla, BVI, and Cayman, review the existing incentives for these OTs to take appropriate action, and consider options to improve these.

8. Review Process
Desk review by project management team.