Type of Review: Annual Review

Project Title:	English in Action Bangladesh

Date started:	January 2008	Date review undertaken: May 2012

## Introduction and Context

What support is the UK providing?
English in Action (EIA) is a £50 million programme which will take place over nine years.

What are the expected results?
EIA expects to increase social and economic inclusion for more than 25 million Bangladeshis by developing English language skills for school pupils and adult learners. The project also expects to contribute to the economic growth of Bangladesh by providing English language as a tool for better access to the world economy. EIA will take this forward through the development and delivery of an inclusive national programme. The beneficiaries will be male and female adults in urban and rural communities, and school-aged children. Progressive and innovative approaches to teaching and learning will ensure that beneficiaries will have the opportunity to develop English as a technical skill. / By the end of the final year of the programme (2016/17), we are expecting to see the following outputs and impacts under this programme; / The proficiency in communicative English among the population of Bangladesh to increase measured objectively using trinity levels. / Employer satisfaction (with applicants’ / employees’ communicative English) to increase from 68% of employers in the baseline to 80% by 2016/17. / Pass rates in English at SSC and HSC to increase as follows; / Boys Girls / SSC Baseline 76.96% 73.97% / Target 85% 86% / HSC Baseline 81.42% 78.94% / Target 80% 80% / Motivation for learning and using English among the population of Bangladesh (students 51% to 65%, teachers from 64% of to 80%). / Increase the numbers of schools, teachers and pupils participating in English in Action primary interventions to 30,000 schools, 67,500 primary teachers and 6.75 million pupils (3.29 million M; 3.46 million F). / A cumulative total of 8.5 million people will have used BBC produced EIA media products regularly by the end of Mar 2014. / National systems and structures take on the programme initiatives (training methodology, revised curriculum, research, etc.) as business as usual.

What is the context in which UK support is provided?
EIA was designed in response to a request from the Government of Bangladesh. English language teaching capacity has atrophied in Bangladesh due to the lack of trained English teachers in a centralised education system that expanded rapidly in the 1970s. Few people under fifty are confident, fluent English speakers, and English is the most commonly failed examination subject at the secondary certificate level. Lack of English language skills is regarded as a constraint to economic development. For example, employers state that job applicants and employees lack English language skills necessary to work effectively. A pre-appraisal mission recommended that the problem be addressed at scale, through a project that would have substantial reach and impact.

## Section A: Detailed Output Scoring
Output 1 English language proficiency of both students and teachers, and the pedagogic practice of teachers enhanced and sustained through the development of interactive audio instruction package for use in primary schools
Output 1 score and performance description / Overall score: A+ / This output is performing well and has a workable model for both enhancing language proficiency and changing classroom practice. Upscaling will be challenging but the review team find that the schools component is well placed to take this work forward. We note that delay in approvals has had an impact on implementation of the next phase. However, overall the outputs meet expectation. In particular, we recognise that the methods for improving the quality of English teaching are very transferable to other subjects – by improving the quality of teaching, this intervention can be of much greater value beyond the EIA programme, by demonstrating effective ways of improving the quality of learning in Bangladesh more generally. / Summary Performance description: activities and achievements 2011 – 2012 / Improved materials / Modifications/ improvements to materials, were done to strengthen the effectiveness of training approaches. For example, video materials previously used actors to model the desired classroom approaches. These now show EIA trained teachers working in their classrooms. This increased authenticity, and is likely to increase the transfer of techniques learned in training into actual classroom practices. / Classroom materials now have a better fit with the core textbook, English for Today, and an improved integration of the four language skills. / Materials are now fully compatible with the time allocation of 2 x 35 minute lessons per week. / Materials include positive images of vulnerable and disadvantaged groups in Bangladesh –Dalits, working children, residents of remote areas, disabled people, slum dwellers, and women and girls. / Collectively, these improvements to materials should strengthen ongoing progress against indicator 2 (Practice) / The Teachers’ Guide modules now take a more systematic approach to pedagogy. / Materials now include dedicated English language development materials in the form of recorded discussions (Teachers talking), classroom language and links from each module to the English Language for Teachers (EL4T) materials. The BBC mobile lesson series Pronunciation and Practical Vocabulary are now part of the EL4T materials – a good example of co-operation across the schools/ media and adult learning strands of EIA. / This stronger emphasis on building English language skills should support progress against indicator 3 (English Language (EL) competence). / Involvement of Head Teachers / In primary schools, head teachers often teach English language. Head teachers also play an important role in ensuring that innovative approaches are understood and accepted at a whole school level. / During 2011 – 2012, EIA involved Head Teachers (33% of the trainees) in the Phase 3 training. / New training materials have been developed for this group, to provide whole-school level support for EIA pedagogical approaches; the materials also focus on wider issues of leadership and management. / Dedicated cluster group meetings have been set up for this group, led by facilitators who are themselves head teachers. / Progress against indicators / Indicator 1: Reach: The numbers of schools, teachers, and pupils participating in English in Action primary interventions. / In 2012 the up scaling of EIA began. The preparatory work for this is in place, the models and processes are well thought through and firmly linked to mainstream structures. For example, the Upazila resource centres/ Upazila Education officers are actively involved in teacher support. / The upscaling process has been held back due to a delay in sign-off from GoB. However, spend and activities for 2012 – 2014 have been re-profiled to enable targets to be reached in spite of this delay. From 2012 to 2014, 108 Upazilas will be involved in EIA training. These Upazilas are representative of the geographical diversity of Bangladesh and have been selected with the UNICEF poverty map in mind, ensuring that the project can reach the poorest and disadvantaged groups. / This indicator is on target against the revised 2011/ 2012 milestones: / 200 schools / 400 teachers (160M/ 240F) / 16,000 pupils / These targets may appear modest, but this is because of the timing of the annual review, and the slight delay in upscaling as the project moves into phase 4. / Indicator Achieved for 2011/2012 and on track for 2014 / Indicator 2: Practice: The numbers of teachers evidencing communicative language teaching approaches in their classroom practice. / Data show that the EIA intervention has had a positive impact on classroom practice. Headline results are: / A substantial and sustained increase in student talk (for 27% of the lesson) / A substantial and sustained increase in students’ spoken English - 81% of student talk was in English after 12 months – this is particularly impressive for young learners / Student participation in communicative activities / However, research data show a decrease in certain aspects of CLT at this point in the project. After 4 months of EIA, on average, 14% of student activity was pair work and 15% of student activity was group work. After 12 months, this had fallen back – only 5% of student activity involved pair work and 4% was group work. There has also been an increase in teacher presenting, and a decrease in giving feedback between Study 2a, undertaken in 2010, and Study 2a2, undertaken in 2011. / In a language development project with a 9 year time scale which aims to make radical changes to classroom practice, some backsliding is to be expected. Nevertheless, the 2011 quantitative data indicates a need for ongoing support and renewed focus in areas where there is a decrease in uptake of CLT methodology. / This indicator is on target against 2011/2012 milestones: / % student talk in a lesson = 20% / % of that talk in English = 50% / Indicator Achieved for 2011/2012 and on track for 2014 milestones / Indicator 3: EL competence: The number of teachers and students with demonstrable competence in communicative English Language
Against baseline data, 10% of teachers show increased levels of EL competence as measured by the Trinity Examination Board scale. / Self-report data - 95% of teachers reported that EIA had helped improve their own language skills. In the focus group discussion conducted by the review team: participants were unanimous in stating that their English language, and confidence in using English in class, had improved as a result of engagement with EIA. This is a strong achievement and deserves to be highlighted in dissemination activity. / On target against 2011/ 2012 milestones: / Increase of 10% of teachers reaching Trinity level 2 and above / Increase of 5% of students reaching Trinity level 1 and above / Indicator Achieved for 2011/2012 and on track for 2014 / Impact weighting: 25% / Recommendations (these apply to both Output 1 and 3): / We recommend that the positive achievements are disseminated effectively – so that the effects of training are clearly recognized. / Qualitative data relating to the schools component is highly positive, though the sample sizes are modest relative to the scale of the project. We recommend that self-report data be gathered from a larger sample of EIA teachers relating to, e.g. increased fluency, confidence, and ongoing training needs. This could be achieved, e.g., by the administration of a questionnaire using restricted response items – so that we can hear the teachers’ voices more broadly and respond to their expressed needs.

Output 2: Change people’s perceptions of English language learning, reduce barriers to English, and support the development of an English language media sector through the innovative use of television, mobile phones, and other media platforms
Output 2 score and performance description / Overall score: A+ / The review team commend the highly innovative work of this component, and value the work which has been taken forward to demonstrate and respond to engagement with socio- economic class E and the ‘media dark’. We note the excellent pedagogical approaches which are embedded within the media/ adult learning output. Performance has gained clear external recognition – this output has won 4 international awards over the review period. / Summary Performance description: activities and achievements 2011 – 2012 / Syllabus aligned across TV, web, WAP, and print. Innovative for ELT m-learning as it offers personalised learning. Initial findings: / Television: 12.6 million people watched Mojay Mojay Shekha 2 in its first month. / Mobile: 473,923 calls to the course: of which 300,000 are regular users. / Website: 115,924 unique visitors, with 26,396 registered for the new course so far. Dwell time increased from 10 to 17 minutes. / 262 pieces of media coverage about the new course. / Other progress over past year:- / TV: 14.8 million watched repeat broadcasts of Bishaash (Drama) and 13 million watched repeats of Mojay Mojay Sheka 1 (half watched five or more episodes). / Mobile phone: lessons used by approximately one million regular users (five times or more). / Internet: an additional 305,000 unique visitors (averages 1,050 visits per day). / Newspapers: 3.3 million people used BBC Janala Prothom Alo lessons as of November 2011, compared to only 1.7 million people at the time of the 2011 midline review. The total number of users has almost doubled. 0.8 million people currently use lessons in Prothom Alo 2 to 3 times per week. / Capacity building: two workshops held with 50 industry professionals (media and ELT). More scheduled for every quarter in 2012. / English Clubs: strategy and products (CDs and books) developed, user tested; first 1,000 clubs will launch this month. Also available to download on website. / Community radio stations piloted. / Maximised reach of archive material: published three BBC Janala CDs containing the mobile English language lessons. First book of Prothom Alo archive lessons published / Certificates of achievement available to learners on successful completion of course. / Progress against indicators / Indicator 1: Number of Bangladeshis accessing BBC produced EIA media products (target 6 million) / By April 2011, 6.8 million regular users of BBC produced EIA products / Indicator Achieved and on target for 2014 milestone / Indicator 2: Perception of reduced barriers and increased positivity towards learning communicative English amongst school leavers and adults / Perceived barriers: / ‘English is expensive to learn’ – decreased from 38% to 27% of highly exposed learners / ‘English is difficult to learn’ – decreased from 44% (baseline figure) to 22% of highly exposed learners / Increased motivation/ confidence to learn and use English reported by 36% of BBC produced EIA products, compared to 15% of those not exposed. / Indicator Achieved and on track for 2014 milestone / Indicator 3: Influencing the development of an English language media sector through improvements in capacity to develop products and programmes / Prominent programming slots negotiated with media companies for free distribution of all BBC media outputs available / 50 participants last year in week long creative workshops (ELT media alliance emerged from this.) / Four more creative workshops are scheduled for the coming year – one a quarter, with 25 participants in each workshop / Indicator Achieved and on track for 2014 milestone / Indicator 4: EL competence – the number of Course 1 users with demonstrable competence in communicative English language (Note: this indicator introduced following 2011 annual review) / A competency test was developed quickly in response to this new indicator. Baseline testing took place before the course. / Cohorts have shown improvements in rural villages and improvements amongst people who have used mobile phone lessons / Indicator in progress / Engaging the poor / The brief for the media sector was to work with socio- economic classes A to D. However, research shows that the poorest have been reached. Half of the viewers of Mojay Mojay Shekha are from socio-economic group E. Community Fairs and English Clubs are likely to increase this reach. At present, BBC are also conducting research centred round how best to reach the 18% of the Bangladeshi who remain ‘media dark’ and cannot access BBC Janala products and platforms. / Recommendations / BBC should engage an international EL testing expert to support the piloting and modification of the course competency testing. / DFID should clarify if it wants BBC Media Action to widen its remit to reach out further to the poorest. In the interim, BBC to obtain media exposure analysis for socio-economic group E if possible, research community radio audiences, and identify further low/no cost tools to publicise the mobile course to the poorest, / The marketing drive for Amar Engreji Course 1 resulted in high uptake. Course 2 is not due to launch until February 2013, and Course 3 one year later. We recommend that, if possible, BBC should accelerate the production of Courses 2 and 3, publishing as soon as possible on the websites and handsets, to avoid losing momentum. / Impact weighting: 25%

Output 3: Communicative English language teaching practices promoted through information and communications Technology enhanced Teacher Professional Development interventions that are tested and adapted in secondary schools
Output 3 score and performance description / Overall score: A / As for Output 1, this output is performing well and has a workable model for both enhancing language proficiency and changing classroom practice. Upscaling will be challenging but the review team find that the schools component is well placed to take this work forward. We note that delay in approvals has had an impact on implementation of the next phase. However, overall the outputs meet expectation. / Summary Performance description: activities and achievements 2011 – 2012 / As for the primary schools component, secondary school activities over the last year have had a focus on improvements to materials and technology. EIA materials have been more tightly linked to the prescribed Government textbook, English for Today. This will increase the practical relevance of the project, and will further strengthen the transfer of training approaches to the classroom. All materials are now firmly based in the realities of Bangladeshi classrooms, and are appropriate for the increased inclusiveness and geographical spread which will form part of the upscaling phase. / Eight teacher training modules have been produced; after teachers work through/ try out module content in class, cluster meetings will take place. Leadership will be provided by the teacher facilitator, and peer support will be available from participating teachers. / The modules will simultaneously develop English language skills and provide training in communicative language techniques. Importantly, the modules contain sections on working with large classes. As for Output 1, concepts and approaches to social inclusion are embedded within the materials. / Every part of English for Today that is more than a few lines long has been recorded for use in secondary schools. These recordings can be used to practice language skills directly with the class through the provision of the audio speaker and mobile phone. The review team observed the effective use of this technology in the classroom. The recorded materials and technology are likely to have a significant impact on the development of listening and speaking skills. / Self-study materials to enrich the English language competence of secondary school teachers have also been produced – this is shared with the primary schools component and will support attainment against indicator 3 (the development of EL competence) / In April 2012 the Teacher Facilitators were introduced to the Secondary materials and to the concepts and processes of their role. The core trainers report that / “the initial week long workshops seem to have been very successful with an encouraging sense of both enthusiasm and buy in from the participants. There was a consistently repeated recognition from the TFs that the methodology of EIA, with its commitment to on-going classroom based teacher development using innovative technology, was culturally appropriate, considered teachers and students real needs, and would make a lasting difference.” / The review team was able to attend an initial training session and the team discussed the work of EIA with participants. We found high levels of enthusiasm and motivation, and a strong recognition of the value of the work of the schools component. / Progress against indicators / Indicator 1: Reach: The numbers of schools, teachers, and pupils participating in English in Action primary interventions. / In 2012 the upscaling of EIA is beginning. The preparatory work for this is in place, the models and processes are well thought through and firmly linked to mainstream structures. / On target against 2011/ 2012 milestones (revised): / 100 schools / 200 teachers (160M/ 240F) / 24,000 pupils / Indicator Achieved for 2011/2012 and on track for 2014 / Indicator 2: Practice: The numbers of teachers evidencing communicative language teaching approaches in their classroom practice. / Comments as for Output 1 with respect to the need for emphasis on CLT. / Additionally, the review team point out that the washback effect from the examination system is likely to be stronger in the secondary schools component: SSC and HSC examinations are clearly examples of ‘high stakes’ testing. (However, we note the very recent introduction of testing in primary schools). Washback from examinations will mitigate against the continued uptake of EIA approaches in schools. / The review team note that efforts are being made to increase the alignment of assessment principles with sound pedagogical practice. We urge that efforts to reform assessment and testing procedures are given priority. This is a key issue in ensuring that the excellent work of the schools component can be sustained. / Note: We recommend that the purpose level indicator “Pass rates in English at SSC and HSC” is removed from the logframe. There is no direct causal link and influence of EIA activity and examination pass/ fail rates, and the decreasing percentages of pass rates are open to negative interpretation. / On target against 2011/2012 milestones: / % student talk in a lesson = 20% / % of that talk in English = 50% / Indicator Achieved for 2011/2012 and on track for 2014 / Indicator 3: EL competence: The number of teachers and students with demonstrable competence in communicative English Language
Against baseline data, 10% of teachers show increased levels of EL competence as measured by the Trinity scale. / On target against 2011/ 2012 milestones: / Increase of 10% of teachers reaching Trinity level 2 and above / Increase of 5% of students reaching Trinity level 1 and above / These targets have been fully met. Comments as for Output 1. / Indicator Achieved for 2011/ 2012 and on track for 2014 / Impact weighting: 25% / Recommendations: / As for Output 1

Output 4: A rigorous monitoring and evaluation framework and research framework built upon baseline studies to monitor and assess project impact and generate knowledge products and support capacity building.
Output 4 score and performance description: B / This output moderately did not meet expectation. This is largely due to the lack of effective dissemination activities (Indicator 3) for the schools components. The review team would also like to see greater breadth of scope in the evaluation activities undertaken by this strand. EIA needs strong advocacy to communicate its clear successes nationally, regionally, and internationally. / Summary performance descriptor: activities and achievements 2011 - 2012 / Media and adult learning component / A comprehensive evaluation report on BBC Janala was carried out in February 2011. The performance of this strand of the project is considered under Output 2. BBC have an extensive and rich bank of research data, however they are just using it for internal purposes, e.g. baseline surveys, design testing, impact measurement. There is a wealth of useful insights which could be shared, however there is little spare capacity to polish and disseminate this research. / Schools component / Indicator 1: Evaluation activities taking place according to the M&E framework / Evaluation activities are on track and systematically recorded. The EIA research team have collected substantial amounts of quantitative and qualitative data over successive cycles of sampling, and the results are contained in internal reports totalling several hundred pages and giving clear and detailed descriptions of the findings. Particular strengths of the work are the use of direct classroom observation with standard schedules and independent testing of English language competence. These bring an exemplary level of objectivity to the assessment of outcomes from the project. / Indicator Achieved / Indicator 2: Monitoring activities taking place according to M&E framework and PMIS / A quality assurance system has been developed that involves collecting information at school and cluster level. A series of QA instruments supported by guidelines have been developed and trialled. The QA forms are currently being integrated into the Project Management Information System. / Indicator Achieved / Indicator 3: Disseminating research to key local, district, national, and international audiences, via appropriate knowledge products / Dissemination of findings demonstrating effectiveness of the programme is a critical issue for the project as a whole, since promotion of English language teaching as a tool for development has historically met resistance and scepticism in some quarters. A substantial asset here is the body of evidence already collected by EIA researchers demonstrating the impact of the project on students and teachers. However, this evidence is primarily available only as internal EIA reports. / The log frame is vague and rather circular with respect to requirements for dissemination, and we believe that more specific and measurable targets should be set. The review team took the position that by the mid-term stage a project funded at this level should be beginning to achieve wide recognition for its successes. However, the rich data which is being gathered as part of the Schools component to meet other indicators is not being used optimally to ensure effective dissemination of project findings. / Indicator not fully achieved / Impact weighting: 10%
Recommendations / We recommend that the logframe should be fully targeted (i.e. SMART) and linked to broader project goals – aim to publish in specific journals and other outlets and take work forward with this in view / We recommend that all dissemination work should bear in mind the guidelines set out in EIA’s communications strategy / We recommend that the schools components engage external support for evaluation research linked to effective dissemination, using ELT expertise. / BBC should work with EIA and OU to identify any potential cost- and time-efficient ways to polish and disseminate key BBC research findings.

Output 5 (New from 2009): Influence institutionalisation and sustainability of EIA approach through critical engagement with crucial stakeholders and advise on revised English Language Education Policy for GoB.
Output 5 score and performance description: / Overall score: A+ / This output has moderately exceeded expectation through excellent relationship building and the existing and planned embedding of EIA approaches in mainstream education approaches; media sector engagement with EIA/BBC Janala is strong. We commend the team for their consistency and patience in taking this work forward.
Progress against indicators: / Indicator 1: Developing sustainable strategic partnerships with key institutions / the formal and informal educational community and building necessary capacities to sustain EIA interventions beyond the life of the project. / Key strategic partnerships have been built with the Government (especially Ministry of Primary and Mass Education, MOPME) – there is evidence of excellent relationships and good co-operation. The MoPME secretary has become a ‘champion’ of the primary school component and indeed of the project in general. / For Primary education, EIA work will be a project within the Third Primary Education Development Programme (PEDP III). / For secondary education, EIA is building links with Secondary Education Quality and Access Enhancement project (SEQAEP) / For pre-service teacher training, EIA approaches are being embedded within the one year pre-service teacher training curriculum (Diploma in Education). The Diploma course is also being used as in-service training for the large numbers of practicing teachers who have never received training in education. / From 2015, EIA will be part of regular GoB teacher training. This is cross-curricular, and is evidence of the broader relevance of the activity-based, learner-centred approaches of the project. There are plans to further explore the links between EIA and mainstream teacher professional development activities. / Work promoting EIA approaches is being taken forward with local institutions: Underprivileged Children’s Education Programme (UCEP), Friends In Village Development Bangladesh (FIVBD), Dhaka University, UNICEF Bangladesh, and World Bank. / The review team is impressed by the relationship building and capacity development which has taken place in support of sustainability and we value the combination of top-down and bottom-up approaches. / Indicator Achieved for 2011/ 2012 and on track for 2014 / Indicator 2: Media sector engagement with project goal and purpose / Key media partners agree to carry and repeat BBC Media Action produced EIA media content / Two capacity building workshops have been held with 50 industry professionals / Media partners provide space without charge for BBC products (for example, Bangladesh Television and Prothom Alo). / Indicator Achieved and on track for 2014 milestone / Indicator 3 English language education policy in Bangladesh supporting communicative language teaching practices / There is ongoing strategic dialogue with policy stakeholders. Key achievements against this indicator are planned for the future. In addition to the influence of EIA on PEDP III and SEQAEP, the following changes will take place in the future to ensure support for CLT practices: / From 2015, EIA is part of mainstream GoB in-service teacher training / From 2015, EIA approaches have a strong influence on pre-service teacher training / The project is also building capacity and creating ownership for other stakeholders to take over materials development – for example, within the National Academy of Primary Education, the Primary Teachers’ Institute, the Teacher Training Colleges, and the private sector. / General Capacity building for sustainability - the project is building capacity at Upazila level, with the Upazila Education Officers, to carry out classroom observation; the research strand is also building capacity within the University of Dhaka Institute for Research in Education (IER) by training students to undertake research into changes in classroom practices. / Indicator Achieved and on track for 2014 milestones / Indicator 4: Influencing and ultimately changing curriculum, textbook, and assessment to support Communicative English language teaching. / Work is taking place to align assessment and testing practices to communicative language teaching approaches / EIA staff is working with SEQAEP to support textbook revision. / EIA is involved in curricular revision, through active engagement with the National Curriculum and Textbook Board (NCTB). / EIA materials are approved by GoB for classroom use. / Indicator achieved and progressing well towards 2014 milestone / Impact weighting: 15% / Recommendations / Sustainability – For media/ adult learning / EIA and DfID (DfID economist and private sector team representative) to engage with BBC Janala to map out potential future models in an options paper by the next annual review; DfID Bangladesh to explore examples of what has been done in other offices to extend the life of media content (for example, Shujaaz in DfID Kenya) / We note that BBC have benefitted from recent interaction and advice from DfID’s economist; the media and adult learning team would welcome more expert advice from DfID private sector team and economic advisors in relation to sustainability / Sustainability: For Schools / That DfID continues to communicate with other donors to build support for the mainstreaming of EIA approaches – in PEDP III, and in SEQEAP (this is especially important for the secondary sector where there is no sector programme). This would support the shift from good co-operation from GoB to full ownership.

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Yes / 1.2 Overall Output Score and Description: A+ / The overall programme outputs moderately exceed expectation. The media/ adult learning component is highly innovative. We commend BBC Media Action for thinking imaginatively to sustain achievements beyond 2017, and value the work being undertaken (eg EL competence testing) to provide evidence of impact. The review team finds the work of the schools component to be highly successful at this stage, and strongly encourage the broader communication of this message through enhanced dissemination activities. Evidence from previous EL programmes show that gains are fragile unless fully embedded in mainstream practice. We are impressed by the work of the institutionalisation strand in attempting to secure that EIA approaches become ‘business as usual’. / 1.3 Direct feedback from beneficiaries / Schools components / The annual review timeframe was short (6 days). Half a day was given over to a field visit. The team visited two schools The first was a UCEP school, where we observed two classes – grade 2 and grade 7, and a secondary school, where we observed a grade 7 lesson. We also conducted a focus group discussion with EIA teachers and teacher facilitators. Classroom observation provided clear and positive evidence that the schools component is broadly achieving its aims. We saw teachers implementing the methodological approaches which EIA promotes. This included an observation of a newly trained teacher who used pedagogical techniques which she had first encountered in training one week before. It is important for the success of the schools component that teachers are able to transfer skills learned in training to their classroom practice. / Focus group discussion with teachers showed fully positive attitudes to the work of the schools component. Teachers felt that cluster group meetings were particularly useful, and that the peer support provided through these meetings was invaluable. Concerns were raised about progress when levels of support were reduced or withdrawn, however. Since peer support is highly regarded, it may be worth investigating how best to support earlier batches of trainees to continue this work on a self-help, autonomous basis. The Upazila Education Officers may be well-placed to support this development. / It should be noted that for the review team, direct contact with beneficiaries –pupils, teachers, and teacher trainers – was of necessity limited. Overall, however, the review team formed a strongly positive view of the work of EIA schools component as a result of the field visit.
1.4 Summary of overall progress / The 2011 annual review made recommendations over five broad areas. These recommendations, and actions taken as a result of the recommendations, are summarised below. / Recommendations from 2011 OPR Summary of actions taken and 2012 review team comments / One EIA (unifying the project strands) Joint work has taken place. Some excellent examples of this are: the new website, EIA film, and community fairs: future joint activities are planned. The review team also recognise that joint work is not always appropriate and that separate branding and discrete approaches are appropriate for the project. As an example of this, EIA is not a well-known brand, and sustainability depends upon the ‘disappearance’ of EIA into mainstream approaches. BBC Janala has high brand recognition and this is, at present, an advantage which helps secure reach for the media and adult learning component. / Social inclusion A comprehensive social inclusion strategy is in place, and this provides good practice guidelines for all project partners. This joint social inclusion strategy and action plan is evidence of integration across project strands. / Recommendation EIA would value expert input from a DfID social inclusion advisor to further strengthen and operationalise the Social Inclusion strategy. / Research, Monitoring, and Evaluation (RME) An RME strategy document is now in place. We note the comments of the 2011 review team relating to the very different approaches to RME for the BBC Media and Open University components. We view this as fully understandable, given the different aims and roles which RME play within each organisation. / Institutionalisation (sustainability) An institutionalisation strategy is now in place. / Logframe revision A draft revised logframe was in place for the review process, and is currently being finalised. / Overall progress / EIA has continued to make good progress since the annual review in 2011. / Schools components / The schools components have in place a well-functioning, scalable model for English language teaching. In Phase 3, the highly demanding work of going to scale has begun. Over the last year significant improvements have been made to materials and structures based on lessons learned from the previous phase. / Media and adult learning / April 2011 to April 2012 has been a highly successful year for the BBC Janala EIA project. All targets for deliverables have been achieved, and steady progress is being made towards 2014 milestones. The Media and adult learning component has demonstrated excellent, innovative work. This excellence has resulted in BBC Janala winning a number of international awards: / Global Mobile Award for best initiative for underserved audiences / World Innovation Summit for Education award for innovation in learning / Mbillionth Award for m-learning / E-Asia award for best open and distance learning
1.5 Key challenges / Sustainability: schools component / Whilst the review team finds that, over the last year, excellent progress has been made to institutionalise the EIA approach, sustainability of the schools components remains a key challenge. Every effort is being made by relevant project staff. Nevertheless, political factors which are beyond the control of EIA may have an impact on sustainability. For example, in three years there will be a general election, and this may result in a lack of continuity. / Sustainability: costs and value for money / Driving down unit costs is essential for the sustainability of EIA – in the long term the project approaches must be affordable for GoB. / Sustainability: Media and Adult learning / BBC Media Action is exploring various options around sustainability. Future approaches must be affordable for the majority of Bangladeshis. / RME for schools components / EIA in schools, at present, is overall, a success story. Over a nine year project, there is a need for a strongly focused and staged dissemination plan to ensure that project successes are communicated clearly to relevant stakeholder groups. There is a wealth of monitoring and evaluation data available for the schools components, targeted and high level dissemination is not yet transmitting the success stories of the project.
1.6 Annual Outcome Assessment / Are the outputs going to achieve purpose? / Theory of change / EIA began in 2008.The 2011 annual review commented on broader issues relating to the purpose statement and goal statement within the logical framework. For example, the review team noted that the project does not have the scope to bring about ‘full participation in economic and social activities and opportunities.’ In 2011 DFID asked that projects develop a ‘theory of change’ at inception stage. This is now a requirement for research projects. Nevertheless, it would be useful for key stakeholders to jointly develop a theory of change for EIA, focusing on prioritising a set of research questions, and agreeing how best these questions might be answered. There has already been progress in this area. BMB, BBC, and OU have a drafted a ‘pathways’ approach which could contribute to this work: / “Following on from the DFID strategy meeting in December, there has been ongoing work to further develop the ‘critical pathways’ that link the output to purpose and purpose to goal indicators, and to consider the currently available research evidence to substantiate these. In addition, there has been further consideration with the DFID development economist to examine the nature of macro-economic indicators that could be used at goal level, in relation to the critical pathways. The outcomes of this work will be a set of clearly defined critical pathways, linking output to purpose to goal, with associated macro-economic indicators, upon which basis we will conduct research to collect relevant data.” / ( Extracted from EIA quarterly report for January – March 2012) / In summary, it is important that EIA addresses to what extent, in the context of Bangladesh, enhanced English language skills can make a significant contribution to economic growth, and whether, and to what extent, enhanced English skills enable fuller participation in economic and social activities and opportunities. There is thus a need for a fuller examination of links between outputs and purpose – the case for an overall causal link between English language skills and economic development has not yet been made. This is a growing research field, and research evidence is of necessity nuanced and confined to a specific geographical context. EIA has the potential to contribute to this research field; to take this work forward, the project needs to strengthen links with technical and vocational initiatives, with industry, and with employers. Across the project, monitoring, evaluation, and research which will provide evidence of the impact of EIA on economic and social participation, and employability, could be strengthened. This would provide evidence of how, and in what ways, the project outputs contribute towards the overall purpose.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / Key cost drivers appear to be well-identified and managed. Detailed comments can be found in Section 5 / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Please see section 1.6. A fully developed theory of change may indicate changes in evidence and their implication for the project. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation is currently planned

4. Risk
4.1 Output Risk Rating: Medium / English in Action is a medium risk programme. / 4.2 Assessment of the risk level / The main risk for the EIA programme is its sustainability. Sustainability (Institutionalisation) is being taken forward as a separate output from 2009 and the review team have confidence in the quality, appropriacy, and targeting of activities under this output. Nevertheless, political instability could impact strongly on the project’s ability to implement. This is not within EIA’s control. / The project management team maintains a comprehensive risk management matrix. This is clearly organised against goal, purpose, and the five outputs, and the sections on mitigating risk are strong.
Risk of funds not being used as intended / In line with the previous review, the Team found the project to be tightly managed and costs controlled. Quarterly financial reports are provided on time and to a high standard. / In the last 12 months, the project has recruited Field Coordinators to manage training and undertake the monitoring of Teacher Facilitators across seven districts. A manual for the Field Coordinators stating project financial management procedures been produced and training provided. / As part of the Quality Assurance system, a monitoring system for procured technology is in place. This uses the field coordinators to ensure that the technology provided under the project (Ipods/mobile phones) is tracked. / The recently formed UK watchdog, the Independent Commission for Aid Impact (ICAI), visited DFID Bangladesh in 2011 to undertake a study on possible corruption. The EIA programme was reviewed and no issue concerning misuse of funds within the project was raised.

5. Value for Money
5.1 Performance on VfM measures / As recommended in the 2011 review, the project has developed key performance indicators on Value for Money. These measures focus on the cost of inputs (materials) and outputs (cost per teacher/child/adult learner reached). We recommend that EIA also monitor the cost per child or adult with improved learning outcomes. This will demonstrate how cost-effective the intervention is at improving language skills of those reached. / 5.2 Commercial Improvement and Value for Money / Schools component / Value for Money of the schools based component will be dependent on the number of schools reached and the effectiveness of the communicative learning materials in improving children’s English competence. The project intends to reach 12,500 teachers by 2014 and 67,000 teachers by 2017. Three alternative models for scaling up were costed and the most cost effective model selected. Based on projected figures, the cost per teacher of delivering the primary school based component has been reduced from £600 in phase 2 to £220 in phase 3, and the cost per child from £6 to £2.75. If the EIA approach is adopted by the GoB, there is the potential to reach over 18 million children within the school system, dramatically reducing the cost per child reached. / Key cost drivers of the teacher training package are technology (mobile phones, SD cards and amplifiers). The cost of materials has been reduced from £210 per school in phase 2 to £60 in phase 3. These savings have been achieved by larger print runs and rationalising the number and type of learning aids produced; for example by reducing the number of posters to one set per school instead of per grade. / Recommendations / We recommend that the project continues to refine the materials to ensure that they are low cost, durable and potentially affordable for GoB to reproduce after the end of the EIA programme. The indicative per teacher or pupil spend on materials under the PEDP III programme could be used as a benchmark against which to compare project spend. / We also recommend that DFID reviews the public facing materials (i.e. hard cover notebooks, pens, bags) produced by the project and ensures these are in line with DFID Communications Policy. We recommend that Promotional items without a development goal should be stopped, for example, EIA branded notepads and pens. / Value for Money: Media and adult learning / Discounts/added value negotiated on all transactions at procurement stage. E.g. BBC negotiated with mobile operators, resulting in callers paying ¼ the cost of a normal telephone call, meaning to complete course 1 costs as little as 200 taka (£1.5), average 500 taka (£4). BBC also secured the promotion of BBC Janala 3000 number via SMS at no cost to all of the mobile operators network users as part of their ‘value added service’. / Marketing: free air time secured on BTV, reduced rates secured across other channels. / Newspaper: Prothom Alo provide space for lessons four times a week without charging the BBC. / CDs and books produced last year with archive English lessons, further maximising reach and increasing value for money. / Costs drastically reduced for final series of Mojay Mojay Shekha; e.g. by training local staff to film and edit, reducing shoot time, filmed out of the studio on location, smaller production team, etc. Repeat broadcasts planned for 2012, to maximise reach, impact, and value for money. / Spend and forecasting analysed quarterly with EIA, however this does not break down to unit costs so industry comparisons are difficult. / Admin costs hover around 10% which is reasonable and in line with other DFID projects. / Unit costs: difficult to assess vfm of the impact of BBC Janala (in future, could be linked to the new competency test). However, the vfm for components can be looked at; for 2011/12, BBC Janala costs average: / TV: 13p per person reached (repeat screenings will deliver more vfm) / Mobile: 24p per person who called (£1.32 per person if counting only regular users) / Website: 79p per unique visitor / English clubs: £55.73 per person / Industry training: £2,048 per participant / Course 1 marketing campaign reached a potential 32 million people, costing less than 1 Taka per person reached / Recommendations / BBC/EIA to further drill down and track unit costs for each component to enable industry comparisons (both in the UK and Bangladesh), and cost per learner per component, to better assess value for money and identify where costs could/should be reduced further. / English Clubs and creative industry workshop training crucial for sustainability; however potential savings and economies of scale should be identified to try to bring down the cost per learner. / Costs and timescales / The project is on track against financial forecasts. Training of the first 4000 teachers under Output 1 and 3 was set back by six months due to a delay in GoB approving the project. Activities and budget have been re-profiled and approved by DFID to ensure outputs will still be achieved by 2014. / Over the period under review, EIA have taken a number of strategic decisions to further improve the VFM of project management and implementation. The following examples were provided by the project partners; / Using local service providers where possible, e.g. Bangaldeshi production companies, printing and communication agencies. / Management agent providing a support and challenge approach with all project partners to improve VFM / Delivering through local partners where possible, e.g. Institute of Education Research, Dhaka University, use of UCEP offices to house EIA Field Coordinators. / Robust internal procurement procedures for service contracts / Use of VC to reduce UK-Bangladesh flights and modest accommodation (£25) for international expertise whilst in Dhaka. / 5.3 Role of project partners / The project is managed by BMB. In agreement with the 2011 annual review, we find that this is an area of strength for EIA. The project is tightly managed project and processes are transparent and thoroughly documented. Procedures for planning, financial monitoring and forecasting, resource management, and procurement issues are effective and transparent. The two main delivery partners, OU and BBC Media Action, have diverse skills and approaches - for example, very different approaches to research, monitoring and evaluation. / We find that, overall, BMB Mott McDonald have demonstrated considerable skills in managing the main delivery partners – OU and BBC Media Action. / The 2011 annual review’s recommendation that project strands become more closely integrated (‘One EIA’) has resulted in joint working and synergy across the schools and media/ adult learning strand. / The review team suggest that relationship building could be strengthened across the project strands, however. The review team note the need for more effective dissemination of project achievements, and quarterly communications meetings would also provide a structured way of ensuring that this work is taken forward across the project strands. / Brand: in its upcoming branding review, BBC should research awareness of UK Government funding for BBC Janala and ‘English in Action’. If possible, the research should also establish brand recognition and value-added of using ‘English in Action’. The findings will inform decisions re: the use of EIA branding in the media element – if it does not add value, it should only be used where sensible and not extensively. Instead preference should be put on using ‘funded by the UK Government’. Explore benefits of cross-marketing, e.g. publicising BBC Janala in the schools component. / Recommendation / We recommend that quarterly communications meetings are set up from this point onwards, to strengthen relationships, joint working, value for money, and dissemination work. / The BBC's upcoming brand research should include examination of awareness of UK funding for BBC Janala and English in Action. / Local partners: There are two local partners – UCEP and FIVBD. UCEP plays a key role in the project; UCEP schools and teachers have been involved in the pilot phase and will continue to be involved in the upscaling phase. FIVBD have played a more restricted role in the project; and their activity has been largely confined to piloting and using the reading scheme produced through the schools component. We note, and welcome, the interest from UNICEF in the work of EIA, and would encourage engagement with other relevant NGOs / Recommendation / We recommend that the involvement of local partners be given prominence in forthcoming dissemination work, since this gives clear messages that EIA targets and supports the poorest in Bangladesh. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Not applicable

7. Conclusions and actions
We found EIA to be a well-managed project, working to a highly ambitious agenda. We believe that a strong case can be made for the impact of the media/ adult learning component, relating to EL competence indicators and reporting of the pedagogic theories which underpin the products and platforms. We are impressed by the thorough and imaginative ways in which sustainability for the work of BBC Janala is progressing. / For the schools components, we are convinced of the high quality and impact of teacher training and support, and overall, research shows that the work is being embedded in classroom practices. We are impressed by the sensitive ways in which recent changes to materials have fully contextualized the intervention to the needs and realities of Bangladeshi classrooms. / We find that the project has some strong stories to tell. We are in year four of a nine-year project. The review team is most keen that the positive impacts of EIA are captured in a clear and accessible way and disseminated as widely as possible. / Sustainability (output 5, Institutionalisation) has been taken forward fully and sensitively by a strong EIA team. We commend this work highly, and we can already see ways in which the EIA approach for schools will become embedded in mainstream practice. Hopefully, this highly positive influence will have a cross-curricular impact. For media/ adult learning, sustainability planning is going forward steadily, and support from DfID in this area has been useful and supportive. / Nevertheless, sustainability is ultimately dependent on political factors which are beyond the direct control of EIA, and so this remains an area of risk for the programme. / We would welcome the development of a theory of change for the programme, and we believe that this might feed into monitoring, research, and dissemination activities. / Overall, EIA has had a successful year. / Recommendations / Please see the summary of recommendations in the accompanying document.

8. Review Process
The review team visited EIA Bangladesh for six days from 5th to 10th May 2012. The following forms of data collection were used: / Documentary review – 138 documents were made available to the review team on the project extranet / Presentations on annual progress by implementing partners / Observation of teaching in two EIA schools / Focus group discussion with participating teachers / Separate meetings with OU and BBC senior staff / Meetings with BMB senior staff, including meetings dedicated to financial management and VFM / Meeting with the MoPME Secretary / Informal meeting with the wider EIA ‘family’