Type of Review: 2nd Annual Review
Project Title: Punjab Economic Opportunities Programme

Date started: July, 2010 Date review undertaken: July 16-18, 2012

## Introduction and Context
What support is the UK providing?
Punjab Economic Opportunities Programme (PEOP) is a £ 55 million intervention being undertaken in four districts of South Punjab ranked amongst the poorest ten i.e. Bahawalpur, Bahawalnagar, Lodhran and Muzaffargarh. The Programme has two components sponsored jointly by the Government of the Punjab (GoPb) and DFID: the Skills Component (£ 25 million) and a Livestock Component (£ 25 million) which are being supported with Technical Cooperation worth £5 million, the latter being managed by DFID. DFID and GoPb contribute equally (£12.5 million each) to each of the two main programme components while the Technical Cooperation Component is fully financed by DFID. / The Skills Component is being executed through the establishment of the Punjab Skills Development Fund (PSDF) which acts as a purchaser of vocational training services working under the principles of competition. PSDF, which is an independent, not-for-profit corporate entity established under the Companies Ordinance, 1984. PSDF works under the supervision of a private-sector-led Board of Directors and is managed by competitively hired professional staff. PSDF intends to expand the provincial training capacity by engaging private providers for the skills development of 80,000 individuals. Its target beneficiaries are the poor and the vulnerable (40% women) belonging to the four districts. (Poor are defined as those with consumption of $ 2 a day and vulnerable defined as those with consumption level below $ 4 but more than $ 2 a day). / The Livestock and Dairy Development component is housed within the Livestock and Dairy Development Department (L&D Department) of the GoPb and is being implemented by a Programme Implementation Team (PIT) based in Bahawalpur. The aim of this component is to expand veterinary and extension services to livestock farmers, thereby enabling them to improve the quality and quantity of their milk yields and earn more income. The PIT designs the L&D interventions including the monitoring and evaluation approach to be followed and then contracts them out on competitive basis to private parties and/or public parties for delivery. / The TA being provided by DFID covers advisory and technical support to help build the capacity of the implementing partners and deliver the programme, monitoring and evaluation and most importantly a set of baseline surveys (household survey, employers’ survey, livestock supply side surveys) and a mid-term and final evaluation of the activities following a Randomized Control Trials methodology. Research data is also helping to shape the design of the interventions to ensure maximum development impact of the Programme.

What are the expected results?
The expected impact of the program is “reduction in poverty in the PEOP districts”, measured through following three indicators and targets for 2015: / Poverty Headcount Ratio (‘Poor’ defined as those with consumption levels below $ 2 a day in the PEOP districts). TARGET (2015): Reduction of 5% from baseline of 32.97%) / Poverty Gap Ratio for the PEOP districts; TARGET (2015) Reduction of 1% i.e. from baseline of 9.7% to 8.7%. / Vulnerability Gap Ratio for the PEOP districts; (Vulnerable defined as those with consumption level between $2 and $4 a day). TARGET (2015): Reduction of 1% i.e. from baseline of 14.5% to 13.5%. / The expected outcome of the program is “poor and vulnerable people actively engaged in productive economic activities in the 4 selected PEOP districts”, measured through following 6 indicators and targets for 2015. The first 3 indicators are for the PSDF while the remaining 3 are for the livestock and dairy component: / PSDF indicators: / Per capita household consumption in the target population to increase by 13%, 14% and 15% while consumption at the individual level (also measured through the RCT impact evaluation as the gap between the treated and control households based on tracer, midline and end line surveys) to increase by 6.5%, 7% and 7.5%. / Index of State Engagement (0.1 standard deviation increase in treatment verses control households) / Index of Wellbeing (0.1 standard deviation increase in treatment verses control households) / (All of the above indicators will be measured through RCT impact evaluation as the difference between treatment and control households based on tracker, midline and end line surveys.) / L&D indicators: / Number of socially and/or economically marginalized women owning at least 1 small ruminant (goats/sheep) for livestock farming; TARGET (2015): Increase of 8,000 women owning at least 1 small ruminant / No. of farmers accessing veterinary and extension services; TARGET (2015): Increase in access of farmers to veterinary and extension by 10% / Average animal milk yields amongst beneficiary livestock farmers; TARGET (2015): Average milk yields amongst targeted livestock farmers increased by 20% / The outputs and targets are given below: / PSDF Outputs: / Output 1: Development of a sustainable model for funding competitive skills delivery. / The level of maturity of PSDF as an innovative model for skills financing will be measured. / Target by June, 2015: / It is expected that by the end of the Programme duration, PSDF will be recognized as a successful skills funding model. Prior to PEOP no skills funding agency existed in Punjab. / Output 2: Number of individuals trained in the four PEOP districts / Target by June, 2015: / PSDF shall finance the trainings of 80,000 individuals belonging to the four PEOP districts, 40% of these (i.e. 32,000) shall be women. / Output 3: Private training places mobilized / Percentage of private sector places created as a result of PSDF funding will be measured. / Target by June, 2015: / PSDF shall stimulate private provision of skills and increase the share of private sector capacity in its contracted trainings to 80% by the end of the Programme duration. / L&D Outputs: / Output 4: Output 4 – Access to yield enhancing practices, better healthcare, and better animal nutrition available to livestock farmers in the selected 4 districts. / Target by June, 2015: / Increase in access of veterinary and extension services to 150,000 farmers / Output 5 – Livestock asset transfer to primary and secondary beneficiary families in selected 4 districts / Target by June, 2015: / Transfer of livestock assets to 8,000 primary and secondary beneficiary marginalized women in 4 PEOP districts / Output 6 – Feedlot fattening of animals for enhancing meat production / Target by June, 2015: / 10% increase in animal price of fattened animals. / Output 7 – Policy and Regulatory Environment: a) Support to GoPb for skills policy framework; b) Appropriate policies and regulatory framework to enable the private sector to participate in livestock markets (liberalize livestock sale and purchase). / Target by June, 2015: / Improved policy and regulatory environment for skills / Regulatory framework (policy, law, rules) in place and implementation initiated to allow farmers to fetch competitive prices, reflecting quality and weight of animals. / Output 8 – Knowledge management and sharing / Target by June, 2015: / Final RCT Evaluation Reports Produced (Skills and Livestock) (By October 2015) / (Over the course of the Programme, survey-based reports i.e. 2 household reports, an employer’s survey report, livestock supply-side survey reports, and reports of mid-term and final RCT evaluations) are prepared and are publicly available.

What is the context in which UK support is provided?
Prior to the recent economic slowdown, the Punjab Province in Pakistan had been enjoying a relatively high level of economic growth (6-7%). However, this growth has been uneven and has left many districts in the south and west of the province untouched, with poverty head count figures in these districts (at tehsil level) ranging between 48 – 64% compared to an average of 10-35% in the North and Centre[1]. Poverty in these districts is structural and non-transitory. / Analysis of poverty in Punjab shows that diversification of employment out of agriculture; access to remittance income; access to irrigated land; ownership of livestock; and human capital attainment are the major drivers out of poverty for a household. In South Punjab, extreme poverty and a historical presence of radical religious organisations (amongst others) have resulted in a trend of increasing militancy among the poor youth[2]. PEOP will make a contribution towards halting this trend through provision of economic opportunities to unemployed poor youth and tackling the causes of poverty and not merely its symptoms. It is vital that skills development opportunities in Southern Punjab, which are considerably below international benchmarks, are expanded to improve access of its under-privileged population to self- and wage- employment, thereby also enhancing trust in the state and self-confidence especially amongst women / Other Donors in Skills and L&D Sectors in Punjab / Currently the major player in the skills sector is DFID itself with its investment in PSDF. World Bank is contemplating a £50 million investment in the sector, the design of which is currently under consideration though its focus will be predominantly on TEVTA reforms and possibility of cofounding PSDF. GIZ and EU have a TEVT sector reform programme at the federal level with NAVTEC (apex skills body) which is focusing more on developing the TEVT infrastructures i.e. skills standards, revision of curricula, teachers training etc. Proactive coordination has been made with the WB which is planning its investments to complement the work of PSDF while the GIZ-EU programme draws regularly on the work of the PSDF to inform its own activities. / Though a number of donors are working for the development of the livestock sector in Punjab, among the larger development programmes are those of Haleeb Foods ($25 million) and DFID itself. USAID (through DRDF) ($14 million), IFAD ($7 million), and PRMP/ADB ($5 million) working at the provincial level are the other notable programmes. CIDA and AusAid collectively have programmes worth $2.5 million. DFID provided TA support to help organize a donor coordination conference in March, 2012 to harmonize the investments coming to the sector. The follow up conference planned in June, 2012 got delayed as the priority for the PEOP DFID team was to make the PEOP L&D activities operational and the Secretary L&D Department was engaged in resolving issues of livestock related public sector companies.
[1] Baseline Report of TAMA, 2009
[2] Terror’s Training Ground; Ayesha Siddiqa (2009); Newsline Pakistan issue of 9th September, 2009; accessed on 13th August, 2012; 2. From FATA to South Punjab – The Looming Leap of Islamic Radicalism in Pakistan; P. K. Upadhyay; Institute for Defense Studies and Analyses; 2009. 3       Pakistan’s New Generation of Terrorists; Jayshree Bajoria; Backgrounder prepared by Council on Foreign Relations, USA; 2011

## Section A: Detailed Output Scoring

Output 1: Sustainable model for funding competitive training delivery
Output 1 score and performance description: A. Output has met expectations / Indicator: Level of Maturity of PSDF as an innovative model for skills financing Baseline: Prior to PSDF no such skills funding agency existed. Milestone for 2011-12 is: PSDF funding model established and tested first generation products / Progress against expected results: / Milestone for 2010/11 Achieved July 2011 Milestone for 2011/12 Achieved July 2012 % of Total Project / PSDF to be established as an indpendent corporate body PSDF incorporated in Oct, 2010 PSDF Funding model established and 1st generation products tested Target accomplished. See the narrative below 50% achieved
Both at the institutional level and as a business model, PSDF’s performance has been promising over the last one year, particularly given that it was incorporated only in October, 2010, and business operations commenced in June, 2011 after the CEO and the staff were engaged following a competitive process by end of May, 2011. / Progress at the Institutional Level: / Robust Governance: PSDF has a private sector led Board which is very intensively and proactively involved in providing the Fund strategic guidance and support and scrutinizing its work. The Board has had ten meetings until May, 2012, though under the Companies Ordinance, 1984 it is required to meet only once in a quarter. The Fund has constituted 3 sub-committees to oversee finances, skills interventions and human resource issues. / Lean Management: Following the recommendations in the first annual review of the programme, two new members/directors were added to strengthen the private sector voice in the Board The organizational structure of the Fund was rationalized by the Board and a lean management structure was approved. Total staff strength at the end of May 2012 was 23 against 73 positions envisioned in the original staffing plan approved in the PC 1 by the GoPb. PSDF developed and adopted its own Employee Service Rules after approval by the Board of Directors. / Financial Management on Track: PSDF implemented a Financial Management System (SAP) in March 2012 to manage its internal accounts. An independent chartered accountancy firm hired competitively and approved by the Board conducted the first audit covering 2010/11 which was approved by the Board. The second audit is underway. In response to the FRA recommendation, the position of an Internal Auditor has been approved by the Board and is expected to be filled by September, 2012. / Vigorous Monitoring: A system of external monitoring (including a Monitoring and Reporting Manual) was designed in-house and a third party monitoring firm (Semiotics) has been engaged to monitor the first skills scheme of the PSDF i.e. Skills for Employability under which 17,000 trainees and training providers will be monitored to help with contract management. The Fund developed Business Rules for dealing with violations of contractual obligations which were expressly linked with payments. An online system to check identity frauds and dual enrolments was operative and being used by providers in May 2012.Technical assistance support is being provided to help PSDF develop a MIS system that can meet the monitoring and evaluation information requirements, particularly as more skill schemes are introduced by the Fund and the scale of the data management exceeds the capacity of the existing software/Excel being used. / Increasing Interest of Potential Investors: PSDF was approached by UNICEF and Citi Foundation for a possible contribution. Citi Foundation has to date communicated its acceptance of the funding case worth USD 30,000 (final decision pending approval of NY office). Meanwhile, the World Bank is closely aligning its potential investment of $50 million in the skills sector with PSDF and there is considerable interest within the GoPb to direct the WB funding to the Fund itself. Conversations are on-going and the scale of WB investment is not defined yet. / Progress as a Funding Model: / Cost Effective Model: Following good procurement principles to generate competition among skill providers[3], PSDF is offering cost effective training. Proposals are assessed against quality and cost. PSDF has adopted a trainee-financing/output based model which is contrary to the practice in the public sector, where skill providers are paid according to the services that they render to individual trainees. / A Cost Comparison- PSDF Vs Public and Donor Funded Training Programmes / From the graph above, it can be seen that PSDF’s fully loaded[4] per trainee cost has been is Rs. 42,000 which is good value for money when compared with public sector costs[5] in Pakistan and the costs of other recent donor funded programmes in Pakistan and other developing countries. PSDF’s operational expense is only 7% of the budget[6]. The Fund is also promoting transparency in aid as it is governed by the rules and regulations of the Securities and Exchange Commission of Pakistan (SECP) and audited under the Companies Ordinance 1984. / Focusing on Core Expertise and Outsourcing M&E and Research: PSDF is singularly focused on its core function of funding skill providers to provide training. Only operational expenses of the skill providers are financed and not any capital expenditures. The tasks performed in-house by PSDF include: i) designing and rolling out of skill financing schemes in line with market demands and the need to reach the poor and the vulnerable groups, ii) technical and financial evaluation of proposals, and iii) pricing of training services. The critical functions of monitoring and evaluation and evidence to guide interventions have been outsourced to third party, specialized entities with expertise in these areas. The outputs of these two processes are, however, critical in guiding Fund’s future course and are helping it to tailor its operations accordingly and ensure provision of quality training. For example currently PSDF primarily finances pre-employment vocational training. However, depending on evidence of needs, it may also support in-service training, technical education, apprenticeships and development of core skills. / Progress of First Generation Skills Schemes: / PSDF has developed its procurement documents including the design of EOI and RFP forms and a bid evaluation system. A Product Design and Evaluation Committee headed by a Board member was formulated and became active in the scrutiny and endorsement of the bid evaluation process undertaken by the management. / As the riverine floods of August 2011 had ravaged one of the target districts, PSDF was requested to launch a special product for the disaster affected in rural areas in Muzaffargarh. The first pilot product was launched in May, 2011. / The first large scale EOI was advertised in June, 2011, which launched the PSDF scheme “Skills for Employability”. 117 EOIs were received against which 54 proposals were submitted after shortlisting. 43 proposals were technically qualified and contracts were signed with 31 training providers. A contract management and payment system was developed and is currently functioning under the supervision of the company CFO. / Learning by Doing and Reliance on Research: The PSDF has adopted a continuous process of evidence informing delivery and vice versa. Evidence is playing a critical role in the design of PSDF interventions. For example, the experience of the first two skills schemes of PSDF along with the results of the CERP baseline Phase 1 household survey have shaped the design of the next two skill schemes advertised recently. Experience has shown that two thirds of the training places offered by private skill providers have a minimum entry level of primary or above. Only one third of the training places have an entry level requirement below primary. The CERP baseline survey reveals that setting an entry level of primary excludes 40% of the total urban population and 60% of the rural population. In PSDF’s first skill scheme[7] while one third of the training places could theoretically be accessed by people with education level below primary, in practice, the average educational level of students was higher due to training providers’ tendency to screen for better candidates. / In order to ensure that lesser educated people get a fair chance to acquire skills, a two-pronged approach has been adopted by segmenting the market to address access-related issues. PSDF has designed new products, namely Skills for Jobs and Skills for Markets to address two distinct segments: the former delivering standard training courses with external certification; and the latter offering skills courses for the marginalized (especially the less educated and rural women). The latter segment will consist of providers specializing in locally contextualized skills development that requires little or no education for entry. / Recommendations: / Given the significance of proactive and strong private sector governance for retaining the autonomy and market orientation of the Fund, Board should replace inactive Board members and the seats left vacant by the departure of two private business sector Board members should be filled by appropriate private business representatives. The private sector strength of the Board may be enhanced further given its scale up plans. Further, Secretary Agriculture may be invited to join the Board given the Fund’s plans to introduce agriculture and livestock and dairy related skills in future. / PSDF should market itself to receive funding from additional national and international sources. This will serve to improve the sustainability prospects for the Fund and provide resources for complementary activities currently not within the ambit of PEOP but which can help improve market linkages of its trainees. / A complex system of procurement, contract management and monitoring has been adopted which requires specialized competencies within the organization, particularly as the scale of the Fund grows further. Locating the head office of the PSDF in Lahore will be helpful in attracting the required expertise to the Fund which are challenging to find in/attract to the districts. Meanwhile, continued TA support (Skills Strategy Adviser) is recommended to fill the capacity gap and to assist in the future scale up plans. Additionally, in order to strengthen institutional capabilities of the organisation and avoid leadership gaps a succession plan should be developed to groom and develop the next tier of managers. / Impact Weighting: 8% / Revised since last Annual Review? The log frame of the PEOP was revised in April, 2012 and this is a new output not present in the original log frame. / Risk: Medium / Revised since last Annual Review? The risk is medium and can be mitigated by ensuring that the private sector Board members who leave or are inactive are replaced by the Board without delay so that the private sector orientation of the Board is not compromised. Other risks are associated with lack of a strong second tier management that can fill the gap in CEO’s absence and potential risk of attracting the required expertise in Bahawalpur. Acting on the recommendations proposed above can help mitigate the risks.
[3] All kinds of skill providers may apply such as for profit-training institutes, NGOs, companies, businesses, academic institutions and public sector providers.+
[4] Including management and monitoring and evaluation costs.
[5] Direct training costs includes: trainers’ remuneration, fixed costs of training sites, consumables and costs incurred in developing training materials.
[6] The management is only 1/3 of what has been provided for in the GoPb’s Programme Document. provides
[7] First skill scheme of the PSDF is called Skills for Employment.

Output 2: Skilled Trainees – Number of people trained in PEOP districts
Output 2 score and performance description: A+. Output moderately exceeds expectation / The end of project target for output 2: “Number of individuals trained in the four PEOP districts” is 80,000 with 40% women. The baseline value for above indicator was zero as PSDF was established under PEOP.Milestone for 2011-12 is 10,000 trained (40% women) For the year 2011-12, / PSDF was to deliver training of 10,000 individuals (out of which 4000 are to be women). During 2012-13, 30,000 trainings have to be undertaken followed by 35,000 during the next year and 5000 in the final year of operation. / The Board revised the original target of training 250,000 to 150,000 poor and vulnerable based on actual experience of the Fund and the cost quotes that it received from skill providers in response to its call for proposals. / Progress against expected results: / Milestone for 2010/11 Achieved July 2011 Milestone for 2011/12 Achieved July 2012 % of Total Project / 0 0 10,000 trained (40% women) SFE= 9,459 + Model Villages = 680. Total = 10,139 (101.4% of target) 42% are women 13% / During its first year of operation, July 2010- June 2011, no training output was expected due to preparatory activities such as staffing, budgeting, formation of Board Committees and carrying out of a baseline survey.
During the year 2011-12, two vocational schemes were operational: Skills/Vocational Training in Six Model Villages (pilot scheme for training 500 people) and Skills for Employability (total target of 17,000) in the four target districts. / As of July, 2012 under the SFE training of 6237 students is underway while under the Model Villages Scheme has been completed. / Based on its initial experience of SFE, the Fund has designed Skills for Markets, a scheme that aims to target trainees in the rural areas and particularly women. In order to overcome issues of mobility training will be provided closer to the beneficiaries enabling women to overcome issues of mobility. / Recommendations: / The log frame needs to capture the quality aspect of the training, beyond the number of people who have been trained. Inclusion of indicators reflecting the income earning impact of the training, and/or % of people who have received certified training etc needs to be considered. / PSDF management has adopted a practise of preparing and disseminating a monthly progress report. This enables the Board and sponsors to clearly ascertain the achievement of milestones especially the number of trained and those under training. The report however provides an overall number which is not gender disaggregated. PSDF should strengthen its MIS to enable gender-based reporting and reporting that meets DFID’s quarterly operational reporting requirement. / With close to 9,000 trainees entering the labour market, PSDF choice of trades and providers should be guided by employability of trainees. It should develop a system of feedback and course correction to align its sectoral targets with the employment status and incomes of those recently trained. A tracer study may be conducted to ascertain the employability of recent graduates of the Skills for Employability at suitable intervals e.g. at three months, six months and one year. / Being a new Fund, working in poor districts and in low economic growth environment PSDF has focused on delivering ‘number of trained’. Nevertheless, going forward the Fund should develop and articulate its outreach strategy explicitly to ensure an inclusive programme and its performance should capture outputs related to employability and quality of training. This is all the more important given that the Board members think that the focus of a scaled up PSDF should be on inclusive economic growth and not poverty reduction per se. / BISP has launched its training component and offering stipends as high as PKR 6,000 per head which is much higher than what PSDF is offering (Rs.1,000 for within district and Rs.3,000/month for those training outside districts). Since BISP is a national programme, the risk of people taking advantage of BISP and PSDF training needs to be mitigated by sharing information and coordinating activities. Both DFID and the PSDF Board need to pursue the matter with BISP. / Impact Weighting: 30% / Revised since last Annual Review? Since the log frame has been substantially revised and new outputs have been introduced on the skills side the impact weight of this output has been revised from 25% to 30%. / Risk: Medium / Revised since last Annual Review? The risk of PSDF not delivering the training is medium as the total number of people to be trained has been rationalized and the Fund has slightly exceeded its target for the year under review. The risk is not reduced to low as the performance of the Fund with increased work load (with introduction of new skill schemes being planned) will be tested.

Output 3: Private Training Places Mobilised
Output 3 score and performance description: A++. Output exceeded expectations / Indicator: % of private sector places created as a result of PSDF funding. The baseline for this indicator was 0, as no organization was working to mobilise private sector training places.
Progress: / Milestone for 2010/11 Achieved July 2011 Milestone for 2011/12 Achieved July 2012 / 0 0 50% of total PSDF funded training places 77% achieved (3% short of the end of the programme target) / The target is to improve the mix of available training capacity for the target districts in favour of the private sector. “Private” is defined as inclusive of training places offered by for-profit and not-for-profit organisations but is exclusive of training capacity in TEVTA and PVTC (the two public providers of Punjab Province). / In the first pilot scheme (Skills/Vocational Training for Six Model Villages), two out of the three selected training service providers were from the private sector (66%). / In the subsequent scheme (Skills for Employability), 3 out of 31 organisations were public (i.e. 10%); the remaining 90% were all “private”. / A good mix of organisations responded to PSDF’s invitation to bid. Amongst the selected organisations were NGO’s, private firms, private training institutes, not-for-profit companies and public private partnerships. Private entities have also been able to leverage public sector training capacity after signing partnership agreements with public sector training institutes. There is evidence that PSDF has supported expansion of capacity in current training providers such as College of Tourism and Hospitality Management (COTHM Institute has set up a small campus in Multan and Descon’s school of welding is under construction. However, PSDF does not finance capital assets but only operational expenses of the trainers. Hence, no new training provider has entered the market. / Key activity results: / Contracts signed with 34 service providers for the training of 17,500 people. / Training activities commenced by all 34 training service providers / New skills such as Plant Doctor, Education Entrepreneurs, etc have been introduced / 3x increase in private sector capacity as compared to registered capacity in the districts. / Vocational training in 17 sectors and 68 trades / Recommendation: / The Annual Review endorses the rationale for expanding PSDF to across Punjab most importantly because the model is cost effective and design of skills schemes is dependent on course corrections based on research and actual experience. The recommendation under Output 1 of relocating the Fund Headquarter to Lahore with a strong regional presence will be critical for its positioning as a provincial funding agency, attracting new investors, contracting new potential providers, and influencing skills policy for providing a conducive environment for private investment in skills training. / PSDF should design skills schemes that will help promote new training providers in the private sector. / PSDF’s first generation products left the onus of identifying skills to be provided on the skill providers based on their assessment of employment potential of trades within the districts. Since then PSDF has moved on to matching skills supply with individual aspirations. PSDF needs to have independent assessments of potential of different trades by having better understanding of the labour market demand and giving more weight to it. / Given that PSDF has mobilized 77% private sector training places against a target of 50%, milestones for subsequent years should be revised and PSDF should aim to maintain at least 75% of its total training places mobilized/annum through private providers until the end of the Programme. / Impact Weighting:6% / Revised since last Annual Review? Y/N / Risk: Low / Revised since last Annual Review? New indicator not part of the earlier log frame. Risk rating is low as PSDF represents the only systematic funding window through which private providers can access public funding support. Hence the response of the private sector is expected to be strong.

Output 4: Access to yield enhancing practices, better healthcare, and better animal nutrition available to livestock farmers in the selected 4 districts.
Indicator for this output is the number of farmers accessing veterinary and extension services through PEOP. The baseline for this output is 0 in the absence of the Programme. / Output 4 score and performance description: B. Though the performance exceeds expectations in terms of exceeding the number of farmers that were reached, the output score is B and not A+, since the quality of the Farmers Days has been mixed. (See Section B, point 1.3 ‘direct feedback from beneficiaries). / Milestone for 2010/11 Achieved July 2011 Milestone for 2011/12 Achieved July 2012 % of Total Project / 0 0 5,000 farmers (20% women) 6,652 (27% women) 0.003% / PIT has completed the Farmers Day initiative, at 26 locations where 6,695 framers were provided advisory related to yield enhancing practices and better healthcare against a target of 5,000 farmers for this year. Two days were reserved for the Farmer Days. Day-1 for awareness raising and Day-2 for animal vaccination. An NGO consortium (leading organisation from Bahawalpur with district partner NGOs) was engaged through a competitive bidding process for the initial social mobilisation for two weeks, followed by the Farmer Days. 27,500 large animals (buffalo, cow) were treated 24,499 small animals (goats, sheep) were vaccinated. / 6,695 farmers reached this year is a negligible achievement considering the overall target of 150,000. This target was set during the log frame revisions as this is what was realistically possible to achieve by the PIT and that too only with the support of the Technical Assistance that was engaged in September, 2011. / (The TA along with the Secretary L&DD Department has been central in identifying and planning all the activities of the PIT that are currently underway and those that are planned in future and most importantly providing de facto leadership to the PIT team for identifying, designing and delivering interventions. / With the help of the TA, additional projects were planned such as the Mobile Veterinary and Extension Services and training of 5,000 paravets which are expected to reach the higher target number of farmers planned in subsequent years of the Programme. TA also helped design and initiate a PEOP scholarship program which is currently training 260 (30 women) veterinary assistants from the target districts. They are enrolled in three universities, in campuses of Patoki, Sheikhupura, Khoshab, Jhung, Faisalabad and Multan. All girls are enrolled in Patoki. These VAs will also be a ready source of such services in their respective communities. PIT/PEOP has also recently signed an MoU with Telenor to provide advisory services to farmers through mobile services on a pilot basis. The services have been initiated and so far being sent to 2,000 farmers on a pilot basis. The company is earning its revenues from advertising lumped together with the audio message. / Recommendations: / From speaking with beneficiaries in Bahawalpur, it shows that a one-day event i.e. Farmers Day is insufficient to properly convey the L&D related awareness messages to farmers and follow on activities that take a more long term perspective of raising farmers awareness and providing extension/veterinary services are essential. / In order to ensure that the poor and vulnerable farmers benefit from interventions, better targeting and social mobilization efforts are required. Otherwise the relatively well-off farmers will take advantage of the interventions instead of the intended beneficiaries.
Impact Weighting: 30% / Revised since last Annual Review? This is a new output which was not part of the earlier log frame / Risk: High / Revised since last Annual Review? The risk has been revised from medium to high in light of the implementation delays due to a weak PIT working at the field level, low department wide ownership of the L&DD, high dependence on consultants and time consuming documentary requirements/approval procedures required for approval of PIT activities.

Output 5: Livestock asset transfer to 8,000 primary and secondary beneficiary marginalized women in selected 4 districts
Output 5 score and performance description: C. New output introduced in the revised log frame.
Progress against expected results: / PIT is planning to transfer menu of livestock assets to 4,000 women initially, who in turn will transfer the off springs to another 4,000 women. No procurement or implementation has been initiated yet. The project is being planned in consultation with CERP, which has developed a concept note on asset transfer. / A well-targeted approach is required to ensure that only the marginalized women are included. / Impact Weighting (%): 5% / Revised since last Annual Review? This is a new output not part of the earlier log frame / Risk: High / Revised since last Annual Review? Yes
Output 6: Feedlot fattening of animals for enhancing meat production / Output 6 score and performance description: C. New output. / Progress against expected results: / No procurement or implementation has been initiated yet. The project for feedlot fattening has been approved by the departmental committee of the L&D Department (DDSC). / Impact Weighting: 5% / Revised since last Annual Review? Yes / Risk: High / Revised since last Annual Review? The output was not part of the earlier log frame
Output 7: Policy and Regulatory Environment / Indicator: a) Support to Government of Punjab for skills policy framework; b) Appropriate policies and regulatory framework to enable the private sector to participate in livestock markets (liberalize livestock sale and purchase). Baseline for these / Output 7 score and performance description: B. Output moderately did not meet expectation / Milestone for 2010/11 Achieved July 2011 Milestone for 2011/12 Achieved July 2012 / Skills Policy / L&D Policy: 0 / 0 Request for TA for policy met / Review of earlier reform work initiated -PSDF and TA provided comments on the draft of the Youth Skills Development Authority’s proposed functions + close coordination with the WB to ensure its investment is aligned with PSDF + draft Scale up Strategy for PSDF has been prepared and is going to be peer reviewed. / Not initiated / Inspired by the successful model of PSDF, the CM had constituted a committee to rationalize the skills regulatory environment in Punjab. The committee had proposed the formation of a skills apex body i.e. the Youth Skills Development Authority (YSDA). The CEO PSDF and the Skills Strategy Adviser for PSDF provided detailed inputs and comments on TVET structures in other countries and the draft functions of the YSDA and raised concerns about contradictory mandates of the Authority and its overlap with NAVTEC (apex skills body at the federal level). GoPb/P&DD reports that the YSDA legislation has now gone in background given its conflicting mandate and role. / Meanwhile, World Bank’s proposed investment of $50 million for TVET sector reforms in Punjab is being closely aligned with PSDF and there is possibility of WB investing in the Fund. / Draft PSDF Scale up Strategy has been prepared. The objective of the scale up is to establish PSDF as the sole window for directing public funds on a competitive basis to private skill providers and build a market of private skill provision. / PIT was unable to initiate work in this area due to preoccupation with preparing a work plan, identifying a menu of interventions, designing those interventions, preparing their PC-1 and soliciting departmental approval and trying to initiate implementation of the initial activities. / Recommendation: / Proactive coordination with the WB and other donors in the skills sector is required to ensure that the skills policy agenda is collectively taken forward. / impact Weighting: 10% / Revised since last Annual Review? Yes. In the original log frame this output was an indicator of a broader output the progress on which was to be reflected by 3 indicators covering access of farmers to microfinance, improved policies for private sector’s participation in L&D markets and regulation to enable farmers to fetch better prices. / Risk: Medium / Revised since last Annual Review? The risk of the broader output in the original log frame was medium and the risk for this output is also assessed as medium.
Output 8: Knowledge Management and Sharing / This output pertains to the publication and sharing of reports and data to be generated by the Centre for Economic Research Pakistan (CERP) that has an Accountable Grant Agreement with DFID to conduct the baseline household surveys covering skills and livestock and dairy, and other related surveys to inform the work of the PSDF and PIT. CERP is also to conduct a mid-term and end of the Programme evaluation of PEOP following RCT methodology. / Output 8 score and performance description: B. Output moderately did not meet expectations (high quality reports but delivery delayed due to reasons exogenous to CERP) / Progress against expected results: / Milestone for 2010/11 Achieved July 2011 Milestone for 2011/12 Achieved July 2012 / CERP Phase 1 Baseline HH Survey Reports (skills and livestock produced) The report was delayed and delivered in December, 2011 CERP Phase 2 Baseline HH Survey Reports (skills and livestock) / Employers Survey Report / Skill Providers Survey / Livestock Supply Side Survey Reports (8) Expected in Aug 2012 / Expected in Nov, 2012 / Expected in Nov/Dec, 2012 / Milestone for 2010/11 was delayed as the CERP proposal originally focused only on skills. Nevertheless, since PEOP covers both skills and L&D, the PSC decided that L&D should also be covered in the baseline surveys. Thereafter time was spent in identifying appropriate Principal investigators in the area of L&D and finalizing areas of research in conjunction with the PIT team. Delay also occurred due to non-cooperation of the FBS for providing the listing frames for conducting the household survey despite best efforts of the GoPb, CERP and DFID. As a result considerable time was lost and negotiations had to be initiated with the Punjab Bureau of Statistics from scratch. Plus, a new activity of household and enterprise listing in 861 primary sampling units was added to CERP’s original work plan. Further delay occurred as the initiation of the survey was postponed until after Ramadan-Eid, 2011. / The CERP Phase 2 household survey reports were expected by June, 2012. However, the enumerators were stopped in some areas by intelligence agencies. With the help of the P&DD, CERP and the consultants engaged under TA the matter was resolved and the survey was completed. / There has been considerable delay in the Employers Survey due to reluctance of the FBS to share the employers frame. Consequently, CERP has had to find alternative sources for collating the universe of the large and small commercial players in the PEOP districts. Further, there has been reluctance on the part of large employers to respond to the survey and cooperation of the Chambers of Commerce is being sought by CERP. / In light of extensive information obtained on wide ranging skill providers by PSDF through its bidding process it was decided to drop the Skill Providers survey for now and to conduct it later only if the need for this arises at PSDF. The savings made were used to finance: i) the livestock supply side surveys which were originally envisioned at a much smaller scale than the demand expressed by PIT later and the understanding gained by the Principal Investigators of CERP working on the L&D side. ii) a quick and dirty tracker report of the graduates of PSDF under its very first skill initiative for model villages and iii) a report on the uptake of the small scale vouchers experiment (900) (also administered by CERP) and a report on the Farmers Days. / The hh survey on skills indicated high demand and awareness about skills and its value. Nevertheless, the uptake of vouchers among the ‘infra-marginal individuals[8]’ on a pilot basis shows very low uptake of 5% due to reasons such as opportunity cost of training, distance of skill provider, responsibilities at home etc even though these people expressed interest in acquiring skills at the time of the hh survey. The low uptake almost across all segments is not unusual from the experience in other developing countries and shows that in addition to vouchers the recipients need to be provided an additional feature that will help overcome their reason for not availing the voucher. CERP is currently designing these ‘voucher plus’ schemes to see how uptake can be improved. / Recommendations: / Given the changes in the research agenda of the AG agreement of CERP with DFID and the delays in the surveys, the revised proposal for a cost and time extension needs to be provided by CERP at its earliest. / The proposal should also include ‘ over subscription design[9]’ RCT evaluation of the Programme along with associated costs as an alternative should uptake of the vouchers among the general public remain an issue. / Employers’ survey should be managed on priority basis so that PSDF has a demand side perspective which can be incorporated in the design of the skill schemes. / Impact Weighting: 6% / Revised since last Annual Review? Yes. The original log frame envisioned the creation of a Research Centre for Inclusive Growth for which the impact Weight was 8%. After the first annual review the idea of establishing a new institution was dropped in favour of focusing on PEOP sectors and RCT evaluation to be conducted by CERP. / Risk: Medium / Revised since last Annual Review? The risk rating for the output is the same. Risks emanating from non-cooperation of FBS, the absence of required listing frames and administrative issues in the field are tackled by CERP by finding alternative solutions. Issues pertain mostly to delays rather than the quality of the surveys.
[8] Individuals identified by hh during the survey as the most appropriate people within the home to acquire skills training. Interest to acquire training was confirmed from these individuals.
[9] Meant to measure the difference that skills bring about between those student who do acquire training vis-à-vis those who get selected but are unable to attend due to limited seats.

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? Yes. / During the MYR in April 2012, major changes were made to PEOP’s logframe in light of the actual experience of the PSDF, PIT baseline findings and the RCT evaluation approach that has been adopted for PEOP. The revisions have also helped to ensure consistency with DFID guidelines, logical connection between outputs, outcomes and impact level indicators. Provisional permission was obtained to use the revised logframe for this AR, but the final version of the logframe needs to be formally approved by the Head of Office. During the AR, the logframe was further fine-tuned / The changes in the logframe were made in consultation with all concerned stakeholders including PSDF, Planning & Development Department, PIT (staff and consultants), Livestock and Dairy Development Department and CERP. / Major changes in the log frame have been summarized below. The full revised and the old log frame are attached as Annex A and B. / Target Group: As a result of the mid-year review in April, 2012, an agreement has been reached with the GoPb to define the target population for PSDF as the poor and the vulnerable, using the thresholds of $ 2 and $ 4 as maximum daily consumption levels, respectively for these two groups. The Baseline Survey of Households (Phase 1 completed in late 2011) revealed that a large proportion of population in the four districts is clustered around the poverty line (the poor and vulnerable collectively constitute 80%). This means that a significant proportion of the district population is prone to adverse income shocks. / Original log frame had no baselines and milestones which are included in the revised version. / Consumption based indicators: Income based indicators have been replaced as they are noisy and less accurate than consumption based indicators which will now be measured at the household and beneficiary level. Consumption of target groups will be measured vis-à-vis that of the control groups following RCT evaluation to show the ‘with and without’ programme effects. CERP mid-term and final evaluation will assist in measuring the revised indicators. / Research and policy focus on PEOP sectors: Rather than focusing on development of a GoPb policy document for the development of poor districts policy focus is on the 2 sectors of PEOP interventions. The original log frame did not include any skills policy output. The objective of establishing a Centre for Research on Inclusive Growth has been dropped. Instead the focus is on research on PEOP areas i.e. skills and livestock and the tracker, mid-term and final evaluation of the programme following RCT. / PSDF specific changes: The outputs and indicators for PSDF have been expanded to capture achievements not envisioned at the time of Programme design. Total number of people to be trained has been rationalized in light of actual experience and costs. The use of vouchers for promoting demand among potential skill students is being conducted on an experimental basis rather than using it for reaching 64% of PSDF beneficiaries. / L&D specific changes: L&D outputs were also rationalized keeping in view the baseline household survey results, the capacity of the PIT team and the outcome and impact to be achieved. The policy and regulatory work envisioned under the original log frame was narrowed down. In light of the baseline research focus on micro finance was dropped as it did not fare as a major issue for the livestock farmers. / Recommendations: / The time frame of the PEOP needs to be enhanced until June, 2015 (evaluation results to be available by October, 2015) in order to deliver the Programme outputs. / The revised log frame (excluding the L&D component) be approved in light of the suggestion explained further below to terminate the L&D component. / 1.2 Overall Output Score and Description: A. Outputs met expectations / The overall output is A because the negative effect of the B and C scores awarded to the livestock and dairy outputs have been more than offset by the A, A+ and A++ performance of the PSDF. As per the revised logical framework for PEOP, the collective impact weight of the PSDF related outputs is 44%, whereas the collective impact weight of the L&D related outputs is 40%. Output 8 related to Knowledge Management and Sharing is to be delivered by CERP and has a B rating while output 7 related to policy work has an impact weight of 10% split equally between skills and L&D and this too has a rating of B given the developments in the skills sector. / 1.3 Direct feedback from beneficiaries / L&D/PIT: In 2011, the PIT team consulted the Provincial Livestock Forum (includes a wide range of L&D related stakeholders) regarding the L&D focus of the PEOP. Subsequently district level consultations took place to solicit the feedback of the potential beneficiaries and local stakeholders for determining the menu of interventions and their design. / During the AR, direct feedback of the beneficiaries was solicited on the 2 activities launched to date i.e. the Farmers Days and the Veterinary Assistant’s Scholarship Scheme. / Farmers Days: The meeting with farmers and the PIT team indicate that the social mobilisation was not properly designed to reach the most vulnerable. The farmers inputs were not solicited for designing the content/identification of issues to be addressed at the Farmers Days. Women were not targeted at all in the respective village but they were obliged to come, owning the call from the land lord. The farmers considered the messages of the Farmers Day very generic and did not seem to add anything new to their knowledge. They were of the view that such programmes are also conducted by other NGOs and private companies. What attracted big numbers to the events was the free vaccination of the animals and the free lunch. A report on Farmers Days by CERP is expected in late August, 2012. / Veterinary Assistant’s Scholarship Scheme: A list of 6 students was provided by the PIT Management. 3 male and 3 female students were telephonically interviewed. The selection of all participants was based on their matriculation marks. The selection process did not take into consideration the socio-economic background of the student (which was never asked for) nor were the students interviewed. Majority of the students are from urban areas and targeting of the students in rural areas has been weak. With the exception of one, all others are from modest middle class background. Most importantly 5 of the 6 students have higher qualification (MBA, BA and FSc.) against the pre-requisite qualification of matriculation. / Observations - Mobile Messaging Service: The economic profile of the farmers is unknown and could not be verified during the field visit. Messages are of mixed quality. For example, they may identify what should not be done (which may be obvious enough to the farmers) but do not always propose a solution. The results of the pilot intervention need to be evaluated to determine its future scope. / PSDF: PSDF enjoys a good reputation in the districts. Local politicians speak well of it in terms of its mandate and the work that it is doing in poor districts. During the review a training session on IT was observed. Given the nature of the training the participants’ background was generally from the urban areas and they were from middle income backgrounds. The participants appreciated the quality of training and rated it of higher quality than the other training available in the market. The Monitoring and Evaluation System of the PSDF also enables the students to provide feedback regarding the quality of the training (teacher’s attendance, provision of training materials, quality of teaching etc) in response to which correcting actions are taken. / Anecdotal stories from meeting with the beneficiaries at the Skills Fair organized by PSDF in December, 2011 also shows high satisfaction level with the quality of training and the popularity of the courses being offered through PSDF in terms of their income earning potential. / Recommendation: / While students speak well of the skills being offered, the test of the quality being offered will be better tested by the employment/income outputs which need to be assessed by the Fund. / A well thought out Outreach Strategy should help identify explicitly who exactly the Fund should target and help determine the profile of the students and assess how inclusive the approach is. Currently, it is the skill providers who select the students based on an aptitude test. The Fund’s targeting strategy is indirect based on the fact that it is functioning in districts where 80% are poor and vulnerable and the fact that vocational skills (usually associated with groups of people that are academically lower-achieving and poorer)are being offered.
1.4 Summary of overall progress / L&D Component: The progress so far is negligible and the stipulated targets very ambitious. The currently well-defined plans of PIT to deliver the revised outputs seem unrealistic in view of the host of other issues that PIT faces in implementing its plans. These issues have been summarized below: / Cumbersome Govt. Procedures: The PIT team is working under the L&DD Department and follows the GoPb rules of business, with the Team Leader (TL) of PIT reporting to the Secretary L&DD Department. The PIT team has been very weak since the beginning of the project including the Team Leader (TL). The position of the TL requires very strong project management skills and experience, whereas the selection criteria set by the GoPb leaned heavily in favour of a PhD in veterinary sciences. Consequently the TL engaged did not have the project management expertise to deliver a Programme of the scale of PEOP. Thus, the work plans produced were inadequate and no activities could be initiated. / Removing and replacing the TL is cumbersome under the GoPb rules and involves a procedure under which a TL can easily challenge the decision of the Department in the courts. Plus, revision of the selection criteria of the TL also involves approval of various sections/departments including the final approval of the Chief Minister. The TL finally left in May 2012 and the revised selection criteria including work management expertise for the TL have reportedly been approved only recently. / As of July, 2012 of the 14 managerial positions 8 are vacant including that of the TL. Overall 40% of the staff positions are unfilled. In mid-2011, when the PIT staff was being hired, one of the rejected candidates challenged his non-selection in the courts. Consequently, all hiring was frozen until the resolution of the case. The case was resolved out of court through the offices of the senior bureaucrats at the L&DD Department. This caused delay in putting the team together and some of the selected staff lost interest in the vacancies. / It is difficult to attract experienced private sector managers to Bahawalpur for government projects (since they have short lives as compared to career jobs and require know-how of government systems in order to work efficiently within the system). Meanwhile, the government staff is unwilling to compete for project jobs due a GoPb notification which bars government staff (even if hired on open competition basis) to get allowances/private sector salaries. Thus, while competent government staff is reluctant to locate to a poor district without added benefits, attracting competent and experienced private sector staff is difficult given that programme positions are for a few years and not the same as permanent jobs. Currently, all four project districts have no livestock development officer. At the farm level, women are heavily engaged in taking care of the livestock, however PIT’s management does not include any women. In the recently advertised positions no women have applied. In comparison women technical staff’s visibility in the private sector in Bahawalpur is high. / Approval Process for L&D Projects: Restrictions by Planning and Development Department prevented PIT to incur more than 10% of the any project’s cost as capital expenditure and more than 5% for the overall program cost. This resulted in impeding some of the initial projects conceived by PIT. Additionally, although the PEOP PC-I was approved by CDWP and ECNEC and the PC-I empowered the Steering Committee to provide approvals of any sub-projects, the issue became a serious bottleneck for the project. Steering Committee constituted Livestock Development Committee and delegated its power to this committee to approve livestock component’s work plans. However, P&D later raised this issue that LDC is not empowered to grant financial approval of projects and these projects have to be routed through traditional approval channels of the government, such as DDSC and PDWP. This defeated the very purpose of having a well-designed program in place and resulted in severe delays in approvals, as each project has to go through multiple approval layers, such as LDC, DDSC, etc. This actually made this process more lengthy as compared to other development project. / Taking cognizance of the staff issues at PIT, and the weak and stretched capacity of the L&DD Department in September 2011, 2 full time TA positions were assigned to PIT in order to bridge the work planning and management gap and ensure sound procurement of services. These positions were: Project Development and Design Specialist and Procurement Specialist. With the engagement of the consultants a work plan was produced and a menu of activities was shortlisted. / High Dependence on TA: While work planning and implementation progress to date can be attributed largely to the impetus provided by the TA, this implementation arrangement is precarious as it involves heavy involvement of consultants, negligible ownership of the L&DDD Programme beyond Secretary’s level and a weak PIT management. This in turn raises serious issues about delivering the Programme, particularly given its complexity and scale and most importantly raises the question regarding the sustainability of the activities beyond the Programme’s life and the long term impact of the Programme on the sector and the L&DD Department. / L&D not an Area of Competitive Advantage for DFID: In addition, DFID does not enjoy any competitive advantage in the livestock and dairy sector. DFID is increasing its development investments in Pakistan and priorities focus on education, health, governance, and wealth creation (microfinance and skills) and to help build on the successes achieved through programmes in these areas. Moreover, the focus is on working through the private sector and effective PPP modalities that offer good value for money for UK tax payers’ money. Given the performance of the L&D component and DFID’s interest in consolidating and building on its strengths, continuation of the L&D programme seems unjustifiable, particularly since an alternative option for investment for DFID in Punjab i.e. supporting the scale up of PSDF exists. / L&D related Skills Through PSDF: Moreover, the PSDF is keen to sponsor short term training in the agriculture sector (including livestock and dairy) given the dominance of this sector in the pilot districts and the number of people involved in it. As a first step in this direction, the PSDF organized a workshop in May, 2012 to help understand the skills related demand and supply side gaps in the agriculture sector and determine how best it should intervene. PSDF represents a cost effective and efficient platform through which skills related interventions in the L&D sector can be introduced. / PSDF: The overall progress of the PSDF is noteworthy both at the institutional level and in terms of the outputs that it has delivered. Its scale up across Punjab is endorsed by the GoPb and its Board, and there are indications of other investors interest (WB and Citi Foundation). The Board is of the opinion that going forward, the aim of the Fund should be to contribute to inclusive economic development and not poverty reduction per se. For targeting the poor (especially the poorest), social safety net type interventions are more suitable due to high uptake rates. Besides if the poor are to take full advantage of the vocational skills on offer, they also need access to ‘core skills’ (i.e. functional literacy, numeracy, communications, planning etc). Designing and/or identifying programmes intertwining vocational and core skills is a challenge that the Fund is grappling with.
1.5 Key challenges / PSDF: / Retaining autonomy of the Board, so that the interest and engagement of the private sector in PSDF is maintained and it is able to attract experienced and relevant private sector representatives. / Ensuring non-interference in the management of PSDF. / Redefining the role of the PSC as PEOP evolves from a dual sector regional Programme to a skills focused provincial initiative. / L&DD: / Attracting competent and committed staff has been a major issue. After almost 2 years, PIT remains understaffed. The TL and one of the Deputy Team Leaders has resigned in the last few months. / Related to the above constraint is the weak capacity within PIT to design and articulate demand driven interventions and a resultant heavy reliance on consultants. / Lengthy procedures for approval of sub-projects has been a major issue which in turn has diluted the interest of the Livestock Development Committee which was expected to bring in private sector expertise to the L&D component, approve the team’s work plans and provide it with strategic direction. / Recommendations: / In addition to recommendations proposed under assessment of Output 1, proactive lobbying at the higher political levels by HMG is essential. / A possible role for the PSC can be to serve as the umbrella forum for providing strategic guidance and support for formation of conducive policies and regulations in the skills sector and coordinating public and donor funds coming to the sector. / Given the high opportunity and transaction costs of facilitating and following up the L&D component it is advised that DFID withdraw its potential investments from this sector and direct it towards the scale up of PSDF which has a more robust implementation mechanism.
1.6 Annual Outcome Assessment / There are 6 outcome indicators of which 3 (i.e. per capita consumption at the household and individual level, index of well-being and index of state engagement pertain to PSDF). The remaining 3 indicators i.e. number of marginalized women owning atleast 1 ruminant, percentage of farmers accessing veterinary and extension services, and increase in milk yields related to the L&D component. / The CERP baseline surveys, tracker and mid-term and final evaluations of the Programme planned in 12/13 and then at the end of the programme in 2015 will help ascertain the accomplishment of the Programme at the outcome level. / While it is recommended that DFID pull out of the livestock sector, the performance of the PSDF in helping to achieve the outcome rests squarely on the income earning potential of its students. Tracker studies planned by CERP will help ascertain the progress being made in this regard.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / Status of PSDF: / The programme has spent 70% of the budget forecast (June, 2011 to July 2012). The utilisation rates of Programme Costs and Operational Costs have been 69.5% and 81%, respectively. Main reasons for under-spend are: / Only 13, out of the 31 selected training service providers under SFE applied for mobilisation advance which was admissible for upto 10% of the contract amount. / Public providers (TEVTA and PVTC) have preferred an end-of-training payment rather than monthly payment, to avoid preparation of monthly claims. This is due to their better liquidity situation vis-a-vis private providers. / The Board decided to launch a pilot programme in six model villages of Muzaffargarh. The first pilot programme was approved in April, 2011 along with the organisation’s staffing, constitution of committee and the annual budget. This was followed by the large scale launch of Skills for Employability. Contracts for SFE were approved by the Board in November, 2012. / July 2011 to June, 2012 / Budgeted (in million Rs) Actual (in million Rs) Utilisation Rate / Programme Costs 468.6 325.03 69.4% / Operating Costs 36.16 29.29 81% / Capital Costs 4.88 3.61 73.7% / Total 509.6 357.9 70.2% / 2.2 Key cost drivers / Training capacity within the four districts remains an issue. However, since training providers outside the target districts have responded well to PSDF’s call for proposals, the costs of accommodation and stipend have been important drivers of cost. After location, duration of training and the type of trade have had significant impact on per trainee costs. Under Skills for Employability, the range of per trainee cost (normalised to a month) had considerable variation. The minimum cost was Rs 1,435 (for carpet weaving) and Rs 31,000 (for village milk collection agent). It is expected that with the segregation of formal certified trades and informal, locally delivered training courses, the range of per trainee costs within each category will narrow down. / However, there will still remain certain trades for which due to high cost of consumables, the per trainee cost is high and is expected to remain so. Overall the fully loaded costs for certified trades are estimated to be around Rs.50,000 per trade while that for the informal trades is expected to be Rs.20,000. / The management and the Board have been cognizant of this. While setting price negotiation guidelines for single bids under the Skills for Jobs Scheme, the Board allowed deviation for heavy machinery operator courses from the overall price ceiling (of Rs 8,700 for nationally certified trades and Rs 9100 for internationally certified trades). / At this stage of operations, it is clear the cost structures are quite different than the one envisaged in the programme document. (The programme was costed at £100 per trainee for an entire course). In view of this the Board has revised the target number of trainings to be delivered through PSDF from 250,000 to 80,000. / In future, it is expected that competition may drive down the per trainee costs for some trades. For others where competition is limited, higher than average prices will still be driven by high cost of consumables. The effect of monopoly power will be limited due to the fact that single bidder of high costs trades are mostly public entities. / Status of L&D Component: / The financial forecasts are quite ambitious, in the face of the issues of staff adequacy and competencies being faced by the team, and the procedures required for interventions approval. To date under £100,000 has been spent on programmatic activities (with impetus coming from the consultants rather than the team). At this pace it seems unrealistic to expect the team to spend its financial forecast for 12/13 of about £1.7 million. / 2.3 Is the project on-track against original timescale: No / The logical framework document has been revised in the light of findings of the baseline survey, the emerging costs structures in the inception phase and delay in project start up. Extension of the Programme until June, 2015 is recommended to enable the Fund to deliver the revised targets. / The PSDF Board has rationalised PSDF’s targets in view of the above factors. Against the revised logframe indicators, the following milestones have been achieved: / Punjab Skills Development Fund has been established and its first generation product has been tested. / Against the target of 10,000 trainees, a little over 10,000 have completed training. / 77% of the training places have been created in the private sector against a target of 50%. / Against the revised targets, the achievement rate is from 100% to over 100%.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Farmers Day has been a 2-day exercise (one day for awareness raising and the second day for vaccination of animals). Given the feedback received from beneficiaries about the quality of the events, the fact that these are not going to be repeated and that DFID intends to pull out of the L&D sector, it deems appropriate to drop the idea of conducting their RCT evaluation. / In the case of PSDF if the low uptake of the vouchers persists, CERP will need to design an alternative RCT evaluation of the programme based on over subscription of the skills schemes being offered by PSDF. / Lessons Learned: / Programmes/Projects should be housed within the government only if there is practical evidence of wide government ownership of strengthening a given provincial department, and engaging with a project/programme for building its own long term expertise. Otherwise, projects/programmes are better placed with competitively engaged private sector parties. Government of Punjab has developed and implemented several area development projects in the past with the help of Asian Development Bank, World Bank and UNDP. The ones which relate to PEOP include Barani Area Development Project (ABAD), Bahawalpur Rural Development Project, DG Khan Development Programme and Devolution Support Programme. A key lesson from these programmes is their slow implementation through failure to get broad government ownership including political level. / In programmes involving partnership with the government, it is important to have well thought out roles and responsibilities of the government departments, which they need to comply with. For example policies for ensuring competent staff can be engaged for the programme and continuity of the government staff during the life of the programme. Though the government is a partner in the PEOP it’s notification which bars government staff (even if hired on competition basis) to draw allowances and private sector salaries, is a big obstacle for attracting competent government staff to projects in poorer districts. Between October, 2010 to present the L&DD has had 3 Secretaries and the Additional Secretary has also been changed. Though there has been high commitment at the senior bureaucratic level, frequent shifting of senior staff can cause unnecessary breaks and time is lost in bringing new staff up to speed on programme issues and progress. / Undertaking development interventions in remote areas is challenging in itself and therefore requires high quality committed implementation teams. Both components of PEOP have encountered serious human resource hiring and retention issues. A revised incentive based policy by the GoPb is required to attract required development expertise to/for the underdeveloped regions and safeguard future DFID investments. / Programmes/Projects need to be designed with a clear vision of the legacy they intend to leave and how they aim to change the market/sector that they are working in. The two components of the PEOP present a striking example in this regard. Where PSDF is targeting a fundamental flaw in the skills market through an innovative public-private business model, the L&D component has adopted a more traditional route of working through a government department and under its rules for implementing a set of activities in the L&D sector. / Forecasting of implementing partners needs to be cross verified and checked based on the capacity of the partner to deliver, or else money can sit useless in a bank account. / Research agenda in a sector/area where beneficiary behavior is little known, should be allowed to have flexibility so that research findings from one tier of research can influence and shape the design of the subsequent planned research. / Not being allowed to sit on the Board of a company co-funded by DFID, limits DFID’s capacity to gain first hand understanding of the Board’s dynamics, finer nuances of issues and potential risks. Acquiring accurate understanding through Board minutes, and talking with partners involved is not a substitute for in person attendance of Board meetings. / The high level of private sector providers interest in PSDF and evidence of cost efficient delivery through them, endorses the need to assess how a more private sector orientation in TEVTA institutes can be introduced since it is the single largest recipient of public sector funds and provider of vocational and technical supplier in the province with over 400 institutions. / 3.2 Where an evaluation is planned what progress has been made? / Under an Accountable Grant Agreement, DFID commissioned an evaluation of both the skills and livestock components to be done by the Centre for Economic research Pakistan (CERP) in collaboration with the International Growth Centre, London. The aim of the evaluation is to measure the impact of the programme (see indicators against Impact) and the outcome of the Programme against the indicators defined for the skills and the livestock and dairy component. / Skills Component: Evaluation of the Skills Component: / The aim of the CERP evaluation is to measure the impact of PSDF’s interventions on household consumption (proxy for income), engagement and trust vis-a-vis the state and individual well-being. This will consist of mid-term and end-of-project evaluations based on randomised controlled trials (RCT). / A pilot RCT was rolled out to evaluate PSDF’s first product, Skills for Employability (SFE). Baseline and tracker survey instruments were prepared. A voucher was designed and delivered following an “encouragement design.” First stage findings exploring the uptake of the CERP voucher report a low uptake. A report will be shared by CERP in August, 2012. / As both CERP, DFID and PSDF agree on the need for scientifically rigorous evaluation, the following course of action will be adopted: / An RCT based on encouragement design for the two new products of PSDF (Skills for Job- SFJ and Skills for Market- SFM) will be rolled out following approval of the revised proposal of the AG. This round will attempt to provide an early evaluation of voucher uptake and medium term impact of the PSDF programme. / RCT variations shall be designed around the product SFM with a view to improve uptake amongst the target population. / An alternative strategy based on “over-subscription design” has been discussed in case of persistence of low voucher uptake in the target population which does not provide a treatment group large enough for statistically significant results. The decision to proceed with the alternative evaluation will be taken after analyzing the initial results from the incidence of uptake in the mid-year RCT roll out (encouragement design). / L&D Component: / The aim of the evaluation is to measure the percentage of farmers accessing veterinary and extension services, the number of socially and/or economically marginalized women owning atleast 1 small ruminant for livestock farming and percentage change in average milk yield amongst beneficiary livestock farmers. / A summary of the RCT evaluations planned so far with progress is as follows: / ACTIVITY DELIVERABLE PROGRESS / Sampling of Villages- Identification of sample villages for Livestock Interventions-Farmer Days Quarter III of 2011-12 Completed in Quarter III of 2011-12 / Design and finalization of Baseline evaluation instrument- Livestock ownership profile forms/feedback/registration forms Quarter III of 2011-12 Completed in Quarter III of 2011-12 / Design and finalization of the evaluation protocols related to logistical roll-out of the intervention Quarter III of 2011-12 Completed in Quarter III of 2011-12 / Roll-out of Farmers Day and collaboration with PIT/L&DDD in implementation of RCT protocols (farmer registration and data/feedback gathering) Quarter IV of 2011-12 Completed in Quarter IV of 2011-12 / Initiation of initial assessment the intervention based on preliminary data and findings Quarter I of 2012-13 Additional Activity which will be delivered by the 2nd Week of August 2012 / Tracker Surveys of the CERP- PEOP Households which participated in the Farmer Days in the treatment villages (New activity) Quarter II of 2012-13 Planned for October 2012, contingent on the availability of funds for the RCT Phase. / Finalization of the Intervention Evaluation Report based on the Tracker Surveys, Baseline Household Survey and data collected at the Farmer Days Quarter II/III of 2012-13 To begin as per timeline, contingent on the item above.

4. Risk
4.1 Output Risk Rating: Medium / The L&D component has high risks given the challenges involved in implementing it. The outputs related to PSDF have medium risk as does the output associated with CERP. / 4.2 Assessment of the risk level / A major risk for the PSDF remains the dilution of interest of the private sector Board members due to interference in the Fund’s business. Political risks associated with change in government and weakening of government’s interest in the Fund, or the Fund’s high jacking by political interest groups is low. Political parties likely to emerge strong in Punjab post the elections have high buy-in of the Fund and support its mandate.
Risk of funds not being used as intended / The risk is minimized at PSDF through the appointment of an independent audit firm that has been appointed by the Finance Committee of the Board following a competitive process. Secondly, payments require signatures of two signatories which include the CFO and the CEO. Thirdly the financial management systems at PSDF are strong. Budgets are approved by the Board after scrutiny of the Finance Committee. / Payments to skill providers are contingent upon satisfactory reports of a very robust third party M&E system. In some cases payments have been withheld an in 1 case a contract was cancelled due to non-compliance. 250 students were expelled who had enrolled in more than 1 course in lure of the stipend. / While in year July 2010 to June 2011 PIT did not incur any expenses, during the current year the limited programme activities that did take place, followed procurement of services following the PPRA rules. The procurement procedures were further quality controlled by the Procurement Specialist engaged under the TA by DFID for the L&D component. The Auditor General’s office has been requested by P&DD to conduct the audit of the PIT the report of which is expected sometime in the last quarter of this year. / Climate and Environment Risk / There is no significant environment risk associated with the PEOP that came up during the annual review. Climatic changes such as potential floods can have bearing on the livestock assets of the households and impede training taking place in the districts in future.

5. Value for Money
5.1 Performance on VfM measures / PSDF: A complete Value for Money analysis cannot be conducted due to insufficient data on returns to skills. However, the following supports VfM considerations: / Government of the Punjab has honoured its commitment to co-finance PSDF to the extent of 50%. More than 50% of the total releases to PSDF have been out of Government of the Punjab funds. / Level of stipend being offered under PSDF has been almost half of that being offered in comparable programmes of skills development being implemented elsewhere in Pakistan. The decision has been based on the CERP finding in the baseline survey. / The recently launched new phase of a World Bank Programme (Benazir Bhutto Shaheed Youth Development Programme) in Sindh has been worked out at a per trainee cost of Rs 38,000 excluding management costs. The average per trainee cost of contracted trainings under SFE is Rs 28, 723/ i.e . 24% lower than the Sindh programme. / A tracer study of the pilot trainees and more importantly that of the SFE graduates will be the first systematic result of strictly financial benefits of PSDF interventions. / VfM in terms of increased state engagement and increased self- confidence of women expected as a result of being skilled in this politically volatile and traditional region will depend on the subjective value assigned to these outcomes. / PIT: The L&D component does not represent good value for money. The transaction cost in trying to expedite implementation of PIT activities is high (PEOP lead adviser, programme manager and 3 consultant’s time) and in comparison implementation and L&DD Department’s ownership is weak. / Focused planning for implementation and implementation of initial activities happened only over the last 10 months, once TA was engaged to provide technical support. To date only Rs 54.13 million has been spent (of which only Rs.13.35 is on programme activities while the remaining Rs.40.78 million is operational expense of PIT) i.e. a total expenditure of 2% against a total resource envelop of Rs.3,422 million. On the management side, there is strong realization that it would be a stretch to expect PIT to hire quality human resources at non-market salaries for working in remote districts of the province and to deliver a programme whose delivery structure is interwoven with the provincial Livestock Department which further slows down the project activities. / L&D Component: Value for Money for Outputs: / Output 4: For Farmer Days intervention, 6,652 farmers were reached for advisory support and vaccination & de-worming, while vaccination services were provided to 54,000 animals. This translates into an estimated average of PKR 433 per farmer (based on 6,000 farmers), covering participation in the advisory/dissemination event and PKR 850 per farmer (6-7 small and large ruminants per farmer) for door-step services for vaccination, deworming of large and small ruminants. / VA Scholarship Scheme: 260 students (30 women) from the 4 pilot districts have been enrolled for a 2 year diploma course at University of Veterinary and Animal Sciences (UVAS) campuses in Punjab at a total cost of Rs. 310,846 per student / 5.2 Commercial Improvement and Value for Money / PSDF has adopted a competitive tendering process for selection of training service providers. A healthy response has been received from TSP’s in the first two large scale EOIs. The number of organisations which responded to SFE and SFJ were 117 and 125, respectively. / With the introduction of trade-based competition, increased competition is expected in TEVTA trades, as result of which per trainee cost is expected to fall. In new, high cost trades, however, the competition will remain thin which is the inevitable cost of innovation. / Fiduciary Risk Assessment which was conducted by DFID last year rated PIT to be high/ substantial risk in terms of adherence to budgetary procedures and processes, expenditure management, and risk mitigating initiatives. To address these concerns PIT adopted government of Punjab budget rules and the standard government classification codes for booking expenditures. Different committees were constituted to ensure transparency and mitigate risks of misappropriation. Two different Procurement Committees were established- one for programmatic activities and the other for operational purchases- Consultant Selection Committee was constituted for consultant selection. Also a scrutiny committee was constituted to review the proposed projects with respect to cost and adherence of the proposed activities with programme objectives. The external audit which is to be carried out by the Auditor General has become due at the end of financial year (June 30, 2012). This will be useful in identifying any aberration from the standard practices and any unauthorised expenditures. / 5.3 Role of project partners / PSDF: should continue to engage new training providers by developing a reputation for transparency and fair play. PSDF views government interest in reform of TEVTA as a welcome step, as partnerships between the private and public sectors could encourage more intensive utilisation of government infrastructure and help address quality issues with government-certified trainings. While there is limited scope for public providers to compete for PSDF funds, sector-building efforts by them (such as training of trainers and development of training products) are crucial for private sector development in the skills sector. / Apart from engaging the consulting firms for service delivery PIT has and can partner with public sector universities having veterinary disciplines. / 5.4 Does the project still represent Value for Money : / PSDF: The PSDF represents good value for money. It is enabling private sector skill providers access to resources for delivering training cost-effectively (see the table on page 6) when compared with public providers or donor programmes. The original cost estimate of £100/person is out-dated as it was made in 2007 under the assumption that largely public sector (which offers heavily subsidized training) will respond to calls for proposals of the Fund. Secondly, by rationalizing the management structure, the Board has reduced the staff strength to 1/3 of what was approved in the PC-1, bringing the operational expenses to 7% of the budget. / Most importantly, the PSDF has introduced competition in skill providers market which is a sharp departure from how funds have been allocated to the skill providers in the past. / TA: The TA is being administered directly by DFID and has responsive to the needs of the implementing partners. Following the decision of the third Steering Committee meeting, a TA committee comprising of relevant stakeholders should be formed so that the decisions on TA proposals coming from the implementing partners are taken expeditiously. The idea of engaging a TA management agency was dropped given the overhead charges of a TAMA and the fact that a major proportion of the PEOP TA has been either booked or earmarked. / L&D Component: The L&D component does not represent good value for money for reasons described above. The individual outputs are cost efficient, nevertheless there are issues of targeting in both the VA scholarship scheme and the Farmers Day. In addition the quality of the Farmers Days has been mixed (vaccination was well received but awareness raising messages were considered too generic). / 5.5 If not, what action will you take? / Recommended Actions: / Given the political buy in for scaling up PSDF, the promising record of the Fund, and the emphasis of DFID on results it is recommended that DFID diverts its funding support to PSDF and withdraw from the L&D sector. This decision has been agreed with the P&DD and needs the endorsement of the Programme Steering Committee for finalization. DFID’s with drawl will not leave a vacuum as IFAD has had a $49.1 million poverty alleviation programme approved for South Punjab under which it will be investing predominantly in the livestock and dairy sector. Besides, the GoPb may want to continue to maintain its commitment to the L&D sector made under PEOP. / With the termination of the L&D component from PEOP, it is suggested that the PSC’s role and composition be revisited. A new role of the PSC as the umbrella forum for providing strategic guidance and facilitative support for rationalizing the skills policy and regulatory environment can be considered. The Skills PSC can also serve as the forum for additional donor investments in the skills sector of Punjab including the potential WB investment. / Following the decision of the 2nd PSC a TA committee of the PSC should be constituted immediately for scrutinizing and approving the TA proposals so that the TA needs can be delivered expeditiously for PSDF.

6. Conditionality
6.1 Update on specific conditions / There are no specific conditions attached to this programme. However, an important underlying principle for the success of PEOP is that the GoPb and DFID remain committed to implementing it and providing timely funds as agreed. / The Programme Document specifies that if during annual reviews of the programme, or at another time, DFID and / or the GoPb judge that the programme is seriously off-track or under threat, the programme (or component parts) may be suspended or terminated in line with DFID’s standard procedures. which will be set out in the Memorandum of Understanding signed between DFID and the Government of Punjab.

7. Conclusions and actions
In light of the performance of the Fund since its incorporation in late, 2010, its scale up is endorsed both by the GoPb and its Board, going forward the overall goal of the Fund i.e. poverty alleviation or inclusive economic development will need to be revisited and the log frame will need to be revised accordingly. (DFID to lead, in the design phase for scaling up the Fund) / Given the challenges associated with the L&D component and an alternative opportunity for investment i.e. scale up of PSDF which enjoys high political buy in it is recommended that DFID diverts its funding support to PSDF and withdraw from the L&D sector. This decision has been agreed with the P&DD and needs the endorsement of the Programme Steering Committee for finalisation for which the fourth meeting of the PSC should be called on a priority basis. DFID’s with drawl will not leave a vacuum as IFAD has had a $49.1 million poverty alleviation programme approved for South Punjab under which it will be investing in the livestock and dairy sector. Besides, the GoPb may want to continue to maintain its commitment to the L&D sector made under PEOP. (DFID to present the case at the PSC, managing the implications of the decision needs to be agreed with the P&DD) / Dates for Steering Committee meetings to be set in advance so they can be used as an impetus to drive action and strategic decision making body. / Implications of DFID’s with drawl from the L&D roll up on the livestock supply side surveys, the Farmers Days, the VA scholarship scheme and the funds committed by GoPb for PEOP need to discussed between the GoPb and DFID. (DFID, L&DDD and P&DD) / The revised log frame (excluding the L&D component) be reviewed again without the L&D component and approved. (DFID) / The time frame of the PEOP needs to be enhanced until June, 2015 (evaluation results to be available by October, 2015) in order to deliver the Programme outputs. (DFID and P&DD) / The Board should replace inactive Board members and the seats left vacant by the departure of two private business sector Board members should be filled by appropriate private business representatives. The private sector strength of the Board may be enhanced further given its scale up plans. Further, Secretary Agriculture may be invited to join the Board given the Fund’s plans to introduce agriculture and livestock and dairy related skills in future. (Board, DFID and P&DD) / PSDF should market itself to receive funding from additional national and international sources. This will serve to improve the sustainability prospects for the Fund and provide resources for complementary activities currently not within the ambit of PEOP but which can help improve market linkages of its trainees. (PSDF, DFID and GoPb). / Locating the head office of the PSDF in Lahore will be helpful in attracting the required expertise to the Fund which are challenging to find in/attract to the districts. Meanwhile, continued TA support (Skills Strategy Adviser) is recommended to fill the capacity gap and to assist in the future scale up plans. Additionally, in order to leadership gaps a succession plan should be developed to groom and develop the next tier of managers.(PSDF) / PSDF should strengthen its MIS to enable gender-based reporting and reporting that meets DFID’s quarterly operational reporting requirement. (PSDF) / The log frame needs to capture the quality aspect of the training, beyond the number of people who have been trained. Inclusion of indicators reflecting the income earning impact of the training, and/or % of people who have received certified training etc needs to be considered.(PSDF) / A tracer study may be conducted to ascertain the employability of recent graduates of the Skills for Employability at suitable intervals e.g. at three months, six months and one year.(DFID, CERP, PSDF) / Proactive lobbying with the WB and P&DD is required to ensure that the skills policy agenda is seen through.(DFID and PSDF) / Going forward the Fund should develop and articulate its outreach strategy explicitly to ensure an inclusive programme and its performance should capture outputs related to employability and quality of training. DFID should ensure that the outreach plan explores linkages with the education programme of DFID in Punjab. (PSDF and DFID) / BISP has launched its training component and offering stipends as high as PKR 6,000 per head which is much higher than what PSDF is offering (Rs.1,000 for within district and Rs.3,000/month for those training outside districts). Since BISP is a national programme, the risk of a person taking advantage of both BISP and PSDF training needs to be mitigated by sharing information and ensuring maximum people can take advantage of the public funds without distorting the market. Both DFID and the PSDF Board need to pursue the matter with BISP. (Board and the DFID) / Given the changes in the research agenda of the AG agreement of CERP with DFID and the delays in the surveys, the revised proposal for a cost and time extension needs to be provided by CERP at its earliest. (CERP and DFID) / The proposal should also include ‘over subscription design[10]’ RCT evaluation of the Programme as an alternative should uptake of the vouchers among the general public remain an issue. (CERP) / Employers’ survey should be managed on priority basis so that PSDF has a demand side perspective which can be incorporated in the design of the skill schemes. (CERP, DFID, PSDF) / Farmers Day has been a 2-day exercise (one day for awareness raising and the second day for vaccination of animals). Given the feedback received from beneficiaries about the quality of the events, the fact that these are not going to be repeated and that DFID intends to pull out of the L&D sector, it deems appropriate to drop the idea of conducting their RCT evaluation. (DFID, CERP and L&DDD). / There is a need to redefine the role of the PSC as PEOP evolves from a dual sector regional Programme to a skills focused provincial initiative. The role of the PSC as the umbrella forum for rationalizing skills policy and regulatory issues should be considered. (PSC and P&DD) / Both components of PEOP have encountered serious human resource hiring and retention issues. A revised incentive based policy by the GoPb is required to attract required development expertise to/for the underdeveloped regions and safeguard future DFID investments. (GoPb) / Following the decision of the 2nd PSC a TA committee drawing on the members of the PSC should be constituted immediately for scrutinizing and approving the TA proposals so that the TA needs can be delivered expeditiously. (PSC) / Currently there are three conflicting sets of financial projections: i) DFID internal disbursement estimates; ii) P&D annual allocation for PEOP; iii) PSDF and Livestock component disbursement figures; and iv) PC-I planning figures. The Planning and Coordination Unit will be well advised to align (ii) and (iii), reflect adjusted figures in revised PC-I and then DFID may also project its disbursements based on overall revised figures, commitment to contribute to 50% of project costs and what it has already released to the project. (P&DD) / PC-I needs to be revised to accommodate: i) cost (for PSDF) and time extensions; ii) Exclusion of L&D from PEOP; and iii) reflect lean structure of PSDF and iv) Revised role and ToR for the PSC. (P&DD) / P&DD to provide monthly financial statements and updates on forecasts, while DFID team to actively monitor and interpret. (P&DD) / P&DD to establish standard ways of working with PIT and PSDF and hold regular operational meetings that include DFID. (P&DD) / P&DD to provide details required for EoL amendment as early as possible. (P&DD) / Audit reports are required for FYs’ 2010/11 and 2011/12. P&DD to provide DFID with a letter confirming the date that the audit will take place. DFID requires Annual Audited Statements from the Auditor General’s office and/or other certified auditors confirming that its funds have been used for the intended purpose. DFID’s internal compliance requires bank statements until the annual audit for 2010/11 for L&D component is conducted (being conducted along with the audit for 2011/12, in order to conform the assertion that no spend was undertaken in 2011/12. (P&DD). / Management recommendations: / Strengthen overall programme management, with a particular focus on financial management. Consider the use of disbursement linked indicators for any future release of funds. / Establish regular operational management meetings/phone calls to cover financial management and other issues. / Spend more time in districts where programme is being implemented and interacting with beneficiaries. / DFID team, PIT and PSDF to draft individual lessons learned document from the last year.
[10] Meant to measure the difference that skills bring about between those student who do acquire training vis-à-vis those who get selected but are unable to attend due to limited seats.

8. Review Process
The review was conducted by the GoPb and DFID collectively and independent third party perspective was provided by Azhar Rauf, PSDF Adviser based in London. The review took place over July 16-18, 2012 and the team comprised the following: / DFID: Fatimah Afzal, Lead Adviser for PEOP; Louisa Brewin, Programme Manager; Azhar Rauf, PSD Adviser, London (for third party perspective) Ali Naqvi, Social Development Adviser; Raza Khan, Results Adviser; Waqas ul Hasan, PSD Adviser (for inputs on the L&D institutional arrangement); Shumaila Rafaqat, Governance Adviser; Nyda Mukhtar (contributing to the economic appraisal for the PSDF scale up). / GoPb: Dr. Arif Raza, Assistant Regional Planning, P&DD as representative of the GoPb. / Meetings were held with the Secretary P&DD, Senior Chief Regional Planning P&DD, senior management of the PSDF, Skills Strategy Adviser, the PIT team, 3 PIT consultants, Board members (Chairman Dr.Ejaz Nabi and Almas Haider) and Saaud Majeed (member Steering Committee) and the CERP team took place in Lahore and Islamabad. To the extent possible information was triangulated to ensure its validity. / Meanwhile visits were also made to Multan and Bahawalpur in order to obtain the feedback of local stakeholders and beneficiaries. Ali Naqvi, Social Development Adviser visited Bahawalpur and met with the implementers of both components of PEOP (PIT and PSDF). The field visits were in conjunction with Farmer Days (PIT) and observing the IT training (PSDF). Scholarship grantees for the Veterinary Assistant’s Scholarship Scheme (Six, 3 men and 3 women) were telephonically interviewed. / The main objective of the review was to ascertain progress over the last 1 year of the Programme, collectively gain a sense of the challenges and risks, determine the mitigation measures, assess viability of the L&D component and the institutional arrangement for its delivery, agree on financial reporting, coordination measures, and documentary requirements with the P&DD. / For the detailed schedule and ToR of the review please see Annex C and D.