Annual Review

Project Title: Support to the UK International Emergency Trauma Register (202878)

Date started:	October 2011	Date review undertaken: October 2012

What support is the UK providing?
The UK is providing £655,000 over three years (2011-2014) to support the establishment and maintenance of the UK International Emergency Trauma Register (UKIETR), covering running costs, insurance and training costs of register members. The UKIETR is managed by UKMED. / If a UKIETR medical / surgical team is deployed by DFID during an emergency response, specific funding will be approved at the time.

What are the expected results?
Three main results have been identified: / The number of trained medical and surgical personnel registered by UKIETR for deployment in humanitarian emergencies will increase to 400 people by the end of the project, ensuring that the UK (including NGOs) has the capacity to rapidly deploy high quality surgical teams in disaster situations after ﻿earthquakes and other sudden onset emergencies; / By deploying NHS medical and surgical expertise, UK resources will be focused on niche areas where the UK can add value to an emergency response, and which provides value for money in terms of numbers of lives saved and people receiving assistance; / The UK will provide international leadership during humanitarian emergencies through the deployment of appropriate medical/surgical teams.

What is the context in which UK support is provided?
The UK supports a range of interventions in humanitarian response, including search and rescue, provision of surgical teams, and use of specialist equipment and supplies. The Humanitarian Emergency Response Review (HERR) 2011 recognised that whilst all these interventions have value in saving lives and reducing suffering some can help greater numbers of people than others. For example, the HERR noted that in terms of lives saved the cost of search and rescue operations was over £250,000 per life saved, compared to around £2,500 per life saved for surgical teams. The HERR recommended that the UK should “incorporate surgical teams into first phase deployments especially after earthquakes” with the aim of enabling direct despatch of British surgical teams to save life and limb. / In response to the Haiti earthquake – where an estimated 300,000 people required treatment, the UK deployed a team of highly qualified surgeons to work on complicated trauma wounds. The UK medical facility was in Haiti for 14 weeks and treated an average 200 patients a day. From these were drawn a smaller number requiring major surgery with 623 operations carried out. Evidence from Haiti demonstrated that UK surgical teams can save lives and limbs if appropriately trained staff are deployed quickly. UK teams were also deployed in North Africa in 2011. / The UK surgical team which responded to the Haiti earthquake although extremely effective was rather ad hoc in terms of its composition and how it deployed. By formalising the structure and training of the teams through the UKIETR and supporting the way they deploy, the UK can not only save lives and limbs but also lead by example in terms of the quality of the surgical response provided, and provide better value for money.. The World Health Organisation (WHO) has recently convened a Foreign Medical Teams Working Group, which is chaired by the director of UKMED, which will offer an opportunity for the UK to take the lead in establishing future best practice for global surgical interventions in a post-disaster setting. / UK support will help to address the problems often arising during these emergencies, when an influx of foreign medical/surgical teams of variable quality surge into an affected country, overwhelming local coordination structures, not following international/ host country guidelines and standards, and with a lack of accountability to the host country. In the immediate aftermath of a disaster, neither governments nor international coordination systems may have the opportunity and ability to check and validate the skills, practices and experience of foreign teams.

## Section A: Detailed Output Scoring
Output 1: A cadre of trained UK medical /surgical staff
Output 1 score and performance description: A
Progress against expected results: / The number of medical and surgical personnel registered for deployment rose form 230 people on 1 October 2011 to 342 people by end September 2012. This is slightly under the milestone target of 350 people by this stage, mainly due to people moving around, but does not affect deployment capability. The project remains on track to have 400 people on the Register by September 2013. / A fresh recruitment drive will be organised in early 2013 to coincide with publicity around the next surgical course. / Recommendations: / The Output remains on track – there are no recommendations. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: UK medical / surgical staff ready for deployment
Output 2 score and performance description: A
Progress against expected results: / Progress is running in line with Year 1 milestone targets: / Working in hostile environments: A pre-deployment course, including working in hostile environments, was developed earlier this year, with the first course for 20 people taking place in July 2012. Following feedback, course content has been reviewed and the hostile environment element of the course will be strengthened in future rollouts. Further courses are planned for November and December 2012. Course spaces have been deliberately allocated across the range of specialities, which will mean that 60 people (equivalent to 5 deployable teams, plus back-up) will have received hostile environment training by the end of 2012. / Specialised surgical training: UKMED have established a partnership with the Royal College of Surgeons of England to run a specialist training programme for surgery for disasters during January/February 2013. There will be 20 participants on the course. / To further support deployment readiness, UKMED have arranged a comprehensive insurance policy for all team members, and purchased essential equipment to support response deployments. / Recommendations: / The Output remains on track – there are no recommendations. / Impact Weighting (%): 50 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: A / 1.3 Direct feedback from beneficiaries / The UKIETR team has not been deployed by DFID in any humanitarian response during the past year – therefore feedback from beneficiaries is not available.
Summary of overall progress / Project outputs are broadly on track to be achieved by project end: / The Register of deployable medical and surgical personnel available in an emergency has been strengthened; / Appropriate training courses have been arranged to ensure the readiness of medical and surgical personnel in an emergency response. / DFID has not deployed any personnel from the UKIETR during the past year. NGOs have used the UKIETR to deploy members to North Africa and the Middle East in 2011-12: / Two members deployed for Merlin and one for IMC in Libya/Tunisia, up to 4 weeks each; / One member deployed for MSF in Syria for 4 weeks.
Key challenges / The key challenge is to ensure that the UK can deploy surgical trauma teams effectively in whatever conditions may be encountered. DFID is developing a logistical platform to deploy medical / surgical teams under a range of different scenarios, including deploying a fully equipped stand-alone surgical facility in worst case situations, where local health structures have been destroyed or do not exist. DFID is working with partners to establish this facility by the end of 2012 (this is outside the work budgeted for under the project Business Case). / An ongoing challenge is to maintain the vital support of the Department of Health and NHS Trusts in enabling staff to make themselves available for the deployment. Resource restraints following the Comprehensive Spending Review could impact on the level of support available, although there is no evidence for this at present.
1.6 Annual Outcome Assessment / Output progress is on track to achieve the project outcome, which is: “UK able to provide an effective and accountable rapid surgical response during humanitarian emergencies.” / The number of UKIETR medical/surgical personnel available has been increased to ensure that up to five deployable teams, plus back-up, are available for deployment, and that all have received appropriate specialist and hostile working environment training. / The UK, through DFID, has not deployed any UKIETR teams to sudden onset emergencies during 2012. UKIETR members were deployed by NGOs to provide assistance in Libya, Tunisia and Syria in 2011-12. / Although not tested, tools have been developed to assess the humanitarian value for money for this project. These will capture lives saved, disability averted, plus cost, quality and speed of response.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / The main cost drivers are for: / Arranging the training courses for specialist surgical personnel, and the general safety and security courses for all personnel; / Ensuring medical malpractice and indemnity insurance is in place for all deployable personnel; / Provision of essential surgical equipment for team deployment. / Personnel costs to the project will be minimised as all members of the register are NHS volunteers. They require no additional salary payments during training or when deployed. DFID will meet travel and subsistence costs, which will be agreed in advance of deployment. / UKIETR administration costs will be minimised as the office and phone lines are provided without charge by the University Hospital of South Manchester. Computer and software development were similarly purchased privately. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / 26. There have been no changes in the evidence base for this project. / 3.2 Where an evaluation is planned what progress has been made? / 27. The project will be monitored and evaluated through routine DFID reporting processes.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The risk assessment included in the Business Case remains accurate and no amendments are proposed. / Key risks remain: / Medical / surgical teams are not required: Given the deployment of medical surgical teams in Haiti and the demand so far from NGOs for UKIETR services the probability that these services will not be required in the future is low. / Medical / surgical staff not appropriately trained or resourced for deployment: This could have a high impact but the likelihood of this occurring is judged low. Results from Year 1 of the project show significant progress has been made to ensure that there are sufficient numbers of trained staff permanently available on a rota basis for deployment, with adequate access to surgical kits and other resources. / Medical / surgical staff not available for deployment: Pre-agreements are in place with NHS Trusts to cooperate and release staff on the Register if they are required to deploy during an emergency response. However, the arrangements are untested so are judged a medium risk. / UKIETR proves to be unsustainable long term: The funding model relies on the NHS to cover salary costs and release staff – pressures on NHS resources could affect their ability to meet these costs and alternative funding arrangements would then be required. This would have a high impact on the UK ability to respond to humanitarian emergency situations. / Deployment support is not in place: DFID is developing full deployment support platform for the medical teams to give them full self-sufficiency and enable them to be deployed in a disaster zone of total devastation. The medical team already has the capability to deploy and function effectively where medical facilities and infrastructure have survived the disaster.
Risk of funds not being used as intended / The risk of funds not being used as intended is low. Within DFID, the CHASE Humanitarian Response Group will manage expenditure. Audit, accounting and reporting / monitoring arrangements have been clearly specified in the Accountable Grant. Final reports are requested within three months of the project completion. DFID requires partners to provide a copy of their certified Annual Audited Accounts (AAA) and that they clearly show DFID funding as a distinct line of income. / 4.4 Climate and Environment Risk / The climate and environment risks and opportunities remain low. As described in the Business Case, there will be appropriate procedures in place to ensure that the very small, localised risk of contamination from medical waste during deployments can be managed. During deployments, there may be limited opportunities to spread good sanitation practice slightly more widely beyond the immediate area of operation.

5. Value for Money
5.1 Performance on VfM measures / During the course of the project UKMED will develop measures to report to DFID in terms of value for money: cost, quality and speed, including measures on how fast the UKIETR members were able to deploy, how many lives they saved and estimates of how many disability-adjusted-life-years (DALYs) they averted. There are, on the DFID humanitarian network, many tools for assessing the impact of humanitarian medical interventions which can be used in assessments. As no full UKIETR surgical / medical teams have been deployed for emergency responses during the first year of the project performance on value for money measures has yet to be assessed. / It is expected that the UKIETR project will provide good value for money for the UK to rapidly deploy specialist NHS medical/surgical resources, supported by a surgical deployment platform if required. This will directly benefit those stricken by sudden onset disasters overseas. It will enable DFID to better focus its resources on those in need during major disasters. / The major benefit will be the numbers of patients provided with life-saving or limb saving surgery. This latter category provides an opportunity to save individual patients (and the state apparatus which is responsible for them) the costs of life-long disability related care. Figures for annual care costs by type of disability are available in some countries and this could provide quite accurate measures of value for money for this type of intervention. / 5.2 Commercial Improvement and Value for Money / To enable UKIETR personnel to deploy safely and effectively, the project will develop specialist surgical skills training and awareness courses on safety and security in hostile environments. To achieve better value for money there is scope for these training programmes to become self-funding. It is anticipated that the specialist surgical training will be taken over by the Royal Colleges who will offer it as one of their professional development courses. The more general pre-deployment training is already attracting interest from NGOs who wish to provide hostile environment training with a medical aspect to their deployable medical and health staff. The increased revenue generated by charging these organisations for their participation will allow NHS UKIETR members to be trained free of charge or at a significantly reduced cost. / 5.3 Role of project partners / The UKIETR has the full support of the Department of Health International Health Advisory Board and is represented on the NHS International Health Group and NHS Staff Volunteering Group. The UKIETR will ensure a fair distribution of volunteers across the NHS and assurance that only those with appropriate skills are deployed. The agreement is that those on the register can be seconded for deployment at 24 to 48 hours notice for an initial 2 to 3 weeks deployment. Their salary will be paid while they are away and colleagues will cover their duties. A letter of support from the Department of Health has gone to all NHS Trusts. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions : Not applicable.

7. Conclusions and actions
The UKIETR project is on track to achieve both its outcome and outputs by target end dates. During Year 1: / The Register of deployable medical and surgical personnel available in an emergency has been strengthened; / Appropriate training courses have been arranged to ensure the readiness and safety of medical and surgical personnel deployed in an emergency response. / Whilst DFID has not deployed any personnel from the UKIETR during the past year, the Register has been used by several NGOs to deploy UKIETR members to North Africa and the Middle East in 2011-12. / There are no specific actions or recommendations regarding project outcome and outputs. A key challenge for DFID is to ensure that the UK can deploy surgical trauma teams effectively in whatever conditions that may be encountered. DFID is developing a logistical platform to deploy medical / surgical teams under a range of different scenarios. This includes the capability to deploy a fully equipped stand-alone surgical facility in worst case situations, where local health structures have been destroyed or do not exist. DFID is working with partners to establish this facility by the end of 2012.

8. Review Process
DFID desk review based on annual reporting received from UKMED.