Type of Review: Annual Review
Project Title: Education Programme Burma
Date started:	October 2011	Date review undertaken: 1 October 2012
Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
DFID is providing £10.5 million over four years to increase the number and proportion of children in Burma accessing and completing a quality basic education. The programme will run from October 2011 to December 2015 and consists of 4 components: / UNICEF: Quality Basic Education Programme (QBEP): This is financed by the Multi-Donor Education Fund (MDEF) supported by AusAID, DFID, EU, Denmark and Norway. Total DFID contribution is £3 million which is 7% of total MDEF fund. / Save the Children: Early Learning and Transition to Primary School: New Generation Programme. DFID’s contribution is up to £2.6 million. / Shalom Foundation: Creating an Improved Learning Environment in Kachin and Mon State (CILE). DFID’s contribution is up to £1.9 million. / Myanmar Education Consortium (MEC): An innovative programme supporting INGOs and Local organisations access support for non-formal support to Education and increase their own influence in policy dialogue. Current funding comes jointly from DFID and AusAID with a commitment to date of $ 20 million. Total DFID contribution is £ 3 million (approximately $ 5 million) which is 25% of current total fund.

What are the expected results?
The intended impact of the programme is to increase the number and proportion of children in Burma accessing and completing a quality basic education. / The intended outcome is 200,000 children supported to remain in school with an increase in survival rates during early years of primary school and to Grade 5. [1] / The expected Outputs for the programme as a whole (including other donor contributions to the Multi-Donor Education Fund (MDEF) and the Myanmar Education Consortium (MEC) are: / 125,000 children will benefit from improved Early Childhood and Development services, particularly in poorer, rural areas / 1.1 million primary school children will have improved access to quality teaching and learning in schools / 81,000 children will have improved access to quality non-formal, alternative and life skills education / Schools from 25 townships will have improved management and accountability to local communities
[1] DFID, as part of MDEF (7% share) and the MEC (25% share for first 2 years of the programme)

What is the context in which UK support is provided?
Burma is off-track to meet MDG2, ensuring that all children complete a full course of primary school. Thousands of children do not even start primary school. Thousands more drop out of school every year. The proportion of children that complete the full five years of primary school is estimated at 50-60%, and there is significant disadvantage for children in rural areas compared with urban populations. Standards of literacy, numeracy and overall attainment are low. An even smaller proportion of children, usually from richer families, have access to secondary and higher education. / More positively, Burma appears close to meeting MDG3, ensuring gender equality. At the primary level the ratio of boys to girls is broadly equal with no overt discrimination against girls in teaching practice. However, there are variations across different regions and there is some evidence that more boys drop out in the later years of primary school in order to work. Government figures suggest that women outnumber men significantly in higher education. / At the political level, the 2010 elections and the subsequent coming to power of a new parliamentary government, has resulted in progress in laying out a reform agenda for the education sector. President Thein Sein, in the first regular session of Parliament, encouraged lawmakers to improve the national education system and, in early 2012, the Ministry of Education (MOE), with support from a range of stakeholders, has initiated a process for a sector-wide review in basic education. / Despite these positive political developments, the education system still suffers from decades of chronic underinvestment and failure to reform by the Burmese government.. A large proportion of Government expenditure is still devoted to the military and although support to social services such as health and education is increasing, absolute levels remain low. It is estimated that Burma spent only 0.5 percent of its GDP on basic education – primary and lower secondary – in 2009, compared with 14.6% in other parts of the region. / A significant number of children who cannot access public schools rely on education services provided by monasteries and other religious organisations, community groups, and ethnic minority state administrations operating outside the control of the Burmese government. These schools receive little or no financial or management support from the central government or local authorities but provide services to some of the poorest and most vulnerable children in Burma as the cost of attending them is relatively low. / DFID Burma’s education programme has a strong focus on access, quality and inclusion of the poorest and most marginalised children. There is an increasing focus on demand-side approaches, including increased community participation and mechanisms to increase accountability and responsiveness of the education system to meet the needs of communities and their children.

## Section A: Detailed Output Scoring
Output 1: Improved ECD service delivery and coverage, particularly in poorer rural areas
Output 1 score and performance description: B / Output 1 is measured by 3 indicators / Number of children who have benefitted from ECD services / % of ECD centres that meet minimum quality standards (school and community based) / Multi-sector ECD national action plan/policy in place / Results achieved in 2012 / 17,558 children (61% of target) have benefitted from ECD services / No target set for 2012 for % of ECD centers met minimum quality standards (school and community based) / Multi-sector ECD policy outline developed. / For output one results moderately did not meet expectation and therefore output 1 is scored at B. This is mainly due to report timing as well as in delays in the initial project start-up phase. For Output 1 indicator 1, as of September, both UNICEF and SCF were only midway through the implementation and data reported is up to June 2012. The late targets from Y1 was planned to meet in Y2 Annual Review after 1.5 year of completed implementation. For indicator 2, it is too early to assess quality standard in their first year of implementation. However, indicator 3, the upstream work on an ECD national policy framework exceeded expectations with numerous additional initiatives on policy guidelines as well as work through the recent Comprehensive Educations Sector Review (CESR). / Output (1) Indicator (1) Target Achieved / Number of children who have benefitted from ECD services 28,841 children / UNICEF: 20,000 / MEC: not started in 2012 / Save: 8,841 17,558 children / UNICEF: 17,318 / MEC: not started in 2012 / Save: 2, 740 (1,347 boys and 1,343 girls) / Progress against expected results: / UNICEF: / Through partnerships with NGOs, the Department of Social Welfare (DSW) and Ministry of Education (MoE), 17,318 children aged 0-5 benefitted from accessing facility based ECD services during the first half of 2012. / For school based ECD, UNICEF has prioritised schools that need the most support to establish ECD centres. In addition, 1,538 sets of play and learning materials, 1,896 sets of teaching materials for ECD teachers and 1,458 sets of children story books were distributed to 313 schools and 22 communities. 1,253 sets of children story books for parenting education session were also distributed and mother circles have been pilot testing these in IDP camps in Waing Maw and Myitkyina. / Save The Children Fund(SCF): / A total of 2,740 children are newly benefitting from centre based ECD in 9 townships. Among them 12 children were identified as having a disability. This represents 31% of the milestone of 8,841 children with the shortfall due to the withdrawal of the Save the Children project from Nam Kham Township following the unexpected and rapid deterioration of the security situation, the subsequent delay in starting work in the substitution villages and the wider delays in recruitment and set-up encountered at the very start of the project. / In order to reach more remote and disadvantaged communities, SCF piloted a new alternative approach in 50% of implementing villages. The alternative PE services will be provided by training village facilitators who are guided by a mobile team to gradually establish ECD services. / Output (1) Indicator (2) Target Achieved / % of ECD centres that meet minimum quality standards (school and community based) No target set for 2012 / (UNICEF, MEC, Save) Baseline on quality of school-based preschools conducted in 15 townships and 181 schools were monitored by UNICEF. / Progress against expected results: / UNICEF: / In order to strengthen the focus on quality of ECD, a baseline study was conducted in 181 schools in 15 townships. The baseline showed only 2% met the 15 core quality indicators and 54% needed urgent attention on sufficiency of play materials, children’s development progress record keeping amongst other areas. / 609 new preschool teachers from 313 school based ECD centres were trained on developmentally appropriate ECD practices. In addition, partnering with local NGOs, 2,280 ECD workers from communities received both technical and organisational development training. Refresher trainings for 437 ECD teachers from 25 Townships was organised in June 2012 to improve the quality of services provided for children. / Output (1) Indicator (3) Target Achieved / Multi-sector ECD national action plan/policy in place Policy Framework designed / (UNICEF, Save) National Steering Committee and Task Force established. Policy outline has been developed. / Progress against expected results: / Save and UNICEF have provided technical assistance to develop the multi-sectoral ECD policy framework in 2012 under the leadership of the Ministry of Social Welfare. A steering committee and task force committees were established and policy outline developed with the support from the international consultant. A total of 12 nationwide consultations with broad stakeholder participation were held to document their views, ideas and concerns regarding issues affecting young children. A high-level advocacy was carried out with Ministers and parliamentarians during the consultation meeting. UNICEF plans to do a situational analysis of young children as part of the policy development in later 2012. UNICEF and Save also provided support on broadening strategic partnerships to support ECD implementation by local NGOs to expand community based ECD facilities, particularly in ethnic and hard-to-reach areas.
Recommendations: / DFID will ensure a strong communication mechanism between MDEF donors, UNICEF, MoE, DSW and other ECD partners in order to facilitate links between programmes and coordinate with others involved in ECD activities. / DFID will ensure the programme responds fully to the opportunities offered by the changing political economy around ECD and Education sector in Burma. / DFID will ensure sufficient technical inputs as well as monitoring for the quality assurance of both school and community based ECD activities. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Improved access to quality teaching and learning in schools
Output 2 score and performance description: A / Output 2 is measured by 3 indicators / No. of students in targeted townships provided with essential supplies and textbook including humanitarian support. / % of primary teachers applying improved teaching methods as defined by classroom observation criteria. / No. of primary teachers receiving training. / Results achieved in 2012 / 622,777 students (95% of target) in targeted townships provided with essential supplies and textbook including humanitarian support / No target set for 2012 for % of primary teachers applied improved teaching methods as defined by classroom observation criteria: / 9,452 primary teachers (92% of target) received training. / The output results demonstrate that the targets are moderately under achieved. UNICEF is able to almost meet targets set for output indicators with the programme delivering the key areas of support. In Shalom’s programme, implemented in Kachin and Mon States, the intensified conflict and instability in Kachin meant the targets were not achieved as envisaged in the original work plan. However, Shalom is trying to use different secure channels for supplies to ensure they arrive on time to the students. In addition to these results there have been great advances in the extent of dialogue and policy influencing with government, especially on the issues of access and quality (see page.9). In light of this output 2 is scored at A.. / Output (2) Indicator (1) Target Achieved / No. of students in targeted townships provided with essential supplies and textbook including humanitarian support 658,051 children / UNICEF: 620,000 / Shalom: 21,745 in KIO + 16,306 in Mon = 38,051 622,777 children / UNICEF: 592, 894 / Shalom: 15,312 in KIO + 14,571 in Mon = 29,883 / Progress against expected results: / UNICEF: / 592,894 school children have been provided with essential supplies and textbooks in 25 targeted townships. In addition, 276,000 sets of language enrichment programme materials (story books, teachers’ guide and textbooks) were distributed to 23 townships. / Shalom: / A total number of 29,883 students from 408 non-state schools and IDP camp schools in Kachin and Mon states received teaching and learning materials and text book for 2012-13 school year. As Kachin has been in conflict more than 1 year and most of the parents and students are living at IDP camps with limited livelihood activities, text books and exercise books are the most requirements for students but least affordable for the parents. / Output (2) Indicator (2) Target Achieved / % of primary teachers applying improved teaching methods as defined by classroom observation criteria No target set for 2012 / (UNICEF) Baseline report on teacher practices in classroom has been finalized. / (UNICEF) / Progress against expected results: / UNICEF: / A baseline survey on classroom practices conducted in 229 primary schools in 25 targeted townships in order to assess teachers’ methods and effectiveness as well as to assess effectiveness of in-service teachers’ training. A significant finding were 80% teacher-directed and only 4% on child-centred. It was observed in the study that the prominent teaching method was whole-class teaching involving closed-ended questions, cued elicitation or writing on chalk board. Group works, students explaining learnt concepts to peers were almost absent and child centred teaching took only 2% of lesson time. / In order to strengthen in-service teacher training, the training manual was revised incorporating additional module as well as extending duration of the training. / Output (2) Indicator (3) Target Achieved / No. of primary teachers receiving training 10,256 teachers trained / UNICEF: 8,250 Face-to-Face+1,000 INSET / MEC: not started yet / Shalom: 1,006 9,452 teachers trained / UNICEF: 8,178 Face-to-Face+ 1,125 INSET / Shalom: 149 / Progress against expected results: / UNICEF: / Altogether 8,178 primary teachers (national trainers, township level trainers and primary teachers) were trained on the new training module as part of in-service teachers’ face-to-face training. 1,125 Grade 4 and 5 teachers were trained for Language Enrichment programme. / With support from UNICEF, MoE also developed an innovative school based in service teacher training module on Effective Teaching and Learning. It was implemented in 4 targeted townships with training of 205 head teachers. / Shalom: / A total of 149 newly recruited teachers (84 Kachin+65 Mon) had been trained on CCA. The achievement was only 15% of the set targets for 2012 because of the conflict in Kachin states and difficulties in recruiting new teachers and organising trainings.
Recommendations: / DFID will continue to closely monitor Shalom’s activities in Kachin State to ensure supply risks are being adequately monitored and managed. / DFID will ensure the programme responds fully to the opportunities offered by the changing political economy around the Basic Education sector in Burma, utilising high level representation, such as the Ambassador, to ensure the CESR remains on track. / DFID is an important and valued player in the education field. As the current Education adviser (15% input) and in-country education lead will be leaving within the next 12 months, DFID Burma will need to consider future staffing requirements. / Impact Weighting (%): 35 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Improved access to quality non-formal, alternative and life skills education
Output 3 score and performance description: A+ / Output 3 is measured by 2 indicators / No. of children who have accessed non-formal, alternative or life skills education / Percentage of reached out of school adolescents completing EXCEL in targeted townships / Results achieved in 2012 / 20,708 children (104% of target) have accessed non-formal, alternative or life skills education / 96% of reached out of school adolescents completing EXCEL in targeted townships in 2011-12 academic year. / The output results demonstrate that the targets were moderately over-achieved and therefore the output 3 is scored at A+. For Indicator (2), 2011-12 data is currently available and 2012-13 data will be available by end of school year which is February-March 2013. The lengthy design of the MEC has resulted in a comprehensive and innovative approach to non-formal and alternative education which will bring in new people involved in education sector and deliver ambitious results. / Output (3) Indicator (1) Target Achieved / No. of children who have accessed non-formal, alternative or life skills education 20,000 children / UNICEF: 14,000 EXCEL+6,000 NFE / MEC: not started in 2012 20,708 children / UNICEF: 10,357 EXCEL+ 10,351 NFE / Progress against expected results: / UNICEF / Extended and Continuous Education and Learning (EXCEL) / 10,357 out-of-school children for academic year 2012-13 in 230 villages in 29 townships are benefitted from EXCEL programme. 372 facilitators are trained. In order to promote parents’ understanding and support, more than 2,700 parents received selected EXCEL lessons to promote their awareness on EXCEL and components of EXCEL lessons. / Non Formal Primary Education (NFPE) / 10,351 out-of-school children for academic year 2012-13 in 498 centres in 73 townships are benefitted from NFPE programme. 977 NFPE facilitators are trained. Accelerating the upstream work to institutionalised NFPE and the equivalency programme and with facilitation from UNICEF, MoE formed a task force that includes staff from MoE, Education colleges and a local NGO: MLRC. The first coordination meeting was conducted and the agreed plan is to prepare for development of a national standardised equivalency examination to re-enter into the formal education system. / Output (3) Indicator (2) Target Achieved / Percentage of reached out of school adolescents completing EXCEL in targeted township 85 % / (UNICEF) 96% for EXCEL (2011-12) / 2012-2013 completion data will be collected later in the school year. / (UNICEF) / Progress against expected results: / For academic year 2011-12, 10,568 out-of-school children, including 35 children with disabilities from 221 villages in 24 townships completed phase 3 of EXCEL programme which was 96% completion rate. 2012-13 completion data will be available by end of school season and reported in next Annual Review process.
Recommendations: / In NFE, the lack of a clear policy framework is the key limiting factor to expansion. DFID will ensure upstream advocacy initiatives through UNICEF to be highlighted on the policy agenda in terms of expanding the service providers and getting MoE endorsement. / In EXCEL, the key issue is that it needs to include literacy and numeracy as part of core curriculum. Without this, the benefits are hugely diminished. DFID will make sure that the implementing partners are fully aware this need and implemented. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Improved management of schools and accountability to local communities
Output 4 score and performance description: B / Output 4 is measured by 2 indicators / Proportion of schools with operationalised SSAs/SIPss in targeted townships / No. of townships with TEMIS fully operational / Results achieved in 2012 / No target set for 2012 for % of schools have operationalised SSAs/SIPs in targeted township. / 25 Townships with TEMIS partially operational / Where these is data, the output results demonstrate that the targets were moderately not achieved and therefore the output 4 is scored at B. Delays were mainly due to the initial start up phase of the project activities by UNICEF with MoE. The programme team will be able to report more fully on the results for this in the next report. / Output (4) Indicator (1) Target Achieved / Proportion of schools with operationalised SSAs/SIPs in targeted townships No target set for 2012 1000 schools received training on SSA/SIP process, 5000 PTAs members trained on school improvement plan / Progress against expected results: / UNICEF: / A set of targeted activities were conducted to strengthen the capacity of schools, clusters and townships in education planning, management and mentoring during the reporting period. 1000 schools received training on SSA/SIP process, 5000 PTAs members trained on school improvement plan and 100 school received grants for implementation of improvement plans, capacity building of Township Education Officers and school heads on instructional leadership were carried out. / Output (4) Indicator (2) Target Achieved / No. of townships with TEMIS fully operational TEMIS partially operationalised in 3 townships In the selected 25 townships for TEMIS programme, school data is being collected with revised TEMIS forms and data entry on computer database for collected TEMIS data is in the progress. / Progress against expected results: / A review of the revised Township Education Management Information System (TEMIS) forms was conducted and identified essential data required for quality TEMIS reports that can inform evidence based management decisions at different level.
Recommendations: / DFID and UNICEF will need to work closely together to ensure that TEMIS collected data are transformed into useful information for evidence based education planning in the future. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N / Additional Activities or Achievements during the reporting period / Comprehensive Education Sector Review (CESR) / Myanmar has embarked on several reforms in the overall new governance context, with economic reform at the top of the Government’s agenda. A significant step toward a change in the education sector occurred during February 2012 conference on “Development of policy options with special reference to Health and Education”, where a major recommendation was to conduct the first comprehensive education sector review in 19 years. Subsequent approval for the CESR came directly from the President. / The CESR process will help to develop a body of knowledge that can inform the adoption of solid, evidence based education policies and strategies which further strengthen the education system and ensure the rights of all children to education. The process will also involve the development of costed interim and long term sector plans and it will contribute to Education for All national goal and Millennium Development Goal 2. UNICEF and MDEF (DFID as part of the donors) supported the process by assisting in the recruitment of international consultants and covered costs for assessment and analysis work. / The CESR will be conducted in 3 phases: Rapid Assessment, In-Depth Analysis and Development of Education Sector Plan and total estimated time planned for 2 year for the whole process starting from mid-2012 till mid-2014. / Myanmar Education Consortium / Save the Children, Burnet Institute and World Vision have been working closely and intensively with DFID and AusAID on the development of the Myanmar Education Consortium (MEC). MEC is a programme designed to build on skills and existing work of a diverse range of civil society agencies to address the overwhelming basic education needs in Myanmar. This will be a four year programme which comprises the building of the capacity of complimentary (non government) education systems and structures including community and school based early childhood development, non-formal education programs for vulnerable children and young people who cannot attend government school. The proposal was successfully passed through the internal review processes for DFID and AusAID and implementation is due to begin in November 2012. / Education Coordination Mechanism / Joint Monitoring Visits / Annual joint monitoring visits to UNICEF and Save the Children programmes have occurred with the participation of MoE, DSW, UN and NGOs and Donors (AusAID, DFID, EU). During these visits, partners are able to see first-hand the challenges of implementation, understand exactly how funds flow to the community level, gain first hand feedback from beneficiaries and field staff and – where possible – conduct basic asset and financial checks. These visits also allow partners to check whether other actors are working on the ground and we are appropriately avoiding any duplication of effort through poor coordination. / Education Thematic Working Group (ETWG) / ETWG is a valuable mechanism for MoE, Development partners, UN agencies, INGOs, LNGOs and other stakeholders in education sector to coordinate sectoral programming, information and activities. 3 regular meetings carried out in November, January and March 2012. / ECD Technical Working Group / It was a sub-group of ETWG which brings together concerned agencies on ECD field to ensure consistency and excellence in ECD provision. The group focuses on harmonising of approaches, developing and jointly monitoring quality standards and developing ECD materials jointly. The meetings occurred quarterly.

## Section B: Results and Value for Money.
1. Progress and results

1.1 Has the logframe been updated since last review? Y / This is the first review but since the Business Case was approved the logframe was been updated to reflect the final design of there of the four components of the programme: / UNICEF: Quality Basic Education Programme (QBEP) / Save the Children: Early Learning and Transition to Primary School: New Generation Programme / Shalom: Creating an Improved Learning Environment in Kachin and Mon State(CILE) / Myanmar Education Consortium (MEC) / 1.2 Overall Output Score and Description: / Though, output 1 and 4 are scored as B, output 2 scored A while output 3 as A+. / The final output score is A as per the AR calculator which means that the outputs met the expectation. The implementing partners delivered the majority of agreed activities though there were major constraints such as delays in implementation due to the late start up of the project activities and the ethnic conflict in the project areas (Kachin and Northern Shan state). In order to compensate those delays, the implementing partners have to speed up with their existing resources as well as change in the strategies. E.g. There was a change of targeted villages for 2 townships in Northern Shan State by Save the Children as there was a limitation on the movement of project staff due to security concern. Additional recruitment of front line staff to deliver more effectively at the field level. In addition, the military tensions and fighting between the Kachin Independence Army (KIA) and Burmese Army has delayed most of the activities set by Shalom CILE programme in Kachin. / 1.3 Direct feedback from beneficiaries / During field visits by implementing partners and DFID staff the following direct feedback from beneficiaries was collected: / Beneficiaries feedback on ECD / “My daughter has always been disabled. She could not walk or speak and was unable to mover her hand. When I first sent to ECD centre, she is shy and afraid. Now she is confident, she has friends and started speaking with slight lisp, but clearer than before” a mother of disable child from ECD centre in Mawlamyaingyun Township, Delta. “Now I am very happy to see my daughter who has developed so much since attending ECD centre. So, I will tell the community about the benefit of sending their children to ECD centre.” / Beneficiaries feedback on establishing ECD in the community / “Now, we have a practice of meeting at least once a month and sometimes twice in case of emergency to discuss ECD activities and village welfare. The matching fund was provided by Save the Children and the construction, fund raising, labour and materials for ECD centre were provided by community members. We are eager for the ECD centre as we all aware that it is beneficial to our children”. A community member as well as the president of ECD committee from Hlaing Bwe Township, Kayin State. “We will continue to motivate the community for development of our future work. We will work to acquire more matching fund, more salary for care givers and to build up the capacity of management team”. / Beneficiaries feedback on teachers training / “Training in language and in multi-grade teaching is the most difficult and required more time to perfect these skills.” Post evaluation feedback from in-service teacher training. / Beneficiaries feedback on EXCEL / “I Can Set My Own Ambition in Life”: A 16-year-old maternal orphan boy is a carpenter. Neither he nor his siblings had ever attended school, he didn’t know how to write, read or do math when he started to join EXCEL. He recalled his experience, he felt frustrated, discouraged at first. Now, he had taught to read, write and simple calculation. He said: “I am now happy to attend the EXCEL training. After studying the lessons, I stopped chewing betel and drinking alcohol. I gained a lot of knowledge on infectious disease especially on HIV transmission. Now, I know that I shouldn’t try drugs and I can set my own ambition in my life.”
1.4 Summary of overall progress / The programme commenced on 1 November 2011 with 4 components: / UNICEF: Quality Basic Education Programme (QBEP) / Save the Children: Early Learning and Transition to Primary School: New Generation Programme / Shalom: Creating an Improved Learning Environment in Kachin and Mon State(CILE) / Myanmar Education Consortium (MEC) / Apart from MEC, the three components have all started during the reporting period, project staff recruited and the majority of activities in work plans completed. Up to June 2012, the programme has progressed well and achieved nearly 90% of the target set for 2012. MEC design is now in the final stage and is planned to start in early November 2012. / A key area where the programme has demonstrated progress that has exceeded expectations is at the policy level where new opportunities, such as the CESR, have created further space for dialogue through which partners, including DFID, can influence and support the government’s education policy making. Examples of progress on advocacy include: / Upstream work on ECD policy with engagement from DSW and higher level government officials and Civil Society Organisations / Comprehensive Education Sector Review (review on basic education policy, teachers quality, human resourcing, text book, school years, compulsory primary education, etc) / Establishment of ETWG with regular coordination and communication mechanism on Education Sector / Provision of essential school supplies and text book (compulsory free education for primary schools) in order to reduce burden on parents for education / Government permission for local NGO to implement NFPE and EXCEL activities / Increase cooperation and coordination between ECD working groups at national, state/division, township and community level
Key challenges / The main challenge faced by the programme as a whole arose from the continuing conflict in Kachin State, which started in June 9, 2011 and continuing till now. Many villages, houses and some schools were burnt down and destroyed. IDPs are increased day by day in all camps and still conflict is active. Most of the schools under KIO administrated areas were unable to open in regular. It has disrupted children’s education and hampered implementation of Shalom and QBEP activities in Kachin State. For example, programme implementation was affected in 3 targeted townships in Kachin (Mansi, Waingmaw and Pharkhant) for QBEP and education activities (teachers’ training on CCA, administration and leadership trainings) for Shalom CILE Project. There were difficulties in the distribution of school supplies (transportation cost, estimated no. of kids in IDP camps). / The emergence of new partners interested in supporting teacher education a need exists for a strengthened coordination mechanism to ensure harmonisation and less demand on the MoE. / The human resource gap at the MoE: Deployment of 20 people from different departments of MoE for CESR and the delay in filling this gap has added to the existing human resource constraints in implementation of the QBEP programme by MoE. / Lengthy process in MEC design phase as it was both innovative and involved oragnisations working together as a consortium. The set up arrangements for MEC on good governance, firewall and coordination mechanism in place brought some delays for programme start up. However, as compared to the start of the programme in October 2011, the MEC process is moving forward and the consortium team have put their utmost effort to set up and start working the programme from 1 October 2012. / Changing ingrained habits and practices with what teacher have learned from the training (CCA, LEP) appears to be quite difficult for most teachers. / There is still a dissonance between government and community contribution to schools. Communities continue to cover large costs of education in terms of school maintenance, repair and paying salaries of community teachers.
Annual Outcome Assessment / It is still early in the programme to attribute outcome results against the programme log frame as data from baseline surveys is still being processed. Based on the reports from the implementing partners after 6 months of implementation, the project is broadly on-track to meet the log frame output targets. While we will have to wait for the full outcome data, evidence gathered in field visits demonstrates a positive correlation between these output indicator results and whether children remain in school with positive survival rates during the early years of primary school.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Total committed funds from DFID until 2016 are £10.5m and to date, £4.1m (39%) has been spent. / Expenditures (Budget Vs Actual as of September 2012) / Component Budget planned (£) 2011-15 October 2011-September 2012 % Spend as per planned budget for 2011-12 Remarks / Budget Planned (£) Actual Spent (£) / Design for Burma Education Programme 31,000 31,000 29,445 95% Completed / Save the Children: Early Learning and Transition to Primary School: New Generation Programme 2,127,831 2,127,831 1,459,613 69% Ongoing Implementation and progress has been slight underachieved due to delay start up and relocation of townships due to conflict affected areas. / UNICEF: Quality Basic Education Programme 3,000,000 2,250,000 2,250,000 100% Ongoing Implementation and progress is on track / Shalom: Creating an Improved Learning Environment 1,604,223 580,000 412,066 71% Ongoing Implementation and progress has been slowed due to continued conflict in Kachin / Myanmar Education Consortium 3,738,837 0 0 0% The plan is to start in October 2012 / Total 10,500,000 4,988,831 4,151,124 83% / 2.2 Key cost drivers / Transportation cost / During the intensified conflict in Kachin state, the cost of transportation charges has increased significantly with the price sometimes three fold that of the usual price in Kachin. Shalom CILE programme has to re-adjust the budget based on the inflated cost. / Exchange Rate / After stabilising of the exchange rate, Save the children project were able to recruit 30 additional field workers by April. This will ensure that the field teams are better equipped to meet targets. / Training Cost / Save the Children Early Learning and Transition to Primary School programme has budgeted for training in Year 1. However, the actual spend of training activities was less than expected due to : Combining training activities , conduct training in less cost by using a less expensive venue and cheaper accommodation costs. The remaining budget balance for the training will be reprogrammed into other activities. / Unit Cost on ECD supplies / UNICEF calculated a unit cost for ECD kit with $66 in budget preparation. In mid year financial statement, a unit cost for ECD kits became $82. Moreover, no. of unit rose from 900 to 1990 units. A combination of price and unit increase in ECD kits has resulted $84K over expenditure under ECD supplies. This was mainly due to increased local market prices for ECD supplies as well as working through partners for wider coverage. These over expenses has been compensated by less expenditures on ECD printing cost ($138K) using lump sum printing and reduced total transportation cost ($6K) for ECD supplies. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Based on the new, clearly defined logical framework for the QBEP, a corresponding monitoring and evaluation system has been put in place in the first half of 2012. This includes the identification and sequencing of all required data collection, the allocation and recruitment of education field staff, capacity building of government staff and implementing partners and setting of clear guidelines and procedures for the joint monitoring of activities of implementing partners. / UNICEF QBEP has placed dual track monitoring system to strengthen field level routine data collection. Data collection for quantitative statistical analysis will be conducted in August of each year through a structured questionnaire and checklist. This will be complemented by more frequent field level monitoring and joint field visit. / 3.2 Where an evaluation is planned what progress has been made? / A large scale baseline survey on learning achievements in Math and the Myanmar language for grade 3 and 5 covering up to 1000 schools was conducted in February 2012. In 229 schools, class room observations followed by a rigorous data collection protocol were conducted to assess teaching and learning practices at the beginning of the QBEP. The same sample of schools will then be revisited in 2015 to measure progress made in the core townships. / The baseline has also been conducted for an evaluation into teaching and learning practice through classroom observation (174 schools). This is a qualitative process using video and classroom observation. It already has key findings of less teaching with child-centred approaches in very small and very large class sizes, non-Myanmar and multi-grade classes, and less effective in language class compared to maths. The in-depth findings will be released shortly. The final evaluation is due in 2015.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Political Risk / There have been key changes in the Education sector with several new initiatives from MoE and the President’s office, including the CESR, presenting important opportunities for the programme to achieve transformational impact. With a fluid political context DFID and its partners will need to remain in close contact with the government whilst ensuring the voice of civil society and other political groups are not lost. / Other substantial changes happening include the promotion of the majority of front line staff (headmasters, teachers), the decentralization of management to state education offices and increase in capital grants for school running as the first time. / Human Capacity Risk / In DFID’s programmes, within the MoE and within DFID Burma itself we need to ensure high quality workforce planning and that capable staff are in post. For the MEC, recruiting highly skilled people to the MEC Programme Unit quickly will be essential. At the MoE there is a clear need for better workforce planning in MoE, especially for the CESR process, as well as effective engagement from other relevant ministries. Finally, in DFID Burma both the individuals currently employed as the Programme Manager and Education Advisor (15%) on the programme are due to leave within the next year. Careful consideration will be needed of future staffing needs. / Institutional Risk / The emergence of new partners and donor funds in the education sector increase the risk of poor coordination with government and other partners. In order to mitigate this, DFID has been part of the Multi Donor Education Fund for Education where all donors have agreed to a sector wide programme approach agreed by government and donors. In addition, the Myanmar Education Consortium is another initiative which will look to strengthen coordination, especially in the non-formal sector and between non-state education service providers. This has reduced the reliance of DFID and other donors on a narrow range of organisations for evidence, analysis and advocacy. / Development partners have also increased efforts to coordinate, both amongst themselves and with government, through the newly formed Education Development Partner Coordination Group and the Joint Education Sector Working Group. / Fiduciary Risk / Organisation receiving funding from DFID has assessed on their systems for managing and accounting for funds. MoU and accountable grant arrangement included submission of Annual Audit Report from each partner annually. / Conflict Risk / Ongoing conflict in Kachin and ethnic conflict in Rakhine has resulted in displacement, loss of lives and livelihoods with many children unable to attend schools. One key issue that emerged from this is a need to build in a conflict sensitive approach. A political and conflict analysis might be needed to enhance the effectiveness of the programme.
Risk of funds not being used as intended / Medium / Partner organisations implementing and managing sub-grants have strong financial reporting and audit systems and have trained local partners in reporting and financial management. / There have been two allegations of fraud within DFID’s partners, both of which have been reported to the Counter Fraud Unit and the cases subsequently closed due to insufficient evidence of significant fraud. / DFID’s Fraud Liaison Officer will be convening a session of partners in the coming months, including those working on education, aimed at ensuring all partners are aware of donor policies on fraud detection and reporting as well as help facilitate better intelligence sharing between partners and best practice on fraud detection and prevention. / As the space opens up to work closer with government systems on education rigorous assessments will be required to ensure the robustness of financial systems and reporting to ensure the risk fraud is absolutely minimised. / 4.4 Climate and Environment Risk / No change. The risk remains low.

5. Value for Money
5.1 Performance on VfM measures / Teaching and learning materials: / The cost of the production of textbooks by UNICEF ($2,10) is well within the range of international comparators in the Business Case. / ECCD Provision: / Costs of ECD programs across the world vary significantly caused by differences in program characteristics, delivery mode (e.g. parental education, home-based care models, community-managed or school-based ECD services), focus of the intervention, age range of children, staff requirements, frequency of duration. As part of the design of the Myanmar Education Consortium we requested all partner to submit a detailed annex with a breakdown of the unit cost for the various ECD models being used. There was a wide range of unit cost per child per year depending on how many future beneficiaries were included in the calculation. Despite this, the costs all fell within the range of the international comparators used in the Business Case. The MEC unit cost analysis is the start of a longer-term process of linking quality indicators to these unit costs to build an evidence of what cost effective ECD provision – whether school-based or community based – should be in Myanmar. This work will also be picked up by the CESR as it examines the efficiency and costs of ECD delivery in school and community based models. / Commercial Improvement and Value for Money / The programme has introduced measures which have contributed to increased commercial viability and will support VFM such as: / Involving communities and local government leaders not only to provide financial and material support to education activities, but also to help create awareness about the need for education, change attitudes, mobilize the community for action and facilitate replication / Targeting complementary education systems / Set-up costs: Recruitment of experienced staff and staff those are involved in the previous projects. Familiarity and experience of the team will engender an acceleration of delivery towards results / Procurement of items that are available in local markets in the required quality and quantity / Enabling communities to manage and sustain ECD centres through provision of revolving fund, capacity building on fund management and income generation and ongoing monitoring support and guidance during project implementation. / 5.3 Role of project partners / As part of the design of the MEC partners have agreed to a number of principles to ensure value for money is achieved throughout programme implementation. / Economy / Giving priority to sourcing local goods manufactured in the area of operation and supplies or services readily available locally / Saving cost through bulk purchasing / Conducting competitive tendering for contracts for goods and services and use benchmarked fee rates to ensure competitive rates / Ensuring that all procurement activities are fully and transparently documented to promote fairness and minimize the risk of corruption / Comparable market rates for salaries, consultancies / Efficiency / Encouraging involvement and meaningful participation of communities and local authorities to ensure that highest priorities and immediate needs are addressed so that the use of scarce resources for development can be maximized. / Promoting efficient program implementation through systematic professional development and coaching for local partners; / Organizing annual review and evaluation meetings where different implementing partners will meet to share and reflect on effective approaches, lessons and ideas of their work; / Increasing efficiency through improved knowledge management processes; / Effectiveness / It is early to assess the effectiveness of the programme, however, strategies adopted to ensure effectiveness are: / Conducting evaluations and regular monitoring of the activities / Assessing learning outcomes through the M&E framework with outcome-level indicators focusing on learning gains / Introducing appropriate evaluation follow-up mechanisms / Assessing and managing risks / Equity / Targeting most vulnerable groups, ethnic minority and disability / Working with a results-framework that disaggregates data across different target groups (e.g. girls, boys, children with special needs), yielding lessons applicable to their needs. / 5.4 Does the project still represent Value for Money : Y/N / Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / The EU restrictive measures effecting Burma were suspended for one year in May 2012. Up until that point the programme has been implemented within the parameters of the EU common position on Burma. Following the suspension, there is now further flexibility to explore the potential for closer working with government systems, including a move to transferring funds through the township level. These changes will require rigorous assessment and monitoring to ensure they represent the best value for money modalities and have adequate fiduciary controls.

7. Conclusions and actions
The programme is progressing well with the majority of current outputs meeting expectations. / With the completion of the design of the MEC the full programme now covers comprehensive support in basic education (state and non-state run) with an inclusive approach to benefit all children to get a chance for accessing basic education (formal and informal). / There have been key changes in the political economy of the education sector, including the CESR, staffing changes, increasing education budget and decentralization approach. However, there are still some reasons for caution such as fluid political context, weak coordination and limited human resources. / Factoring in the above mentioned opportunities and challenges, as the programme moves forward existing coordination mechanism will need to be strengthened with programmes adopting a reflective and flexible approach to respond to the opportunities offered by the changing political environment. Sustained technical and programme management inputs will continue to be needed to ensure the programme is progressing well to achieve target results by end of 2015.

8. Review Process
The annual review and scoring is based on: / UNICEF: Quality Basic Education Programme (QBEP) Mid Year Report 2012 (January – June 2012) / Save the Children: Early Learning and Transition to Primary School: New Generation Programme Progress Report 2012 (November 2011 – April 2012) / Shalom: Creating an Improved Learning Environment in Kachin and Mon State(CILE) Progress Report 2012 (November 2011 – April 2012) / Myanmar Education Consortium (MEC) Project Design Document / The review took place over the period of 20 September-10 October 2012 and DFID review team comprise Renwick Irvine, Education Advisor, Dominic Ashton, Education Lead (in country) and Mya Thet Su Maw, Programme Officer.

## List of Acronyms
AusAID:	Australian Agency for International Development
CCA:	Child Centred Approach
CESR:	Comprehensive Education Sector Review
CFS:	Child Friendly School
CILE:	Creating an Improved Learning Environment Project
DSW:	Department of Social Welfare
ECD:	Early Childhood Development
ETWG:	Education Thematic Working Group
EU:	European Commission
EXCEL:	Extended and Continuous Education and Learning
IDP:	Internally Displaced Person
INSET:	In-Service Teacher Training
JICA:	Japan International Cooperation Agency
LEP:	Language Enrichment Programme
MDEF:	Multi Donor Education Fund
MEC:	Myanmar Education Consortium
MOE:	Ministry of Education
MoRA:	Ministry of Religious Affairs
MoU:	Memorandum of understanding
MLRC:	Myanmar Literacy Resource Centre
NFPE:	Non Formal Primary Education
NGOs:	Non Government Organisations
QBEP:	Quality Basic Education Programme
SCF:	Save the Children Fund
SSA/SIP:	School Self Assessment/School Improvement Plan
TEMIS:	Township Education Management Information System
WFP:	World Food Programme
UNDP:	United Nations Development Programme
UNESCO:	United Nations Education, Scientific and Cultural Organization
UNHCR:	United Nations High Commissioners for Refugees
UNICEF:	United Nations Children’s Fund