Title: Improved Public Financial Management and Accountability

Business Case and Intervention Summary

Intervention Summary

What support will the UK provide?
The UK, through DFID, will provide £8 million to support public finance management reform at the sub-national and sectoral level and greater accountability of national government in Nepal. / £5 million will be allocated directly to the Asian Development Bank (ADB) ‘Strengthening Public Management Programme’ to deliver public finance management reform at the local level and greater accountability of national government. The detailed programme documents for this component are at FLAG D. / £3 million would be allocated to a contracted service provider to support sectoral public finance management reform. / Funding covers 4 financial years from 2012/13 to 2015/16
Why is UK support required?
Nepal’s systems for public financial management (PFM) are weak at all levels. As a result funding that flows through Nepal government systems can be at high risk from fraud and corruption and efficiency and impact of spending through national government systems is limited. / We currently support work to improve public financial management and accountability through the World Bank managed public financial management multi donor trust fund, through limited support available in some of our sectoral programmes and through our funding for civil society. Evidence suggests that national public financial management reforms are increasingly making progress and should result in improvements in related ‘public expenditure and financial accountability (PEFA) assessments, due early 2013. / Our Operational Plan, agreed with the Government of Nepal, recognises that weak accountability, corruption, the risk of economic instability and need for economic growth and the inclusion of marginalised groups (including through enhanced service delivery) are critical issues which need to be supportive for sustainable peace. Public finance reforms, supported by stronger systems for accountability, are recognised as key to addressing these issues. The plan committed us to scale up our support for public finance reform, accountability and anti-corruption. This was supported by the UK Independent Commission on Aid Impact report on anti-corruption (2011). Our new ‘Anti-Corruption and Counter Fraud Strategy’ (2012) includes this work as a major plank of our efforts to ‘step up’ on fraud and corruption. / This programme will for the first time, result in significant support for public financial management reforms at the sub-national and sectoral levels. International evidence suggests that public financial management reform is a slow process, but promoting platform (basic) reforms from multiple entry points (national, sub-national and sectoral), is critical to improving pace of and support for reform. / This programme should also result in significant cost savings and efficiency improvements for the UK taxpayer, by combining contracting for the (up to ten) required annual fiduciary risk assessments, for the life of the current operational plan.
What are the expected results?
The four headline results are: / A reduction by £6m (20%) in disallowed government expenditures, as measured by external audits *(based on current exchange rates and figures in the 49th report of the Nepal Office of Auditor General 2012 / There will be a 40% of increase of own-source revenues of pilot municipalities using the ‘Municipal Administration and Revenue System’ (MARS). / The scope, nature and follow up of external audit of local bodies will be better. / 24 Fiduciary Risk Assessments (FRA) and Annual Statement of Progress (ASP) completed.

## Business Case: Improved Public Financial Management and Accountability
The Strategic Case

A. Context and need for DFID intervention / Public Financial Management and Accountability in Nepal: Context, Performance and Trends: / Nepal’s systems for public financial management (PFM[1]) are weak at all levels (national and sub-national).[2] For example, budgets, when available, lack transparency (this is particularly true for transfers to local government units). A large portion of government spend is off budget[3]. On budget expenditure is weakly aligned to country priorities, including for poverty reduction. Spending control is weak as is revenue collection[4]. Internal audit often non-existent or ineffective. / Weak PFM is partly the result of weak skills to implement the PFM systems that exist. In addition, weak accountability mechanisms and political instability[5] limit the use of available systems. / Systems are even weaker in sub-national units of government (the District Development Committee and Village Development Committee) in comparison to the national level[6]. / Sectors (ranging from health to infrastructure), which tend to have an institutional presence at both national and sub-national levels, and use these systems, also suffer from weak PFM[7]. / On the positive side, the Government of Nepal (GON) has, over the last few years, worked to improve parts of the PFM system[8], culminating, in 2009, in the adoption of a national PFM reform strategy, led by the Ministry of Finance (MoF)[9], the establishment of a PEFA Secretariat, hosted in the Ministry of Finance and sectoral Strategy Documents for the Office of the Auditor General (OAG) and Public Procurement Monitoring Office (PPMO). This has resulted in some improvements, primarily at the ‘up-stream’ / central / national level and within the Finance Ministry. For example, expenditure controls are improving through the gradual adoption of a single government bank account (called the Treasury Single Account), budget classification is now recognised as transparent and the information provided in the budget comprehensive[10]. Recently the GON has started to encourage sub-national and sectoral units to adopt PFM reform plans through PEFA sub-units. / Progress has been promoted through the actions of civil society. Social movements have increasingly gained traction, with service user groups in sectors increasingly holding government to account[11] (for more details on corruption see endnotes[12]). / Despite areas of progress, public finance management remains weak, particularly at sub-national and sectoral levels. Compared to other ‘fragile states’, Nepal has seen relatively less progress on PFM reforms since the end of the conflict[13]. Weak PFM therefore remains a major contributing factor to low levels of executive accountability[14]. Nepal’s Office of the Auditor General (OAG) provides some limited oversight. Both the OAG and the major anti-corruption agency (the Commission for the Investigation of the Abuse of Authority - CIAA) have however operated in a weakened capacity, without Chairpersons and with many posts unfilled. Nepal’s Parliament and its related Committees (including the Public Accounts Committee) had started to play a role in holding the executive to account but were recently lost, due to the dissolution of the Parliament[15]. As a result, executive, legislative and independent scrutiny of budgets and spend is limited. Nepal has worked to improve its related legislation, passing a new ‘right to information’ act, new procurement legislation and a ‘whistle-blowers act’. Pest performance suggests that implementation of legislation is likely to take time. / Impact on conflict, fragility and poverty: / Weak PFM and accountability, contribute to poor governance, which is undermining the pace of poverty reduction in Nepal[16] and critical state and peace building processes. / For example, public expenditure per capita is low[17]. The share of the budget going to pro-poor expenditure is small compared to other countries in the region (linked to weak planning and budgeting and skewed expenditures, for example with salaries as approximately one quarter of the budget). The budget is not fully executed[18]. As a result, adequate resources do not arrive at front line facilities. / Looking forward growing public and private (banking) debts, threaten macro-economic stability, with implications for state stability. / At its worst, weak PFM[19] provides the opportunity for personal enrichment, embezzlement and the misuse of funds and could be a reason for Nepal’s high perceptions of corruption[20] [21]. / Nepal also suffers from a geographical mismatch between poverty, concentrated in the west, and government spending, focused more on the east and the Kathmandu valley. Poverty was also concentrated amongst certain disadvantaged groups (for example by ethnicity and cast), often poorly targeted by government spending. This mismatch was a factor that drove conflict and addressing this inequality is a critical aspect of peace building. / Nepal is also contemplating a significantly restructured and devolved system of government, for the delivery, for example, of basic services. Building the foundations now, to ensure that the future state can deliver this system, is a critical component of effective state building. / Finally, weaker governance and accountability systems[22] limit both the UK and Nepal’s ability to reduce poverty. For the UK, this requires us to allocate additional funds to systems to protect UK money from corruption and reduces our ability to streamline funding through budget support. World-wide corruption tends to result in weaker poverty reduction[23]. In Nepal, corruption is widely cited as a major barrier to poverty reduction[24]. / The need: The size of Nepal, its lack of connectivity and its diversity, all represent major challenges to developing and implementing PFM reforms and developing an accountable state in Nepal. / Part of the solution is through the adoption of a simpler and more effective public finance system, supported by the skills to deliver. In parallel, Nepal needs the political and bureaucratic will, driven by accountability, to use these systems and deliver on its anti-corruption commitments. / International experience suggests that a key issue will be the ability of Government to prioritize its reform agenda (building the foundations of a PFM system before seeking to implement more complex and ‘flashy’ reforms), and the ability of donors to align with and respect this prioritization. / At a national level, Nepal has identified a strong, well sequenced (platform) of reforms, required to strengthen public financial management reform programme (the PFMRP 09-12). Parts of this plan (improved external scrutiny and audit and improved accounting and reporting) have been supported by international donors, including the UK, through a World Bank managed Multi Donor Trust Fund[25] (WB-PFM-MDTF). / At the sub-national level, the Nepal government has very recently (2012) adopted a strong, well sequenced (platform) of reforms.[26] There is currently no mechanism for donors to support these reforms. A previous UN technical assistance fund, had provided very limited support for earlier reforms. / In some sectors, financial management reform actions plans have been adopted or are being developed. In others little action. Some international support for sectoral PFM reforms has been provided through sectoral programmes, but the scale, quality and impact of support has generally been limited. / International experience suggests that tackling and supporting PFM reform from the top down (through the finance ministry) either fails or delivers very slowly, in part due to a lack of ownership outside of the central ministry(ies). By contrast, taking a multi-pronged approach, supporting, coordinated, reforms from a national, sub-national and sectoral level tends to increase the pace of reform. / There is therefore a need to plug gaps in support at the sub-national, sectoral and even the national level (where only a few of the identified reforms are being supported). This is particularly important for the sub-national level. The peace agreement committed Nepal to shift towards de-centralised government, requiring a significant shift in the management and oversight of finances from national to local levels, as state functions are devolved. This means that there are on-going and growing demands on Nepal’s public finance systems, where they are at their weakest, increasing the risks that funds are poorly used or lost. / In addition, international experience suggests that reforms progress quicker when there is a strong level of public engagement PFM, often facilitated by civil society (the ‘demand-side’) or elections. DFID has been working with the Government of Nepal to supporting the public to demand accountability: including through anti-corruption focused NGOs, such as Transparency International – Nepal, and mainstreamed support for social accountability approaches, such as social and public audits, through a combination of programmes (the Community Support Programme; Local Governance and Community Development Programme and Enabling State Programme). / Throughout this sector, there is a continual and growing need for a strong evidence and analytical base (through studies such as fiduciary risk assessments; vulnerability to corruption assessments; expenditure tracker surveys; payroll audits) to protect public (Nepali and UK) funds, to inform reform plans, to enable monitoring of progress and to open space for reform dialogue. DFID alone is required to deliver 24 FRAs and ASPs from 2012 to the end of the Operational Plan period. / UK and DFID role: HMG support to Nepal aims to strengthen efforts to reduce political instability, the most significant barrier to poverty reduction (DFID Nepal Operational Plan 2011-15). The UK recognises that weak accountability, corruption, the risk of economic instability and need for economic growth and the inclusion of marginalised groups (including through enhanced service delivery) are critical issues which need to be dealt with to prevent a re-emergence of conflict and instability. Public finance reforms, supported by stronger systems for accountability, are recognised as key to addressing these issues. / The Operational Plan highlighted corruption as a key risk to delivery and committed DFID to scaling up support for public finance reform, accountability and anti-corruption[27] (this focus was supported by the UK Independent Commission on Aid Impact and is captured in the DFID Nepal 2012 ‘Anti-Corruption and Counter Fraud’ (ACCF) Strategy [28]. / Areas for UK support: Of the needs identified, some can and will be addressed through existing mechanisms. The WB-PFM-MDTF will likely expand in 2012 to ensure that comprehensive support is provide to the platform reforms identified at the national level in the GON PFMRP (Improved policy based budget formulation – including planning; budget execution; and internal audit). / In this Business Case, we will address existing PFM constraints by i) providing support to PFM reforms at the sub-national level[29]; ii) providing support to PFM reforms in the sectors (including health, rural infrastructure, forestry, climate change and disaster risk reduction), iii) promoting accountability through key national accountability and anti-corruption agencies and by integrating citizen engagement in PFM processes; and iv) for delivering a robust evidence and analytical base. / In parallel we will continue to support the political will to tackle corruption, strengthen accountability and improve PFM through diplomatic and development dialogue, as outlined in our ACCF strategy. / Consequences of not funding: As above, the UK recognises that investments in this area are critical to both speeding up the pace of poverty reduction (by maximising the potential of both donor and GoN investments) and to reducing the risks of a re-emergence of conflict and instability. / The evidence base: for this proposal is strong (see key references). / Related Issues: For further issues see end-notes[30].
[1] There is no agreed definition of Public Financial Management (PFM). DFID (2011 How to Note on Managing Fudiciary Risk when Providing Financial Aid) defines PFM as “the system by which financial resources are planned, directed and controlled to enable and influence the efficient delivery of public service goals”. Generally PFM is understood as including all components of a country’s budget process – both upstream (including strategic planning, medium-term expenditure framework, annual budgeting) and downstream (including revenue management, procurement, control, accounting, reporting, monitoring and evaluation, audit and oversight). Sound PFM supports aggregate control, prioritization, accountability and efficiency in the management of public resources and delivery of services, which are critical to the achievement of public policy objectives such as the MDGs.
[2] See 2008 Public Expenditure and Financial Accountability (PEFA) Assessment and annual World Bank Governance Data (CPIA) – for example the 2008 PEFA illustrates very weak performance with a majority of D and C scores out of 28 indicators (on a scale of A to D, with D as the weakest ranking). World Bank country governance data also shows extremely weak performance at all levels of the PFM cycle, from revenue collection to budgeting, budget execution, control and reporting and external accountability.
[3] See 2008 PEFA indicators PI-7 on extent of off budget expenditure, PI-8 on transparency of intergovernmental fiscal relations, and PI-10 on public access to information graded D). The share of off budget and off accounts expenditure is very high, as well as the use of exceptional expenditures bypassing mainstream expenditure processes (PI-7 on the extent of off budget expenditure graded D)
[4] There has been an increase in revenue collection in the last few years but still very low expenditure per capita compared to other countries. Major sources of revenue still escape the public expenditure process.
[5] The lack of regularly elected representatives, rapidly changing political leadership and senior civil service, political actors focused on peace agreements.
[6] See Annual Local Government Fudicial Risk Assessments and 2011 Local Government Public Expenditure Tracker Survey.
[7] See annual sectoral Fudicial Risk Assessments.
[8] Successful technical PFM reforms are slowly reducing the space for corrupt actions: The Government of Nepal has started to roll out a Treasury Single Account system, closing 7117 of 14,000 spending unit bank accounts, allowing better scrutiny and controls over 30% of the national budget. Procurement reforms by the Public Procurement Monitoring Office (PPMO), such as the piloting of E-Procurement, have reduced room for malfeasance.
[9] Government of Nepal, Public Financial Management Reform Programme (PFMRP), 2009-12.
[10] 2008 PEFA PI-5 and PI-6 graded respectively A and B. Progress will need to be confirmed through a second PEFA exercise proposed to be carried out in 2012/13.
[11] LGCDP Status Report 2011.
[12] Nepal has seen sporadic high level political efforts to combat corruption. After the 2006 peace agreement there was a brief state led anti-corruption drive, fronted by the national anti-corruption agency (the CIAA). Under political pressure momentum reversed from 2008-11. The necessary legal frameworks and policies have been put in place (including ratification of UNCAC in 2011 and the development of a reasonable national anti-corruption law). The Judiciary have slowly improved their reputation for impartiality regards high profile anti-corruption cases (in March 2011 the Supreme Court upheld a former Minister’s 2004 court conviction for corruption). In 2011, with some political will under a new Prime Minister the CIAA become slightly more active in generating and submitting cases for prosecution (In parallel, the Prime Minister’s Office has promoted some anti-corruption initiatives, including a ‘hot desk/call centre). However, generally national leadership on anti-corruption has been and remains weak. Oversight bodies, such as the CIAA and Office of the Auditor General have been undermined by failures to appoint Commissioners, staff or provide adequate funding. CIAA investigations require participation and a response by government agencies and individuals investigated, which has been regularly lacking. Donor support to the CIAA is therefore current limited.
[13] See World Bank CPIA data on country trends.Public Financial Management (PFM) in Nepal is recorded as below the South Asian average and in the bottom quartile of the World Bank’s global ratings.
[14] 2008 PEFA indicators PI-26, PI-27 and PI-28 on external oversight graded D+, C+ and D.
[15] DFID Nepal Anti-Corruption and Counter Fraud Public Strategy 2012
[16] Nepal: Critical Development Constraints.2009.Manila, Asian Development Bank.
[17] Source 2011 World Economic Outlook
[18] Annexure: PEFA 2006 report.
[19] 2010 Annual Statement of Progress for Fiduciary Risk.
[20] Better quality PFM systems are correlated to lower levels of corruption. In other words, robust PFM systems raise the risk of detection and the cost for bad behaviour. Please note that there is no single, universally-accepted definition of corruption. The United Nations Convention against Corruption (UNCAC) does not contain a specific definition. It rather defines specific acts of corruption that should be considered in every jurisdiction covered by UNCAC. These include bribery and embezzlement, abuse of function, trading in influence, illicit enrichment, bribery within the private sector, but also money laundering, concealment and obstruction of justice. The most commonly used definition is that of Transparency International, who define corruption as "the abuse of entrusted power for private gain". This can mean not only financial gain but also non-financial advantages.
[21] Transparency International, Corruption perception Index: Nepal fell from 146 to 154th among 183 countries surveyed, scoring 2.2 out of 10.
[22] The 2010 Annual Statement of Progress for Fiduciary Risk concludes that the overall level of fiduciary and corruption risks associated with funding through government systems is ‘high’
[23] This is a contested topic. It is increasingly accepted that not all types and forms of corruption reduce poverty (see literature by Mushtaq Khan), but that this is often the exception and not the rule. It is important to target forms of corruption, particularly those that limit access to key social services, that most effect poverty: IMF, 1998, ‘Does Corruption Effect Income Inequality and Poverty’, “high and rising corruption reduces income inequality and poverty by reducing economic growth, the progressivity of the tax system, the level and effectiveness of social spending, and the formation of human capital and by perpetuating an unequal distribution of asset ownership and unequal access to education” Chetwynd, Corruption and Poverty: A Review of Recent Literature, 2003, “corruption does exacerbate and promote poverty, but this pattern is complex and moderated by economic and governance factors. Based on these findings, anti-corruption programs that are crafted to address issues of economic growth, income distribution, governance capacity, government services in health and education, and public trust in government are likely to not only reduce corruption, but reduce poverty as well. Ogboru Ishmael, 2010, ‘The Impact of Corruption On Poverty reduction Efforts in Nigeria’.
[24] In a Gallup survey of public opinion in Nepal conducted in 2011 for the South Asia Democratic Forum (SADF), a lack of political leadership and corruption were by far the most frequently mentioned factors as preventing economic growth in Nepal.
[25] The World Bank managed Multi Donor Trust Fund (MDTF) for PFM reform: is currently focused on i) Strengthening core PFM Systems (including Treasury Single Account, Nepal Public Sector Accounting Standards and the building blocks for a Integrated Financial Management Information System - IFMIS); ii) Strengthening the Office of the Auditor General and; iii) Supporting the public and civil society to demand better PFM systems (The UK provides £3.5m to this programme, 2010-2014).
[26] Ministry of Federal Affairs and Local Development Financial Reform Action Plan (FRAP) 2012.
[27] The DFID Nepal Operational Plan includes in its results targets: - Outcome 3 and related Outputs: An improved PFM system and stronger public scrutiny of government spending (measured by improvements to Nepal’s PEFA assessment and perception surveys); - Outcome 4 and related Outputs: Adverse progress on corruption in Nepal halted and improvements achieved, including in the implementation of the National Anti-corruption (AC) plan (measured by successful prosecutions by the CIAA); - Outcome 5: More capable, accountable and responsive local government able to deliver core functions: including through better local PFM (measured by an increase in the percentage of social audits). The plan envisages a balance in support for ‘supply-side’ interventions (strengthening government systems) and ‘demand-side’ interventions (supporting civil society and citizens to hold Government to account).
[28] The UK and DFID, have a strong comparative advantage in PFM programming in Nepal. DFID has been the leading bilateral donor on PFM reform for over a decade and has built up a strong reputation with Government of Nepal partners. We are the bilateral donor of choice for the Government of Nepal in this sector. We are also a significant sector budget support donor, providing us with direct access to policymaking on PFM reform across major government spend sectors and giving the UK an incentive to manage fiduciary risk for around £20m of financial assistance annually.
[29] According to the World Bank PFM handbook there are three levels of PFM. Level 1: Aggregate fiscal discipline; Level 2: Allocation of resources in accordance with strategic priorities (allocative efficiency); and Level 3: Efficient and effective use of resources in the implementation of strategic priorities. This programme will focus primarily on level 3, with more limited work on level 2.
[30] Coordination and sequencing of support for PFM reforms is critical to achieving results. Government of Nepal leadership is being provided by a PEFA Steering Committee (plus sectoral and local sub-committees) chaired by the Finance Secretary. This system is critical in ensuring strong linkages between reforms at national, sub-national and sectoral level. Donor coordination is being managed by a PFM-donor working group. There is a risk that during the period of design or implementation of this work, Nepal adopts a new system of government. This programme is designed to minimise the risks around this transition, by ensuring that Nepal has the systems and capacity to deliver poverty reducing investments, through its new, likely devolved, system of government. Programme design will need to be flexible to ensure that it can respond to whatever structure is adopted by Nepal. Some forms of corruption, particularly bribery, abuse of function and trading in influence, will not be the primary targets of this business case. These require linked interventions, for example through civil service reform and are not a focus for the DFID Nepal operational plan. They are being targeted through the work of donor partners and within sectoral interventions. Civil service reform, in particular addressing the civil service census, payroll and retirement issues, but also staff motivation and capacity is also a central element to enhancing the role of the state. Improvements in this area are important for PFMA to fully achieve its objectives. There is also an urgent need for Nepal to introduce these reforms in order to secure a stable macroeconomic environment and support pro-poor growth. DFID is in the process of developing a ‘macro-stability support package’. Whilst this will be submitted in a separate Business Case, both cases can be seen as complimentary and part of a coordinated stability package (one more focused on macro and one on micro reforms).

B. Expected Impact and Outcome / We expect that through the provision of the following outputs: / Improved local budget and fiscal management– delivering uniform Village Development Committee (VDC) accounting software used in 1,000 VDCs; performance indicators and guidelines developed and applied for allocating block grants to 1,000 Village Development Committees; improving the effectiveness of internal audit based on local PEFA assessment. / Strengthened sub-national fiduciary risk management at the local level – delivering VDC annual plans coming through ward citizen forums for 1,000 VDCs; risk based management audit conducted in 15 District Development Committees (DDCs), 15 municipalities and 150 VDCs / Enhanced public procurement system – delivering procurement plans of 8 ministries published electronically; procurement officials of 8 ministries and 35 districts trained in public procurement. / Strengthened institutions of oversight and accountability – delivering improved ranking of Nepal in Transparency International's Corruption Perception Index for Nepal from 2.2 to 2.4; percentage of senior civil servants that comply with submission of assets declaration increased from 63% to 90%; / Counter Fraud Analysis and Support for Sectoral Public Financial Management Reform delivering 5 fiduciary risk assessment and 19 annual statements of progress; 7 reports on Public Finance Management reform in key sectors; and implementation of sectoral Public Finance Management reform action plans in key sectors / We will achieve the following outcome: “Enhanced efficiency, transparency, and integrity of public finances at the national, sectoral and sub-national level” –Government of Nepal will recover 20% of the amount disallowed by the auditor-general by the third year. In total GON will recover about £6m during the life of this project. This is estimated based on current exchange rate and on the 49th report of the Office of Auditor General 2012.; 40% of increase of own-source revenues of pilot municipalities using the ‘Municipal Administration and Revenue System’ (MARS); better scope, nature and follow up of external audit of local bodies. / With the resultant impact: “Overall improvement in PFM performance over time”, This will be measured by PFFA assessment where we expect the PEFA scores of all dimensions to be improved by at least one step. / Enhanced PFM and accountability should also contribute to better value for money of the whole DFID programme and aid to Nepal in general, in the medium term laying the ground for increasing use of country systems by donors. / The process is the basic theory of change for the proposed intervention. / See logical framework at Annex C.

## Business Case: Improved Public Financial Management and Accountability

The Appraisal Case

B. Feasible options / The following options have been identified as realistic options, given the identified theory of change, to deliver the desired impact and outcome: / Option 1 – Coordinated delivery of Sectoral and Local PFM Results through 2 components: i) A contracted Service Provider and; ii) the ADB Strengthening Public Management Programme (1st phase August 2012-April 2014 and second phase May 2014-April 2016): / Detailed terms of reference (TORs) for the Service Provider to support sectoral PFM reforms are attached at FLAG C. / Detailed programme design for ADB SPMP are at FLAG D. The programme aims to deliver the required results in terms of PFM reforms at the sub-national level, and includes flexible support to accountability institutions and efforts to mainstream public participation. This programme will be a combination of grant (£13.5m sector budget support) and technical assistance (£4.2m). ADB, in future with likely additional support from the EU, have adequate grant funding, but do not have funds for TA, which will be critical for success. / Option 2 – Delivery of Sectoral and Local PFM Results through the World Bank: through the expansion of the existing WB-MDTF in public finance management. / A third Option entailing delivering through Government was initially considered but discounted as not feasible due to high fiduciary risks (now higher given the loss of some formal Government of Nepal Accountability mechanisms such as the Public Accounts Committee), and will not be part of this appraisal case. / These options are appraised against a counterfactual where UK-DFID maintains its current level and scope of support on PFM reform and building accountability. Under this scenario, the current PFM work carried out by DFID and other donors will continue. This includes the WB-PFM-MDTF, which will likely expand in 2012 (subject to a successful mid-term review) to ensure that comprehensive support is provided to the platform reforms identified at the national level in the GoN PFMRP. In parallel DFID will continue to work on reducing corruption, strengthen accountability and improve PFM through diplomatic and development dialogue, as outlined in our ACCF strategy.
B. Assessing the strength of the evidence base for each feasible option / Support, including technical assistance, for PFM reforms has generally delivered results, although at a slow pace. / The 2010 Review of DFID’s governance portfolio[31] (from 2004/5-8/9) found a net improvement in public financial management in the countries in which DFID engaged in this area of reform. The review also found that components on taxation in particular produced large and measurable increases in tax/GDP ratios and customs revenue and that ensuring that sector projects include an element of governance reform was often critical to their success. / The results that we anticipate delivering through this programme are reasonable and informed by the results achieved and expect from DFID-PFM programmes worldwide. For example, a cross-country study by ODI (2010) showed that on average countries that received more PFM-related technical assistance have better PFM systems[32] (for additional evidence see a detailed case study of the results of PFM reform in Palestine[33]; World Bank research on the impact of medium term expenditure frameworks[34];. / The ODI study also found that a longer period of donor engagement is associated with better performance in upstream (institutional/legal) and concentrated processes. It is understood that this is in part due to donors’ historical tendency to pay more attention to these more accessible reform areas, neglecting downstream processes (sub-national and sectoral reforms) which can take longer to improve. This business case is designed to directly address this tendency. / Evidence around the ability/likelihood of each Option to deliver is based on a mixture of sources including: / Performance appraisals of existing PFM reform initiatives in Nepal: including evaluations of the Government of Nepal Public Financial Management Reform Program (PFMRP) 2009-2012; the 2012 DFID Annual Review of the Local Governance and Community Development Programme (LGCDP) and related ‘Risk Management Minute’ (LGCDP includes a small PFM reform component); Performance analysis of DFID Nepal’s sectoral PFM reform initiatives, evidence of reform captured in Nepal Fiduciary Risk Analysis/Annual Statement of Progress and the last Public Expenditure and Financial Accountability (PEFA) Assessment; The latest performance based assessment of local government functioning (MCMP); / Evidence of similar intervention in Southeast Asia: including the DFID Bangladesh Strengthening Public Expenditure Management Programme and its predecessors.[35] / Evidence of the performance of potential delivery partners to date both in Nepal and in the Region: including the December 2011 DFID Annual Review of the WB-PFM-MDTF. This evidence suggests that the WB in Nepal is currently struggling to deliver on its existing PFM reform portfolio (to date, the MDTF has been slow in disbursing funds, numerous projects of the MDTF have or continue to face significant delays. A major review of the MDTF is due in November / Dec this year). Evidence suggests that if the WB MDTF was to expand, it has better capacity to expand into other ‘upstream’/national level reforms (such as planning and budgeting), than into sectoral and sub-national PFM reform. / For these reasons, the evidence on Option 2 being able to deliver the desired impact is assessed as ‘limited’, whilst the evidence on Option 1 being able to deliver the desired impact is assessed as ‘medium’: / Evidence of Impact / Option 1 Medium / Option 2 Limited
C. What are the costs and benefits of each feasible option? / D. What measures can be used to assess Value for Money for the intervention? / E. Summary Value for Money Statement for the preferred option / This section summarises the in depth economic, political, institution, social, conflict, climate and environment analysis provided in FLAG B ‘Detailed Appraisals’. Please refer to this document for more information. / Aside from the political appraisal, which is neutral, the appraisals conclude that Option 1 is the preferred option. The counterfactual (do nothing option), is rejected given the significant needs and opportunities for impact identified: / The Economic Appraisal of costs, benefits and value for money: In the economic appraisal, Net Present Values (NPVs) and Internal Rates of Return (IRRs) were calculated to test the value for money (VFM) of the two Options. The appraisal concluded that, under several assumptions, Option 1 would deliver the highest benefits compared to Option 2, and hence is the preferred option. / The benefits from the programme include i) improved budget credibility ii) improved revenue collection from local governments and reduced financial mismanagement iii) cost savings in public procurement through the adoption of electronic government procurement (e-GP) and iv) strengthened oversight resulting in reduced corruption. / Examples of quantified benefits include i) Nepal’s annual spend of approximately $750m on procurement of goods works and services. By assuming e-GP will deliver efficiency saving of only 1% of the current spend, this would be equal to $7.5m (£4.7m) annually; ii) In 2008 and 2009, total irregularities in budget expenditure amounted to approximately NRP 1bn, or £7.3m, each year. Even a small reduction of 2% per year as a result of the reforms, would equate to total of £730,000 over 5 years. ADB estimates the reforms supported by the SPMP programme could result in a reduction of financial irregularities at the subnational level in the order of about $5m (£3.1m) per annum, based on the assumption that 50% of reported irregularities at the local level are avoided[36]. / All of the BC costs are towards technical support in the form of high quality consulting and analytical work, capacity support and implementation pilots. 72% of the TA costs provided by DFID are towards supporting the ADB SPMP. The remaining 28% are for supporting bilateral analytical work on PFM to be managed by DFID. The ADB TA is about 42% of the SPMP programme. These TA inputs are substantial and are designed to provide high quality analytical and implementation support. / The institutional Appraisal: The evidence of fiduciary risk and inefficiency in government spending shows that ADB’s proposed programme to support local level and sectoral PFM is crucial. Through previous work, ADB has strong credibility and a track record of supporting decentralization, local governance and local PFM reform in Nepal (ADB is the designated by LGCDP DPs as the lead in financial management working with MLD and supporting the implementation of the FRRAP). An emerging division of labour, overseen by the IDPG-PFM group, supports a focus for the WB as the donor lead on national level PFM reform and the ADB as the donor lead on local level PFM reform. / Sectoral PFM tends to ‘fall through the cracks’. Although some sectoral mechanisms provide limited support and the WB is looking to support some sectors, work tends to fall to the bottom of a long priority list. Getting one contracted service provider able to provide support across sectors is institutionally more efficient and can ensure consistency in approach and level of support. The contracted service delivery model for Nepal has worked well for discrete tasks such as the bundling of FRA/ASPs as well undertaking analytical work such as on PETS / Option 1 is assessed as institutionally more efficient and more likely to deliver the desired results. Option 1 should ensure that World Bank, ADB and service provider have a sensible and meaningful division of labour, which can be joined up effectively, through the government and donor coordination mechanisms, to improve Nepal’s weak PFM systems. / The political appraisal: Politically neither option is necessarily better or worse. Either option will have to manage potentially major political challenges. This programme is likely to be affected by political instability over the next 1-2 years in Nepal. As a result any major financial management policy reforms or legislative changes (such as enabling the auditing of VDCs by the OAG) that require Cabinet or Parliamentary approval may not be completed. In addition there are huge uncertainties about the move to federalism (the number of provinces, future inter-governmental revenue and expenditure assignments and service delivery responsibilities) that the programme will need to respond to and help prepare for. Finally, local government in Nepal is working in a political vacuum as local elections have not been held since 2002 meaning informal influence of political party members will likely remain high, potentially undermining technical moves to strengthen resource allocation at the district and village level, and other anti-corruption measures. / The Conflict Appraisal: Expected improvements in public service delivery combined with more transparent procurement and strengthened oversight and accountability could help reduce grievances related to perceived exclusion from state services, and help strengthen state-citizen relations. The expected strengthening of local government PFM capacity will be an essential step in preparing it for devolved/federal responsibilities. But alongside these expected gains if the programme fails to deliver it could reinforce public scepticism about the state. / The flexibility offered by the twin track approach of Option 1, combined with the proven capacity and track record of the existing ADB SPMP, suggest that this option would be the most likely to deliver expected results, maximize the programme’s peace building potential and manage conflict related risks. Option 1 is therefore the preferred option. On the counterfactual whilst this would avoid DFID exposing itself to the identified conflict risks, it is considered that the opportunities for contributing to essential peace building and state building processes outweigh the conflict risks associated with the programme. This option is therefore not recommended. / The social appraisal: In Nepal, PFM systems are more important for poor women and socially excluded populations as they are less able to substitute the services offered by the public sector. Bottom up planning and budgeting approaches, whilst a good start, are far from inclusive. The lack of gender responsive budgeting and planning delays the process of attaining equality. Decentralized governance offers some space for the poor and excluded to put forward their issues, however this space has been captured by local elites. Community based organizations of the poor women and socially excluded groups can be empowered and mobilized to hold state accountable and serve as a link between the state and excluded citizenry. / Option 1 is likely to best enable the poor and socially to overcome the barriers they face while accessing public services. This flexibility offered by the contracted Service Provider should enable responsive capacity building activities for the poor and excluded, to support supply side capacity and system development. The ADB Strengthening Public Management Program will be able to improve public service delivery and bring in issues around women and excluded groups to the heart of system design. Option 2 is weaker given the World Bank’s lower capacity to work at the local implementation level. / The climate and environment appraisal: The assessment indicates that this project is rated C with limited, direct climate and environment implications/opportunities. Although the intervention will have limited direct environmental impacts, it does provide opportunities to improve the financial performance within key sectors managing environmental resources. Consequently from a Climate and Environment perspective the option that is likely to provide the most flexibility in terms of supporting specific sector activities will be preferred. From analysis this appears to be option one. / Summary of recommendations from the appraisals to be addressed during implementation: (responsibilities and timings allocated in Flag B) / Coordination: ADB to show growing leadership on local PFM; ADB to effectively link their national level work on procurement reforms with procurement reform at the local level; DFID to support and encourage the ADB, WB and service provider to coordinate efforts, through the government’s PFM reform mechanisms (PEFA secretariats) and through the International Development Partner Group IDPG-PFM group; / Monitoring and Evaluation: DFID to monitor and ensure that the work-plan and products of the service provider are owned by the stakeholders of the individual programmes to which they are linked; ADB to monitor Fiduciary Risk Reduction Action Plan MLD-FRRAP implementation on a quarterly basis and share progress with DPs; DFID to measure the success of the technical assistance provided in terms of effective service delivery, including by satisfaction of those using the services, particularly men and women from poor and socially excluded groups / Technical Assistance: ADB to work towards a sustainable Technical Assistance (TA) support mechanism, largely contracted by MLD (with quality controls) and not dependent on International Agencies; ADB to ensure coherence from and learning from the previous UN led TA (ADB to undertake an assessment of the UN-TA) ; ADB TA to be mobilized by October; / Constitutional Reform / Federalism: The programme to monitor the policy directions on local governance restructuring carefully and be ready to adopt and adapt to the changes. For example, The Ministry of Local Development has very recently been renamed as the Ministry of Federal Affairs and Local Development. In this light, the programme may need to be flexible about supporting elements of fiscal federalism which may be implemented by MLD. This programme needs to link with and benefit from the technical work on fiscal federalism through the PMO. In particular, there may a greater role for Local Bodies Fiscal Commission (LBFC) which is responsible for annually undertaking the MC/PM for local bodies to provide to formula-based funds to local bodies. The programme should consider keeping funds for supporting the LBFC; DFID to review how the budget execution plays out in FY 12/13 and any implications for the programme; / Communications: The ADB programme to develop a proactive communications strategy to build public trust and participation in relevant processes (such as public audits); / Exclusion: ADB to complete a careful analysis of the structural and attitudinal barriers of the service providers running and managing the system at all levels; ADB to conduct research to deepen our understanding of where the PFM system fails to demonstrate accountability (differently for men, women and socially excluded groups) and to identify corrective measures; Seek to design responsive capacity building activities for poor and excluded groups in parallel to efforts to support supply side capacity and system development / Climate and environment: Through the sectoral support, i) programme specific activities should be included to implement PFM, accountability and anti-corruption action plans in forestry and climate change; ii) support should be provided to help Nepal develop its emerging climate finance management systems and institutional structures. The programme should include a logframe indicator that will ensure progress on these issues are monitored.
[31] DFID, “A Review of DFID’s Governance Portfolio 2004/5 – 2008/9”, September 2010. One third of DFID’s direct governance investment was through budget support (£931m), with budget and financial management the main focus. Other major areas of investment included public financial management (including taxation) at £365m.
[32] De Rienzo et al (2010), ‘Evaluation of Donor Support to Public Financial Management (PFM) Reform in Developing Countries. Analytical study of quantitative cross-country evidence’
[33] # P.17 DFID Draft interim guidance on undertaking Cost-Benefit Analysis of Public Financial Management Projects.
[34] p.22, DFID Draft interim guidance on undertaking Cost-Benefit Analysis of Public Financial Management Projects.
[35] See QUEST document (3361554) ‘Covering Minute on SPEMP annual review 2011’ and document: (3361553) SPEM Annual Review 2011.
[36] In its 2008 Annual Report, the OAG has found irregularities in local bodies of about 861 million rupees or around $10 million. This is arguably only a small fraction of total irregularities at the local level, as the OAG only audits up to the district level, and its depth of its coverage at this tier of government is uneven.

## Business Case Improved Public Finance Management & Accountability

The Commercial Case

Direct procurement
A. Clearly state the procurement/commercial requirements for intervention / The first component of this programme will be delivered by a service provider, competitively contracted, through the DFID PFM framework arrangement, against the terms of reference (TORs) attached at FLAG C. / We expect high value for money for this component. For example, DFID Nepal used to contract multiple, separate, fiduciary risk assessments and annual statements of progress annually. We now intend to select a single supplier for the operational plan period. This approach will enable the supplier to reduce incidental costs and improve quality.
B. How does the intervention design use competition to drive commercial advantage for DFID? / As above, the first component of this programme will be delivered by a service provider, competitively contracted. The TOR for this component has been cleared with procurement group and clear deliverables have been specified. Procurement group has agreed to use an existing PFM framework arrangement for the procurement. The procurement group will run a mini competition from among the suppliers in the framework and we expect everyone in the framework to be interested to bid ensuring strong competition. / Component 2 will be delivered through a memorandum of understanding with the ADB. By utilising ABD and not extending an existing WB programme, DFID is encouraging to improve the performance of multilateral partners in line with the multilateral aid review.
C. How do we expect the market place will respond to this opportunity? / We expect that all vendors in the central DFID PFM Framework will compete for the contract. / We anticipate that having 3 major service providers working on PFM in Nepal (the WB, ADB and our contracted service provider) will increase competition to deliver results to gain future funding, especially if work-streams are carefully coordinated and monitored.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Costs to DFID are expected to be significant reduced as this contract represents a clustering of what would have been an estimated 30 separate contracts, enabling the supplier to drive down price by minimising staffing, travel and accommodation costs. It is also expected that this clustering will drive up quality of work, as the service provided is able to build on each piece of work. The service providers role is detailed at FLAG C. Evaluation criteria will be developed based on the draft criteria in the logical framework at FLAG E.
E. What is the intended Procurement Process to support contract award? / As above, for component 1, DFID Nepal will utilise the existing Framework Agreement. The procurement group will run a mini competition. DFID Nepal will evaluate the bid technically and the procurement group will do the financial evaluation. DFID Nepal will identify the evaluation criteria and will agree with the procurement group.
F. How will contract & supplier performance be managed through the life of the intervention? / The contract for component 1 will be performance based. The service provider will be expected to submit an inception report including the detailed work plan for this component. Contract performance will be monitored against monthly invoices submitted by the supplier. DFID Nepal will request for monthly updates against the work plan and will monitor the supplier accordingly / Overall programme performance, including for the ADB component, will be monitored through a nested logical framework (at FLAG E), which builds on the ADB-SPMP design and monitoring framework.

Indirect procurement
A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / Component 2 will be delivered through a memorandum of understanding with the ADB. ADB have been selected as the implementing partner for this component based on their track record; capacity and mandate (see detailed appraisals at FLAG B). ADB will be providing USD21.5m in grants and loan to the government of Nepal to undertake the programme. UK funds will provide technical assistance, to support programme delivery.
B. Value for money through procurement / DFID expects that ADB will obtain the best value for money for all procurement using their own financial management and procurement procedures for this project. DFID will be part of the committee that selects the TA suppliers and will ensure that economy, efficiency and effectiveness will be achieved during the procurement process and during the implementation of the programme. A procurement self-assessment questionnaire has been sent to ADB and DFID Nepal will follow up on the assessment as necessary. / ADB has procurement guidelines for both procurement of goods and for consultants. They are based on five basic principles: / (a) the proceeds of ADB financing can be used only for procurement of goods and works supplied from, and produced in, member countries of ADB; (b) the need for economy and efficiency in the implementation of the project; (c) ADB’s interest in giving all eligible bidders from developed and developing countries the same information and equal opportunity to compete in providing goods, works and services financed by ADB; (d) ADB’s interest in encouraging the development of domestic contracting and manufacturing industries in the country of the borrower; and (e) the importance of transparency in the procurement process. / Open competition (international and national) is the basis for efficient public procurement. ADB’s procurement guidelines describe various methods of procurement and the circumstances under which their application would be appropriate. The particular methods that may be followed for procurement under a given project are provided for in the financing agreement. These procurement guidelines apply to all contracts for goods, works and consulting services financed in whole or in part from loans, TAs or other grants or ADB-administered funds implemented by ADB or a borrower. To foster competition ADB permits bidders from all eligible member countries to offer goods, works, and services for ADB-financed projects.

## Business Case: Improved Public Financial Management and Accountability

The Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total cost of this business case is estimated to be £8m, over 4 years (FY 2012/13 to FY 2015/16). This covers the 3 remaining years of the operational plan and 1 year beyond. This spend profile was selected to enable DFID Nepal to deliver on the results promised in the Operational Plan, whilst best harmonising with the end dates of projects that may be funded through this Business Case. / Funding for this results area, in the current Operational Plan was estimated at £10.55m. With £3.6m already allocated to the current phase of the PFM MDT, £6.95m officially remains un-allocated. The total cost of this project requested from the current operational plan (to FY 2014/15) is estimated to be £6.45m (an average of £2.15m per financial year). / The detailed spend projection is below. / FY 12/13 FY 13/14 FY 14/15 FY 15/16 Current OP Total in this BC Total Additional Requested for future OP Total in this BC / (current OP period) (current OP period) (current OP period) (next OP period) / Funding to the ADB managed SPM Programme £2.20 £0.00 £2.00 £0.80 £4.20 £0.80 £5.00 / Funding to in internationally procured contractor for analysis and additional sector support £0.75 £0.75 £0.75 £0.75 £2.25 £0.75 £3.00 / Total £2.95 £0.75 £2.75 £1.55 £6.45 £1.55 £8.00 / Note: All figures in million pounds
B. How will it be funded: capital/programme/admin? / Both components are confirmed as programme spend resource departmental expenditure limit (RDEL).
C. How will funds be paid out? / For component 1 (contracted service provider) implementation payments will be pre-financed by the supplier and reimbursed by DFID, based on proof of delivery and expenditure. DFID Nepal will monitor the performance of the supplier based on the agreed work plan before the reimbursement is made to the supplier. / For component 2, (ADB), tranches to the GON will be done based on the tranche agreement in the memorandum of understanding, based on GON-ADB agreement. However quarterly payment will be done for the technical assistance managed by ADB.
D. What is the assessment of financial risk and fraud? / For component 1 (contracted service provider) given direct implementation, and if the actions for contractors, identified in the DFID Nepal ‘Anti-Corruption and Counter Fraud’ strategy are implemented (e.g. awareness raising of contractors) fiduciary risks and fraud risks are assessed as low. / For component 2, (ADB), given use of ADB systems, but recognising that government could, through the life of the programme, play an increasing role in selecting and contracting technical support, corruption and fraud risk is assessed as medium.
E. How will expenditure be monitored, reported, and accounted for? / For component 1, the supplier will prepare invoices and accompanying progress reports, detailing progress on key outputs on which to base DFID’s reimbursements. The service provider will also prepare more detailed progress and financial reports on a quarterly basis. The report will include progress on activities, expenditure, updated cost projections and progress against the log frame indicators. A formal presentation of the quarterly report will be done to DFID during quarterly meetings. The actions agreed and revised progressed indicators will then be used by DFID as further delivery indicators against which to base payments. In addition, the supplier will conduct an annual audit. Copies of audit reports will be submitted to DFID. / For component 2, quarterly meetings will be held with ADB and government partners on the technical assistance component as well as for the whole programme, where detailed progress and financial progress will be updated by ADB against log frame indicators. Funds will be released to ADB based on the quarterly forecasts and previous quarter’s expenses for the ADB managed TA component. / DFID Nepal will conduct annual reviews and project completion reviews together with ADB and GON.

## Business Case: Improved Public Financial Management and Accountability

The Management Case

A. What are the Management Arrangements for implementing the intervention? / To deliver the results targeted in this business case requires close coordination of and government of Nepal leadership of reform efforts. In order to support and develop this, as noted in the institutional appraisal, the UK will work to ensure an active PFM-IDPG (the donor coordination mechanism) sub group that meets regularly and is co-chaired by the Government of Nepal. / DFID will also work to empower and press for Government of Nepal leadership by ensuring that each component (and all interventions) are coordinated through the GoN PEFA Steering Committee, chaired by the Finance Secretary and supported by a GoN PEFA Secretariat, at the Nepal Financial Comptroller Generals Office (FCGO). / The combination of GoN and donor coordination mechanisms should ensure that overlaps and minimised, lessons learnt accross interventions and reform initiatives move at pace. In addition to these general approaches to management arrangements there are specific arrangements for each component: / For component 1, DFID Nepal will manage an internationally procured contract. The lead Adviser will be responsible for overall management and technical oversight, assisted by the Public Finance Programme Manager. The Governance and Security Programme Manager / Officer will be responsible to ensure compliance with DFID Programme Cycle Management procedures. This core team will draw in technical support where required on social, conflict and economic issues, backed up by the Team Leader and the Senor Programme Manager of the governance and security team. / DFID will contract a supplier to manage the internationally procured contract through a mini competitive bidding process on DFID framework arrangement, The detailed TOR is at FLAG C. / Day to day, as written in the TORs for this component, sectoral teams in DFID Nepal that wish to utilise the support offered by the service provider, will appoint a lead advisor and lead programme officer to manage the work (including to draft work-plans; seek sign-off on these work-plans from the Public Finance Programme Manager; manage sectoral relationships with other donor partners and GoN partners). / For component 2, the Nepal Ministry of Finance (MOF) will be the Program’s Executing Agency (EA). At the policy level, the Program will be guided by the PEFA Steering Committee chaired by the MOF Secretary. The PEFA Secretariat at the FCGO will serve as the Program Management Unit (PMU) and provide (i) technical guidance, (ii) monitor and review implementation, and (iii) ensure coordination with the PFM MDTF and the PFM Thematic Group. The implementing agencies (IAs) will be the Ministry of Local Development for Components 1 and 2, the Public Procurement Monitoring Office (PPMO) for Component 3, and the National Vigilance Centre (NVC) for Component 4. The PPMO and NVC will each establish a program implementation unit while the MLD will utilize the existing PMU for LGCDP. These project implementatino units (PIUs) will (i) supervise implementation of component activities, (ii) prepare and submit progress reports, and (iii) coordinate implementation with the PMU. / DFID Nepal’s 2012 Evaluation Strategy recommends that between 2-5% of the overall project budget should be allocated to evaluation. This level of budget is available through component 1. An impact evaluation will be carried out in FY 15/16, funded through component 1. If agreed with the government of Nepal, this evaluation will assess both our sectoral work and the WB and ADB PFM reform programmes.
B. What are the risks and how these will be managed? / Risks and mitigation measures are identified at FLAG F. / These will be written into DFID Governance and Security Team’s and DFID Nepal’s overarching risk matrices and monitored through weekly Governance and Security Team meetings and DFID Nepal Leadership team risk appraisals, as well as through annual programme reviews.
C. What conditions apply (for financial aid only)? / Not applicable. For component 1, all funds will be advanced by the service provider and reimbursed by DFID. For component 2, funds will be transferred to ADB.
D. How will progress and results be monitored, measured and evaluated? / At the basic level, monitoring and evaluation will be completed through annual reviews against the programmes nested logical framework. This will be supplemented by a possible mid-term evaluation, government of Nepal led evaluation (through the PEFA Secretariat, including the planned 2013 PEFA assessment).
Lograme / The Quest No of logframe for this intervention is 3605773