Type of Review: Annual Review

Project Title: Africa Enterprise Challenge Fund South Sudan Window
Aries Ref: 40063178
Date started:	September 2011
Date review undertaken: 16 November – 07 December 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID has committed £6m to the Africa Enterprise Challenge Fund South Sudan Window (AECF SSW) to provide support to selected enterprises in the agribusiness and agriculture sector that will have an impact on the rural areas of South Sudan. / An Accountable Grant of £6m has been signed between DFID and the Alliance for a Green Revolution in Africa (AGRA[1]), a non-for profit organisation based in Nairobi with effect in October 2011 until December 2014. AECF is a special partnership initiative of AGRA. / The Fund Manager (FM) of the AECF SSW is KPMG International Development Advisory Services Africa, based in Nairobi. A dedicated Adviser with the right experience was recruited by the Fund Manager to lead the SSW. The AECF SSW Team is based in Nairobi at AECF Head Office and has travelled extensively in South Sudan for the marketing, relationship management and assessment of the Business Plans. / AECF SSW was launched in October 2011 with a series of well-attended events, with the Minister of Agriculture of the Government of South Sudan (GoSS) in London (with DFID Secretary of State) and Johannesburg at a regional agriculture conference. It was accompanied by a promotion campaign in South Sudan and in the Region targeted at potential investors. / This first year of operation has been focused on launching the web-based competition (Oct-Dec 2011), on project selection (Jan-May 2012), on due diligence on potential grantees and on managing the approval process by AECF Investment Committee (IC) (May-Aug 2012). / Six projects have been approved that represent US$4,4m of total commitment, an average of $0.7m per project. Matching funds of $5.4m (a leverage ratio of 1:1.26)[2] will be provided by project sponsors. Contracts with grantees should be signed by the end of January 2013 and some grant disbursements are expected by March 2013, provided the Fund Manager is satisfied with the grantees’ efforts to bring their financial management systems to standards. / At 29 November 2012, the total disbursed by DFID on the Programme (Aries code 202848 – PO 40054233) was £349,269 and £90,105 was under process by DFID systems, representing the management fee paid in quarterly arrears, in accordance with the terms of the accountable grant. / Purpose and scope of this Annual Review / The aim of this first Annual Review undertaken between 16 November and 06 December 2012 by an independent consultant is “to judge the progress made by AECF over the past year and to inform DFID’s decision-making on the future of this programme”. / Beyond the usual assessment of achievements and performance progress against the project proposal and logframe (recently updated and still under discussion between DFID and its partners), this review will make recommendations whether DFID should continue funding the South Sudan Window as planned. / The South Sudan Window cannot be interpreted in isolation from the global AECF Programme. This South Sudan Window is the 11th competition window launched by the AECF in Africa and is benefiting from a solid experience that has been recently assessed by DFID Africa Regional Department (ARD) and other donors and whose performance is highly praised by DFID. / AECF is managing approximately $200m from a dozen donors and impact investors, including £55m of funds committed by DFID. It has completed 16 competition rounds between 5 June 2008 and 30 June 2012; received 4,456 concept notes; assessed 318 business plans and approved 87 grants for an amount of $62.4m. / 187 concept notes submitted / 116 concept notes eligible and assessed / 41 concept notes presented to Committee / 15 Concept notes approved for next stage / 11 Business Plans assessed / 6 Projects approved by Committee
[1] The reader can find a list of acronyms in appendix
[2] Source: Draft minutes from the August Investment Committee. More detail in the commercially sensitive options paper.

What are the expected results?
The Africa Enterprise Challenge Fund South Sudan Window supports private enterprises that will contribute to the expansion of an innovative and commercially viable agricultural and agribusiness sector that benefits the rural poor in South Sudan. / This programme expects to benefit: / 50,000 farmers/out-growers and clients directly and between 250,000 and 350,000[3] when their family members are included (data on household size in this new country need to be confirmed); / The positive income effect of the projects on the farmers involved will be at least 25% of their current income; / over 330 new jobs will be created in the companies supported by AECF SSW; / 50% of the businesses/business ideas supported will be profitable by the end of Year 4; / The demonstration effect from the success of these projects will encourage other businesses to invest in the agriculture sector in South Sudan / These are the objectives based on the submission approved by DFID Head of Office. They have been included in a tentative logframe that is currently fine-tuned between DFID, AGRA and AECF. / It is to be noted that following DFID-commissioned mid-term review, AECF will move towards a results framework based on the recommendations of the DCED (Donor Committee for Enterprise Development), to capture better AECF wider impact. / Recommendation: Measuring results will need to be coherent with the standards applied across all DFID-funded windows of the AECF, to facilitate monitoring and assessment of the performance of AECF Fund Manager. Recommendations in this review may be superseded by any global agreement currently discussed by DFID ARD and AGRA on aligning AECF M&E on DCED best practice.
[3] There is a pending discussion between AECF FM and AGRA that prefer a cautious 5 people per household across the AECF portfolio, DFID initial estimate of 7 people per household based on UN data in the North and DFID Livelihood Advisory Cadre that recommends 6 people

What is the context in which UK support is provided?
The investment thesis remains powerful but the macro-economic profile of the Country has become more challenging, impinging on the private sector actors targeted by the Programme: / 1. South Sudan is a new country with vast opportunities to tap, especially in the agriculture sector. / - South Sudan can rely on abundant natural resources, especially in the southern provinces; it is not densely populated and land is available for new ventures; / - GoSS is “keen to cultivate and nurture a conducive investment environment in the country”. Private sector investors are protected under The Investment Promotion Act of South Sudan of 2011. / - South Sudan can attract the type of investors who want to benefit from the first mover advantage and have an appetite for high risk/high reward. / - It is close to the neighbouring countries of the East African Common Market. During this review, the EAC Heads of State have received a technical report on South Sudan candidacy[4] and decided to postpone its membership until the country addresses certain challenges, notably in terms of weak institutional capacity. / 2. However challenges remain immense and the analysis done in the DFID Submission remains valid. / Despite progress since the Comprehensive Peace Agreement (CPA) signed in 2005, the economy remains very much “post-conflict” in its nature and, confirmed by surveys such as the World Bank Doing Business in Juba 2011, is affected by: / - weak private sector capacity; / - lack of infrastructure, and especially poor road and transport network to serve agriculture areas; / - incomplete regulatory framework. GoSS has low capacity to put in place the policies and institutions that will create an enabling environment for private sector investors and owners. / To these well-rehearsed factors must be added the negative perception about farm work amongst the population, especially the young, and the low productivity of the labour force. South Sudan labour cost is significantly higher than its neighbours. / 3. DFID and GoSS agree as well as major donors that the agriculture sector is key to development and poverty alleviation and that the private sector has a unique role to play to drive a development strategy – This was reiterated by the Government when they inaugurated the second Agricultural Trade Fair that took place in Juba on 27-30 November, during this review and that we visited. / - 82% of the population live in rural areas and work in agriculture; poverty ratio is 55.4% (2009 World Bank data); / - It is a sustainable alternative to the oil sector that represent 70% of the GDP , 98% of revenues and will be depleted in 7-8 years; / - The country is affected by severe food shortages and a vibrant agribusiness sector is an obvious exit strategy to short term emergency and humanitarian aid. / 4. However the Investment Climate has significantly deteriorated since the appraisal of the Programme by DFID and its partners / - the decision by the GoSS to shut the oil pipeline and the subsequent “austerity” measures have dampened demand and created foreign exchange rationing [as well as inflation that is estimated at 22% by the latest World Economic Outlook Report; an increase of public internal debt with private sector agents]; / - some geographic areas have witnessed security tension, detrimental to free movement of goods and people, and to long term investors’ confidence. This has concretely impacted on a few possible grantees of the AECF SSW. / - the GoSS has been distracted from its focus on reforms, notably land reform policies, and on much needed investment in rural infrastructure; / In conclusion this degraded (dis)enabling environment however does vindicate the urgency of programmes like AECF that can accelerate an import substitution strategy and reduce dependency on humanitarian assistance. / Recommendation: The analysis at appraisal was pertinent. / DFID South Sudan can be praised for its proximity to key players involved in the agriculture sector. It shall remain alert to updated information that will come from the World Bank in 2013: analytical work done on agriculture value-chains and an updated Doing Business Report, and adjust the Programme risk matrix accordingly.
[4] ### Section 11 of the Communiqué of the 14th Ordinary Summit of EAC Heads of States: the summit received progress report on the application of the republic of South Sudan to join the East African Community. the summit directed the council of ministers to commence negotiations with the Republic of South Sudan while taking into consideration the findings in the verification committee’s report.

## Section A: Detailed Output Scoring[5]
[5] At the time of this review, the definitive logframe has not been fully discussed and approved amongst the 3 key partners, DFID, AGRA and AECF Fund Manager. This Review is based on the consensus so far and will comment from time to time on the need to agree key changes before the next review.

Output 1: Innovative agribusiness provided with finance and credit facilities required to get off the ground
Output 1 score and performance description: C output substantially did not meet expectations / 6 projects out of 11 intended have been approved and the time from launch to first disbursement, likely in February-March 2013, will be 14-15 months rather than 8 months expected.
Progress against expected results: So far the Programme has achieved half of what was expected in terms of volume of business, quality of applications and timeliness. Some remedial actions can be taken but they are unlikely to redress these initial faults before the next annual review. / The Programme initially started well against its initial work plan. AGRA took the risk to fund the initial stages of the Window launch before the legal documentation was completed; and the performance of the Fund Manager exceeded DFID expectations in terms of time-to-market with a launch of the competition in October and its conclusion by mid-December. This resulted in a high level of concept notes, 181 were received vs. 150 expected. / However at the later stages of the rigorous selection process adopted by the Fund Manager, weaknesses and constraints that had been probably under-estimated revealed South Sudan challenges, especially amongst the medium sized, South Sudanese owned and managed, businesses that have formed the core of the proposals. / A certain number of reasons have been advanced by the Fund Manager that have been cross-referenced with other managers of donor-funded agriculture and agribusiness facilities (USAID and Dutch mainly) and private equity investors: / - Average quality of the SSW proposals is below AECF average recorded in its other facilities, even compared with the other existing conflict-affected window at the time, Zimbabwe, and subsequently verified with the new Post Conflict Facility that works in Sierra Leone, Liberia, DRC and Somalia/Somaliland. / - The pool of entrepreneurs is shallower and could be explained by one or several of these factors: lower level of education, especially in numeracy and business skills; few role models from the diaspora; limited exposure to large-scale farm estates before and during the civil war. / - A negative perception about farm work amongst the population and especially the young. Many stakeholders involved in concrete projects face challenges in terms of recruitment, motivation, productivity and retention of farm labour which put South Sudanese enterprises at a competitive disadvantage with their neighbours. / - A weak financial culture with a poor understanding of modern financial planning (forecasting and budgeting) and monitoring compounded by limited professional resources in Juba that entrepreneurs can tap. A seasoned Fund Manager commented to the Review that South Sudan did not have the “ecosystem” of accountants, auditors, lawyers and business consultants found in the Region. / - Potential investors known of the AECF Team and who had shown some initial interest in the SSW concept did not materialise, especially multinational companies or powerful family regional groups (apart one exception from Egypt). / The result is that due diligence needed to bring the concept notes to AECF standards has taken more time and resources than expected and that the initial good pace at the early stage is now drifting. / Recommendation: The logframe needs to be amended. This can be based on the exchanges between DFID, AGRA and AECF Fund Manager since October 2012 but not yet concluded: / 1.“Years” need to be clearly defined for the initial year and then subsequent milestones; either based on the date of the launch (i.e. Oct - Sep); based on AECF reporting periods (i.e. July-June) or based on DFID Financial Year (April-March); / 2. Due to the late implementation of the first six projects and lag time of availability of data from the M&E system, it is recommended that a milestone 1 is measured from 31 March 2013 and a milestone 2 from June 2014; / 3. The original logframe included the fund raising and launch of a second window sometime after 2014. This opinion of the reviewer would be to drop it from this Programme to focus AECF SSW partners on the success of current activities. However for presentation and communication purposes in South Sudan, it may be deemed preferable to keep such an option as an aspiration. / Impact Weighting (%): 35% / Revised since last Annual Review? No – first review / Risk: Medium / Revised since last Annual Review? No – first review / The reviewer proposes a revision to “High risk” due to a combination of internal factors (the lower quality of the proposals compared to AECF average portfolio and the acknowledged weaker capacity of SSW selected grantees) and the significant increase in the country risk perception that likely include “providers of finance and credit facilities” in the agribusiness sector.

Output 2: Increase in commercial private sector investment in agriculture and agribusiness
Output 2 score and performance description: B = Output moderately did not meet expectation Businesses supported by the AECF SSW have committed to mobilise $5.3m (vs. $7.2m /£4.8m expected)
Progress against expected results: The six approved projects could be on track provided the timetable is amended in accordance with the delay in disbursing the grants. / The decision by the Investment Committee not to lower its standards and to maintain a high selectivity in initial approved projects means that increased investment from the six approved grantees should be meeting expectations raised in the DFID submission, at the lower end of the $7.2-21.6m (£4.8-14.4m) range. / There is a variation of promised “matching funds” from the grantees, coming from an injection of equity from the business shareholders; some private equity partners; mobilisation of bank facilities or possible leasing of farm machinery and other sources such as advances from a diversified holding company. The Fund Manager will need to be strict in assessing in-kind contributions that can be more easily over-inflated. / Recommendations for the logframe, once the dates have been amended (see output 1) / - Indicator 1 on amount of finance leveraged: the milestones look fine, even with the current 6 projects only. However this must be verified by the Fund Manager grantee by grantee as in-kind matching may be considered satisfactory from time to time whereby DFID and AGRA want to capture mainly “new money” coming into South Sudan. / - Indicator 2 on sustainability: DFID, AGRA and the AECF Fund Manager should be able to capture through the MIS a proxy indicator to agree on (such as break-even point or cash-flow positive) rather than “profit” if this cannot be relied upon. However this change of indicator should be vetted by AECF Global Lead Adviser to avoid confusion across other windows. / - The founding partners should review what could be considered a success for AECF SSW. Due to the small sample of approved projects, the low diversification of the portfolio (two projects are in the same activity, seeds) and a more challenging investment climate (3 projects out of 6 becoming sustainable?). / Impact Weighting (%): 35% / Revised since last Annual Review? No – first year / Risk: Medium / Revised since last Annual Review? No / Recommendation: The medium risk rating could be amended to high depending on chosen options for the remaining of DFID funding: will the grantees improve their management and financial systems? Will the in-kind matching funds be properly assessed and accounted for? Will the MIS capture the trigger when the businesses become profitable (or equivalent)?

Output 3: New business models demonstrated
Output 3 score and performance description: A Output meets expectation / The average innovation score for approved business plans is 4.4, above the 3 benchmark
Progress against expected results: / This reviewer has requested an analysis of the Investment Committee “innovation scores” of all projects approved at Business Plan stage. However it seems that there has not been consistent scoring amongst markers. / Beyond the score remains the principle that investing in South Sudan agribusiness sector is innovative and can have a demonstration effect if appropriately communicated. All grantees who have been met during the review (5 management teams and business owners) have shared their willingness to promote the AECF, investment in South Sudan and to actively participate in organised public private dialogue. / Recommendations: Some adjustment in the wording of both indicators may be needed after the decisions of the new AECF Board Committee that meets on 3-5 December. / 1. In the context of South Sudan, the second indicator (innovation scoring) may be too restrictive in capturing the AECF SSW impact. The reviewer suggests a dialogue between AECF and DFID Lead Advisers and M&E experts on the pro-poor dimension of the AECF SSW using the M4P methodology (Making Markets Work for the Poor) as a guide: can poor people benefit as consumers because the AECF grantees will bring better quality, more diversity of foodstuff sourcing and competition / lower prices? / This will link with DFID submission that embraced the AECF within DFID food security agenda. / 2. Future Annual reviews will assess the use of the £158k budget that has been ring-fenced to disseminate case studies, best practice to communicate on the AECF impact. But there is currently a debate about the ownership of such an output: AGRA or even DFID rather than the Fund Manager? / . / Impact Weighting (%): 30% / Revised since last Annual Review? No – first review / Risk: Medium / Revised since last Annual Review? No – first review

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes / This is the first review since the Programme has been approved with a tentative logframe. Negotiations to finalise the logframe between DFID and its contracting party, AGRA, have not been completed. / The AECF SSW Fund Manager, concretely delivering the outputs of the logframe has provided comments that have been cascaded to AGRA, but not to DFID Team yet. The 3 partners should be able to agree now on a common logframe. / 1.2 Overall Output Score and Description: / B - Outputs moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / The feedback from beneficiaries (we met 5 out of 6 approved grantees but we have not interviewed applicants who have been rejected) is largely positive. / Even though beneficiaries mention the efforts (a few the “pain”) that are needed to abide by a rigorous AECF process they acknowledge this grant money must follow strict rules and cannot be wasted; they all approve the discipline it brings to their own understanding of their business plan and that they have a duty to make it a success so that it can benefit other South Sudanese bidders. / They also praise the interaction with the Fund Manager’s team, its expertise and availability; the chance to defend their project in person in front of the Investment Committee. They nevertheless regret that the Fund Manager has no permanent staff in Juba. / No one complained about the proportion of pure grant/reimbursable grant, underlining that it will allow replication and for more South Sudan businesses to benefit from recycled funds. / Some beneficiaries commented on two criteria that may have inhibited young and promising but not yet established entrepreneurs: the 3-year proven track record and the 1:1 matching grant rule.
1.4 Summary of overall progress / Overall progress during this first year is disappointing when compared with first milestones and expectations and will remain so until the first grant agreements are signed, disbursed and the first achievements of the AECF SSW grantees can be measured.
1.5 Key challenges / The Programme had to face unexpected exogenous factors: / a weakened macro-economic situation since the decision to shut the oil pipeline, with lower growth, lower public investment in key infrastructure and higher inflation, and / a pace of reforms that is slowing down, mainly due to low institutional capacity / But also faced more severe constraints than expected probably due to the dire available information on market conditions and entrepreneurs’ skills: / a lack of appetite from solid multinational companies who still prefer sitting on the fence or develop alternative strategies than investing in long term assets / a shallower than expected pool of talented local (or diaspora) entrepreneurs with a practice and understanding of the importance of robust financial management systems
1.6 Annual Outcome Assessment / The outcome of the AECF SSW is “Jobs created and income increased for the rural poor” as well as “Wider market systems improved”. / As the achievements towards the outcome are concerned, the Programme is on track. A cursory examination of the commitments of the six approved grants confirms it. This is because of the rigorous selection of projects by the Fund Manager and the Investment Committee, reflected by the composition of the IC and a high weighting (35%) given the development impact of AECF SSW applications. / The risk of failure is more that the management systems of the grantees will not capture well the development impact rather than the impact will not happen. There are the usual challenges of what is a formal job, how to assess increase in farmers’ income in a context where formality is low and seasonal variances dramatic. / This is why all grantees have been through an M&E induction workshop that was organised on 31 October to imprint the importance of having the right methodology in place to capture this development impact. / Recommendation on outcome indicators; DFID, AGRA and the Fund Manager have to agree on indicators that are both relevant to the South Sudan context and coherent with all AECF windows.

2. Costs and timescale
There is a need for the parties to this Programme to agree on a common budget and timetable. It is not clear to this reviewer that they are currently “singing from the same hymn sheet”. / 2.1 Is the project on-track against financial forecasts: No – zero grant disbursement so far / The Programme is underspent vis a vis the schedule of funds envisaged at appraisal (as attached by AGRA to its Concept Note) and very unlikely that the schedule in the budget of the DFID submission (section 5.3 page 17) that seems to have been prepared by the Fund Manager, can be met. / Admittedly the AGRA schedule [provided by DFID South Sudan out of Quest records] was qualified as a “suggested schedule of reimbursements”, based on an aggressive grant implementation timetable; on early call for fund mobilisation and on advance payments acceptable by DFID. / This reviewer has not found a disbursement forecast that was agreed by 3 parties so has regularly alerted all parties (including DFID) during the review to raise their game in terms of budget forecasting and disbursement scheduling. / During this annual review, the forecast provided verbally by the Fund Manager Team do not let much hope that the schedule in the submission / Urgent recommendation: / 1. By mid December 2012, the Fund Manager to submit an amended disbursement forecast for its 6 approved grantees, especially to help DFID South Sudan Team with its end of financial year forecast. / 2. DFID, AGRA and the Fund Manager agree by end January 2013 a revised disbursement schedule. This will be a tool to ease joint monitoring. FM will report variance against this amended schedule when AGRA sends its quarterly request for payment to DFID. / 2.2 Key cost drivers / The key cost drivers are “establishment” cost to kick-start a new Programme: / - market assessment and initial marketing to build a healthy and diversified pipeline (in AECF parlance called “concept notes”); / - due diligence to transform pipeline in investable deals (in AECF parlance Business Plans). / - financial, legal and regulatory due diligence; risk analysis and measures taken for risk mitigation. / These costs that have been agreed between DFID Head Office and AGRA seem in accordance with common fund management practice, i.e. significant front loaded in this launch phase and largely more fixed than variable (except the 4 days per visit). They have to be incurred as part of “market discovery”. / AECF Fund Manager can count on its proven procedures and processes to gain insight and needs nevertheless to invest additional resources to compensate for the context of a conflict country: severe information failure; insecurity; poor infrastructure and embryonic from professional support. / To be noted that AECF Fund Manager did not open an Office in Juba as it cannot be justified before 20 approved projects, according to AECF Zimbabwe practice. / These total costs represent £439 k at 30 Sep 2012, including the supported provided by Farm Africa as an adviser to smaller businesses (£32k so far). To be commented further in the VfM section and in the Options Paper. / 2.3 Is the project on-track against original timescale: No, but the original timescale was probably unrealistic. / It is still possible to catch up on the original assumption in the DFID submission budget: / - that 25% of the funds could be disbursed by August 2013. However that should be probably adjusted prorata with the volume of business deemed acceptable by the Investment Committee during the Round 1; / - that 100% of the funds committed at Round 1 are disbursed by March 2015.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The reviewer has discussed the theory of change separately with key stakeholders (AGRA Executive Director; AECF Director and SSW Window Manager; DFID Lead Adviser and DFID Acting Head of Office) and it does not seem that the disappointing first results of the first call for proposals challenge it. / There is still a belief in the investment thesis that agribusiness development is the cornerstone of a balanced growth strategy, pro rural and pro-poor in South Sudan and that the private sector can play a crucial role (esp. in the regional context with the EAC… / However quality is not there probably because the AECF SSW is too early in the market (for instance the WB Agri experts will announce the results of their 1-year analytical work on value-chains in June 2013; other fund managers the reviewer has investigated do not invest yet in the agri sector (except one). / AECF SSW stakeholders are however more critical on assumptions that would need to be re-assessed in case of further commitment / at goal/impact level, political economy is less conducive and market conditions are tougher than expected; / the building blocks of an enabling business environment are not there. The new Doing Business Report by the World Bank will help to see clearer progress. / For DFID there are however some benefits to use AECF as a pilot testing this investment climate ahead of the large livelihoods programmes under design. The reviewer has had the opportunity to discuss with several donors and managers of facilities that support farmer groups (USAID-funded) and smaller entrepreneurs (Spark ABC pilot scheme). / In the absence of a significant private equity/project finance market or of an IFC or CDC portfolio; there is nothing similar to AECF SSW to provide credible market signals to DFID and the the donor community and to inform a robust public-private dialogue in the country. / 3.2 Where an evaluation is planned what progress has been made? Not applicable / 3.3. Note / Recommendation to DFID South Sudan Office on record keeping: / There is a need to collect and record in Quest in a unique location the key documents governing the relationship between DFID, AGRA and the Fund Manager. That should be done retrospectively to keep a record of the appendixes to the accountable grant. / It will streamline oversight in a fast-paced Office when key DFID relationship officers change[6].
[6] 3 DFID Programme Managers and 2 Advisers in 15 months

4. Risk
4.1 Output Risk Rating: see comments for each output above / 4.2 Assessment of the risk level / The risk analysis proposed at the appraisal stage “Medium”, must now be seriously re-appraised and DFID South Sudan management must be aware that the Programme belongs more to the high risk/high reward segment of its portfolio. / The reviewer has requested the latest review of the AECF Zimbabwe Window performed by an AusAid Team (one of the lead donors with DFID) and has had discussion with the Team Leader of the new Post conflict window operating in Sierra Leone, Liberia, Somalia/Somaliland and DRC. / It is apparent that the AECF SSW presents challenges of the highest order and more efforts (and resources?) must be invested by DFID and its partners to reassess, monitor and mitigate risks. It can also have many benefits for other DFID Programming in South Sudan. / Recommendations: review the matrix risk and the monitoring procedure in partnership with DFID Global Lead Advisory Team in Africa Regional Division, AGRA and the Fund Manager. / DFID South Sudan and ARD to consider a joint approach with AusAid and SIDA to be (re)assured that the new Governing Structure of AGRA/AECF increase its conflict-affected and fragile state expertise. / See also suggestions in appended matrix
Risk of funds not being used as intended / The culture of fiduciary duty vis a vis DFID/UK taxpayer’ funds is high amongst all stakeholders met, at Officer and Senior Manager levels, but also with grantees. This was striking as it was not prompted by the reviewer. / See comments in appended matrix about the need to be more strategic in tackling such a risk. / 4.4 Climate and Environment Risk / This was stressed at appraisal stage and it has been taken seriously by the Fund Manager (manual of procedures) and by the Investment Committee (verified from the minutes during the review). Several times the IC has made environmental recommendations, including the need for a formal EIA.

5. Value for Money
5.1 Performance on VfM measures / 5.1.1. Wider AECF context / The contract for this South Sudan Window entered between DFID and AGRA, then AGRA and the Fund Manager, is an ancillary to the global arrangements approved at the level of DFID Africa Regional Department, notably based on the good performance rating of the latest MTR. / DFID SSW benefited from a know how transfer (systems, procedures and historical perspective) developed by AECF over 4 years. / However this reviewer is of the opinion that the accountable grant signed between DFID and AGRA for the AECF SSW is not the right instrument and that it does not provide the right level of clarity, transparency and mutual accountability and does not permit DFID SSW Office to play its role of probing the performance of the Fund Manager, including in terms of VfM. / This reviewer praises the good quality of consultation amongst DFID Office advisers facilitated by London. / Recommendation: DFID SSW should discuss with AECF Lead Team in ARD how the new governance context of the AECF can also formalise the relationship between DFID, AGRA and the Fund Manager in order to maximise transparency, mutual accountability and efficiency. / 5.1.2. Applying DFID VfM guidelines and DFID South Sudan VfM strategy and Action Plan to the AECF SSW VfM / The volume of business written by the Fund is lower than expected; quality of approved grantees will be of lesser standards; risk is and will be higher than expected and delays are building up at the disbursement stage. / Economy: DFID South Sudan pays for good, competent, developmentally-focused expertise in Agra and in KPMG. The feedback from approved grantees, from DFID Office and our review of documents confirm that there is the right level of competence and availability for the required tasks. / Efficiency: The launch of the AECF has been done in accordance with AECF best practice. AGRA has even accepted to advance expenses on promotion before its contract conditions were firmed up with DFID. / In terms of process (to which DFID Lead Adviser has been associated as an IC Observer), the selection and sifting process of the concept notes, then of the projects open to further business plans, then of the 6 grantees for which a grant has been awarded, looks in accordance with good principles and in line with AECF other windows. / Recommendation: the three AECF SSW partners should watch the current phase of checking the conditions precedent before completion, the revision of the business plans before signature and disbursement at it seems to drift. / The Fund Manager, in agreement with DFID and AGRA, may consider a deadline for the grantees to execute their obligations. / This process benefited, in its initial stage, from the support of a special facility that bidders could mobilise to help them present their project. AGRA hired a local firm, Farm Africa, at arms’ length from the Fund Manager to do some hand holding. / Supported by / Farm Africa Total Ratio / Completed concept notes 35 116 30% / Selected by the Fund Manager [7] 20 41 49% / Approved Business Plans 12 15 80% / Drop outs 4 4 100% / Approved grants 3 6 50% / Comment: This recourse to Farm Africa was good value for money, but with hindsight may have introduced a selection bias by propping up projects that were not able to perform well through the next selection loops. / One solution would be to provide capacity enhancement along the whole process, including up to the monitoring phase. This is discussed in the Options Paper. / Effectiveness: The reviewer has read the IC detailed (draft) minutes, various documents from the Fund Manager (especially the cover note by the Fund Manager alerting the Committee on South Sudan bidder’s critical weaknesses), and met several people who have attended the IC discussions: there is a consensus that the quality of this first AECF SSW intake did not justify more than 6 approvals. Market quality was/is just not there. / Recommendation: Whatever the political momentum and shared enthusiasm, a basic market survey of the population of potential grantees, based on evidence gathering, would have been beneficial. / This is specifically important in post-conflict countries where information is scarce. / A market survey with a SWOT [Strengths – weaknesses – opportunities and threats] analysis should be a condition precedent to any consideration of investing further DFID funds. / Cost Effectiveness: DFID has adopted in South Sudan a fee formula that is benchmarked on usual AECF / AGRA and AGRA / Fund Manager fee arrangements, in conformity with the SSW appraisal (notably the financial case section of the DFID submission) and taking into account the positive feedback of the global AECF MTR. / - AGRA gets an administration fee of £36.7k or 0.57% p.a. of committed fund that will represent after 7 years 4% of the 6,436k AECF SSW; / - the Fund Manager is charging a management fee of £322k, 225k, 161k, 161k and 161k for the first 5 years of the life of the SSW Fund. It does represent 5%, 3.5% 2.5%, 2.5% and 2.5% of committed funds. It should represent 16% of committed funds at the end of the 7-year project. / Comment: These costs look aligned with normal fund management practice in Africa[8] that tend to hover around 2.5-3% of funds under management for smaller funds and 1.5-2.5% for larger funds. / The discussion should rather focus on the other side of the ratio: how to achieve the level of business initially envisaged for this cost. / Equity: The Fund Manager and the Investment Committee have treated fairly and transparently bidders. The support from Farm Africa (that was publicized on the web site with the bidding documents) has helped those who were not familiar with these procedures. / A few observers have commented that the AECF may appear complex and daunting for inexpert bidders, especially with a poor command of English. However one can argue that AECF SSW beneficiaries must have the capacity to manage the relationship with the grantor in order to report on development impact. Highly subsidized grants cannot come without strings attached. / Evidence: the context of South Sudan, a new country with acknowledged low institutional capacity and hardly any statistic available, will make evidence gathering difficult. / AECF SSW will have to rely on the theory of change of the global AECF project that is based on Challenge Funds (M-Pesa for instance) and M4P track record. / As an example, SAB Miller, funded by an earlier AECF window, including in South Sudan, is replicating an innovative method to process cassava across Africa. / Moreover any success by grantees (such as better seeds; quality maize flour processed on an industrial scale or increase in chicken meat) should be able to be captured by World Bank household surveys and/or prices and quantity of foodstuff by FewsNet[9] or similar. / 5.2 Commercial Improvement and Value for Money / Recommendation: further thinking on services delivered by AGRA and the Fund Manager must be led by DFID ARD. The next in-depth review of the global AECF should look at these questions that AECF South Sudan raise: / - Is the light touch approach chosen by AECF sufficient in the context of a post conflict country? - Shall DFID be ready to spend more to have better outputs and a better chance to achieve significant results, as it has tested with Farm Africa? / - What does it mean to “fund the business plan globally” and “not line by line” in terms of procurement and VfM risk? / - What are the procedures that AGRA deploys in very weak institutional context to protect itself against over-invoicing, fraud, money laundering (including bank failure)? / 5.3 Role of project partners / There is a mismatch between the AECF Project cycle (6 to 7 years after first disbursement of the grant) and the choice made by DFID and AGRA of an accountable grant as an instrument to govern their relationship. / The fact that the AECF Fund Manager, key implementer and first responsible for delivery, is not i/ a party to DFID-AGRA contractual relationship ii/ is not accountable of its performance to DFID does not help to find remedial actions when performance diverges from expectation. / A dialogue could start with DFID AECF Lead Adviser in accordance with fund management best practice with advice taken from DFID CDC Team, the Africa Venture Capital Association (supported by DFID) and from a recent World Bank Lessons Paper of its Agriculture Innovative Matching Grant Facilities (reference in Options Paper – see especially Chap 6). / As SSW is concerned, the current accountable grant dates (Oct 2011 to December 2014) do not reflect DFID approval of a 4-year programme, do not provide assurance that significant results will be captured in 2015 and 2016. / Recommendation: Once DFID, AGRA and AECF have agreed on their preferred option for the remaining uncommitted grant funds (see Options Paper), then appropriate objectives in terms of timetable and indicators should be selected. / The absence of a direct contractual relationship between DFID and the AECF Fund Manager who is the main driver of improvements does not help a healthy dialogue on VfM-related issues. / It would also help if there was more clarity about the cost allocation, direct vs. indirect; fixed and variable of the Fund Manager. / Recommendation: the scope of the next in-depth review of the global AECF or the next SSW annual review must include a detailed discussion with the Fund Manager and AGRA financial managers about staff timesheets and inputs, direct and variable costs... This should be done with an objective that it does improve the governance of AECF. / The reviewer is confident that it will show that the findings about the AECF SSW are in line with those of AECF Global Facility that have been assessed as satisfactory by the latest MTR. / 5.4 Does the project still represent Value for Money: Yes, but the 3 founding partners must re-mobilise their resources to achieve the initial objective of a portfolio of 11 good projects / In terms of costs, the reviewer is of opinion that the AECF SSW costs are in accordance with fund management standards. / Experience of the reviewer with SME funds in Africa in the last 20 years is that it is difficult to manage successfully a fund with spending less than $500-600k p.a. (lessons from CDC, Aureos, AfricInvest, Cauris, Grofin involved in the same SME segment); / Private equity and venture capital funds specialised in frontier and post conflict markets usually access high level of technical assistance funds to remedy structural weaknesses in their markets and with their investees. In the South Sudan context, it would mean increasing 10 times the size of the Farm Africa facility. This has been supported by DFID in the past with AfriCap 1 and has been replicated by donors such as the Dutch, the Nordics or French AFD and USAID. / The challenge is more at the qualitative dimension of the VfM: / - There is an urgency to find ways to address the low quality of the bidders so far. / - The reviewer’s opinion is that a small portfolio of 6 grantees cannot provide a sample large enough, from a statistical point of view, to have a demonstrable impact either way that the results of the Programme have been achieved. / - DFID must consider if spending more money on the Programme may increase its probability to achieve better returns and close to its intended results.
[7] Support ceased at this stage
[8] DFID ARD and South Sudan could get some insider’s knowledge from DFID teams in the Private Sector Department who have been working on CDC reform or with the Africa Venture Capital Association. David Porteous and David Irwin have also commented on cost of Challenge Fund in their seminal report on the FDCF, predecessor to the AECF
[9] http://www.fews.net/docs/Publications/South%20Sudan_2012_11.pdf

6. Conditionality
6.1 Update on specific conditions – not relevant

7. Conclusions and actions
The AECF South Sudan Window is work in progress and it is not yet clear if it will achieve its intended results. / After a boisterous launch in phase with the warm welcoming of a new country, reality started to seep in with the Fund Manager but also amongst donors, development specialists, private sector investors and other stakeholders that there are huge challenges ahead that need to be tackled before new investment can flow in the country. / Moreover AECF has positioned itself on the most difficult segment of the market, agriculture that requires investors who take long positions at a time when the investment horizon is clouded by uncertainty from the Government oil policy, facing tougher macro-economic conditions (growth, inflation, debt…) and reform of the investment climate in key areas such as land policies and rural infrastructure is stalling. / AGRA and the Fund Manager as well as DFID have invested significant resources, know-how and reputation to make this South Sudan Window of the AECF happen. They can rebound from a first year that finishes on a disappointing note. / Priorities must be: / To complete the first six grant approvals as a matter of urgency (Fund Manager lead) / To provide DFID with a revised disbursement schedule as a matter of urgency (AGRA lead based on Fund Manager MIS) / To consider how weaknesses of existing grantees can be addressed in the long run so that there is a good chance to capture impact from the Fund (Fund Manager lead, to make a proposal to DFID SSW) / Then the three partners should start an in-depth policy dialogue: / To review the AECF business model in fragile and conflict countries, based on experience in Zimbabwe, South Sudan and the new Conflict Facility in four other conflict countries (DFID ARD and new AECF Governing Council lead) / To assess the feasibility of a second call for proposal for the SSW, based on a more sophisticated prior market analysis and that would include a marginal cost/benefit assessment to show if the Value for Money would be enhanced by a larger and more diversified portfolio (FM lead). / To consider linkages with other DFID Programmes in South Sudan (DFID South Sudan Office Management lead): / Can DFID livelihoods programmes address some of the issues faced by the agriculture sector as revealed by the AECF bidders? / Shall DFID probe donors and GoSS champions involved in Private Sector enabling environment to do more to tackle constraints in the enabling environment? / and on a more long term note, how can DFID large education programmes include in their design findings about labour shortages and perceptions about rural jobs

8. Review Process
The review was performed by an independent consultant with a good knowledge of DFID systems, challenge funds, investment in Africa and fragile state context (Nigeria, Afghanistan, Cote d’Ivoire…). The Programme Officer accompanied the reviewer in Nairobi but did not participate in meetings with AECF and AGRA managers when they provided feedback on DFID relationship. / The review was prepared by interviews in London with DFID ARD AECF Lead Adviser and the Attaché Commercial at the GoSS Embassy. The reviewer investigated available information on investment climate, portfolios of private equity funds and DFIs, and met a sample of actors in this field when in Juba (WB, USAID, Dutch Embassy; a private equity fund manager, a bank) and in Nairobi (Trade Mark East Africa for the EAC regional dimension). / Evidence provided by the Fund Manager documentation and by interviews with AGRA and Fund Manager senior management and staff was corroborated with audited accounts, Aries/Quest documents and by interviews with grantees, other managers of facilities involved in the agriculture sector or to support entrepreneurship, as well as with an independent member of the Investment Committee. / This information has been cross referenced on a regular basis with several DFID advisors and programme managers. The reviewer met DFID Deputy Head of Office. / The reviewer is thankful for the excellent cooperation he has received from all these stakeholders.

Annex: Risk Matrix

	Risk	Suggested / Revised Probability	Suggested Revised Impact	Why?
1.	Global market conditions deter investment in South Sudan	L to move to Medium	H	MNCs and their financiers are cautious and look at country risk in a holistic way. South Sudan is not a “must have” country. / It seems that alternative strategies such as a regional processing presence with a light trading subsidiary is the favourite model. / However it can shift quickly for those believing in the “first mover advantage” thesis.
2.	Political situation in South Sudan deteriorates, and conditions for doing agribusiness in Africa worsen / Shall DFID consider to separate the 2 risks that do not fit together logically; merge with n#3 part and see new one	M	H	To replace by a component on country attraction assessed by / 1 investment climate monitored by WB DoB progress (and donors and GoSS programmes to tackle it), and / 2. FDI (UNCTAD or IGC)
3.	Conditions for doing agribusiness in South Sudan worsen	L to move to M [even H if not progress]	H	Land policies, rural infrastructure and rural roads, security, availability of labour are all mitigations more than what AGRA can do [even though it is well involved in the PASS Seed improvement progress and with USAID guarantee fund]
4.	Loss of credibility by AECF deters applicants from business for new competition	L – keep low as blame remains subdued so far	H	AECF brand is strong through extensive marketing and PR efforts. Response from private sector to previous competitions has been immense. The AECF will market the new competition including calling on its extensive contact list/pipeline of potential business applicants
5.	Poor management by successful companies leads to poor results of AECF projects	M – move to High	M	Fund Manager’s due diligence of business proposals includes rigorous assessment of capacity of company to deliver initiative successfully. / Fund Manager’s M&E system combining grantee self-reporting validated by Fund Manager’s field sites, picks up difficulties at an early stage. / FM and AGRA as well as DFID are worried by the sheer week financial culture of grantees
6.	Business idea fails to be financially viable or have development impact anticipated	M – Keep as medium and even consider to move to low re impact	M	Fund Manager and Investment Committee assessments of business proposals probes fully the feasibility of proposal achieving financial viability and achieving development impacts. / No worsening in terms of development impact potential.
7.	Fraud and misuse of funds by applicant	L – move to medium	L – move to medium	AGRA’s financial controls and accounting procedures are sufficient. In addition, agreed sum to be set aside for more in-depth due diligence of certain investments and full investigative audits of 10% of the projects / Reviewer not sure that AGRA and AECF have the resources to deal with detailed compliance in a context that is highlighted by everyone as institutionally weak. / Would affect AECF FM reputation outside SSW. / Need to be discussed further with AECF Lead Adviser.
8.	Operational risk at

Risk Matrix Summary
		Impact
Probability		High	Medium	Low
	H
	M	[2]	[5] [6]
	L	[1] [3] [4]		[7]

New matrix to be discussed		Impact
Probability		High	Medium	Low
	H	[2 to be redefined]	[5]
	M	[1] [3]	[6] [7]
	L	[4]

Appendix: List of acronyms and abbreviations

AECF	Africa Enterprise Challenge Fund
AECF SSW	Africa Enterprise Challenge Fund South Sudan Window
AGRA	Alliance for a Green Revolution in Africa
ARD	Africa Regional Department, DFID Department in Head Office that is leading on AECF global activities
AusAid	Australian bilateral Aid Agency
DCED	Donor Committee for Enterprise Development, a forum for donors to share their experience in private sector development. DCED is developing a standard for measuring and reporting results: http://www.enterprise-development.org/page/measuring-and-reporting-results
DoB	Doing Business, a joint project of the World Bank and IFC that provides “objective measures of business regulations for local firms in 185 economies and selected cities at the subnational level”
EAC	East Africa Community
FM	Fund Manager of AECF. i.e. KPMG International Development Advisory Services Africa
GoSS	Government of South Sudan
IC	Investment Committee
IFC	International Finance Corporation, the private arm of the World Bank
Logframe	Logical framework
MTR	Mid Term Review
SIDA	Swedish bilateral Aid Agency
SME	Small and medium-sized enterprise
USAID	US bilateral Aid Agency
WB	World Bank