Annual Review

Project Title: GOU/UN Joint Programme on Population in Uganda

Date started: December 2010	Date review undertaken: November 2012

 Introduction and Context

What support is the UK providing?
DFID plans to provide £30,000,000 for implementation of the Government of Uganda/UN Joint Programme on Population (GoU/UN JPP) over four years (2011-15).

What are the expected results?
The goal of the GoU/UN JPP is to accelerate the onset of a beneficial demographic transition in Uganda between December 2010 and December 2014. The joint programme will support an expansion of both the supply of, demand for and utilization of family planning services primarily through the public sector, to accelerate reductions in fertility in Uganda. At the same time it will support improvement in safe delivery and other maternal health services, a bursary scheme for girls for secondary education and employment of youth. / The programme, complemented by the DFID and USAID funded Accelerating the Rise in Contraceptive Prevalence rate in Uganda (ARC) programme[1], will contribute to a broader, transformative impact on the Ugandan economy, given the risks to economic and social development posed by the current rate of population growth and the opportunity of social sector savings from lower demands on public services. / The GoU/UN JPP and ARC programmes will enable 1.64 million additional women to voluntarily use modern family planning methods of their choice. They will contribute to increasing the contraceptive prevalence rate by 2.5 percentage points per year. / DFID attributable planned outputs from the GoU/UN JPP by December 2014; / Fertility reduced in line with the choices of individuals and couples, especially young people. / 15% young people (10-24 years) with accurate information on family planning in the target districts[2] / 95 health centre IIIs and IVs providing youth friendly services in target districts / 75% of health facilities in target districts without stock outs of pills, male condoms and injectables / Prepared, protected and healthy mothers children and youth. / 1,000 girls retained in school through the secondary bursary programme / 50% deliveries occurring in health facilities in the target districts / Youth and vulnerable groups have competitive skills and opportunities to actively participate in the economy for sustainable livelihoods. / 35% of youth accessing skills development and employment opportunities in target districts / An adequately resourced, coordinated and managed national population programme. / All target districts allocating and disbursing funds to population issues / All target district development plans developed based on socio-economic, demographic and other data sources
[1] ARC jointly implemented with USAID to increase family planning choices through non-state actors.
[2] 15 hard-to-reach districts with over 5 million people.

What is the context in which UK support is provided?
Uganda has one of the youngest and most rapidly growing populations in the world. With a total fertility rate estimated at 6.2 children per woman, the country’s population growth rate, currently at 3.3% is one of the highest in the world. About half (48.7%) of Uganda’s population is younger than 15, well above Sub-Saharan Africa’s average of 43.2% and the world average of 26.8%. The very high youth dependency ratio represents a major challenge for Uganda in the short and medium term. Due to population increases, Uganda’s real income growth per capita has been half its total GDP growth at about 3.4% during the 1990’s and 4% since 2000[3]. The high rate of population growth also creates strains on the country’s natural resources including arable land and public services such as health care. Unemployment and underemployment are serious concerns in Uganda, despite relatively high access to education. / Over 2 million people, thirty four percent of women in the reproductive age group, have an unmet need for family planning[4]. About 44% of all pregnancies are unintended, and these account for the deaths of around 3,000 women every year[5]. The burden of unwanted pregnancy and its consequences disproportionately falls on poor women and adolescents. However, supply of services also needs to be complemented with activities to improve demand for services. Uganda’s maternal mortality ratio has remained relatively high decreasing from 505 deaths in 2001 to 438 deaths per 100,000 live births in 2011. Although the proportion of deliveries taking place in health facilities is increasing at an impressive pace, the quality of care provided for deliveries is not able to maximise the opportunity to reduce maternal death rates. / In order to change its population age structure faster, Uganda needs to accelerate the demographic transition, namely the shift from high to low levels of mortality and fertility. However, the potential benefits of the demographic dividend are not automatic. The supply of good quality family planning services is a key element to accelerate the pace of the demographic transition. Additionally, there needs to be a strong focus on human capital, with intensive investments in education particularly girls’ education. Education transforms countries and societies as well as the lives of individuals and it has been shown that an extra year of quality schooling lifts a country’s annual economic growth by 1%[6]. / The DFID funded GoU/UN JPP is a strategic programme through nine UN agencies in support of the National Population Policy. It is hoped that it will help to make population issues more compelling to Uganda’s leaders as a critical factor in economic growth and development as well as to fulfil the rights of individuals and communities. It will help shape the policy environment to one that has propelled rapid fertility declines elsewhere in the world and help Uganda’s leadership move from strategy to effective implementation. / The programme will contribute to accelerating the onset of a beneficial demographic transition in Uganda. The approach combines a focus on reducing fertility with broader outputs around empowering women and girls through education, health and economic opportunities, and with an underpinning emphasis on better shared evidence for decision making and accountability. The programme is directly contributing to the achievement of GoU targets under the National Population Policy and the National Development Plan. It is also facilitating the UN’s own institutional reform agenda of “delivering as one”.
[3] Ministry of Finance, Planning and Economic Development, Uganda: Population Factors and National Development, January 2010
[4] Uganda Demographic Health Survey, 2011
[5] Calculated from the Uganda Demographic Health Survey 2011 estimates. As per the UDHS 2011, Uganda experiences 438 maternal deaths per 100,000 live births. This implies that around 6,600 maternal deaths take place per year in Uganda, and 3,000 deaths represents around 44% of all maternal deaths.
[6] UK aid: Changing lives delivering results

## Section A: Detailed Output Scoring

Output 1: Fertility reduced in line with choices of individual and couples, especially of young people
Output 1 score and performance description: B / Output 1 has three indicators of which one met expectation and two moderately did not meet expectation. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2012- Dec 2012) Achieved / (Jan 2012- Aug 2012) / 1.1 Proportion of young people (10-24 years) with accurate information on use of contraceptive pills, male condoms and emergency pills in target districts N/A 5% 1.3% / 1.2 Number of HC IIIs and HC IVs providing youth friendly services in target districts 5 (HC IV) / 0 (HC III) / ( UNFPA report 2011) 8 (HC IV) / 35 (HC III) 6 (HC IV) / 37 (HC III) / 1.3 Proportion of health facilities in target districts without stock-outs of 3 most commonly used contraceptive methods (pills, male condoms, depo-provera) in the past 3 months N/A 65% 59.5%
Summary of activities / The programme reached 427,711 of the 1,527,214 young people in the 15 districts with information on adolescent, sexual and reproductive health (ASRH). This was enabled by training peer educators to support youth friendly corners and outreach to communities and schools as well as training health workers in providing youth friendly services. The low proportion of youth with accurate information on family planning suggests the need to strengthen the approach and messaging to young people in the multiple settings through which they are being reached such as schools, worksites, radio talk shows, peer educators and from health workers. / In collaboration with the MoH, guidelines and job aides on providing youth friendly services (YFS) were developed and 234 health care workers trained in the provision of YFS. These health workers now have the capacity to address ASRH health challenges faced by youth including counseling and management of sexually transmitted infections, pregnancy and HIV/AIDS. Eight of the facilities providing YFS were equipped with posters and brochures on ASRH, games equipment and television sets to operate youth corners. However the annual review field visits found that the relevance and impact of the services provided at youth corners was not always apparent. In addition, many young people who are attending family planning or outpatient services are not always provided adolescent specific information, since many health facilities are struggling with low levels of human resources, and staff do not have the time to provide structured counseling to groups of adolescents. / The programme supported procurement of 105,400 injectables, 27,216,000 male condoms, 76,896 Inter Uterine Devices (IUDs) and 218,624 Implanon units for national distribution representing 18% of the national requirements. DFID through this programme and the ARC programme co-funded with USAID, contributed £4,500,000 last year to procurement of contraceptives. This has had a tremendous impact on reproductive health commodities security improving availability of contraceptives nationwide. With the increased supply of contraceptives, the demand for contraceptives particularly long term methods, at lower health facilities is on the rise. The availability of six tracer drugs, including contraceptives, has increased from 43% in 2010/11 to 70% in 2011/12 in Uganda[7]. However, concerns remain about the proportion of facilities with stock outs of contraceptives. / Recommendations: / There is need for formative research to understand the most appropriate messages and channels for reaching young people at scale with accurate information on ASRH during the remaining period of the programme. / The relevance and impact of providing youth corners at 17 facilities out of the 350 facilities in 15 district’s needs to be urgently reviewed. / Engage National Medical Stores and the Ministry of Health (MoH) on the revision of commodity kits sent to health centres, particularly HCIIIs, to reflect increased demand for particularly long term methods of family planning at lower level facilities. / Enhance the skills of health care providers at lower level health facilities for administration of long term methods of family planning methods, particularly implants. Many providers at lower level facilities are already providing injectables, oral pills and condoms. / Impact Weighting: 50% / The review found no reason to change the impact weighting. / Risk: Medium / The review found no reason to change the risk rating.
Output 2: Prepared, protected and healthy mothers, children and youth
Output 2 score and performance description: B / Output 2 has two indicators of which one met expectation and the other substantially did not meet expectation. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2012- Dec 2012) Achieved / (Jan 2012- Aug 2012) / 2.1 Number of girls retained in school through the secondary bursary programme 0 / (2010) 1000 1000 / 2.2 Proportion of deliveries occurring in health facilities in the 15 target districts 31% / (HMIS 2010/11) 39% 20%
Summary of activities / By August 2012, 1,000 girls had been enrolled and retained in the bursary programme in 8 districts. 854 of these are in secondary schools while 146 have been enrolled into Business Technical and Vocational Educational Training Institutes. This year 29 girls will sit their exams for lower secondary and graduate from the programme. / A total of 47,809 deliveries against a target of 90,000 deliveries occurred in health facilities in the target districts. However complete reports for 6 districts for the period under review are yet to be received. Over 42,000 mama kits were distributed to 7 districts and additional mama kits worth £2,000,000 are being procured to be distributed nationally to reduce one of the key barriers to accessing safe delivery services at public health facilities[8]. Mama kits provide women with essential supplies for the birth process. 215 Village Health Teams (VHTs) received training in the new born care package and in an effort to scale up the village phone initiative for maternal health emergencies, 257 VHTs received mobile phones to be used for emergency referrals. Progress has been slower than anticipated in increasing the numbers of women delivering at health facilities in the target districts. Many facilities still grapple with lack of trained midwives, basic equipment and supplies and the physical distance between health facilities and homesteads. Availability of timely referral is needed if a woman encounters complications during delivery. In 2011, the GoU/JPP funded the procurement 11 ambulances and there is an opportunity to use this investment to demonstrate a well-functioning referral system. / Recommendations: / Need to increase efforts to improve quality of care at health facilities, particularly in terms of skilled staff and essential supplies. The GoU/JPP should review work on training for emergency obstetric care, in the context of the GoU’s broader maternal mortality reduction strategies. / In a bid to strengthen the referral network, the functionality of the 11 ambulances and the VHT mobile phone referral system should be reviewed to prepare and implement a referral plan for pregnant women in the target districts. / The girls graduating from the bursary programme should be linked to other organisations that provide scholarships such as Forum for African Women Educationists (FAWE) and Irish Aid to ensure that they can continue to higher secondary level. / Impact Weighting: 20% / The review found no reason to change the impact weighting. / Risk: Medium / The review found no reason to change the risk rating.
[7] MoH Annual Health Sector Performance report 2011/2012
[8] Others barriers include lack of skilled providers and transport to health facilities

Output 3: Youth and vulnerable groups have competitive skills and opportunities to actively participate in the economy for sustainable livelihoods
Output 3 score and performance description: B / Output 3 has one indicator which moderately did not meet expectation. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2012- Dec 2012) Achieved / (Jan 2012- Aug 2012) / 3.1 Percent of youth accessing skills development and employment opportunities in target districts N/A 23% 19.3% / Summary of activities / 3.1 Through the programme, 158 youth were supported to access training in formal vocational skills in tailoring, motor vehicle and mechanics, catering, carpentry and joinery among others. 1,032 youth were equipped with informal business development skills such as candle and soap making, energy saving stoves production and waste management and recycling. In addition, 768 vulnerable young women, who are household heads, were assisted to access informal agricultural employment in two districts. However, there was no information to assess whether the skills training had resulted in employment opportunities and if this had been measured. / Following a labour market analysis based on the results of the national labour force survey, new interventions under this outcome have been proposed. While the proposed interventions seem better aligned to strategic intervention compared to previous interventions under this outcome, the possibility of whether these interventions can deliver value for money in the next two years is questionable. / Recommendations: / Two years into the programme, it is unclear how far this output is contributing to the overall goal and purpose of the programme. It may be necessary to consider whether funds allocated to this outcome would have an increased impact on the overall GoU/UN JPP through interventions under other outcomes (1 and 2 in particular) which need additional investments to meet their targets. / Impact Weighting: 10% / The review found no reason to change the impact weighting. / Risk: Medium / The original risk rating was low. Given the challenges implementing activities under this outcome, the risk rating has been revised to medium.

Output 4: An adequately resourced, coordinated and managed national population programme
Output 4 score and performance description: A / Output 4 has two indicators of which one substantially exceeded expectation and the other substantially did not meet expectation. / Indicators Baseline Milestone / (Jan 2012- Dec 2012) Achieved / (Jan 2012- Aug 2012) / 4.1 Proportion of target districts allocating and disbursing funds to population issues N/A 60% 40% / 4.2 Proportion of district development plans developed based on socio-economic, demographic and other data sources N/A 60% 87%
Summary of activities / 4.1 While all districts allocated funds to population issues, only 6 districts had actually spent at least 30% of their budgets on population issues. The challenge most districts face in budgeting for and spending on population issues is that the unconditional/un-earmarked funds of the district budget are limited. 44 champions at district and national level established through this programme have been instrumental in advocating for population and development agenda. At national level, the champions that are members of parliament contributed to the successful push for an increase in the health budget to improve access to safe delivery and reproductive health services. / 4.2 With support through this programme, six data sources including the Uganda Demographic Health Survey 2011, Annual Panel Survey and district statistical abstracts are now available for use for planning at both national and district level. The Uganda Bureau of Statistics provided technical support to the districts to improve use of data in development of district development plans. To enhance use of data at the district level, a centralised district database to collect aggregated data has been established in 15 districts. However the database functionality is not yet optimal and districts still struggle with submission of high quality data in a timely manner. / Recommendations: / The results of Annual Panel Survey provide important annual estimates for planning and for this data to be more relevant, the results need to be made available within three months after completion. / Results of the GoU/UN JPP mid-term evaluation should be made available by November 2013 and the final evaluation by November 2014. / The support to district planning needs to be realigned to improve delivery of services including family planning, maternal health services and education. / Impact Weighting: 20% / The review found no reason to change the impact weighting. / Risk: Medium / The original risk rating was low. Given the challenges of delays in receiving funds at the district and the fact that un-conditional grants form a small percentage of the district budget, the risk rating has been revised to medium.

## Section B: Results and Value for Money.

1. Progress and results

Has the log frame been updated since last review? Yes / There was a considerable delay in completing the baseline survey. The log frame (annexed) has been revised to reflect changes in the work plan following the first annual review, the findings of the GoU/UN JPP baseline survey completed in 2012 and the 2011 Uganda Demographic Health Survey. / Overall Output Score and Description: B / While the programme achieved the milestones for some indicators, overall the programme moderately did not meet expectation. / 1.3 Direct feedback from beneficiaries / The Assistant Commissioner, Reproductive Health says that “the programme is timely” and the Ministry of Health (MoH) appreciates the support particularly because the 15 districts of the GoU/UN JPP are hard to reach areas with poor health indicators. The Ministry is aware of the enormous challenges in the public sector such as; lack of skilled staff, equipment, drugs and supplies and the challenges of inconsistent and late reporting of data from the districts which are at the core of the GoU/UN JPP. The Ministry of health officials also highlight the policy and advocacy role played by the GOU/UN JPP as instrumental in raising awareness among leaders on the importance of population issues. This year with support from the programme, the Ministry of health has been able to develop and disseminate key policies and guidelines on reproductive health which would otherwise not have been possible. However, officials from the Ministry of Health request that expansion of the GoU/UN JPP to the Busoga region should be considered as it has one of the highest total fertility rates in the country. Health care workers interviewed reported that while there is an improvement in supply of contraceptives there are still several challenges around institutional deliveries including lack of basic supplies and equipment. The operating table in one district hospital visited was rusty and falling apart. While Maternal and Peri-natal Death Review (MPDR) committees have been formed in some facilities, more needs to be done to improve their functionality. Lastly, several family planning clients interviewed at health centres visited reported that they have a wider choice of contraceptives to choose from which is contributing to uptake of family planning. / 1.4 Summary of overall progress / Two years into the programme there has been good progress in some areas such as girl education and the procurement and distribution of contraceptives. £10 million of the total programme budget is earmarked for procurement of contraceptives. Based on recent data from the Annual Health Sector Performance report (2011/2012), there has been a decrease in stock outs of commodities including contraceptives at health facilities. During the field visits it was evident that health facilities have stocks of contraceptives, although for some contraceptives the baseline study indicated availability at peripheral facilities was still an issue. / Formulation of new policies and guidelines and advocacy at the national levels have raised awareness on population issues and contributed to increased allocations to the health sector. Through this programme several policies, guidelines and strategies were finalized and disseminated including the adolescent health policy and strategy and the current HMIS form revised to capture data on adolescents to improve planning for adolescent health. UNFPA also played a key role in mobilisation of government leaders and stakeholders in preparation for the July 2012 summit on family planning held in London. The participation of the President of Uganda at the summit played a crucial role in boosting efforts in Uganda to raise awareness on the importance of population issues in relation to development / Discussions held with clients at health facilities show that there is a growing demand for contraceptives particularly implants. However many staff at lower levels of the health system (below HC IV) have not been trained on implant insertion. Through this programme 92,683 additional women are using modern family planning methods as compared to 61,117 last year, mainly through outreach camps conducted by civil society organisations. The healthy choices radio programme for social behaviour change communication reached 2,516,989 people with information on family planning increasing demand in the target districts. / However results in some areas have not been as expected. While new users of modern family planning have increased in the second year, it fell way short of expectation and there is an opportunity to increase these numbers particularly through routine service delivery in public health facilities. Challenges in the health system have contributed to the slow progress in increasing institutional deliveries and the value for money of high spend activities such as the youth corners and male action groups is not very obvious. In theory, while the role of VHTs in increasing demand and utilisation of health services is widely agreed, on the ground there is little evidence of their ability to carry out their activities with minimal resources and supervision from the district. The data capturing and sharing skills of the VHTs are still minimal and the expectations being placed on them may be too high. It will therefore be important to review the implementation of the VHT component of the programme to ensure that the VHTs can effectively carry out assigned tasks. Lastly, the impact of the activities under outcome 3 on the overall goal of the programme, are still not evident. / Opportunities / There is an opportunity to integrate family planning camps with other reproductive health services such as treatment of sexually transmitted infections, HIV counselling and testing. / There is also an opportunity to strengthen youth friendly services being provided to young people who are accessing routine care at health facilities. / There is an opportunity to strengthen the linkage between the GoU/UN JPP and the DFID/ USAID funded ARC programme to build capacity of health care workers at lower level health facilities to provide family planning.

Key challenges / Management and coordination of the GoU/UN JPP / Because of the differences in financial years and internal procedures of the Ministry of Health and the respective UN agencies, delays in disbursements of funds between agencies and to implementing partners are experienced. / Human resource capacity / Some of the target districts have a serious shortage of midwives and clinical officers which affects institutional deliveries. Health workers at lower health facilities often do not have the capacity to provide long term family planning methods which are increasing becoming popular e.g. implants. Therefore as the supply and demand for family planning services are steadily increasing, the lack of skilled human resource poses a challenge to achievement of results of the GoU/JPP. / Supply chain management / The push system by National Medical Stores results in over stocking in some areas and stock outs in other areas of key contraceptive commodities. The re-distribution mechanism of commodities between health facilities within the district is not functional in many districts. Unless quality issues are addressed the rise in institutional delivery in Uganda will not be maximised to improve the slowly changing maternal mortality rates. / Quality of care / The health system is struggling to meet the existing demand for maternal and reproductive health services and is often faced with lack of equipment, basic supplies and poor infrastructure all of which affect utilisation of health facilities. / Information management / The collection and utilisation of high quality data is still a challenge. Reports are often incomplete, inconsistent and not submitted in a timely manner making it difficult for district and Ministry officials to plan. At the village level, record keeping and reporting by VHTs is not at the anticipated level. In addition, the absence of data capturing tools in departments with the exception of health and education has hampered operationalization of the harmonised district databases. Data could be better used for planning services reach and availability, including provision of maternal health services.
1.6 Annual Outcome Assessment / The overall purpose of the GoU/UN JPP is that national, community, cultural and issue-based leadership are managing the acceleration of a downward trend in population growth. The log frame contains two indicators against which this purpose is assessed. These include; / Outcome indicator 1 Baseline Milestone / (Jan 2012- Dec 2012) Achieved / (Jan 2012- Aug 2012) / Contraceptive prevalence rate (modern methods: women of reproductive age) 25.6% / (2011) 28.1 % To be determined through the annual panel survey of 2012. The results are likely to be published in 2013. / According to the Annual Panel Survey 2011 and the Uganda Demographic Health Survey (UDHS) 2011 the baseline contraceptive prevalence rate (CPR) for modern methods of contraception is 25.6% and 26% respectively. There has been a significant increase in use of modern contraceptives over the previous year with fewer facilities reporting stock outs of family planning commodities. The increase in contraceptive prevalence rate from the baseline will be determined through the next panel survey. / Outcome indicator 2 Baseline Milestone / (Jan 2012- Dec 2012) Achieved / (Jan 2012- Aug 2012) / Teenage pregnancy rate 24% / (2011) 22.5% No data to access progress / The Uganda Demographic Health Survey (UDHS) 2011 shows that 24 percent of teenagers had begun childbearing a decline over time from 43 percent in the 1995 UDHS. The percentage of teenagers who had begun childbearing varies by region, the Karamoja region having one of the highest percentages compared to other regions (around 30 percent). However data from the Annual Panel Survey is not available to assess progress on this indicator.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The annual budget planned for the year January 2012 to December 2012 was $15,377,682 of which DFID contributed $12,537,901. The preliminary report on allocations and expenditure as of October 2012 is outlined below. The final figures will be submitted by 31st May 2013. The expenditure does not include $3,209,076 disbursed to UNICEF in November 2012 for purchase of mama kits. / UN Agency Funds planned Jan-Dec 2012 Funds received Jan-Sept 2012* Funds received Oct 2012-Mar 2013 Total funds received Jan 2012-Mar 2013 Funds spent Jan-Oct 2012 Percentage expenditure of funds received / WHO 2,462,530 2,697,404 413279 3,110,683 2,674,889 85.99 / UNFPA 7,022,861 6,395,653 2427040 8,822,693 5,758,207 65.27 / UNHCR 431,935 397,570 236762 634,332 414,184 65.29 / UNICEF 1,360,351 1,578,973 382755 1,961,728 1,391,954 70.96 / WFP 485,755 625,200 109242 734,442 Not available Not available / ILO 175,408 256,188 0 256,188 188,934 73.75 / IOM 245,509 222,144 24176 246,320 237,321 96.35 / UNHABITAT 250,693 229,334 89012 318,346 220,139 69.15 / UNWOMEN 102,859 99,554 3305 102,859 89,914 87.14 / TOTAL 12,537,901 12,505,020 3,685,571 16,187,591 10,975,542 67.80 / *includes additional funds carried over from 2011 / The expenditure against planned budget registered good performance. Most agencies achieved spend above 65% and it is projected that all the funds will be expended before the end of the fiscal year. In September 2012, the Steering committee authorised scaling up of activities in the 2012 work plan using funds disbursed for January to March 2013. This supplementary work plan and budget totalling to $1,976,639 will be the framework for programme implementation between January to March 2013 until the 2013 work plan is approved. / 2.2 Key cost drivers / Distribution of funds spent by expense category (Jan- Oct 2012) / Expense category Amount spent (USD) % of expenditure Expense description / Management costs 1,999,634 18.22 Staff related costs, vehicle procurement and maintenance, purchase of office equipment, office operational costs and general overhead costs / Supplies, commodities and materials 4,543,282 41.39 Family planning commodities and mama kits, printing resource materials on Reproductive Health and vocational skills toolkits / Contractual services 816,712 7.44 Printing Information Education and Communication materials and guidelines / Training and travel 1,684,217 15.35 Health workers training workshops and support supervision activities / Transfers and grants counterparts 1,931,699 17.60 Direct financial contributions to partners for implementation and support supervision of UNJPP activities / Total 10,975,543 100.00 / * The above analysis does not include expenditure by WFP. / The overall management cost appears very high at 18.22%. A detailed review of the management costs needs to be undertaken to determine value for money and where possible assign more resources to areas of service provision through the facilities and outreaches. / 2.3 Is the project on-track against original timescale: No / The original assumptions on which this programme is based need to be re-assessed. While the progress towards some outputs appears in line with time expectations, how achievements of these outputs will lead to improvements in programme outcomes and goals are a bit unclear. There is need to revise the log frame and intensify efforts to ensure that targets for the next two years particularly institutional deliveries, new clients on family planning and proportion of youths with accurate information on ASRH are met.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Following the last annual review of the programme, it was recommended that the scope of activities in the 2012 work plan be scaled down to prioritise activities with a proven evidence base. As a result the planned activities were reduced from 182 to 61 for a more focused approach. However there is still concern about the evidence that underpins male action groups and youth friendly corners and their contribution to achievement of results on a large scale. Emerging evidence on key interventions, such as creation of youth corners to extend reproductive health services to youth, voluntary male action groups and voluntary engagement of VHTs to improve awareness about RH/FP services, appears mixed. Most of these interventions rely on voluntarism and do not provide any compensation/reimbursement for food/travel. There is increasing global evidence on how community level workers can contribute to improved health outcomes, some of which was presented at the recent Beijing conference on health systems research. UN partners should be encouraged to access this global evidence in their planning. / The evidence base as well as the performance of these interventions will be discussed with UN agencies and GoU ministries participating in the GoU/UN JPP in January 2013 and remedial actions will be incorporated into the 2013 work plan. / 3.2 Where an evaluation is planned what progress has been made? / A mid-term evaluation of DFID’s family planning programmes including this programme is planned for 2013. The process of procuring a contractor has been initiated and the evaluation is expected to start in June 2013.

4. Risk
4.1 Output Risk Rating: / 4.2 Assessment of the risk level / The GoU/UN JPP programme document contains a set of risk categories against which the overall programme risk can be determined and scored. An assessment of these risks to the delivery of expected results and an assessment of whether the mitigation actions directly address the identified risks is contained in the table below. / Description of risk Status and mitigating action Rating / UN agencies are unable to work closely together and cohere around shared objectives The UN agencies do not have one programming approach and so challenges exist in relation to their approach taken to some activities and the streamlining of financing and reporting. Ensuring representation of all agencies at the steering committee meetings twice a year and the quarterly coordination team meetings fosters joint working. Challenges to joint working will be discussed with the UN agencies following this review. Probability: medium Impact: high / Recommendation: keep rating as above / Participating GoU and national institutions lack implementing capacity There are 8 key sectorial ministries and 2 government agencies involved in the GoU/UN JPP. As co-chair of the steering committee, government is involved at the highest level in decision making for the programme. However weak district capacity and structures pose a challenge to coordination on the ground. District capacity building activities and field monitoring visits are conducted to improve implementation at the district. Probability: medium Impact: medium / Recommendation: keep rating as above as activities to increase the capacity of the districts to deliver quality services are intensified / Government commitment to programme aims is reduced Government has consistently shown high levels of commitment to the programme and continue to participate actively at steering committee meetings and in joint monitoring visits. Probability: low / Impact: high / Recommendation: keep rating as above / Increasing demand for family planning cannot be met due to supply-side funding gap DFID and USAID together fund approximately 80% of the contraceptive commodities for the country and over the last years there has been a decline in stock outs of key contraceptives though some supply chain management challenges still exist. While more commodities are making their way to the health facilities, it will be important to ensure that the health care workers have the right skills to administer the methods, particularly long term methods. Probability: low Impact: high / Recommendation: keep rating as above as efforts are made to build the capacity of health workers to provide particularly long term family planning methods.
Risk of funds not being used as intended / The GoU/UN JPP funds are disbursed directly to and managed by UNFPA, the Administrative Agent. Funds are made available to the participating UN agencies for specific activities through the UN “pass-through” funding modality. The financial accountability for use of the funds is the responsibility of each participating agency. For agencies that engage implementing partners a detailed risk assessment is undertaken by some of the agencies to review and identify strengths and weaknesses in the partners capacity for financial management and to establish appropriate financial modalities, procedures, and assurance activities. These risk assessments are important and should be undertaken by all agencies before engaging with any implementing partners. / Funds are disbursed to implementing partners, in accordance with a general annual work plan approved by the Steering Committee and more detailed quarterly work plans, which are agreed with the participating UN agency. Usually advances are only given on a quarterly basis, with a requirement that accountability for the previous period needs to be submitted before the next tranche can be disbursed. Following disbursement a programme officer is assigned to each partner to monitor progress and expenditures. Field monitoring visits with government officials and beneficiaries also provides a checking mechanism to ensure funds are being used for the intended purpose. / In light of recent misappropriation of funds and freezing of financial aid to the GoU, in November 2012 a review was done of the systems and checks in place to safeguard funds that go through the UN to implementing partners including the GoU. The review showed that UNFPA’s systems seem quite robust, with a seemingly significant level of oversight applied regularly and rigorously. The programme has a full time Financial Specialist, who works closely with UNFPA’s International Operations Manager to monitor financial spend of recipient agencies’ and conduct systematic follow-up to previous quarters’ (and previous audit) recommendations. / 4.4 Climate and Environment Risk / Improved population planning has the potential to make a significant contribution to more environmentally sustainable development. While the design of the GoU/UN JPP does not focus explicitly on aspects of the National Population Policy related to environmental management, through output 4 there is an opportunity to provide better data, evidence and analysis around the impact of the growing population on the rural and urban environment and the environmental benefits of improved population planning. In addition, DFID ensures that approval of work plans takes into account and incorporates opportunities for environmental benefits where possible. Summarised below are the potential detrimental environmental impacts of the programme and the corresponding mitigating action. / Potential detrimental environmental impact Mitigating action / The release of carbon dioxide through transport of the outreach teams and support supervision teams The programme has procured vehicles with modern fuel combustion systems. / Waste generated as a result of used contraceptive commodities and supplies used for deliveries Health care workers have been trained in infection control and medical waste management and disposal.

5. Value for Money
5.1 Performance on VfM measures / In the absence of detailed expenditure on various elements of the programme it is difficult to calculate the precise unit cost per Couple Years of Protection (CYP)[9]. However based on broad approximations, the cost per CYP of the GoU/UN JPP between January 2012 and August 2012 is approximately £13[10]. The cost per CYP in other Sub-saharan African countries ranges from £4.9 for social marketing to £12 for clinic based services[11]. Therefore it could be inferred that the value for money for family planning service delivery through the GoU/UN JPP is comparable to similar programmes. The cost per girl educated through the bursary scheme is approximately £540 which seems high despite reductions following the last annual review. The reductions in management costs however enabled the programme to scale up enrolment from 839 girls last year to 1000 girls this year. The final expenditure for the year (January 2012 to December 2012) will be available in January 2013. Therefore, a more detailed value for money assessment of this programme will be undertaken next year. / 5.2 Commercial Improvement and Value for Money / Procurement of contraceptives in Uganda is based on quantification and procurement plans agreed by the members of the national Reproductive Health Commodities Security Committee on which UNFPA sits. This ensures that the right quantities are delivered in a timely manner to the country reducing oversupply and stock outs. £10 million of the total GoU/UN JPP funding is earmarked for procurement of contraceptives through UNFPA that receives 5% of this expenditure to cover indirect costs. From January 2012 to October 2012 approximately £3,608,800 was spent on procurement of contraceptives. / UNFPA procures through the UNFPA procurement services branch at the headquarters. UNFPA has established procedures for ensuring that the commodities they purchase and supply live up to the highest international standards. UNFPA has extensive experience and a solid track record in procurement of contraceptives and related commodities. Because of the significant volumes procured and market influence, this allows them to access the most favourable international pricing resulting in value for money. Procurements are delivered to UNFPA Uganda as the consignee for delivery to National Medical Stores or the Uganda Health Marketing Group for onward transmission to health facilities / 5.3 Role of project partners / Coordination of the Joint UN programme / The Steering Committee which is the executive decision making body of the GOU/UN JPP includes representation from the Ministry of Local Government, Ministry of Lands, Housing and Urban Development, Ministry of Education and Sports, Ministry of Health, Ministry of Gender, Labour and Social development, the Population Secretariat and the Uganda Registration Services Bureau. Strong government representation encourages government ownership. / This committee meets twice a year to review programme and financial progress reports and approve work plans and fund allocations and/or re-allocations. The programme is coordinated through the coordination team and outcome technical working groups that meet quarterly. Through joint planning, a national stakeholder annual review meeting and joint field monitoring visits the coordination team assesses progress towards achieving agreed results. / The Steering Committee is the executive decision making body of the GoU/UN JPP. It provides overall oversight and governance for the joint programme through the review of reports and other documents prepared by the coordination team. The Steering Committee makes decisions by consensus and is co-chaired by the Government of Uganda and the UN Resident Coordinator. Members include heads of the participating UN Agencies, government representatives from all the 8 key sectors and DFID. The coordination team provides strategic guidance for planning and implementation of the programme and coordinates the reporting processes. This team consists of the programme secretariat and the chairs of the four outcomes. / 5.4 Does the project still represent Value for Money: Partially / There is concern that the activities under Outcome 3, the male action groups and youth corners do not represent value for money. An analysis of results achieved and funds spent shows that minimal results have been achieved for these high spend activities. / 5.5 If not, what action will you take? / We recommend that re-programming be done to modify activities around the male action groups and youth corners to achieve high impact for the programme through other activities.
[9] CYP refers to “the estimated protection provided by contraceptive methods during a one-year period based upon the volume of all contraceptives sold or provided/distributed to clients during a specified period. ‘CYP’ is a way to estimate coverage of contraceptive. While CYP is a useful measure to gauge reach/coverage/access of contraceptives, it does not necessarily reflect the actual use or impact of contraceptives.
[10] This cost does not include the re-current costs incurred by government such as salaries of health care workers and infrastructural costs.
[11] Barberis, M. and P.D.Harvey. 1997. “Costs of Family Planning Programmes in Fourteen Developing Countries by Method of Service Delivery.” Journal of Biosocial Science 29(2): 219–33.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The review found that there has been progress made since the last annual review in some areas such as school bursaries for girl education and the procurement and distribution of contraceptives. While progress has been made in new clients on family planning and institutional deliveries, given the increasing demand for these services, this programme has the potential to support the delivery of services to a larger number of clients. Lastly, two years into implementation of the programme, the results achieved for some activities make it difficult to justify their continued funding. The following actions are recommended to guide the improved implementation of the activities under the programme. / The log frame should be revised to improve alignment of outputs to the expected outcomes. / Stop activities under outcome 3 and consider a separate project on improving youth skills and productivity outside of the GoU/UN JPP. / Increase efforts to build capacity of the health facilities to provide quality maternal and reproductive health care. In addition, the skills of health care providers at lower level health facilities for administration of long term methods of family planning methods should be enhanced. / Because the impact of male action groups and youth corners on the overall goal of the programme is minimal, phase out these activities and re-programme these funds to other activities that will yield high impact results in the next two years. / Commission a study to understand the most appropriate messages and channels for reaching young people at scale with accurate information on ASRH. / Commission an analysis to review management costs and identify possible mechanisms to reduce these costs.

8. Review Process
The review was conducted by a team from DFID Uganda in collaboration with the outcome leads from the UN agencies. The team from DFID Uganda was supported by Mr. Billy Stewart (Senior health adviser, DFID India) and Mr. Richard Jones (Country engagement manager, United Nations and Common Wealth department). / Period of Review: 19th November 2012 -7th December 2012 / Methodology / Structured key informant interviews were conducted at national level with Ministry of Health officials, the population secretariat and all participating UN agencies. The outputs of the national GoU/JPP stakeholders meeting held on the 28th and 29th of November also fed into the review process. A team from DFID visited Bundibugyo and Mubende districts to assess implementation of the programme on the ground. In the districts, interviews were conducted with the respective district health officers, reproductive health focal persons, population officers, health care providers, community health workers, male action group members and clients at public health facilities. / The team also reviewed documentation relevant to the programme including; / The programme document / Log frame / Progress reports / Uganda Demographic Health Survey 2011 / The table below shows key stakeholders interviewed. The list of stakeholders interviewed at district level is available. / No Name Title Organisation / 1 Ms. Ahuuma Resident Coordinator UN / 2 Ms. Janet Jackson Representative UNFPA / 3 Mr. Jhamba Tapiwa GOU/JPP coordinator UNFPA / 4 Mr. Patrick Orotin GOU/JPP M&E specialist UNFPA / 5 Mr. Charles Zirarema Acting director POPSEC / 6 Ms. Grace Odeke Senior National Programme Officer POPSEC / 7 Mr. Hannington Burunde Head Information and communication POPSEC / 8 Mr. Andrew Tiondi Head monitoring and Evaluation POPSEC / 9 Mr. Stephen Opio Programme Coordinator ILO / 10 Dr. Olive Sentumbwe FH and population adviser WHO / 11 Mr. George Ebong Education Specialist UNICEF / 12 Mr.. Gerard Waite Chief of Mission IOM / 13 Ms. Regina Mutiti GoU/JPP Finance manager UNFPA / 14 Dr. Collin Tusingwire Ag. Assistant commissioner reproductive health MOH / 15 Mr. Albert Kalangwa RH commodities security officer MOH / 16 Ms. Miriam Namugere Principle Nursing Officer, RH division MOH

## References