Type of Review: Annual Review

Project Title: Strategic Impact Fund for the Occupied Palestinian Territories

Date started:	22/12/11	Date review undertaken: 14/12/12

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK will provide £1 million to finance at least 12 small projects over 4 years which will support work by the Department for International Development and our partners to improve the lives of Palestinian people and contribute towards the Middle East Peace Process. The Strategic Impact Fund will be used to strengthen the evidence base for DFID and partner programmes, improve DFID’s influencing ability with donors and the wider community, and support innovation to drive improvements in project delivery and value for money.

What are the expected results?
The project will help DFID and its partners to deliver high quality programmes which will improve the lives of Palestinian people and contribute to a two state solution, as measured by year on year improvement in the Palestinian Programme portfolio quality score. This will be achieved through the generation and use of new evidence, new pilot studies and new ways of working, with at least 75% of interventions in these fields meeting or exceeding expectations in delivering strategic impact. The project will produce at least: / 2 high quality studies which strengthen the evidence base for DFID, Palestinian Authority and other partner projects, ensuring projects stay relevant and effective in a fast-moving political and economic environment, and leading to better value for money and reduced risks to project delivery / 1 pilot projects that assess and develop innovative approaches to project delivery and which are taken forward by DFID/other partners to increase the returns on investment / 1 influencing activities which bring together key development actors working to support Palestinians in order to improve harmonisation and coordination of development activity and leverage development outcomes beyond that which a single actor can deliver alone.

What is the context in which UK support is provided?
Economic conditions in the OPTs are closely tied to political developments as a result of the on-going conflict and occupation. Israeli movement and access restrictions in the West Bank, incursions, and its almost complete control over Area C (60% of the West Bank), East Jerusalem and the Gaza Strip act as major impediments to economic development. For example, the IMF estimate that if there is significant easing of movement and access restrictions, growth in the OPTs will be at 7-10% per year 2012-14, whereas if the status quo is maintained (line B), growth will be under 4%. The Palestinian Authority (PA), has very limited control over its income, given the unpredictable nature of aid flows (37% of its income in 2010), and the fact that tax revenues (41% of its income in 2010) are transferred to the PA via Israel, which collects on the PA’s behalf. Both sources of finance are vulnerable to political leverage (for example in response to Hamas/Fatah reconciliation, and Palestinian action at the UN). Political change thus could lead to either rapid deterioration or continued improvements in conditions in the OPTs. The situation in Gaza is particularly fragile and a future humanitarian crisis cannot be ruled out. Our support is likely to need to respond to major changes in the political and operating environments over the course of the next four years. / In order to maintain the ability to respond effectively to the changing political and humanitarian/developmental situation on the ground, and to continue to deliver development objectives effectively, we have identified the need for a mechanism, capable of supporting targeted inventions aimed at addressing emerging risks, opportunities and issues within and across projects, which cannot be easily incorporated into our on-going projects or carried out by others. These interventions fall into three main areas: strengthening the evidence base for DFID and partner projects; supporting innovation and improving DFID’s influencing ability with donors and the wider community. These are therefore logically best addressed by an overarching Business Case addressing these three areas in a strategic, planned way rather than by ad hoc, individual interventions. / Much of DFID’s work in the OPTs and the near region is carried out in partnership with large multilateral organisations, such as UN agencies. Multiple layers of bureaucracy and cumbersome procedures mean many of these organisations lack the speed and flexibility needed to support small-scale, rapid interventions which can take advantage of windows of opportunity or address new risks to stability. Organisations which are capable of doing this work often do not have the capacity or finances available to carry out the intervention when needed. An ability to support a range of interventions would enable the programme to maintain maximum flexibility and resilience. This type of work also informs our own programme and has significant impact in taking forward UK lobbying priorities.

## Section A: Detailed Output Scoring

Output 1: Strengthened evidence base for DFID, Palestinian Authority and other partner's programmes and policies / Indicator: Number of high quality new studies disseminated within time frame agreed in proposal form / Milestone 2012: conduct 2 studies
Output 1 score and performance description: / Score A, Output met expectation, 2 studies conducted
Progress against expected results: / Two SIF4 projects started in August 2012 to help strengthen the evidence base for DFID, Palestinian Authority and other partners programmes and policies. / Project 1: Deployment of emergency preparedness and response officer. / DFID has funded UNRWA to finance the deployment of an emergency preparedness and response officer. Their role is to improve UNRWA’s emergency preparedness and response measures, by bringing together existing and best practice in emergency preparedness and using these to put mechanisms in place to ensure UNRWA can respond adequately to multi-hazards and potential threats. This will ensure that essential services are maintained for Palestine refugees at time of political, environmental and humanitarian instability and will also identify priorities for further work on emergency preparedness. / Hiring of officer took place late August 2012. This was later than expected due to on-going regional situation which affects UNRWA field operations. However consultant has made good progress and is on track to deliver against the agreed activities and outcomes. To date Consultant has: / Finalised and standardised tools / Moved forward with linking emergency preparedness and response with wider agency planning processes such as integrated risk management, security and safety framework and IT recovery. / Worked with UNRWA field officers on implementing new coherent emergency preparedness and response planning methodology. / Project 2: Research into links between economics and conflict in the Occupied Palestinian Territories (OPTS) / DFID has established an Accountable Grant with the Overseas Development Institute to research the links between economics and conflict in OPTs. Understanding the truth on this issue is important to inform Palestinian, Israel and international approaches to the conflict. / The research will significantly expand and improve on the existing evidence by: / Establishing direction of causality to make it easier to draw policy implications / Looking at the wider measures of the conflict in particular will broaden the scope of analysis to include the attitudes to conflict (both through opinion poll surveys and voting behaviour) / Comparing economic and non-economic drivers / Researching the time horizon of effects, distinguishing between short and long term effects as long term effects matter more when it comes to putting an end to a conflict episode. / Producing the first coherent description of the conflict across different localities for both the West Bank and Gaza over a long period of time (i.e. first intifada and 2010)Exploring the effects of economic variables not only on the intensity of the conflict but also on the onset of violence spurts. This is important as reductions in violence are different from the end of violence. / To date the researcher has collected one of the largest datasets on economic, socio-demographic and conflict related variables at the locality level in the OPTs and has been analysing the data. Main results will be presented shortly, at the DIW, a prominent German research centre working on conflict issues. The public sector paper will be presented at the 2013 annual World Bank conference on development economics. / Recommendations: / Regularly hold brain storming sessions with DFID State building, Wealth Creation and Poverty and Vulnerability Pillar leads. First session to take place in first quarter of new calendar year. / Keep the overall target on logical framework as is but amend 2013 milestones to two. Four studies might be over ambitious for this period. / Project Officer to actively encourage projects to present studies within required timeframe by setting clearer milestone for data collection, analysis and write up of papers. / Continue to use local consultants to keep costs low and negotiate daily consultancy fees downwards / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: High quality innovative pilots conducted for scale up / Indicator: Number of innovative pilots conducted / Milestone 2012: conduct 1pilot
Output 2 score and performance description: / Score C, Outputs substantially did not meet expectation, 1 pilot planned but none carried out.
Progress against expected results: / Two pilots were submitted, one was refused after further exploration showed it did not fully meet the SIF criteria. The second was cancelled after DFID learned a similar pilot was being undertaken by another organisation therefore did not feel that it was value for money to continue with it. / Project officers changed in the first year which left a management gap of 4 months which had an impact on encouraging State building, Wealth Creation and Poverty and Vulnerability Pillar leads to push forward high quality proposals. / Recommendations: / New project officer will increase support to DFID Pillar Leads to help produce high quality proposals / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthened influencing across donor and wider community / Indicator: Number of specific influencing activities which take place to bring together different actors / Milestone 2012: conduct 1activity
Output 3 score and performance description: / Score A, Output met expectation, 1 activity planned and 1 carried out
Progress against expected results: / As part of the UNRWA emergency preparedness project, DFID has asked the emergency preparedness officer to carry out influencing activities which bring together different actors, utilising workshops or other mechanisms to engage different stakeholders. The purpose of these influencing activities will be to get other organisations thinking about how they can better coordinate emergency preparedness activities in UNRWA’s fields of operation. The influencing activities will take place towards the end of the six month project so are planned but not yet complete (although the emergency preparedness officer has had some initial meetings with stakeholders to lay the ground for future influencing events) We judge this indicator to be achieved as the milestone “conduct one activity” refers to incorporating one such activity in a SIF project, to be completed by the end of that project. We are on track to do this. / Recommendations: / Hold discussion sessions with other donors in addition to DFID Pillar Leads, to explore possible future activities that could be achieved through SIF. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y/N / No / 1.2 Overall Output Score and Description: / Score B, Outputs moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / After discussions with implementing agencies a common theme was identified. Both believed that longer timescales would give better achievements due to the time required at design and implementation stages.
1.4 Summary of overall progress / The project is producing useful research which is improving the evidence base in OPT. Two studies have been produced and there has been some influencing activity. Two innovative pilots were explored although did not come to fruition, one for value for money reasons and the other did not meet the SIF criteria on further exploration.
1.5 Key challenges / The main challenge is encouraging DFID Pillar Leads to take time out from their busy schedules to consider and submit ideas to SIF and work with the new project officer to help translate them into projects. There also has to be more discussion with other donors, organisations etc. to ensure time is not being wasted on exploring duplicate ideas. / Producing the number of studies given in the logical framework, for each year of the project, will pose some problems, although the focus should be more on quality than quantity.
1.6 Annual Outcome Assessment / The project’s outcome is expected to be met over the lifetime of the project and should continue to produce useful research to improve the evidence base in the OPTs. The milestones in the logframe should be reviewed to give greater flexibility in the number of studies completed each year and should also consider extending the life time of individual projects up to 15 months to allow more time for design and implementation. The overall target on the logframe should remain the same.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / No. For 2011/12 there have been bids of £140,000 for projects to the end of the current financial year, there will not be a fixed amount for each year which cannot be exceeded, but there will be a target for each year to ensure that the funding is spent across the term of the project; so the profile which was suggested is as explained below; / 2011/12 - £140,000 / 2012/13 - £286,000 / 2013/14 - £287,000 / 2014/15 - £287,000 / . / The actual first year of the project during which the projects took place was 2012/2013, the budget for the two projects in total is £155,912. Since spending for these projects are preferred to be on accrual basis, the actual spent amount until the reporting period is £14,600. / 2.2 Key cost drivers / The key cost drivers of SIF are consultancy rates and admin costs for providing venues for influencing activities. / 2.3 Is the project on-track against original timescale: No / No, the project is off-track against the original timescale. It became live in December 2011 and the actual funding of submissions took place August 2012. The overall project budget should be reviewed and modified accordingly.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no new evidence currently available which challenges the project design or rational, if anything the project itself is helping to improve the availability of evidence in OPTs, for example the study on Economics and Conflict. / 3.2 Where an evaluation is planned what progress has been made? / Given the relatively small budget, it is judged that this Annual Review is sufficient and an Evaluation will take place at the end of the project.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium / 4.2 Assessment of the risk level / Progress of this project has been slow, due to changes in staffing, and lack of initial ideas which was down to not understanding the processes involved. There has now been a restructure of the team for more support and relevant staff now has a better idea of how funds can be used so it is envisaged that risk level should reduce.
Risk of funds not being used as intended / Very low, since all spending is made against invoices provided by a reputable international consultancy partners. / 4.4 Climate and Environment Risk / There is not judged to be any impact either positive or negative.

5. Value for Money
5.1 Performance on VfM measures / SIF 4 provides an opportunity to improve value for money by: developing innovative approaches to maximise project outcomes relative to costs; providing evidence to ensure our projects remain appropriate and effective in a changing environment; leveraging input from others to deliver greater impact and reducing duplication. One of the focuses for SIF interventions will be identifying efficiencies, for example through alternative delivery models for United Nations Relief and Work Agency services in Palestinian refugee camps. Lower transaction costs (by reducing the need for separate project management, implementation and monitoring arrangements) means this option is likely to deliver greater value for money. / 5.2 Commercial Improvement and Value for Money / Since SIF4 provides various implementing organisations with the opportunity to propose and implement projects that comes under SIF4; each organisation could implement the project according to its procurement procedures, as long as they are in consistence with DFID VFM. Some partners agreed with DFID that they will pay the expenses of the project until it’s finished, and DFID after receiving the narrative and financial report supported with all the documents, will pay them on accrual basis. / We will continually strive to make use of local consultants in order to keep costs low and as with all OPTs projects will scrutinise budgets and negotiate daily consultancy fees downwards. / Role of project partners / Partner UNRWA: Produce Emergency preparedness plan; The project will be cash-in-kind support. Cost efficiencies will be gained by placing the incumbent in Jerusalem under the direct supervision of the HQ Emergency Officer, with direct access to the West Bank Field Office. UNRWA will also cover the cost of travel to and from Gaza, and Jordan (not included in the budget). However, the majority of the communication will be done through email, video and telephone conferencing to reduce costs. / Partner ODI: Research into the links between economics and conflict in the Occupied Palestinian Territories (OPTs); Economy: the researchers’ daily rate of £500 is slightly below the market rate (given the researchers’ expertise and competence) as the research is of particular interest to them. In addition, ODI’s administrative fee has been reduced from the usual 20% to 10% and applies only to the researchers’ cost. This compares favourably to the industry’s practice for such research projects. The value of ODI’s involvement would include the association of the research to one of the most reputable research institutions working on international development and humanitarian assistance, ODI’s experience in managing efficiently relatively complex contracts involving multiple transactions, and ODI’s editorial and online communications services, which may be important to enhance the outreach of the research’s findings. / Efficiency: the average direct cost per paper is below £28,000, which compares favourably with the production of high quality international academic research.[1] That also includes the policy briefings in English, Arabic and Hebrew. Even taking the gross costs into account (i.e. including all of the project’s costs), the cost per paper is £33,300, which is still on the low end of the spectrum for research of this type. The relatively low cost in this case is a product of two things. Firstly, low data collection costs due to the team’s extensive knowledge of data in the OPT context as well as good access to the data sources. Secondly, economies of scale from the three research projects being produced together: data collection is done more efficiently together for all data sources by the same research assistant; the international advisor can contribute more effectively since the research pieces are interrelated; and the research findings can be disseminated together as one package. / 5.4 Does the project still represent Value for Money : Y/N / Yes / 5.5 If not, what action will you take? / Not applicable
[1] This is based on anecdotal evidence on funding/paper ratios for a few research projects on economics and conflict from researchers at UC San Diego as well as at the Hebrew University.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Future recommendations: Arrange meetings with Pillar Leads to discuss future possible SIF4 projects / Extend the life time of future projects, to reach a maximum of 15 months, which allows more time for planning, implementing and reviewing / Keep overall studies target the same on the logframe but change the milestones to give greater flexibility on the number of studies to be completed each year.

8. Review Process
Review submitted by: Sanabel H. Halawani (SIF4 project officer) / Date: December 10th 2012 / Information sources: / Direct feed-back from partners / Correspondence sent from partners via e-mail / SIF4 BC and log-frame / Emergency preparedness Plan BC and Log-frame / Research into the links between economics and conflict in the Occupied Palestinian Territories (OPTs) BC and log-frame