Project Completion Review – post April 2018

Title: Zambia Social Protection Expansion Programme
Final Programme Value £38,365,691	Review Date: / August 2018
Programme Code: / 200625	Start Date: / March 2010	Final End Date: / June 2018

Summary of Programme Performance

Year	2011	2012	2013	2014	2015	2016	2017	2018
Programme Score	82.5	A+	A	A	B	A	A	A
Risk Rating	Medium	High/Medium	High/Medium	High/Medium	High	Major	Major	Major

DevTracker Link to Business Case: / Intervention Summary	No Business case as programme was approved before 2011 through a programme memorandum / http://iati.dfid.gov.uk/iati_documents/3087585.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5505916.xlsx

A. Summary and Overview

Description of programme and what it has achieved

DFID has been supporting the Government of Zambia (GRZ) to pilot and evaluate the Social Cash Transfer (SCT) programme since 2005. The Social Protection Expansion Programme (SPEP) was approved in 2010 to provide £38.4 million to expand coverage of the SCT and gradually roll it out as the basis of a national social protection system.

SPEP was designed to provide financial aid to the Ministry of Community Development and Social Services (MCDSS) to directly finance transfers and related administration alongside technical assistance (TA) though UNICEF to support MCDSS develop the systems to deliver the programme and to evaluate its impact. The programme also supported the direct procurement of goods to enable MCDSS to implement the programme.

The SCT programme provides small grants of approximately £7 per month to extremely poor households with elderly members, people living with a disability, people with chronic illness or in which few people are able to work. It was designed as a response to Zambia’s high levels of poverty and inequality – despite strong economic growth and classification as a Lower Middle Income country, 54.4% of the population live in poverty, with rural poverty rates of 76.6%.

As part of the TA, DFID funded a multi-year impact evaluation. The results have consistently shown that SCTs are effective in reducing extreme poverty and ensuring household food security. Positive impacts have also been seen on a range of other areas like health, schooling, child material well-being and asset ownership. The grant is used to buy food, pay for school fees and invest in productive activities (e.g. purchasing livestock); this not only reduced poverty and food insecurity but can also increase household resilience to future economic shocks.

This evidence has been used to inform Zambian social protection policy, but has also provided vital information on the impact of cash transfers in Africa and their transformational potential. The impact of this evidence goes beyond Zambia and has become a global public good in influencing regional poverty reduction policies.

One of the most significant achievements of the programme has been the increase in GRZ commitment in the programme, from political and policy pronouncements through to increased budget allocation and releases to the programme. Since 2010 the SCT has gone from being approximately 20% GRZ financed to 70%, coverage has extended from 25,000 households to 537,766[1]. Social protection is now recognised by GRZ as a key feature of poverty alleviation and inclusive economic growth. The National Social Protection Policy (2014) and the Seventh National Development Plan (2017) both contain strong commitments to expanding coverage of the SCT and improving efficiency and effectiveness of the programme through better coordination and linkages with other initiatives.
[1] At last payment (June 2018). There are now 574,663 households enrolled on the programme and present on the MIS, but these additions took place during 2018 and the additional households have not yet been paid

This increase in political and financial commitment was at least in part a result of many years of advocacy from the UK, other CPs and the Ministry of Community Development and Social Services (MCDSS), drawing on the results of SCT impact evaluations and amplifying the voices of beneficiaries with decision makers. The programme has provided important lessons to DFID Zambia on how to work with GRZ and influence policy decisions. Central to the success of the programme was identifying an area where there was a potential alignment of interests, generating evidence that there was an affordable, effective and popular solution, and building a coalition of influential supporters of the programme. These lessons are informing DFID Zambia’s approach to policy influencing and advocacy.

As a result of increased GRZ ambition, particularly their desire to increase coverage of the programme faster than initially anticipated, DFID and other CPs agreed to increase their financial support. This lead to DFID Zambia designing a second phase of the programme in 2016, the Social Protection Expansion Programme Phase 2 (SPEP 2), bringing forward disbursements under this programme and agreeing to close it early in 2018. SPEP 2 continues our support to scaling up the SCT but with a greater emphasis on systems strengthening and financing a smaller proportion of direct transfers. This continues our commitment to strengthening Zambia’s ability to take on full ownership and financing of cash transfers by 2021.

Whilst the programme has exceeded expectations in terms of coverage, GRZ ownership and sustainability, it should be noted that progress on SCT implementation has been mixed. There have been a number of systems improvements, including introduction and use of a new electronic Management Information System (MIS) to replace the initial paper based information management and the introduction of mobile based registration (M-tech) to increase the speed and accuracy of targeting and enrolment. However, systems development has not kept pace with programme expansion, and core areas such as grievance redress and electronic payments have not been developed. These systems weaknesses have repeatedly hampered efficient delivery of the SCT, and currently pose the greatest risk to programme sustainability.

Partial and unpredictable funding releases from the Ministry of Finance (MoF) result in non-payment of benefits for 6 months in 2016. Despite efforts to get back on track, continued erratic disbursements have meant that arrears have never been fully cleared – the last payment was processed in June 2018 and covered the January-February 2018 payment window. Failure to pay regular transfers is a key factor driving up the cost transfer ratio and reducing the efficiency of the programme. These issues are explored further in the Value for Money section.

Follow up actions required following approval of this report:
- DFID Zambia continues to support the social protection sector through SPEP 2. This programme recently had its second annual review, where specific issues related to reliability of GRZ disbursements, timeliness of payments to beneficiaries, delivery system weaknesses, programme risk and value for money have been discussed. SPEP 2 has the opportunity to improve these systems and strengthen the delivery of the SCT. Ongoing monitoring of these issues will therefore continue. The SRO should ensure all recommendations from this PCR are translated into the SPEP 2 delivery plan by November 2018.
- A large number of physical assets were procured under this phase of the programme. These have been handed over to the MCDSS, however it will be important for DFID to maintain some level of assurance during SPEP 2 that the assets continue to be used to implement and monitor the SCT. The programme officer should come up with a light touch asset monitoring plan for the remainder of SPEP 2 and incorporate this into the delivery plan by December 2018.
- The programme team should reflect on the processes of risk and results management and share this learning across the DFID Zambia office. This should particularly look at the process for updating risks and reflecting on past risks to inform mitigation strategies, and the process for updating logframes when the scope or focus of a programme changes. The SRO should lead this process in consultation with the Human Investment Team Leader and report back to the Head of Office in October 2018.
- A review of previous annual reviews have identified a number of recommendations that are not specific or time bound to enable an assessment of whether they have been successfully actions. Going forward, DFID Zambia programme teams should ensure that all recommendations are specific, with a responsible person and timeframe for delivery. Higher level recommendations related to policy advocacy, GRZ commitment etc. should be incorporated into logframe indicators if they are central to programme success.
- Beyond programme delivery issues, there are a number of follow up actions that the team should consider to maximise the impact of the investment in the social protection sector. These are not specific, time bound recommendations, but should inform the design of any new interventions that DFID may support in the social protection sector in Zambia.
  - Strengthen linkages to broader social protection and social sector programmes and services to maximise impact. Evidence shows the importance of an integrated approach. DFID should examine how to develop synergies with other initiatives including on governance, anti-corruption, taxation and systems strengthening in health and education
  - Maximise the UK – GRZ relationship to proactively raise the issue of long-term SCT financing, including the impact of delays in payments. This should include a long term advocacy strategy from DFID, UNICEF and other CPs.
  - Build on the success of the evaluation of the programme and continue regular impact assessments and reviews to provide robust evidence of the value and impact of the programme. This should feed into a longer term advocacy strategy and a MCDSS owned monitoring and evaluation strategy to drive programme efficiency and effectiveness and inform future strategic planning on the allocation of resources.

## B: DETAILED OUTPUT SCORING

Output Title	99,000 targeted recipients receive regular social cash transfers by 2015
Output number per LF		1	Output Score	A
Impact weighting (%)?		40	Impact weighting % revised since last AR?	No

Indicator(s)	Baseline (2010)	Target	Progress
1.1 No. of recipients receiving timely and regular payments (DFID attributed); % female (on 31st December, except baseline which is pre-programme)	12,500 (8,300); 60% female	500,000 (60,000) households 60% female, 10%disabled	Met expectations: 574,663 enrolled in the programme (i.e. households that appear on the programme Management Information System), 537,766 (86,042[2]) were enrolled on the programme at 31st December households and included on the 3 payments processed in 2018. Of these, 71% are female headed and 13% are households with a disability. / Challenges with one of the payment service providers has resulted in a number of these beneficiaries not being paid, these numbers range from 18,380 not paid for the November/December payment to 139,371 not paid for September/October. A full verification exercise is ongoing.
1.2 No. of beneficiaries of cash transfer programmes (DFID attributed)	62,500 (41,700)	2,500,000 (300,000)	Met expectations: Assuming an average household size of 5, there are currently 2,688,830 beneficiaries of cash transfer programme. / Total attributed to DFID: 430,210.
1.3 Maximum delay in making transfers available to recipients	6 months	2 months	Did not meet expectations: / The programme is now 3 payment cycles late (i.e. 6 months). Payments have been made more regularly in the last 6 months, however arrears accumulated in 2016 and 2017 could not be cleared to allow the Ministry to resume its normal schedule. Transfers were paid in January, March and June 2018. However, none of these related to the correct payment window, with the June 2018 payment covering the January-February 2018 window.
1.4 Proportion of recipient households in extreme poverty / extreme food insecurity (targeting assessment).		Not measured
[2] The DFID attribution for results is measured on the basis of the proportion of contribution to the overall cost and is calculated using the latest available data.

Provide supporting narrative for the score

The programme has significantly exceeded expectations on the number of poor people reached with cash transfers, with UK support the programme has transitioned from a small, donor funded pilot programme in 2010 into a national cash transfer reaching over 15% of the population.

Social cash transfers continue to have a positive impact on people living with disabilities, supporting some of the poorest and most vulnerable Zambians to meet their basic needs. New targeting criteria agreed for the 2017 expansion not only continued to prioritise households with elderly members or people living with disability, but has also ensured a more inclusive definition of vulnerability, incorporating child headed households, the chronically ill and female headed households supporting many children.

Progress against indictors 1.1 and 1.2 has significantly improved over the last year, with a total caseload of 537,766 households receiving payments and 574,663 enrolled in the programme. Female headed households account for the majority of the recipients at 71%, and the proportion of households that have a disabled member also increased from 12% in 2016 to 13% in 2017. This translates into 80,499 persons with a disability receiving support through the cash transfer.

The programme has almost tripled the number of registered beneficiaries this year; representing a 310% national increase. However, in terms of indicator 1.3 - disbursing payments on time – significant challenges caused by delayed disbursements from both the Ministry of Finance and donors, the pressure of the massive scale up and subsequent challenges with Payment Service Providers have resulted in ongoing payment arrears of 6 months, or 3 payment cycles. This has been an ongoing issue since large arrears were accumulated in 2016 due to lack of resources and in 2017 due to the scale up. 3 payment cycles have been implemented in the last 8 months, but progress is not fast enough to clear arrears accumulated during the scale up. At August 2018 there were insufficient resources to process another payment round, and the risk of increasing arrears is again present.

Given these challenges, whilst the number of enrolled beneficiaries has exceeded expectations, payments have not been timely and therefore the output is considered met rather than exceeded. There is a real risk that the success of the programme expansion will continue to outpace resources for the programme, causing further implementation challenges in future years. This is an area that has been highlighted in the second phase of UK support to the programme, the Social Protection Expansion Programme Phase II (SPEP 2), and will continue to be monitored closely.

Indicator 1.4 was removed from the logframe as plans for a targeting assessment will take place following the completion of the massive scale up in 2018. This will now be taken up in the next phase of the programme. Whilst a formal assessment was not completed in 2017, throughout the course of the programme evidence was generated on targeting. This included qualitative assessments of the targeting, which found that both beneficiaries and their communities found the targeting to be fair; however, they were unclear on the role of the Community Welfare Assistance Committees (CWACS). This assessment fed into changes in the targeting process, with CWACs taking on more of an information and communication role and being removed from selection of specific households. This was welcomed by both communities and CWACs themselves, who felt that it removed pressure from their role.

Whilst the success of the scale up is noted, and is a positive outcome of many years of advocacy and investment in pilots and evidence generation, it is now crucial to focus on improving the timeliness and predictability of the cash transfers. Delays may result in reducing positive impact on recipients, increasing risk of corruption and fraud and undermining credibility and trust in the programme. With continued delays in paying out transfers, there may be a growing perception of misappropriation of funds by civil servants and increasing frustration at community level.

MCDSS has been engaging closely with donors and MoF to normalise the flow of disbursements, and in the next phase of the programme greater advocacy efforts should be focused on getting the systems to work well before further expanding coverage of the programme.

Lessons identified this year linked to this output and recommendations for future programmes

- Strong accountability to beneficiaries for making correct and timely payments is crucial to the success of the programme, and evidence from cash transfer programmes repeatedly demonstrates that regularity is essential to the effectiveness of this type of programme. DFID should continue to work with MCDSS to make clear decisions about how best to deliver cash transfers – whether to devise a new and more realistic payment plan and to agree a process for clearing payment arrears. DFID should also explore more support to social accountability, recognising that beneficiaries have limited voice and additional channels to raise concerns about delayed payments could support MCDSS headquarters to address these in a timelier manner.
- As women and PWDs make up over 60% and 10% of the total target respectively, DFID in consultation with other stakeholders should develop tools to track and better understand the distributional impact of cash transfers on women, PWDs and other vulnerable groups.
- The ZSPEP enrolment and registration process has relied on a National Registration Card (NRC) issued to beneficiaries by the government. As the programme has been scaled up nationwide, the importance of having an NRC will be crucial to the beneficiaries. The national ID registration process, which will form the basis of ensuring eligible beneficiaries are enrolled in the SCT, currently faces challenges. These include exclusion of many older, disabled and other vulnerable groups because they cannot afford the fee for the NRC registration; and due to the longer distances/ transport issues. ZSPEP II should work closely with the relevant stakeholders to address this issue. This could also be used as an opportunity to link the SCT programme with the wider governance issues i.e., getting more people registered will also enable more people to vote.
- As the programme has undertaken national scale up one emerging issue has been a lack of clarity between households listed, enrolled on the programme and actually receiving payments. To address this, SPEP 2 should introduce process indicators to clarify the numbers of households actually receiving payments rather than those that are on the MIS.

Output Title	GRZ implements SCT programme in an efficient and sustainable manner.
Output number per LF		2	Output Score	A
Impact weighting (%)?		60	Impact weighting % revised since last AR?	No

Indicator(s)	Baseline (2010)	Target	Progress
2.1 Operating costs (Total admin costs including procurement of goods, services and M&E)	26% (44%)	25% (35%)	Did not meet expectations: 35% (38%)
2.2 % of funds reported to have been misappropriated according to final annual audit report	Less than 1%	less than 1%	Met expectations: 2016 audit was completed. As with previous audits, a number of issues were found related to unsupported payments and delayed payments of statutory obligations (tax and pensions). These were addressed and closed, with the exception of a case of misappropriation which accounted for 0.03% of the audited funds.
2.3 Government funding to SCT programme in ZMW budgeted and released (% of total)	4,000,000,000 (11%)	ZMW 550m budgeted for 2018; GRZ allocation is 75% of total, 2017 releases 70% of GRZ allocation	Met expectations: ZMW 550m budgeted for 2018, 76% of the allocation for 2018 but only 61% of programme budget (due to large budget shortfall for 2018). / 2017: 353m released (71% of allocation)
2.4 Management systems in place	Project implementation structures not in place	Annual Statement of Progress action plan agreed between MCDSS and CPs	Met Expectations: The ASP was shared with the MCDSS in March 2018 and an action plan developed with support from UNICEF’s Financial Management and DFID’s financial management consultants.
2.5 CP support to the programme	-	Two CP and Ministry management meetings, 1 FTC meeting, 1 meeting with the PS	Met expectations: 2 management meetings have taken place as planned, with 2 additional ad hoc management meeting and a ‘deep dive’ session. There have been 2 meetings with the PS. The FTC ToR is being revised and it has not met, but is scheduled for 4 September. Financial management and the ASP have been added to the routine management meeting agenda.

Provide supporting narrative for the score

During the course of this programme, the implementation of the Social Cash Transfer has been completely transformed given the changes in scale and complexity of the programme.

Over the past 8 years the programme has migrated from a manual management information system to an electronic platform decentralised to all 10 Provinces and manual processing of new beneficiaries has been replaced with mobile registration to improve efficiency. Government budget allocation and releases have improved, enabling the massive scale up of the programme ahead of schedule. Two Fiduciary Risk Assessments and one Annual Statement of Progress completed during the course of the programme identified high risks in relation to financial management and corruption, but were accompanied by action plans to address weaknesses that contributed to a positive direction of travel (as noted in the 2017 Annual Statement of Progress). There have been constant improvements to delivery systems, but these continue to be outpaced by programme scale up. This is discussed further in the risk section below, which highlights the severity of the risk around systems failure in the context of achieving national coverage during the 2017 and 2018 scale ups.

Output 2.1: Operating costs are higher than expected, and are higher than at any point since 2010. This is primarily due to the fact that the SCT programme is in the process of a large scale up. Such a scale up requires a substantial operating budget, including new procurement of vehicles, establishing new district offices, hiring additional staff, and the large costs associated with community sensitisation, targeting and enrolment. This was exacerbated by delayed payment to beneficiaries that reduced the proportion of the budget spent on transfers. Whilst these circumstances are not expected to be repeated in the coming years, overspending on administrative budget centres has been a repeated feature of the programme and has now become somewhat routine. DFID and MCDSS should reassess the targets for operating costs to ensure they are realistic, and during SPEP 2 DFID should engage more proactively with the MCDSS to monitor these expenditures, and introduce ceilings where appropriate. This issue has been picked up in the 2018 annual review for SPEP 2.

The operating costs were almost two times higher than predicted in last years of the programme, and typically this would pose a risk for overall value for money of the programme. Whilst there are questions on the overall efficiency of the programme (see value for money section below), the review team feels there is also an issue related to inappropriate targets. The targets for these years were set before plans for a scale up, and should have been reconsidered on the basis of a rapidly expanding programme and be realistic given the operating context.

Output 2.2: Throughout the course of the programme the Social Cash Transfer has been subject to an annual audit from the Office of the Auditor General (OAG). The key indicator for the programme, having less than 1% of funds reported to have been misappropriated, was set when the budget was significantly less than it currently is. The reflected the known high risk of petty corruption. Whilst audit reports have not found widespread instances of misappropriation of funds, there have been consistent findings of delayed statutory payments and transactions that are missing appropriate approval and documentation. Whilst these are generally of a low value and usually closed through follow up action with the OAG they point to systemic challenges in financial management within the MCDSS. As noted in the delivery section below, the programme has never had an audit committee to follow up on OAG recommendations, and this is something that should be considered under the second phase of the programme.

Output 2.3: The growth in Government funding to the programme has been a huge success, and is unprecedented in the region.  The increase in GRZ funding and inclusion of additional donors has resulted in a significant reduction in DFID’s share of the budget from over 70% to less than 20%. This is a good indication of sustainability but as it has been pointed out earlier, regularity of disbursement is still a challenge.

The government has shown political and financial commitment, especially in the last few years (2016-2018) and this is arguably the greatest success of the whole programme. This high level political support is partially due to the evidence generated under this programme, and ongoing advocacy from the MCDSS and CPs in relation to the benefits of social protection. Whilst releases are not 100% of the budget, this has also been improving in recent years.

Output 2.4: Financial management has been problematic, especially as the programme has expanded and additional pressure put on weak management and reporting systems. There has been some improvement, with the recruitment of the financial management specialist at the end of 2016, 10 Provincial accountants in 2017 and the introduction of improved financial reporting and accounting templates at both the headquarters and district level. An action plan to improve financial management was agreed after the 2015 Annual Statement of Progress (ASP), the 2017 ASP noted a positive trajectory on fiduciary risk, but was maintained at the same risk rating due to additional pressures of the massive scale up and the introduction of new payment mechanisms. A new ASP action plan has been presented to CPs and should contribute to improved reporting and reducing risk levels, and whilst financial reporting is still not up to the standard required for a programme of this size it has significantly approved in the first half of 2018.

During the course of this review an increase in fiduciary risk was noted in relation to the use of third party payment service providers. This primarily related to opaque reporting lines and widespread beneficiary feedback on poor delivery capacity. This is being addressed as part of SPEP 2; more details are provided in the 2018 annual review of that programme and is now noted as the biggest risk to the programme.

Output 2.5: During the course of the programme, DFID, with support from other partners, has built the profile of SCTs and hence was able to not only secure substantial financial contributions from GRZ but also attracted two additional international donors – Sweden and Finland.  Over the course of the programme the relationship between CPs and MCDSS has been extremely strong, although the pressure of the scale up in 2017 and changes of key personnel in all donors and in the Social Welfare Department did lead to challenges after the 2016 elections. These challenges appear to have been addressed, with a close working relationship re-established between the Social Welfare Department and CPs. Overall the MCDSS has welcomed CP support and regular engagement with officials and the PS has been re-established. The relationship has further been strained by an increase in fiduciary risk related to payment service providers, and maintaining this relationship is something that DFID should continue to prioritise in the future to ensure systems strengthening work can be given the level of attention it requires.

MCDSS particularly appreciated the work of DFID and the CPs in delivering evidence that was used to advocate effectively to ministers for the scale up. The Ministry has stressed that CPs should continue generating evidence that can be used for advocacy, especially in the areas of the MIS, the emergency cash transfers and work on disabilities.

Lessons identified this year linked to this output and recommendations for future programmes
- Through ZSPEP II, the MCDSS and other partners should continue working on improving reporting and monitoring tools, particularly budget templates, district monthly and quarterly reports, management information system. This improvement should not be focused on donor reporting, but also on providing accurate management information for decision making in MCDSS headquarters.
- A key lesson is that the cash transfer delivery systems are not yet strong enough to withstand financial pressures. GRZ commitment to a nationwide scale up is a huge achievement, but this scale up has put excessive pressure on weak systems, bringing them close to collapse. Going forward, DFID and other partners should focus more on strengthening systems including agreeing specific success measures to assess systems development against.
- Going forward, DFID should focus more on the systems needed to establish a national social protection system, and how continued advocacy, influencing and social accountability could increase the predictability of GRZ resources for social protection. This should include continued advocacy for, and monitoring of, the roll-out of the grievance mechanism and electronic payment system alongside other systems such as M-tech, MIS and targeting.
- The relationship with the MCDSS and other technical partners needs improvement with work particularly on creating good communication patterns and building trust. Whilst the ZSPEP communication strategy worked in terms of creating awareness and presence, ensuring visibility, information provision and attitude change, it is recommended that ZSPEP II identifies its own set of communications issues to deal with, paying particular attention to communication to beneficiaries and community stakeholders and channelling beneficiary voice and community concerns back into MCDSS and national decision making fora.
- During the course of this review partners recommended that DFID should make more of their own technical staff, including sharing lessons and good practice from other DFID supported cash transfer programmes in the region. DFID has the opportunity to be more involved in building capacity and technical skills of the UN and the ministry staff and should agree the extent to which this can be realised under SPEP 2.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The programme outcome – Households receiving social cash transfers have improved standards of living by 2015 – is measured against six indicators. Progress against these indicators was measured through the impact evaluations for the Child Grant and Multiple Categorical Grant published in 2016. These evaluations showed a positive impact at beneficiary level and results were consistent over time.

In addition to eating more meals and being more food secure, families are also improving their housing conditions, buying more livestock, buying necessities for children, reducing their debt, and investing in productive activities.

The results from these surveys are summarised in the table below:

Outcome Indicators	Baseline 2010	Target (2016)	Achieved*
Food security: % of hhs receiving SCTs having no more than 1 meal per day	21%	10%	Substantially exceeded expectation: 1% / (5pp programme impact)
Education: School enrolment in hhs receiving SCTs	64% of school age children enrolled	90% of school age children enrolled	Met expectation: / 90% (No significant difference between treatment and control)
Health: Proportion of people reporting illness in previous 2 weeks	14%	10%	Moderately exceeded expectation: 8% / (No significant difference between treatment and control)
Child wellbeing: % of children in hhs receiving SCTs with all 3 material needs (pair of shoes, change of clothing and blanket)	11%	No milestone[3]	Substantially exceeded expectation: 71% (32pp programme impact)
Women's empowerment: % of women making sole decisions (in 4 or more out of 7 scenarios given)	61%	No milestone	Not measured (large impacts on savings rates and amounts saved)
Improved livelihoods: Proportion of hhs with livestock (chickens)	50%	No milestone	61% of hhs had livestock (26pp programme impact)
[3] No additional targets were set for 2017 and 2018. The outcome of ZSPEP related to the programme theory of change, and once this was established through impact evaluation it was no longer regularly monitored. ZSPEP 2 has a different outcome statement, focusing on sustaining and institutionalising social protection in Zambia. These outcomes have been monitored in 2017 and 2018 and will continue for the rest of that programme.

 * 48 Month Child Grant Impact Evaluation (2016)

Outcome targets related to food security and child wellbeing were exceeded. There was an improvement on education and health measures; however, there was no difference between the treatment and control group[4]. As such this improvement cannot be attributed to the SCT programme. This may have been due to the relatively low value of the transfer and household prioritisation of food security and livelihoods investment, or due to challenges in the supply side of education and health services.
[4] A difference-in-difference (DID) approach was used to assess outcomes between project participants (intervention) and non-participants (control).

At impact level the programme aimed to reduce extreme poverty in districts covered by the SCT, measured through a reduction in the poverty gap index. The results of the programme evaluation demonstrated that the poverty gap was reduced by 10 percentage points (pp) due to cash transfers, exceeding the programme target. As such the overall assessment is that the programme has met its outcome and impact targets.

Key Successes & Achievements of the programme:

Impact on beneficiaries

Evidence continues to indicate that food security has improved among beneficiaries and improved nutrition is evident in a more balanced and nutritious diet. Investment in productive assets, particularly small livestock or graduation from small to large livestock was reported by most of the beneficiaries, whilst other beneficiaries invest in non-productive assets that contribute to household wellbeing, including repairing thatched roofs, upgrading to iron roofs as well as brick houses from mud.

In addition to the individual and household benefits listed below, evaluations found that the programme has also contributed to improving local economies in communities receiving the transfer. Most of the money is spent within the local community creating multiplier effects. For every Kwacha (100 Ngwee) transferred, beneficiary households have generated an additional 49 to 68 Ngwee in their local economy.

Specific household benefits include:
- The programme significantly improved many indicators commonly associated with resilience, the ability to manage and withstand shocks. The program resulted in significant increases in both non-agricultural (housing quality and possession of durable goods) and agricultural (livestock, tools) assets, implying that households are in a stronger position to withstand future shocks.
- Evidence from Zambia’s child grant impact evaluation[5] (99% of recipients were women) demonstrated that cash transfers doubled the number of women saving, and tripled the amount they saved. Cash transfers also led to a 50%[6] increase in participation in non-farm small businesses.
  [5] Zambia’s Child Grant Program: 48-Month Impact Report.
  [6] ‘Making Money Work: unconditional cash transfers allow women to save and re-invest in rural Zambia’ Natali et al, 2016.
- Findings from the evaluation of the Multiple Categorical Grants evaluation[7] suggest that programme has contributed to a 13% reduction in the poverty headcount among households receiving the transfer, (from 92% to 79%) compared to a 3% reduction in the control group (from 92% to 89%).
  [7] Zambia’s Multiple Category Targeting Grant: 36-Month Impact Report. VAULT ID: 27283534
- In households receiving the cash transfer there was a fourfold increase in the proportion of households meeting the basic material needs of children, including a spare set of clothes, a blanket and shoes (from 11% to 71%); almost three times the size of the increase in the control group (from 18% to 40%).
- Among cash transfer households, the proportion that owned a goat more than quadrupled from 6% to 26%; whereas in the control group it decreased by more than a third from 16% to 10%.

During field visits conducted as part of this project completion review, DFID staff further witnessed the results of the programme. Beneficiaries, especially women, older people and PWDs referred to the positive changes the cash transfers have made, including increased social inclusion, improved self-esteem and empowerment.

Increased coverage

- The programme has exceeded all expectations in relation to number of recipients and total beneficiaries. Approximately half a million households (over 2.5 million people) have been registered on this programme as of December 31, 2017. The programme has almost tripled the number of registered beneficiaries this year; representing a 310% national increase.
- Evaluations have shown that the social cash transfer targeting approach reaches extremely poor and vulnerable households, is generally seen as fair at the community level and has broad political support. This is the only nationwide programme of support to persons with disabilities, the elderly and poorest households.

Good evidence generation and innovative advocacy
- The programme generated evidence of impact, administrative feasibility and long-term sustainability that made the case for a national roll out.
- This programme and broader influencing by DFID and other donors has been instrumental in securing the programme scale up and increase in Government funding from 22% to 76%.
- As a result of continued advocacy and evidence building to increase political support and GRZ commitment, a National Social Protection Policy (NSPP) was approved in 2014. This policy has expanded the scope of the programme and aims to build a broader social protection framework for Zambia by including support for the development of the Social Protection Bill and establishment of a Social Health Insurance Scheme.

Improved efficiency

- Whilst challenges remain, the programme has improved existing delivery mechanisms by rolling out M-Tech registration process and the Management Information Systems. This has improved the accuracy and efficiency of the programme by ensuring fast data entry and improving data quality assurance.
- Whilst there have been significant problems in moving to an electronic payment system, efforts are underway to make this shift which is expected to improve the security and transparency of payments.

Summarise the programme’s theory of change and major changes to it in the past year

The overarching goal of the programme has remained the same since the programme inception – to reduce extreme poverty and vulnerability in Zambia. During the course of the programme different social cash transfer schemes have been piloted and tested to arrive at the current model, which achieves the stated objective of reducing poverty and vulnerability within the contextual limitations of administrative and political acceptability.

Over the last eight years, DFID has successfully supported the Government to take on responsibility for the programme, which is now majority-funded by Government. In 2016, DFID approved the Zambia Social Protection Expansion Programme Phase II (ZSPEP II) for up to £33.8 million for the period 2016 – 2020. This second phase has been designed against a backdrop of a highly successful and effective first phase, supporting GRZ in its ambition to increase the coverage of the SCTs whilst also increasing support on systems strengthening and adapting the programme to be able to respond to potential climate related shocks.

Explain major changes to the logframe in the past year

In December 2017 final year targets were agreed under the existing outcome and output indicators.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

DFID Zambia provided £38 million for programme implementation, this was initially planned to take place over 10 years between 2010 and 2020. The programme operated through the MCDSS, UNICEF and Crown Agents (and later AECOM Limited). The initial breakdown of funds was as follows:
- Financial Assistance (FA) for cash transfers, administrative costs and capacity building for a total value of up to £32 million, this was to be channelled directly to MCDSS through a pooled fund; and
- Technical Assistance (TA) for monitoring and evaluation, systems strengthening, a management agency to procurement goods to support programme implementation, and for an adviser to be based in UNICEF, for a total value of up to £6 million.

Spend against the budget was adjusted throughout the life of the programme to reflect changes in the programme context and allow for a shift of funds across components. The most significant realignment took place in 2014 to support the rapid scale up of the SCT programme between 2014 and 2018.

Following the decision by the government to scale up the SCT programme and to increase their own financial contribution to the programme, MCDSS requested a reallocation of funds from financial aid to technical assistance. This change was necessary for UNICEF to provide additional training and preparations for the scale up and for the procurement of goods for an additional 90 districts. This led to the reallocation of £12million towards technical assistance, leading to a revised breakdown of:
- Financial aid to MCDSS: £20 million
- Technical assistance, including the procurement of goods: £18million

This reallocation was considered good VfM as it would lead to increased coverage, generating economies of scale, and would maximise UNICEF’s comparative advantage in mobilising expertise and resources for training, increasing the efficiency of the scale up. A further adjustment was made in 2015, again updating the allocation to reflect changing context, the rapid scale up and decision by DFID Zambia to design a second phase of the programme. This reallocation resulted in a final breakdown of £26 million for financial aid and £12 million for technical assistance. Again this was considered good VfM as it increased the proportion of DFID resources going directly on cash transfers to the poorest.

The table below summarises spend against main programme components.

Budget: Zambia Social Protection Expansion Programme
Component	Spend	Percentage of overall budget

Financial Aid to MCDSS	26,144,509	68%
Procurement of goods	5,276,116	14%
Technical Assistance (UNICEF)	6,095,831	16%
Total	37,516,456

The remaining programme spend (approximately £700,000) was spent on direct procurement of services for the programme – for example contracting fiduciary risk assessments and specific pieces of policy advocacy – and embedded adviser in UNICEF and some scoping work on social pensions which was not taken forwards.

Key Costs and performance

No VfM indicators were set for this programme as it was designed and approved prior to the business case and smart rules systems. However, VfM in terms of cost transfer ratio (effectiveness) has consistently been monitored since the beginning of the programme and is discussed below. In addition to effectiveness, the programme has monitored other VfM indictors and conducted a good practice analysis in 2015 that found the programme presented good VfM. In 2016 the SPEP 2 business case identified a series of VfM indicators, and these informed a monitoring framework developed in 2017 to ensure that DFID Zambia has greater understanding and oversight of the key cost drivers and performance of the programme, and can engage partners more regularly to address any issues of concern. Where possible, these are discussed below as they relate to the first phase of the programme.

Financial Aid to Ministry of Community Development and Social Services

Financial aid to MCDSS took up the bulk of the budget at £26 million and made up 68% of total programme spend. Cash transfers were the main cost for the programme, accounting for an average of 70% of the budget across the lifetime of the project. The design of the cash transfer was the main cost driver, with the non-cash costs driven by issues such as targeting design and mechanism. Whilst the final targeting mechanism (multiple categorical with a proxy means test) is not the cheapest approach, it was the approach considered acceptable to communities, non-beneficiaries and politicians and therefore sustainability justified the additional targeting costs.

Efficiency
In 2017 transfers made up 65% of programme costs. This is a reduction from 71% in 2016 and 77% in 2015, and demonstrates a worrying decrease in programme efficiency in the last two years of the programme. The biggest driver of worsening efficiency is continued delays in the payment of transfers, with 6 months of arrears accumulating in 2016 and 6 months of delays in payment to new beneficiaries during the 2017 scale up. This has caused the spike in TCTR seen in 2017, with a significant increase in administrative spending at the same time as transfers were not being paid regularly. Essentially the programme scale up has outpaced capacity (both in terms of budget and delivery systems) whilst MCDSS continued to incur operational costs. Whilst transfers still make up the largest single cost item, the delay in payments to beneficiaries is driving administration costs up and consequently the total cost to transfer ratio.

In addition to transfers, the cost drivers relate to administration of the cash transfer, including costs for set up, programme roll-out, operations and monitoring. One of the key factors driving the administration cost is the choice of targeting approach. MCDSS made a decision to have an inclusion targeting mechanism which covers a range of vulnerabilities rather than more categorical approaches. Whilst global evidence has shown that universal approaches such as social pensions or child grants are cheaper, these are less acceptable in the Zambian setting as they are seen as targeting groups that are not particularly vulnerable.

Administration costs have largely stayed above the set benchmarks for other programmes in the region. At programme approval, administration costs were expected to reduce once the programme was at full scale and the systems developed. However, the scale up of the programme has progressed much faster than was envisioned whilst the implementing systems have lagged behind – the programme has not yet had a year of operating at scale without incurring all the costs associated with new targeting, enrolment and registration.

The table below shows the trend in the progression of administration costs and shows that the share has been increasing. This is being monitored more closely and DFID Zambia is in discussion with UNICEF and MCDSS regarding how costs can be capped and how funds can be secured to resume timely payment of transfers. This needs to be urgently addressed as part of DFID’s advocacy and technical support under SPEP 2 to ensure the programme becomes more efficient and can be sustained on domestic resources.

Summary spending and funding levels/ ratios
Ratio/ indicator	2017	2016	2015	2014	2013	2012	2011	2010
Total Government operating costs : transfers ratio	35%	29%	33%	24%	23%	26%	28%	26%
Total admin costs (incl. procurement) as a percentage of total spending	38%	29%	36%	43%	27%	35%	44%	44%
Government funding vs total spending	65%	65%	57%	54%	25%	26%	10%	19%

Effectiveness

A key indicator of effectiveness is the adequacy of transfer – whether the transfer value is sufficient to meet the needs the programme is aiming to support. The transfer value was initially set in relation to the price of maize, and in 2010 that value was K50 per month. This rose to K60 (2012), K70 (2014) and K90 (2017). Transfer value has been discussed on numerous occasions, with MCDSS generally opting to focus on expanding programme coverage rather than increase the transfer value. The Zambian economy faced major pressures in 2015 and 2016 which saw rapid inflation and a sharp deterioration of the real value of the transfer. Intense lobbying and advocacy from DFID and other CPs contributed to a decision from the Ministry of Finance to increase the transfer value in 2017 recognising that inflation had contributed to reduced effectiveness of the programme. This was a positive move, and with inflation relatively stable the adequacy of the transfer has been restored in the later years of the programme. However, beneficiary feedback repeatedly states that the transfer value is insufficient, and food prices have risen sharply over the implementation period. It is recommended that SPEP 2 supports a further adequacy of transfer study to gather more robust evidence and reengage in longer term advocacy around transfer values.

Equity
The programme has exceeded targets related to female headed households and households with a person with disability. Prior to national coverage, geographic targeting prioritised the poorest districts for enrolment on the programme and over time targeting categories became more inclusive to capture a greater range of vulnerabilities. The PCR field visits heard from beneficiaries and government officials that the programme has been successful in breaking stigma around disability, and increasing the visibility of both persons with disability and women in rural communities.

Sustainability
DFID contribution to the cost of transfers has reduced significantly from 75% in 2010 to below 15% in 2018. This is a strong indicator of sustainability, with the programme benefiting from increased GRZ financing and other donor support.

Technical Assistance through UNICEF

There were no VfM indicators set for UNICEF, this is a significant weakness in the programme and prevents a thorough review of performance. DFID Zambia is due to enter into a new agreement with UNICEF to support the social protection sector from 2019 onwards, as has been noted in the SPEP 2 annual review, this should be contingent on agreeing VfM indicators across the 4 E’s.

Economy
UNICEF delivered technical assistance to support the set-up of core systems to support the implementation of a national social cash transfer programme. This included support for monitoring and evaluation, policy, communication and advocacy and the set-up of systems for targeting, registration, grievance and the MIS. The technical assistance budget was broken down as follows:

Component	GBP	%
Research and evaluation	2.9m	49%
Policy development and programme design	0.24m	4%
Capacity building and system strengthening	1.5m	25%
Communication and advocacy	0.37m	6%
UNICEF support costs	0.98m	16%

There is evidence of the efficiency of providing technical assistance through UNICEF. For example, the use of embedded technical assistance alongside long term, in-country technical expertise enabled UNICEF to adapt and provide relevant expertise to MCDSS not only in implementing the cash transfer, but also in advocating for its expansion. Support was tailored to the needs of MCDSS and delivered in a flexible and adaptable manner to respond to changing context. UNICEF Headquarters management cost was 7%, and in-country management cost was negotiated to a fixed cost $50,000 per year.

Effectiveness
Under the research and evaluation, UNICEF commissioned the multi-year impact evaluation of the Child Grant and Multiple Categorical Grant (MCG). The evaluations were carried out between 2010 – 2014. The impact evaluations have been instrumental in informing programme design and influencing GRZ to scale up the programme. A case study on the programme in ‘The Value of Evaluations’ (DFID 2015) estimated the net present value of the social cash transfer evaluation as $15m - $36m, which far outweighs the cost. The evaluation has been repeatedly cited not only by Zambian decisions makers but also in international social protection studies. This demonstrates that it was an effective evaluation – generating robust evidence that was then used to inform policy decisions.

Procurement of Goods through Crown Agents and AECOM Limited

Procurement of goods for the programme was undertaken by procurement agents under direct contract with DFID. A total of £5.2 million was spent on the procurement of goods to support the implementation of the SCT programme. The assets procured included 122 motor vehicles, 7 boats and a range of office equipment for setting up SCT operations in the districts. The purchase of motor vehicles was the key cost driver under this component and accounted for approximately 53% of the total.

Over the lifetime of the programme, procurement has been carried out through well established and preassessed suppliers. This allowed the procurement agent to realise benefits from economies of scale through bulk purchases which reduced transaction costs. Procurement agent fees were agreed upon and ranged between 5.5% to 6% of the total cost of procurement. Having an agreed percentage for procurement fees allowed DFID Zambia to anticipate cost and manage budget forecasts better.

Procurement through AECOM and Crown Agents provided for improved efficiency and economy in the use of funds. To maximise benefits, the procurement agent worked with MCDSS to obtain specifications which took into account local needs. Inspection of items on delivery and reporting any problems in good time allowed for rectification to be done before goods were transported to the districts. In addition, transportation of unassembled goods helped to minimise damage.

Both procurement agents took into account the additional developmental impact of procuring locally produced goods and this was taken into account in assessing bids.

VfM performance compared to the original VfM proposition in the business case

The programme did not have a VfM proposition as it was approved prior to the introduction of the business case. However, an assessment in 2015 identified a number of areas related to VfM. The assessment below provides an updated assessment of how the programme has fared in these areas since 2015.

Good practice (identified 2015)	RAG*		Comments (2018)
CROSS-CUTTING
Overall public financial management (PFM): observe/support sound PFM practices to improve budget credibility, transparency, policy-based budgeting, budget execution, reporting and external audit in CT programmes			There has been some progress against 2015 FRA and the 2017 Annual Statement of Progress noted a positive trajectory. However, there has been limited progress against central PFM reform, budget credibility and execution. / There are serious financial management concerns on the SCT programme and efforts to improve these are not progressing at pace.
ECONOMY
Best practice procurement processes for big ticket items			Procurement of assets was conducted as planned. However, in relation to sustainability, there was limited work to strengthen the procurement capacity of MCDSS as this was all outsourced.
Outsourcing functions which can be provided more cheaply externally			Payments have been outsourced to two payment services providers, ZANACO and Zampost. It was envisaged that costs for the payment providers may be high in the short term but may start to reduce in the long run. However, given the limited coverage of ZANACO and the serious performance concerns with Zampost, these benefits may not be realised as early as desired.
EFFICIENCY
Exploit economies of scale through operation at scale or consolidation of similar interventions			The targeting approach was harmonised for the scale up to minimise the proliferation of different models. SCT targeting was also used for the World Bank Keeping Girls in School programme and the USAID SEEVCA programme. This provided some initial grounds for building linkages with other programmes.
Use of ICT-based single registries and management information systems (MISs) within and across programmes to maximise efficiency, responsiveness and accountability and reduce duplication			The electronic MIS has been decentralised to all districts but is not fully functional for all modules (e.g. grievance). The World Bank Single Registry is being developed but progress has been slow to maximise efficiency. Efforts to harmonise some databases (e.g. agriculture and social cash transfer) are underway but these are not yet delivering efficiency gains.
Use of electronic payment systems			ZANACO only delivers payments in Lusaka district instead of three provinces as initially planned. The roll out has been slow, as such the scale of operation is insufficient to drive efficiency.
Use of simple, transparent eligibility criteria			The eligibility criteria have been simplified to ensure inclusion of the most vulnerable households. It contains some categorical elements which make it easy to understand and it is widely accepted by communities.
Minimise costs to beneficiaries of registration, proving eligibility, collecting payments			The costs associated with registration have decreased in terms of time (with a shift to mobile registration) but the introduction of a new payment provider has introduced new private costs as beneficiaries have to travel to the post office to collect payments. More remote areas have continued to use pay point managers.
Ensure payments are timely, regular and predictable			Transfers have been delayed by over six months.
Provide an effective complaints & grievance mechanism covering both selection & quality of service, adapted to local conditions			New grievance mechanism has been designed but yet to be rolled out. This is significantly delayed, but has been prioritised for action in the last quarter of 2018.
EFFECTIVENESS			2018
Design targeting approach for efficacy, simplicity and fit with long-term national & international goals for social protection, e.g. minimise inclusion & exclusion error, maximise popular support for adequately resourced social protection system anchored in national legislation.			A harmonised targeting approach has been developed and rolled out during the 2017 and 2018 scale ups. This has created one national programme, with easy to understand criteria that are widely accepted by communities. A targeting assessment has been planned and will be undertaken under Phase II of the programme.
Link transfers with other interventions to promote livelihoods and reduce vulnerability			Limited progress but linkages to the national social health insurance and girls bursaries have been identified
Choose transfer levels to optimise balance between coverage, comparability with non-recipients, effectiveness in reaching objectives and cost-efficiency.			Transfer value analysis for 2016 showed that an increase in transfer size would have larger impacts. The transfer value was increased in 2017, with an explicit choice to prioritise programme expansion. Budget limitations have meant that transfer value cannot be increased
Put gender centre-stage in programme design, backed up by appropriate accountability mechanisms. Consider measuring impact by gender and impact on HH dynamics.			71% of primary recipients are women. No negative impacts on gender and other HH dynamics have been found but there are evidence gaps. A gender analysis will feed into the National Social Protection Policy refresh in 2018/19
Enhancing dialogue with government and other key actors in order to maximise outcomes.			Dialogue with government and other stakeholders has generally been very positive, with strong donor coordination and work with the UN and MCDSS. However, this is currently under strain due to financial management challenges. DFID Zambia is in the process of developing a SCT influencing strategy and enhancing relationships across GRZ will be central to this.
Encourage & support funding sustainability, and consider whether programme focus should be more TA than support to transfers			The programme was realigned to support more TA; however the majority of funds remained as FA. Additional donor support was secured (Finland and Sweden) and GRZ budget allocation increased. However, lack of disbursement of GRZ funds means that donors have continued to step in to fill gaps. Current delays in GRZ disbursements coupled with a donor decision to withhold disbursements create a major sustainability risk. DFID Zambia should reconsider this issue under SPEP 2.
*RAG rating for this programme:			= good		= could improve		= needs attention

This analysis shows that the programme performed well on some indicators but that there is scope for considerable improvement in the next phase, particularly in relation to strengthening delivery systems to improve efficiency. Areas where the programme delivered weaker VfM have been identified and will be monitored and measured under the second phase of the programme.

Overall, the programme has achieved or exceeded the majority of the outcomes it set out to achieve, and in doing so created valuable evidence that SCTs can be an effective and efficient way of reducing poverty and improving household resilience. The programme has demonstrated that it is reaching some of the most vulnerable Zambians with assistance that can improve food security, increase school attendance, asset ownership and savings. Indicators above show it is reaching the most vulnerable and as such it represents a good investment of UK assistance. The SCT programme is now the flagship programme for the National Social Protection Policy. Moreover, the evidence generated by the programme is having a global reach.

Recommendations to take forward into SPEP 2:

- There has been a worrying trend of decreasing efficiency in the programme, driven both by high administration costs (partially related to scale up, but also inefficiencies and overspends) and low transfer costs (related to lack of predictable financing). DFID Zambia needs to enhance its monitoring of programme efficiency and sustainability and identify more robust strategies to reduce costs. The SRO should incorporate this recommendation into the SPEP 2 delivery plan in October 2018 and ensure there is a clear plan in place with MCDSS and UNICEF by April 2019.
- Undertake an adequacy of transfer study to assess the (potential) effectiveness of the programme and ensure the results feed into DFID Zambia’s broader advocacy strategy on social cash transfers.
Ensure a VfM matrix with clear indicators across the 4 E’s is agreed before entering into any new agreement with UNICEF or another technical assistance provider.
E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The programme risk was assessed as Major, and (allowing for changes in the classification system) has been since 2012. A range of risks were identified and closely monitored since the beginning of the programme, the major risk of the programme was considered within DFID Zambia’s risk appetite given the expected impact of the programme on poor and vulnerable groups in Zambia.

Fiduciary risk was a consistent feature of the programme and routinely monitored since inception. A fiduciary risk and capacity assessment was conducted in 2012 which rated the overall risk as moderate to substantial. The risk of petty corruption was rated substantial, but a low risk of grand and administrative corruption. These compared favourable to the national Fiduciary Risk Assessment (FRA) of 2010. There was slow progress in 2013 and 2014 on implementing the recommendations from the FRA, and it was partly in response to the concern on slow progress that DFID reallocated some funding away from financial aid and into technical assistance in 2014. A new FRA was conducted in 2015, but again there was slow progress in agreeing an action plan to address the challenges identified. An action plan was agreed in 2016 and implementation began towards the end of 2016. An Annual Statement of Progress in 2017 noted a positive trajectory on risk, but that delays in implementation made it difficult to judge whether these actions were sufficient. The programme received an annual audit by the OAG. Initially this was done independently of the overall audit of MCDSS, however, as the programme expanded it was incorporated into the broader audit of the Ministry. This was done in line government’s efforts to embed the SCT into broader internal processes. Whilst DFID, UNICEF and MCDSS introduced a number of mitigating measures to address fiduciary risk, a common trend throughout the programme was delays in seeing concrete action. Risk recommendations from 2014 and 2015 recommended DFID contracting additional Public Financial Management (PFM) expertise, in 2016 it was agreed that DFID would provide additional in-house PFM support. These mitigation measures did have some positive impact on reducing the risk (as demonstrated in the 2017 ASP), but ultimately they were not enough to keep pace with the programme scale up and as a result the fiduciary risk appetite was breached in 2018 resulting in a decision to withhold future disbursements to the programme. This is documented in the SPEP 2 2018 annual review. In light of this, and continuing unacceptable levels of fiduciary risk, DFID and other CPs should work with the MCDSS and UNICEF to identify what appetite there is for serious financial management and oversight reforms. If these are acceptable to all parties, DFID should agree the nature of support that is needed and ensure it is consistently provided throughout SPEP 2.

Political risk particularly in relation to building support and promoting sustainability of the programme was similarly monitored throughout the programme. The programme continued despite a change in government in 2006 and 2011, which gave promising indication of sustainability and political support. Since 2011 there have been Presidential commitments to improving the scheme and making it sustainable, and significant budget increases since 2014 have somewhat reduced this risk, but in turn increased the risk of rapid scale up to meet political ends. Increased allocation in the 2016-2018 Medium Term Expenditure Framework was a positive sign, but this also increased the risk of political interference (particularly in the run up to the 2016 General election). A greater reliance on domestic financing also increased the risk of delayed disbursements, a risk that has been realised and discussed above. The programme took mitigating measures, including the completion of the 2016 scale up before the election period and intensified lobbying with the MoF on regular releases and reclassifying the programme as a statutory grant, but changes in staff around this time caused the risk to remain high. The lack of regular financing in 2018 has demonstrated that some mitigation measures, such as the reclassification of the programme, have not been effective. Political support to the programme is increasingly secure, however the risks around the impact this has had on implementation continue to rise and are discussed below. The risk of a failed scale up was highlighted in 2014.

Delivery risk particularly in relation to the capacity of the MCDSS to implement a scaled up programme has been an issue throughout the programme. Early in the programme this was mitigated by the recruitment of additional staff and deployment of embedded technical assistants. A focus on systems strengthening was identified as the core mitigation measure in 2013, but a combination of limited resources and political pressures to deliver a scale up have consistently meant that systems strengthening lagged behind an increase in beneficiary numbers. Developing a new MIS greatly reduced administrative burden at district level, as did the introduction of mobile registration. Despite these efforts, scale up continued to outpace systems improvements and staff capacity and the risk of ineffective implementation continued to be an issue. This is particularly the case around contracting of third party payment service providers and rolling out an enhanced grievance redress mechanism. Both of these risks were identified as early as 2011, but repeated failures in procurement and competing priorities mean that, at 2018, the systems to deal with both of these critical issues are not fit for purpose. Particularly in relation to the payment mechanism, changes made in 2017 and 2018 have negatively affected performance and become the most significant programme risk. This issue is further highlighted, along with new mitigation measures, in the 2018 SPEP 2 annual review.

Throughout the course of the programme additional risks have been identified for periods of time. These have included the risk of climate change negatively affecting the resilience of poor households, the risk of inflation reducing the value of the transfer.

Across all risks, the use of UNICEF technical assistance has been used as a mitigating measure –through direct deployment of staff, lobbying GRZ, investing in improved systems or latterly (since 2017) supporting financial management. A number of these initiatives have been successful, but the challenges faced in the programme in 2017/2018 highlighted that these mitigation measures on their own were not sufficient. As part of their ongoing review of SPEP 2, the DFID Zambia programme team should identify additional risk mitigation and assurance strategies that do not rely on UN systems.

Recommendations

A number of the risks identified in earlier years of programme implementation remain relevant for SPEP 2. This is particularly the case in relation to fiduciary and delivery risks. The programme team should conduct a systematic review of historic programme risk to learn lessons about what mitigation strategies work, and what didn’t, to inform their future approach to risk.

Update on partnership principles

DFID Zambia is currently reviewing its assessment of the GRZ’s commitment to the UK’s four partnership principles. Concerns have emerged over public financial management in several sectors, including social protection. We are currently carrying out further analysis and are reviewing our aid modalities in this light. Financial disbursements are currently on hold.

Partnership Principle 1 – Poverty reduction and the Sustainable Development Goals

GRZ has robust policies on poverty reduction and basic services but these are not matched by consistent funding. The 2015 Living Condition Monitoring Survey found that poverty had fallen only slightly from 2010 to 2015, with rural poverty remaining stubbornly high at 76.6% (down from 77.8% in 2010). The strong decade of growth from 2004 to 2014 did not benefit the poor.

GRZ has demonstrated commitment to increase spending on the social cash transfers programme in recent years. It doubled its budget allocation to 500m Kwacha from 2016 to 2017, with a further incremental increase to 550m Kwacha in 2018. The January – December 2017 budget for the programme was 68% GRZ financed, and this has risen to 76% in the 2018 budget, with the programme being on track to transition to full GRZ financing in 2021. But failure to release the budgeted funds in a timely manner has held progress back. The full 2017 payment round was not completed until March 2018.

While budgeted increases point to encouraging progress on political ambition, there has not yet been full recognition of the effectiveness and affordability of social cash transfers as a strategy for reducing poverty. This could be in part because despite electoral promises to improve wellbeing and opportunities for all Zambians, effective strategies to reduce poverty -such as SCTs- are not necessarily perceived to have the strong electoral pay-offs.

Partnership Principle 2 - Commitment to respecting human rights and other international obligations

The Public Order Act continues to be used selectively providing a restrictive environment for those holding dissenting views. There are concerns that a proposed cyber-security bill could further close the political space, and a LGBTQ conviction in August 2018 that could see the convicted men face up to life imprisonment has attracted international attention. We are currently reviewing our assessment of the commitment to this principle in light of these developments.

Partnership Principle 3: Strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption

The government has continued to implement process-oriented reforms in public financial management, and a new Public Expenditure and Financial Accountability Assessment (2016/17) has shown some improvement since 2012 in policy-based budgeting and budget comprehensiveness and transparency. However, it showed little improvement in predictability and controls in budget execution or in accounting, recording and reporting. Irregularities in the management of public funds raised by the Auditor General point to persistent serious weaknesses in public financial management while high-value corruption is perceived to be on the increase. There were calls for the Head of the Financial Intelligence Committee to be removed after publication of an annual trend report which pointed to limited law enforcement follow-up of suspicious transactions flagged by her office.

In light of concerns over public financial management in a number of sectors, the UK is currently reviewing its aid modalities. In social protection, there have been particular concerns that the weak financial management systems may not be able to withstand pressure of the social cash transfers programme scale up. Financial aid disbursements have been put on hold whilst the MCDSS urgently undertakes financial management improvements.

Partnership Principle 4: Strengthening domestic accountability

Commitment to domestic accountability is moderate. Elections have been largely credible and civil society operates freely, but the media is largely state-controlled (even if not state-owned) and there is little scope for dissenting views. Outside of elections there are few effective mechanisms to hold government to account. There have been delays in setting up a grievance mechanisms for recipients of social cash transfers.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

The programme had three major funding channels; financial aid to GRZ, technical assistance to UNICEF and procurement of goods through Crown Agents (2010-2016) and AECOM Limited (2016-18).

DFID has played a pivotal role in the growth of social protection in general and expansion of the social cash transfer in particular. This has been done through regular engagement with the government to lobby for increased funding to the sector and to ensure more predictable disbursement of funds. DFID was co-lead of the Cooperating Partners Group with UNICEF since 2010 until end of 2017. This has allowed for the creation of strong and positive working relationships with other actors in the sector, including the UN and the World Bank. DFID enjoys a positive relationship with MCDSS and has facilitated the entrance of news donors (Sweden and Finland) into the sector. Work commissioned by DFID and Ireland in the earlier stages for the programme such as the impact evaluations and the fiduciary risk assessments have informed decisions by other donors to join the sector.

Joint Annual Reviews, bi-annual Steering Committees and Quarterly (later trimester) Programme management meetings have continued to provide a useful platform for engagement among stakeholders.

MCDSS has been implementing the social cash transfer programme through already existing structures, at community level. This has helped to embed the programme into ministry operations thereby providing a basis for the programme to be sustainable.

Quality of Financial Management:
Disbursement of funds to UNICEF and MCDSS was made on a bi-annual basis, in June/July and November, respectively. Payments were made of the basis of the annual workplan and submission of satisfactory activity and financial reports. Payments to the procurement agent (Crown Agents/ AECOM Ltd) for purchase of goods were made in arrears upon delivery of goods to MCDSS and confirmation that they were in good working condition.

The flow of funds from DFID to MCDSS has been smooth with limited delays in the process with funds requested and disbursed in a timely manner. Audits of the programme were carried out every year, there have been occasions were the audit has identified instances of petty corruption within the programme (as in 2016), and in these instances the appropriate processes have been followed both by DFID and GRZ, including criminal prosecution and attempts to recover funds.

Monitoring the quality of financial management has been a key feature of DFID support over the lifetime of the programme. DFID provided technical assistance to reduce fiduciary risk, for example direct procurement of goods and technical assistance for MCDSS to procure an external payment service provider, and in the later phases of the programme (from 2017) added additional funding for financial management technical assistance. Contracting an external payment service provider was consistently identified as a core fiduciary risk mitigation measure. Unfortunately, this was severely delayed due to two failed procurements before ZANACO was contracted after a third round of procurement. However, ZANACO was slow to begin payments and has not been able to scale up at the planned pace due to their limited network coverage. This has limited the programme’s ability to reduce risks, and as the size of the programme rapidly expanded (in terms of beneficiary numbers, district coverage and total budget) financial management began to fall below acceptable levels. Concerns around financial management escalated in early 2018 which resulted in a decision by DFID and other donors to withhold any further disbursements to the programme.

As the programme increased in size and value, additional measures were put in place for MCDSS to provide more detailed financial reports, particularly clearer documentation of administration costs. The need for this was clearly highlighted in the Fiduciary Risk Assessment that was conducted in 2015. This was to allow for greater transparency into overall expenditure on the programme and to facilitate improved monitoring of costs. This formed part of the financial management action plan which was taken forward by the Financial Technical Committee; however irregular meetings of this committee have hampered the full implementation of the action plan. The revival of the Financial Technical and Audit and Financial Technical Committees can serve as positive initial steps in strengthening financial management for the programme.

DFID signed a contribution arrangement for technical assistance with UNICEF, which ran from 2010 to 2016. UNICEF provided bi-annual activity reports and an annual certified financial statement. No major issues arose in the duration of the programme. Forecasting was a challenge in the initial stages but this improved significantly as the programme became more established and costs were more predictable. UNICEF was also able to make some savings which were made available for the development on the next phase of the UN Joint Programme and for additional activities to support MCDSS with the scale up of the SCT programme.

Quality and timeliness of reporting:
Regular four monthly meetings between MCDSS and the donors were held to review progress in programme implementation and expenditure against the budget. These have continued to run smoothly since the start of the programme. Reports were previously submitted quarterly and every six months for financial reports, but the FRA conducted in 2015 recommended a change to this schedule to allow for more frequent information sharing as the programme has been expanding. This change was made to also allow for more timely decision making and documentation of changes within the programme.

Capacity constraints within MCDSS and preoccupation with the scale up have negatively affected their ability to report in a timely manner. Additional support is now being provided through UNICEF to quality assure all reports. There is still need for additional capacity building in this area to allow for increased accountability and transparency by MCDSS.

Delivery against timeframe:
This programme was approved in April 2010 for a ten year period ending in March 2020. The final disbursement of financial aid (£2.6 million) under this programme component was made in September 2017, whilst £1.3 million was spent on the procurement of goods to support MCDSS in setting up offices in the new districts in 2017. All payments that were due on this programme have been made and the budget has been spent to the full programme amount (£38 million).

Overall, the project has exceeded the number of recipients reached, owing to the decision by government to scale up the programme nationwide much earlier than anticipated. This change resulted in DFID and other donors bringing forward funds that were allocated to later years to respond to the increase in government funding and to re-align technical assistance to better support MCDSS during the scale up. This shift in the timeline has resulted in funds under this programme being used earlier and thus a decision was made to bring forward the end date of this programme forward and to obtain approval for additional funds under a second phase. The new programme was designed to overlap with this phase to allow for completion of the disbursements under the financial aid component and the procurement of goods.

It has been recognised that the SCT programme has potential to deliver stronger development impact through linkages to other programmes and service delivery including health, education and agriculture extension. The benefits of the programme at local level are recognised across sectors, but stronger service delivery is needed to respond to increased demand created. The broader social protection policy development is one of the critical pathways to links different sectors and programmes.

Commercial: The programme had a strong commercial element which comprised indirect and direct procurement of goods and services. Direct procurement was done through an existing framework with PEAKS which made available pre-qualified suppliers. This was for key pieces of work to undertake periodic Fiduciary Risk Assessments of the programme, engagement of experts to provide specialist work and conduct external annual reviews of the programme. A large proportion of procurement of services was done through UNICEF which was responsible for contracting work for the impact evaluation.

Procurement of goods was initially contracted through a framework arrangement with Crown Agents and later with AECOM. This allowed for bulk procurement at competitive prices as the procurement agent were able to draw on global markets to achieve good value for money.

Over the course of the programme there were delays in the procurement of goods which slowed implementation. However, more intense management from DFID and increased local capacity of the procurement agent led to improvement in performance but this had to be closely monitored.

Asset monitoring: MCDSS has maintained an asset register for the entire duration of the programme. DFID procured a range of assets to support the implementation of the SCT programme. This included boosting operations for already existing offices and construction and set up of new office space in some districts. Items procured included 122 motor vehicles (mostly Toyota Landcruisers  as most districts are hard to reach), seven boats for districts that are located on islands or bordered by large water bodies, 47 motor cycles and a range of office equipment and bicycles for use by CWAC members.

DFID conducts periodic asset spot checks in a number of districts to ensure that goods are used for the intended purpose. During this review, the DFID programme team conducted spot checks at four district offices (Limulunga, Mongu, Pemba and Kalabo) and two provincial offices (Western and Southern). All the assets that were procured under this phase of the programme will be carried over to the next phase. Going forward asset monitoring will need to be strengthened and more regular spot checks will be carried out. Given that the programme is nationwide, asset monitoring will be included in office field visits to allow the programme team to have a more robust system for managing programme assets.

Date of last narrative financial report	MCDSS / Narrative: Vault #34949505 / Financial: Vault #34948009
Date of last audited annual statement	UN (UNICEF, IOM, WFP & ILO) / Certified Financial Report: Vault #32381481

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Throughout the implementation of the programme DFID and other cooperating partners have met regularly with GRZ to monitor the implementation of the programmes. As mentioned above, these meetings have changed between quarterly and four-monthly throughout the course of the programme, but have provided a regular platform to share progress on the programme, to inform partners about challenges, to identify solutions and to make strategic decisions on the future of the cash transfer. These have always been supplemented with adhoc management meetings to discuss emerging issues on the programme.

DFID and others CPs have also been involved in supporting MCDSS to identify lessons from different rounds of scale up, both from formal evaluations and also participation in regular lessons learnt workshops to reflect on issues like targeting criteria and performance, scale up performance and challenges in programme implementation.

Throughout the course of the programme numerous field monitoring visits have taken place to all provinces in Zambia. This has included routine programme monitoring from the DFID programme team, joint implementation monitoring visits with MCDSS and UNICEF, high level visits from UK government officials and advocacy visits with members of the Zambian government and parliament.

As part of the development of the national social protection policy an annual Joint Annual Review has taken place, usually in June to align with GRZ planning cycles. The last joint annual review took place in June 2018 and focused on social protection and decentralisation.

Evidence

The programme placed a strong emphasis on generating evidence to test the programme’s theory of change. In addition to evidence generation, the team at DFID, UNICEF and MCDSS placed high importance on communicating evidence and using this to advocate for increased domestic resources to support programme expansion.

An independent impact evaluation following a randomised control trial design was completed on both the child grant and the multiple categorical grant. The evaluation consisted of a baseline measurement and repeated post-intervention measures conducted at both lean and harvest times. Given the use of randomization and the existence of a baseline, differences between the treatment and control groups can be fully attributed to the SCT programme rather than to other differences between the two groups.

Evaluations repeatedly found that targeting was well implemented, it highlighted the benefits of geographic plus categorical targeting that had not previously been used by MCDSS. This was then adopted for the scale up.

The first impact evaluation results were published in 2013 showing positive findings in support of the theory of change. This contributed to early plans to scale up. A further report in 2014 showed positive findings in smoothing of consumption, increases in food and total household expenditure. Recipients were using transfers to reduce debt, send children to school, invest in livestock and improve household conditions.

Additional qualitative data was collected that showed the programme was appreciated by recipients and their communities, it was strongly seen as a government programme, improving a sense of citizenship, and reduced perceived dependency on others. Beneficiaries perceived an improved ability to participate in the community and be respected, particularly with regards to reduced begging. However, the qualitative evidence did show a lack of awareness of rights or procedures for complaint and grievances and a lack of transparency in the role or selections of CWACs. This evidence informed a decision to change the role of the CWACs during targeting, revising their role to provide information about the programme and encourage all eligible households to self-register rather than selecting qualifying households.

The Zambian Government stated in its 2014 budget that the scale up of the programme is a shift from 'poorly targeted subsidy programmes where beneficiaries were not the intended poor' to 'better designed social protection programmes such as the social cash transfer scheme that has been successfully piloted'. This can be at least partially attributed to the widespread communication of the impact of cash transfers, alongside analysis that demonstrated other subsidy schemes were not reaching the poorest.

In 2015 6 reports from the child grant and multiple categorical grant were released. These found that both programmes impact households through increased consumption and diet diversity, reduced debt, and investments towards asset accumulation (tools, housing) and livelihood diversification (nonfarm enterprise, livestock). These increases suggest that households in the program are likely to be much more resilient to shocks and external sources of fluctuations in income.

The programme had strong impacts on reducing extreme poverty and the poverty gap, ultimately reducing the depth of households below the poverty line. The effects on poverty reduction were greater for those farther below the extreme poverty line, evidence of both the highly successful targeting of the SCTs and their impact on welfare.

Figure (impacts of MCG on poverty after 3 years)

SPEP is a positive example of GRZ using evidence to inform public policy and service delivery. This is being translated to elsewhere within MCDSS, for example the impact evaluation of the Supporting Women’s Livelihood (SWL) programme within the Department of Community Development. However, the process of piloting, rigorously evaluating and adapting programmes before making a decision on national policy and programming does not appear to have been shared widely to other relevant departments. During the course of this PCR the MCDSS were extremely positive about the support DFID had provided in evidence generation and learning, but still saw this as an external process that they would like donors to continue with. As part of DFID Zambia’s broader policy influencing strategy they should work with GRZ to internalise this learning approach and use it in other areas, supporting national policies to be more evidence based and adaptive.

Learning

DFID, UNICEF and the MCDSS were consistently learning from the impact evaluation evidence above – particularly in relation to choices in programme design and implementation modalities. This informed different phases of the scale up programme.

More broadly, the programme demonstrated to a range of stakeholders the potential to influence GRZ policy and programming through piloting, rigorously testing and communicating evidence of a well implemented development programme. During the course of this programme, learning generated from evaluations has completely changed the landscape of social protection in Zambia. Evidence generated in Zambia has also contributed to global learning, with the CG and MCG impact evaluations being quoted by programmes across the region.

Whilst this is a positive example of learning from evidence, there are other areas were the programme did not learn quickly enough to improve implementation. As noted in the risk section above, the programme team repeatedly identified risks related to too fast a scale up, weak systems and in particular weak financial management. Mitigation measures were put in place, but with hindsight it is clear that not enough emphasis was placed on these issues. As a result, the same risks are present in the programme today and are jeopardising the entire cash transfer scheme.

On a programme delivery, it is clear that using technical assistance as risk mitigation is not sufficient without strong lines of accountability, clear expectations and monitoring of progress towards agreed targets. Whilst UNICEF did mitigate a number of risks, their primary objective was to support the expansion of the programme, and as such organisational priorities were not always aligned. A lesson to be taken forward in SPEP 2 is that in high risk programmes such as this, DFID Zambia needs to develop stronger internal risk mitigation and assurance strategies, complimented but not replaced by technical assistance programming. This will also help to address challenges of optimism bias and groupthink between the DFID programme team and UNICEF technical assistance and ensure that progress on issues such as systems strengthening is subject to robust, independent assessment.

The programme has focused strongly on capacity building and evidence generation, but one emerging lesson is that the programme has not been able to create a culture that pilots, tests and adapts. The programme has not been successful at embedding a learning culture, and whilst this was not a stated objective, it is an important issue to share with similar programmes, moving beyond the capacity to deliver what is within the programme plan to capacity to deal with complex programmes in a changing environment. Whilst capacity was built in specific areas, difficulties encountered in 2017 and 2018 suggest that this is capacity to deliver a pilot programme rather than capacity to deliver a long term national programme. The programme team should reflect on these lessons, and what this means for DFID supported technical assistance programmes elsewhere.

Going forward, under SPEP 2, the programme team should pay greater attention to learning what works in terms of systems strengthening, particularly how to negotiate systems strengthening in a complex political environment. This will contribute to strengthening the SCT and ensuring it is embedded in GRZ systems for many years to come.

Progress on recommendations from annual reviews for this programme

DFID to ensure the results framework for its new social protection programme includes indicators monitoring UNJPSP progress, particularly their role in institutional strengthening to support scale up and quality implementation. This should be more specific in terms of what systems strengthening activities are expected to be delivered within a given reporting time. (June 2017)	Done: See logframe of SPEP 2. / A challenge remains on assessing the quality and value for money of the UNJPSP, two issues that will be taken forward in design of the new phase of technical assistance from 2019 onward.
DFID, UNJPSP and MCDSS to agree on how to allocate resources to the FRA action plan after DFID additional support ends in 2018 (August 2017)	Done: Some costs mainstreamed into UNJPSP budget, Sweden and Ireland funded the remaining costs for 2018. Agreement that financial management will make up a much larger part of the next phase of TA
DFID to engage in high level advocacy regarding the 2018 SCT budget and 2017 releases with MoF, MCDSS, IMF and other CPs at CPG meetings and ad hoc as opportunities arise	Ongoing: This continues to be a challenge; DFID and other CPs continue to raise it. Minister of Finance announced her commitment at a meeting with the international community but 2019 budget ceiling has been reduced. This demonstrates the need for continual advocacy at many levels.
DFID to ensure learning from their Emergency Cash Transfer programme (DiRECT) is shared with all partners and informs MCDSS' plans to improve the complaints mechanism and begin electronic payments. DFID and UNJPSP to work with MCDSS reviewing the operations of the electronic payment during the mid-term review (Oct 2017) to ensure that beneficiary experience is central to any decision to roll out electronic payments and for district specific piloting to take place before any decision to transfer beneficiaries to an electronic platform.	Partially Done: learning event took place and all partners were invited. Learning on the complaints mechanism was also discussed separately with MCDSS and UNICEF. MCDSS reviewed the grievance plan in light of some of the DiRECT evidence. Field visits during this annual review suggested that Pemba district was trying to use some of the old DiRECT mechanisms for the SCT. / Not done: the issue on electronic payments was discussed, however the procurement and use of the payment service provider went ahead and resulted in severe challenges. Beneficiary feedback has started to feed into a review of this process, but it took too long. For more information see the SPEP 2 annual review (2018).
MCDSS to ensure its staff resources are adequately split between different programmes under its mandate to avoid disruption to programme implementation to be monitored through the quarterly review meetings.	Ongoing: staff capacity at MCDSS remains a challenge, particularly low overall staffing numbers in relation to their increased mandate. This has been discussed, and time spent on other programmes has decreased
DFID to build on the coordination mechanism established between MCDSS and the Disaster Management and Mitigation Unit (DMMU) under the Emergency Cash Transfer (DiRECT) to encourage dialogue around the use of SCT infrastructure to respond to disasters and climate related shocks through facilitating quarterly meetings (July 2017)	Partially done: Discussions with MCDSS, DMMU, UNICEF and WFP on use of SCT to respond to disasters took place in late 2017 and early 2018 and included work planning on how to make the SCT systems more flexible. / However, this was put on hold as a result of challenges with the capacity of systems to deal with the current SCT case load, particularly emerging concerns related to the use of payment service providers.
DFID social protection and agriculture leads to discuss taking a more active role in bridging the gap between social protection and agriculture, particularly in relation to sharing evidence to inform the use of e-vouchers for FISP (July 2017)	Done: Advisers called a joint meeting with agriculture and social protection partners to discuss issues related to poor harvests, FISP, the FRA and food relief. FAO joined the UN joint programme to take this link forward on a more programmatic level
DFID and MCDSS to review indicator 2.1 and assess the impact on VfM as part of the Joint Annual Review (JAR) discussions by September 2017.	Done: This has been discussed at management meetings and at budget meetings both in terms of plans to reduce administrative costs and implications of cost overruns. / Unfortunately it is clear that these discussions are not leading to the necessary reductions in administrative costs. Under SPEP 2 DFID will further analyse these costs to ensure targets are realistic and engage MCDSS in adopting more robust measures to cap costs on certain budget lines to prevent overspending.
The August 2017 annual review of SPEP 2 will report against the VfM metrics as suggested in the business case and should set targets related to operating costs, cost transfer ratio and sustainability. This will enable both programmes to better assess value for money performance.	Done: SPEP 2 reported against a number of VfM indicators and developed a new VfM framework. / However, challenges are still present in the inability of partners to report on economy indicators and failure to meet cost transfer ratio targets. Plans to address this are in place – see SPEP 2018 annual review