Type of Review: Annual Review

Project Title: Public Financial Management Reform Programme

Date started:	23/12/2010
Date review undertaken: December 2012 – January 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK’s contribution to strengthening the Government of Nepal’s (GoN) Public Financial Management (PFM) is £3.5m over 3 years through a World Bank (WB) Multi-Donor Trust Fund (MDTF). It has two core components: / Component A: to support strengthening GoN PFM systems (“supply side”). / Component B: to develop capacities of Nepali Civil Society Organisations to use social accountability approaches (“demand side”). / The programme impact will be an effective PFM system that facilitates the delivery of better public services to improve the lives of people of Nepal. The outcome is “a more efficient PFM system with increased transparency and accountability to citizens”. / The two components represent the initial stages of support to the Public Financial Management Reform Programme (PFMRP) - a comprehensive programme of support to the Government of Nepal to implement PFM reforms. Effective Public Financial Management is a key priority for the UK in order to: / Protect UK funds and help ensure that full benefits are delivered to recipients; / Ensure that the funds of other donors and the Government of Nepal are managed with full accountability. / Reduce the opportunities for corruption and misappropriation of all development funds in Nepal. / The programme plans to build on the reform progress made to date, and reinforce the sound public sector management principles. These initial components build on identified GoN priorities and while most of Component A (supply side) represents technical PFM reform measures, the aim is that they will form part of a broader set of PFM reform measures that address capacity, accountability and incentive issues in the longer term. / DFID has contributed to Multi-Donor Trust Fund (MDTF) and has endorsed three areas of support in the supply side. These are: (1) Treasury Single Account (TSA) implementation; (2) Nepal Public Sector Accounting Standard (NPSAS) implementation; and (3) Capacity Building and Institutional Strengthening of the Public Expenditure and Financial Accountability (PEFA) Secretariat in the Ministry of Finance. / The demand side component will develop the capacities of Nepali Civil Society Organisations to use social accountability approaches and tools to make PFM more accessible and responsive to the needs of all citizens. The programme will be delivered via the Programme for Accountability in Nepal (PRAN), a US$3m programme with an overall life of 3 years.

What are the expected results?
The following are the expected results: / Implementation of Treasury Single Account in all districts to ensure a consolidated and rationalised basis for financial management. This will enable better control of finances and a reduction in idle funds by bringing all GoN bank accounts under the control of the treasury in a single treasury account. / Implementation of NPSAS will result in improved transparency and comprehensiveness in GoN reporting, in particular to ensure the actual financial position of GoN is appropriately represented including budgetary and non-budgetary entities as well as State Owned Enterprises. / Capacity Building and Institutional Strengthening of PEFA Secretariat will result in strengthened institutional capability of the PEFA secretariat to effectively implement and monitor GoN’s Public Financial Management Reform Programme. / The demand side activities will increase the capacities of Nepali social accountability practitioners using a combination of training, specialised workshops and grants to CSOs to improve transparency, efficiency and equity in PFM by: / Participating in budgeting processes to make resource allocation more equitable. / Contributing to budget review through independent analysis, demystifying the budget. / Disseminating analysis of the budget to broaden accessibility by citizens. / Expenditure tracking to ensure resources reaches intended beneficiaries, and that public officials are held accountable for mismanagement and corruption. / Performance monitoring of service delivery to improve quality and accountability, as well as access by socially marginalised groups at municipal and local levels. / Monitoring public procurement to reduce scope for corruption. / Overall Nepal’s PEFA scores should be increased by at least one level.

What is the context in which UK support is provided?
Improving Governance and Accountability underpins the agenda of the Government of Nepal (GoN) for building a New Nepal that is prosperous, peaceful and just. Strengthening Public Financial Management (PFM) is a key element of the GoN’s strategy for strengthening governance, optimizing outputs from public resources and for ensuring inclusive and broad-based development. / The UK, along with other Donor Partners, has also been expressing concern about weaknesses in PFM systems that may pose significant fiduciary risks to donor financed projects. DFID’s own assessments highlight the fiduciary risk in Nepal as high and all UK funds going through public systems are subject to special mitigation measures to ensure they are delivered in a secure and accountable manner. Overall, there has been increasing demand for effective use of resources provided for development efforts in order to ensure value for money through a sound PFM system and for better results measured through technical reviews of performance. / A 2008 Public Expenditure and Financial Accountability (PEFA) Assessment, to assess the performance of the country’s PFM systems in comparison with internationally accepted benchmarks, was initiated to provide a basis for objectively assessing the country's Public Financial Management (PFM) systems. The scope of the assessment covered fiscal and debt management, budget formulation, budget execution, internal controls, procurement, accounting and reporting, auditing, transparency and external scrutiny. / The assessment concluded that the country’s PFM System was well-designed but unevenly implemented, thus posing fiscal and fiduciary risks to budgetary resources and donor funds. Following the PEFA assessment, the GoN in collaboration with Development Partners (DPs), formulated a Development Action Plan (DAP) that described the menu of actions for strengthening PFM systems and processes. In 2008, the GoN formed a PFM Steering Committee (chaired by the Finance Secretary) and set up a PEFA Secretariat in the Ministry of Finance to drive and coordinate PFM reform efforts. / Following the PEFA assessment, with the support of the World Bank and DFID, the GoN formulated a Public Financial Management Reform Program (PFMRP) Strategy, Phase I (2010-2013), with the objective of adopting a holistic government-wide approach to PFM reforms encompassing both the institutional and technical aspects. This is intended to be a gradual and long-term process which will contribute to reducing fiduciary risks as well as improving transparency and accountability of public financial management. It provides a framework in which all related reform initiatives can be incorporated under a single ‘umbrella’ and under which the development partners can provide their funding on a joint and ‘programmatic’ basis. / The PFMRP strategy has two key priorities for the short term: (1) to deliver actions that yield effective results in strengthening the PFM system, and (2) to build the capacity of the PEFA Secretariat to lead the PEFA agenda and institutionalize the reform process. The success of the reform program will depend on commitment and ownership by responsible agencies, strong political commitment and the sustained partnership of development partners. / The following priorities have been identified in the area of public expenditure and financial accountability: Sustaining technical support on basic budgeting and treasury functions; supporting outreach and consensus building on the need for PFM reforms among government and civil society stakeholders; leveraging information technologies such as Integrated Financial Management Information Systems (IFMIS); strengthening the audit function of the Auditor General; strengthening the parliamentary oversight function carried out by the Public Accounts Committee (PAC – when reconstituted); moving from a rules-based to principles-based approach in line with international standards; supporting the institutional development of the primary institutions of accountability in Nepal; strengthening PFM monitoring by both State and non-State actors, including independent verification interventions; and supporting the design of a sound financial management system in the context of state restructuring and transition to a possible federal system.

## Section A: Detailed Output Scoring

Output 1: Treasury Single Account (TSA) implemented at District Treasury Comptroller’s Office (DTCO)
Output 1 score and performance description: A++ / Indicator 1.1: Number of DTCOs where the TSA has been implemented. / Baseline: 2 (2009) / Target: 25 or more / Achievement as of September 2012 / Single Treasury System of Accounts (TSA) rolled out to 60 districts, covering about 95% of government expenditures and 98% of government revenues exceeding the original target. Approximately 12,500 bank accounts out of 14,000 accounts of various spending units have been closed. The remaining 15 districts are the remote districts, where the volume of financial transactions is low. These districts are also aimed to be covered starting from FY2013/14. / The government has managed this process efficiently and effectively in implementing the TSA without major set-backs, as the volume of financial transactions and the number of spending units is very high. This is a major success for the programme. / Indicator 1.2: Cash flow management and payment/receipt settlement through District Treasury Comptroller’s Office (DTCO) / Baseline: 2 (2009) / Target:25 or more / Achievement as of September 2012 / As above, this has reached 60 districts, covering 60 DTCOs.
Progress against expected results: / Recommendations: / Good progress made so far needs to be maintained and the scheduled roll out in the high altitude districts needs to be managed well. The government should ensure that the staffing issues in the remote high mountainous districts are not a constraint. / Currently, the DTCO prepares the cheques and hands them over to the spending unit. Internal controls can be further enhanced if payments can be made directly through bank transfers to the suppliers’ bank accounts, not through cheques. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: TSA implemented at the FCGO
Output 2 score and performance description: A / Indicator 2.1 Status of implementation at the FCGO / Baseline: Manual / Target::Procurement process completed and company starts work (2011). / Achievement as of Sept 2012: Procurement of servers for the upgrade of IFMIS has been done and is operational. / The procurement of consultants to modify IFMIS has been done. Software for Budget Management System, Financial Management Information System (FMIS) has been developed by the consultants and are operational. / Indicator 2.2 Network system established. / Baseline: Not in place / Target: System Analysis / Achievement as of Sept 2012: / The FCGO IT organisation review has been completed. The districts are currently connected with FCGO network in 68 districts. Out of which 7 districts are now connected via optical fibre network 53 districts are connected via ADSL. In the 15 non-TSA districts FCGO connects via ADSL through a web based network and only 7 districts have a stand-alone system. / Indicator 2.3 Network reporting and FMIS. / Baseline: Not in place / Target: Preparation and development. / Achievement as of Sept 2012: / Same as above.
Progress against expected results: / There has been good progress in this area. / Recommendations: / All the districts and FCGO should be connected by Optical Fibre to ensure reliable connectivity. Networking in the remaining non-TSA remote districts needs to be done and the government has planned to implement TSA in all 75 districts by July 2013. It will be a challenge to carry this out due to the remoteness of the districts and GoN needs to plan carefully and ensure that qualified and trained staff remains in the remote districts. / Impact Weighting 10% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Cash Receipts and Payments (CR&P) Statement and Budget/Actual Comparative Statement for budgetary and non-budgetary entities in accordance with Part 1, Cash IPSAS
Output 3 score and performance description: C / Indicator 3.1 Extent to which CR&P and Budget / Actual Comparative Statements are prepared / Baseline: None / Target: Selected entities trained in the preparation of CR&P and Budget / Actual Comparative Statements in IPSAS format by 2011 / CR&P and Budget/Actual Comparative Statements published in IPSAS format by each pilot entity by 2012 / Achievement as of Dec 2012: / Slow progress. / The translation of NPSAS is in progress and will be piloted in 2 ministries i.e. Ministry of Physical Planning, Works and Transport Management and in Ministry of Women, Children and Social Welfare. Training and piloting will be done after the translation has been completed. / Indicator 3.2 Preparation of CP&P statement by all budgetary; and non-budgetary controlled entities / Baseline: Financial statements published in current format by all entities / Target:: CR&P and Budget / Actual Comparative Statements published in IPSAS format by each budgetary and non-budgetary entity by 2011 / Achievement as of Dec 2012: / See above. There is little progress on this.
Progress against expected results: / There is little progress on this. / Recommendations: / To speed up the process. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: State Owned Enterprises (SOEs) produce Accrual financial statements in accordance with International Accounting Standards (IAS)/International Financial Reporting Standards (IFRS).
Output 4 score and performance description: C / Indicator 4.1 Preparation of accrual statements by SOEs selected to pilot procedures / Baseline: Financial statements published in current format by SOE / Target: All SOEs trained in the preparation of accrual statements in IAS/FRS format published the statement in the new format by 2012 / Achievement as of Dec 2012: / Slow Progress / The Office of the Auditor General has directed to the relevant SOEs and to the private sector to prepare statements according to International Accounting Standards (IAS) / International Financial Reporting Standards (IFRS). Consequently Accounting Standards Boards (ASB) has prepared the procedures and has recommended the Institute of Chartered Accountants of Nepal (ICAN) for implementation.
Progress against expected results: / There is little progress on this. ICAN has planned to prepare the statements based on IFRS by Nepali Fiscal Year 2014/15 for financial institutions and for other institutions by 2015/16. / Recommendations: / To speed up the process and to revise the target and the milestones. / Impact Weighting (%): 5% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 5: Government of Nepal produce consolidated Cash Receipts and Payments (CR&P) Statement
Output 5 score and performance description: C / Indicator 5.1 # of consolidated financial statements tested/produced / Baseline: Does not exist / Target: Train appropriate accounting personnel on consolidation procedures and commitment accounting by 2011 / Achievement as of Dec 2012 / There is little progress on this. / Indicator 5.2 # of consolidated financial statements tested and produced / Baseline: Does not exist / Target: Publish consolidated financial statements for all controlled governmental entities (within central government) to include budgetary, non-budgetary, and SOEs with Part 1, Cash IPSAS by 2012 / Achievement as of Dec 2012
Progress against expected results: / Work not started. / Recommendations: / Ensure that work starts. / Impact Weighting (%): 5% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 6: Well-functioning PEFA secretariat established
Output 6 score and performance description: B / Indicator 6.1 PEFA secretariat plays catalytic role in PFM reform process / Baseline: Not established (2010) / Target: Employees allocated to PEFA secretariat. External consultants appointed, manuals, directives prepared for PFM assessments and in house PEFA assessment (2011) / Achievement as of Dec 2012: / The PEFA Secretariat has been established and is active. GoN has deployed staff in the secretariat. The secretariat has prepared the following manuals and directives: / PEFA Handbook / PFFA Journal / PEFA Information Education and Communication Strategy / PEFA Newsletters / Operational Guidelines and Procedures produced for PEFA implementation Units (PIU) (at ministry level) and District PEFA implementation Units DPIU / However, risks have emerged affecting the overall implementation progress of the project. Continuing changes in management and staff – Project Director transferred in October 2012, frequent transfers of other staffs of the PEFA Secretariat and FCGO. This will have negative impact on PEFA secretariat playing a catalytic role in the PFM reform process. / Indicator 6.2 Develop implementation mechanism of overall PFMRP strategy / Baseline: None established / Target: Work with all line ministries to prepare an overall strategy (2011) / Finalise work on the overall PFMRP strategy (2012) / Achievement as of Dec 2012: / The government has decided to continue with the existing PFMRP strategy. PEFA units have been established in 15 line ministries. These have started to coordinate with the PEFA secretariat. PEFA Secretariat has agreed with line ministries to appoint a focal person, who will update PEFA secretariat on the status of indicators on a periodic basis. / Indicator 6.3 Reinforce PEFA Implementation Units (PIU) in line ministries / Baseline: None / Target: Establish PEFA Implementation Units (PIU) in 50% of line ministries and provide training to key staff / Achievement as of Dec 2012 / PEFA Implementation Units have been established in 15 line ministries (60%) and 53 District PEFA Implementation Units (DPIUs) have been established out of 75 districts (71%). PEFA has provided orientation to 5 PIUs. Orientation has been provided to 24 DPIUs. The orientation is a good start but PEFA secretariat needs to interact more with PIUs and DPIUs and mainstream PFM reforms into the ministries / districts and connect more with the Units. Clarity of purpose is needed in establishing units.. / Indicator 6.4 Capacity of accounting professionals in financial planning a programming / Baseline Low capacity of accounting professionals in financial planning and programming (2010) / Target: Training Needs Assessment Undertaken / Achievement as of Dec 2012: / There has been no progress on this.
Progress against expected results: / There has been some progress in this area but the PEFA secretariat needs to work more to enhance the capacity of accounting professionals if GoN is to implement cash IPSAS. / Recommendations: / PEFA secretariat needs to start work on developing the capacity of the accounting professionals and needs to interact more with the PIUs and DPIUs and mainstream PFM reforms. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 7: Nepali CSOs use Social Accountability (SA) Tools and Techniques
Output 7 score and performance description: C / Indicator 7.1 # of CSOs using SA tools by trained practitioners to promote transparency, efficiency and equity in PFM / Baseline: Trainee knowledge and skills based on in-take survey / Target 28 SA trainings, targeting inclusion of groups working on gender issues / Achievement as of Dec 2012 / Very little progress till date as this component was approved only in August 2012. / Indicator 7.2 # of grants awarded to NGOs for adaptation and application of best practice SA approaches and tools by practitioners to influence PFM / Baseline: Trainee knowledge and usage of SA approaches and tools to influence PFM based on in-take survey of trainees / Target: Distribution of 8 grants to pilot and develop SA techniques and tools in PFM using gender filter. / Achievement as of Dec 2012 / No grants have been made yet. / Indicator 7.3 # of NGOs using SA approaches to improve PEM / Baseline: Methods used by practitioners to capture and share lessons from SA activities based on baseline survey of program beneficiaries / Target: Active web-site for knowledge sharing; coalition of CSOs and network of practitioners; publication of lessons learned from workshop / Achievement as of Dec 2012 / PRAN has produced a manual but this has not been put onto a website yet. / Indicator 7.4 Monitoring and evaluation of funded activities / Baseline Knowledge, skills and usage of SA to improve PEM among practitioners based on mapping and surveys / Target: Design tools for monitoring and evaluation (NRI) (2010) / Interim report on monitoring and evaluation of funded activities (NRI) (2011) / Achievement as of Dec 2012 / The monitoring and evaluation work has not been set up.
Progress against expected results: / This component was approved in August 2012 and very little progress has been done as of date. Much of the design work has been done for PRAN outside the MDTF PFM component’s funding. / Recommendations: / Ensure fast delivery and speed up the planned activities. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? N / This review has been undertaken using the existing log frame and needs to be updated. A mission has been fielded by the Bank to update the overall results framework and a draft has been presented to the MDTF donors for comments. A mission has been scheduled by the World Bank towards the end of January 2013 to finalise the Framework. The DFID logframe will be updated after the results framework has been finalised. / 1.2 Overall Output Score and Description: B / Good progress has been made in areas like in establishment of TSA where activities have been carried out. However, progress has been slow in much of other output areas and ample work needs to be done. / 1.3 Direct feedback from beneficiaries / This has been a desk based review and we are unable to report on this but a mid-term evaluation will pick up on these issues
1.4 Summary of overall progress / The overall progress of this project has been slow. As reported in last year’s annual review, slow internal procedures of the Bank to approve projects has had a knock on effect on the overall implementation. / This year the government dissolved the parliament and announced elections. Consequently the national budget was approved through ordinance in two stages based on last years’ budget approval. Thus no new allocations were made in the national budget. This has affected the project.
1.5 Key challenges / The most significant challenge being the non-availability of full year budget within Government leading to very slow procurement and delayed decision making and the frequent transfers of staff in the PEFA Secretariat and FCGO. Because of slow spend, the FCGO allocation for this year is lower and this may further slow progress. / The Bank has appointed task team leaders for each of the components of the MDTF. It has been felt by the MDTF donors that the Bank needs to depute one person to co-ordinate the MDTF activities. This will result in the ownership of MDTF activities by a single person and for the delivery of results for this project in both demand and supply side activities. / DFID has co-financed a programme ‘Strengthening Public Management Programme’ with the Asian Development Bank recently. Coordination of activities between the two banks needs to be done to increase synergy and lessons learned are shared on PFM reforms at the central and the local levels.
1.6 Annual Outcome Assessment / The outcome of this project is ‘A more efficient Public Financial Management system with increased transparency and accountability to citizens.’ / Purpose indicator 1: 5 of the 6 dimensions increased by at least one step. / We are unable to report against this indicator as the repeat PEFA assessment has slipped. GoN and the Bank are planning to start work on the repeat assessment in 2013. / Purpose indicator 2: Perception surveys: Key stakeholders perceive that Public Financial Management system to be more transparent, accountable, responsible and effective / Not done by PRAN as this component agreement was signed in August 2012 only.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / The project needs to speed up the activities urgently to bring the forecasts back on track. Where activities have been carried out they have been very successful and represent good value for money. / 2.2 Key cost drivers / The project has been facing delays from the inception due to lengthy World Bank procedures. This has now been aggravated due to the National budget being based on last year’s spending. Consequently the project is well behind schedule. Where activities have been carried out they have been very successful and represent good VFM. / 2.3 Is the project on-track against original timescale: No Reasons cited above.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No change. PFM remains a key priority with the potential for large-scale impact in improving the accountability of development funds. / 3.2 Where an evaluation is planned what progress has been made? / A mid-term evaluation has been proposed by the Bank. The evaluation is planned to commence in April and the findings will be presented in June 2013 PCC meeting.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / The risk level remains high. The accountability institutions such as the Auditor General and the Chief Commissioner of Commission of Abuse of Authority (CIAA) have remained vacant for the past five years. Parliament has been dissolved and there is no scrutiny of annual audited accounts of the government by the Public Accounts Committee.
Risk of funds not being used as intended / Low risk due to World Bank oversight. / 4.4 Climate and Environment Risk / Unchanged

5. Value for Money
5.1 Performance on VfM measures / About 12,500 bank accounts out of 14,000 have been closed till end September 2012 after the roll out of the TSA. The government can now use the idle balances in those bank accounts. This has increased the value for money to the government in comparison to the amount that has been spent to get this system going. / Furthermore, the District Treasury Comptrollers’ Office (DTCO) now input all the data into the Financial Management Information System, The government is able to view the treasury position in real time for about 95% of the government expenditures and 98% of the revenues. / 5.2 Commercial Improvement and Value for Money / The introduction of treasury single account has now significantly improved internal control. The risk of inserting bills / vouchers at a later date is now next to impossible as opposed to the hand written vouchers that this system replaced. The line agencies now do not have to wait for bank transfers into individual project / office accounts as DTCOs will make payment based on approved budgets. This will contribute to the improvement of service delivery. / 5.3 Role of project partners / Financial Comptroller General’s Office (FCGO), PEFA secretariat, Office of the Auditor General, District Treasury Comptrollers’ Office are critical project actors for the implementation of TSA. There has been strong ownership of the successful roll out of TSA. Similarly, civil society partners will be essential in holding the government to account. / The Accounting Standards Board, Institute of Chartered Accountants of Nepal and State Owned Enterprises, and the private sectors are key partners for the roll out of Nepal Public Accounting Standard (NPSAS) and International Financial Reporting Standard (IFRS.) / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions / No conditionality is applied.

7. Conclusions and actions
The project is behind schedule and the Government and the World Bank including MDTF donors needs to drive this more to so that the PFM reform agenda based on the Public Financial Management Reform Programme is achieved despite the political hurdles. / The following are recommended to be carried out: / Accelerate the activities of the programme. Request the Bank to depute one person to co-ordinate the MDTF activities and make that person responsible for the overall results of the programme. / Revise the DFID logframe following the finalisation of the Overall Results Framework being developed by the Bank. / Ensure that the future work programme of PFM reform are based on the recommendations of the Operational Risk Assessment. / Support Technical Assistance in the PEFA Secretariat to coordinate work between the World Bank and Asian Development Bank programmes and PFM reforms at central and local levels. / Accelerate PRAN’s work and keep up the civil society monitoring to hold the government to account. This component’s importance has increased more now due to the vacuum created by the loss of elected oversight agency such as the Public Accounts Committee and the ineffectiveness of CIAA. / Support the mid-term-evaluation of MDTF and ensure that it is informed by the Operational Risk Assessment / Political Economy Analysis. / It is recommended to have a more comprehensive annual review next time as we expect increased activities and delivery of results.

8. Review Process
This has been a desk based review. The review took place between December 1012 and January 2013. Colleagues from PEFA secretariat, World Bank, TSA consultant have been consulted, including the former chief of the Accounting Standard Board.