Project Completion Review

Title: Global Mine Action Programme (GMAP)
Final Programme Value £ (full life): £40,423,338.96	Review Date: / January 2014 to September 2018
Programme Code: / 203243	Start Date / 28/07/2014	Final End Date: / 30/06/2018

Summary of Programme Performance

Year	2014	2015	2016	2017
Programme Score	A	A	A+	A+
Risk Rating	M	M	M	M

A. Summary and Overview

The problem of landmines and explosive remnants of war (ERW)[1] remains immense. In 2014, when the Global Mine Action Programme (GMAP) programme started, it was estimated that 3,678[2] people were killed or injured by landmines and ERW. Many people in post-conflict countries live alongside land littered by landmines, grenades, rockets and ammunition. This is a major threat to the physical safety of communities, denying them the use of agricultural land and the ability to access essential services, such as health and education. The presence of landmines and ERW also hampers freedom of movement, prevents the repatriation of internally displaced persons (IDPs) and refugees and obstructs the delivery of humanitarian aid.
[1] Unexploded weapons such as artillery shells, mortars, grenades, bombs and rockets, left behind after an armed conflict.
[2] http://www.the-monitor.org/en-gb/reports/2015/landmine-monitor-2015.aspx

GMAP aimed to reduce the humanitarian and development impact of landmines and ERW by clearing land contaminated by landmines and ERW; reducing the size of suspected hazardous areas; reducing the risk of harm through mine risk education (MRE) for communities living nearby; and building the capacity of national and provincial authorities to regulate and manage their own mine action programmes. GMAP has operated in some of the densest minefields in the world, for example the border minefields with Thailand in Cambodia; former battlefields in Zimbabwe; and land contaminated by more recent conflicts in Somalia and South Sudan. GMAP made a significant contribution to Mozambique, once one of the most heavily contaminated countries in the world, declaring itself ‘mine-free’ in 2015.

The GMAP business case was approved in January 2014 and operations began in July 2014. The programme came to an end in June 2018. The programme delivered in 9 countries: Burma, Cambodia, Laos, Mozambique, Somalia, South Sudan, Sri Lanka, Vietnam and Zimbabwe. GMAP was centrally managed by DFID’s Conflict, Humanitarian and Security Department (CHASE), supported by advisers from DFID country offices, and Embassies and Posts in countries where there was no DFID office.

The programme was delivered in two phases.

The first phase ran from July 2014 to July 2016 and included the following activities:

- Contracts for land release and MRE with The Halo Trust (HALO) in Laos, Cambodia, Sri Lanka and Mozambique, and Mines Advisory Group (MAG) in Laos and Vietnam.
- The project in Sri Lanka ended in 2015. The programmes in Vietnam and Laos ended in 2016. Mozambique was declared ‘mine free’ in 2015 although the project was extended to ensure the correct disposal of the DFID-funded assets. The phase 1 contract with HALO in Cambodia was extended to run concurrently with phase 2 of GMAP.
- A capacity development contract with Norwegian People’s Aid (NPA), in partnership with the Geneva International Centre for Humanitarian Demining (GICHD), to strengthen the ability of national partners to manage their own mine action programmes. This contract ran from August 2014 to 31 March 2018 and included activities in Sri Lanka, Cambodia, Somalia, Vietnam, Laos and Mozambique.

The second phase ran from August 2016 to June 2018 and included the following activities:

- A single contract was agreed with a consortium of HALO, MAG and NPA for landmine and ERW clearance and MRE in four DFID priority countries; Burma, Somalia, South Sudan and Zimbabwe. This contract was extended twice and delivered all contracted outputs.
- A contract for the monitoring and evaluation of GMAP was awarded to Itad Ltd through competitive tender in December 2015 with the contract ending on 30 April 2018. Itad delivered an evaluation of the GMAP programme, eight quarterly monitoring reports, 6 country case studies and completed 10 monitoring visits. The contract delivered all contracted outputs.

Results

The GMAP programme was designed to make communities contaminated by landmines and ERW safer, and support partner governments to effectively manage their own mine action programmes. The programmes were contracted on the basis of a set of internationally recognised output measures for mine action: land released for productive use in square metres and beneficiaries of MRE. In addition, DFID contracted a set of outputs that would strengthen the capacity of national mine action authorities.

Between July 2014 and June 2018 the GMAP programme released over 169,000,000 square metres of land, making it available for productive use or safe passage. The expected outcome of GMAP is that land would then be used productively by communities, or open up access to essential services. At the end of the GMAP programme 38,939,112 square meters of land released was either in use, or with firm plans in place for use. This was nearly 9,000,000 square metres more than expected at the start of the programme. On average 74% of direct beneficiaries surveyed reported improved livelihood opportunities following land release activities, with 44% reporting increased access to basic services and infrastructure.

Between July 2014 and June 2018 the GMAP programme delivered 31,856 MRE sessions to help communities understand the dangers of landmines and ERW, including teaching children how to recognise dangerous devices and providing emergency numbers to report devices if found. Following MRE sessions 76% of direct beneficiaries surveyed demonstrated increased understanding of MRE messages, with 51% of direct beneficiaries surveyed reported feeling safer after land release or MRE activities. These sessions were tailored depending on the audience. Girls, boys, men and women have different needs. For example girls and boys need to understand how to recognise the devices and report back to adults; while men and women may need advice on navigating contaminated land they have no choice but to cross or use.

Over the course of the GMAP programme there were measurable improvements in national mine action authorities in Cambodia, Laos, Somalia, Sri Lanka, Vietnam and Mozambique. In addition, the evaluation of the GMAP programme noted that even in countries not part of the capacity development contract there is evidence of GMAP suppliers assisting the national authorities to improve the regulation, management and coordination of mine action authorities.

Most, but not all outputs for the capacity development programme were delivered. It is important to note that capacity development is progressive and incremental, and requires continued support for mine action by partner governments. There have been notable successes. In Laos NPA worked with the National Regulatory Authority (NRA) on improving management of information on contamination and improving the way the nationwide survey is conducted. This was critical in managing the immense challenge of unexploded ordnance in Laos, thought to be one of the most heavily contaminated countries in the world. In Cambodia GMAP helped draft standards and policies on prioritisation, and drafted sections of the national mine action strategic plan with the Cambodian Mine Action Authority.

In addition to routine monitoring conducted by the team in CHASE, a monitoring and evaluation provider, Itad, was contracted to provide analysis of the outcomes and impact delivered by the programme and advice on improvements to GMAP design and delivery. This included an evaluation of GMAP which has informed this Project Completion Report.

The monitoring and evaluation contract was put in place as phase 1 of the programme was coming to an end, and allowed CHASE an opportunity to reflect on lessons from phase 1 and consider what should be applied throughout phase 2. Itad gave CHASE an objective view on how delivery could be strengthened, with actions for suppliers and the CHASE team. A summary of these lessons is in section G and included: closer collaboration with DFID country offices; extending the timeframe for suppliers’ collection of post-clearance impact data; and encouraging collocation of capacity development experts and national mine action authorities in country. In addition to lessons learnt and applied during the lifetime of GMAP, CHASE was also able to draw on the monitoring and evaluation services to learn lessons for future DFID mine action programmes.

## B: DETAILED OUTPUT SCORING

Output Title	Land released for productive use following effective tasking and prioritisation.
Output number per LF		1	Output Score	A+
Impact weighting (%)?		75	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones as at 30 June 2018	Progress as at 30 June 2018
1.1 Land cleared (Square Metres)	32,145,228	36,546,300 (exceeded)
1.2 Land reduced (Square Metres)	8,552,014	15,459,803 (substantially exceeded)
1.3 Land cancelled (Square Metres)	59,854,072	117,669,857 (substantially exceeded)
Total land release	100,551,314	169,675,960 (substantially exceeded)

Land release is defined as the process of applying all reasonable effort to identify, define, and remove the presence and suspicion of mines or ERW through non-technical survey, technical survey and clearance. This definition of land release used by GMAP follows the International Mine Action Standards (IMAS)[3] which sets global standards for mine action authorities and operators. GMAP recorded three types of land release: cleared land; reduced land; and cancelled land.
[3] https://www.mineactionstandards.org/

Non-technical survey is the collection and analysis of data about the presence of mines or ERW without the use of technical interventions (like metal detectors or sniffer dogs). Depending on the context, non-technical survey can include interviews with communities, consulting military records or looking at casualty data. Non-technical survey can lead to the cancellation of previously suspicious land, or provide sufficient evidence that land may be contaminated and require technical survey to confirm.

Technical survey is the collection and analysis of data using appropriate technical interventions, like the use of metal detectors or sniffer dogs, to confirm the location of mines or ERW. If no mines or ERW are identified following technical survey, land can be reduced. If mines or ERW are identified, land will be put aside for clearance.

Land is allocated to operators for non-technical survey, technical survey and clearance by national mine action authorities. During implementation of GMAP activity was focused on releasing land that would have the maximum humanitarian impact by allowing safe passage and enabling land to be returned to productive use. GMAP suppliers, HALO, MAG and NPA, worked alongside national mine action authorities to ensure the right land was being prioritised for land release activities.

Land release targets, marked by the milestones detailed above, were exceeded in both phases of GMAP. This applied to all three categories of land release: clearance; reduction; and cancellation.

Between July 2014 and June 2018 the total amount of land cleared by GMAP was 36,546,300 square metres, 13% more than expected. Nearly twice as much land was reduced over the course of GMAP as expected, a total of 15,459,803 square metres.

The rate of land cancellation significantly exceeded the initial milestone of 59,854,072 square metres. By the end of June 2018 more than twice as much land had been cancelled, a total of 117,669,857 square metres. Cancelling land is a benefit to communities as it confirms that land suspected of contamination by landmines and ERW is confirmed as safe. However, such confirmation may have a lower impact as communities are often aware that land isn’t contaminated and make use of it prior to formal cancellation. It is also difficult to predict, and therefore set milestones, for land cancellation.

Over the course of the GMAP programme clearance and technical survey resulted in 799,369 direct beneficiaries and 1,229,281 indirect beneficiaries of land release activities. GMAP benefitted women, men, girls and boys relatively equally. 53% of beneficiaries were men and boys, 47% women and girls.

Over the four years GMAP was operational DFID expected to see increasing efficiency in the rate of land cleared and reduced. The increased efficiency was expected to be the result of technological and operational innovation. These efficiencies were realised throughout GMAP. Examples of these innovations in the GMAP programme are the use of new mechanical assets to cut down vegetation which speeds up survey and the use of large-loop detectors when surveying anti-tank minefields.

A significant development during phase 1 of the programme, and an area where future DFID mine action programmes will benefit, was the adoption by many operators of the Cluster Munitions Remnants Survey (CMRS) system developed by NPA. This is a more efficient way of surveying and then clearing land contaminated by unexploded ordnance (UXO), which is the dominant form of contamination in Laos and Vietnam.

Phase 1 land release results by country

In Mozambique, 140,928 square metres of land was released, exceeding the land release target by 20%. The GMAP programme made a significant contribution to Mozambique being declared ‘mine free’ in September 2015 by surveying and clearing some of the last remaining minefields in Mozambique. GMAP reached 13,544 direct beneficiaries, and 95,121 square meters of land was in use or firm plans were in place for its use when the programme closed.

In Sri Lanka, land release activities were based in Jaffna, Kilinochchhi and Mullaitivu Districts in the north of Sri Lanka. 1,628,631 square metres of land was released, exceeding the original target by 33%. Efficiency gains were made throughout the programme, for example the use of a new sand filtering machine and the use of new data capture software, Fulcrum, that recorded information in real time in the field, saving time and reducing the possibility of errors in recording data. GMAP reached 7,051 direct beneficiaries, and 869,818 square meters of land was in use or firm plans were in place for its use when the programme closed.

In Laos there were two programmes, one in Xieng Khouang Province implemented by MAG, and one in Savannakhet Province implemented by HALO. Both projects ended on 30 June 2016. The total area of land released for productive use in Laos was 60,519,642 square metres and exceeded the combined project targets by 73%. There were significant opportunities to cancel land in Laos which accounted for the majority of the 73% increase in productivity. During the programme MAG introduced a new evidence based mapping process which reduced the time required for survey. HALO introduced the use of Fulcrum software, as in Sri Lanka. GMAP reached 42,745 direct beneficiaries, and 4,106,828 square meters of land was in use or firm plans were in place for its use when the programme closed.

In Vietnam, MAG had released a total of 4,079,249 square metres of land, exceeding the total land release target by 30%, in Quang Tri Province, one of the most heavily contaminated provinces in Vietnam. The most significant efficiency gain throughout the programme in Vietnam were the improvements in site assessment and clearance plans, facilitated through the integrated approach with NPA and the provincial authority, who led surveys using the CMRS system. GMAP reached 8,284 direct beneficiaries, and 2,946,751 square meters of land was in use or firm plans were in place for its use when the programme closed.

Phase 2 land release results by country

The phase 1 programme in Cambodia continued beyond 2016 (when the rest of phase 1 closed) and ran concurrently with phase 2 until the end of June 2018. Land release activities were located in the north-west of Cambodia in the provinces of Battambang, Banteay Meanchey, Otdar Meanchey, Preah Vehear, Pursat and Pailin. This border area with Thailand is heavily contaminated with 1,000 landmines per kilometre along the 720km border. This makes it one of the most heavily contaminated areas in the world. In Cambodia the overall amount of land made available for potentially productive use was 75,463,241 square metres, 5% above the expected target. GMAP reached 120,352 direct beneficiaries, and 22,635,169 square meters of land was in use or firm plans were in place for its use when the programme closed.

During phase 2, land release activities were conducted in South Sudan, Somalia and Zimbabwe by the HALO led consortium. It was only possible to deliver MRE in Burma.

Considerable security issues in South Sudan led to an adjustment in the areas where contractors operated compared to original plans. In mid-July 2016, the security situation in Central Equatoria deteriorated, making field operations impossible. NPA chose to exit South Sudan. MAG judged they were able to continue to operate but shifted operations from the original site in Juba County of Central Equatoria to Tindalo. MAG worked with the monitoring provider to adjust projected targets for land release following this move. On completion of the contract, MAG released 13,152,932 square metres of land and exceeded the land release target by 90%. It should be noted that this over achievement was largely due to cancellation of land, activity completed with UK funding on the request of the United Nations Mine Action Service. Land clearance and reduction targets were met as planned. GMAP reached 2,746 direct beneficiaries, and 1,577,242 square meters of land was in use or firm plans were in place for its use when the programme closed.

Land release activity in Zimbabwe was delivered in Mashonaland Central, Mashonaland East and Manicaland Provinces along the border with Mozambique. The overall amount of land made available for productive use was 3,443,400 square metres, 46% above the original target. GMAP reached 16,150 direct beneficiaries, and most of the land released was in use or firm plans were in place for its use when the programme closed.

The overall amount of land made available for potentially productive use in Somalia was 7,453,109 square metres, exceeding the original target by 20%. GMAP reached 9,805 direct beneficiaries, and 1,908,397 square meters of land was in use or firm plans were in place for its use when the programme closed.

Output Title	Affected communities aware of the risks of landmines and ERW
Output number per LF		2	Output Score	A+
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	N

Indicator(s)		Milestones as at 30 June 2018	Progress as at 30 June 2018
Number of MRE sessions delivered		27,083	31,856 (exceeded)
Number of direct beneficiaries of MRE	Women	132,902	129,192 (almost met within 10%)
	Men	123,056	110,732 (almost met within 10%)
	Girls	129,073	203,590 (significantly exceeded)
	Boys	133,069	210,599 (significantly exceeded)
Total over both phases		518,100	654,113 (exceeded)

MRE is delivered through a combination of education sessions held in communities; public safety messages communicated via radio broadcasts; or information on the threat and advice on safe behaviour distributed via leaflets or posters. The education sessions in communities include large group discussions at community centres where the types of devices known to be in the area are described and advice on the ways to avoid and report them are shared. Sessions in schools will be tailored for a younger audience and include, for example, songs that help children remember what to do if they see a dangerous item.

The GMAP suppliers conducted baseline surveys to determine where MRE sessions were most needed and assessed attitudes to safety. Following this assessment, community safety mapping and surveys were conducted. Suppliers shared their findings with the communities to ensure everyone was aware of their findings and had the opportunity to contribute. Post-clearance surveys were conducted by the suppliers 12 months after clearance to assess whether real behaviour change had been achieved.

Phase 1

Of the total number of MRE sessions delivered across the full GMAP programme, 11,921 sessions were delivered in phase 1, exceeding the predicted target by 14%. However, the number of direct beneficiaries of MRE in phase 1 (161,708 of the total 654,113) was significantly lower than the predicated number of 214,372. Although it is possible for suppliers to predict with confidence the number of sessions to be delivered, it is harder to guarantee how many people will attend. Fewer adults than predicted attended sessions in the phase 1 countries where communities have been living with the contamination for many years. In contrast, the milestone target for adult attendance at MRE sessions in Burma in phase 2, where contamination is more recent, was exceeded by 10%. The demand for MRE in communities emerging from conflict and living with a new risk is higher. A lesson for future programming, when dealing with legacy contamination, is to ensure that needs assessments for MRE are more effective at tracking needs so messages aren’t repeated, or sessions are poorly attended.

Phase 2

Of the total number of MRE sessions delivered across the full GMAP programme, 19,935 were conducted in phase 2 exceeding the predicted target by 23%. 492,405 people directly benefitted from the MRE sessions, exceeding the target by 36%.

The table below details MRE delivery for phase 2 by country, covering the period September 2016 – June 2018.

Country	MRE Sessions planned	MRE Sessions delivered	Direct beneficiaries target	Direct beneficiaries reached
Burma	1,811	2,122	63,074	91,955
Cambodia	6,147	7,830	78,979	121,743
Somalia	6,700	8,296	175,504	217,881
South Sudan	1,443	1,565	30,990	34,777
Zimbabwe	84	122	12,218	26,049
Total	16,185	19,935	360,765	492,405

In Burma, GMAP activities were carried out in Kayin State where the state government initiated the first formal discussions on mine clearance in the country. This was a positive step towards international operators being able to clear minefields in an area that remains political complex and casualty rates, as recorded by the land mine monitor[4], continue to rise. As noted above, take up of MRE sessions in Burma was higher than expected, especially amongst adults. 2,122 sessions were delivered, 17% above the initial target.
[4] http://www.the-monitor.org/en-gb/reports/2018/myanmar_burma/casualties.aspx

The number of MRE sessions delivered in Somalia was 8,296, 19% above the predicted target, with 71% of those surveyed reporting feeling safer.

The number of MRE sessions conducted in South Sudan was 1,565, 8% above predicted, with 88% of those surveyed demonstrating an improvement in their knowledge of the dangers of landmines and ERW.

The total number of MRE sessions conducted in Zimbabwe was 122, 31% above target, resulting in 88% of beneficiaries surveyed reporting an increased understanding of mine risks. A notable development in Zimbabwe was the relocation of MRE sessions to boreholes, where women in particular were more likely to take up the MRE offer and attend sessions.

In Cambodia, the total number of MRE sessions (covering the full GMAP period July 2014 – June 2018) was 11,197, exceeding the target by 12%. Of the 5,136 beneficiaries surveyed, 97% people had an increased understanding of mine risks following an MRE session.

Output Title	Strengthened capacity in national mine action authorities (NMAAs)
Output number per LF		3	Output Score	A
Impact weighting (%)?		10	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones as at 31 March 2018	Progress as at 31 March 2018
3.1 NMAAs are managing and setting direction of their own national mine action strategies more effectively	NMAAs have a baseline understanding based on national surveys, are able to extract meaningful information from their databases upon which they have based clear plans and national strategies on which progress is being made.	Outputs delivered in Laos, Cambodia, Vietnam-Quang Tri Province, Sri Lanka and Vietnam. Some outputs not delivered at the national level in Vietnam and in Mozambique.
3.2 NMAAs coordinate the mine action sector more effectively	NMAAs conducting regular (monthly or quarterly depending on country) coordination meetings with proper documentation and communicating with other stakeholders and relevant ministries also on a regular (monthly) basis, proactively reaching out to other stakeholders.	Outputs delivered in Laos, Vietnam - Quang Tri Province, Cambodia, Sri Lanka and Somalia. Partly achieved in Vietnam nationally.
3.3 NMAAs regulate the mine action sector more effectively	NMAAs have up-to-date standards in place, appropriately qualified monitoring personnel, are conducting regular and documented QA/QC visits, and prompt handover of released areas.	Not fully achieved at the national level in Vietnam. Sri Lanka made good progress and will continue with remote support, funded by another donor. Laos has completed work. Cambodia has not fully completed this output. Not applicable in Somalia.

A single contract was awarded to NPA, with GICHD as a supporting supplier, to conduct capacity development activities in Laos, Cambodia, Vietnam, Sri Lanka, Mozambique and Somalia.
The ultimate responsibility for eradicating landmine and ERW contamination lies with national authorities in affected countries. All funding for mine action capacity support is channelled through INGOs. The activities are country specific and aim to enable national and provincial authorities to regulate, coordinate and manage the mine action sector in their countries more effectively. As such they rely on the partner government to accept plans and work in cooperation with DFID funded suppliers. This is a key assumption underpinning the theory of change which did not always hold. Support from partner governments held in most GMAP countries, with variations over time, apart from Mozambique where some outputs were delivered but ultimately the Government of Mozambique chose not to accept a major output, the strategic plan for transition.
In Laos, there was a specific focus on improving the way survey was delivered and coordinated by the national regulatory authority, the NRA. A joint survey by NPA and UXO-Laos, the national mine action operator, introduced more efficient ways of conducting survey, and simultaneously built the capacity of UXO-Laos as the largest national mine action organisation. The three GMAP suppliers (HALO, MAG and NPA) worked with the NRA to develop a strategy based on this approach which increased the productivity of land release. In addition, GICHD coordinated a workshop for a long term risk management project which will help Laos plan for the transition between dealing with large scale clearance to gradually working toward mine free status. In March 2018, 38 participants from all organisations in the UXO sector attended along with the Ministries of Defence and Foreign Affairs. This signalled continued support for strategic planning in mine action in Laos.
In Cambodia, the focus was on training and developing the capacity of the Cambodian Mine Action Authority (CMAA) and the provincial Mine Action Planning Units. GMAP provided funding through NPA for two full time national staff who worked in CMAA and seven full time staff who worked in the CMAA database unit (DBU). Examples of successful deliverables was the launch of an online application that allows mine action data collected to be uploaded immediately from smartphones or tablets to the national database, and the completion of the information management sections of the Cambodia 2018-2025 Mine Action Strategy.
In Vietnam, the focus was on strengthening the capacity of national (VNMAC) and provincial coordination mechanisms (Quang Tri Legacy of War Coordination Centre, LWCC). GMAP supported the development of the national plan for mine action which is awaiting Prime Ministerial Approval. A revised national quality management system was piloted in the LWCC in Quang Tri Province with a view to being implemented nationally. The LWCC is recognised as the most effective provincial level coordination centre in Vietnam.
In Sri Lanka, GMAP supported the Sri Lankan National Mine Action Centre (SLNMAC) in applying consistent standards for quality management of released land, and interventions to improve information management. Revisions to the National Mine Action Standards were been agreed by SLNMAC and are now awaiting government approval. It should be noted that Sri Lanka acceded to the Anti-Personnel Mine Ban Convention in December 2017, which is a significant development and indicator of partner government support for mine action.
In Mozambique, the majority of the capacity development outputs were delivered including training for national staff on the Information Management System for Mine Action (IMSMA) database and delivery of staff training on a standard curriculum for mapping and survey. However a key deliverable that could not be completed successfully was agreeing a strategic plan for transition with the Government of Mozambique. During GMAP, Mozambique was declared mine free, which meant it had removed all but the last ‘residual risk’ of landmines and ERW and met Article 5 obligations under the Ottawa Treaty. The strategic plan for transition, developed by NPA, was intended to support the transition from clearance and survey to managing any residual risk, as defined by the Ottawa Treaty. This was a significant disappointment for GMAP, and an example of a key assumption not holding. CHASE discussed this output with suppliers and Itad and ensured lessons were learnt and applied to the remaining capacity development activities. A key change has been a more direct involvement by CHASE, and DFID country offices and Embassies, with national mine action authorities to ensure capacity development deliverables remain on track.
In Somalia, activities were divided in to two phases. Phase 1 provided recommendations for the role of the national mine action authority, including training on using the IMSMA database, and developing an implementation plan for a national survey of landmine and ERW contamination. Phase 2 started in May 2017 following signature of a Memorandum of Understanding between the Somali national mine action authority (SEMA) and NPA, allowing for survey activities to start. Over the course of GMAP, 95 villages were surveyed and the resulting data on contamination was entered onto the Somalia IMSMA database.
## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

At an impact level, the GMAP programme aimed to make a contribution to ‘Poverty reduction and improved physical security leading to better livelihoods and progress against the Millennium Development Goals’. At the outcome level the expected outcomes were:

Target communities feel safer, leading to increased well-being;
- Formerly contaminated land used productively by target communities, with increased access to markets, leading to improved livelihoods;
- Target communities have increased access to basic services provided by national governments or NGOs;
- Effective mine action programmes increasingly managed by national authorities with minimal outside technical or financial input;
- Measurable progress toward Ottawa Treaty, the Convention of Cluster Munitions (CCM) and Convention on Certain Conventional Weapons (CCW) compliance.

Although there is a lack of macro level data available to link mine action directly to the impact statement, it was possible to gather village and household level data to understand the contribution GMAP has made to the expected outcomes. The independent evaluation of GMAP, conducted by Itad, contributed significantly to CHASE’s understanding of the strengths and weaknesses of the GMAP design, and led to revisions to the theory of change which have been worked into a new phase of UK funded mine action programming. The extent to which outcomes were realised is described below.

Target communities feel safer, leading to increased well-being

GMAP has contributed to a safer environment for mine and ERW-affected communities in most countries (all except for Burma where no clearance has been permitted) due to the physical act of removing potentially deadly items from the land where communities live. At the point of closure, GMAP had made 169,675,960 square metres of land safe through clearance and technical survey. Over the course of the programme GMAP made a significant contribution to Mozambique declaring ‘mine-free’ status, and clearing some of the densest minefields in the world like the border between Cambodia and Thailand, and the border between Mozambique and Zimbabwe.

Post-clearance survey is conducted between 6 and 12 months after land release to investigate the socio-economic consequences, costs and benefits of land release. These surveys assess the impact of both land release and the delivery of MRE. Of the benefitting communities surveyed, contractors reported that 46% of women, 47% of men, 56% of girls and 56% of boys felt safer after land release activity.

Overall, GMAP has removed and reduced the risk of harm from mines and ERW, and to a lesser extent, has reduced communities’ perception or fear of risk. Future DFID mine action programming should seek to ensure MRE, survey and clearance are closely sequenced so communities see action taken more quickly once the hazard is identified. This also requires close cooperation with the national authorities who lead the process of prioritising land. Future programmes should also seek to strengthen the way behaviour change is assessed.

Formerly contaminated land is used productively by target communities, with increased access to markets, leading to improved livelihoods.

A combination of case study reports, baseline reports, post-clearance surveys and quarterly updates reported improved livelihoods of beneficiaries due to increased access to land after mine action activities across the programme. The table below shows the m2 of contaminated land either in use, or with firm plans to be in use following the land release activities of GMAP.

Land use	Somalia	South Sudan	Zimbabwe	Cambodia	Laos	Mozambique	Sri Lanka	Vietnam
Residential	51,821	2,334	350,139	637,078	25,852	N/A	70,245	47,560
Agricultural Pastoral	227,254	428,007	1,899,323	16,601,381	3,928,243	50,000	146,897	4,100,013
Community development	334,443	7,180	155,272	187,755	N/A	N/A	69,201	88,749
Natural resources	N/A	1,046,772	240,169	60,447	125,000	5,000	337,900	N/A
Infrastructure	3,060	14,360	291,825	N/A	27,733	36,621	63,059	N/A
Access	1,291,819	78,589	396,258	3,058,014	N/A	3,500	147,875	39,815
Unreported land use	N/A	N/A	110,414	2,090,494	N/A	N/A	61,641	N/A
Total	1,908,397	1,577,242	3,443,400	22,635,169	4,106,828	95,121	896,818	4,276,137

While the above data is useful in understanding what communities plan to use released land for, it does not give a clear picture of the impact of mine action in different contexts. A key change made in the course of the GMAP programme, which strengthened insights in to land use, was the in depth livelihoods analysis was increasingly completed 12, rather than 6, months after clearance was conducted. The level of development return on mine action investments varies considerably between countries. A key lesson for future mine action programmes are that country-specific outcomes should be defined rather than relying on a global set. This will help CHASE understand more accurately exactly who in a community is benefitting from the land release, and what the most urgent priorities in a community are. For example a community may be in need of emergency assistance and therefore it will be more meaningful to monitor and record clearance of roads for access, rather than how much land is being used for agricultural activity. This approach is currently being taken as part of the inception phase of the new DFID mine action programme.

For example, in Mozambique, where demining was focused on the few remaining areas that were mined in the country, it was not possible to determine a clear direct impact for communities as the areas cleared were those left to last, largely because they were the most difficult to clear. For example, areas under bridges or along power lines that would not be used for agriculture or developed. GMAP made a clear contribution to Mozambique being declared mine free in 2015 and supported another outcome, that of supporting obligations to mine action treaties and conventions. The expected impact in countries approaching full clearance status should be weighted toward this outcome.

Safe passage is also a key benefit of demining. The benefits of creating safe passage for humanitarian services and market access can be substantial, especially where demining takes place in the early stages of post-conflict recovery. In Somaliland, 92% of beneficiaries surveyed reported improved access to services and/or infrastructure following mine clearance, which suggests a significant positive outcome. During beneficiary feedback sessions undertaken as part of the Itad evaluation, villagers in rural Cambodia consistently reflected on the very significant benefit initial land release had in terms of them being able to access food aid, and then access to markets as their rural economies developed.

Target communities have increased access to basic services provided by national governments or NGOs

GMAP land release has resulted in roads and tracks becoming available for regular use which increases access to basic goods and services. In Sri Lanka and Cambodia, clearance enabled the return of internally displaced people. In Somaliland, 92% of adults reported an increase in access to basic service and infrastructure following land release. Working through GMAP, MAG drilled three boreholes in South Sudan in an area it shares with local communities. On completion of their work in the area, these boreholes were gifted to the local community.

Mine action programmes are managed, coordinated and regulated more effectively by mine action authorities

One objective of GMAP was to support national mine action authorities so they can effectively manage their own mine action programmes. For example, in Laos, GMAP has delivered improvements in the management of mine action by the national regulatory authority (NRA). The GMAP delivery partners worked with the NRA to develop a survey strategy which increased the productivity of UXO survey and clearance processes.

Throughout GMAP the contracted partners used local implementing partners with a strong understanding of the country context to deliver mine action. In some countries where the security and political situation was challenging, using local partners represented particularly good value for money and allowed access to restricted areas. GMAP capacity development increased local capacity, provided employment and built partnerships in country. For example the joint NPA/UXO-Lao survey in Laos gathered data on contamination and transferred new survey skills to UXO-Lao staff, the largest national operator.

Measurable progress towards Ottawa Treaty, CCM & CCW compliance

A reduction in the remaining areas of contaminated land has been reported for all signatory countries to the Ottawa[5] Treaty to ban anti-personnel mines, and the Oslo[6] Convention to ban cluster munitions, within the GMAP contract. Mozambique became ‘mine-free’ in 2015. GMAP helped countries to meet international treaty obligations by encouraging data collection, resulting in more accurate information being loaded onto national databases that detail where landmines and ERW are located. GMAP partners, HALO and GICHD, were also successful in their advocacy efforts when Sri Lanka agreed to the Anti-Personnel Mine Ban Convention on 13 December 2017.
[5] https://www.apminebanconvention.org/
[6] http://www.clusterconvention.org/

Summarise the programme’s theory of change and major changes to it in the past year

There were no major changes to the theory of change over the course of the GMAP programme. However, early findings from the Itad evaluation of GMAP found some weaknesses in the relationship between the outputs and expected outcomes and suggested some improvements could be made for future programme design. Following this advice, in March 2017, CHASE commissioned a review of the GMAP theory of change. The main change proposed was the use of immediate outcomes which refer to short-term changes that are directly attributable to the work of the GMAP contracts, and intermediate outcomes which refer to longer-term socio-economic and security changes to which GMAP will contribute. These changes put more emphasis on partners to align GMAP with security, humanitarian and development activities; the contribution of GMAP to the stabilisation of the country; and the importance of capacity development. These revisions were used as the basis for the business case for new mine action programming over the period 2018-2020.

Explain major changes to the logframe in the past year

The GMAP logframe includes 39 sets of quantitative data for each of the ten demining and MRE country projects, and three qualitative sets of data for each of the six capacity development country projects. In addition, contractors conduct post-clearance surveys which provide additional data on the benefits at household level.

Changes were made to the targets for some outcome and output indicators when the GMAP logframe was revised at the start of phase 2. The changes were accompanied by updated common definitions of direct and indirect mine action beneficiaries. This enabled a breakdown of individual outcome results by supplier and country which could then be more usefully combined at the global GMAP level. There were no major changes to the expected impact of the programme.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

The original business case considered the VfM of GMAP in terms of economy, efficiency, effectiveness and cost-effectiveness. The independent evaluation of GMAP concluded that GMAP demonstrated good VfM. However, there are lessons to learn for future programming, particularly in terms of economy and efficiency gains. These lessons have been considered as part of the design of the new phase of mine action programming.

Key cost drivers and performance
The two key cost drivers in GMAP are staff and assets.
Mine action programmes tend to be run using large numbers of national staff, recruited locally to work as deminers or deliver MRE. International staff are considerably more expensive than national staff and tend to be employed in small numbers as Country Directors or expert, technical staff. It is important to note that all three of the main contractors increasingly used national staff in key management positions over the course of GMAP. International staff increasingly tend to be used only for positions requiring higher management or technical qualifications and experience. Using managers with international qualifications is sometimes mandatory for organisations to be accredited to operate in mine-affected countries. During monitoring visits to the programme, DFID staff and Itad met with national staff who have been promoted through the organisations from deminer to taking on senior management positions. This demonstrated the success of incentives to keep capable and well trained staff in the organisations, and provided communities with career progression in these organisations.
The Itad evaluation found that GMAP has been delivered efficiently, keeping costs proportionate to the local context. For example, as mine action is labour-intensive, employing large numbers of manual mine action teams, the main cost driver is local salaries. The evaluation found that salaries are set against local comparators benchmarking salaries against other mine action operators in each country.
A key risk to the GMAP programme was losing highly trained staff to other sectors. Contractors have invested in incentive schemes to retain highly trained staff. Innovative approaches have increased staff retention for both female and male staff. For example, recruiting locally makes logistics easier and encourages the retention of women, as observed in Laos, Cambodia, and Zimbabwe. Further improvements can be made, in particular by sharing and streamlining approaches where consortium models are used, including shared positions on the appropriate use of comparators for salaries.

Vehicles and specialist equipment represent the largest capital cost to each project. In 2016 Itad reviewed the asset lists prepared by the contractors. As a result, assets were revalued in line with central DFID guidance. In Cambodia and Vietnam, much of the equipment used for GMAP was carried over from previous DFID funding. Capital equipment in Burma was primarily limited to a small number of vehicles and the contractors were careful not to purchase assets unnecessarily.

Over the lifetime of GMAP, two issues have been noted and taken forward as part of the new mine action programme:
The ‘useful life’ of vehicles tends to be five years, and for major operational items such as mine detectors, it is usually four years. In practice, vehicles and mine detectors are kept longer but the cost of repairs and upgrades increases substantially beyond the ‘useful life’. In calculating the annual cost of a mine action project, the capital cost of assets should be amortised over their ‘useful life’. This has been taken forward as part of the inception phase of the new programme.

Over the course of the GMAP programme evidence has found that the original statement in the business case that ‘….as contracts come to an end, assets with residual value will be sold and the proceeds refunded to DFID” has not happened in practice. As has been the case across the programme, the host country waives import taxes on vehicles and equipment, and often require the assets to be transferred to the host government at the end of the contract as an investment in sustainable mine action in that country. More often assets are transferred to a follow-on supplier if the donor continues to fund mine action in the country. Early planning for the useful transfer of assets will be actioned as part of the new programme, with a critical assessment of the assumption that funds would return to DFID. Most assets have remained in use as part of DFID projects or have been transferred to partner governments to support sustainable mine action programmes, in line with Smart Rules, but the value of this has been very low in relation to the total value of GMAP. During the lifetime of GMAP the total value of equipment transferred was £72,725.38, which was kept in use as part of mine action programmes, and in line with Smart Rules. Reflecting on the cost of start-up, capital goods should be understood as an investment over the course of the programme and across future programmes. DFID also expects transfer of assets at the start and end of programmes if suppliers change.

Technological innovation has also improved efficiencies. In Zimbabwe, both contractors have agreed with the national mine action centre (ZIMAC) to reduce the requirement for conducting ‘fade-out’ from 10 metres from the last mine found to 5 metres, making savings in productivity. In practice this means the mine action teams have to search a reduced area of land. In Somaliland, HALO uses the Road Threat Reduction system, which comprises a multi-drive tractor towing a ‘detonation’ trailer which would activate any mines that remain buried in a road. The system rapidly confirms the absence of mines, and this encourages people to use routes which were previously avoided.

Addendums to the business case

There were two formal addendums to the original business case over the course of the programme:

In April 2017 approval was granted to extend to phase 2 countries, and extend the phase 1 contract in Cambodia and the capacity development programme. The addendum did not make any amendments to the activities agreed in the business case but sought approval for a costed extension of £8,125,089 for the period 30/06/2017 to 31/03/2018.

A second addendum was approved in February 2018 to extend the only the phase 2 contract for three months at a value of £3million for the period 1/04/2018 to 30/06/2018.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Overall risk rating: moderate/medium.

The business case for GMAP assessed the likelihood of a negative event happening as low, apart from the risk that returns would be lower than projected which was assessed as high. The impacts across identified risks were assessed as low – medium. The addendums to the business case made no change to the likelihood or impact of risks to the programme.

Overview of programme risk
Overall risk management in GMAP was adequate and met the requirements set out in the Smart Rules. CHASE were kept well informed by suppliers when changes to the risk registers were required, and discussed mitigating actions with the team and Itad. Risk or fraud was tracked adequately. Suppliers responded constructively to requests for enhanced information on safeguarding procedures and DFID was satisfied that the suppliers had the right policies and procedures in place.
Each supplier submitted a risk assessment to DFID as part of its tender. Every three months the supplier informed DFID whether a risk had materialised, and the mitigating actions being taken to minimise the impact. Quarterly meetings with CHASE and suppliers were framed around the risk matrix.
For the phase 1 countries, risks reported by the contractors referred to technical challenges, such as flooding preventing access to operational sites, or delays in getting national authorities to sign MoUs. For each risk, the supplier proposed mitigation actions. A key risk that was not fully addressed was gaining support from DFID country office and/or British Embassy in assisting the suppliers in their negotiations for new MoUs or adjustments to areas of operation. This was also accepted as a lesson by the team in CHASE who have been pro-active in ensuring this support was sought in country when required.
For phase 2 countries, the primary risks were political uncertainty and security challenges. In Somalia a number of security incidents raised the risk level in Somalia and weekly updates on the operating environment were introduced. This involved weekly written updates to CHASE followed up with a monthly telephone call with each of the partner organisations. This ensured DFID was kept updated and the partners were sharing information and lesson learned.

In 2016, as the security situation in South Sudan deteriorated, the MAG and NPA teams stood down and evacuated expatriate staff. By late 2016, MAG made arrangements to return and, following accreditation conducted mine and cluster munition clearance in and around the village of Tindalo. NPA did not deploy to Tinadlo and, in late 2017, made the decision to close down activities in South Sudan.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Performance of Partnerships

At both headquarters and at country level, the relationship between HALO, MAG, NPA and GICHD has been cooperative and consistent. Lead suppliers submitted quarterly progress reports for each country detailing progress and risks to CHASE, and then to Itad when the monitoring and evaluation contract began.

There were two major developments in how suppliers delivered GMAP over the lifetime of the programme: the evolution of a consortium for the Phase 2 project covering Zimbabwe, Somalia, South Sudan and Burma; and the start of the monitoring and evaluation contract with Itad. The consortium model, led by HALO, enabled CHASE and the suppliers to work in closer collaboration, promoting standardised terminology and operational activities across the programme and ensured the partners shared lessons learned. The introduction of the monitoring and evaluation contract strengthened oversight of the global programme and enabled access to third party mine action expertise.

Suppliers were expected to submit quarterly financial forecasts for the year ahead along with the actual expenditure for the previous quarter. HALO, MAG and NPA provided forecasts with each invoice along with the quarterly progress reports; however, occasionally they were late to update CHASE on changes in country that affected the forecasts and didn’t take into account issues that could have been foreseen. For example in Cambodia in 2017 information on HALO invoices submitted to CHASE did not reflect the situation on the ground. This was promptly rectified by the end of the next quarter.

Following recommendations from the 2016 GMAP Annual Review, NPA appointed a contract coordinator in their headquarters in Norway. This helped improve the communication between NPA headquarters, County Directors and CHASE. Financial reporting also improved throughout 2017 with NPA providing accurate forecasts and clear statements on what was achieved ensuring CHASE were kept up to date.

Compliance

GMAP was part of the DFID delivery chain mapping pilot, with partners complying with DFID transparency regulations by providing information of the delivery chain down to recipient. This allowed DFID to have clearer oversight of the full chain of partners for each UK funded programme. GMAP partners have been compliant with the UK aid branding guidance by completing the UK aid visibility statement. All GMAP suppliers responded constructively to enhanced due diligence actions over the course of the programme, including providing information on safeguarding policies and procedures in 2018.

Suppliers provided CHASE with sufficient data on programme delivery to track outputs and outcomes against spend inputs. The GMAP logframe includes 39 sets of quantitative data for each of the ten demining and MRE country projects, and three qualitative sets of data for each of the six capacity development country projects. In addition, contractors conducted post-clearance surveys which provided additional data on the benefits at household level. Over the course of GMAP the suppliers started to conduct post-clearance surveys up to 12 months after activities ended, which has helped capture a more accurate picture of how land is used, accepting that change doesn’t happen immediately in every country context. The GMAP suppliers have continued to disaggregate data according to gender and age. Discussions on methods to accurately capture data on disability were started during GMAP and are continuing under the mine action programme.

In addition to tracking beneficiaries according to gender the suppliers also provided information on initiatives to encourage women to join demining teams, and achieve a gender balance in their organisations. In 2017 there was an increase in the number of female national staff employed in both demining and MRE roles. The GMAP project in Cambodia saw a significant increase in female HALO deminers from 21% in 2014 to 45% in 2018. In addition to the disaggregation of data by gender, these actions demonstrated a commitment to all obligations under the International Development (Gender Equality) Act.

Finance and Asset Monitoring

Suppliers were expected to submit quarterly financial forecasts for the year ahead along with the actual expenditure for the previous quarter. This ensured CHASE was compliant with the rules and principles set out in the Treasury’s Managing Public Money and Consolidated Budgeting Guidance. Agreed budgets were managed in-year to ensure that DFID remained within its overall budget to deliver mine action commitments. Any variance to forecasts was shared with CHASE on the understanding that failure to comply with this would result in loss of funds from the programme. Suppliers performed well across the lifetime of the programme and managed variances increasingly efficiently.

GMAP required partners to procure, manage and maintain high value assets including vehicles, mechanical demining equipment, mine detectors, radios and personal protective equipment. The suppliers were required to keep an up to date inventory of vehicles and equipment, their condition and location which would be made available to CHASE on request. 90 days from the end day partners submitted a proposal for the disposal of the DFID-funded assets for the programme. On monitoring visits, Itad assessed the partners care and due diligence by reviewing their management policies and procedures, reviewing asset lists, sample testing and reviewing the service and repair facility.

At the end of the capacity development contract DFID agreed to transfer ownership of a small number of assets to the Somali national mine action authority. When signing over ownership DFID confirmed that assets will continue to be used for mine action; that the recipient had adequate resources to maintain and operate the asset, including purchase of any consumables; that they will not be sold or disposed of, or diverted for another purpose, within a responsible time period; that the recipient has adequate controls in place to ensure that the assets are used as intended; and that any local requirements, regarding duties and taxes or any other formalities, on transfer will be met, in line with DFID’s Smart Rules.

Mozambique was declared mine free in 2015. However, HALO continued to deal with questions over the disposal of a number of assets, like mine detectors and some vehicles that were now redundant after large scale mine action activities had come to an end. It was established in 2015 that there was no active market for re-sale of these items and export licences, to allow equipment to be used in mine action programmes in other contaminated countries, would not be authorised. In consultation with number of donors who also supported mine action in Mozambique a proposal was agreed with the Government of Mozambique to make best use of the remaining assets. It has been agreed that the remaining assets will be split in to three with one third being transferred to the Government of Mozambique for use in managing residual risk of contamination; one third to be retained by mine action operators; and one third to be sold, with the profit going to fund Government of Mozambique Mine and ERW residual risk management. This resolution represents value for money for DFID as the assets have a low or redundant resale value and those not sold will continue to be used for mine action activities

Date of last narrative financial report	07/08/2018
Date of last audited annual statement	31/03/2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

The introduction of a monitoring and evaluation contract with Itad in April 2016 allowed DFID access to expert mine action advisory services, strengthening the CHASE monitoring activities during phase 1 and 2 of GMAP.

Itad services included reviewing the partner’s progress reports and producing a single quarterly report on the programme. This report included recommendations for any adjustments in milestone targets; advice on proposed personnel changes in supplier’s teams; changes to the risk register; and identification of areas where DFID would need to intervene at an official level with partner governments. This provided additional assurance to CHASE against suppliers reporting of successes, risks and challenges and helped CHASE ensure GMAP was delivering effectively.

Itad updated the logframe and worked with suppliers on adjustments to milestone targets for land release and MRE. Every six months, Itad provided additional information on programme delivery to CHASE, including updates on DFID-funded assets, examples of how the contractors were using innovative approaches in programme delivery, and case studies for specific countries. In addition, Itad conducted a number of monitoring visits covering all GMAP programmes apart from Sri Lanka, where a proportionate desk based exercise was completed. Throughout GMAP, Itad have provided valuable insights about GMAP and engaged constructively with suppliers to ensure VfM and impact were paramount in any adjustments to programme activities and targets.

This PCR was completed using documentation from the GMAP suppliers which was supplied on a quarterly basis, and end of project reports provided for Phase 1 countries. Itad monitoring reports, country case studies, discussions in quarterly meetings and the evaluation have been drawn on. In addition CHASE completed field visits to Cambodia, Laos, Vietnam and Zimbabwe.

Key Lessons

Over the course of GMAP, CHASE has worked closely with suppliers to ensure the programme design remained relevant, and appropriate milestone targets were set at quarterly intervals. Since April 2016, Itad have supported CHASE in monitoring these lessons and, as part of the final evaluation which was delivered in June 2018, were able to report on how GMAP has responded to these lessons. It was possible to respond to the majority of the lessons, while some have been worked in to the new DFID mine action programme.

Lessons from phase 1 and initial delivery of phase 2	Progress in implementing lesson
More use should be made of the suppliers in-country experience in assessing the relevance and design of GMAP activities	This lesson emerged from assessments of the phase 1 programmes and changes were applied to phase 2 countries. In both Burma and Somalia CHASE was able to adjust the scope and form of GMAP based on feedback from the suppliers, bringing in support from country offices and Embassies and Posts where appropriate.
More consistent UK political engagement with national authorities is needed to support GMAP projects and facilitate outcomes.	From July 2016, during delivery of phase 2, CHASE built up a network of mine action points of contact in DFID offices and Embassies or posts where there was no DFID office. Significantly more involvement from this network was noted in the Itad evaluation. This network enabled the CHASE team to intervene more effectively with national authorities when required, particularly in Cambodia, Laos and Somalia.
The most successful country capacity development projects are those where the supplier has full-time presence in-country, often collocated with the national or provincial authorities.	This was a weakness identified in the Sri Lanka programme in particular, where technical assistance was provided remotely with occasional visits from experts. During phase 2 NPA collocated with the Somalia national mine action authority (SEMA) which had an impact on the gradual strengthening of SEMA and the successful delivery of GMAP outputs.
In depth livelihoods analysis 12-18 months after clearance should be conducted to discover if there is a correlation between demining and increased income.	Post-clearance surveys are now being conducted by suppliers up to 12 months after clearance.
Gender-disaggregated outcome data should be more clearly articulated by suppliers in their quarterly reports	Some progress has been made in providing both the data and analysis of how suppliers have then used the data – for example in better targeting women where there is a need for MRE, but under-representation in attendance at sessions.

Lessons for future mine action programmes

GMAP has provided a number of lessons that have been absorbed by CHASE to apply to future mine action programmes.

Major findings include the need for programmes to be designed and developed, and implemented, to maximise outcomes as well as outputs, and take better account of the specific country context. The GMAP theory of change was designed as a global framework and is heavily weighted toward tracking outcomes related to livelihoods, like the productive use of land. While this is useful for some contexts, the expected outcomes should be tailored to each country context. This will help strengthen prioritisation of land and tracking of beneficiaries where the outcomes may be more related to facilitating humanitarian access, or allowing the return of IDPs.

As a centrally managed programme, GMAP has required substantial levels of engagement with DFID country offices and British embassies in order to generate, or sustain, political support in partner governments for mine action. This has to be maintained in future programmes to maximise the value of the mine action programmes and the impact for beneficiaries.

The operational reach of GMAP has been increased effectively through local implementing partners and this should be encouraged in future programmes. In Burma, Laos and southern Somalia, GMAP has demonstrated that mine action can be delivered effectively and safely through local mine action implementing partners. The use of local partners is likely to increase in the future to enable operational access to areas where international NGOs cannot safely reach, and as a positive move towards greater national ownership and sustainability of national mine action programmes.

In future programmes CHASE should prioritise the clearance and reduction of land, rather than treating cancellation as an equally weighted activity. It is difficult for suppliers to predict when land will be available for cancellation and at what volume, and we know that clearance and reduction of land has a greater positive impact on communities when that land is released.