Annual Review

Title: Strategic Partnership with UK Office for National Statistics
Programme Value £ (full life): £4,500,000		Review Date: Sept 2017 – June 2018
Programme Code: 300443	Start Date: Sept 2017	End Date: March 2020

Summary of Programme Performance
Year	2018	2019	2020
Programme Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/15270940.odt
DevTracker Link to Log frame:

A. Summary and Overview

This programme is building a strategic partnership between DFID and the UK Office for National Statistics (ONS). The programme builds on ONS’ current small scale international development work and is helping them to build their own capacity so they can scale up the technical assistance they provide to developing countries.
Since implementation of this programme, ONS have begun establishing new medium to long term partnerships with three African countries (Ghana, Kenya and Rwanda) and with the UN Economic Commission for Africa (UNECA) through their Africa Centre for Statistics (ACS). There has been good progress made so far on these partnerships, although the length of time that is has taken to recruit in-country advisors to lead the partnerships, has slightly slowed anticipated results.
Alongside the four partnerships, ONS have also developed a short term flexible support component which has provided short-term support to DFID and wider statistical capacity building initiatives. Over the last year there have been eight projects that the Flexible Facility has funded, each varying in scope, scale and financial contribution.
This is DFID’s first Annual Review (AR) for the programme and it will focus on activities from the start of the programme in September 2017 up until the end of June 2018. This review is based on results reported quarterly, and as the latest report was submitted up to June 2018, the review will only consider results up to June 2018 so as not to delay the annual review (due beginning of September).
The reader may find the indicators on the progress on the partnerships slightly unusual, as they are numerical values, rather than descriptions of achievement. The reader is encouraged to look at Annex A where there is a key to the indicators and the relevant scoring.

Summary supporting narrative for the overall score in this review

This programme has received an A for its first annual review. This indicates that the programme outputs ‘met expectations’. ONS should be pleased with the progress of their work over the last year, there have been substantial achievements in the flexible facility and the beginnings of long-standing relationships in the four partnerships.
The arrival of the advisors in the four partner organisations will shift how ONS is able to work and will hopefully ensure that all output milestones for the second year, are realised. As these partnerships grow it is important that ONS considers the sustainability and exit of each of these partnerships and that this is openly discussed with all stakeholders to ensure all partners are aware of each other’s’ expectations.

Recommendations for the year ahead

Recommendations
Output 1 (Kenya)	DFID and ONS to ensure the work programme with KNBS is flexible and is aligned with wider UK work on supporting Kenyan systems and capacity building work
Output 2 (Ghana)	Ensure future Ghana post-holder engages not only with UK government priorities, but brings other donors to support GSS’ work plan and aim to improve SDG reporting
	Add output indicators 2.3, 2.4 and 2.5 to the logframe and begin to monitor them.
Output 3 (Rwanda)	Add output indicators 3.3, 3.4, 3.5 and 3.6 to the logframe and begin to monitor for NISR
	DFID and ONS to look for creative ways to fill the adviser posts including using UK advisers travelling to the region and looking at creative ways to train and incentivise staff to work overseas
Output 4 (UNECA)	DFID and ONS to ensure the work programme is flexible but that it also has clear tangible outputs for UNECA’s workstream
Output 5 (Flexible Facility)	DFID to engage further with the Trailblazer work (FF5) and ensure there is joined up coordination across both departments, departments should consider working on a joint online platform to improve communication.
	DFID and ONS to develop a prioritised action plan for the coming year and agree a new log frame indicator to capture the progress of FF5 in subsequent annual reviews
	It is recommended that ONS develop specific output based targets for each of the task forces in FF 8 and capture these in the log frame under target 5.3
VFM	ONS and DFID to create VFM indicators for the programme in order to assess and quantify progress on VfM
Risk	ONS to continue developing risks registers specifically related to individual country partnerships and develop their risk appetite
Overall	ONS to consider sustainability and exit of each of the partnerships and communicate this with partners

## B: DETAILED OUTPUT SCORING

Output Title	Kenya National Bureau of Statistics (KNBS) increases the availability and quality of SDG data, with ONS support
Output number per LF		1	Output Score	B
Impact weighting (%):		20	Impact weighting % revised since last AR?	N
Risk rating		Moderate

Indicator(s)	Milestone(s) for this review	Progress
1.1: Measure of progress on implementing the project work plan	2	1
1.2 Measure of partner commitment towards establishing effective partnership with ONS	2	1

Overall Output 1 moderately did not meet expectations.
Indicator 1.1 – Milestone not met
ONS’ work with the Kenya National Bureau of Statistics (KNBS) has not reached the expected achievements but progress has been made since the start of the programme. ONS and KNBS have identified potential areas for collaboration but the work plan is still being developed. A number of quick wins have been identified, which will be taken forward alongside the development of a final work plan and output targets. A peer-to-peer relationship has been set up between the UK National Statistician and the Director General of KNBS and they have had their first one-to-one meeting. The Director General found this meeting extremely helpful and is very keen to continue this relationship. This partnership has been hindered by not having an ONS staff member embedded in KNBS, as was originally planned. ONS have found it challenging understanding KNBS’s priorities remotely, especially during a particularly busy period for KNBS due to Kenya’s upcoming census. Once an ONS adviser is in post, and based in Kenya, the programme is aiming to identify specific output indicators within three months of the Adviser being in post.
Indicator 1.2 – Milestone not met
As mentioned in indicator 1.1, not having an ONS member of staff in Kenya has made it more difficult to engage with KNBS and the content of and timings for visits have so far, been largely driven by ONS. KNBS agree that a partnership would be beneficial, but the engagement is currently primarily with the Director General and the Directors of each business area, and the progress on the partnership has not yet been widely shared with their Statistics Board or the Ministers. KNBS have recently appointed a new member of staff in the strategic directorate to lead engagement with ONS, and once the ONS lead adviser is appointed, we should expect more rapid progress.
Lessons identified this year, and recommendations for the year ahead linked to this output
The future ONS staff member will have to be flexible and work with and alongside KNBS, ONS, DFID, FCO and the British High Commission. In order for this partnership to be a true UK-Kenya partnership, the adviser should ensure that the strategic relationship between ONS-KNBS are also aligned with the wider UK work on supporting Kenyan systems and capacity building work.

Recommendations
Output 1	DFID and ONS to ensure the work programme is flexible and is aligned with wider UK work on supporting Kenyan systems and capacity building work.

Output Title	Ghana Statistical Service increases the availability and quality of SDG data, with ONS support
Output number per LF		2	Output Score	B
Impact weighting (%):		20	Impact weighting % revised since last AR?	N
Risk:		Minor

Indicator(s)	Milestone(s) for this review	Progress
2.1: Measure of progress on implementing the project work plan	2	2
2.2 Measure of partner commitment towards establishing effective partnership with ONS	2	1

Overall output 2 moderately did not meet expectations.
Indicator 2.1 – Milestone met
ONS and the Ghana Statistical Service (GSS) have created and agreed on a work plan, with tangible activities and measures of success identified. The work plan has been discussed with senior GSS management and has also been presented to the GSS Steering Committee in June 2018, which includes a wide range of stakeholders.
The work plan has a range of clear outputs and activities which includes the following priorities:
- Building partnerships with data suppliers to facilitate gaining access to new data sources;
- Developing a matching strategy that enables GSS to link record level administrative data in the absence of a population register / ID scheme;
- Developing a quality framework to enable GSS to assess the statistical quality of administrative data, and enable feedback loops with data suppliers to improve the quality;
- Communicating the impact of GSS statistics to key stakeholders to raise GSS’ profile and continue making the case for sharing data;
- Build GSS capability in change management and influencing senior managers;
- Support progression of the SDGs, including technical support to a National Reporting Platform;
- Support in conducing 2020 census and beyond; and
- Other ad hoc support.
Indicator 2.2 – Milestone not met

ONS have found engagement with the GSS to be very positive and responsive. This can be demonstrated by the full engagement in the visit to ONS as part of the data festival, where four GSS delegates visited the ONS office (only two funded through this project, the other two funded by GSS) and the agenda was very much shaped by their inputs. However, given the high number of staff vacancies, and the multiple donor projects operating in the GSS, remote engagement has been more challenging, with the agenda and timing of visits to Ghana primarily driven by ONS. When ONS staff and GSS staff meet face to face, the visits are very productive and the GSS make the most of the expertise available. These visits are enhanced when the same delegation from GSS and ONS meet, helping deepen relationships, which has not always been the case. However, having an advisor in post will ensure consistency and aligned messaging from ONS.

ONS has provided remote support to GSS, commenting on their new Statistical Bill. Whilst the Bill is not yet law it is anticipated it will strengthen the GSS to uphold the basic principles of professional independence, confidentiality, impartiality, relevance and reliability of statistics: and give a mandate for data collection. A communications expert visited the GSS to provide advice on their communications strategy, but this is still at the very early draft stage, and we expect that over the next year this work will continue. These activities will be covered under a proposed new indicator 2.3 in future years.

Lessons identified this year, and recommendations for the year ahead linked to this output
A recommendation for the future advisor in post is to ensure that they not only engage with the DFID and UK government priorities but that they continue engaging with other donors, and help shape the wider engagement and support around this important piece of work.
As a result of the work plan with GSS being established, ONS and DFID have agreed to add more indicators under Output 2. These are listed below, and although not part of this review’s scoring, will be part of next year’s review. These include the following output indicators:
- Indicator 2.3: Number of cases of where ONS have provided advice on strategic policy documents: (e.g. Statistical Bill, communications strategy, other policy documents) and there is evidence that this advice has had an influence on the final product (cumulative)
- Indicator 2.4: Number of leaders mentored or trained by ONS support (cumulative number of individuals)
- Indicator 2.5: Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative).

Recommendations
Output 2	Ensure future Ghana post-holder engages not only with UK government priorities, but brings other donors to support GSS’ work plan and aim to improve SDG reporting
	Add output indicators 2.3, 2.4 and 2.5 to the log frame and begin to monitor them.

Output Title	Rwanda Statistics Office increases the availability and quality of SDG data, with ONS support
Output number per LF		3	Output Score	A+
Impact weighting (%):		20	Impact weighting % revised since last AR?	N
Risk rating:		Minor

Indicator(s)	Milestone(s) for this review	Progress
3.1: Measure of progress on implementing the project work plan	2	3
3.2 Measure of partner commitment towards establishing effective partnership with ONS	2	3

Output 3 moderately exceeded expectations.

Indicator 3.1 – Milestone exceeded
During the last year, a clear work plan has been agreed with the National Institute of Statistics Rwanda (NISR), with tangible activities and measures of success identified. The work plan was agreed in March 2018 and several activities have now started. These include visits to NISR to support communications, developing a training plan, and identifying data science projects to be taken forward. University of Rwanda lecturers visited the UK Data Science Campus in May/June 2018 and met with ONS’ UK academic partners. NISR staff have also undertaken training in the UK; one NISR staff member attended a Data Science Foundations MSc module in the ONS and visited ONS’ Newport Office and campus for two weeks at the end of May/early June 2018.
The partnership will focus on:
•	The development and delivery of a data revolution plan for Rwanda;
•	Data science projects;
•	The establishment of the NISR Training Centre and Data Hub;
•	Capability building and collaboration.

There are three data science projects in the pipeline. One (the SDG platform) is underway, with the platform being built and currently being populated. Two others are at the scoping stage:
Developing a Reproducible Analytical Pipeline for Producer Price Index and Production Index; and
Mining data from a new Electronic Data Warehouse at the National Bank of Rwanda which pulls together granular data daily from over 600 banks, insurers and other financial organisations.
This activity will be covered under a new indicator 3.4 for future years.
Indicator 3.2 – Milestone exceeded
It is has become apparent over the course of the year, that NISR are driving the ONS-NISR partnership. NISR have been the ones to request support in key areas and push ONS to fulfil their requests. For example NISR have been proactively chasing ONS to send someone to support them to develop their ICT systems to facilitate analysis and management of larger and more complex data sets securely. ONS have not yet been able to send someone to support this work, due to commitments of ONS staff, and have been trying to support through remote exchanges. NISR have been extremely proactive in ensuring that ONS meet their deadlines, rather than the other way around.
Lessons identified this year, and recommendations for the year ahead linked to this output
A lesson learnt is that recruitment is a slow process and there is a very limited pool of applicants, this has been a common theme with all of the posts advertised for the ONS programme, and not unique to Rwanda. Although it has taken time to recruit an adviser to work with NISR, these delays have helped ONS to realise which activities can be conducted remotely and will lead to a different type of partnership.
Similarly to Ghana, since the establishment of the work plan ONS and DFID have agreed to add more indicators for next year’s annual review. Although not contributing to this year’s scoring, the proposed output indicators are listed below:
- Indicator 3.3: Number of national statistical strategies / sectoral modernisation plans or equivalent informed by ONS advice
- Indicator 3.4: Number of joint data science projects, with published results
- Indicator 3.5: Number of stories of change of where ONS has helped NSOs to develop training materials / capacity development approaches
- Indicator 3.6 Number of people trained with ONS support (cumulative)

Recommendations
Output 3	Add output indicators 3.3, 3.4, 3.5 and 3.6 to the log frame and begin to monitor
	DFID and ONS to look for creative ways to fill the adviser posts including using UK advisers travelling to the region and looking at creative ways to train and incentivise staff to work overseas.

Output Title	UNECA’s Africa Centre for Statistics (ACS) provide an enabling environment for African National Statistics Offices, with ONS support
Output number per LF		4	Output Score	B
Impact weighting (%):		15	Impact weighting % revised since last AR?	N
Risk:		Minor

Indicator(s)	Milestone(s) for this review	Progress
4.1 Progress towards establishing an effective project work plan	2	1
4.2 Measure of partner commitment towards establishing effective partnership with ONS	2	2

Overall this output moderately did not meet expectations.

Indicator 4.1 – Milestone not met
No work plan has been established yet, although United Nations Economic Commission for Africa (UNECA) through their Africa Centre for Statistics (ACS) and ONS have identified a number of potential areas for collaboration including: census 2020, Civil registration and vital statistics work, data science, leadership training and economic statistics. A few draft work plans have been created but these have largely been not implemented. This is due to organisational capacity at both ends, and should be resolved once the Adviser is in position (in September 2018). An exciting development is that following the visit to the ONS Data Science Campus in March, ACS are now considering creating a data science campus for the region (UNECA member states), and ONS have begun drawing on experiences from the UK and Rwanda.
Indicator 4.2 – Milestone met
ACS have engaged with ONS positively and respond quickly to suggestions for support and potential collaboration. ONS have welcomed how ACS are able to articulate their views and needs in an open and timely manner, providing priorities and timings for activities. However, planning activities remotely have been extremely challenging and ONS hope that this will no longer be an issue come September.
ONS was pleased that the Director of the African Centre for Statistics at UNECA was able to visit ONS for productive discussions in March, and also attended the Data for Development festival in Bristol 21 – 23rd March 2018.
Lessons identified this year, and recommendations for the year ahead linked to this output
The remit of the ACS is very wide and there are many areas where ONS could partner with them. These could include providing additional technical inputs to allow ACS reach to be much wider, or to bring additional expertise where ACS currently has skills gaps. The scoping team recommended a short list of areas, which were based on a combination of ACS’ priorities, ONS’ comparative advantages and the objectives of this programme as defined by DFID. The Adviser must work together with management at ACS and ONS to ensure that the key deliverables are the most strategic and tangible.

Recommendations
Output 4	DFID and ONS to ensure the work programme is flexible but that it also has clear tangible outputs.

Output Title	Flexible short term facility
Output number per LF		5	Output Score	A+
Impact weighting (%):		25	Impact weighting % revised since last AR?	N
Risk		Minor

Indicator(s)[1]	Milestone(s) for this review	Progress
5.1 Weighted average (by spend) of scores for flexible facility activities related to ONS engagement in key data for development international events	A	A++
5.2 Number of case studies of partner countries successfully cloning and using UK/US SDG platform as a direct result of ONS support (cumulative) [FF1]	1	2 countries
5.3 Effective participation of ONS in ICP technical working groups [FF8]	Work plan developed and participation initiated. Targets for future years set.	Targets for ONS participation have been set and participation has been initiated.
5.4 Effective progress towards targets in work plan for project to improve the quality consistency and dissemination of statistics on employment and productivity [FF2]	A	B
[1] It was agreed that indicators would capture large one off events (indicator 5.1) and other indicators would relate to each major FF project activities that go beyond one year and with a budget >£100,000

Overall this output is slightly exceeding expectations
There have been eight projects in the past year through the flexible facility. Each project has a set of clear targets and indicators in the terms of reference (apart from FF5), which were agreed by the DFID/ONS steering committee. These will be monitored after the event and reported back to the steering committee. Indicator 5.1 relates to projects which are events, or less than one year and for this annual review included FF3, 4, 6 and 7. Indicator 5.2 relates to FF1, indicator 5.3 to FF8 and indicator 5.4 to FF2.

Flexible Facility Project[2]	Budget Spent £	Overall weight	Project Score
FF3 - Age and Ageing	1,522	4%	A+
FF4 - Global Platform for Data	1,749	4%	A
FF5 – Data Trailblazers	14,974	35%	N/A
FF6 - Data for Development Festival March 2018	23,601	54%	A++
FF7- OECD launch of Development Co-operation Report	1,486	3%	A
TOTAL	43,332	100%	A++
[2] Scores for FF 3,4,6 and 7 based on narrative reporting and overall indicator score is weighted by budget

Indicator 5.1 – Milestone exceeded
Based on performance of FF3, 4, 6 and 7 this indicator has scored an A++ primarily driven by the excellent work and success of FF6. More details of each of the projects are listed below.
Below is more detail on each of this year’s projects:
FF1 – SDG Reporting Platform 2017- 2020 (see indicator 5.2)
This project aims to provide developing countries with an open source tool for collecting and reporting SDG data, and with supporting materials to facilitate implementation and analysis. Over the year ONS has produced manuals to help other countries how to copy the UK SDG Reporting Platform, and presented their SDG reporting platform at the UN with representatives from other national statistical offices. Both Ghana and Rwanda have replicated the US/UK SDG reporting platform as a direct result of ONS engagement, and it is anticipated that their platforms will be launched before the end of 2018. In addition ONS understands that a number of other countries (including Australia and possibly Canada) have also used the open source materials to replicate the US/UK platform themselves.
FF2 - Improving measurement of jobs and productivity, 2017 – 2020 (see indicator 5.4)
This project’s aim is to improve the quality, consistency and dissemination of statistics on employment quality and productivity with the ultimate objective of creating more productive, high wage employment and productive economies in low income countries.
A key achievement of the last year has been getting the statistics team at the International Labour Office (ILO) to complete a draft of a detailed study report of key considerations for developing countries regarding the collection and production of labour statistics. This work feeds off their current programme of pilot studies where a number of new survey approaches have been tested among selected countries. Going forward, ONS will collaborate with the ILO to design algorithm for helping countries determine the most appropriate data collection methods with respect to their priority areas of interest. An informal working group continues to work on this, and the World Bank have participated in this and have delivered their initial element of the work plan in the form of an inventory of household surveys that produce labour statistics. Further progress is envisaged at the ILO-hosted International Conference of Labour Statisticians (a 5-yearly event) in October where ONS will be working with ILO colleagues to increase the profile of the working group.
FF3 - Age and Ageing, 2017-2020
This project aims to support the United Nations ‘Titchfield City Group on Ageing’ by helping to improve the collection, analysis and use of good quality data on age and ageing in developing countries, to evidence the equitable delivery of the SDGs, and support the international community’s pledge to leave no one behind. The group was officially endorsed and established by the UN Statistical Commission in March 2018. Spend in this area from the DFID budgets has been relatively small, but ONS organised and hosted the first meeting of the Titchfield City Group on Ageing, which was held on 26-27th June 2018. The event was well-received and ONS organised speakers from developing countries to attend, to ensure developing country voices were heard and taken into account in proposed measures for improving the availability, quality and sharing of data and statistics on older persons. However, as the majority of the sponsorship cost was covered by UNDP and the four delegates ONS were due to sponsor were unable to get an approved visa in time to attend, therefore there was very little spend required through FF3.

FF4 - Global Platform for Data, 2017 - 2020
This project aims to support the UN Global Platform for Data, Applications and methods to be of most relevance for developing countries. So far the funding has only been used to fund a delegate from Mexico to attend the Global Platform meeting in the UK, October 2017.
The vision for the Global Platform is a public private partnership, building a platform to allow data to be shared for statistical and research purposes, to enable data-driven transformation for better decision making, and to improve the world by providing access to trusted data for use at local, national and global levels. The aim is for both developing and developed countries to be significant beneficiaries.
Data sharing is an important initiative, however, the Global Platform has struggled to communicate clearly what types of barriers they are seeking to tackle, nor what types of data they are focusing on. It is recommended that ONS continue shaping the Global Platform and encourage better external communication. As this project continues DFID and ONS will continually review opportunities to ensure that the design and implementation of the Global Platform consider the needs of developing countries. Proposals will be put to the steering committee for any opportunities for this project to support this aim.
FF5 – Data Trailblazers, 2017 - 2020
This project aims to support DFID in transforming their collection, management and analysis of administrative data, including the use of data collected by external partners, to create an efficient automated data management system, with agreed data standards, and systems for open data publication. ONS and DFID had extremely positive engagement in April 2018 and ONS have brought along valuable skillsets not available in DFID, which is helping shape the work.
This project has the potential to revolutionise the way DFID collects, manages and analyses results data, finance data and more. ONS have developed a new logframe tool called ‘DART’ (Development Activities Results Tracker) which is expected to be further developed in autumn 2018. ONS has progressed this line of work as far as possible and there now needs to be further engagement and decisions to be made by DFID. It is recommended that FF5 develops an indicator for Output 5.
FF6 - Data for Development Festival March 2018 (see indicator 5.1)
The Data for Development Festival, and the ONS side visit held in March 2018, was an extremely successful project. More than 400 delegates attended, with equal sectoral representation from governments, civil society, NGOs, and the private sector. Nearly 1,500 people joined the conversation online using #Data4DevFest, helping them reach more than six million people across six continents. A private sector delegate commented “I am continually amazed at how this community of practice has come together to not just talk, but to put the wheels of action into motion.[3]” All of the targets that ONS set to measure the success of this event were exceeded. 78% of the 163 people, who responded to a survey on the Festival, indicated they felt it had left them better equipped to contribute to achieving the Sustainable Development Goals.
[3] http://www.data4sdgs.org/sites/default/files/2018-06/Data%20Fest%20Report_Final_11June_compressed.pdf
ONS contributed to the festival by organising a side visit to the Newport offices and data campus, where half of the attendees from the festival joined for the ONS trip. ONS were able to showcase their work and make a number of invaluable connections and potential collaborations identified. ONS’ work on the SDGs, which are universal for all countries enabled ONS to engage as an equal partner with developing countries. As a result of the Data for Development Festival, a number of collaborations were identified, which ONS are now progressing with.
Feedback on the ONS campus field visit was very positive; comments in ONS feedback survey were that visitors learned a lot, especially about “How data science, new technologies/data sources, and innovation can play a role in national statistical offices” and how ONS is responding to the SDG agenda. Additionally, visitors valued “the energy and enthusiasm of staff working to modernize ONS”. There were lots of positive comments on the welcome received: “For me, this was one of the highlights of the Data Festival. I appreciate the ONS' herculean effort to organize the visit, making staff available to talk about specifics, and provide hospitality (including the choir). In all, a very productive and enjoyable field trip!“ and “It was a fantastic visit. The hospitality and engagement of all ONS colleagues provided invaluable insights and ideas on how to improve our own work. Thank you sincerely!”.
FF7- OECD launch of Development Co-operation Report 2017: Data for development[4], October 2017
[4] OECD (2017), Development Co-operation Report 2017: Data for Development, OECD Publishing, Paris,https://doi.org/10.1787/dcr-2017-en.
This small project supported developing country participation in a one off event: international discussions on bridging the data divide. ONS supported the participation of a Right to Access Information Commissioner from Sierra Leone which ensured a balanced discussion. No specific measures of success were set, but the work has been going forward with further discussions in the margins of the World Bank Spring Meetings (April) and then at the High Level Group (8 May) and the High Level Political Forum (July).
FF8 - Technical contribution to the International Comparison Programme (ICP),Jan 2018 – 2020 (see indicator 5.3)
The ICP aims to estimate Purchasing Power Parities (PPPs) for use as currency converters to compare the size and price levels of economies around the world. Comparisons of the economic size of countries can be used as an indication of the economic welfare of their populations. In addition, comparisons of expenditure in specific sectors, such as education or health, can support policy and resource allocation decisions - for example, by governments, international organisations and donors. PPPs also inform updates to the International Poverty Line and therefore the count of the global poor, the SDGs and the Human Development Index.
ONS has agreed to participate in a number of Taskforces since January 2018 by contributing expertise to the ICP’s technical research agenda in order to improve the methodology, and data quality and availability underlying the ICP, to improve overall data quality over the new three-year comparison cycle. They have also been the main author of a practical guidance document on the production of regional data. The specific task forces ONS is a member of are:
•	Task Force 2 - Operational Guidelines and Procedures; [Operational and formed]
•	Task Force 4 - PPP Uses [not yet formed]; and
•	Task Force 7 - PPP Quality and Reliability [not yet formed].
It is recommended that ONS develop specific output based targets for each of the task forces once the task forces have been formed and the roles of group members assigned.
Lessons identified this year, and recommendations for the year ahead linked to this output
A lesson learnt over the year is the importance of ensuring that the DFID sponsor for each of these Flexible Facility projects are regularly updated and communicated with. ONS should ensure that any material going to the ONS-DFID steering committee that concerns one of the FF projects, has also been seen by the DFID sponsor of that project.
The Trailblazer work has demonstrated the importance of having strong engagement by both DFID and ONS and how the departments can work well together.

Recommendations
Output 5	DFID to engage further with the Trailblazer work (FF5) and ensure there is joined up coordination across both departments, departments should consider working on a joint online platform to improve communication.
	DFID and ONS to develop a prioritised action plan for the coming year and agree a new log frame indicator to capture the progress of FF5 in subsequent annual reviews.
	It is recommended that ONS develop specific output based targets for each of the task forces in FF 8 and capture these in the log frame under target 5.3.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change and any major changes in the past year
The theory of change is based on the idea that ONS works in partnership with both country governments and regional partners, to enhance the capacity of their statistical organisations through dedicated technical assistance and capacity building work. Through these partnerships, the organisations’ capacity will improve and their commitment to quality data will be strengthened. The increased availability and frequency of data will help inform decision makers and enable citizens to hold their governments to account.
As ONS conduct this work they will also learn more about practices used by other countries and this will also feedback into learning for the ONS in terms of how they collect and analyse data. For example, the ONS SDG team, through their discussions with Ghana and Rwanda, have identified a number of future enhancements which they will be making to the UK SDG platform.
Importantly this programme will work/ is working alongside other DFID programmes that are aiming to improve developing countries’ capacity to monitor the Global Goals, as well as the global community’s ambition to report on progress in 2020 and 2030.
During the first year of this programme, there have not been any changes to the theory of change.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The programme is currently on track to deliver the expected outcomes, although it has had a slightly slower start than anticipated as ONS were unable to place key staff in country. As this was ONS’ first time to place staff overseas, a number of policies and procedures needed to be in place before staff could be posted overseas e.g. security, allowances, health care. The processes have now been set up whereby ONS staff are ‘loaned’ to the Foreign and Commonwealth Office, so that the ONS staff are covered by the appropriate systems and procedures.
The lack of in-country staff has not significantly delayed activities but rather has modified how ONS have interacted with the national governments. It has helped to build a different type of relationship between the UK based ONS office and governments, rather than relying on in-country ONS staff. The cultivation of these long-distance relationships has enabled ONS to judge where it is essential to have key personnel in post to drive forward activities, and where support can be provided from their UK based staff.
Explain major changes to the logframe in the past year
Over the last year the logframe has been developed and finalised with detailed consultation between DFID and ONS. A sophisticated methodology has been developed to support monitoring of technical assistance and how effective the capacity building activities have been, something which is often difficult to quantify.
Describe any planned changes to the logframe as a result of this review
After this annual review, new indicators will be added to Outputs 2 and 3, as a result of the work plans being developed and clear milestones being set.
Details of these are already listed under the Output sections.
ONS and DFID will also consider how to develop an outcome indicator on the capacity of ONS; this may include surveying ONS staff about their experiences and confidence of their ability to work in international development projects.
As part of this partnership, the flexible facility project 5 ‘Trailblazer’ has been developing a new logframe tool called ‘DART’. Although not yet complete for this annual review, ONS will continue to develop DART and use it as part of their programme. It is hoped that DART will be ready soon, and be used for the next review period.

## D: VALUE FOR MONEY
The main cost drivers, staff and travel costs, were identified in the business case and remain the same. Current spending levels have been slightly lower this year than anticipated, due to the fact that overseas staff are not yet in post, but from September 2018 there should be a rise in spending as staff start to fill these posts.
There were no specific VfM indicators developed during the first year of the programme but the time is now appropriate that they are developed so they can be measured over the coming year.
There are a number of examples of how the ONS partnership does demonstrate VfM as outlined below:
- Economy: [Cost of all inputs] As stated above the main cost drivers are personnel and their travel. ONS have consistently pushed for better value for money. For example, negotiating discounts with hotels once it became apparent that the travel agent was not providing ONS with the same discount available to DFID and FCO; using the lowest cost for all flights; booking travel as far in advance and at off-peak times and dates where possible to ensure low prices.
- Efficiency: [Productivity of inputs] ONS have demonstrated how their technical assistance has brought about progress towards this programme’s outputs and the value both the partnerships and ONS receive from that is very high. Additionally, the ONS team utilise the inputs of this programme by successfully making linkages between the flexible facility activities and the partnerships they have with national governments. For example, one of the flexible facility’s programmes was the Data for Development Festival (March 2018 Bristol), and ONS used this opportunity to strengthen the partnership with Ghana, Rwanda and UNECA by encouraging them to visit ONS and have productive meetings and consultations with each. Similarly when the Director of KNBS visited New York, ONS set up a mentoring discussion with the UK National Statistician who was also there. In a different scenario, the flexible facility project FF1 (SDG platform) was able to utilise the ONS relationship with Ghana and Rwanda to help the SDG team to research the type of development that would be of most benefit to developing countries, and they are currently developing online platforms for Ghana and Rwanda as priorities.
- Effectiveness: [What outcomes are achieved] As the project is still in the early stages it is not yet possible to assess outcomes across all of the programme, however for shorter term projects such as the Data for Development Festival (FF6) the result was an extremely effective project that signaled ONS’ leadership on data, and in particular, innovation. In addition, the Strategic Partnership with ONS has an active steering committee, which is used as a governance mechanism to ensure the effectiveness and best of use of ONS resources.
- Equity: [Outcomes for whom?] This partnership is helping to support developing countries’ national statistics offices, which should mean governments are better informed as to their population needs. Another primary user of this programme is of course, ONS itself. ONS has benefitted from receiving DFID technical expertise, especially on guidance on ODA spending. This will help inform ONS’ bid for ODA money once the spending review has opened, and enable them to scale up their international development work.

Recommendations
VfM	ONS and DFID to create VFM indicators for the programme in order to assess and quantify progress on VfM.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
This programme continues to represent good value for money. It is a key part of the Data for Development team’s portfolio, as it contributes to a number of key areas: harnessing innovation (for example through data science projects), it is seeking to modernise national statistical systems which in turn should contribute to the improved monitoring of the SDGs. The partnerships with the three governments should improve their capacity, which will subsequently contribute to collecting and disseminating data on the SDGs. It also works with UNECA which helps to ensure the longer term sustainability of the project as UNECA will be able to continue to work with the countries.
Another advantage to this programme is the flexible facility. The flexible facility’s work allows small-scale or short-term projects to be enacted once approved by the programme’s steering committee. The flexible facility provides excellent value for money as it enables pieces of work that would not always be enacted in such a quick and effective method, whilst facilitating the expertise and skills of ONS and DFID staff. DFID have particularly benefited from ONS’ expertise in flexible facility projects 2 and 8 where their inputs have been extremely valued by all DFID staff.
Additionally, this programme enhances ONS’ capacity to deliver international statistics programmes in the future. It is helping to improve their programme management skills as well as political economy skills so they can work more effectively in specific developing countries. In the next Comprehensive Spending Review, ONS are planning to bid for their own Official Development Assistance (ODA) directly from Treasury, rather than working through DFID. This partnership will have helped ensure VfM is further embedded in ONS’ development programmes and that ONS have built up both the skills and the processes which will enable them to work effectively in a range of developing countries.

E: RISK
Overview of programme risk
This programme’s risk is classed as minor. Of the risks that are on the risk register, the one that still remains the most likely is that the demand for ONS’ staff and time outweighs supply. As the flexible facility expands and takes on new projects, some which are quite complex, there is a need to ensure communication is maintained where projects require action from both DFID and ONS. Both departments should consider how to collaborate and work together more effectively e.g. using joint platforms to share documents or online initiatives to enable departments to monitor progress.
As ONS embeds personnel in country, ONS should strengthen the country specific risk registers which will highlight the key risks to success in working with each of the organisations. ONS should work with DFID and FCO experts in each country to ensure that any specific risks around the political economy or context in each country, are fully understood and monitored, as well as security risks.
As set out in the business case, ONS are the primary owners of the risks and will escalate to DFID as and when necessary. If any risks on the risk register increase they will act quickly to escalate these and take controlling actions. Moderate risks will be escalated to the DFID SRO and major and severe risks will be escalated to the Steering Group. As of yet, there has not been a significant change to the risks register and these actions have not had to materialise; instead over the past few months, ONS have developed their country-focused risk register which enables them to have risk at a strategic level and at a local level.

Recommendations
Risk	ONS to continue developing risks registers specifically related to individual country partnerships and develop their risk appetite

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Performance of partners and DFID, notably on commercial, and financial issues
This programme has one partner, the UK Office for National Statistics (ONS). DFID has found working with ONS extremely productive and they are an engaging partner. ONS have communicated early with DFID as and when there have been changes in the spending levels, financial forecasts or if there have been any financial challenges. ONS provide timely quarterly reports, which contain a detailed narrative of the last quarter, a breakdown of spending, as well as forecasted spending over the next year. ONS have been especially responsive to any financial queries DFID has had and there is an excellent line of communication between the departments.
In terms of the performance of the delivery partners, this partnership is only between the two Government Departments and as such, ONS are only using their own staff and have not sub-contracted out delivery.
ONS and DFID have developed a strong working relationship throughout this programme, the two departments coordinate attendance and participation at external events and have regular discussions with teams to ensure the two departments are joined up. Messages to senior management and Minsters are done jointly which ensures the UK Government is having a more joined-up approach to challenges and opportunities of the sustainable development goals data.

Date of last narrative financial report(s)	June 2018
Date of last audited annual statement (s)	5th July 2018

G: MONITORING, EVIDENCE & LEARNING
Monitoring
The steering committee provides strategic direction for the programme and an accountability mechanism. Each of the major partnerships (Ghana, Kenya, Rwanda and UNECA) have a set of outputs, outcomes, indicators, milestones and targets which they are monitored against, as do each of the flexible facility projects. ONS produce detailed quarterly reports for DFID outlining progress and explaining where progress may be off track, and the reasons for this. The ONS team are developing a new tool for storing and presenting results data for this project, in place of using the DFID logframe template (DART tool).
This annual review was conducted by the programme manager and technical advisor to the programme. The annual review benefited by having discussions with ONS and inputs from DFID in-country staff, as well as input from DFID staff supporting the flexible facility. This review was drafted and agreed in partnership with ONS. The review was also peer-reviewed by a DFID statistician, not involved with the programme, before final quality assurance by DFID’s Chief Statistician.

Evidence

ONS are planning to conduct a review that will look at the effectiveness of ONS’ approach and their work, rather than focusing on whether the outputs have been successfully achieved or not. The review will be done by either ONS/DFID staff not associated with the programme or from the National School of Government International (NSGI). The NSGI specialise in supporting UK government’s partnerships with recipient governments, and will be well placed to look at the success of the partnerships of this programme. The review has not been finalised but may consider (but is not limited to) the relevance of the ONS modernisation for developing country partners and the advice being given; and/or the efficiency and effectiveness of ONS’ international development approach. The review could also critically challenge the assumptions in the ToC and use the findings from the review to feed into the design and implementation of other DFID and ONS statistical capacity building programmes.

Learning
This year has been a year full of learning for ONS, not only on processes strictly related to ODA spending, embedding staff in country, travel policies but also the time and commitment from staff needed to run effective ODA programmes.
To build the learning and capacity of ONS internally, they have ensured that they use all cross-government opportunities to build the capacity of their staff e.g. through the NSGI network and visiting other government departments who are further developed in this type of work. ONS also encourages learning across their staff by ensuring more than one member of staff visits partner organisations, to ensure that knowledge is captured by more than one individual. ONS are also surveying staff to see how their experiences change over the lifetime of this project, and these results will help improve the quality of their international development programming. DFID and ONS will continue to develop the political thinking behind this programme, linking with DFID governance advisers in each country.
Finally, following on from experiences in Rwanda, ONS’ Data Science Campus is developing guidance for ‘data science in a box’, that is hoped to be a useful tool to countries wishing to embed data science in their national statistics systems. The ‘data science in a box’ will set out some of the key steps that an organisation must consider (for example legal, ICT and policy developments needed, as well as training materials that can be used), and it is hoped that this tool will provide a framework for other countries to take the lessons learnt from ONS and apply them.
The Data for Development Festival was an example of sharing learning across a range of organisations working in development data. The side event organised by ONS encouraged countries to share lessons and learn from each other, as well as showcase ONS’ work.
In the coming year ONS will be focused on how to support advisers in country, and being preparations for the Spending Review. Both of these activities will draw heavily on the past year’s lessons learnt and experiences.

Progress on recommendations from previous reviews
N/A - first annual review

Annex A: Key to methodology for indicators on Outputs 1 – 4