Annual Review

ASIA REGIONAL ANTI-TRAFFICKING PROGRAMME - PILOT PROGRAMME

Date started: November 2011 Date review undertaken: December 2012 – January 2013

## Introduction and Context

What support is the UK providing?
The UK is providing £544,780 to pilot different approaches and develop evidence and lessons on how best to help women and girls protect themselves from being trafficked in South Asia. The purpose is to inform the design of DFID’s new programme to prevent trafficking of women and girls from South Asia in the garment and domestic work sectors, which is intended to run from 2012/13 – 2016/17.

What are the expected results?
This Annual Review assesses the first stage of the Asia Regional Human Trafficking Programme and focuses on Design & Inception, with the aim of conducting pilot projects and generating an improved evidence base. / The expected outputs are: / 5 pilot projects, delivered by the International Labour Organisation (ILO), Global Alliance Against Traffic in Women (GAATW), Nimbus Social Enterprise Consulting Ltd and Anti-Slavery International; / 3 literature reviews, delivered by the London School of Hygiene and Tropical Medicine, the Governance and Social Development Resource Centre and a partnership between DFID and the John F. Kennedy School of Government at Harvard University; / A workshop in the region to share latest evidence and lessons; and / A robust measurement and evaluation framework, undertaken by the London School of Hygiene and Tropical Medicine (LSHTM). / Across these outputs, the expected results are: / Robust insights and evidence of trafficking interventions that work, specifically within the garment and domestic sectors; / Evidence of approaches and interventions that use technology and communication systems to tackle trafficking and that give voice to trafficked women so that their experience can inform more effective strategies to preventing forced labour; / Demonstration of practices, approaches and results that show an integrated approach with potential for scalability, partnership and innovation. / A deeper understanding of the legal, policy, institutional and implementation issues of trafficking women and girls in the labour sector in South Asia. / Engagement with over 60 experts in the field, including government, donor, private sector and civil society actors, to share latest evidence and lessons; / Deeper insights into how to design an effective measurement and evaluation framework for DFID’s Asia Regional Human Trafficking Programme. / These results are intended to inform the design of the second phase of the Asia Regional Human Trafficking Programme, which could support results and interventions such as providing pre-departure training for vulnerable women, working with private sector recruitment agents and helping domestic workers secure legal contracts and a decent wage by providing skills training.

What is the context in which UK support is provided?
Millions of people in South Asia attempt to escape grinding poverty by migrating to richer countries in search of work. There is increasingly strong evidence to show that this has a major role to play in tackling poverty, by improving migrants’ wages, standards of living and employability but also by assisting family members and their communities back home through sending remittances. Remittances to Bangladesh, for example, were estimated to account for 12% of its GDP in 2010. / However, many migrants - particularly women and children – are at risk of being trafficked, exploited and abused. This is especially the case for women and girls from South Asia, where gender inequality indicators are amongst the worst globally and women and girls face discrimination and exclusion from economic, political and social opportunities. / Asia has the highest number of trafficking victims. According to the ILO, there are 21 million men, women and children trafficked and in forced labour worldwide, the majority of whom are in Asia (11.7 million). Approximately four million victims of forced labour are from Bangladesh, India and Nepal. / Human trafficking is a crime and a human rights violation. It restricts the ability of people to lift themselves and their families and communities out of poverty. The economic costs of trafficking are considerable. It is estimated that the opportunity costs of forced labour amount to $21 billion annually. / The UN definition of trafficking includes the recruitment, transportation or harbouring of human beings by threat, use of force, coercion, abduction, fraud, deception and/or abuse of power for the purpose of exploitation. Most of the international effort on human trafficking has focused on sexual exploitation. However labour trafficking, which is far more prevalent, has been relatively neglected. / However, preventing trafficking and forced labour of women and girls is complex and challenging. There is little robust research and evidence on trafficking in the garment or domestic work sectors in South Asia. And there is little available data as it is a criminal act that takes place under the radar and is fuelled by corruption. What evidence does exist has not been coordinated or adequately captured and as such remains weak. There are also different approaches to tackling trafficking and it requires careful coordination across different government ministries, agencies, international organisations and civil society groups. That’s why the purpose of this first stage of DFID’s Human Trafficking programme has been to support the development of an improved evidence base so that we can understand the nature of the problem, review the evidence and identify DFID’s comparative advantage. / The programme to tackle trafficking will help deliver DFID’s Strategic Vision for Girls and Women in two priority areas - Preventing Violence against Women and Girls; and increasing Direct Assets for Girls and Women through better wages, working conditions and remittances from safe labour migration. It will also help deliver DFID’s public commitments as part of the UK Government Strategy on Human Trafficking.

## Section A: Detailed Output Scoring

Output 1: To demonstrate practices, approaches and results that can prevent trafficking of girls and women into domestic and garment sectors in South Asia and that show an integrated approach with potential for scalability, partnership and innovation.
Output 1 score and performance description: A+ (Outputs moderately exceeded expectation) / Under this output, a number of external partners were contracted to deliver five pilot projects that: ‘demonstrated practices, approaches and results that can prevent trafficking of girls and women into the domestic and garment sectors in South Asia and that show an integrated approach with potential for scalability, partnership and innovation’. / All five pilots have now been delivered, and all met and in some cases exceeded the expectations set out in their respective Terms of Reference. The pilot projects were (with the contracted organisation shown in brackets): / Vivhaan: Using Innovative Technologies to Prevent Human Trafficking (Nimbus) / Voice and Participation of Trafficked Women and Girls (GAATW) / Preventing Trafficking of Women and Girls into the Garment Industry (ILO) / Preventing Trafficking of Women and Girls for Domestic Work (ILO) / Personal Costs: An analysis of the policies and practices affecting Nepalese migrant domestic workers travelling to Lebanon (Anti-Slavery International)
Taken together, the pilots delivered an impressive set of results, including: / Over 4,000 vulnerable women and girls were engaged in face to face dialogue on human trafficking, for example through community workers who conducted local visits; / Over 650 police were trained to better respond to labour trafficking; / 82 community workers were trained to either travel to local, vulnerable communities and help women and girls avoid being trafficked or work with victims of trafficking. / A new web and mobile platform was built to empower women and girls to find decent jobs and migrate safely; / A wide range of capacity building initiatives were supported to help governments, police and local officials, trade unions and civil society groups better respond to human trafficking in the textile and domestic work sectors; / And while not explicitly the role of these pilots, 14 instances of trafficking were identified leading to the rescue of 4 victims, re-uniting them with their families. / Across these activities, the pilots generated a wealth of insights and findings that together contribute to achieving Output 1. These are set out in detail in the five ‘end of pilot’ reports but, to demonstrate delivery against expected output for the purposes of this Annual Review, these include: / Why women migrate – Research conducted as part of the pilots found that two of the key drivers of women migrating for work are low family income (women who migrate are often the sole provider of income for their family) and a lack of local opportunities. / Victims of trafficking? - Talking to returned migrant women, one of the pilots learnt that many don’t view themselves as having been trafficked, despite the fact that the suffered terrible abuse and exploitation. This is largely because they decided freely to move to another country to seek work. / Recognising labour trafficking - One of the key challenges has been getting the conversation on human trafficking to recognise the issue labour trafficking, as much as sex trafficking. There are few trafficking programmes specifically addressing labour trafficking. And many victims are not identified as ‘trafficked’ by legislation - in either their destination or country of origin – so few ‘anti-trafficking interventions’ are able to reach them. / Face to face outreach works - Surveys showed that women who participated in such sessions within their local communities achieved significant increases in knowledge (e.g. awareness of the availability of pre departure training increased from 50% to 96%). / Use of innovative technologies such as tablet computers by Community Knowledge Workers (CKWs) worked well. The tablets generated interest and awareness with women in local meetings (e.g. via video, women’s stories and visual tips for safe travel). They not only helped to establish CKWs’ status on arriving in a community, but also provided an opening to discuss the issues, helped avoid ‘loss of message’ and worked especially well for people with low literacy. / Pre-departure training – Focus groups demonstrated that women for the most part did receive pre-departure training on the risks they could face, but that it didn’t provide what would have been most useful to them – information and advice on what to do if they find themselves exploited, trafficked or abused (e.g. where they can go to seek help – organisations, embassies, the authorities), and what they were entitled to (e.g. Government insurance schemes in Nepal before departing). / Big brands working with trade unions - Working with the private sector within the global supply chain to join them in dialogue with trade unions meant they were able to understand that a) they had a responsibility to help ensure they didn’t employ trafficked workers and b) that trade unions weren’t just a force that advocated against employers but could work closely with employers and help them to overcome some of these issues. / Multi-dimension interventions are needed - Donor funding for purely project/activity based interventions needs to be matched by allocations for building research, analysis or advocacy capacity of NGOs, the authorities and others to ensure sustainability. / Multi- partner approach - The model of involving a number of partners in delivering anti-trafficking projects proved highly successful – it enriched available expertise and improved project implementation, and should be built on in future programmes. / All of these insights (and significantly more within the fuller pilot findings) are able to inform the design of DFID’s anti-trafficking programme in the region to ensure it delivers effective outcomes and achieves the desired impact. / Recommendations: / This review concludes that the logframe target for Output 1 has been achieved and that no adjustments are required. / Impact Weighting: 50% / Revised since last Annual Review? No – this is the first annual review / Risk: Medium / Revised since last Annual Review? No – this is the first annual review

Output 2: To develop evidence and lessons of what works on labour trafficking prevention in South Asia.
Output 2 score and performance description: A+ (Outputs moderately exceeded expectation)
Progress against expected results: / Work towards this output has performed well, exceeding expected results targets as described below. / This Output exploited the expertise of LSHTM, ILO, academics, donors, private foundations, NGOs, global and regional trafficking experts, practitioners and policy makers. As such, it enabled a wide-ranging review of the evidence and experience in this field and lessons to inform the design of the programme. Trafficking work until now has been extremely contentious, polarised and project-based, with little collaboration between the key stakeholders. DFID was seen as a catalyst for transparent and collaborative knowledge-sharing in the field of trafficking and praised by global experts as modelling good practice on evidence-based policy and programming. This was done in a cost-effective way and delivered good value for money. / Output Indicator 2.1: Number of literature review papers that examine legal, policy, institutional and implementation issues of trafficking women and girls in the labour sector in South Asia. [Target: 3] / The Governance and Social Development Resource Centre was commissioned to undertake a rapid literature review that assessed the evidence of impact from trafficking programmes globally and in South Asia. Their work outlined promising examples of success and lesson-learning. It also identified the key actors with an established track record of programming and credibility on trafficking, particularly in South Asia. / A non-funding partnership with the Harvard Kennedy School of Government provided a legal expert for six weeks to conduct a literature review that analysed each target country separately (Bangladesh, Nepal and India). It delineated the laws and policies relating to trafficking, labour and migration, and analysed the evidence of government measures successfully implemented and gaps that remain. It reviewed programmes in Asia aimed at influencing legal and policy change, and the support provided by donors, international, regional and non-governmental organisations, and the private sector. The paper also made recommendations for potential approaches, priorities and gaps requiring further work. / The London School of Hygiene and Tropical Medicine (LSHTM) were identified as the implementing partner leading on this component for the pilot project phase. The LSHTM has over ten years of experience of research and evaluation work on trafficking and violence against women, and is regarded as a global leader in this field of research. / The LSHTM conducted two systematic reviews of interventions looking at bibliographic databases for relevant articles published in English between 2005 and 2012. Additional documents were located through consultation with experts, search of relevant websites and using reference snowballing techniques. The study was additionally guided by two key questions: / Which are priority components that are either essential to or most likely to have the greatest impact on reducing trafficking of women and girls for domestic or garment labour? / Which are the most complementary or synergistic activities that, when conducted in parallel or together, are most likely to achieve ‘more than the sum of their parts’? / Results found no peer-reviewed articles on evaluation of anti-trafficking programmes for forced labour or labour exploitation in the garment or domestic work sectors. Documents most commonly located were process evaluations, operational studies and dissemination reports, primarily based on qualitative data and desk reviews. In the absence of rigorous evaluation data it was difficult to gauge the effectiveness of interventions. Aims of the most common intervention activities were to: strengthen legislation and law enforcement; reduce higher risk labour migration; and detect and interrupt trafficking situations at destination or offer assistance to leave trafficking situations. / Output Indicator 2.2: Number of workshops supported that bring key donors and stakeholders together to share latest evidence and lessons on preventing labour-related trafficking in the garment and domestic work sectors in South Asia. [Target: 1] / DFID held a South Asia Regional Anti-Trafficking Workshop in Bangkok over 26-28 June 2012 in conjunction with the ILO. This expert group meeting aimed to build a platform for knowledge, programming and coordination to identify and implement the most promising intervention approaches. It shared evidence and lessons on trafficking interventions in the garment and domestic work sectors in South Asia, including findings achieved through the DFID sponsored pilot projects. / The workshop benefitted from excellent attendance with over 60 experts participating, including representatives from international and non-governmental organisations, and government and private donors focussing on trafficking and forced labour. Groups included organisations providing direct services, conducting advocacy, forming coalitions and providing funding, technical and other support for activities to prevent or interrupt human trafficking, specifically programming that included women and girls in forced labour in the garment and domestic work sectors. / Evidence from the final report of the workshop shows that it achieved its objectives, and that the dialogue was “constructive” and helped to establish where DFID could “add value to existing anti-trafficking efforts” and “what works, what’s replicable or scale-able in other sectors or countries”. / In particular, it met its objectives: / To network and build partnerships; / To learn lessons from our pilot programmes – including discussing lessons around “building coalitions, trying more integrated and ‘whole trafficking chain’ approaches”; / To build the evidence – helping to understand “the data and evidence there is on what works and why, and identifying gaps”; and / To help DFID think through the design of its programme – “building and complementing what’s there already, identifying key gaps and specific indicators and outcomes we want to support and help partner countries deliver”. / It exceeded its objectives in a number of areas that were unforeseen: / It fostered new partnerships and collaboration by bringing together key actors in the field of trafficking that were previously highly polarised and hostile towards one another – particularly on approaches to sex trafficking. Participants reflected that “it was the first time this set of actors had all been in the same room at the same time – learning from one another and developing new insights”. This happened because DFID’s approach was to encourage lesson-learning in an open, transparent way, and invited a wide range of stakeholders with experience and expertise on labour trafficking and labour migration – including victims of trafficking, trade unions, policy makers and international agencies. / DFID was praised for modelling good practice in evidence-based programming: it subjected pilot programmes to open and transparent peer review and scrutiny (unheard of previously, according to those present). It also broke new ground by inviting a wide range of actors to help design a theory of change for DFID’s new programme based on lessons and experience of what has failed, and what works. It was clear that most donors did not share their evaluations of anti-trafficking programmes, and continued to design new programmes despite evaluations showing poor results, and demonstrated little attempt to learn lessons. DFID’s focus on building an evidence base is regarded as one of the most valuable contributions it could make to the global knowledge public goods because a rigorous evidence base does not exist. / Output Indicator 2.3: Number of logframes designed that provide a robust measurement and evaluation framework for delivery of DFID’s Asia Regional Human Trafficking Programme. [Target: 1] / As part of work to design the programme for full implementation, a logframe was developed jointly between DFID, LSHTM, and the ILO, to provide a robust framework to support the monitoring and evaluation of DFID’s Asia Regional Human Trafficking Programme. This drew extensively on the theory of change for the project developed with the LSHTM, which in turn considered in full the existing evidence as outlined in the literature reviewed discussed above. The result is a logframe complete, in general, with indicators, baselines, milestones, targets and assumptions. There are some details currently omitted from the logframe which should be completed as soon as possible and before the next review, as described below. / In addition to the monitoring framework set out in the logframe, great consideration has been given to the evaluation of the ARHTP, in consultation with the LSHTM, ILO and DFID. This is likely to include two Impact Evaluations to build the evidence base for what works to prevent labour-trafficking in the garment and domestic sectors of South Asia. It is notable that the considerations are continuing apace at this early stage of the project, in order to inform an appropriate and rigorous Ex-Ante Impact Evaluation design. The inclusion of monitoring and evaluation partners at the early stages of design of a programme is not usual, but is regarded as best practice in evaluation. It ensures that indicators set in the logframe are evaluable and will enable wider conclusions to be drawn for the benefit of others. / Recommendations: / This review concludes that the logframe targets for Output 2 have been achieved and that no adjustments are required. / It is recommended that when possible, and before the next review, the logframe (for Phase 2 of the programme) be updated to include: / Baseline and milestones for output indicators 2.3 and 3.3 / Inputs in HR and financial terms / Risk Ratings for each output. / Impact Weighting: 50% / Revised since last Annual Review? No – this is the first annual review / Risk: Medium / Revised since last Annual Review? No – this is the first annual review

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes. (The logframe has been updated since it was originally published) / The original logframe provided a framework for the full, multi-year anti-trafficking programme (i.e. Phase 2 (Implementation) rather than specifically for the outputs contained within Phase 1 (Design and Inception), which this Annual Review addresses. / The programme design work that has taken place since the outset of this project has resulted in the second phase of the programme taking a different shape and timeframe to what was originally conceived. This is based largely on the improved evidence made available through the piloting and inception phase and is intended to deliver a more effective programme in the long term. For this reason the programme is being logically split into two distinct elements – Phases 1 and 2 – enabling each to have their own detailed and robust logframe. / 1.2 Overall Output Score and Description: A+ (Outputs moderately exceeded expectation) / All key activities fully and successfully achieved their objectives. Some exceeded the objectives. / 1.3 Direct feedback from beneficiaries / All of the pilots engaged with target groups of vulnerable women and children in focus groups, community village meetings, through trade union or migrant worker associations to inform their interventions and to ensure they were relevant to the needs of migrant women. There was positive feedback from beneficiaries who said they felt pleased to be engaged as key stakeholders and not just recipients of project interventions. . For example, beneficiaries of the ILO-led pilot project on domestic work said they “felt empowered after the completion of pilot training activities”. / The pilot projects also engaged in a range of training and capacity building initiatives, which received positive direct feedback from beneficiaries and participants. For example 94% of government and other key stakeholders who participated in the ILO-led training/workshops felt their workplace would benefit from their newly acquired knowledge. And the Nimbus-led work to train police officers in garment sector related trafficking was very well received – to the extent that it secured the commitment to include a bonded labour curriculum in standard police training in Chennai, which will reach over 12,000 new police recruits this year alone. / One of the pilots (delivered by the Global Alliance Against Traffic in Women) specifically focused on voice and participation of the beneficiaries of anti-trafficking programmes. In-depth interviews were carried out with 420 women in 8 locations across India, Bangladesh and Nepal. These provided rich information and analysis that will ensure better design and delivery of the DFID programme so that they meet the needs and priorities of those who experience the direct impacts of trafficking. After participating, women also had a visible increase in confidence, an ability to better articulate and analyse their own experience and a feeling of being part of a group.
1.4 Summary of overall progress / In this first year of operation, the pilot projects and other activities to build the evidence base have achieved significant and impressive results. This is evidenced not just by the accomplishment of the key outputs (including 5 pilot projects and 4 literature reviews) but also by the fact the work reached a significant number of beneficiaries (including some 4,000 vulnerable women and girls and 650 police officers) as well as being able to demonstrate a range of practices and approaches with potential for scale-up.
1.5 Key challenges / While successful in achieving its objectives to date, there have been a number of key challenges across the projects. / Timeframe: Nine months was an extremely short period of time to set up pilots and deliver results. This was especially challenging because pilot partners were expected to work in collaboration with others. Partnership building takes time to establish common objectives, comparative advantages and agree deliverables. Reaching vulnerable women and children that live in remote rural areas takes time, and identifying the right community interlocutors at village level also takes time, trust building and sensitivity. Fortunately, the pilot partners selected had good networks, but there were invariably some delays because of flooding, logistics and other unforeseen circumstances, and some partners requested no-cost extensions to complete their work. / Funding: Each partner had limited funds (grants were no more than £100,000 – some considerably less) yet were expected to demonstrate innovative approaches that had potential for scale-up. / Contracting delays: DFID’s new procurement systems made it challenging for pilot partners to register and receive contracts – which constrained the time they had to deliver results. / DFID staff time: Intensive time was needed by DFID staff leading the programme because this required new ways of working, new partnerships and a high level of ambition. / Technology: The pilot project that aimed to trial innovative methods to tackle trafficking through communication technologies encountered a number of technical issues that limited the reach of its mobile phone, tablet and SMS services – all valuable lessons for future programme design. / Baseline data: Because of a lack of baseline data, some pilots used the opportunity to develop baseline data as one component of their deliverables. Others however used process surveys and evaluations to verify their results, but impact assessment of the pilot programmes was not achievable nor expected in this phase. / In terms of challenges going forward, due to the difficult operating environment and design issues, it will be challenging to ensure baseline data is collected in a rigorous and timely manner in order to inform effective monitoring and evaluation of the project into implementation. This is being actively considered by implementing partners as a corner-stone to the project’s success. / 1.6 Annual Outcome Assessment / The expected Outcome is the design of a new programme to help women and girls protect themselves from being trafficked is based on evidence of effectiveness and impact. / Based on the available evidence, and the positive results from this piloting phase, it is expected that the Outcome will be fully achieved. The logframe and Business Case for the new programme have already been developed – and incorporate evidence and lessons from the work in Phase 1 – and the final programme design is expected to be approved shortly.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / £500,000 was approved for the Inception and Pilot Phase of the programme, and a further, £50,000 was requested to cover additional costs for a multi-stakeholder planning workshop and costs for monitoring and evaluating the inception phase. Total costs for the pilot phase are just under £550,000 with the bulk of those costs being used to finance the five pilot programmes. / 2.2 Key cost drivers / The key cost drivers in this pilot were to ensure that the bulk of the costs were spent on delivering direct benefits for women and girls, rather than on institutional costs or legal and policy work. To achieve this, there was a reliance partners’ existing institutional arrangements and partnerships to ensure an enabling environment for these interventions. This was viable only because it was a short-term pilot, but was delivered at the cost of partners’ own resources, and could not have been sustainable in the long term. / 2.3 Is the project on-track against original timescale: N/A / There have been some delays due to unforeseen circumstances such as those detailed above (contracting delays, localised flooding etc). This meant that some of the projects were not able to follow the original timetable. However all have now been delivered and have been able to contribute to the design of the full anti-trafficking programme, which was the intended purpose of their work.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / As a direct result of the piloting and evidence work carried out as part of this project, there has been a notable improvement in evidence in relation to the specific field of the trafficking of women and children into garment and domestic work in South Asia. This will have benefits and implications for the detailed design of future programmes run by DFID and other partners. / 3.2 Where an evaluation is planned what progress has been made? / N/A. While a robust Measurement and Evaluation programme has been designed it relates to the main implementation phase of this programme, which is yet to begin.

4. Risk
4.1 Output Risk Rating: Medium / The risks for this phase of the project have been defined as medium. Detailed risk assessments will be carried out in later stages as the programme enters its implementation phase. / 4.2 Assessment of the risk level / This could have been assessed as a high risk programme, as there was no evidence to support the approach and interventions, and relied heavily on selecting the right partners and exploiting their good will and enthusiasm to deliver an ambitious ask. However the financial and time cost implications for DFID were limited, and the time and as such, Medium Risk was an appropriate assessment.
Risk of funds not being used as intended / The programme is almost complete, awaiting only final expenditure figures and completion reports for no-cost, additional extension components. All results have been achieved exceeding expectation in some areas, and there is no risk of funds not being used for their intended purpose. / 4.4 Climate and Environment Risk / Environmental degradation and climate change can have an impact on human trafficking. There are indications that growing numbers of migrants today are those who've experienced economic and livelihood shocks as a result of natural disasters or environmental degradation. When poor families are desperate to migrate abroad for jobs quickly, they are more vulnerable and at risk of using traffickers as intermediaries. The UN’s recent report (‘Human Security, Climate Change and Environmentally Induced Migration’) for example identified that 125 million people are likely to migrate in the Indian sub-continent in the coming century due to environmentally induced factors. / The work to tackle human trafficking can therefore have a potentially positive effect on people impacted by climate change. It is also able to help improve the financial literacy of vulnerable families and their working conditions when migrating for jobs. / If migration continues to increase there is likely to be an increased burden on natural resources (energy for transport, impact in urban areas on water, food etc) in the long term. However, since this programme is not promoting migration per se, but merely seeking to ensure it is safe and free of trafficking, this impact risk cannot be attributed to this programme. However, travel undertaken for programme activities contributed to increased carbon emissions. The requirement to travel was considered carefully and minimised wherever possible. Virtual meetings and email communication were used as much as possible.

5. Value for Money
5.1 Performance on VfM measures / This programme represents strong value for money across a number of areas. First, by involving a significant number of other multilateral and NGO partners, this programme uses their stakeholders and existing resources to generate additional value for money. (A result that achieves ‘economies of scale’ and that is greater than the sum of its parts). / DFID was able to exploit the expertise and institutional infrastructure of each of the pilot partners to ensure that only new, innovative and catalytic interventions were funded. Whilst the larger institutions could absorb these costs, it was more challenging for smaller organisations. However each pilot partner was keen to be part of this initiative, and as such, found ways to draw down other resources. / Two of the contributions to Output 2 to build the evidence were cost-free: the GSDRC Helpline service, and a non-funding partnership with Harvard Kennedy School for a six-week graduate internship using a legal expert on trafficking. / The work also dovetailed with wider activities and initiatives, such as DFID’s Responsible and Accountable Garment Sector (RAGS) Challenge Fund and its Retail Business Innovative Facility (RBIF) and together helped to improve working conditions and responsible labour practices, especially for women and girls, in a more efficient manner. / 5.2 Commercial Improvement and Value for Money / The Monitoring and Evaluation Manager was selected through a competitive tendering process managed by Procurement Department, meeting requirements of OJEU. The Board comprised a representative from Procurement Department, Evaluations Department, a DFID country office, the Lead Adviser and Programme Manager in the Asia Regional Team and an external trafficking expert from Newcastle University. The Board agreed the Terms of Reference, and scrutinised two stages of bids over a period of four months before deciding on the London School of Hygiene and Tropical Medicine. The LSHTM is a trusted and credible evaluation partner for DFID on a number of global programmes. / A competitive bidding process was used for the pilot partners. Terms of Reference were shared widely through DFID’s own resource centre networks as well as key trafficking delivery and policy institutions operating globally and in Asia. There was a high level of interest and wide range of bids received from stakeholders that reviewed by a Board of DFID staff from different departments and country offices before selecting the five projects. / Value for Money, track record of results, credibility of delivery partners and individuals were amongst the factors considered, meeting best practice in DFID’s procurement procedures. / Costs for the regional workshop were carefully considered with high attention to value for money and limiting budget expenditure. The decision to hold the workshop in Bangkok was made because many of the Asia regional institutions tackling trafficking are based there. Hotel and flight costs were also far cheaper for people travelling from Bangladesh, India and Nepal, and visa restrictions in some countries also made this a good choice to secure participation from all key stakeholders. A modest hotel and conference centre were selected from a range of options. Relative costs and feasibility were investigated for hosting this event in Bangladesh, India and Nepal – including in DFID offices - but were found to be not as cost-effective or reliable as Bangkok (there were a number of other factors such as political instability and flooding taken into consideration). Where possible, attendees paid for their own flight and accommodation costs; and none of the invited experts were paid a consultancy rate to attend and share their expertise. Other costs such as note-taking and translation that are normal for such an event were not incurred because attendees were asked to volunteer their time for these tasks. / 5.3 Role of project partners / This project has intentionally taken an approach that involves multiple project partners. All partners performed well and met or exceeded their objectives, either in quantity of results achieved and/or quality. Feedback has been that the model of involving a number of partners in delivering anti-trafficking measures has proven highly successful. It enriched available expertise and improved project implementation, and should be built on in future programmes. / 5.4 Does the project still represent Value for Money : Yes / The projects have delivered a wide-ranging and impressive set of activities and results for an extremely modest investment. / For example, for an investment of less than £100,000, Nimbus worked with six other partners to deliver an impressive set of results in just 3 months, and help make a tangible difference to people’s lives. The project reached 3,500 people; trained 30 Community Knowledge Workers to travel to local communities and work with them on the issue of trafficking; trained 650 police officers to improve how they identify and respond to victims of trafficking, and identified 14 instances of trafficking, so far leading to the rescue of 4 victims, re-uniting them with their families. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A. This project does not provide Financial Aid given directly to a partner government so this section on UK conditionality does not apply.

7. Conclusions and actions
The pilot phase of DFID’s Asia Regional Human Trafficking programme has been ambitious but our partners and contractors have delivered a set of impressive results commensurate to the challenge, which have either met or exceeded expectations and that have demonstrated excellent value for money. This has directly helped DFID teams to design a new Human Trafficking programme that draws on the lessons and findings of the pilot project work.

8. Review Process
DFID requested all project partners to complete final reports detailing activity completed against the Terms of Reference, findings and results, financial data and where relevant providing ratings against delivery. / In addition to reviewing the five project completion reports, the Review incorporated an appraisal of following documents: / Theorising and measuring change: Prevention of trafficking of women and girls for domestic and garment work, LSHTM, June 2012 / Review of the literature on interventions to prevent trafficking for labour exploitation, LSHTM, June 2012 / Human Trafficking in South Asia: Piloting new approaches and improving the evidence base - A summary of results from DFID’s five pilot projects, DFID internal document, Autumn 2012 / Asia Regional Trafficking Programme (ARTP): Report from the expert group meeting (26-28 June 2012) to inform DfID’s trafficking prevention programming 2012-2015 (July 2012) / The Business Case for the Asia Regional Anti-Trafficking Programme – Pilot Programme (DFID 2011) / The Logframe for the Asia Regional Anti-Trafficking Programme – Pilot Programme (DFID 2011) / The four Terms of Reference for each of the primary pilot project contractors (2011-12) / The detailed guidance (How to Note) - Reviewing and Scoring Projects (Nov 2011) / Key data from ARIES, including the risk rating / The separate project scoring calculation sheet / The Review also incorporated meetings, discussions and inputs from DFID including the Senior Social Development Adviser for Asia, the Senior Health Adviser for Asia, the Regional Statistics Adviser, Regional Economist and the Programme Manager for the Asia Regional Team. / In line with DFID guidance, the relatively small-scale budget for this programme has dictated an appropriate and proportionate investment of staff administrative and management time. However a rigorous approach was none-the-less taken to assessing this inception phase. / This Review was conducted over December 2012-January 2013 by the Policy and Partnerships Manager within the Asia Regional Team at DFID. The post-holder was new in post and was not involved in the development of the programme and has therefore been able to provide an independent view, based on the documentation and evidence available.