Type of Review: Annual Review

Project Title:Education Sector Support Programme in Nigeria (ESSPIN)

Date started:	July, 2008

Date review undertaken: 2 – 22 October 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet willcalculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meetexpectation C

## Introduction and Context

What support is the UK providing?
A programme of technical assistance and direct project support, with a total value of £83.5m, to help 6 Nigerian State governments (Enugu, Jigawa, Kaduna, Kano, Kwara and Lagos) and key federal institutions get more children into schools of acceptable quality and ensure that they achieve meaningful learning outcomes. / The UK’s investment will demonstrate school improvement approaches that work. It will also improve the capacities of state governments and local communities to actively support school level changes. This will lead to the states utilising their own resources more effectively and scaling up the impact of DFID’s investment.

What are the expected results?
By 2014, an estimated 4 million Nigerian children (at least 47% of them girls) will be receiving better quality basic education in 10,500 schools (both public and non-state) across the 6 states with a real chance of improving their knowledge and skills in basic literacy and numeracy. / With the UK’s support, the states will be using their own financial resources efficiently and effectively to provide good quality education for all categories of children, regardless of different characteristics or circumstances. / The capability of the focus basic education schools to provide improved learning outcomes will have been strengthened. They will have head teachers operating effectively and using school development plans, competent teachers delivering good lessons, supportive School Based Management Committees (SBMCs) mobilising community support, and improved water and sanitation facilities.

What is the context in which UK support is provided?
The 6 States supported by the UK are amongst the most populous in Nigeria and account for 40 million people, a quarter of Nigeria’s total population. Approximately 6 million of these are children of school age. The States have a combined total of 17,000 public primary and junior secondary schools. / The Education for All Global Monitoring Report (September 2012) signals that Nigeria will not achieve its Millennium Development Goals for basic education or gender equity. Nigeria has 10% of the World’s out of school children. 55% of Nigerian girls are out of school. Progress in the northern states is especially weak. / The schools are generally of poor quality and the children who attend them do not learn very much. Teachers are not motivated and lack the skills to perform well. Communities are fragmented and lack the voice to call education service providers to account. School infrastructure is inadequate, decaying or both. The flow of direct funds to schools is poor. Government planning systems are weak and not / based on evidence, and there is very little monitoring of schools. As a result many parents have lost faith in the public school system. / The approach to reform in these 6 ESSPIN states is, therefore, to establish an effective school improvement model with demonstrable results, to secure state government buy-in and to convince the states to utilise their own considerable resources to expand the positive impact of the model to all children. Encouraging state governments to allocate and release budgets for school improvement is a challenging task that brings to light the weak fiscal performance of Nigeria’s public sector. / Several of the 6 partner States – especially Kano and Kaduna - have been directly affected by the security crisis in northern Nigeria. Programme operations have had to be readjusted constantly to ensure that staff and partners continue to be safe and programme targets remain on course. ESSPIN has been most effective in managing security challenges.

## Section A: Detailed Output Scoring

Output 1: Federal government systems that support states' implementation of school improvement strengthened and functioning
Output 1 score and performance description: / A+ / ESSPIN has exercised considerable influence over policy at the federal and state level. / Capacity- building activities at the federal level have been successful and have also made significant impact at state level. / Important improvements have been realised and actual disbursements have increased from the federal level to the states. Over the 3-year period 2009-2011, disbursements of UBE Intervention Funds to ESSPIN’s 6 focus states totalled N12.2 billion, 88% of total allocations. In comparison over the same period, disbursements to the remaining 30 states and the FCT totalled N61.6 billion, 66% of total allocations.
Progress against expected results: / Indicator 1: Disbursement rate of UBE Intervention Funds for basic education (3-year rolling) / ESSPIN states 88%; ( ESSPIN Target was 80% against 67% in 2009 ) non-ESSPIN states 66% / Over the period 2009-2011, the average disbursement for ESSPIN states (88%) exceeds that for non-ESSPIN states (66%). / [All the above data has been drawn from the ESSPIN Annual Report 2011-12; and disbursement figures from the Universal Basic Education Commission ( UBEC)’s quarterly disbursement records 2008-2012, released 13th August 2012, available on the UBEC website:ubeconline.com.] / ESSPIN has helped clarify what federal funding is available to states for basic education, through different funding channels and has also assisted UBEC produce revised guidelines to better enable states to access funding. They have also supported SUBEBS to develop action plans to access teacher development funding. / A public expenditure tracking survey has been initiated in Kaduna, Lagos and Jigawa to ensure cost effective spending. / Indicator 2: National systems have been established for a) Monitoring Levels of Achievement b) Assessment of Teacher Competence c) Annual School Census d) Quality Assurance e) Accreditation of Teacher Education Colleges and f) SBMC implementation / Progress has been slow towards the development of national systems for both Monitoring of Learning Achievement (MLA) and the assessment of teachers. ESSPIN established baselines for both at the beginning of the project and has conducted a composite survey which will, by the end of January 2013, demonstrate precise levels of impact on student learning and teacher capability disaggregated by state. ESSPIN is influencing the development of national systems in slower time. / Review by the IMEP team of all aspects of ESSPIN progress was based on an objective annual self-assessment system which has been used by all 6 states. It is rigorous, evidence based and internationally acceptable. It is based on the standard PEFA methodology used in public financial management circles and has also been used by the State Partnership and Accountability and Responsiveness Programme (SPARC) from whom ESSPIN has adopted it. / Work at the federal and state level has included the development of a quality assurance framework, methodology and instruments including those developed in the National Commission for Colleges of Education (NCCE) which govern and regulate State Colleges of Education and will have an impact on improved pre- service teacher training for basic education. / ESSPIN’s influencing on the federal SBMC strategy has been most effective. UBEC has already replicated the roll out of the ESSPIN SBMC training model in 6 non ESSPIN states and plans to roll this out across the remaining 24 states of Nigeria. / ESSPIN is working with the FME on the development of an Annual School Census (ASC). Important progress has been made in ESSPIN states, but there appears to be a disappointing level of progress in non ESSPIN states. / The Federal Minister’s 4-Year Strategy for Education was launched in 2012. Technical committees have been set up to develop implementation plans for each of the 6 national systems. (ESSPIN supports the committees on MLA, teacher assessment and Quality Assurance.) / Recommendations: ESSPIN to continue engagement with FME/UBEC and SUBEBs to ensure policy direction and release of funding for basic education to the states. / Impact Weighting (%): 9% / Revised since last Annual Review? Y / Risk: Low/Medium/High / Revised since last Annual Review? Y

Output 2: Capability of State and Local Governments for governance and management of basic education at State and LGEA levels strengthened
Output 2 score and performance description: / A / ESSPIN has been a key influence in building state and local government capacity. The AR team reported that 18 out of 24 milestones have been achieved, auguring well for the likelihood of high output milestone achievements across the board up to 2014. However there is qualitative difference in progress and performance across the 6 states, as might be expected. / The ESSPIN exercise on annual self -assessment of this output, mentioned earlier was carried out by the states. It was facilitated by external consultants and based on clear performance criteria and hard evidence. (This was endorsed and used by the Annual Review Team in making their assessments).
Progress against expected results: / Indicator 1: Quality of strategic and operational planning and budgeting, budget execution, performance monitoring and reporting at State and LGEA level / Kwara, Jigawa and Lagos have well established MTSS processes in place. Kano and Kaduna have established MTSS and budget processes but stronger links with LGEA planning and other budgetary processes are needed. Progress in Enugu which started a year later than other states has been slow. / Indicator 2: Quality of service delivery systems and processes at State and LGEA level / Lagos has succeeded with a functional review and achieved reforms in financial and procurement management systems, including the State Procurement Law (April 2012) . Kano has also fast tracked a State Procurement Bill and conducted a Teacher Head Count with ESSPIN’s support. Only Enugu seems to be lagging behind. / Review of progress was based on annual self-assessment exercise involving state and LGEA level stakeholders. This exercise was facilitated by external consultants and based on clear performance criteria and hard evidence. There is variable progress across the states, reflected in their respective ratings, with regards to organisational development systems including functional and process reviews, establishment of HR systems, financial management reforms and procurement practices. / Indicator 3: Quality of school support and quality assurance services at State and LGEA level / There is variable progress across the states, reflected in their respective self assessment ratings, with regards to institutional capacity for and coordination of QA, development of QA policies and legislative frameworks, and linkage of the QA system to planning and budgeting processes. Kwara is ahead of other states in that it has established a Quality Assurance Bureau, trained its staff and developed clear job descriptions. Poor funding of QA linked to slow or inadequate budget releases is a problem across states. / Indicator 4: Level and quality of State/LGEA engagement with local communities on school improvement / Review of progress was based on annual self-assessment exercises involving state and LGEA level stakeholders. Each exercise was facilitated by external consultants and based on clear performance criteria and hard evidence. There is variable progress across the states, reflected in their respective ratings, with regards to operational social mobilisation departments at state and LGEA level, mechanisms for stakeholder participation, engagement with civil society and civil society involvement in the state planning process. / Lagos exceeded its milestones for engaging with local communities, in a context where the majority of children attend low cost private schools. This indicates a commitment to improving the public sector. Kano did not meet its milestone. It is by far the largest state and the target was set ambitiously higher than other states. However, the AR team saw good LGEA support there for different types of schools including public, tsangaya and islamiyya. Enugu also failed to reach its milestone. / Recommendations: / Consolidation of achievements for all four indicators, with particular attention to underperforming states. / Impact Weighting (%): 16% / Revised since last Annual Review? Y / Risk: Low/Medium/High / Revised since last Annual Review? Y

Output 3: Capability of primary schools to provide improved learning outcomes strengthened
Output 3 score and performance description: / A+ / Excellent results have been achieved by ESSPIN regarding the number of focal schools in which the whole integrated school improvement package is rolled out. The majority of milestones have been met or surpassed. The Annual Review team agreed with the ESSPIN Annual Report July 2012 that most ESSPIN schools now benefit in varying degrees from the strategy to implement school development plans and this is the fulcrum of the integrated school improvement strategy. Whilst good quantitative results have been realised and many milestones achieved, there is limited evidence on improved quality at school and classroom levels and improved learning outcomes. The results of the rigorous composite survey carried out in June 2012 will provide evidence of learning improvement and teacher performance. The results will be available by the end of January 2013.
Progress against expected results: / Indicator 1: Number and proportion of public primary and JSS using a school development plan / Primary planned 829; achieved 1,660 / The planned milestone is based on 80% of the total number of Phase 1 schools in all States (except Kwara where only a subset of schools which received school grants is used). The achieved result (primary) is much higher than planned.Both Kwara and Lagos show growth rates substantially above their June milestones. Enugu and Jigawa exceeded their milestones by 30%. / Indicator 2: Number and proportion of head teachers in public and non-State primary and JSS operating effectively / Public Primary ; Planned 1783; achieved 1,712 / The ESSPIN logframe reports 1712 head teachers who are operating effectively against a milestone of 1783, an achievement rate of 96%. / Achievement milestones are reported only when heads have reached an appropriate stage in the reporting cycle. Lagos achieved a milestone of 521 against a target of 80 which appears to inflate the overall aggregate achievement data. However, it is positive in that the Lagos state government provided funding early to increase the number of beneficiary head teachers. In Kano, Jigawa and Enugu, some criteria of head teacher effectiveness are yet to be fully covered in all schools (see criteria in the ESSPIN logframe Handbook). The training cycle was delayed in Kano and Jigawa by slow budget release. Enugu started a year later than the other States and its head teachers are yet to fulfil the criteria for effectiveness. Data collection has taken place in public primary schools only. JSS (Kano and Jigawa) and non-State (Enugu) data will be collected in the next reporting round. / Indicator 3: Number and proportion of teachers in public and non-State primary and JSS who can deliver competent lessons in literacy and numeracy / Public Primary; planned 7126; achieved 7,877 Non-State Primary; planned; 247: achieved 602 / The Annual Review focused predominantly on public primary schools. There appears to have been very little activity at JSS level with only Jigawa and Kano targeting JSS in Phase1 schools, based on decisions by other states to focus only on primary. In Lagos JSS is covered by another donor (World Bank). The planned milestone is based on 70% of all teachers trained in Phase 1 schools in all States. The achieved result is higher than planned. Kwara has a high milestone (4061) since it has targeted all its teachers within its ground breaking literacy and numeracy programme. Kaduna is ahead of its milestone and Enugu, Jigawa and Kaduna have achieved their milestones. While these milestones have been achieved, teachers still require substantial support with literacy and numeracy approaches. Non-state teacher results achieved for these is also higher than planned as there has been a rapid expansion of tsangaya schools based on increased state government support. Teacher competence in the IQTE programme is determined by support teacher observations and assessment of learning outcomes carried out on completion of each learning module. JSS data (public primary in Kano and Jigawa) will be collected in next reporting round. / Indicator 4: Number of learners, especially girls, benefiting from better infrastructure: a) toilets b) clean water c) new or renovated classrooms / Planned and achieved / Toilets - 122,000 children (50,600 girls); Water - 165,000 children (65,500 girls); Classrooms - 14,230 children (1,245 girls) / NB. The reason why the actual numbers correlate so closely to the targets is explained in the log frame handbook. Infrastructure targets were set as the total number of children in schools receiving water and sanitation facilities and for classrooms (40 children multiplied by the total number of classrooms provided). These targets were set as part of log frame finalisation in February 2012. / The milestones are based on total enrolment figures in beneficiary schools, i.e. the total number of children in all schools that have received new water, toilet and classroom facilities directly funded by DFID. The results achieved would be higher if facilities provided with state government funding are included e.g. Lagos would see an additional 35,000 children benefiting. Criteria for attribution are being clarified, however, and state funded facilities will be included in the next reporting round. / Impact Weighting (%): 43% / Revised since last Annual Review? Y / Risk: Low/Medium/High / Revised since last Annual Review? Y

Output 4: Capability of communities and civil society to support learner participation and articulate demand for inclusive, quality basic education services strengthened
Output 4 score and performance description: / A / Significant progress has been realised regarding the establishment of functioning School Based Management Committees (SBMCs) that generate and show ownership of ‘their’ schools. These committees actively liaise with local governments and civil society organisations. This is one of the highlights of the programme. In addition UBEC has made a policy decision, as mentioned earlier, under Output One, to roll out this model across Nigeria and state Ministries have committed to fund and roll out the ESSPIN model for SBMC development. / There appears to be some, progress towards inclusive education policy and practice, particularly relating to the Fulani nomads, the deaf, albinos and other vulnerable children and girls in all groups.
Progress against expected results: / Indicator 1a: Number of public and non-state primary schools with functioning SBMCs / Public ; planned 829 achieved; 962 / The planned milestone is based on 80% of Phase 1 school communities in all States supported to establish SBMCs. The result achieved is 16% higher than planned with regards to the number of fully functioning SBMCs following a cycle of training and mentoring. Phase 1 SBMC development has been at primary level only. Phase 2 roll out will include JSS in Kwara, Kano and Jigawa and some non-state school communities (Mission schools in Enugu and nomadic community schools in Jigawa). / Indicator 1b: Number of communities where SBMCs reflect concerns of women and children / Planned; 749 achieved 716 / Some states have exceeded their targets for women and children’s participation in SBMCs though participation may not include active participation. Kaduna and Enugu failed to reach their targets. In Lagos women are well represented on SBMCs and are used to mobilise mothers around issues like punctuality,“ meals” and children’s health and cleanliness. SBMCs and especially their women members are yet to be effective partners in decision making about the school and its management as a whole . / This is a particularly challenging aspect of SBMC development, especially in northern States. Getting women and men to sit together in training situations, getting male dominated SBMCs to recognise and respect women committees and seriously consider their views in decision making are improved practices. Efforts to increase women’s voice and confidence, through setting up “Safe Spaces” committees is a significant development. It will take time for cultural obstacles and attitudinal barriers to be overcome and for women’s voice and confidence to grow. / Indicator 2: Quality of civil society advocacy and mobilisation for school improvement and marginalised groups at community and LGA level / There is variable progress across the states, reflected in their respective self- assessment ratings. Civil society organisations engaged by ESSPIN in Enugu to support communities and drive advocacy campaigns were comparatively less effective, possibly due to the fact that Enugu came into the programme a year later than the other States and its CSOs have, therefore, had less support. Three States – Jigawa, Lagos and Kwara – did well reflecting the positive assessments by the CSOs of their relationship with State governments in rolling out SBMC development, engagement with local communities, particularly women and children, and their growing capacity to undertake focused advocacy. All states recognise however that the advocacy dimension of their work still needs strengthening. / Indicator 3a: Inclusive education policies at State level / Kaduna was the first state to initiate an inclusive education programme and roll out to other States commenced in 2011/12. There is variable progress across the states in relation to inclusive education. Kaduna has conducted a state wide census of out-of-school children and a report is being finalised. A multi-stakeholder committee on inclusive education has been established and is being coordinated by the SUBEB. Extensive training in inclusive education practices for LGEA desk officers and teachers has taken place. These dimensions have been initiated in Kwara, Enugu and Lagos. Kano and Jigawa were prioritised last for broadening this work stream as they already had specific inclusive education projects directed at girls e.g, the conditional cash transfer pilot in Kano and a girls’ education initiative in Jigawa. / Indicator 3b: Number of inclusive schools (based on pre-defined parameters) / Data not yet available / Previously defined as a qualitative sub-indicator, this sub-indicator is now quantitative and will be reported in the next SSO reporting round. / Indicator 3c: Number of communities supporting inclusive education / Planned 829 achieved 891 / The planned milestone is based on 80% of Phase 1 school communities, whose SBMCs have received training support. The SMO reports showed actuals exceeding the target, indicating that local communities were actively monitoring the situation of out-of-school children and ensuring that those in school remain there. / Recommendations: / Attention should be given to the generation of more reliable data to attribute and validate progress against the qualitative milestones. This will include further support for EMIS in the six States. / Continued attention to roll out of school improvement as approved in the ESSPIN strategic plan including strong engagement with States/SUBEBs on (a) State funding (b) the necessary conditions for sustainability. / More attention to policies for and practices of inclusive education, including girls, out of school children, minority groups and the disadvantaged / Impact Weighting (%): 32% / Revised since last Annual Review? Y / Risk: Low/Medium/High / Revised since last Annual Review? Y

## If the project involves more than 4 Outputs please copy the box above and paste below.

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the log-frame been updated since last review? / Yes. December 2011 and February 2012 / 1.2 Overall Output Score and Description: / A / A As the above analysis and summaries indicate, ESSPIN isa complex programme. Output One political influence at federal and state level- (weighting 9%) and Output 3 school improvement ( weighting 43% ) both achieved A+.(total 52%). The other two outputs have been rated A. Compared with other programmes in Nigeria, ESSPIN’s data base is better than most but needs further strengthening and improvement . / 1.3 Direct feedback from beneficiaries / Both DFID and ESSPIN have questioned elements of the analysis contained within the IMEP Annual Review report, especially around work on Value for Money, their Monitoring and Evaluation Strategy, the extent to which ESSPIN is embedded in state systems and the “depth of evidence provided for the effective training of Head teachers and teachers.
1.4 Summary of Overall Progress / A major achievement has been the establishment of a positive school ‘ethos’ but there is much still to be done towards improving the overall quality of the teaching-and-learning contexts and of learning achievement as ESSPIN is fully aware. / Excellent results have been achieved in relation to the number of focal schools in which the integrated school improvement package is rolled out. In the last year 3,700 focal schools were reached, compared with 2,300 schools the previous year.. Through these schools 1.1 million children have been reached, including 525,000 girls. ESSPIN has supported 1,800 “effective” heads, 8,000 “competent,” teachers and 1,000 “ functioning School-Based Management Committees. / ESSPIN has achieved a significant roll out of focus public schools in focus states; so far reaching 22% of schools in six partner states. It has ambitious targets for 2014 but these will entail only 40% of the total number of public schools in these focus states. If individual state governments commit resources to greater coverage of schools in their states, this target will be significantly exceeded. / There are positive results at Output level. However, the Annual Review team felt they could only make tentative judgements on progress towards Outcome and that ESSPIN had yet to demonstrate progress towards the realisation of its Outcomes. / Nigeria will not achieve its MDG goals. ESSPIN was designed only to contribute to Nigeria’s efforts. Even with the increased focus on service delivery a larger effort over a longer time frame will be required to raise standards across Nigeria to the appropriate level. The advent of Global Partnership money in 2013 should assist progress in five states and help move things forward. The future is largely dependent on the political will to prioritise education through appropriate budgeting and release of funding. / Key challenges / Nigeria has some of the worst educational indicators in the world. ESSPIN’s challenges are vast. The IMEP review team concluded that “The programme is to be congratulated upon its successes and the way it continues to face new challenges, including security issues, in realistic ways together with its partners and stakeholders.“
1.6 Annual Outcome Assessment / As the Review conclusions indicate there an identifiable, overall, positive interim outcomes in terms of improved school ‘ethos’. The consolidated findings of the Composite Survey, which ESSPIN has commissioned as the evidence base, is going to prove critical in establishing the extent to which ESSPIN is making measurable progress towards its perceived outcomes. / Based on the emerging findings of the Composite Survey, ESSPIN expresses confidence that it is making progress in generating the necessary information.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The total approved DFID budget for ESSPIN (2008-2014) is £83.5 million, of which £59.1 million (70%) had been spent by the end of year 4. In year 4, ESSPIN expenditures have come up to speed with a total of £ 20.3 million (in line with the budget for year 4), compared with £ 38.8 for the years 1 to 3 together. / 2.2 Key cost drivers / According to ESSPIN’s own annual and quarterly financial, the project support activities have been the main cost driver in year 4 (48%), followed by overheads (29%), long term technical assistance (13%) and short term technical assistance (11%). / Cost drivers Budget Actual Realisation% / PSA 9,903 9,751 98% / STTA 2,062 2,189 106% / LTTA 2,773 2,536 91% / Overheads 5,537 5,785 104% / Total 20,274 20,261 100% / 2.3 Is the project on-track against original timescale: Y/N / yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The Annual Review team reported an overall weak evidence-base and did not rate ESSPIN’s Monitoring and Evaluation systems though they are established, outlined below and reported in quarterly and annual reporting from ESSPIN. / ESSPIN has worked with states to establish an integrated M and E system which correlates states’ annual reporting requirements with ESSPIN’s programme needs. Based on this integration, both ESSPIN’s annual report and states annual sector reports derive evidence from SSO and SMO reporting systems ( quantitative service delivery results; annual self- assessments- state and federal ( qualitative governance results); and special impact studies implemented in partnership. This approach builds M and E capacity within states, ensures ESSPIN’s logframe does not exist in isolation from states’ own indicators and sets a foundation for long term sustainability. / Whilst ESSPIN is able to demonstrate progress towards the achievement of its Outputs, the review team felt inconclusive about whether ESSPIN is showing progress towards Outcomes and Impact. / The review team has recommended improvement of Monitoring and Evaluation as a key action for ESSPIN and its partners in the period till 2014. / 3.2 Where an evaluation is planned what progress has been made? / ESSPIN’s Theory of Change has been the driver for all its work. / A Composite Survey is almost complete. A further evaluation is planned for 2014. Delivery is currently behind schedule.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / 4.2 Assessment of the risk level / ESSPIN’s risk assessment strategy identifies both security and programmatic risks. It identifies high programmatic risks. These include VfM in infrastructure projects; state support and use of funds including Conditional Cash Transfers. / The review team feels that there are high risks of (a) non availability of State funds; (b) the potential sustainability of the ESSPIN School Improvement model (c) major inherent resistance to the school improvement model from educational stakeholders. It could be that ESSPIN under estimates these.
Risk of funds not being used as intended / There is a particular need in the Nigerian context to operate rigorous fiduciary control and vigilance. / The ESSPIN risk management strategy and its log-frame identify the range of risks and assumptions that militate against the achievement of Outcomes, Outputs and Impact. ESSPIN expresses these in its Risk register with rating according to the probability of occurrence. The only risks listed where the probability is High are; Infrastructure programmes continue to side step sound procurement supervision and practices; VfM in infrastructure projects; conditional cash transfers diverted from legitimate beneficiaries; lack of state government’s recognition of NGOs. / 4.4 Climate and Environment Risk / There are no prominent environmental risks

5. Value for Money
5.1 Performance on VfM measures / DFID has to an extent taken issue with the Annual Review Team’s assessment of ESSPIN’s approach to VfM and has included here more evidence from ESSPIN’s own value for money strategy. The ESSPIN Annual review (July 2012) gave interesting examples of how ESSPIN is not only driving down costs but demonstrating that cost is about results not just inputs. The best example given to date is in paragraph 130 of ESSPIN’s Annual Report. The head teacher and teacher training programmes are intensive and the unit costs are £700 and £140 respectively. However when consideration is given to the fact that teachers may teach 1000 learners each over the next 20 years the cost per learner is measured at approximately one and a half pence per child. Another relevant example ESSPIN quote in their Annual Report is the significant gain over time that the initial investment of £760 in a functioning SBMC will bring. It will be good VfM when SBMCs monitor teacher attendance; provide furniture , learning materials, uniforms and food, organise days for parents to interact with their children’s teachers and see what they are learning, organise rotas for ensuring children travel to and from school safely, negotiate reduction in transport fares and set up welfare committees. All these are seen as SBMC responsibilities. This type of approach is precisely what DFID’s own VfM strategy is encouraging. / 5.2 Commercial Improvement and Value for Money / The Annual Review team did however consider that the new VFM approach was an appropriate response to DFID’s requirements. Firstly, ESSPIN has made good progress since 2011 towards improving the financial reporting structure, which is now clearly linked with the revised (December 2011) logframe. All expenditure data for year 4 have been prepared according to the suggested format and can be traced towards outputs and States. The budget for year 5 also follows the same logic. This allows for a VFM analysis through close examination of the linkages between expenditure, log-frame activities, (sub-) outputs, and outcomes. / 5.3 Role of project partners / ESSPIN is working with six State governments and key departments within them,(these are Enugu, Jigawa, Kaduna, Kano, Kwara, Lagos), as well as with the Federal Ministry of Education and the Universal Basic Education Commission and other parastatals. ESSPIN also works with programmes funded by other development partners, and with a range of other CSOs and NGOs. / 5.4 Does the project still represent Value for Money : Y / The IMEP AR team reported that they experienced difficulty in collecting both input data (money) and even more so in verifying reported results (value). They felt that concrete evidence that ESSPIN is actually providing value for money is limited. / At impact level, it is important to consider Indicator 2b “number of children supported by DFID per annum in primary and lower secondary education” -as this is one of the ultimate objectives of DFID’s country strategy. For this indicator, ESSPIN uses the total enrolment of children in focus public primary and junior secondary schools in focus states, i.e. cumulative total number of focus schools in 2012, 2013 and 2014 multiplied by a pre-determined average number of children per school. In the design of ESSPIN there is an implicit assumption that £30 spent per child is good Value for Money. While the £30 is not the total cost per child educated (viz it should e.g. be corrected for costs not included in this figure- like teacher salaries). The AR considers this amount to be low and indeed good Value for Money, especially when considering that the child will benefit from the skills for life. Assuming sustainability of results after year 6, new cohorts of children will also benefit, which will only further decrease the investment amount per child .At the moment £ 82 has been spent per child in school. Keeping in mind that the relationship between costs and results is not linear, this is well on track against its own benchmark. Future reviews will be able to track whether ESSPIN is achieving economies of scale as the expansion continues over the next two years and the cost per child continues to fall. / 5.5 If not, what action will you take? / The review concluded that there is room for more flexibility in how resources are deployed across States based on demonstrable need. School improvement programmes and governance reform - initially driven by a uniform TA package – should increasingly be driven by ownership at the State level. ESSPIN is being responsive and reactive to political developments to maximize its leverage and replication strategy and needs to continue to do so. The MTR already made this observation. ESSPIN together with DFID needs to take a strategic decision whether or not to intensify the operations in the weaker performing States to bring results to an acceptable level or to focus more on the best performing States in order to maximize results. The latter strategy naturally has a higher return in terms of Value for Money, although it is recognized that other considerations should be taken into the account -for instance the equity objective as well as the potential for weaker States to improve their performances over time. / Importantly, the ESSPIN contact was signed before the VfM concept was on DFID’s agenda and the required mid-programme shift is a major challenge. Future programmes would require substantially clearer guidelines on what kind of reporting for Value for Money is expected from the start in order to avoid the substantial difficulties that ESSPIN has had to face since the programme was in the middle of implementation.

6. Conditionality
6.1 Update on specific conditions / There are no explicit conditionalities applied to ESSPIN’s work at Federal and State level.

7. Conclusions and actions
Conclusions / The IMEP AR review identified progress in the shift from governance to service delivery. / It signalled progress towards the adoption of school improvement, but cautions against expectation of quick results. / It questioned whether the ESSPIN model would be sustainable and whether it will be adapted or adopted up to 2014 and beyond. / It challenged as to how well grounded and embedded ESSPIN is or will be within the States’ education systems. / It signalled the substantial development of SBMCs and the need to deepen approaches to the improvement of the teaching-and-learning contexts. / It identified slow progress towards inclusivity and the need to deepen this work. / It identifies the need to make more progress on Monitoring and Evaluation / It identified the need for more work on VfM but that there are positive signals about the VfM work done to date. / It argued the need for consolidation rather than new directions for ESSPIN up to 2014, endorsing the November 2011 strategy. / As ESSPIN moves forwards to 2014 and beyond, there are important questions of balance and priorities for ESSPIN - between governance and service delivery, though these were largely decided in the revised strategy approved by DFID in November 2011 between different Outputs (even between different States); between different interest groups e.g. SUBEBs and LGEAs; between SBMCs and teachers. Getting that balance and priorities right will be the key to ESSPIN’s sustainability. / Recommendations: / ESSPIN produces its Draft Action Plan for its sustainability strategy up to 2014 taking into account questions of sustainability 2014 and beyond. / ESSPIN intensifies its planned SIP roll-out strategy, 2012 – 2014. / DFID seeks explicit lessons learned from similar interventions. / ESSPIN focuses explicit priority attention on the challenges of school quality – particularly teacher performance and pupil attainments. / ESSPIN strengthens its approaches towards inclusivity. / ESSPIN intensifies strengthening of the data management and M&E systems of itself and its stakeholders, especially at State level. / DFID provides ESSPIN (and partners) clear VfM guidelines in education; and clear guidelines for the use of ARIES. / ESSPIN focusses as a priority on the consolidation of its post-MTR strategy.

8. Review Process
ESSPIN was reviewed by an independent review team, managed by IMEP, from 2nd – 22nd October 2012