##### Type of Review: Project Completion Review

Project Title: Kenya Harmonised HIV and AIDS programme

Date started: 2007 Date review undertaken: August 2012
Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation / List of Abbreviations / AIDS Acquired Immune Deficiency Syndrome / AMREF African Medical and Research Foundation / ART Anti-retroviral Treatment / ARV Anti-retroviral drug / BCC Behaviour Change Communication / CACC CountyAIDS Coordinating Council / CER Cost-effectiveness Ratio / CSOs Civil Society Organisation / CSW Commercial Sex Worker / DFID Department for International Development / e-MTCT Elimination of Mother-to-Child Transmission / FAO (UN) Food and Agricultural Organisation / FSW Female Sex Workers / GIPA Greater involvement of people living with HIV/AIDS / GoK Government of Kenya / HBC Home-based care / HCBC Home and Community Based Care / HIV Human Immunodeficiency Virus / HTC HIV Testing and Counselling / IDUs Injecting Drug Users / ICC Inter-agency Coordination Committee / JAPR Joint HIV and AIDS Programme Review / KABP Knowledge, Attitudes, Behaviour, Practice / KDHS Kenya Demographic and Health Survey / KNASP Kenya National AIDS Strategic Plan / M&E Monitoring and Evaluation / MARPS Most-at-Risk Populations / MC Male circumcision / MoMS Ministries of Medical Services / MoPHS Ministry of Public Health and Sanitation / MSM Men who have sex with men / NACC National AIDS Control Council / NASCOP National AIDS STI Control Programme / OPR Output to Purpose Review / OVC Orphans and Vulnerable Children / PCR Project Completion Report / PEPFAR President’s Emergency Plan for AIDS Relief / PLHIV People Living with HIV / PLWHA People Living with HIV/AIDS / PMTCT Prevention of Mother-to-Child Transmission / PSO Private Sector Organisation / PWP Prevention with Positives / Sida Swedish International Development Agency / SW Sex Worker / STI Sexually Transmitted Infection / TA Technical Assistance / TasP Treatment as Prevention / TOR Terms of Reference / TOT Training of Trainers / TOWA Total War against AIDS / TWG Technical Working Group / UN United Nations / UNAIDS Joint United Nations Program on AIDS / UNCT United Nations Country Team / UNDP United Nations Development Program / UNESCO United Nations Education, Social and Cultural Organisation / UNFPA United Nations Fund for Population and Development / UNICEF United Nations Children’s Fund / UNJP United Nations Joint Programme / UNODC United Nations Office for Drug Control / USAID United States Agency for International Development / VCT Voluntary Counselling and Testing / VfM Value for money / WB World Bank / WHO World Health Organisation

## Introduction and Context
What support did the UK provide?
The DFID Harmonised HIV and AIDS Programme 2007 - 2012 was specifically designed to support existing Kenyan structures and institutions to engage and function more effectively. The original programme identified three main channels for support as follows: / Direct funding via the National AIDS Control Council (NACC) to the HIV and AIDS Total War on AIDS in Kenya (TOWA) ‘TOWA Project’, a discrete, World Bank-funded project that falls under Kenya’s broader ‘Total War on AIDS’. The plan was to provide joint funding with the World Bank in a pooled funding arrangement. / Supporting technical assistance to the implementation of the Kenya National HIVand AIDS Strategic Plan (KNASP) through the United Nations Joint Program (UNJP). / Supporting strengthened integration and coordination between civil society and government through Maanisha - a SIDA-funded community mobilisation project managed by the African Medical Research Foundation (AMREF). / After the programme was designed, civil unrest following the 2008 elections led to withholding of approval for DFID funding for the TOWA project. The revised project mainly supported two components: the UN Joint Team and the AMREF Maanisha Project. Support for the World Bank TOWA project consisted only of the secondment of a Senior Health Specialist to the Nairobi World Bank office. / Total financial support: / UN Joint Program – £ 10 million (US$ 15 million). / Maanisha Programme - DFID £ 10 million (and SIDA US$ 10.8 million). / World Bank secondee - £385,512.

What were the expected results?
The Project Goal as in the log frame was to “reduce the spread of HIV, improve the quality of life of those infected and affected and mitigate the socio-economic impact of the epidemic in Kenya”. The indicators for this were based on data found in the Kenya Aids Indicator Survey (KAIS) 2007 report that showed evidence of anincreased national HIV prevalence, positive changes in behaviour and increased numbers of people accessing treatment. / Percentage of adults 15-64 infected by HIV (disaggregated by sex, age group) / Baseline - 15-49: 7.45% 15-64: 7.1% Target (2012) - 15-49: 7% 15-64: 7% / Percentage of adults aged 15-49 years who had sexual intercourse with more than one partner in the last 12 months / Baseline - M:11.9%, F:1.7% Target (2012) - M: 5% F: 1% / Percentage of adults and children with advanced HIV infection receiving Antiretroviral(ARVs) / Baseline – 47% Target (2012) – 67% / The Project Purpose as in the log frame was: to support the effective implementation of the KNASP through harmonised approaches. The indicators for this included two process indicators (percentage of funded Civil Society Organisation (CSOs) meeting set targets, and percentage of KNASP III targets achieved) and a behavioural indicator - percentage of adults aged 15-49 years who had more than one sexual partner in the past 12 months who report the use of a condom during their last intercourse. / Percentage of funded CSOs meeting set targets / Baseline 80% Target (2012) 85% / Percentage of KNASP III targets achieved / Baseline – N/A Target (2012) 70% / Percentage of adults aged 15-49 years who had more than one sexual partner in the past 12 months who report the use of a condom during their last intercourse / Baseline - M: 42.5% F: 25.7% Target (2012) – M: 50% F: 35%

What was the context in which UK support was provided?
DFID began supporting HIV and AIDS in Kenya in 1997, mainly through the HIV and AIDS Prevention and Care (HAPAC) programme which ended in 2008. At its end, it was noted that there were multiple partners engaged in the response to HIV and AIDS in Kenya including NACC (in the office of the President) and National Aids and STI Control Programme (NASCOP) (in the Kenyan Ministry of Health) as well as a large number of civil society organisations. The HIV and AIDS programme was largely funded by donors (98%) and mainly off budget (80%) of which US Government contribution was the largest by a considerable margin. This multiplicity of partners had led to a variety of different programmes, outcomes, funding channels and processes at all levels. As a relatively small donor (compared with US Government, the World Bank and the Global Fund), the decision was therefore made not to continue a separate vertical project, but to exploit DFID’s comparative advantage in terms of responsiveness and flexibility by supporting greater harmonisation of approaches to deliver the results of the Kenya National AIDS Strategic Plan (KNASP). / A Scoping Mission in 2006 recommended that DFID “engage with selected partners in pooling arrangements for discrete purposes, but with the explicit intention.....of evolving towards a multi-sector HIV/AIDS Sector-wide Approach (SWAp) in which all partners engage with the entire KNASP”. While the SWAp was being organised, the report advised that DFID should “conclude fund pooling agreements with selected partners for a number of high priority discrete purposes”. / The scoping report further suggested that DFID might consider interventions where DFID might be prepared to act more vigorously or focus on included highly vulnerable but stigmatised groups, such as sex workers (SWs), injection drug users (IDUs), men-who-have-sex-with-men (MSMs) and prisoners. As well, areas which were inadequately covered and which could be supported included counselling for discordant couples, prevention of mother-to-child transmission (PMTCT), home-based care, and support for orphans and vulnerable children might be considered. The report also suggested that in any project that was developed, NACC should take the lead both in the harmonisation process as well as in the allocation of innovation grants. / At about the same time as the project was being developed, two important studies were being conducted in Kenya that informed the DFID Project and subsequently had an impact on Kenya HIV/AIDS policy. The Kenya AIDS Indicator Survey (KAIS) in 2007 was a population-based survey that focussed on HIV issues but also compared itself to the Demographic and Health Survey of 2003. Whereas the 2003 Kenya Demographic and Health Survey (KDHS) estimated a prevalence of 6.7 percent among 15-49 year olds, for the same age group, KAIS estimates that 7.8% were infected. Much debate ensued as to whether this indicated a rising prevalence and whether the difference between the two values was significant. Whatever the answer, the KAIS demonstrated that at the very least, the prevalence in Kenya was not decreasing. / The KAIS also reported that as in the 2003 KDHS, more women than men were infected (prevalences of 8.7% and 5.6% respectively) and that the prevalence in both sexes were higher than 2003. The heterogeneity of the epidemic was demonstrated by comparing the prevalence in Nyanza (15.3%, more than double the national prevalence estimate) with Nairobi (9.0%), Coast (7.9 %), Rift Valley (7.0 %) and so on down to North Eastern province with an adult HIV prevalence of only 1%. Together, Nyanza and Rift Valley were home to half of all HIV-infected adults. The KAIS also surveyed women age 50-64 and men age 55-64 who had not been included in past HIV serosurveys and who had previously been considered low risk. Prevalence among Kenyans age 50 and older was greater than among the youngest Kenyans; which may reflect both cumulative lifetime exposure to HIV as well as ongoing transmission. / In 2008 the Kenya Modes of Transmission Study (MOT) expanded on the findings of the KAIS, and modelled the transmission patterns of the epidemic based on available data. While the study confirmed that about 40% of the transmission occurred in stable heterosexual couples, and another 20% occurred as a result of casual heterosexual encounters, about one-third of all transmission occurred in so-called most-at-risk populations (MARPs): sex workers and their clients (14%), men-who-have-sex-with-men (MSMs) and in prisons (15%), and in injection drug users (IDUs) (4%). The findings of the KAIS and MOT studies led directly to the revisions of the Kenya National Strategic Plan (KNASP) to include components addressing HIV prevention and care in MARPs populations, as well as recognising the challenge of addressing HIV issues in stable HIV discordant couples. / The KAIS also informed the development of the DFID Harmonised HIV Project. The goal of the project: to reduce the spread of HIV, improve the quality of life of those infected and affected and mitigate the socio-economic impact of the epidemic in Kenya, and it was to be measured through indicators based on the findings of the KAIS 2007.

## Section A: Detailed Output Scoring

Output 1: To maintain the performance of the NACC in the implementation of KNASP
Output 1: final score and performance description: A – met expectation / This output is measured by two indicators of which one moderately exceeded expectation and one moderately did not meet expectation. Averaging these scores, since both indicators were weighted the same, we judge that overall the output met expectations. This view is backed up by further positive evidence of NACC work to implement the KNASP, which was not reflected in the log frame (e.g. on monitoring and evaluation). / Indicator 1.1: Stakeholder satisfaction with NACC as shown in the annual satisfaction survey / Baseline 58.5% 2011 Target: 65% Achieved: 78% (measured in 2010). Score A+ / Indicator 1.2: Financial management rating / Baseline – Moderately satisfactory (June 2009 – TOWA review) 2011 target: Very good Achieved: Good- Score B / (Assessment based on annual review reports 2010 and 2011 and information from stakeholders on achievements in the past year). / (In the original log frame, as well as the revision in 2010, a third indicator under Output 1 was the “NACC composite score on the annual independent performance evaluation” – this was actually a measure of the TOWA project, and as the TOWA component never came into being, this indicator was subsequently dropped by the time of the 2011 review). / Support has been provided to NACC in the form of technical support via the UN Joint Programme and the Maanisha programme. The UN joint programme has provided support to NACC through a number of agencies and included generation of strategic information, support to the national Monitoring and Evaluation (M&E) coordination component, and strengthening HIV leadership and governance. NACC’s achievements include developing and launching the national monitoring and evaluation framework and greater standardisation of monitoring and evaluation tools across sectors. The first national Biennial Research Conference was held in May 2011. NACC also led the 2011 Joint AIDS Programme Review, the mid-term review of KNASP III.
Final results: / Sustained, high quality technical assistance to NACC, NASCOP and other key partners facilitated; / National AIDS Spending Assessment (NASA) Report 2009 done and Phase II planned; / Review of KNASP II and development of KNASP III; / Operational Research and Conference supported. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2: Effective, evidence based, nationally led, multi-sectoral programming for KNASP with coherent & consolidated UN support
Output 2: final score and performance description: A - overall met expectation. / This output is comprised of 4 indicators of which only 3 can be scored, with scores of B, A++ and B respectively. Qualitative evidence suggests that the timing of DFID’s support was significant regarding UN integration in the sector and thus we judge that on balance this output scored A.There is good evidence that there has been increased harmonisation within the UN system as a result of the formation of the UN Joint Team with support from this project. There is harmonised planning at the UN level. There is also evidence of increased harmonisation at the national level in the communication and planning between NACC and NASCOP. / Indicator 2.1: UN Resources on HIV fund-raised and allocated in common throughout the UN Joint Programme on HIV and AIDS / Baseline 28% (in original logframe) 2012 Target: 50% Achieved: $21million. Cannot be scored / It is unclear what the baseline and target percentages refer to as they have not been reported on in the past two reviews. This is an example of the shifting log frame during the course of the project. / Though a relatively small part of the overall UN Joint Programme, the timing of DFID support from 2008 specifically to support joint programming is considered to have been a significant factor in facilitating the process of UN integration. During 2010, DFID funding supported 10 agencies, whose reliance on DFID resources for HIV activities varied from 1.7% (UNODC) to 100% (FAO). / Indicator 2.2: % key results achieved of the Rolling Annual Work plan of the Joint UN Team on AIDS / Baseline 2009 – 80% 2012 Target 95% Achieved: around 85% implementation rate against planned outputs, based on UN reports and comments from stakeholders. Scored B. / Indicator 2.3: % HIV positive people who received antiretroviral drugs to reduce risk of Mother To Child Transmission(MTCT) / Baseline – 58.2% 2012 Target: 80% Achieved: 78%, based on NASCOP reports. Scored B(did not meet the set target). / Indicator 2.4: Number of individuals who received testing and counselling and received their results / Baseline - 2.8million 2012 Target – 4.2 million Achieved: 6.3 million. Score A++ / (NB. The above results from the 2011 Annual review, are not quite the same as those reported in the latest Kenya UNGASS Report). / The UN-Kenya Joint Team has developed a coherent joint programme with clearly defined division of labour between agencies. A new Results Matrix and work plan for the UN-Kenya Joint Programme of Support on AIDS 2011-2013 were developed, which are directly linked to the KNASP III. DFID support from 2008 to support joint programming is considered to have been a significant factor in facilitating the process of UN integration. / A fifth indicator in the original log frame was “the development of national strategies on the prevention of HIV in most-at-risk populations”. The programme had not defined the target for this indicator; however this was partially accomplished through the inclusion of MARPs targets in the revised KNASP. Specific strategies for groups such as sex workers, MSMs, and IDUs have been drafted in the past year and are in the process of final revisions.
Final results: / A number of new initiatives and policies were developed, partly as a result of increased harmonisation of the UN program and more effective support to NACC and NASCOP: / HIV prevention coordination and acceleration improved; / National structures and capacity to manage and coordinate effective Behaviour Change Communication(BCC) programmes in place; / National comprehensive programme on prevention of mother-to-child transmission (PMTCT) in place and supported by all stakeholders, and with links to paediatric AIDS treatment; / Technical support to e-MTCT and KNASP carried out; / Prevention among most-at-risk groups (IDUs, sex workers, truckers, prisoners, MSM) advocated and scaled up as part of the national response; / Male circumcision policy, strategy and surgical manual developed and launched; / A total of 6,000 MARPs targeted for and received Home Based Testing and Counselling (HTC) (in the Maanisha Programme only); / Policy reviewed on HIV prevention and care for IDUs; / National Condom Strategy revised and Action Plan developed; / Antiretroviral Therapy (ART) decentralisation policy prepared and launched; / National HIV Drug Resistance plan developed and piloted; / Forecasting and monitoring of Antiretroviral (ARV) stocks in place; / HIV Impact study on Governance, Justice, Law and Order, and Security sectors conducted; / HIV Impact Analysis of the Education Sector. / Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Improved institutional & resource capacity & increased capability of civil society organisations engaged in HIV & AIDS contributing to the KNASP
Output 3: final score and performance description: A+ - overall moderately exceeded expectation / This output is assessed by 3 indicators of which one scored A+ and the other two A++. Beyond the summary indicators, a long list of results are evident with regard to this output. Overall we judge that the output scored A +. / Indicator 3.1: Percentage of Civil Society organisations scoring >2 on AMREF organization scan tool / Baseline 60% 2012 Target – 70% Achieved: 99%. Score A++ / Based on Maanisha reports and reports from stakeholders and beneficiaries / Indicator 3.2: Percentage of CSOs reporting to CACCs according to COBPAR system / Baseline 60% 2012 Target: 80% Achieved 91%. Score A++ / Based on Maanisha reports and reports from stakeholders / Indicator 3.3: % of CSOs/PSOs using finances as per approved work plans and budgets / Baseline 65% 2012 Target: 85% Achieved 93% (measured in 2011). Score A+ / Based on Maanisha reports, reports from stakeholders, and the Maanisha Evaluation Report. / The main activity under Output 3 has been support to the Maanisha Project. Maanisha is a community focused initiative to control HIV and AIDS in Kenya, implemented by AMREF in partnership with GoK structures, Civil Society Organisations (CSOs) and Private Sector Organisations (PSOs). / The project has five results areas that relate to: / capacity building of CSOs and PSOs; / strengthening the coordination environment and mechanisms; / promotion of safer sexual behaviour; / enhancing the quality of care for vulnerable population groups; and / Influencing policy and practice. / The most recent annual report demonstrates activities undertaken under each of these results areas: / Strengthening Facilitation, Harmonisation and Coordination / A total of 91% of CSOs reported to Constituency Aids Control Committee(CACCs) using the Community Organisation Programme Based Report(COBPAR) tool; / A total of 111 CSOs/PSOs participated in implementation of community strategy; / A total of 81 CSOs/PSOs participated in AOP 7 process and their budgets and plans incorporated; / Provided quality assurance to NACC TOWA capacity building project, by supporting 9 Regional Facilitating Agencies (RFAs) to develop and execute implementation plans. As a result, 36 RFA staff, 9 NACC field officers, 210 CACC Coordinators and 978 TOWA funded and potential CSOs were trained on Organisational Development and Systems Strengthening(ODSS) using a cascade approach; / Key coordination gaps were identified and addressed in 7 districts using the Health System Linkages and Coordination Strengthening Framework, resulting in improved dialogue and trust among players in the health system; / Facilitated 8 consultative meetings with DHMTs on supervision of CSOs/PSOs resulting in direct support supervision from DHMTs to 233 CSOs/PSOs; / Supported 81 commemoration events at the district, provincial and national levels including World AIDS Day, World TB day and Day of the African child. / Promotion of safer sexual behaviour and practices among at risk and vulnerable groups / A total of 97 CSOs targeting MARPs reached 83,155 MARPs with HIV risk reduction and prevention messages, HTC and supplied with condoms; / A total of 176 CSOs were supported to conduct community prevention with positives (PWP) and reached 287,349 PLHIV and community members; / Supported 276 CSOs to address human rights issues and 283 cases successfully concluded. / Improving Quality of Life for PLHIV and OVC / Supported 83 CSOs to train 6,148 Home and Community Based Care(HCBC) caregivers who reached out to 21,124 People Living with HIV(PLHIV); / A total of 241 CSOs were supported to establish formal linkages with health facilities resulting in 23,864 PLHIV referrals; / Trained 2,319 ART adherence supporters who in turn, supported 15,920 PLHIV to adhere to their ART regimens; / Total of 26,465 PLHIV received nutritional education and counseling, while 9,221 PLHIV were equipped with knowledge and skills on modern farming methods and farm inputs; / Conducted 3 Trainer of Trainees(ToT) trainings on OVC care and support - 92 ToTs including 5 MoPHS officers; / A total of 65,619 Orphans and Vulnerable Children (OVC) received primary support; 1,112 started on ART and 4,048 supported to adhere to ART. / Influencing Policy and Practice in HIV and AIDS programming / A total of 2,500 and 3,500 copies of the BCC, and ODSS toolkits printed and distributed to GoK partners, CSOs, NGOs and donors; / Conducted the second annual knowledge dissemination workshop where 52 best practices that had been documented were shared for replication; / Two papers published - “Making aid effective at the community level: The AMREF experience.” and “Addressing HIV and Gender from the Ground up”; / Conducted a rapid assessment survey and documented a report on how the programme has enhanced the community voices to demand for better health services from the duty bearers.
Final results: / The Maanisha project is praised as a great success by all parties that the end of project evaluation team met with, and available documentation corroborates this. More than 700 CSOs have been supported, and their capacity to plan programmes and budgets, account for their resources, report to international standards and submit to audits has been improved. A number of CSOs have been able to secure additional funding as a result of the training they received under Maanisha. / The Maanisha Project Evaluation Report concluded that “The Maanisha programme accomplished its purpose as CSOs were capacity-built and 76% are now able to raise resources from other sources and 69% are being supervised by District Technical Committee (DTC) and CACC, ensuring their sustainability. Beneficiaries were empowered and given voices, particularly women who are now participating in various forums and meetings including those organized by government. Lives of those infected and affected by HIV have improved tremendously through provision of services like HCBC and support to OVC.” / In terms of impact, the sentinel surveillance data of 2006-2010 [1] indicates that HIV prevalence decreased in the three provinces that Maanisha was implemented in between 2006 and 2010 - Western (6.2% vs. 5.0%), Eastern (5.6% vs. 4.0%), Rift Valley (5.2% vs. 4.7%). However, in Nyanza, HIV prevalence increased from 11.4% in 2006 to 15.4 % in 2010. The report also indicated a general decrease in the prevalence of HIV among the young age groups. Specifically, there was a decrease in the trend of HIV prevalence among women aged 15-24 (5.7%vs. 5.6%) and the age group 25-29 years (5.7% vs.4.6%). The decline in HIV prevalence among the young age groups and in the general population in Eastern, Rift Valley and Western provinces could denote a success in prevention interventions put in place by various programmes, including Maanisha. For Nyanza, it may be necessary to wait for the results of the KAIS to be done in 2013 to make a conclusion. / Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[1] ANC HIV Sentinel Surveillance Report-2010 , MOPHS & MoMS.

Output 4: Harmonised & aligned funding arrangements in support of the KNASP
Output 4: final score and performance description: B – Moderately did not meet expectation / This output had two indicators, which were scored A+ and C respectively, one indicator exceeded expectation and the other moderately did not meet expectation. A summary score of B is graded for this indicator because indicator 4.2 was weighted higher than indicator 4.1. / Indicator 4.1: Number of partners included in the NACC-led programming for the implementation of the KNASP / Baseline – 0 2012 Target: 3 Achieved: 6 (2012). Score A+ / Indicator 4.2: Number of donors providing on-budget funding through NACC coordination / Baseline – 1 Target - 3 Achieved: 1(DFID only). Score C / Based on UNAIDS reports and feedback from stakeholders. / Despite the failure of supporting the World Bank TOWA, DFID has been providing in-house technical support on HIV to the World Bank TOWA programme through the secondment of a Senior Health Specialist. Progress has been made towards greater donor coordination and harmonisation, including the establishment of regular monthly Development Partners Meetings for HIV and AIDS. Up to nine agencies attend the meeting, representing a core group of five donors. Following the 2011 Annual review recommendation NACC representation in this meetinghas significantly improved. / There has been relatively little progress on providing on-budget funding through NACC coordination, largely for reasons outside the programme’s control. Political instability following the 2008 elections, combined with a series of high-level governance and transparency issues in Kenya undermined the primary assumptions upon which this component was designed and contributed to the indefinite postponement of donor plans to fund vertical HIV and AIDS programmes through government systems.
Final results: / The establishment and support of the single UN Joint Programme was, in itself, a key objective of the Harmonised programme. This has become a model for other joint programming in the UN. Progress has been made towards greater harmonisation and alignment among donors. The UN Joint Programme is becoming increasingly focused on delivering KNASP results and donors have begun sharing information more routinely through regular monthly Development Partner Meetings. Collaboration and joint planning between the World Bank and DFID has remained strong over the years. / The usefulness of the UNJP on HIV and AIDS as a model for other joint programming was noted by several respondents. It was noted during the 2010 annual review that UNJT and cluster had developed a strong working relationship as individuals and representatives of their individual agencies. There was good evidence of collaboration, joint-reporting and joint-decision making. Information flows across clusters and agencies and flows up to UNCT. It has allowed for greater coherence in supporting the national response and in turn allowed for greater efficiencies within the UN. / In summary, it was felt that while a great deal of harmonisation had been accomplished, there was still room for improvement. It was felt that while coordinated planning was happening at the national level, it had not yet filtered down to the provincial and district level. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the log frame been changed since the last review? No / The log frame has not changed since the last annual review in 2011. However, it was recognised after project activities were well underway that the indicators of the original log frame did not adequately capture the activities, results and achievements that were taking place. The log frame was changed at least twice during the course of the project, most significantly after the 2010 review, with minor changes being made while the 2011 review was in progress. Most respondents, both in DFID and the UN Joint Program, still found the log frame (as revised) inadequate to adequately capture project activities and achievements, but in the last annual review in 2011 it was decided that it was not worthwhile revising the log frame at such a late date in the project. / 1.2 Final Output score and description: A – generally met expectation / As can be seen, most of the output indicators listed in the log frame were achieved or exceeded by 2011. There is however a question, as to whether these indicators are an accurate and useful measure of what the project was seeking to achieve. In the case of the support to the UN Joint Program, the output indicators measure some components of an improved response to HIV, but they do not illustrate the level of collaboration and harmonisation that has been achieved in the UN agencies, nor the working relationship that has been established with NACC and NASCOP. In the case of Maanisha, the indicators demonstrate improved capacity in the CSO administration to report and account, but they do not describe the on-the-ground activities that the CSOs are executing (or not) as a result of their increased capacities.
Direct feedback from beneficiaries / No attempt was made to get feedback from the “ultimate” beneficiaries of such a program – ordinary Kenyans who were either at risk of contracting HIV or already living with the virus. However, given that the project was working at the donor/government policy level, it is unlikely that the average Kenyan would have been qualified to contribute many insights into the workings of the UN Joint Program or the Maanisha Project. / There are two categories of beneficiaries in this project – those involved in the UN Joint Team support component and those involved in the Maanisha support. Meetings were held with representatives of both groups, and in general feedback was positive from all who were interviewed. / Beneficiaries in the first group would include stakeholders who would be the participants or recipients of the activities of the UN Joint Program or who sit on the national technical advisory bodies or working groups. Representatives from the various UN agencies, NACC, NASCOP as well as civil society stakeholders all confirmed that the UN Joint Team is working more effectively than it did some years ago, that there is a spirit of collaboration between the donors, and that the harmonised approach is bearing some fruit. In fact, representatives of organisations representing people living with HIV/AIDS as well as MARPS umbrella organisations, such as ISHTAR, noted that they are now part of the decision-making processes at the technical working group level, and that they have access to higher officials in NACC and NASCOPsomething they did not previously have. / Beneficiaries from the second group would include representatives from the various CBOs supported through the Maanisha program. These organisations have generally benefited from their Maanisha support, having improved their accountability and administrative mechanisms to the point where they have been capable of securing higher-level funding from the Global Fund and other sources. Feedback from government members of the Maanisha Advisory Board confirmed that the project has had a positive effect at the Community Based Organisation (CBO) level.
Overall Outcome score and description: A – met expectations / Outcome indicators (as in the log frame) / There were 3 outcome indicators for this programme, which were scored as A+ and B, the second indicator was not scored. Overall the programme met expectation and was scored A. / Percentage of funded CSOs meeting set targets / Baseline 80% Target (2012) 85% Achieved 90%. Score A+ / Based on Maanisha reports / Percentage of KNASP III targets achieved / Baseline – N/A Target (2012) 70%. Not scored / Hard to gauge because of the revisions of the KNASP / Percentage of adults aged 15-49 years who had more than one sexual partner in the past 12 months who report the use of a condom during their last intercourse / Baseline - M: 42.5% F: 25.7% Target (2012) – M: 50% F: 35% Achieved – M – 37% F – 31% (based on data in KDHS 2010).Score B / It is unclear where the baseline figures in the log frame were derived. The data given here is the most recent available – from the Kenya Progress report 2012, which quotes data from the 2010 KDHS. / The Project Purpose as in the log frame was: to support the effective implementation of the KNASP through harmonised approaches. There is good evidence that there has been increased harmonisation at several levels: within the UN system as a result of the formation of the UN Joint Team. There is harmonised planning at the UN level, and the UN is supposedly “speaking with one voice” in their dealings with NACC and NASCOP.There is also evidence of increased harmonisation at the national level in the communication and planning between NACC and NASCOP. The fact that over the course of the project all parties agreed to revise the KNASP II to KNASP III, and that the KNASP III will soon undergo a further revision is evidence of increased collaboration and harmonisation between the various agencies and stakeholder groups. The fact that 76% of the CSOs supported by Maanisha are now self-sufficient is evidence of a further positive outcome from the DFID support to AMREF. / 1.5 Impact and Sustainability / The impact indicators (at the goal level) in the log frame included a reduced national HIV prevalence, changes in behaviour and increased numbers of people on treatment. All of these have been achieved over the course of the project: the national HIV prevalence of 6.8% (KDHS 2010) is a slight reduction over the 7.4% seen in 2007. The percentage of men reporting multiple partners has been halved (from 11.9% to about 5%) and the number of people on ARVs as a percentage of those who need to be on ARVs has almost doubled, from 40% in 2007 to more than 70% in 2011 (and this considering that during the project, the criteria for being on ARVs was broadened to include everyone with a CD4 count of less than 350). The question of attribution needs to be raised as to how much the DFID support to the UN Joint Team and Maanisha contributed to this. However, it was argued by some respondents that the increased harmonisation and coordination led to the support of the Modes of Transmission study in 2009.This in turn led to changes in the KNASP II, a broadening of interventions for high-risk populations and other policy developments (such as the scale-up of circumcision), thus creating an increased programme response, which may have been contributory to the improved HIV data as of 2012. / The impact of the DFID HIV programme on the epidemic in Kenya is an open question for two reasons. The first one relates to the fact that DFID has been indirectly supporting implementation of effective evidence-based HIV sub-programmes/ interventions by strengthening the strategic planning, monitoring and evaluations of programmes and leadership of the Kenya HIV and AIDS response: assisting the Government in doing the right things – not doing them. However, as the strategies, policies and plans are a prerequisite for effective and efficient implementation. DFID supported development of various policies on HIV such as PMTCT, the development of a circumcision policy and the roll-out of the VMMC program. / The second reason for uncertainties about impact is technical and relates to the logical framework of the project that focused on output evaluation of the various key interventions the UN supported over the years. The ideal would have been to also focus on establishing the cost-effectiveness of the HIV interventions. However, it is only within recent years that NACC has become interested in unit costs, programme costs and the efficiency of interventions. / Overall the sustainability of the DFID HIV programme in Kenya is assessed to be good to high. The UN components are assessed to have done very well on transforming the UN to work as one UN and harmonisation and cooperation between UN and NACC has improved over the years of the programme, although more needs to improve. The working relationship and cooperation between Government institutions is still not optimal, but has also improved over the programme period. There is little to indicate that the achievements reached in how the key stakeholders in HIV work together will be rolled back in the coming years; on the contrary, everything seems to point toward the probability that developments will continue and spread to other areas of interest between the UN and the Government. / The Maanisha project is praised as a great success by all parties that the end of project evaluation team met with, and available documentation corroborates this. However, all experience shows that it is difficult to sustain community projects if funding or other support is not continued at some level. The Maanisha project did not only capacity build the CSO/PSO in the community but also the decentralised Government institutions such as the CACC. Some CSOs/PSOs have managed to attract “new” money after the Maanisha support stopped – not least thanks to the quality of the capacity building by the programme. Other CSOs are carrying on their work based on voluntary work after Maanisha stopped its funding and some of these might be able to continue their work even in the longer term. / The number of CSOs who were supported by Maanisha who will still be able to use what they learnt in the project and benefit their communities after one or even five years is of course difficult to project. However the estimates obtained by the AMREF evaluation team varied between 30-45% of CSOs will be sustainable within the first year, which is assessed to be a satisfactory level. Therefore the results of the Maanisha programme are considered to be sustainable, assisted by the fact that the programme implemented a multi-dimensional sustainability plan. In terms of financial sustainability, 76% of CSOs are able to access resources outside Maanisha, and on social responsibility, 86% of the CSOs provided HCBC according to government guidelines, while 69% of the CSOs were supported by the District Technical Committees (DTCs) and CACCs, thus ensuring sustainability. / Challenges remaining: The evaluation team did not come across any plans for sustaining the capacity of community organisations including CACCs in the Government. / Opportunities not realised: The UN component improved the level of joint planning between UN and the Government, but the optimal level of collaboration has not yet been reached. There is evidence that while progress has also been made on reducing transactional costs, there is still some way to go to improve mechanisms to cut the financial input and increase resources spent on assistance to the Government in the fight against HIV in Kenya.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / 2.2 Key cost drivers / 2.2.1 Allocated to Maanisha - Over 2008/09-2012 Maanishareceived the total grant until March 31 2011 (audit report): US$ 32.4 million (100%) divided between DFID £10 million and SIDA US$ 13.1 million. / 2.2.2 Allocated to UNJP – £10 million (approximately US$ 15 million). / UNJP Spent to date- September 2012 – £ 9.4 million / UNJP outcomes Pounds DFID % / outcome / Outcome 1 4,020,741 48.11% / Outcome 2 974,184 11.66% / Outcome 3 987, 821 11.82% / Outcome 4 2,375,242 28.42% / The sum spent on different outputs amounts to approximately £ 9.4 million up to the end of September 2012. However, UNJP has been granted a no-cost extension period up to March 2013 to implement the currently planned activities. The budget for these remaining activities amount to £560,280 approximately (USD $879,640). / 2.3 Was the project completed within the expected timescale: No - The exact end date of this project was September 2012, however the UNJP has been granted extension of expenditures up to March 2013. This is to allow for finalisation of end term project documentation and dissemination.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / This project was designed to support a harmonised evidence-based HIV and AIDS programme informed by the rigorous analysis of Kenya’s AIDS epidemic, following the KAIS and MOT studies done in 2007 and 2008 respectively. There has not been any recent new evidence over the course of the programme that affected the implementation of the project. / In terms of a Theory of Change, it was always going to be difficult to make connections between improved harmonisation of different UN programs and their relationships with NACC and NASCOP, and an ultimate reduction of HIV prevalence in Kenya, and the best that can be said is to note the various policy documents and studies that have been generated in the past four years – the Modes of Transmission Study, the scale-up of PMTCT, the development of a circumcision policy and the roll-out of the Voluntary medical male circumcision (VMMC) programme etc. All of these have been seen to be contributing to the ultimate project goal, and it could be argued that these initiatives occurred directly as a result of the increased harmonisation and improved working relationships created by the DFID project. / Similarly, the capacity-strengthening of CBOs by Maanisha could be argued to have a downstream effect of improving their community-based programmes, and promoted behaviour change in the local populations on HIV prevention. / 3.2 Set out what plans are in place for an evaluation. / Not applicable

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? No / The annual reviews in 2010 and 2011 did not include a risk rating. / 4.2 Risk funds not used for purposes intended / The funds provided under this programme were used for the intended purpose. / The original programme design had identified three main channels for HIV and AIDS support in Kenya, but only two components were funded. After the programme was designed, civil unrest following the 2008 elections combined with a series of issues around governance and transparency led to withholding of approval for DFID direct funding via the National AIDS Control Council (NACC) to the World Bank HIV and AIDS ‘TOWA Project’ due to perceived fiduciary risk. / 4.3Climate and Environment Impact / Not applicable

5. Value for Money (VfM)
5.1 Performance on VfM measures / There were no specific VFM indicators in the log frame (or KNASP II) that would have been helpful to assess VfM for the programme. However there are other studies that have been done in Kenya by other partners that have identified interventions that have demonstrated VfM. / These studies by other partners include cost-effectiveness information on interventions that have been priorities in the KNASP over the past five years, taking into account available findings and information. These HIV interventions include: 1) circumcision as a prevention measure, 2) VCT scale up, including VCT as part of interventions for discordant couples, and 3) interventions targeting MARPs in Kenya. / Two unit cost studies on male circumcision have been carried out in Nyanza Kenya, of adult men undergoing circumcision. The first one by Kioko using a model developed by Futures Group estimated the unit cost at USD 36-42 depending on site. The second cost study was carried out by Marseilles et al and arrived at a very similar unit cost USD 29-46. Both cost studies operate with a range of assumptions and do not incorporate costs of campaigns to ensure demand and cover costs of complications. All cost-effectiveness studies agree that male circumcision in high prevalence areas has cost-saving potential compared to lifelong ART. UN’s support to Government to ensure coordination and implementation of male circumcision as a means to prevent HIV infections in Kenya is thus per se resources well spent and value for money. / Regarding PMTCT, a Global review of cost-effectiveness of PMTCT by Johri and Ako-Arrey (2011), includes information for a study carried out in Kenya by Sweat et al (2000). The study concluded that it costs Int$ 4,800 per infant infection averted – the study does not include the benefit of treating the mother, and that would have to be added since ART is now available for HIV positive pregnant women and mothers, and the result is thus an underestimation of the programme effectiveness. The cost-effectiveness ratio (CER) is comparable to that of male circumcision. UN’s support to NACC to effectively coordinate the implementation of e-MTCT in Kenya is thus per se resources well spent and value for money. / Ten years ago Sweat et al (in Creese et al 2002) carried out a study on impact of VCT on the HIV epidemic simultaneously in both Kenya and Tanzania for couples with high prevalence rates (20%). The study showed that it costs Int$ 29-31 to provide the Voluntary Counseling and Testing (VCT) services in stand alone clinics and the CER was as low as Int$ 393-482 per HIV averted. The result demonstrates high levels of cost-effectiveness for VCT, with a substantially better CER than for both PMTCT and MC. / From the studies available Female Sex Workers (FSW) interventions were, and probably remain, best buys in HIV prevention: lowest cost per HIV averted – approximately Int$ 60 per HIV averted (2002 prices). / A number of cost-effectiveness studies from Asia and Eastern-and Central Europe are available showing that investing in IDU HIV interventions are very cost-effective interventions. No studies are available for Sub-Saharan Africa. / Recently the World Bank published documentation on the HIV epidemic among MSM including modeling of costs and cost-effectiveness of MSM interventions. The case study countries from Africa were Kenya, Malawi and Senegal. The cost-effectiveness results show that MSM interventions are very cost-effective. The modeling operated at coverage levels at 30-60% and had results of approximately USD 270-1100 per HIV averted. The modeling includes the saving gains of ART for HIV averted. The assumptions used in the World Bank modeling are far from the realities on the ground for MSM interventions in Kenya in 2012, but the modeling provides the potential gain that is today not being harvested. / 5.2 Commercial Improvement and Value for Money / Not applicable to this project / 5.3 Role of project partners / The value of spending £ 10 million to achieve the level of harmonisation, coordination and alignment for the UN component over what has turned out to be 3-4 years of implementation can be argued as money that has been well spent: the UN system has managed to perform well and now acts as one UN program fighting HIV in Kenya. / The total resources allocated to Maanisha from the pooled DFID and SIDA resources have been approximately USD 32 million (DFID’s share being £10 million). Of this financial input AMREF has consumed approximately USD 10 million for capacity building over 3-4 years. For this amount of money one can expect a lot – and given the original indicators a lot has been achieved, leading to the conclusion that the money has been well spent, based on CSOs and donors’ satisfaction with the project.The programme was implemented in a timely and efficient manner, meaning that everything was done according to plan. Maanisha management was organised to provide strategic and technical direction to the programme, facilitate, efficient internal operations and foster good working environment. / Did the project represent Value for Money: Yes / The Government of Kenya has had a full agenda on HIV over the past five years accommodating new (e-PMTCT and circumcision as prevention) and revised interventions (changing the eligibility criteria for ART to include PLHIV earlier in the course of the disease). Cost-effectiveness evidence shows that PMTCT, the use of interventions targeting discordant couples offering VCT,and male circumcision as HIV prevention measures are all cost-effectiveness interventions in Kenya context and VfM since they could have a significant impact on the epidemic.

6. Conditionality
6.1 Update on specific conditions / Not applicable to this project

7. Conclusions
The DFID Kenya Harmonised HIV Programme was originally envisaged to be a three-component project, with support to the UN Joint Program, the World Bank TOWA Project, and the AMREF Maanisha Programme.In the end, only the UNJP and Maanisha were supported, and the project completion review team felt that in reality DFID had been supporting two distinct projects under a single funding umbrella. / As evidenced by the reporting against outputs and outcomes, both components were successful: the UN Joint Program was harmonised and through its support to NACC and the Government of Kenya, a number of research initiatives, policy documents, planning strategies and both prevention and treatment/care interventions were implemented in the country over the past four years.The Maanisha Programme meanwhile built the capacity of several hundred CSOs in four provinces, with the assumption that their strengthened capacity would lead to better HIV programming. / The Maanisha programme accomplished its purpose, as the CSOscapacity was improved and a total of 76% are now able to attract funding from other sources, while 69% continue to be supervised by the District Technical Committees (DTCs) and Constituency AIDS Control Coordinators (CACCs), thus ensuring that they offer quality services. Beneficiaries were empowered with 94% of PLHIV receiving skills training. Furthermore, they were given voices and visibility, particularly women who are now participating in various forums. A total of 74% of women beneficiaries received training on human rights. Lives of those infected and affected by HIV have improved tremendously, with 95% of beneficiaries reporting that Maanisha work had improved their quality of life. This was achieved through the provision of services like Home and Community Based Care (HCBC) and support to orphans and vulnerable children (OVC). More important was the empowerment of these beneficiaries through income-generation activities (IGA) which will enable them to access services they require with minimum external assistance. / The programme has ended with no directfollow-up programme or next phase. However DFID Kenya supports other HIV and AID related programmes and initiatives including supportingsocial marketing of condoms for HIV prevention, and for family planning throughout the country. A key element of the programme is increasing access to condoms through social marketing interventions, support to the GoK to distribute free condoms to those who cannot afford them, and behaviour change communication to drive demand for safer sexual behaviours. The same programme aims to support national health strategic objectives to increase use of family planning products and services by increasing access to, and demand for, modern contraceptives to women of reproductive age. DFID Kenya will continue to support HIV and AIDS intervention in the country through on-going programmes as well as other broader integrated health system strengthening programmes with coordination with other key stakeholders.

8. Review Process
Two consultants conducted the review, beginning with a survey and analysis of available project documents (previous OPRs, six monthly & annual reports, and emerging data or research papers). Over twelve days in Kenya, the review team conducted multiple meetings with each partner (AMREF and the UN-Kenya Joint Team on AIDS) as well as meeting with key stakeholders from NACC, NASCOP, and SIDA and other development partners. More than twenty key informant interviews were held with representatives from the implementing agencies, government and civil society, program officers from DFID and other donors, as well as beneficiary groups. At the completion of the fieldwork, a presentation of preliminary findings was made to representatives of DFID, UNAIDS and AMREF, and their comments and feedback were incorporated into the final report. / The independent consultants undertaking the review proposed the output and outcome scores shown here based on their findings. Using the evidence presented DFID staff have added indicator level scores as required in DFID Kenya and have edited and added more detailed explanations.DFID Reproductive Health adviser provided significant input into the review and finalised the drafting process (updating some of the results to reflect latest reporting and adding some additional qualitative assessment and reflections).