## Sheet1
PROJECT NAME | UNICEF Nutrition Surveillance Project, Fast Track Aproach in Ethiopia
IMPACT | Impact Indicator 1 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project | Assumptions
Improve timeliness, targeting, coverage of humanitarian response | % of timely response to the crisis in priority 1 woredas | Planned | Response delayed by 4-6 months | Timely response to the crisis | Response adapted to the stage of the crisis | Timely warning and appropriate response ensured by the end of two years | Government ownership; System credibility; System sustainability; Decision making based on triangulation of nutrition indicators with food security and other context data;Independent system; Technical staff turnover at the selected Woredas remain minimal
Achieved
Source
Response Reports (OCHA, ENCU)
| Impact Indicator 2 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
| % response in priority 1 woredas that used the monthly nutrition trends | Planned | Lack of trend data | > 50% of priority 1 woredas used the monthly nutrition trends for decision making and response | > 80% of priority 1 woredas used the monthly nutrition trends for decision making and response | 100% of priority 1 woredas used the monthly nutrition trends for decision making and response
Achieved
Source
Quarterly bulletins (TFP, CBN, and CHD indicators); Biannual standard nutrition surveys; validation reports (small scale surveys on sub-sample); monitoring reports
Outcome | Outcome Indicator 1 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project | Assumptions
| % of bi-annual survey woredas providing timely nutrition report | Planned | Delay by 2-3 months | Nutrition survey report available within 6 weeks for 80% of the woredas | Nutrition survey report available within 4 weeks for 90% of the woredas | Nutrition survey report available within 4 weeks for 100% of the woredas | Consensus reached on the data sources and minimum indicators
Achieved
Source
Bi-annual nutrition survey reports (ENCU)
Timely availability and quality nutrition report linked to agro-economic baseline data (HEA/LIU) and early warning data (EWS) | Outcome Indicator 2 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
| % of priority 1 woredas reporting all agreed monthly nutrition indicators | Planned | Poor reporting rate | > 65% reporting all agreed nutrition indicators | > 75% reporting all agreed nutrition indicators | >85% reporting all agreed nutrition indicators
Achieved
Source
TFP,CHD,CBN reports, Monitoring reports (Internal Quality Assurance);Validation reports / Standard Nutrition Surveys (External Quality Assurance)
NPUTS (USD) | DFID (USD) |  | GOV/WB (USD) | UNICEF (USD) | Total (USD) | DFID SHARE (%)
| 2910900 |  | 1713550 | 1521366 | 6145816 | 47%
NPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Indicator (1) |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project | Assumptions
Timely availability of Nutrition indicators from existing CBN/TFP/CHD data systems to feed into early warning system | Five agreed indicators on CBN (1. Coverage, 2. Underweight and 3. Severe underweight) and TFP (1. Reporting Rate OTP; 2. New admissions OTP) consistently reported (%) | Planned | Poor reporting rate | > 80% of woredas reporting all five agreed indicators | > 90% of woredas reporting all five agreed indicators | 100% of woredas reporting all five agreed indicators | CBN/OTP expansion to ensure 100% coverage at woreda level; CBN Program continues to work on quality improvement of weighing and reporting at community level; TFP Program continues to work on quality improvement of reporting at OTP site levels. All children are admitted in the OTP based on eligibility
Achieved
Source
FENCU monthly updates, TFP reports, CBN/CHD reports; Monitoring reports (Internal Quality Assurance);Validation reports
| Indicator (2) |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
| Number of weeks from collection to availability of data | Planned | Delay up to 8 weeks | Reducing delays to 6 weeks | Reducing delays to 4 weeks | Reducing delays to 4 weeks
Achieved
Source
FENCU monthly updates, TFP reports, CBN/CHD reports; Monitoring reports (Internal Quality Assurance);Validation reports
| Indicator (3) |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
| Availability of new technology - database | Planned | None | None | none | In place
Achieved
Source
Consulting firm report; Steering committee reports, Monitoring reports (Internal Quality Assurance);Validation reports
IMPACT WEIGHTING | Indicator |  | Baseline Year | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
50% |  | Planned
Achieved
|  |  | Source |  |  |  | RISK RATING
LOW
NPUTS (USD) | DFID (USD) |  | GOV/WB (USD) | UNICEF (USD) | Total (USD) | DFID SHARE (%)
| 1006466 |  | 1713550 | 1444148 | 4164164 | 24%
NPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project | Assumptions
Timely availability and quality of bi-annual nutrition survey indicators | Number of surveys implemented on seasonal calander | Planned | Delay in approval | 50% surveys conducted based on seasonal calander | 80% of surveys conducted based on seasonal calendar | 100% of surveys implemented according to seasonal calendar | Consensus reached with the Government
Achieved
Source
| Output Indicator 2.2 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
| Number of survey reports endorsed within two weeks of release of reports | Planned | Delay in endorsement | 100% of survey reports endorsed within two weeks | 100% of survey reports endorsed within two weeks | 100% of survey reports endorsed within two weeks
Achieved
Source
Output Indicator 2.3
| E-learning training modules developed for improved capacity development | Planned |  |  |  | 100% of e-learning training modules developed for use by nutrition staff
IMPACT WEIGHTING | Output Indicator |  | Baseline Year | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
40% |  | Planned
Achieved
|  |  | Source |  |  |  | RISK RATING
High
NPUTS (USD) | DFID (USD) |  | GOV/WB (USD) | UNICEF (USD) | Total (USD) | DFID SHARE (%)
| 1695434 |  |  | 77218 | 1772652 | 96%
NPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project | Assumptions
Increased knowledge and guidance on nutrition data collection and interpretation in pastoral areas | Operational research conducted on nutrition in pastoral areas | Planned | NA |  | TOR developed and process initiated | Operational research completed | Access to pastoralist populations in regions of Somali and Afar
Achieved
Source
| Output Indicator 3.2 |  | Baseline 2010 | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
| Best practice note(s) produced | Planned | NA |  |  | Best practice completed
Achieved
Source
IMPACT WEIGHTING | Output Indicator |  | Baseline Year | Milestone 1 12 months from start of project | Milestone 2 18 months from start of project | Target (October 2012) At completion of project 24 months after start of project
10% |  | Planned
Achieved
|  |  | Source |  |  |  | RISK RATING
High
NPUTS (USD) | DFID (USD) |  | GOV/WB (USD) | UNICEF (USD) | Total (USD) | DFID SHARE (%)
| 210000 |  | 0 | 0 | 210000 | 100%
NPUTS (HR) | DFID (FTEs)
Note on B39: ABAILES: We discussed that FMOH was looking into the use of cellphones, but the possibility of the FMOH considering it for the nutrition database has not been discussed with ministry.