Type of Review: Annual Review

Project Title: Social Fund for Development (Phase IV)

Date started: Dec 2012	Date review undertaken: Dec 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
In 2010, DFID committed to provide £100 million over five years between January 2011 and December 2015 to Phase IV of the Yemeni Social Fund for Development (SFD) to improve access to basic services, enhance economic opportunities and reduce vulnerability for the poor.

What are the expected results?
What will change as a result of our support? / DFID support will enable SFD to meet their overall aim to improve the lives of the Yemeni poor. The main objectives of our support are: / improve access to basic services, such as education and health facilities; / create economic opportunities and improve the business environment; / create employment opportunities for the poor; and / increase the ability of local authorities, NGOs, and communities to manage, monitor and evaluate development programmes. / What are the planned outputs of the project attributable to UK support?[1] / In total, the programme will: / enable the construction and/or rehabilitation of 9,000 classrooms and 80 health centres / provide access to credit and savings for 100,000 clients / provide employment opportunities for 300,000 poor people / train 7,720 individuals and organisations in project planning / This is a multi-donor supported project and DFID’s contribution equates to 14% of the total budget. Key results attributable to DFID therefore include: / Over 50,000 pupils enrolled in SFD-supported schools / 6,720 households provided with new/improved drinking water / Over 150,000m3 of water stored in protected facilities / 3,360,000 employment days created
[1] While DFID’s total pledge (£155 million) to SFD Phase IV currently amounts to 28.5 per cent of total donor pledges to date, it represents 14 per cent of the overall budget for Phase IV. Thus, burdenshare is likely to become more equitable amongst donors as additional pledges and funding are received. To calculate cumulative results attributable to DFID, DFID multiplies the total results delivered by SFD by 14 per cent.

What is the context in which UK support is provided?
Yemen is one of the poorest countries in the Middle East and poverty is widespread with 47% of the population living on less than $2 a day.[2] Rural areas are home to 73 per cent of the population but 84 per cent of the poor.[3] Remote, widely scattered villages and poor road conditions make access to health and other social services extremely difficult. Educational facilities are also inadequate, both in number and in the quality of teaching materials. / Yemen is the tenth most food insecure country in the world, ranking 70 out of 79 countries in the 2012 Global Hunger Index. In recent months, food insecurity has soared to acute levels and more than 10 million Yemenis, or 44.5% of the population, are now food insecure.[4] Yemen imports over 90% of its wheat, making it particularly vulnerable to fluctuations and volatility in global food prices. / Population growth is one of the world’s highest at 3.03% with the current population of 24 million expected to reach 60 million by 2050 (UNFPA). Under this scenario 2.2 million new jobs would be needed, and there would be 14.7 million children in primary school, requiring 490,000 teachers (IRIN Middle East). In addition, estimates suggest that unemployment, and particularly youth unemployment, is high, nearing 70 per cent. There are few viable employment opportunities for the rural poor and generating income through agriculture is difficult as access to markets and arable land are limited and livestock production unsustainable. This has contributed to Yemen’s alarmingly high rates of undernourishment. / Poverty in Yemen is political and multi-dimensional, linked to both social and economic inequalities. Power relations determine the distribution of opportunities and benefits and local social structures and power dynamics must be understood to adequately address and reduce poverty levels.[5] In Yemen, qualitative as well as quantitative measures of poverty are needed as access to and control over resources and opportunities are often determined by tribe or social group, age, race and ethnicity, gender, religion, nationality and displacement status, and social identities are often rigid. / Following popular protests and a political crisis triggered by the Arab Spring, Yemen is now emerging from a period of unprecedented economic contraction, widespread insecurity and conflict, all of which have exacerbated already alarming rates of poverty and vulnerability. Though the situation is improving, it is still extremely fragile. To help lift poor households out of poverty, the World Bank estimates that the government would need to allocate at least four per cent of its GDP to help fill the gap between the actual spending of poor households and the poverty line.[6] Yet, social spending in 2012 accounted for just 1.9 per cent of GDP and only 0.65 per cent of GDP was allocated to the Social Welfare Fund in 2011.[7] / Yemen’s existing public social protection system consists of programmes that provide income assistance, training, small and micro-credit, public works and community-driven operations. It also includes contributory social security and pensions for public and private employees. There are several government agencies and departments tasked with delivering social protection. The most prominent include the Social Welfare Fund (SWF) and the Public Works Project. The Social Fund for Development (SFD) operates as a non-governmental organisation (NGO), receiving regular funding and loans from the Government of Yemen but without the direct oversight and control that the Government has over, for example, the Social Welfare Fund and the Public Works Programme. Along with private sector and NGO representatives, a number of government ministers sit on SFD’s Board of Directors which is chaired by the Prime Minister. / The international donor community increasingly recognises social protection as an appropriate short- and long-term response to poverty and vulnerability in Yemen. The Government of Yemen’s (GoY) ability to provide social security for the poor is ineffective and in much need for reform. In order to achieve these necessary reforms, GoY needs to address the issue of unsustainable fuel subsidies (currently 37% of the budget) which largely benefits better-off Yemenis and to increase their expenditure on state welfare, currently 0.6% (below the average for other developing countries). / The Transitional Programme for Stability and Development 2012-2014 (TPSD) and the Mutual Accountability Framework (MAF) identify support for social protection as a key priority. Donors and multi-lateral agencies have provided core support for social protection institutions in Yemen, such as the Social Welfare Fund (SWF) and the Social Fund for Development (SFD), and have increased support for cash transfers, public works programmes and other interventions to protect poor people from both transitory shocks and chronic poverty.
[2] World Development Indicators, 2005.
[3] World Bank, Yemen Overview. Last updated September 2012.
[4] WFP, Comprehensive Food Security Strategy, 2012.
[5] Poverty Analysis Discussion Group, “Understanding Poverty and Well-Being: A Note with Implications for Research and Policy.” April 2012.
[6] Government of Yemen, The World Bank, and the UN Development Program, “Yemen Poverty Assessment.” November 2007.
[7] Data from Ministry of Finance, Government of Yemen and the World Bank, “Joint Social and Economic Assessment for the Republic of Yemen.” 2012

## Section A: Detailed Output Scoring

Output 1: Basic services improved
Output 1 performance description: / A+ – (Output moderately exceeded expectation)[8] / Indicator Cumulative target for this review [9] Cumulative achievements [10] Cumulative achievements attributable to DFID / Number of classrooms constructed or rehabilitated 2,400 total 2,721 total 381 / Number of pupils benefitting from SFD-supported schools 96,000 total / - 53,760 boys / - 42,240 girls / - 1,625 special needs children 148,340 total / - 83,440 boys / - 64,900 girls / - 1,824 special needs children 20,768 / - 11,682 boys / - 9,086 girls / - 255 special needs children / Number of teachers trained 80 total / - 40 male / - 40 female 770 total / - 180 male / - 590 female 108 / - 25 male / - 83 female / Number of other educational professionals trained 552 total / - 312 male / - 240 female 751 total / - 438 male / - 313 female 105 / - 61 male / - 44 female / Number of health facilities constructed or rehabilitated or equipped 40 73 10 / Number of health professionals trained (sex disaggregated) 1,100 total / - 550 male / - 550 female 1,898 total / - 569 male / - 1,329 female 266 / - 80 male / - 186 / Number of households provided with new/improved drinking water sources 19,200 39,193 5,487 / Volume of improved drinking water stored in facilities (m3) 440,000 895,147 125,321 / Number of households provided with new/improved sanitation facilities 10,400 9,156 1,282 / Total km of rural roads built or upgraded 730 323 45
Progress against expected results: / SFD’s Community and Local Development Programme (CLD) aims to improve access to basic social services by implementing community-based projects and building the capacity of local authorities implementing development projects. Sectors of work include, among others, health, water and sanitation, education, and agriculture and rural roads. The CLD programme also seeks to equip local authorities’ and communities’ with improved participatory planning and management skills. At 63 per cent, SFD’s CLD Programme represents the largest share of the total planned budget for Phase IV. / SFD has met most of the milestones for 2012 in the CLD programme and in many cases exceeded them. The sole exceptions to this are the number of households provided with new/improved sanitation facilities and rural road construction. / Rural road construction / Since the start of Phase IV, SFD helped to build and/or upgrade 323 kilometres of rural road, 44% of the expected target for this period. This is largely due to an overly ambitious target. As SFD has now completed the second year of Phase IV, they will conduct a mid-term review of the programme with donors in 2013. This will provide an opportunity to revise overly ambitious or modest targets, refine and update indicators and amend the results framework. During this review, the target for rural roads will be reviewed and revised accordingly. / Sanitation facilities / Since the start of Phase IV, SFD has provided 9,156 households with new or improved sanitation facilities, 88% of the expected target for this period. SFD reports that promoting proper sanitation in Yemen remains a challenge. Only 26 per cent of rural households have adequate sanitation systems.[11] The National Water and Sanitation Authority retains responsibility for urban water and sanitation while the General Authority for Rural Water Supply (GARWS) retains responsibility for rural water only and has played no role in addressing rural sanitation issues. Thus rural communities are left to address their sanitation needs themselves which remain woefully unmet.[12] In the past, rural communities—as well as many households in urban settlements—used traditional dehydration latrine facilities or waterless toilets. However, since the 1970s, the Government of Yemen has promoted sanitation systems that require high-water consumption.[13] This has discouraged the use of traditional low-water consumption facilities as many rural communities desire parity with Sana’a and therefore high-water consumption sanitation facilities.[14] / SFD continues to advocate for expanded support for rural sanitation, particularly hygiene promotion. However, the GoY does not maintain standards for hygiene promotion and thus water and sanitation (WASH) actors, particularly humanitarian actors, have not approached it uniformly.[15] During 2011 and 2012, SFD rolled out Community-Led Total Sanitation (CLTS) activities were implemented in 295 villages out of which 50 villages have achieved the target of being free of open defecation. CLTS activities include hygiene and environment awareness campaigns to deliver three key messages: sanitation, hand washing and water treatment at household-level. CLTS interventions have shown some preliminary signs of success and humanitarian agencies have expressed interest learning more about the approach. SFD is helping to facilitate a training on best practices in water and sanitation and maintains contact with UNICEF and other the WASH cluster actors to harmonise approaches / Against other indicators, such as the number of teachers trained and cubic metres of improved water storage, SFD significantly exceeded targets. This can be explained by additional funding provided by the European Union which specifically targeted girls’ education and teachers’ training, thus increasing performance against this indicator. While impressive, this indicates that a thorough review of targets and milestones is necessary, revising them as necessary to ensure they maintain an adequate balance between achievable and aspirational, particularly as new earmarked projects and funding come on-line. / Recommendations: / Despite impressive performance against most of the indicators for the CLD programme, SFD should review and revise these indicators and targets during the forthcoming mid-term review to ensure they are fit-for-purpose and are achievable and realistic. / DFID will seek to include, where and as possible, inputs from other advisors within DFID, such as education, health and water and sanitation specialists, in the upcoming mid-term review and planned revision of the results framework to ensure expert input is provided. / Through its support for UN agencies, the Emergency Response Fund (ERF) and other humanitarian programmes in Yemen, DFID will encourage humanitarian actors to improve coordination and information sharing with SFD sector heads and uptake of best practices and lessons learned, to help bridge the divide between development and humanitarian actors in Yemen. / Impact Weighting (%): 70 / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N
[8] Though only eight of the ten targets were achieved under this output, DFID scored SFD’s performance against this overall output as an A+ based on internal guidance advising that achievements reported within twelve per cent of a target result in a performance score of A.
[9] This target represents total cumulative results since the start of Phase IV, January 2011 through December 2012.
[10] These figures represent total cumulative results since the start of Phase IV, January 2011 through December 2012.
[11] General Authority for Rural Water Supply (GARWS) 2010 survey.
[12] SFD website, http://sfd.sfd-yemen.org/category/10.
[13] For the most part, SFD reports that the Government of Yemen has supported policies and strategies that promote an over-reliance on groundwater at the sake of other approaches such as rooftop rainwater harvesting and other urban rainwater harvesting strategies.
[14] An exception to this is Hadramout where dry toilets are still found in abundance. This is due in large part to the extensive use of water-sensitive adobe in the construction of buildings and the use of human waste as compost in agricultural activity. Rigid and strict societal structures in Hadramout may also affect sanitation systems. Maintenance of public latrines and rubbish collection throughout Yemen is still seen by many as the domain of the al-Muhamasheen, pejoratively referred to as the al-Akhdam or “servant.” An Arabic-speaking, Muslim population who face severe, ethnic-based social exclusion and discrimination, the al-Muhamasheen are treated as an “untouchable” community and in many areas in Yemen work in local sanitation, including latrine cleaning and rubbish collection is relegated to them. This division of labour is still quite common in Hadramout. (Sources: The New York Times and Shadow reports to 104th Session of the UN Human Rights Committee)
[15] SFD presentation, joint-donor review, November 2012.

Output 2: Economic opportunities created
Output 2 score and performance description: / A – (Output met expectation) / Indicator Cumulative Target [16] Cumulative achievements [17] Cumulative achievements attributable to DFID / Number of active borrowers 67,000 clients / - 60% female / - 15% rural 79,563 clients / - 64% female / - More than 15% rural 11,139 / - 64% female / - More than 15% rural / Total value of outstanding loans (Million YR) No target set 5,493 769 / Percentage of active borrowers served by microfinance providers that are financially sustainable 35% 22% 22% / All MFIs have less than 5% Portfolio at Risk (PAR) <5% <5% [18] <5% / Credit bureau legislation/regulation submitted to the government to support positive enabling environment for microfinance First draft prepared Workshop held about credit bureau Workshop held about credit bureau
Progress against expected results: / SFD’s Small and Micro Enterprise Development (SMED) programme aims to strengthen and build the capacity of local microfinance providers and actively promote their entry into the market by creating an enabling environment and encouraging the establishment of new financial service providers. The SMED Programme represents 3 per cent of the total planned budget for Phase IV. / There was mixed progress against indicators in output two. This is in part due to the prolonged effects of the 2011 political crisis, disruptions to regularly parliamentary business and pockets of insecurity throughout the country. Additionally, DFID finds that the indicators are no longer fit for purpose and have not adequately captured the achievements of the SMED programme, particularly in light of recent political and security challenges. These indicators do not accurately capture the progress that SFD is making in SMED and the wider private sector. SFD is leading on some very innovative work, particularly around mobile phone banking technology which has yet to take off in Yemen. / Throughout 2012, the SMED programme continued to support lending activities and provide technical assistance to 24 MFIs and programmes as well as business development services to encourage the development of the SME sector in Yemen. Since the start of Phase IV, SFD has helped MFIs support close to 80,000 active borrowers and more than 117,000 savers with a total loan portfolio of approximately YR 5.5 billion (est. $25.4 million). Despite the crisis, the number of savers has steadily increased steadily since 2008. In 2012, the number of active borrowers, savers, and the outstanding loan portfolio increased by 21%, 34%, and 29% respectively. This suggests a pattern of recovery from the crisis. However, two banks in particular account for much of this increase. Al-Amal and Al-Kuraimi Banks can, by law, accept voluntary savings, while MFIs accept only limited and compulsory savings as a guarantee against micro loans. / Field audits carried out in 2011 and 2012 by the SMED programme also demonstrated improved performance of SFD-supported MFIs. SFD continued planned trainings and workshops through 2012 in the face of on-going security challenges posed by the political crisis and transition. The exception to this strong performance is the Abyan Microfinance Foundation whose five branches have now collapsed, due to the crisis and conflict in Abyan. Prior to this, the Abyan Microfinance Foundation was recognised as one of the best MFIs in Yemen. / Due to increasing competition and overlap between existing lending institutions and programmes, SMED recognized a need to establish a common database to hold the credit history of microfinance clients and minimise the chances of customer duplication. In September 2012, SMED launched the Credit Bureau, a database that includes the names and information of the clients and guarantors of all MFIs in Yemen, including the client's credit history. This information will be regularly updated and open for queries by any MFIs. A specialist in management information systems (MIS) maintains the website and security is maintained through a sophisticated encryption software. To date, SFD has entered information for more than 154,000 clients and over 20,000 queries for information have been submitted. / In 2012, the SMED unit also provided support to the SFD subsidiary, the Small and Micro Enterprises Promotion Services (SMEPS). Realizing the importance of non-financial services, the SFD established the SMEPS to provide specialized business development services for Yemeni entrepreneurs. During its short existence, the agency has implemented a number of successful projects, which have contributed greatly to the development of the sector. / During a meeting with DFID in September 2012, the Executive Director of SMEPS, Wesam Qaid, expressed an interest in increasing SMEPS’ links with SFD’s LIWP. For example, through SMEPS, the Islamic Development Bank is supporting work on value chain development for honey and coffee in Yemen. SMEPS would like to target this project in areas where LIWP-targeted areas to leverage results, as LIWP inputs, such as land and terrace rehabilitation, can help increase production for example through terracing. / Recommendations: / As with output one, DFID recommends a careful and thorough review of the indicators under output two during the mid-term review scheduled for June 2013. SFD should revise indicators and targets accordingly to ensure they are achievable and realistic and capture the impressive work SFD is undertaking to support MFIs and the private sector in Yemen. / DFID will seek to include, where possible, inputs from our Private Sector Advisor and Economist in the upcoming mid-term review and planned revision of the results framework to ensure expert guidance is provided. / DFID will explore ways in which we can help encourage international NGOs with expertise in microfinance operations and other MFIs to establish operations in Yemen and will report against this action point in the 2014 Annual Review. / Impact Weighting (%): 5 / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N
[16] This target represents total cumulative results since the start of Phase IV, January 2011 through September 2012.
[17] These figures represent total cumulative results since the start of Phase IV, January 2011 through November 2012.
[18] The Abyan Microfinance Foundation was excluded as the crisis and conflict in the south has caused all five branches of the MFI to collapse.

Output 3: Reduced vulnerability for the poor
Output 3 score and performance description: / B - Outputs moderately did not meet expectation / Indicator Cumulative Target [19] Cumulative achievements [20] Cumulative achievements attributable to DFID / Number of people directly benefitting from workfare assistance 200,000 166,448 23,303 / Number of days’ employment created under workfare assistance programme 6,000,000 2,322,173 325,104 / Number of households benefitting from community livelihood assets 120,000 39,947 5,593 / Total area of rehabilitated terraces and agricultural land (hectares) 830 821 115 / Number of community projects (by type) No target set 225 32 / Average length of payment delay (Number of days) 5-7 days 6-8 days 6-8 days
Progress against expected results: / SFD’s labour intensive works programme (LIWP) was established to address acute food insecurity for the poorest Yemenis. The LIWP aims to increase the number of short-term employment opportunities by providing immediate cash payments to those who undertake low-paid work in the community to improve or rehabilitate community assets, such as improving rural roads, and building and repairing wells and agricultural terraces. The LIWP represents 20 per cent of the total planned budget for Phase IV. / From January 2011 to December 2012, SFD undertook 225 projects totalling $46.6 million. As of December 2012, more 2.3 million working days were generated in the construction of these projects, benefitting a total of 166,448 people. Projects completed to date have helped to rehabilitate 821 hectares of agricultural land and terraces. / Despite these achievements, SFD has not managed to reach the milestones agreed to in its results framework. This is in part due to the delay in rolling-out LIWP as a component of Phase IV, which commenced only in October 2011. Prior to this, labour intensive works activities were largely implemented under a series of separate pilot projects including DFID’s LIWP and the EU-funded Emergency Social Safety Nets Project (ESSN).[21] / Additionally, the overall design and purpose of the project has been changed in response to emerging needs and a changing context. In early 2012, SFD developed a paper which set out a new approach to labour intensive works to address increasing food insecurity. The original design of the LIWP provided long-term cash-for-work activities to a smaller number of households, ensuring these households had consistent access to employment opportunities over a period of two to three years. In response to the recent crisis, the LIWP was redesigned to increase the number of short-term, one-off initiatives to maximise the number of people benefitting from paid labour rather than the number of days’ employment per household. / However, it remains unclear if the new design of the programme and its poverty-based targeting approach are ideally suited to target food insecurity. By its nature, the LIWP targets households with labour capacity such as those with able-bodied adults fit for productive work. This is likely to exclude poorer households and women who may face physical or social barriers to employment opportunities and thus may benefit less or not at all from labour-based interventions than. In rural areas the efficacy of setting wages at below market rates is limited and can produce perverse effects. / Other issues have posed challenges to the LIWP. Some of the targets originally established for this output appear to have been overly ambitious. These will be reviewed during the mid-term review and modified accordingly. In addition, drawing up contracts with local suppliers has proven complex as many are initially resistant to using local labour in line with SFD’s specifications. Progress is expected to improve in the forthcoming calendar year as collaboration with local suppliers becomes more regular and working relationships ironed out. / Recommendations: / In addition to those recommendations outlined in the programme completion report (PCR) for DFID’s previous support to SFD’s LIWP (Quest #3730859), DFID recommends the following: / To achieve more precise targeting at governorate level, SFD should explore the feasibility of using data from other sources, such as the forthcoming demographic and health survey (DHS), the World Food Programme’s 2012 Comprehensive Food Security Survey (CFSS). The UNICEF SMART Survey and SFD’s Participatory Rapid Appraisals (PRAs) may serve as additional sources of data for assessing food security at community-level. The PRA should be reviewed to ensure it best captures viable measures of food security in both urban and rural settings. / As with outputs one and two, DFID recommends a careful and thorough review of the indicators under this output during the mid-term review scheduled for June 2013. SFD should revise indicators and targets accordingly to ensure they are achievable and realistic and adequately measure progress against the stated objective of the LIWP. This includes reducing the target for the number of households benefitting from community livelihood assets from 120,000 to 55,000, per SFD’s recommendation. / DFID will seek to include, where possible, inputs from our Economist in the upcoming mid-term review and planned revision of the results framework to ensure expert guidance is provided and linked to broader work to revitalise and support the labour market. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N
[19] This target represents total cumulative results since the start of Phase IV, January 2011 through December 2012.
[20] These figures represent total cumulative results since the start of Phase IV, January 2011 through December 2012.
[21] Between March 2010 and March 2012, DFID provided £7.5 million to SFD in support of its LIWP to protect poor and vulnerable households from the increase in food prices by providing temporary employment opportunities. The Project Completion Report (PCR) for this project was completed in December 2012, noting an overall output score of A for the project (Quest #3730859).

Output 4: Stakeholders capable and empowered
Output 4 score and performance description: / A - Outputs moderately did not meet expectation / Indicator Cumulative Target [22] Cumulative achievements [23] Cumulative achievements attributable to DFID / Number of village councils in pilot areas which are functioning effectively[24] 500 1,344 538 / Number of people and organisations trained in M&E, participatory methods, planning or other strategic information management 800 young volunteers / - 500 male / - 300 female / No target for local authorities 655 young volunteers / - 334 male / - 311 female / 1,065 local authority staff trained 92 young volunteers / - 47 male / - 44 female / 149 local authority staff trained
Progress against expected results: / SFD’s Capacity Building Programme contributes to SFD’s three other programmes by building the capacity of local entities, including local and central government bodies, NGOs, and community-level groups and committees. This programme also helps to strengthen SFD’s own institutional capacity, such as support for monitoring and evaluation and programme management. Its interventions are based on on-going plans and needs assessments of the SFD Units working with those organisations and individuals. The Capacity Building Programme does not directly target poor communities but instead works with community structures or service providers that may include those providing services to poor people and communities. The Capacity Building Programme represents 14 per cent of the total planned budget for Phase IV but is the most underfunded programme of SFD’s four, with only 25 per cent of its planned budget covered by donor pledges. / There was mixed progress against indicators in output four. This is in part due to the limited ability of the logframe and indicators to aptly capture all the wide-ranging activities and achievements that fall within the remit of the Capacity Building programme. This is particularly true for the Empowerment for Local Development (ELD) project. / The ELD programme mobilises communities to lead their own development and to strengthen the links with the district authority. From the perspective of the communities, ELD has reversed the planning process from top-down to bottom-up, enabling communities to identify their need priorities and available local resources to address these priorities. Decisions are based on data collected at community level, and a systematic approach to planning is followed, thus ensuring transparency and accountability. As a result, communities and uslas (sub-districts) are able to feed their priorities into a district plan.[25] SFD works with village and usla committees to design and implement community-based, self-help projects, such as road rehabilitations, literacy classes, and improving local water storage. To date, communities have funded and implemented more than 3,700 self-help projects at a total value of more than YR 511 million (approximately $2.4 million). However, an indicator measuring this achievement is not included within DFID’s logframe. / The long-term success and sustainability of the ELD programme is contingent upon the Government of Yemen’s support of fiscal and administrative decentralisation which has, to date, been stalled. In some cases, this has meant that the plans development by local committees remain unfunded, calling into question SFD’s investment in ELD and increasing the risk of generating communities’ frustration with higher-level governance authorities. / As with output two, DFID finds that many of the indicators contained within our logframe are no longer fit for purpose and should be revised to ensure they capture the impressive achievements SFD have made to date. This holds particularly true for the ELD programme, which, despite its impressive performance in encouraging communities to help themselves, operates in an ever-changing and complex political environment. / Recommendations: / As with outputs one, two and three, DFID recommends a careful and thorough review of the indicators under this output during the mid-term review scheduled for June 2013. SFD should revise indicators and targets accordingly to ensure they are achievable and realistic and adequately measure progress against the stated objective of output four. / DFID will seek to include, where possible, inputs from our Assistant Governance Advisor in the upcoming mid-term review and planned revision of the results framework to ensure expert guidance is provided, particularly as it relates to the ELD project. / Impact Weighting (%): 5 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[22] This target represents total cumulative results since the start of Phase IV, January 2011 through December 2012.
[23] These figures represent total cumulative results since the start of Phase IV, January 2011 through December 2012.
[24] Defined as those that meet regularly, include broad participation from community members (sex-disaggregated), and execute self-help initiatives.
[25] Jennings, Mary, “DFID Yemen Social Fund for Development: Institutional Evaluation 2009, Final Institutional Evaluation Report.” The Recovery and Development Consortium, 2009.

## Section B: Results and Value for Money

1. Progress and results
1.1 Has the logframe been updated since last review? N / The DFID logframe was agreed at the outset of the project in March 2010. This is based largely on the Joint Donor Results Framework to reduce the reporting burden on SFD. The results framework will be reviewed and updated as necessary during the Mid-Term Review meeting in June 2013. This will provide an opportunity to ensure that indicators, milestones and targets are still relevant and achievable. The revised RFW will be used to update and revise the DFID logframe. The outcomes of this mid-term review and recommended changes to the DFID logframe, as well as any other updates, will be captured in a summary review of this programme, planned for August 2013. / 1.2 Overall Output Score and Description: / A – (Outputs met expectations) / In the face of significant deterioration in the political and security situation and the exceptional economic challenges that gripped Yemen throughout 2011 and into 2012, SFD achieved impressive results. The Labour Intensive Works Project proved to be a vital social protection instrument that provided much-needed support to Yemen’s poorest at a crucial time in the country’s history. The CLD programme achieved exceptional results during this period. Despite the very difficult circumstances present in Yemen during the project period, SFD has demonstrated its ability to provide services and support for poor Yemenis. / 1.3 Direct feedback from beneficiaries / Due to the challenging security situation in Yemen it has not been possible for DFID staff to collect direct feedback from beneficiaries to verify the information SFD provided in its narrative reports and evaluations. DFID hope to collect this data in future through sporadic field visits and spot-checks and potentially through the establishment of a third party monitoring system which will aim to verify and triangulate information submitted to DFID by its partners.
1.4 Summary of overall progress / SFD is a non-governmental organisation that delivers essential basic services, such as health, education and water, to poor and vulnerable Yemenis. Social safety nets, such as SFD’s cash-for-work project, help prevent the poorest and most vulnerable from falling further into poverty. / SFD’s work has been particularly important during the transition period by delivering jobs and basic services to people across Yemen. SFD remains one of the few Yemeni development partners who are able to work across the country, in all of Yemen’s 333 districts. The National Unity Government of Yemen has also underscored the critical role of institutions such as the SFD in its Transitional Programme for Stabilisation and Development (TPSD) and has encouraged donors to channel recently pledged funds through SFD. / To expand the social benefits of this programme, SFD and donors should review the findings of the review of SFD’s targeting approaches carried out in 2012 with a view to taking up the recommendations contained therein. The targeting performance of the SFD Phase IV as is currently measured by a single indicator in the Results Framework, which states that at least 50 per cent of SFD resources should go to the lowest three income deciles of the country. However, SFD have noted that this is unachievable and, in the case of some programmes, contravenes programmes-specific visions and objectives, as not all programmes necessarily target the poorest 30 per cent of Yemenis.
1.5 Key challenges / SFD face a number of political and operational challenges. SFD has been without a Managing Director for almost 20 months since Al Arhabi’s departure in April 2011. During this period Abdullah Al-Dailami, a senior technocrat who has played a key leadership role within SFD for almost a decade, has been heading SFD in his capacity as Deputy Managing Director. He is highly respected by SFD staff and donors for his personal integrity, pragmatism and commitment to the SFD vision. DFID has been happy with his performance to date and has not noted any cause for concern. However, the prolonged absence of a permanent Managing Director leaves SFD without the ability to plan for the medium- and long-term. The recruitment process has been slow but DFID welcomes the commitment by SFD’s Board of Directors to a fair, transparent and competitive process. / As a key stakeholder, the Government of Yemen has committed $100 million to SFD Phase IV. The Government delivered on its 2012 commitments and disbursed YR 6.2 billion, approximately $29.1 million. However, the economic situation and fiscal constraints on the budget has increased competition for resources which has meant that government oversight has become increasingly onerous. SFD have responded to numerous requests from the Ministry of Finance (MoF) for very detailed information about individual sub-projects, of which SFD manages over 2,000. SFD has compared their situation to that of the Public Works Project (PWP) who do not face similar challenges from the MoF. / Due to the challenging security situation in Yemen it has not been possible for DFID staff to directly assess SFD’s performance against the information provided in its narrative reports and evaluations. DFID maintains regular contact with SFD to track project progress, assess the impact of the political situation, and discuss ways to strengthen delivery of results. DFID continues to look for creative ways to monitor progress and continues to work closely with SFD and other donors to strengthen the institution’s monitoring and evaluation efforts. / SFD has a very comprehensive management information system and is able to generate an enormous amount of information quickly and easily, particularly as it relates to the number of projects commissioned, their value and the total beneficiaries. However, reporting against targets beyond activity and output level remains weak, particularly with regards to activities such as training and workshops. During the mid-term review, SFD and its donors should explore ways to measure transformation, behaviour change and broader changes in well-being in communities benefitting from SFD support.
1.6 Annual Outcome Assessment / Based on its overall performance and in light of the considerable security and political challenges in 2011 and 2012, this project scored an A at output level (outputs met expectations) and an A at outcome level (outcome met expectations). / Summary of DFID-attributable results / Target by project end, Dec 2015 Milestone and results at last review Cumulative milestone and results for this review / 24 million days’ employment created under workfare assistance programme (3.36 million attributable to DFID) Milestone: 2 million days Milestone: 6 million days / Result: Too early to tell, estimated at 307,445 days Result: 2.32 million (322,000 attributable to DFID) / 360,000 pupils enrolled in SFD-supported primary schools, at least 44% of whom are girls (50,400 attributable to DFID) Milestone: 8,000, 44% girls Milestone: 96,000, 44% girls / Result: 235 pupils, 40% girls Result: 148,340 total, 44% girls (20,768 attributable to DFID) / 48,000 households provided with new/improved drinking water sources (6,720 attributable to DFID) Milestone: 9,600 Milestone: 19,200 / Result: 5,500 Result: 39,193 (5,487 attributable to DFID) / 26,000 households provided with new/improved sanitation facilities (3,640 attributable to DFID) Milestone: 5,200 Milestone: 10,400 / Result: 577 Result: 9,156 (1,282 attributable to DFID) / 100,000 active borrowers accessing microfinance services supported by SFD, at least 60% women and 20 % rural (140,000 attributable to DFID) Milestone: 57,000, 60% female, 15% rural Milestone: 67,000, 60% female, 15% rural / Result: 66,948, 67% women Result: 79,563, 64% female, 15% rural (11,139 attributable to DFID) / 40 district authorities are certified and implementing development projects funded by SFD Milestone: 0 Milestone: 0 / Result: 0 Result: 0. No results expected until 2013.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / The total cost of the project is $1.126 million of which DFID has committed £100 million over five years, estimated at $155 million. As of 25 November 2012 SFD had received commitments worth $542.4 million to fund SFD Phase IV activities, plus an additional $65 million currently under negotiation. The financing gap for Phase IV stands at $584.2 million. / As of 31 December 2012, DFID had disbursed £21.5 million. We are on track to disburse our committed £100 million by December 2015. / 2.2 Key cost drivers / SFD manage all procurement in line with their policy. DFID helped to ensure that key principles were compliant with our rules and regulations. Increasing inflation due to the political crisis of 2011, and the resulting increase in the cost of commodities, such as building materials and fuel, increased the overall unit cost of some SFD project activities. SFD mitigate against these fluctuations in costs by employing creative strategies, such as the use of horse/donkey drawn carts instead of vehicles due to scarce fuel supplies. SFD has also previously provided transportation for field staff to limit disruption to staff attendance due to limited fuel supply. / 2.3 Is the project on-track against original timescale: Y / SFD Phase IV is a five year project which commenced in January 2011 and is due to end on 31 December 2015. SFD is confident that the agreed results will be delivered within this timeframe. However, this will be considered as part of the wider mid-term review, currently scheduled to take place in June 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Since the start of Phase IV, DFID has commissioned a number of global research studies on the benefits of cash transfers, including cash-for-work schemes, and has published a Policy Paper titled “Evidence Paper on Cash Transfers”. This paper notes that there is extensive and potentially generalizable evidence that cash transfers, including cash-for-work schemes, have reduced the depth or severity of poverty. One of the strongest and most consistent findings regarding the impact of cash transfer programmes is their contribution to reducing food insecurity. Regardless of the form of transfer, households receiving transfers typically spend more and consume more food. / In 2012, DFID commissioned the Overseas Development Institute (ODI) to carry out research in five countries where DFID currently supports cash transfer programmes; this included Yemen. The final study, entitled Transforming Cash Transfers, presents the results of research on beneficiary and community perceptions of the Social Welfare Fund (SWF) cash transfer programme in Yemen. Though the report had no explicit findings or recommendations related to SFD, the report contained some interesting findings and recommendations related to cash transfers in general, some of which may be relevant to SFD’s support for labour-intensive works. (http://www.dfid.gov.uk/Documents/publications1/Transforming-Cash-Transfers-Yemen.pdf) / Despite this promising research, there remains a paucity of Yemen-specific evidence on the impact of cash transfers. The quality of design and implementation, local context and the presence and impact of complementary services and benefits are all important predictors of success and, to date, these have not been evaluated in Yemen. DFID continues to work with other donors to identify ways to close the research gap and understand how social transfer programmes, like this cash-for-work programme, perform in conflict-affected and fragile states like Yemen. / SFD has worked closely with experts from the University of Berkeley in California to carry out an impact evaluation of the LIWP. The final report was not available at the time of writing this annual review. The delay to the publication of this report has resulted in a lack of verifiable data with which DFID were able to assess the impact of the LIWP. The final report is due to be shared with donors in early 2013. / In 2012, SFD also contracted a consultant to help examine current targeting mechanisms and determine how SFD’s targeting mechanisms can be assessed during routine project monitoring and periodic evaluation. The targeting performance of SFD Phase IV is currently measured by a single indicator in the Results Framework which states that at least 50 per cent of SFD resources benefit the lowest three income deciles of the country. This overall objective has come into question as it does not accurately capture SFD’s institutional approach; SFD's methods and mechanisms of targeting vary depending on the programme. / The consultant’s draft report, provided in January 2013 (Quest #3833146), concluded that “SFD does not consider itself responsible for providing for the 'poorest of the poor' in terms of households and individuals. Rather it sees its ultimate target population as poor and deprived communities, as measured by the national poverty rate and a variety of socio-economic welfare and lack of access to basic services indicators. This mandate seems sensible given SFD’s core competencies.” Thus “a single indicator for monitoring the targeting performance of all SFD’s interventions is … not appropriate.” / DFID broadly supports the findings of this report and will work closely with SFD to review the recommendations in detail to determine those that can be implemented during the project period, providing support for their implementation as necessary and where feasible. This is particularly true for the recommendation which calls for more clarity on the beneficiaries for the CLD programme. Uptake of its key findings and recommendations will help to improve SFD’s targeting and assist in the review of SFD’s Result Framework and key indicators. / New data from the upcoming 2013/14 HBS and 2014 census will also be crucial in helping SFD to update its geographical targeting. The census data is vital to SFD because it provides an objective measure of deprivation down to the village level. SFD should seek to influence the design of the census to ensure it captures relevant data. The village deprivation index should be remodelled in good time before this so as to ensure viable indices for both urban and rural areas may be produced from the new census data. / Where an evaluation is planned what progress has been made? / In the past, SFD has carried out an Impact Evaluation every three years. The impact evaluation scheduled for 2011 was postponed due to the political crisis. SFD are currently developing their plans for the next impact evaluation. The scope and objectives of future evaluations and improvements to SFD’s monitoring system will be agreed as part of the mid-term review in June 2013. At that time, DFID will determine the extent to which we lend technical and other assistance for these efforts. / DFID intend to develop an evaluation strategy for this project and will include this as an annex to the next scheduled Annual Review for SFD Phase IV (Jan 2014). Among other things, this strategy will note: / The role DFID intends to play in the planning and implementation of SFD’s next independent impact evaluation. At the time of writing, DFID plans to scale back its involvement in the design and implementation of the impact evaluation and will provide individual-level input and technical assistance as requested by SFD, such as reviewing and commenting on questionnaires, other tools, and the evaluation methodology. / Steps DFID will take to develop a final evaluation for this project. This evaluation will focus on generating new and compelling evidence that would both help with DFID in its future programme-planning as well as benefit SFD. / Concrete steps on how DFID can work with SFD to strengthen their in-house capacity for regular monitoring and evaluation. This will include revised guidance and templates for narrative and financial reporting to DFID as well as ways in which SFD can improve data analysis.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Given the political transition and challenging economic and security situation in Yemen, the risk to our programme portfolio remains high. However, SFD has a good track record for delivery and has demonstrated that is it able to continue to work in some of the most challenging environments in Yemen despite a number of operating challenges. Identified risks related to SFD are deemed to be manageable.
Risk of funds not being used as intended / At the outset of the project, DFID assessed the fiduciary risk to be of low probability but high impact. The team has implemented a number of internal risk management and mitigation measures to ensure that our funds were used for their intended purposes. / Moving forward, DFID intends to carry out additional work to ensure that all investments in SFD are underpinned by a robust and detailed assessment and analysis of fiduciary and political risks. The US Agency for International Development (USAID) plan to scale up their work with SFD in 2013 and will be undertaking a thorough assessment of SFD’s procurement and financial systems and procedures. USAID has sought DFID’s input on the Terms of Reference (ToR) for this review and USAID has agreed to share the findings of the assessments with DFID and other interested donors. This assessment will help to deepen our understanding of the fiduciary risks related to our work with SFD and provide assurance on the robustness of SFD’s financial processes and controls. Due process in the appointment of the Managing Director will be critical for maintaining donor confidence in fiduciary management. DFID will consider the possibility of carrying-out a joint assessment of the national level context and risks of political influence in the governance of SFD. / We recognise that this will not address the challenges posed by remote monitoring. DFID are considering establishing a third party monitoring system to better monitor and evaluate our programmes and partner institutions, and to understand the risks to project implementation. DFID have also developed an internal Anti-Corruption and Counter Fraud Strategy that sets out key action points to help identify and reduce risks related to our investment in SFD IV. Some of these action points will be taken up by the end of March 2013; the feasibility for implementing other action points will be assessed. / 4.4 Climate and Environment Risk / SFD Phase IV is likely to have important environmental impacts and benefits. However, the small scale nature of these interventions are likely to limit any environmental impacts to the locality within which they are implemented. Examples of the likely impacts will be those associated with terrace rehabilitation, reduction in soil erosion, enhancing groundwater recharge, increasing vegetation cover, and reducing siltation in wadis and downstream water structures, as in the case of dams. For urban projects providing stone pavement the positive impacts may include reducing dust and subsequently air pollution, but there may be negative impacts related to the reduction of reducing groundwater recharge. In this case, to mitigate against the lack of ground water recharge, percolation pits will be installed. / All project activities are undertaken in accordance with SFD’s Environmental Management Plan (EMP) which has been agreed with all participating donor agencies. At project level the EMP provides guidance on analysing and managing environmental impacts (positive and negative). In some cases an Environmental Impact Assessment is carried out in accordance with Yemeni law. / Conflict over environmental resources, particularly land and water, are commonplace throughout Yemen. SFD have long practised inclusive and participatory approaches to project identification and design. They have a good track record of conflict mitigation at local levels. This programme will builds on this experience and ensure that any potential conflicts resulting from infrastructure interventions are minimised. / In 2013, DFID will explore the feasibility of conducting a climate and environment assessment to evaluate the net impact of SFD interventions on the environment, particularly road repair, agricultural rehabilitation and terracing.

5. Value for Money
5.1 Performance on VfM measures / No explicit VfM measures were agreed upon during the design of this project but SFD management demonstrates good VfM in various ways, for example by keeping overhead costs below six per cent, targeting funds toward high-impact activities and responding creatively to increased costs. It is recommended that following this Annual Review, SFD and DFID agree on VfM measures that will be assessed as part of the on-going work under Phase IV and measured under the next Annual Review, scheduled for January 2014. / The original economic appraisal assessed a wide range of tangible social and economic benefits, particularly in the fields of education, water and sanitation, rural roads and labour intensive works. Combined, SFD’s interventions in these areas amount to close to two-thirds of the total budget for Phase IV. Given the wide-ranging nature of the programme, and the fact that most of SFD’s projects are demand-driven and thus their ultimate aim was unknown at the start of Phase IV, a traditional ex-ante cost-benefit analysis of the whole programme was not possible. Instead, a separate analysis of the education, rural roads, labour intensive works and water aspects of the programme was carried out. / The original economic appraisal anticipated that these sectors would generate positive discounted net benefits. In total using a conservative estimate of benefits, interventions in these 4 sectors alone are expected to generate positive discounted net benefits of $90 million by the end of the project in December 2015. However, the overall benefits are expected to be much greater. / 5.2 Commercial Improvement and Value for Money / SFD uses established benchmarks to determine costs of suppliers and procurement specialists are responsible for ensuring cost controls are in place and that consultants are delivering the required level and quality of services contracted. / 5.3 Role of project partners / SFD were responsible for project delivery. Field offices are responsible for recruiting local technical experts or consultants to assist with the implementation of project activities, however all aspects of procurement and project management were managed by SFD field staff. / 5.4 Did the project represent Value for Money : Yes / This project represents value for money as we estimate that the majority of the project’s benefits were distributed to some of the poorest communities in Yemen.

6. Conditionality
6.1 Update on specific conditions / There are no conditions attached to this project.

7. Conclusions and actions
Summary of the programmes achieved targets, and comments: / Since the start of this project, DFID has provided £21.5 million to SFD to improve access to basic services, enhance economic opportunities and reduce vulnerability for the poor. / This programme faced a number of implementation challenges during the two years, including delays to programme start-up, a significant deterioration in the political and security situation, and exceptional economic decline leading to inflation, unemployment and increasing costs of commodities. / In the face of these challenges, SFD achieved impressive results and was able to meet the majority of their milestones. Cumulative results attributable to DFID include: / 20,768 pupils benefitting from SFD-supported schools / 5,487 households provided with new/improved drinking water sources / 1,282 households provided with new/improved sanitation facilities / 11,139 active borrowers accessing credit through micro-finance institutions / 325,104 days’ employment created under workfare assistance programme / Based on this performance, this project scored an A at output level (outputs met expectations) and an A at outcome level (outcome met expectations). DFID recommends the following action points and will work closely with SFD and other donors to help implement these. / Monitoring and evaluation / DFID will develop an evaluation strategy for this project and will include this as an annex to the next scheduled Annual Review for SFD Phase IV (Jan 2014). Among other things, this strategy will include concrete steps on how to strengthen SFD’s capacity for regular monitoring and evaluation as well as revised guidance and templates for narrative and financial reporting. / SFD will conduct a mid-term review of the programme with donors in June 2013. This will provide an opportunity to revise overly ambitious or modest targets and milestones, refine and update indicators and amend the results framework to ensure is remains fit-for-purpose and captures the impressive work SFD is undertaking. The revised RFW will be used to update and revise the DFID logframe. The outcomes of this mid-term review and recommended changes to the DFID logframe, as well as any other updates, will be captured in a summary review of this programme, planned for August 2013. / The following indicators and related milestones and targets, in particular, should be reviewed: / Rural road rehabilitation and construction / Number of teachers and other education professionals trained / Cubic metres of improved water storage / Number of households benefitting from community livelihood assets / DFID will seek to include, where and as possible, inputs from other advisors within DFID—particularly education, governance and wealth creation advisors—in the upcoming mid-term review. / During the mid-term review, SFD and its donors should consider if and how to measure transformation, behaviour change and broader changes in well-being in communities benefitting from SFD support. / Targeting / SFD and donors will review the findings and recommendations of the 2012 review of SFD’s targeting approaches to determine those that can be implemented during the project period, providing support for their implementation as necessary and where feasible. / To achieve more precise targeting at governorate level, SFD should explore the feasibility of using data from other sources. To this end, SFD should seek to influence the design of the 2014 census to ensure it captures relevant data, working with DFID as needed and where possible. / Coordination / Through its support for UN agencies, the Emergency Response Fund (ERF) and other humanitarian programmes in Yemen, DFID will encourage humanitarian actors to improve coordination and information sharing with SFD sector heads and uptake of best practices and lessons learned, to help bridge the divide between development and humanitarian actors in Yemen. / DFID will explore ways in which we can help encourage international NGOs with expertise in microfinance operations and other MFIs to establish operations in Yemen and will report against this action point in the 2013 Annual Review. / Other issues / Due process in the appointment of the Managing Director will be critical for maintaining donor confidence in fiduciary management and DFID will closely monitor the recruitment process. / SFD and DFID will work together to agree on VfM measures that will be assessed and measured during the next annual review, scheduled for January 2014. / In 2013, DFID will explore the feasibility of conducting a climate and environment assessment to evaluate the net impact of SFD interventions on the environment, particularly road repair, agricultural rehabilitation and terracing. / DFID will work with other donors, particularly USAID, to carry out additional work to ensure that all investments in SFD are underpinned by a robust and detailed assessment and analysis of fiduciary and political risks.

8. Review Process
This Annual Review was completed by the DFID Yemen Social Development Adviser (SDA) and Deputy Programme Manager as a combined desk-based and field review. The data for the review is based largely on narrative and financial reports provided by SFD as well as data and reports provided during the joint-donor reviews held in June 2012 in Amman, Jordan and November 2012 in Sana’a. Further supplementary emails containing information on progress were also reviewed. / In addition the DFID SDA held discussions with key SFD staff including the Deputy Managing Director; Head of Monitoring and Evaluation Unit; and Lead Donor Coordination Officer during a field mission to Sana'a in September 2012. DFID Yemen staff also held a round-table discussion with SFD beneficiaries, which was arranged by SFD staff. Participants consisted chiefly of local government representatives and staff from community-based organisations and NGOs. DFID staff also visited projects benefitting from SFD assistance in Sana’a which included a primary school, a primary healthcare facility and a vocational training centre.