## Sheet1
PROJECT NAME | DFID-Malawi Agricultural Programme 2011/12-14/15
IMPACT | Impact Indicator 1 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
Increased agricultural growth, food security and reduced hunger | Growth rate of Agricultural output (four year average) | Planned | 7.6% | >6% | >6% | >= 6% (2012-15 average)
Achieved
Source: IMF, NSO (national accounts)
| Impact Indicator 2 |  | Baseline 2009 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Poverty headcount using national poverty line | Planned | 52% | 50% | 48% | 45%
|  | Achieved |  | 50.2%
Source:Integrated Household Survey 3 (IHS3) ; future Welfare Monitoring Surveys (all from National Statistics Office)
| Impact Indicator 3 |  | Baseline (2010) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Under 5 malnutrition (measured by stunting) | Planned | 46% (43% for girls) | 45% | 40% | <= 40% (35% girls)
|  | Achieved |  | 46% (43% girls)
Source
Demographic health survey 2010 (baseline); future health surveys from NSO
OUTCOME | Outcome Indicator 1 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015) | Assumptions
| Incremental maize production attributed to FISP (tonnes) | Planned | 750k tons | > 750,000 | > 750,000 | > 750,000 | Political commitment to agriculture remains; with regard to FISP; no major drought flood or other natural disasters; Macro-economic stability and economic growth are maintained; political stability in the country with progressive democratic syste maintained; partnership principles between DFID and GoM are not broken; No major corruption scandals in GoM or NGOs we are supporting.
Increase in sustainable agricultural productivity and production (focused on crops and dairy) |  | Achieved |  | 837,000 tons
Source
MoAFS (crop estimates), Independent Evaluation Reports
| Outcome Indicator 2 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Average maize yields per hectare | Planned | 2 tons per hectare | 2.15 tons per hectare | 2.2 tons per hectare | 2.3 tons per hectare
|  | Achieved |  | 2 tons per hectare
Source:
MoAFS crop estimate reports
| Outcome Indicator 3 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Total Legume Production | Planned | 692 tonnes | 20% higher than baseline | 25% higher than baseline | 25% higher than baseline
|  | Achieved |  | 840k tons (21% higher than baseline)
Source:
MoAFS crop estimate reports
| Outcome Indicator 4 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Increase in domestic smallholder milk production per year | Planned | 0 | 10% | 15% | >=25% increase
|  | Achieved |  | awaiting data
Source:
Project monitoring reports and evaluations
| Outcome Indicator 5 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Average yield increases for additional land under conservation agriculture supported by this programme, compared to prior to the programme | Planned | 0 | >10% | >10% | >20%
|  | Achieved |  | awaiting data (progress reports)
Source
Project monitoring reports and evaluations
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
35 million
INPUTS (HR) | DFID (FTEs)
2 FTE p.a. (1 economic adviser on programme costs x 0.8 - plus support from other adviser; 1 programme management staff at 0.7 - plus support from deputy)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015) | Assumption
Increased uptake of high qualtiy seeds (legume and improved maize) and input market development | Proportion of smallholder maize cultivated area allocated to high yielding maize varieties (hybrid+ OPV) | Planned | 66% | 70% | 75% | >= 75% | Government remain committed to private sector development, Government and donors committed to the medium term plan for predictability of FISP
|  | Achieved |  | 70.4%
Source
MoAFS crop estimates
| Output Indicator 1.2 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Increase in improved maize and legume seed distributed by the private sector (subsidy and commercial) | Planned | 13652 tonnes maize 1,551 tonnes legume | 10% above baseline | 15% above baseline | 20% above baseline
|  | Achieved |  | 15807 tons (16% above baseline)
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (2010) | Milestone 1(2013) | Milestone 2 (2014) | Target (Average 2011-2015)
40% | Average number of households per year of programme provided with improved seeds through the Farm Input Subsidy Programme (and those attributable to DFID) [% of female headed households) | Planned | 1.6 million [25% of households in population are female headed] | 1.4 million (350,000 attributable to DFID) [at least 25% female headed] | 1.4 million (350,000) [at least 25% female headed household] | 1.4 million (350,000) [at least 25% female headed household by 2015]
|  | Achieved |  | 1.4 million (882,000 attributable to DFID) [25.5% female headed]
|  | Source |  |  |  |  | RISK RATING
|  |  | Logistics Unit Reports |  |  |  | medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
17
INPUTS (HR) | DFID (FTEs)
0.6 FTE (0.3 adviser + 0.3 programme management
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2010/11) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015) | Assumptions
Improved management and implementation of the Farm Input Subsidy Programme | Benefit to cost ratio of FISP programme | Planned | 1.18 (four year average of 2007-2010) | > 1.2 | > 1.2 | > 1.2 (four year average of 2011-2015) | Government and donors committed to the medium term plan to ensure predictability of FISP; economic crisis does not undermine implementation; Government able to meet commitments to reduce corruption
|  | Achieved |  | BCR = 1.5
Source
Independent Annual Evaluation Reports (Dorward et al 2012)
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Date when coupon distribution completed | Planned |  | end October | end October | end October
30% |  | Achieved |  | end October
|  | Source |  |  |  |  | RISK RATING
|  | Independent Annual Evaluation Reports; Logistics Unit Reports (2012) |  |  |  |  | high
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
2.5
INPUTS (HR) | DFID (FTEs)
0.8 FTE (0.4 adviser + 0.4 programme management
OUTPUT 3 | Output Indicator 1.1 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015) | Assumption
Increased uptake of conservation farming and other environmental sustainable farming practices | Number of additional farmers adopting conservation agriculture attributable to the DFID programme [% that are women] | Planned | 0 | 40,000 [at least 25 % female headed households] | 75,000 [ at least 25% female headed households] | 90,000 [ at least 25% female headed households]
|  | Achieved |  | information not yet available
Source
Project monitoring reports
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Additional trees planted (reforestation) using DFID fundings | Planned | 0 | 3miilion | 5million | 6 million
15% |  | Achieved |  | information not yet available
Source
Project monitoring reports
| Output Indicator 1.3 |  | Baseline (average 2006-2011) | Milestone 1(2013) | Milestone 2 (2014) | Target (2015) | RISK RATING
| Amount of additional land under conservation agriculture attributed to DFID intervention | Planned | 0 | information not yet available | 30,000 hectares | 35,000 hectares | medium
Achieved
Source
Project monitoring reports and evaluations
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
7.5
INPUTS (HR) | DFID (FTEs)
0.3 FTE (0.1.5 adviser + 0.1,5 programme management)
OUTPUT 4 | Output Indicator 1.1 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015) | Assumption
Increased number of successful dairy farmers | Number of new dairy farmers attributable to DFID funds [% that are women] | Planned | 0 | 500 [>50%] | 1000 [>50%] | 2000 [>50%] | Domestic dairy markets are competitive and increasing; NGOs have capacity to scale up effectively; Farmers
|  | Achieved |  | 92
Source
Project monitoring reports (SHMPA Progress Report Oct 2012)
| Output Indicator 1.2 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Number of well trained MBG, accessing artificial insemination and vet services and function milk storage facilities and linked to the market (dairy processors) through DFID funds, as % of total MBGs | Planned | 0 | 10% | 40% | >=50%
|  | Achieved |  | 0%
Source
Project monitoring reports (SHMPA Progress Report Oct 2012)
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline 2010 | Milestone 1(2013) | Milestone 2 (2014) | Target (2015)
| Number of existing farmers supported to increase their net income from dairy farming by at least 30% | Planned | 0 | 3000 | 5000 | 7000
15% |  | Achieved |  | information not yet available
|  | Source |  |  |  |  | RISK RATING
|  |  | Project monitoring reports |  |  |  | medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
7.5
INPUTS (HR) | DFID (FTEs)
0.3 FTE (0.1.5 adviser + 0.1,5 programme management)
Note on E59: Teddie Nakhumwa: >30% is beyond national average for female headed houseolds, which is 25%. Propose it should read at least 25% female headed household