Type of Review: Project Completion Review

Project Title: Goal: Provision of Effective and Sustainable Health, Nutrition, and Education Support to Vulnerable Communities in Sudan

Date started: 01/04/2007	Date review undertaken: May 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK provided £7,377,883 to GOAL for the provision of effective and sustainable health, nutrition and educational support to vulnerable communities in Sudan between April 2007 and January 2012.

What were the expected results?
The project aimed to achieve the following results at the end of the project: / 242,281 people with access to health facilities / 11,148 people with access to livelihoods activities / 21,620 Children supported with outpatient therapeutic feeding programme / 4,164 women empowered by the adult’s education (REFLECT)

What was the context in which UK support was provided?
Sudan is dominated by complex emergencies and humanitarian needs. High poverty rates and underdevelopment are both a cause and a consequence of conflict, the primary driver of humanitarian needs in the country. On-going violent conflict has resulted in multiple displacements, the need for a range of humanitarian assistance, and specific protection concerns. To date about 4.2 million people have been displaced in Darfur. / Acute malnutrition levels in Sudan average 16.4% countrywide, above the internationally accepted emergency threshold of 15%. In Darfur, 5.3% of children are severely acutely malnourished in Darfur, and one in three children across Sudan is stunted. Health outcomes are also poor. Approximately 24% of women giving birth do not have access to proper medical consultation or services. Access to clean water is also a serious concern in the conflict-affected areas, at times exposing women and girls to harassment and other forms of gender-based violence in their search for water / The project’s impact is to contribute to the reduction of poor health, food insecurity, poverty and inequality in vulnerable communities across three states in Sudan. The outcome is to increase access to quality, sustainable primary health care (PHC), nutrition and livelihoods support in Kutum and Abyei and educational support for vulnerable communities in Kassala. / During the grant implementation, the context changed and evolved significantly, impacting on GOAL programming. As a result, the project has been extended four times. This has allowed flexibility to continue responding to immediate humanitarian needs and the challenging operating environment. / Furthermore, this project developed from what was emergency response to early recovery, allowing for a more strategic approach to planning and capacity building of national staff and local counterparts. This enabled GOAL to support continued integration of sectoral approaches and consequently facilitated a longer term and more sustained focus on outcomes. Since grant implementation, the following was achieved with support from DFID:

## Section A: Detailed Output Scoring

Output 1: Provision of good quality primary health care (PHC) services with a particular focus on children < 5 and women of child bearing age in Abyei and Kutum
Output 1: A - Output met expectation / Final results: / Most indicators were achieved and some indicators exceeded the target. In general the population in both Kutum and Abyei benefited from a greater access to quality primary health services. / There was an increase in the number of women attending ANC2 over the last five years in Kutum. This achievement may have been influenced by GOAL’s effective promotion of services and sensitisation to reproductive health though an increasing number of women from outside the population catchment area may have also been accessing the clinics due to lack of facilities in their areas. In Abyei, targets were not achieved because other service providers, Medecins Sans Frontieres (MSF) and MoH in the area of operation in 2010 increased the coverage, thus there was a reduced utilization of the GOAL provided services in Abyei. / GOAL was able to engage more community members in training and strengthening of local capacities to predict, prepare for, respond to, mitigate and manage the health risks of communicable diseases and seasonal emergencies. Topics covered throughout the course of the grant included nutrition, communicable diseases, HIV and sanitation. Furthermore, during the grant there were outbreaks of meningitis, diphtheria, measles and Acute Watery Diarrhoea (AWD), but with responses initiated within 24 hours in collaboration with WHO and MoH, there was successful containment. / Some of the challenges for not achieving targets in Abyei includes conflict and insecurity; thus an increase in movement of populations and on positive side the opening of other clinic by MSF. / The table and graphics below show the actual target and achievements of each indicator. / Indicator 1.1: Annual number and percentage of all pregnant women within the catchment population attending Antenatal Care 2 / Kutum / 2009 2011 Jan 2012 Abyei / 2009 2011 Jan 2012 / Target 4,690 -80% 5,963- 100% 771 – 100% 1,487 – 60% 2,610 – 70% 652 – 100% / achievement 4,127 -70.4% 7,496 – 116% 771-100% 1,066 – 43% 1,197 – 36.5% *0 / * This is due to lack of access / The graphic below show comparable figures of pregnant women that attended ANC2 on yearly basis / Indicator 1.2: Percentage of diagnosis and treatment conforming to relevant MoH and WHO protocols / Kutum Abyei / Target >90% >90% / achievement 95.33% 73.50% / Indicator 1.3: Number of health staff and influential community members trained on health topics / Kutum Abyei / Target 289 63 / achievement 426 (204 female and 222 male) 230 (126 female and 104 male) / The figure below show number of staff trained on yearly basis
Impact Weighting (%): 45% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Improved access to quality nutritional support in Abyei and Kutum
Output 2: A - Output met expectation / Final Results: / All indicators achieved the target. / Between 2008 and 2011 Kutum achievements against indicators were in line with SPHERE Minimum Standards with Average Weight Gain (AWG), at 4/g/kg/day. In January 2012, there were significant improvements in most indicators from the baseline, however average length of stay and AWG were not in line with SPHERE. GOAL worked on improving the follow up of children that were not gaining weight as expected in their homes and advised mothers on child caring practices. In Abyei, all indicators reached SPHERE standards except the defaulter rate. This was because during the months of December 2011 and January 2012 the population began to move back North of the River Kiir where GOAL was not able to operate for security reasons. Therefore absentees were unable to be traced and consequently became defaulters. / In Kutum, 65.9% of mothers engaged with breastfeeding, exceeding the target of 15%. This was a considerable improvement from 1.5% achieved in 2009. In Abyei, 36.9% of mothers engaged with breastfeeding, exceeding the target which was set at 25%, as well as significantly improving on 12.5% which was achieved in 2009. This may have been influenced by breastfeeding being addressed as a main component in all nutritional programme activities in Kutum. In Abyei, appropriate breastfeeding practices were promoted to communities through Community Health Promoters (CHPs) and Community Nutrition Volunteers (CNVs) in the communities, as well as through clinic staff particularly Ante Natal Care (ANC), Outpatient Therapeutic Programme (OTP) and Growth Monitoring Programme (GMP) staff. / The table and graphics below show actual target and achievements of each indicator. / Indicator 2.1: Number of malnourished children admitted into GOAL OTP facilities and the cure rate, default rate, death rate, average length of stay and average weight gain for these children / Target SPHERE Minimum Standards met Achievements Abyei Achievements in Kutum / 2010[1] 2011 Jan 2012 2008 2011 Jan 2012 / Default rate <15% 24% 14.12% 22.6% 8.5% 8.2% 5.1% / Cure rate >75% 75% 82% 77.4% 81.4% 88.6% 82.1% / Death rate <10% 0% 0% 0% 1.7% 2.1% 3% / Average length of stay in OTP < 60days N/A 39.7 Days 34 Days N/A 42 Days 79 Days / Weight gain >4g/kg/day N/A 5.63g/kg/day 5g/kg/day N/A 4g/kg/day *3g/kg/day / *No clear evidence on why these difficulties in addressing the length of the average stay and averaged weight gained were not in line with SPHERE. But Goal claim to be working on improving their follow up of the children that are not gaining weight as expected in their homes and advice mothers on child care practises. / Indicator 2.2: Number of nutrition circles educating mothers of malnourished or at-risk children / Kutum Abyei / Target 10 nutrition circles, reaching 150 mothers every two month / achievement 10 Nutrition circles running, reaching 150 mothers every two months 10 circles running with 203 mothers admitted throughout January 2012 / Indicator 2.3: Percentage of mothers of children ages 0 to 6 months who report exclusive breastfeeding practices
Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[1] OTP started in Abyei in 2010, hence reporting is for 2010 and not 2008 as is the case with Kutum

Output 3: Increased agricultural productivity and practice of improved agricultural techniques in Abyei and Kutum among targeted community.
Output 3: B - Outputs moderately did not meet expectation / Final results: / Targets were not met. / In Kutum, 502 demonstration farm beneficiaries received training on improved agricultural techniques throughout the course of the grant, this is 63 beneficiaries under the target. In Abyei, 185 beneficiaries received training, this is 90 beneficiaries under the target. The main reason for not meeting the targets were floods that took place in Kutum in 2010, which directly affected Demonstration Farm (DF) infrastructure and destroyed seedlings and vegetables. This overall number of beneficiaries reached is a significant achievement, despite security issues in Abyei. / In Kutum, the target of beneficiaries (bag/home garden and demo farm beneficiaries and target farmers) with income from sale of products they have grown (80%) was reached (98.5%). Income generation activities included firewood, charcoal and poultry trading and a consumer shop. In Abyei, the target was not met due to displacement during Abyei conflict. / Between 2007 and 2008, 90% of target beneficiaries from the nutrition programme in Kutum reported an increase in crop production. In Abyei, 85% of beneficiaries reported an increase in crop production. In 2011, taking into consideration the floods that took place in Kutum in 2010, 81.9% of beneficiaries in Kutum reported a significant increase in their crop production and 92.4% of beneficiaries harvested through the home and bag garden initiative. In January, the total profit from sales for four demonstration farms was 11,373 Sudanese Pounds (SDG) per month and in April 2011 (upon graduation) the total profit reached 18,434 SDG/month. In Abyei, in 2011, 57% of demonstration farm beneficiaries and 60% of home garden beneficiaries reported a significant increase in their crop production. 2011 results were lower in Abyei due to GOAL not being able to access the demonstration farms and beneficiaries north of the river. / The table and graphics below show target and achievement of each indicator. / Indicator 3.1: Number of beneficiaries receiving training on improved agricultural techniques through GOAL demonstration farms / Indicator 3.2: Number of beneficiaries with training and access to increased household food production through home and bag gardens / Indicator 3.3: Number and percentage of targeted beneficiaries (bag/home garden and demo farm beneficiaries, and targeted farmers) with income from the sale of produce that they have grown / Kutum Abyei / Target >328, >80% of targeted 410 beneficiaries 120, 100% / achievement 404, 98.5% *16,13% / *In Abyei target was not met due to not being able to access the Demonstration Farm (DF) and beneficiaries north of the river. 24 beneficiaries from Juljok farm discontinued income generating activities (IGA) due to displacement during Abyei crisis.
Impact Weighting (%): 20% / Revised since last Annual Review? N. / Risk: High / Revised since last Annual Review? N

Output 4: Improved female literacy, numeracy, and income generation
Output 4: B - Outputs moderately did not meet expectation / Final results / Targets were not met but huge progress was made over the course of the grant / REFLECT (Regenerated Freirean Literacy through Empowering Community Techniques) is an innovative approach to adult learning and social change, which fuses the theories of Paulo Freire with the methodologies of Participatory Rural Appraisal (PRA). One of our strongest methods of building resilience in all of our programme areas is through the REFLECT programme. This two-year programme for women builds coping skills such as literacy and numeracy skills, health education and behaviour change strategies, and business skills that help women to see their families through difficult times. The curriculum in the programme is developed through a participatory approach, ensuring that topics covered are relevant to the specific context and reality of the participants. The women in this programme learn protective behaviours that help their families adjust to any shocks. These behaviours include income-generating activities that diversify a family’s income; micro-gardens to improve the nutritional status of their family, thus reducing susceptibility to illness; and enrolling their children in school. / REFLECT was only incorporated into the DFID grant in 2010 and since then GOAL engaged 2,676 REFLECT beneficiaries. This consisted of 2,132 beneficiaries from the Kassala programme, 290 from Kutum and 254 from Abyei. In Kurmuk, due to insecurity the new circles never commenced. / In Kassala, in the first half of 2011, 549 women graduated from 17 year two circles along with 77 men graduating from three year two male circles. In June, 447 women graduated from 12 year one circles and moved on to year two of the programme. Furthermore, an additional 20 new REFLECT circles were opened. / In Abyei, 109 were year two participants who were intended to graduate in July 2011. However, due to the conflict in Abyei in May 2011, circles were inactive until August, delaying the graduation of participants. / In Kutum, there are 10 circles that are expected to graduate in October 2013, assuming that GOAL will secure additional funding to continue support these circles. / In Kurmuk, activities were suspended due to insecurity, causing mass population displacement into South Sudan and Ethiopia. / A key target for the REFLECT programme was for over 80% of participants to gain knowledge on key health and nutrition messages. The graphic below demonstrates the progress made over the course of the grant, with Abyei, Kutum and Kassala all achieving over 80% for this indicator. / Across all programme sites (except Kutum), beneficiaries were trained and supported in Income Generating Activities (IGA). For Kutum, only graduates from the livelihoods demonstration farm six- month practical vegetable cultivation course were trained in IGA as the REFLECT circles had not reached the end of their year two programme. / An impact assessment of the REFLECT programme in Kassala concluded that “participants learned literacy and numeracy skills as well as health-related and income-generating information to some extent applied the learning in their lives. The participants’ experience in the programme was overwhelmingly positive. However, the lasting impact was not found to be significant in the majority of cases” / The table and graphics below show the actual target and achievement of each indicator. / Indicator 4.1: Number of women attending REFLECT circles (GOAL + SOLO) / Kassala Kutum Kurmuk Abyei / Target 2322 250 1217 375 / achievement 2132 (92%) 290 (116%) 0 (0%) 254 (68%) / Indicator 4.2: Number and percentage of GOAL REFLECT participants with knowledge of key health / nutrition messages / Kassala Kutum Kurmuk Abyei / Target >1858 and >80% >200 and >80% >494 and >80% >300 and >80% / achievement 2131 (95%) 290 and 95% 0 254 and 87% / Indicator 4.3: Number of beneficiaries trained and supported in conducting income generating activities (REFLECT & demonstration farms in Kutum) / Kassala Kutum Kurmuk Abyei / Target 626 387 617 125 / achievement 626 (100%) 232 (60%) 0 (0%) 109 (87%)
Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the log frame been changed since the last review? No / 1.2 Final Output score and description: A – Outputs met expectations
Direct feedback from beneficiaries: / The project beneficiaries include IDPs, refugees, host communities, returnees and nomadic communities in Kurmuk, Abyei, Kutum and Kassala. / We have not collected any direct feedback for this PCR, however, through the project life DFID staff have visited Kassala and collected some feedback from the beneficiaries and this is reflected in this review. Furthermore, GOAL commissioned an impact assessment of the REFLECT programme which also included feedback from beneficiaries and we used some of the information from the final report.
1.4 Overall Outcome score and description: A - Outcome met expectation / The project outcome was to increase access to quality, sustainable primary health care, nutrition and livelihoods programmes in Kutum and Abyei and educational support for vulnerable communities in Abyei, Kutum, Kurmuk and Kassala. / The main results achieved are shown in the table below. Most indicators achieved 90% or above apart from adult education, mainly because the activities in Kurmuk was suspended due to insecurity which resulted in mass population displacements into South Sudan and Ethiopia. / Target Achieved / People with access to health facilities 242,281 223,488 (93%) / People with access to livelihoods activities 11,148 9,983 (90%) / Children supported with outpatient therapeutic feeding programme 21,620 20,948 (97%) / Women will be empowered by the adult’s education (REFLECT) 4,164 2,476 (65%) / The key challenges during implementation were: / Security / The operational areas were among the most politically fragile in the country. The security context was very fluid and required ongoing close monitoring as well as an ability to respond rapidly to significant changes in the environment. Such changes included periods of remote management. / Continuous conflict in Abyei and Kutum represented one of the key challenges to delivery of assistance in these areas. GOAL had to adapt different methods of management. For example, in Abyei GOAL relocated to AGOK (35km south of Abyei town) in order to continue support the community affected by conflict. / In 2009, two GOAL international staff were abducted in Kutum. This affected the programme implementation leading to delays and fewer field supervision visits. / Staff capacity / Throughout the project life, GOAL experienced difficulties in recruiting senior management staff due to the perceived insecurity and hardship of the operation’s locations. / To mitigate this, GOAL supported the capacity building of communities by providing regular trainings, aimed at improving the key skills such as traditional birth attendants, community based nutrition workers, clinical staff. / Community acceptance / Given the culture and beliefs, it was difficult to motivate men to work, especially in Abyei where women traditionally do the majority of work. GOAL worked with schools to introduce agriculture into the curriculum. This intervention aimed to motivate boys to work on the land from a young age, in the hope that this habit which would continue to adulthood. / 1.5 Impact and Sustainability / The project contributed to some extent towards achieving the impact – reduced mortality, malnutrition, poverty and inequality amongst vulnerable communities. / Evidence: between 2007 and 2011, the Global Acute Malnutrition (GAM) rate in Kutum and Abyei significantly reduced. GAM in Kutum reduced from 21.5 in 2007 to 16.6 in 2011. In Abyei, the 2007 result was 21.0, reducing to 16.4 in 2011. Severe Acute Malnutrition (SAM) also reduced in Abyei from 1.6 in 2007 to 1.4 in 2011. / To ensure sustainability GOAL worked very closely with the MoH by building capacity of local staff with on-the-job training. Furthermore, GOAL also supported long term training of community members who were eligible to pursue relevant health protection qualifications. / On livelihoods interventions, GOAL have distributed tools, seeds and trained local farmers on various methodologies including implementation of bag and home gardens. To increase sustainability GOAL provided seeds through seed fairs. / Goal has also worked closely with national NGOs and Community Based Organisations (CBOs), providing a strong capacity building. / Despite efforts to ensure long term sustainability in the Sudan context where conflict is frequent. There is no guarantee that project achievements will remain in coming years.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / Yes. / 2.2 Key cost drivers / This project had several extensions, therefore there has been an increase in the initial project cost. The extensions were granted to enable the project to continue operating in a changing context. For example, in 2009 following expulsion of 13 NGOs there were gaps in health coverage of rural areas: 14% of healthcare and 30% of all therapeutic feeding capacity were affected leaving approximately 650,000 people without access to the primary health care services. GOAL had to readjust to meet the needs of an increased population. / The main cost drivers were i) staff cost, this is acceptable given that the project was operating in insecure places and 2) materials and suppliers. / 2.3 Was the project completed within the expected timescale: Y / As mentioned above the project had several extensions, but it was completed within agreed timescale of the last extension.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / There were no changes in evidence during the life of the project: humanitarian needs remained high. / However, some of the risks identified during the design of the project materialised. For example, conflict escalated in some areas, Abyei and Kurmuk, and impacted on the delivery of project results. / Abyei became a focal point of increasing tension and insecurity, particularly from the latter half of 2008 onwards. GOAL programmes were suspended to the North of Abyei and in Abyei town as a result of heightened tension, culminating in heavy fighting between Sudanese Armed Forces (SAF) and the Sudanese Peoples Liberation Army (SPLA) Abyei town was evacuated by all civilians and INGOs and the majority of civilians moved south of the river Kiir. / In Kutum, since elections in April 2010 and with the collapse of the peace process in Doha, the security situation deteriorated considerably and fighting resumed with factions previously involved in the peace process. There were also inter-communal clashes in South Darfur which resulted in a high number of casualties and displacements. / It is quite challenging to monitor change in evidence due to the limitations of relying on project implementers’ reporting their own operational environment and results and performance without our own ability to verify these. While Goal reporting appears robust and the methodology is sound there is always a risk on relying on agencies’ own monitoring. DFID visited Goal in Kassala but in recent years (since 2010) has not been able to visit the Goal programme in Darfur due to security restrictions. Additionally, Goal themselves have had to rely heavily on remote monitoring and programmes implemented via trained national staff. While they are confident in their approach this still represents an accountability risk. / 3.2 Set out what plans are in place for an evaluation. / No evaluation was planned or undertaken for this programme. However, DFID is currently planning an evaluation of all DFID Sudan bilateral support to NGOs, including this project. The recommendations from the evaluation will inform any future bilateral humanitarian programming via INGOs. / This is in line with the Internal Audit recommendation “Independent verification should be sought to the maximum extent possible which may include making use of External Auditors’ reports on the Partners’ financial accounts. Items in Programme Budget supplied by partners can be cross-checked from Audited Financial Accounts for e.g. Project Expenditures, Audit Fees, and so on. yearly totals of payments made to partners should be reconciled against those figures in the audited accounts.”

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? N / 4.2 Risk funds not used for purposes intended / The project provided regular quarterly financial reports and annual audited statements supported by certificate from the Auditors on a DFID specific grant. The programme team scrutinised the reports to ensure that the funds were used for the intended purpose. / 4.3 Climate and Environment Impact / This project was approved before the introduction of new Business Case and climate smart guidance. However the Environmental Screening Note did identify climate change and environmental issues which needed to be addressed during the life of the project. These included issues around: / sustainability and availability of water supply / solid waste management issues related to health component; and / sanitation issues / Unfortunately however, there is insufficient evidence that all issues were fully addressed or systematically monitored during the project life. / There is evidence that community health training did cover waste management and sanitation but not clear whether the negative impact of proper sanitation and waste management negatively impacted on heath of communities. The REFLECT literacy programme did cover health and WASH education and behaviour change strategies related to the top two issues. / There is evidence that the GOAL integrated management approach did develop good coordination and linkages between sanitation and health; and reproductive health clinic facilities did provide latrines and bathrooms / However the lack of clear evidence of any hydrogeological work and systematic examination of the availability and usage of water means that we cannot be sure of the long term sustainable impact of the GOAL interventions on water. There is however evidence that GOAL coordinated their WASH activities with Sudan Water and Environment Sanitation (WES); other donors and UNICEF. This is not well documented through monitoring reports / GOAL recognised that approaches to early recovery which was the main goal of the project requires more focus on long term sustainability

5. Value for Money
5.1 Performance on VfM measures / The project was approved before the introduction of the business case thus no VfM measures were initially agreed. / 5.2 Commercial Improvement and Value for Money / This project was approved before the new business case format, therefore no commercial assessment was undertaken. / The project was managed through an Accountable Grant to a non-profit organisation - GOAL. During the project implementation GOAL applied their procurement rules and regulations. / 5.3 Role of project partners / DFID main partner is GOAL. GOAL has been a valuable partner. Furthermore, GOAL is member of the INGO Steering Committee in Sudan and has provided a lot of informal feedback to DFID on humanitarian issues in Blue Nile, Southern Kordofan, Darfur, Abyei and the East over the past years. This has been a considerable benefit of DFID’s strategic partnership with GOAL. / 5.4 Did the project represent Value for Money : Yes, despite conflict challenges, the project has delivered most of the results. / The main project design did not include indicators to measure Value for Money, and this was not a criterion in project approval. Given the challenges in the external context (security—conflict and banditry--, bureaucratic restrictions), we believe that the project has done well in providing services for conflict-affected people who otherwise would not have had access to healthcare or sanitation. Services were provided mainly according to SPHERE standards. The good standard of their services and their adherence to coordination with the other actors in the field has been mentioned by their partners in Medair’s departure event. / While VfM was not a consideration in approval of this project, there is now some work taking place within the humanitarian cadre at a global level on VfM measures in humanitarian programmes, comparing different organisations in the same country within a similar operating environment, and comparing organisations in different country contexts undertaking similar interventions and allowing for logistics and other transportation costs. It is expected that by the time of establishing business cases for new project partners we will be able to use some of these VfM calculations in partner selection. / With a good conflict analysis at the outset of the project some of the risks in the external context that lead to underperformance on objectives (e.g. security disruptions to project) might be better able to be mitigated in future projects, in some cases. Project outputs and outcomes might then be more sustainable and represent better value for money.

6. Conditionality
6.1 Update on specific conditions / The UK’s conditionality only applies to Financial Aid directly given to a partner government

7. Conclusions
Overall the project met DFID expectations, achieved good results and contributed towards the impact of reduced mortality, malnutrition, poverty and inequality amongst vulnerable communities. / The operating environment in Sudan is very volatile, with continuous emerging conflict and mass movements of people. However, GOAL has done the best they could in order to minimise the impact of disruption and has continued to provide some kind of support, including reallocating to places where people moved to, remote management and training of local communities. / Nonetheless, more could be done in the future on conflict-sensitive analysis prior to programming, and building more resilience to conflict and other shocks into programme design. / The key lessons learnt from this project are: / GOAL invested in developing partnerships with local organisations in order to ensure a smooth exit transition. They also used these partnerships to promote greater coordination, cooperation and networking. This was important where the operating context was fragile. With restrictions to operating, GOAL used these partnerships to ensure continuous delivery of support. / Through consultation and focus groups, GOAL learnt that the community would better use reproductive health centres for clinic based deliveries if there was more privacy, separate latrines, washing facilities and sound-proof doors. To address this, GOAL constructed a delivery room separated from the main clinic facilities with a latrine and bathroom. / The livelihoods intervention focused on the distribution of tools, seeds, and trainings to local farmers, as well as the running of demonstration farms (DF), distribution of inputs and training required for the implementation of bag and home gardens for vulnerable households such as IDPs, nutrition and REFLECT beneficiaries. The demonstration farms were sustainable in so far as the beneficiaries were taught techniques that they could use after their involvement in the programme, GOAL realised that some beneficiaries had limited ability to put this training into action due to limited access to land. Furthermore, many of the demonstration farm beneficiaries did not plan ahead sufficiently to set aside provisions to enable the sustainability of the skills that they had learnt, even if they did have access to land. Though the home gardens were designed to be replicable in all settings, some beneficiaries ceased to undertake further vegetable cultivation following the initial harvest of the original plants grown from the seeds distributed by Goal without harvesting seeds or ploughing back savings/income into new improved seeds. / The REFLECT assessment shows that participants learnt literacy, numeracy and health related and income –generating information and applied it only to some extent. While the project targets are met, further consideration should be given to whether the intended objective is compatible with the social context. / DFID project management was weak. The projects have different logframes reflecting on annual reviews assessing different indicators. There was a lack of field monitoring visits so there is no direct feedback from beneficiaries. Project risks should have been adjusted to reflect change in the operating environment. Some of these aspects have been pointed out in DFID internal audit report and a plan is in place to ensure that future support to NGOs is better managed. / This is in line with the Internal Audit recommendation “Programme staff should ensure that Partners complete them in due diligence. To be able to do so in collaboration with Partners, programme staff should thoroughly understand the project nature. / Programme Staff should ensure that Baseline data is generated and input into Log Frames in such a way that subsequent comparison against progress is possible and accurate. Any revision to the figures in the Log Frame after initial approval should be supported by documentary evidences.”

8. Review Process
The review and scoring was completed by the DFID Sudan Humanitarian Team