ANNUAL REVIEW – SOMALILAND ELECTION PROGRAMME

Implemented by: International Republican Institute, Interpeace and Progressio; Saferworld; Oxfam; and the Committee for Humanitarian Dialogue

December 2012

Type of Review: Annual Review

Project Title: Somaliland Election Programme – International Republican Institute (IRI) with Interpeace and Progressio

Date started:	01/11/2012	Date review undertaken: 19/12/12

## Introduction and Context

What support is the UK providing?
DFID provided a £1,020,800 grant to the International Republican Institute (IRI) to support the effective political and electoral participation of political associations, political parties, local elected councillors and youth and women groups. The grant also aims to support the training of National Electoral Commission (NEC) officials and fund an International Election Observation (IEO) mission to monitor the November 28 local council elections. Through this grant, IRI issued a £375,000 sub-grant to Interpeace to carry out the training of NEC officials and a £65,000 sub-grant to Progressio to conduct an International Election Observation (IEO) mission.

What are the expected results?
The intended outcome of this intervention is: democracy strengthened in Somaliland. / The expected outputs are as follows: / 225 political association representatives (35 women) trained on electoral procedures; / 300 (50 women) representatives from the political associations trained on political party development and organization as well as campaign skills; / Increased participation of women and youth in elections campaigns - 150 (90 women) targeted with 3 intensive one week-long youth and women campaign schools on youth and women outreach skills, campaign message development; / Party agent training - 2750 (500 women) party poll agents trained; / How will we determine whether the expected results have been achieved? / The programme will be monitored by the implementing partners throughout the programme period, and there will be an Annual review by the end of December 2012. An independent evaluation will take place at the end of the programme, the results of which will be used to guide and consider the nature of further funding to elections in Somaliland.

What is the context in which UK support is provided?
DFID support for this programme was provided ahead of Somaliland’s November 28 local council elections. The results of the elections will determine Somaliland’s three official political parties for the next ten years. Fifteen new political associations applied to take part in elections and a Registration and Approval Committee (RAC) was established by the Somaliland government in the latter part of 2011 to manage the political party oversight process. Its task was to register, vet and approve newly established political associations and determine their eligibility to take part in the local council elections. The proliferation of new political organizations and a new and fluid political landscape presented a potential risk to the credibility of the election process. IRI’s DFID funded programme sought to address these risks by building the capacity of Somaliland’s political parties/associations to effectively compete in and monitor Somaliland’s local council elections. IRI’s programme also sought to strengthen RAC’s ability to manage the party registration and determination process. Finally, IRI trained women and youth candidates to effectively run in local council elections. Given that local council elections will result in a number of new local government officials taking office, IRI’s DFID programme includes a local governance initiative focused on equipping new councillors with the skills and resources needed to effectively meet their constituent needs. / The current leadership of the Somaliland National Electoral Commission (NEC) was formed in October 2009, making NEC a relatively new institution. NEC’s mandate of delivering successful local council elections took place in a context made more difficult by the large number of new political organizations contesting the elections and the existence of a new and complex Proportional Representation Open List Voting System. The DFID funded Interpeace programme sought to strengthen the core institutional capacity of NEC through a comprehensive training programme that built their capacity to effectively manage the 2012 local council elections. / Given the complexity of the electoral process and the number of new actors and oversight bodies, IRI - using DFID funds - supported an International Election Observation (IEO) mission carried out by Progressio.
A key contextual issue affecting support to these elections was a highly constrained time frame. It was generally expected that the elections would be held in the spring of 2013. In September 2012 it was announced that they would be held on 28th November 2012. This significantly shortened the amount of time available for the implementation of UK- and other donor-supported programmes, and resulted in the revision of previously discussed, and at times already agreed, plans, and often less support being provided than might otherwise have been the case.

## Section A: Detailed Output Scoring

Output 1.1: Election stakeholders are provided training on electoral procedures
Output 1.1 score and performance description: A / IRI’s sponsorship of RAC town halls about Law 14, Article 6, the party Code of Conduct and the party ranking process was the only informative initiative on these electoral provisions provided in all of Somaliland. Through the RAC town halls, 394 community and political leaders were informed about these important electoral processes. RAC had no contingency plans to educate constituents on the Code of Conduct agreement and without IRI’s intervention this information would not have been disseminated to stakeholders around the country. / Additionally, over the course of multiple trainings for party and association leadership, IRI highlighted the importance of the political party Code of Conduct and provided an overview of election laws related to parties. IRI’s campaign schools also provided pertinent information about electoral procedures to candidates. These activities are described further under output 1.2.
Progress against expected results: / RAC Strategic Planning Sessions / IRI successfully brought RAC councillors together to engage in strategic planning and goal setting for the organization. Progress against this result took place in the following format: / •IRI facilitated a strategic planning session for the Registration and Approval Commission (RAC) on September 25, with a follow up session on September 30, 2012. Six RAC commissioners and one staff member attended the first session and four commissioners attended the second session. These workshops were facilitated by the consultant, an experienced political party consultant from the United States brought in by IRI specifically for this purpose. On September 25, the consultant, worked with RAC commissioners to identify the organization’s mission, mandate, and long and short-term goals. The consultant also led RAC representatives in drafting strategies for strengthening the organization’s relationship with political parties and associations. On September 30, The consultant and RAC reviewed the mission, goals and strategic plan developed in the previous session and refined and finalized the documents. / RAC Town Hall Sessions / IRI also organized a series of town hall sessions to bring RAC commissioners into contact with political/association representatives and the general public in order to explain Law 14, Article 6 to all election stakeholders. These sessions played a critical role in ensuring election stakeholders understood and agreed with the ranking system that would be used to determine the three new official political parties. / IRI coordinated six town hall sessions. Town hall events were held in Burao on November 17, Berbera on November 17, Erigavo on November 20, Borama on November 21, Las Anood on November 22 and Hargeisa on November 25. Over 300 individuals attended the six town hall events, including political party/associations leadership, traditional elders, civil society representatives, women and youth activists, and regional governors and police commissioners. During the town hall sessions, RAC commissioners introduced the Commission and provided participants with an overview of Law 14, Article 6, explaining in detail the ranking system that would determine the winning three political parties. Participants engaged in fruitful discussion with commissioners, and at the close of each session participants demonstrated an understanding and acceptance of the ranking process laid out in Article 6. / Recommendations: / In future elections work, more energy should be dedicated to the dissemination of the political party Code of Conduct or any other electoral regulations agreed to by parties. NEC and CSO civic education efforts did not highlight the party Code of Conduct, and parties did not share the content or importance of the Code with their members or supporters. While the IRI supported RAC town halls and party trainings did contribute to closing the gap in information, time and resource constraints prevented IRI from disseminating information about these electoral provisions even further. / Impact Weighting (30%): / Revised since last Annual Review? / Risk: Low / Revised since last Annual Review? N/A

Output 1.2: Political parties and political associations receive training on internal organization and campaign skills

Output 1.2 score and performance description: A / IRI designed and implemented a series of capacity building trainings for party representatives. The trainings were designed to address skill deficiencies described to IRI by party leaders and to train party coordinators on the general skills and knowledge needed by political organizations to compete in elections. IRI’s workshops were organized by theme and covered a variety of skill areas, described more below. The majority of training participants were party regional and district leaders responsible for managing party operations in their areas. Trainings were offered in Hargeisa and Burao and reached a total of 224 participants, 214 of which were political party representatives and ten of which were NEC or RAC officials. / IRI also provided targeted training to party women and youth candidates. As traditionally marginalized groups in Somaliland, these trainings played a critical role in giving women and youth candidates the ability to reach out to voters, communicate their issue stances and gain constituent support. IRI worked with local Somaliland organizations, the Somaliland National Youth Organization (SONYO) and the NAGAAD women’s organization to implement campaign schools for youth and women candidates. IRI’s women and youth trainings reached 105 youth candidates and 96 women candidates. / Progress against expected results: / Political Party/Association Training / IRI held a series of training sessions for representatives of Somaliland’s political parties and political associations. IRI staff and guest consultants trained party representatives on a number of pre-election skills and topics, including political party structure, party roles and responsibilities, issue based platform development, Get Out the Vote (GOTV) techniques and other topics. Representatives from RAC also attended and contributed to the training sessions. All sessions had representatives from six (and often all seven) of Somaliland’s political parties and political associations. In total, six trainings were held, reaching 224 (F=45; M=179) political party/association representatives. Progress against expected results took place in the following format: / •On September 22, 2012 IRI launched its political party and associations training programme. The workshop took place in Hargeisa and thirty-four participants (F=3; M=31), including representatives from NEC, RAC and 6 political parties/associations (KULMIYE, UCID, WADANI, RAYS, UMADDA and XAQSOOR) were in attendance. During the session, IRI trained attendees on voter targeting, message development and opponent analysis. Participants also reviewed and discussed the key phases of the electoral period, and reviewed the rights and responsibilities of political parties. / •IRI held a second political party and associations training session in Hargeisa on September 29, 2012. Thirty-four (F=10; M=24) leaders from six political parties and associations (KULMIYE, UCID, WADANI, RAYS, UMADDA and XAQSOOR) attended. IRI’s visiting expert, US based political party consultant, trained participants on political party organization and structure, characteristics of a democratic party, party support to candidates and the responsibilities of various party office holders. / •IRI held a political party and associations training in Hargeisa on October 6, 2012. Thirty-nine (F=13; M=26) representatives of all seven political parties/associations participated. IRI trained participants on how to identify topics that are important to the public and develop platforms around those topics. IRI’s polling consultant, from UK based polling firm Opinion Research Business (ORB), gave a presentation on the use of public opinion research for platform development and led participants in reviewing key issue findings from IRI’s survey of Somaliland public opinion conducted (under a separate programme) in June 2012. / •On October 13, 2012 IRI held a political party and associations training in Hargeisa. Participants were trained on field operations strategies and GOTV techniques. Forty-three people (F=15; M=28) representing all seven political parties and associations attended. / •IRI held a two-day political party and associations training in Burao from October 20-21. During the session, political party/association representatives were trained on topics such as managing field operations, implementing GOTV Strategies, engaging in message development and understanding Somaliland’s electoral laws/code of conduct The training was attended by 39 participants (F=1; M=38), comprised of regional and district coordinators and candidates from the seven political parties/associations from Togdheer and Sool Regions. / •IRI held a two-day political party and associations training in Burao from October 23-24. The training was attended by 35 participants (F=3; M=32), representing district coordinators, candidates and members of all seven political political/associations from Sanaag Region. Participants were trained in GOTV techniques, message targeting and the Code of Conduct agreement. / Women and Youth Campaign Training / In order to promote women and youth participation in local council elections, IRI partnered with local organizations the Somaliland National Youth Umbrella Organization (SONYO) and NAGAAD, a women’s organization, to conduct campaign schools for youth and women candidates. In total, six campaign schools were held, reaching 105 youth candidates and 96 women candidates. Progress against expected result took stock place in the following format: / •From October 16-18, 2012 IRI conducted a three day campaign school Training of Trainers (TOT) event for SONYO and NAGAAD facilitators. The session was attended by 17 participants (F=4, M=13) who were trained on campaign school curriculum, which they in turn utilized as trainers of the women and youth campaign schools. The workshop focused on the “T4 Campaign System”, which trained participants on the campaign principles of “Target, Touch, Track and Turnout”. Topics covered through the T4 curriculum included campaign management techniques, effective message development, voter outreach and GOTV strategies, field operations planning, door to door campaigning, public speaking skills, volunteer recruitment and more. / •From October 24-25, 2012 SONYO conducted three campaign school sessions that reached a total of 105 youth candidates (under the age of 35). Two campaign schools took place in Hargeisa and one was held in Burao. IRI trained facilitators led participants through the “T4 Campaign System” curriculum, covering topics such as campaign management, message development, GOTV strategies and field operations, campaign planning, door to door campaigning, public speaking, and volunteer recruitment. The classes also reviewed election rules and procedures and educated participants on the election code of conduct. / The Burao session was featured in the following news article: http://hadhwanaagmedia.info/detail.aspx?id=80113) / •From October 28-30, 2012 NAGAAD conducted three campaign school sessions that reached 96 women candidates and the female campaign managers of women candidates. Two sessions took place in Burao and one in Hargeisa. Participants were trained on the “T4 Campaign System” (see above) and were also trained on electoral rules and procedures, the electoral legal framework and the electoral code of conduct. / Recommendations: / Given time constraints, such as having less than two months from the start of IRI’s DFID grant to the start of the campaign period, IRI had to prioritize the topics covered in its trainings and therefore maintained a focus on campaign related issues. Time constraints also led IRI to hold the majority of trainings in Hargeisa, a central location, and Burao, a location which allowed trainings to reach participants from Somaliland’s eastern regions. IRI recommends that future political party programming begin much earlier, such as several months before elections. This will allow trainings to be held countrywide and to cover more topics, such as much needed internal party organization trainings. This would also allow for one-on-one party trainings and consultations that are specifically targeted to individual party needs. / Impact Weighting (18.43%): / Revised since last Annual Review? / Risk: Low / Revised since last Annual Review? N/A
Output 1.3: Political party poll agents are trained on their roles and responsibilities
Output 1.3 score and performance description: A++ / IRI initially proposed to train up to 3000 political party/association polling agents. However, during consultations with party and association leadership in Hargeisa, IRI was asked to train as many agents as possible. With parties agreeing to fund the transportation of additional agents to IRI’s training sessions, IRI and APD were able to expand the number of workshops held and trained 9,374 political party and association agents, reaching every electoral district. Each participant received a copy of the IRI-produced and published ‘Polling Agent Manual’. Facilitators trained participants on each stage of Election Day, from the opening procedures at polling stations early in the morning to the transportation of ballot boxes to district tabulation centres at night.
Progress against expected results: / Political Party/Association Poll Agent Training / Although IRI originally planned to approximately 3000 agents, IRI successfully expanded the number of workshops held and trained 9,374 party agents to monitor Somaliland’s local council elections. Progress against this result was achieved in the following manner. / IRI contracted with a local organization, the Academy for Peace and Development (APD), to coordinate the roll out of party agent training sessions. Training was conducted through a Training of Trainers (TOT) method. IRI trained 12 regional level APD trainers, and these regional trainers trained 170 district level trainers, on topics including the rights and duties of polling agents; the role of polling station staff; polling station procedures; and the opening, voting, closing, counting and results tabulation processes. These district level trainers conducted trainings in all 21 electoral districts. In total, 9,374 party agents were trained by IRI/APD ahead of Election Day. / IRI expert programme staff drafted a Political Party/Association ‘Polling Agents Manual’ to be used during the training. The manual was translated from English into Somali and 13,500 manuals were printed. The manuals were utilized in all party poll agent training sessions and were provided to all party agents that attended IRI’s poll agent training sessions. Manuals were utilized and referenced by poll agents on Election Day. / Somaliland Pre-Election Watch / IRI published a ‘Somaliland Pre-Election Watch’ article on its website and distributed the write-up to relevant press outlets. / IRI’s ‘Somaliland Pre-Election Watch’ was referenced in the press by the Heritage Foundation and Foreign Policy. / Recommendations: / Given the political wrangling around the party agent per diem issue, it was a significant achievement to be able to train, ultimately, over 9000 party agents. Parties ultimately deployed agents without the external payment of a per diem stipend, a positive sign for party development, demonstrating they recognise the importance of deploying party agents to monitor the polling process. Learning from the success of IRI’s party poll agent trainings, IRI recommends that future party agent initiatives prioritize holding sessions in as many locations, with as much local reach, as possible. IRI and APD offered party poll agent training sessions in all 21 electoral districts. This allowed more agents to attend the trainings and was one factor that contributed to large event turnout. / Impact Weighting (30%): / Revised since last Annual Review? / Risk: Low / Revised since last Annual Review? N/A
Output 2.1: Newly elected local councillors participate in democratic governance orientation programme and citizen groups identify priority issues
Output 2.1 score and performance description: / Not applicable
Progress against expected results: / Activities under this output will be conducted in the second phase of IRI’s programming and will begin after the November 28 local council elections. / Recommendations: / Not applicable / Impact Weighting (14.69%): / Revised since last Annual Review? / Risk: Low / Revised since last Annual Review? N/A

Output 3.1: Assessment of the current state of democracy is undertaken and a comprehensive long-term strategy for future democracy assistance to Somaliland is developed.
Output 3.1 score and performance description: / Not applicable
Progress against expected results: / Activities under this output will be conducted in the second phase of IRI’s programming and will begin after the November 28 local council elections. / Recommendations: / Not applicable / Impact Weighting (4.9%): / Revised since last Annual Review? / Risk: Low / Revised since last Annual Review? N/A
Output 4.1: Interpeace: NEC staff trained for Election Day
Output 4.1 score and performance description: A / Interpeace provided expert guidance to national level NEC staff, trained regional and district electoral officers on their election oversight duties and supported NEC in training 3,477 poll station workers.
Progress against expected results: / NEC Staff Training / Interpeace successfully trained National Electoral Commission (NEC) staff (including polling station staff) in advance of Somaliland’s local council elections. Progress and activities against the expected results took place in the following stages: / NEC Headquarters staff received on-going training through the attachment of imbedded expertise in each of the following areas: operations, warehouse, procurement, security, logistics, electoral management, training, voter education and HR database management. In total, 23 national level NEC officials received training through the use of embedded experts and training provided by Interpeace’s international electoral expert and the NEC Training Department. / Interpeace (IP) contracted an international Training Advisor (TA) to support and advise the National Election Commission’s (NEC) Training Unit (TU) to plan and implement the training activities for the November 2012 local council election. / In addition to embedding international experts within critical NEC units, Interpeace worked with NEC to establish an official ‘Training Department’ that was responsible for planning, coordinating and carrying out the training of all NEC staff and poll workers. Interpeace brought in Marjorie Walla, a Kenyan national with extensive election management, voter education and training experience, as the international training expert to oversee the Training Department. At the same time NEC then recruited two additional professional training officers to staff the Training Department. Mrs. Walla and the training officers worked with Interpeace staff to advise NEC on the development of NEC staff and poll workers training programmes, coordinate the implementation of the training programmes and create all training plans, documents and resource materials / From September 8 – 9, 2012, Interpeace worked with the NEC to train Regional Election Officers (REOs) and District Election Officers (DEOs) at NEC headquarters. Eighty-nine REOs, DEOs and regional coordinators from 21 districts and six regions were present. Training topics included the candidate list vetting process, assessment of polling stations and the process of recruiting poll workers. / A two day training session was held in Hargeisa from November 20-21 to train 33 DEOs on all the key tasks of managing Election Day. The trainings were facilitated by NEC Commissioners and Training Department staff. Participants were trained on Election Day Processes including distributing election materials to polling stations, retrieving election materials, adjudicating disputed ballot papers, determining the seats won by parties/associations, procedures for announcing district electoral results and more. / A one day training session was held in Hargeisa on November 24 to train 12 Regional Election Officers on their key Election Day responsibilities. The trainings were facilitated by NEC Commissioners and training department staff. Topics covered during the training included procedures for collation of election results from polling stations at the district level, completion of paperwork, collating of election results for the region, ranking of Associations/Parties at the Region, completion of Paperwork, reporting of Election Results for the Region / Interpeace held two Training of Trainers workshops in order to train the facilitators that led the regional poll worker training sessions. The trainings were held on November 6-8 for 27 participants from the Saanag, Sool, Sahil and Awdal regions and on November 11-13 for 33 participants from the Togdheer and Maarodijeeh regions. Participants were trained on appropriate polling station procedures and on adult-learning principles to utilize when facilitating regional training sessions. / From November 17-20, 2012, Interpeace trained facilitators held 120 regional training sessions that trained 3,477 polling station staff / Interpeace trained 60 computer operators on the process of inputting data coming from polling stations into district level systems. The training took place between November 21 and 23. / Creation and Distribution of Training Materials and Resources / Interpeace worked in conjunction with NEC to create a number of training materials and resources to train NEC officials on their electoral duties and processes. The following resource materials were developed and distributed: / Procedural Manual / A ‘Procedural Manual for Polling Station Officials’ was created that outlined the appropriate rules, guidelines, actions and procedures for poll workers on Election Day. This extensive manual was translated into English and Somali and was utilized in all poll worker training sessions. The manual was provided to all 3,477 poll workers trained and to all regional and district NEC electoral officers and other relevant audiences. The document is attached as ‘Appendix M: Procedural Manual for Polling Station Officials’ / Trainer Materials / Facilitators Guide for the Training of Trainers - Used by Training Department to train trainers / Trainer’s Guide for Training Polling Station Officials – Used by facilitators to train poll workers / Trainer’s Instructional Guide / Poll Worker Materials / DEO Guide to Results Management – distributed to all District Election Officers (DEOs) / Poll Worker Recruitment Procedures – distributed to all DEOs / Vetting Candidates Procedures – distributed to all DEOs / Poll Station Assessment Procedures – distributed to all DEOs / Procedural Manual for Polling Station Officials – Provided to all poll workers, sees further description above. / Handout - Participatory Approach to Training / Handout - Overview of Electoral Laws and Regulations / Handout - Illustrated Voting Procedures / Handout - Simulation Exercises for Completing Polling Station / Forms / Handout - Financial Guidelines / Recommendations: / Interpeace recommends that the work done and materials prepared by its international training expert and the NEC Training Department be archived and preserved so that they can serve as a platform for future election training materials. Additionally, regular and targeted skill building trainings for NEC officials should be held in the time period between elections to further build NECs technical capacity. / Reports from the Progressio international election observation mission indicate that NEC staff were well trained and performed their duties effectively on election day. / Impact Weighting (36.74%) / Revised since last Annual Review? / Risk: Medium / Revised since last Annual Review? N/A
Output 5.1 Progressio - Immediate pre-election period assessment following discussions with key political, security, civic, media, etc. actors contributes positively to public and stakeholder debate on holding free and fair elections, ensuring acceptable levels of political legitimacy and ways of ensuring continuing steps to democratisation
Output 5.1 score and performance description: A+ / Progressio successfully deployed three long term observers to Somaliland to engage in discussions with key actors regarding Somaliland’s electoral preparations and to contribute to public and stakeholder debate regarding the holding of free and fair elections in Somaliland. Additionally, Progressio issued a pre-election press release and held a pre-election press conference on November 26th.
Progress against expected results: / Pre-Election Discussion and Recommendations / Progress against expected results took place in the following format: / Progressio deployed three long term observers (LTOs) to Somaliland prior to the elections in order to consult with relevant electoral stakeholders and gain feedback on electoral preparations. / The LTOs arrived in Hargeisa on November 3 and engaged in a series of meetings and interviews with stakeholders to assess the conditions for free and fair elections on November 28. Meetings were held with local partner organizations such as women’s organization NAGAAD, youth organization SONYO, the Academy for Peace and Development (APD) and civil society organizations SCISEF and SORADI. Meetings were also held with international organizations such as DANIDA and Interpeace, and international officials such as Ambassador SigurdIlling. LTOs also met political/ party association leadership from the RAYS, KULMIYE and UMADDA political organizations, and met with NEC officials and government representatives, including the Director General for Education, Deputy Minister of Interior and Police SPU Commander. Finally, a number of regional meetings were held, including meetings with NEC Regional Chairs, local governors ( to discuss electoral security issues) and the regional representatives of the UMADDA, DALSAN, UCID and WADDANI political parties/associations (to discuss polling station distribution). Progressio also met with media monitors to gain an understanding of how local media (newspapers, TV, radio, selected websites, etc.) cover election campaign issues and disputes. / Recommendations: / There is concern that voter education may have concentrated too heavily on the technical aspects of the electoral process and that civil society, mainly SONSAF, were trying to fill too big a gap in this area. There was no overarching national voter education process, apart from NEC advertising on TV, radio and mobile phones. This needs to be addressed for future rounds of elections / The absence of a voter registry and weaknesses in related safeguards – primarily the inadequacy of the indelible ink – made polling vulnerable to multiple voting. In advance of the next elections, a recommendation with widespread support is that Somaliland adopts a robust system for voter/citizen registration, in order to deter fraud and improve confidence in the electoral process. / Impact Weighting (4.65%) / Revised since last Annual Review? / Risk: Medium / Revised since last Annual Review? N/A
Output 6.1: Progressio: Election Day(s) observation of polling, vote counting and tabulation, and reporting of findings at a public press conference, and other forms of local and international media engagement
Output 6.1 score and performance description: A+ / Progressio successfully coordinated an International Observation Mission that monitored Somaliland’s November 28 local council elections, generated strong press engagement and disseminated election observation reports to NEC and key electoral stakeholders. Of note, the Progressio IEO mission successfully observed polling in 306 stations, a significant achievement above the target set for this output which was the observation of 200 polling stations.
Progress against expected results: / Progress and activities against expected results took the following form: / Progressio led a team of 50 observers that deployed to all six Somaliland regions to observe elections taking place. On Election Day, international observers visited approximately 18 percent of all polling stations established across the country, and observed polling station counts in all six regions. District tabulation processes were observed in Maroodi-Jeex, Saaxil, Sanaag and Togdheer regions. / Of the observers, three were DFID/Progressio funded long term observers, 10 were DFID/Progressio supported short term observers and 37 were volunteer participants in Progressio’s observation mission. Observers hailed from 17 countries, including Canada, Denmark, Ethiopia, Finland, Ireland, Italy, Kenya, the Netherlands, New Zealand, the Philippines, Serbia, South Africa, Sweden, Uganda, the United Kingdom and the United States of America, with a quarter of representatives from Somaliland’s Diaspora. Additionally, representatives from civil society organisations based in Mogadishu, South Central Somalia and Garowe, Puntland accompanied the observer team to review the technical process of managing an election. / Progressio also coordinated with SONSAF, the lead organization for coordinating Domestic Observers. The LTOs had a series of meetings with SONSAF, including sharing detailed deployment plans before the election. They then ensured that every two-person IEO team had contact information for the relevant regional domestic coordinators and worked alongside the coordinators and domestic observers in polling stations on election-day to compare notes discuss observations, etc. Progressio and SONSAF also shared press releases and assessments and were featured together on press interviews discussing the elections. / Recommendations: / On Election Day, most polling station procedures and staff were positively evaluated by observers. Where problems occurred, the NEC usually addressed them quickly and effectively. However, the absence of a voter registry and weaknesses in related safeguards – primarily the inadequacy of the indelible ink – made polling vulnerable to multiple voting. In advance of the next elections, Progressio recommends that Somaliland adopt a robust system for voter/citizen registration, in order to deter fraud and improve confidence in the electoral process. / Impact Weighting (1.25%) / Revised since last Annual Review? / Risk: Medium / Revised since last Annual Review? N/A
Output 7.1: Progressio - Post-Election processes assessed: verbal reporting as required; confidential assessment report distributed to donors and NEC; media engagement; post-election assessment report edited and made available to public
Output 7.1 score and performance description: A
Progressio has assessed the conduct of election, engaged in verbal reporting and engagement with the media produced an interim assessment report and is currently drafting a final report which is due for publication in mid-2013. / Progress against expected results: / Progressio successfully drafted and presented the preliminary findings of the IEO Mission to Somaliland’s National Electoral Commission on December 3, 2012. / Progressio is currently in the process of preparing a final post-election report which is due for general distribution in June 2013. / Recommendations: / The main recommendations at this stage are for the NEC with regards to weaknesses in voter safeguards to prevent multiple voting. There is a need for a robust voter registration system, increased and more effective voter education and comprehensive training of polling station staff. Progressio is also concerned about the understanding of the parties and the electorate of the implementation of the formula in Law 14, Article 6, which will determine which of the contesting parties and associations, become registered parties. While Progressio welcomed the agreement prior to the election to adopt a code of conduct in the interpretation of the law, they encourage both the NEC and the RAC to continue to work transparently in the district and regional tabulation process and declare results in a timely fashion. / Impact Weighting (0.48%) / Revised since last Annual Review? / Risk: / Revised since last Annual Review? N/A

Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y/N / No / 1.2 Overall Output Score and Description: A+ - moderately exceeded expectation / This was a highly successful project (and one which forms a significant part of the SEP). All of the targets were met and a number were, quantitatively, exceeded, in spite of a highly challenging operating environment and a very short time frame (of, essentially, two months). IRI performed well in managing the two sub-grants. / 1.3 Direct feedback from beneficiaries / IRI / IRI received positive feedback from programme participants at all stages of the programme. At the close of the RAC strategic planning meetings, the chairman of RAC noted that the IRI sessions were the first time Committee RAC members had ever been guided to consider and define their roles themselves and stated the workshops were extremely important as RAC headed into the immediate pre-electoral period. Additionally, at the close of each RAC town hall session, participants expressed their appreciation that RAC had taken the time to travel to the regions to explain electoral regulations and ensure a more full understanding of the electoral process / IRI’s party trainings were well received. Numerous participants indicated that they would share the knowledge gained during the sessions with other members of their political organization, and some requested a soft copy of IRI’s training material so that the information could be shared. Trainings related to the management and execution of campaigns was very popular and participants responded positively to learning about new techniques and strategies for appealing to voters. / Finally, participants at IRI’s party poll agent trainings praised training content and specifically stated that the Poll Agent Manual created by IRI was extremely helpful. Participants indicated that, given the complexity of the subject, it was useful to have the manual available in their native Somali language so that they were able to fully understand and internalize the information. Participants also indicated that it was helpful to be provided poll station checklists to assist in their observation duties as no similar document had been provided by NEC or by political parties/associations. / Interpeace / To gauge the effectiveness and relevance of the training materials and the training workshops, the NEC Training Department developed an evaluation tool that was provided to training participants. According to their feedback, most participants found the trainings relevant to the work they had been assigned to carry out. Participants indicated that they found the training sessions interesting and the topics covered increased their knowledge and skills regarding the conduct and oversight of elections. Participants were pleased with the skills of facilitators and the quality of materials used. / Progressio: / Voters seemed happy to see the international election observers on Election Day. IPOs were received positively at polling stations and there was much news coverage and discussion around IEO activities and reports.
1.4 Summary of overall progress / Significant progress was achieved in a very short period of time, with the wide range of training on electoral management and procedures, voter education and general capacity building enhancing both the management of the elections and the conduct of those contesting them. The international observation was critical to the legitimacy of the elections.
1.5 Key challenges / IRI: / The short amount of programming time meant IRI was unable to conduct trainings in as many locations as would have been preferred. Difficulty of travel and security considerations also posed limitations on IRI’s training reach. Additionally, the limited programming time also meant that IRI could not offer individual political party/association trainings. / The controversy around the non-payment of party agent per-diem made planning for party agent trainings very difficult because parties delayed creating agent lists in the hopes that external per-diem would be forthcoming. As a result of this delay, parties did not have complete party agent lists available as IRI was planning the training workshops. However, IRI and APD were able to work around the party agent issue and trained over three times the proposed number in every electoral district. / Weak internal party organization and structures made coordinating with parties on trainings around the country difficult. Through the persistence of IRI national staff, however, trainings were successful and reached their target audiences. IRI recommends that future party work emphasize internal party organization and the strengthening of party institutions and structures. / Interpeace: / The translation of materials from English to Somali took longer than planned. / Progressio: / Logistical concerns such as procuring vehicles and organising security for the IEO mission was time consuming and took longer than expected.
1.6 Annual Outcome Assessment / IRI / Overall, during this year, political parties and associations have taken important steps in their development as democratic institutions. The maturity of the parties and associations varied greatly, but in a hopeful sign, IRI is particularly pleased that parties managed to recruit and deploy thousands of agents on Election Day without financial assistance from donors. This speaks to parties’ understanding of the central role party agents play in ensuring effective and transparent elections are held. Additionally, that parties agreed to forgo transportation assistance provided by IRI in order to allow IRI and APD to train more agents also speaks to the commitment of parties to make sure they had agents at a significant amount of polling stations on Election Day. IRI is hopeful that in future elections, the precedent has now been set for parties to be wholly responsible for exercising their right to have party agents at polling stations. / What was somewhat surprising, but still a positive sign for the development of parties as institutions in Somaliland, was training participant enthusiasm regarding the topic of message development, especially as applied to the findings of IRI’s nationwide poll. IRI used its poll results in several party trainings and in the training material for the Women and Youth Campaign Schools. The poll asked a number of questions about priority issues for Somaliland citizens and also disaggregated the findings by region. Although initially sceptical as to the value of such data, parties and associations quickly began to see how the information could help those craft messages that appealed to their target regional audiences. In the trainings in which this data was presented, conversation was lively and enthusiastic, as was the corresponding group work, as participants began thinking about how to develop (or change) party and candidate messages. IRI believes the constructive reception to this data is another sign of the maturation of political parties. Parties in Somaliland have not traditionally been issue-based however there appears to be a chance to change parties’ approach to crafting platforms and messages. / Additionally, to help RAC improve their relationship with the parties, IRI encouraged RAC to participate in the opening of IRI’s party training sessions. Not only did this allow RAC to feel included in training, it allowed RAC an opportunity to interact with parties and associations in a neutral environment. RAC, throughout its short tenure, has interacted with parties predominantly as an enforcement body implementing electoral requirements such as party/association registration and vetting. The institution has also been criticized for being partisan and non-transparent. By participating in IRI trainings, RAC was able to present itself as a partner institution, there to help, rather than hinder, parties in their development. / Overall, as Somaliland moves into the post-election phase, it will be important that both the three official parties and the remaining newly formed political associations receive support in building their party structures, increasing their organizational capacity and generally strengthening their ability to act as sustainable organizations that carry out the functions of a political organization even in non-election years. / Interpeace / The work of Interpeace’s trained election administrators led to the delivery of a successful and technically sound electoral process that was commended by international and local observers. A sound election process can significantly deepen peace in a region and should be considered a key peace building opportunity. Having competent staff that is knowledgeable about election laws and procedures was the cornerstone of Somaliland’s election. Trained staffs working on polling day were the face of the election to the public, international observers, domestic observers and the media. Election Day was the climax of all the previous preparation and planning activities of the NEC and without a cadre of trained staff at all levels the elections would have failed. Interpeace’s programme contributed to Somaliland’s democratic development by delivering local council elections that were long overdue and which gave the citizens of Somaliland an opportunity to vote for new local office holders. Successful local elections will serve to reinvigorate the dynamics of local accountability. / The technical competence of these elections were very important because the successful top 3 political entities will be declared by RAC as the official legal political parties for the next ten years. Somaliland is therefore entering a critical moment as the new political landscape will be defined and will affect Parliamentary and Presidential Elections and beyond. A strong and independent election management body with well trained staff was crucial in guiding these processes to ensure that the principles of, and commitment to, democracy, was strengthened in Somaliland. / Progressio / Progressio’s international election observation mission served as a critical resource in assessing the conduct of the Somaliland local elections, sharing assessments with international and national stakeholders regarding the conduct of the Somaliland local elections and making recommendations for future elections. The international election observation mission to Somaliland congratulated the people of Somaliland and the National Electoral Commission (NEC) for efforts to conduct and participate in the November 28, 2012, local council elections, which saw 2,368 candidates contest 379 positions across the country. Election campaigning appears to have been competitive and pluralistic, with seven different parties and associations fielding candidates. Parties and associations generally respected the requirement to campaign on a specific day in the week, and to desist from public campaigning in the second and third weeks of the campaign. With the lowering of the age of candidacy, Progressio welcomed the unprecedented numbers of youth and women candidates. In order to support Somaliland’s democratic development, Progressio drafted and released an Interim report that made 12 recommendations for changes to be made or actions taken in order to bolster future elections. A final report will be released in mid-2013 that expands on these recommendations and further analyses the conduct of elections.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / The key cost drivers in this programme for all partners were travel costs for programme participants, security costs and human resources costs. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No change / 3.2 Where an evaluation is planned what progress has been made? / IRI / IRI assesses all programmes every quarter to measure progress made against documented targets and objectives. IRI submitted a narrative report to DFID in December, 2012 that describes the implemented programme in depth and documents programme results and success. As noted in the quarterly report, IRI developed an SMS texting system as a monitoring and evaluation tool to track the deployment of party poll agents and receive a real time assessment of the achievement of one of IRI’s main indicators. IRI collected the mobile phone numbers of 7,212 of the 9,374 party agents that attended IRI workshops and sent them text messages in which they were asked whether or not they observed the polling process on Election Day. Of the agents texted, IRI received a 70 percent response rate. Of the 5045 who responded, 89.7 percent indicated that they did deploy. IRI has a dedicated monitoring and evaluation team that will further assess programme results, which will be documented in the March quarterly report, additional quarterly reports submit throughout the life of the programme and the programme final report. / Interpeace / NEC, Interpeace and Regional and District NEC Staff will hold a two day lessons learned meeting on December 23 and 24, 2012. An analysis of what went right/what went wrong in the technical sphere will be explored. Identification of core themes and recommendations will emanate from the session. Interpeace is writing a full report on the Elections which will include an evaluation of the technical support provided to NEC. This report will be presented to donors, including DFID, in early January. / Progressio / An internal report on the project to measure achievements against objectives and to analyse progress against Progressio’s wider policy team objectives will be produced. Success will be measured against the relevant indicators in Progressio’s internal monitoring and evaluation system RICA (Regular Impact and Capacity Assessment). This evaluation will be carried out in January 2013, after all programme activities are completed. / Regarding further assessment of Somaliland’s elections as a whole, Progressio will release a final report on the election, including expanded recommendations, in mid-July. This report will be distributed to donors and stakeholders.

4. Risk
4.1 Output Risk Rating: Low/Medium / 4.2 Assessment of the risk level / Political: A perception might have arisen that IRI, Interpeace and /or Progressio were acting or had acted in a non-neutral manner when engaging with state authorities or political associations/parties. No indication was given that this was the case, and positive reputations for impartiality amongst all political groupings were maintained. / Security: Whilst Somaliland remains relatively stable, any programme operating in the broader Somali region is subject to security risks. These risks were mitigated by security procedures and protocols. None of the partners – IRI, Interpeace and Progressio– experienced any security threat.
Risk of funds not being used as intended / This risk was assessed as low, and IRI’s internal financial processes have not raised any concerns. IRI’s management of the sub-grantees was effective and transparent. / 4.4 Climate and Environment Risk / The greatest environmental impact of this project comes from international and domestic travel. This was minimised to the maximum extent possible. / Further attention needs to be paid to minimising environmental and climate impact (looking into internal working practices, energy use, use of paper, etc.). Discussions will be held with the IRI to ensure that they prioritise this.

5. Value for Money
5.1 Performance on VfM measures / VfM indicators need to be reviewed. / The ability to analyse VfM is limited given the difficulty of assessing the value of the outcome (strengthening democracy - it is not possible to quantify the benefits of this activity, which is a contribution to the management and conduct of a (relatively) peaceful election and to the democratisation of Somaliland). / The inputs were delivered efficiently – costs were within the norms associated with this type of activity, and were minimised. / 5.2 Commercial Improvement and Value for Money / No activity undertaken / 5.3 Role of project partners / Sub-grants were made to two technically specialist agencies for niche activities. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / No conditions were associated with this project

7. Conclusions and actions
IRI recommends that future elections programming should start much earlier, to allow for more and sustained training with parties and associations. Given the time constraints, IRI had to prioritize locations and topics, and was unable to provide the one-on-one party training that is extremely valuable in promoting party development. An earlier start would also have allowed more time to be spent with youth and women candidates. Specifically, given the large number of youth candidates in these elections, IRI could have offered additional youth campaign schools had timing allowed. / Similarly, civic education efforts could have been greater. The provisions of Law 14 Article 6 in particular were not well publicized, with very little information being given to the public. IRI worked to address this by supporting RAC regional town halls on the issue, but more time and energy should have been spent by RAC and other partners in educating Somalilanders about the law. / The NEC training sessions resulted in high quality training material that can be built upon for the future election cycle. The mentoring approach taken by Interpeace resulted in the establishment of a well-functioning and organised training unit. Interpeace recommends that this unit and the NEC as a whole be supported with resources and capacity building activities between elections so that NEC’s human and technical capacity to deliver elections continues to be strengthened. / It would also be advisable if DFID had a larger and sustained presence in Somaliland given the number of partners with which DFID works and the breadth of programming funded in the country. / In one of the programmatic challenges, IRI, Interpeace and Progressio found it challenging to meet reporting timelines. With elections taking place on November 28, it was a challenge to compile and submit all narrative and financial reports by December 10, 2012.

8. Review Process
Discussions were held with IRI and Progressio November – prior to the election – and in early and mid- December, both in Nairobi and Hargeisa. Written submissions were made by all three agencies. The fact that no field monitoring took place has limited the comprehensiveness of the review. A full review will be undertaken in 2013 (IRI’s activities will continue until August 2013)

Type of Review: Annual Review

Project Title: Somaliland Election Programme - SAFERWORLD

Date started:	01/11/2012	Date review undertaken: 19/12/2012
## Introduction and Context

What support is the UK providing?
The UK has been providing support to a number of aspects of the Somaliland district council electoral process and the broader democratisation process. It is providing £290,333 to Saferworld to assist with the creation of a civil society electoral umbrella group to strengthen coordination and build consensus among non-state/civil society actors engaged in the democratisation process; and, through this umbrella group, Saferworld has provided assistance to broaden policy dialogue and the training and fielding of election monitors, thereby broadening the involvement of civil society in the democratisation process.

What are the expected results?
The overall impact of the project is to deepen peace and stability in Somaliland. / The intended outcome of the project is that Somaliland citizens and non-state actors influence the policies and behaviour of targeted decision-makers by systematically engaging in policy dialogue on issues related to democratisation with Somaliland government and international actors via SONSAF/SCISEF / The expected outputs are as follows: / Formation of the Somaliland Civil Society Election Forum (SCISEF) and a minimum of two dialogue meetings between SCISEF and state/government structures. / Election observers reporting on the elections. / Somaliland Non State Actor (NSA) platforms are actively engaged in policy dialogue with Somaliland authorities. / How will we determine whether the expected results have been achieved? / The programme will be monitored by the implementing partners throughout the programme period, and there will be an Annual review by the end of December 2012. An independent evaluation will take place at the end of the programme.

What is the context in which UK support is provided?
Over the past two decades Somaliland has emerged as an area of stability in an otherwise volatile region. It has made impressive progress in its democratisation including holding four relatively free and fair elections in 2002, 2003, 2005, and 2010. The November 2012 local council elections had the dual purpose of determining the three national parties for the coming ten years – i.e. the three parties which would be eligible to can contest the parliamentary and presidential elections over this period – and were thus highly significant and the focus of intense competition. Acute internal political splits, largely determined by clan affiliations, have characterised Somaliland politics since its establishment, and their management is key to stability. Somaliland politics remains fragile and there is a very real potential for democracy to be undermined and to generate conflict if electoral processes are not managed in a fair, transparent and inclusive manner. / Consultations undertaken by the Somaliland Non-State Actors Forum (SONSAF) identified that the lack of effective coordination and absence of common positions among civil society actors engaged in the democratisation process in Somaliland was a key need in terms of supporting a fair and transparent election processes.[1]Evidence from these studies suggested that efforts to improve coordination and create common positions, and undertake domestic election observation could contribute significantly to guiding Somaliland through the upcoming local council elections, strengthen the democratisation process in Somaliland and make a positive contribution to overall peace and stability in Somalia. / A key contextual issue affecting support to these elections was a highly constrained time frame. It was generally expected that the elections would be held in the spring of 2013. In September 2012 it was announced that they would be held on 28th November 2012. This significantly shortened the amount of time available for the implementation of UK- and other donor-supported programmes, and resulted in the revision of previously discussed, and at times already agreed, plans, and often less support being provided than might otherwise have been the case.
[1] SONSAF (2011): Somaliland Election Review; SONSAF (2012): Citizens’ Dialogue, Pre-Election consultation Forums on upcoming Local Council Elections.

## Section A: Detailed Output Scoring

Output 1: SONSAF/SCISEF is actively engaged in policy dialogue with Somaliland authorities on issues relating to democratisation with key members of the international community based on timely and constructive consultations with citizens.
Output 1 score and performance description: A / SONSAF successfully created the Somaliland Civil Society Election Forum (SCISEF), established on 3rd October, and the SCISEF Coordination Committee – in spite of a shortened timeframe determined by the premature scheduling of the elections. Both bodies worked effectively to influence policy dialogue, allowed for collective advocacy on electoral issues, facilitated coordination, assisted with improving state-society relations on key issues of democratisation and governance, and increased the level of inclusion in the democratisation process. SCISEF has become a widely recognised and respected voice of civil society.
Progress against expected results: / Key areas of progress and milestones reached included: / Establishing the Somaliland Civil Society Election Forum (SCISEF). Launch and consultation events in Hargeisa and all of the regions reaching 225 delegates including representatives from political party/associations, parliamentarians, government officials, religious and traditional leaders, women organisations, youth groups, media personalities, and members of international organisations and UN agencies. / Significant advocacy and policy analysis led by SCISEF led to policy change and a greater acceptance by authorities of the role of civil society in election monitoring processes, including (as a result of project activities): (i) Both the Parliament and the House of the Guurti, rescinded the previous electoral legislation which stipulated that symbols be used during the local council election, and replaced it with a legislation stipulating that a numerical system be used; (ii) A commitment from the President of Somaliland that his office would do everything possible to ensure that fair and free election took place. A meeting, conveying this message between the President and SONSAF was broadcasted on both TV and radio; and (iii) The Registration and Approval Committee (RAC) initiated an awareness programme to ensure that public and political parties/associations understood the criteria for determining which three parties/associations will be recognized as national parties. / Training and deployment of 800 Domestic Election Observers who were able to visit 60% of polling stations on the day of the election / Detailed activity descriptions: Key activities implemented during the project period included: / SCISEF formation and training on election monitoring and advocacy / Somaliland Civil Society Election Monitoring Forum (SCISEF) brought together 47 civil society/NSA actors from all regions to monitor the forthcoming Local Council Elections taking place on November 28, 2012. Prior to the establishment of SCISEF there existed no recognisable coordination structure among civil society/NSA actors for joint planning, information sharing and facilitating agreements on common positions in relation to the then upcoming Local Council Elections. Once established SCISEF held weekly meetings to discuss issues relating to the elections; undertook public advocacy and awareness rising, including issuing press statements topics including campaigning regulations; publically raised issues pertaining to the rights of minority groups and women; and undertook an overall assessment of the election to guide action. / A SCISEF Coordination Committee, a national governing structure with regional representation, was also established with members representing civil society and non-state actors from across Somaliland. SCISEF also established regional focal points to monitor campaigning taking place in the regions. SCISEF members were trained on election monitoring and, during the awareness workshop, a Terms of Reference and selection criteria for Regional Coordinators (RCs) and Observers were developed. / A SCISEF inauguration ceremony and consultation meeting was held in Hargeisa city on October 3, 2012, which attracted 100 participants including major civil society/NSA actors as well as political party/associations, parliamentarians, government officials, religious/traditional leaders, women organisations, youth groups, media personalities, and members of international organisations and UN agencies. Similarly, regional inauguration ceremonies and consultations were held in Berbera, Burao and Borama between October 2nd - 24th 2012 with 125 participants attending in total, raising awareness of SCISEF and election issues across Somaliland. / Issues which emerged included: / The role of SCISEF and the SCISEF Code of Conduct which defined their roles and responsibilities vis-à-vis state institutions / Election legislation (Council & Presidential Law #20 & Political Party & Political Association Law 14 – see below) / The election quota for women / The lack of opportunity for youth participation in the elections / The lack of an effective voter education programme / The large number of political entities contesting the election and challenges that this might present / The absence of controls against voting irregularities / The absence of objective reporting on the part of the media. / These issues fed into dialogue with the electoral authorities. / Coordinated election monitoring and advocacy through SCISEF / Differing views over the most appropriate system to be used for selecting candidates threatened to delay the elections. The Parliament had passed a law which stipulated that a numbering system should be used during the Local Council Election instead of symbols. However, after complaints from some of the election stakeholders, the Parliament changed the numbering system to symbols. This was followed by a complaint from the National Electoral Commission (NEC), which argued that using symbols would be difficult since there are seven organisations contesting the election; the NEC added that it would be difficult to find a ballot paper that can accommodate the symbols of all candidates. The NEC also raised issues around the increased costs of using symbols. The NEC requested civil society/NSA actors to assist them to resolve the matter in order to proceed with the elections as planned. Subsequently, SONSAF and SCISEF members, invited major civil society/NSAs to a meeting which was held in SONSAF on August 6th, 2012. As a result, SONSAF and other civil society actors issued a press statement on 6th August 2012, which recommended that: / A numbering system be used to avoid delays to the elections / Local Council Elections should be held within 2012 / An effective voter education programme should be implemented by SONSAF members and monitored by SCISEF / Parties/associations should nominate their election candidates on the basis of knowledge, experience, and honesty as opposed to other issues such as clan affiliation / Women and minorities should be given special considerations during the selection of the candidates / The SCISEF Coordination Committee also raised concerns regarding Political Party & Political Association Law #14, Article 6 referring to the criteria used to determine which three parties/associations will become national political parties. SCISEF met with officials from the RAC for political parties and political associations on 24th November 2012, explaining their concerns with this legislation and the proportional representation ranking system. The SCISEF Coordination Committee requested that the RAC undertake an awareness raising programme so that public and political parties/associations would understand how the ranking system works. On SCISEF’s recommendation, the RAC and NEC held a joint press conference and explained to the public their respective responsibilities with regard to election management. / Training and deployment of Domestic Election Observers (DEO) / SONSAF, building on its experience of the 2010 Presidential Elections, deployed 800 domestic election observers across the six regions of Somaliland during the Local Council Elections on November 28, 2012 and covered 60% of the polling stations. During this period key preparations took place including: reviewing and establishing Domestic Election Observation (DEO) documentation; conducting an awareness raising workshop for SCISEF members; recruitment of regional coordinators, election trainers, and observers; establishing MOUs between SONSAF, NEC and Shaqadoon; and the development of a training manual. From October 1st –10th, 2012, the Domestic Election Observation (DEO) office, sitting within SONSAF, successfully recruited domestic observers who had worked during the last elections, thereby bringing their experience and expertise to the process. The DEO office also provided the forms needed by the Domestic Observers when monitoring the elections, established a list of TOT Trainers, recruited Regional Coordinators and appointed focal points. The previous DEO forms were reviewed and amended in light of the increase of political parties and associations. / The DEO unit developed a new training manual for domestic election observers. The training manual summarised details of the elections held in the last ten years, the election cycle and the procedures for opening, voting, closing, and counting. The purpose of the manual, written in Somali, was to assist Regional Coordinators and Observers on the Election Day itself as it contains all necessary election procedures. In total, 800 copies of the training manual were printed and distributed among the Domestic Observers, ensuring one per Observer. / A Training of Trainers (TOT) workshop was held in Hargeisa from 14th - 15th November 2012 with a total of 72 participants attending from SONSAF member organisations. The main objective of the workshops were to train and refresh the master trainers and Regional Coordinators on the concept of election observation in local elections, the national and international legal and regulatory framework, election principles, practices, declarations and the Code of Conduct applicable to local government administration. Upon completion of their training, the participants trained 800 Local Observers. / During the workshop, SONSAF members developed ToRs for the Domestic Election Observers, Trainers of Trainers, and Regional Coordinators, referring back to the ToRs of the 2010 presidential election. The SONSAF Executive Director emphasised that election observers should remain impartial at all times, and should not interfere, under any circumstance, in any aspect of the voting. / Meetings with SCISEF& NEC / On October 8th 2012, SONSAF met with the National Election Commission (NEC) to discuss how SCISEF could participate in the upcoming Local Council Elections, with a particular emphasis on improving voter education. Issues discussed included: / Reviewing the budget estimates available for the voter education programme throughout Somaliland; / The coverage area for the Local Council Elections (the number of districts where the election will take place) / The methodology and resources available for the Voter Education Programme which was delivered under the guidance of the NEC and implemented by SONSAF partners. / At the end of the meeting, NEC requested SONSAF to undertake monitoring activities of the Voter education programme, which SONSAF accepted. As a result of this meeting, the Somaliland National Electoral Commission (NEC) and SONSAF entered into a Memorandum of Understanding in organising and mobilizing domestic election observers during the 2012 Local Council Election in Somaliland. / Meetings with the Democratisation Coordination Committee / On September 18th-19th, SONSAF met with the Democratisation Coordination Committee (DCC) to familiarize NEC members with SONSAF’s SCISEF programme regarding the upcoming local elections and to brief NEC members about the deployment of local observers for the forthcoming Local Council Elections. Issues discussed included deadlines for major activities including submitting the names of local observers and activities that civil society actors would undertake during the forthcoming Local Council Election and the need to establish a focal point to coordinate with NEC so that election-related activities and programmes could be coordinated systematically. A Memorandum of Understanding was drawn up between SONSAF and the NEC to encourage collaborative working, particularly in deploying Domestic Election Observers. A follow-up meeting was held on October 8th 2012 to discuss activities to be undertaken by each civil society organisation which resulted in all CSOs/NSAs coordinating with Interpeace regarding their respective election programmes to promote complementarities and avoid overlapping activities. / Meeting between SCISEF Coordination Committee and Election Monitoring Board / A joint meeting between the Somaliland Civil Society Election Forum (SCISEF) and the Election Monitoring Board (EMB) was held on 21 November, 2012. Issues discussed included: / Complaints from regions regarding the distribution of polling stations / Political Party & Political Association Law #14 concerning how the RAC will select the political parties/associations that would be recognized as national political parties / The current status of the voter education programme / Whether to use a symbol or numerical-based system for political parties in the forthcoming election / It was agreed that the Voter Education programme should be sped up with particular emphasis on the importance of maintaining peace and the consequences of multiple voting. Two days later, the Parliament rescinded the previous legislation that stipulated the usage of symbols, and adopted a new legislation, which authorises that a numbering system should be used during the Local Council Election of 2012 which was presented at a joint press conference by the SCISEF Coordination Committee and the NEC Monitoring Board. / Meeting with the Guurti (the Upper House of Parliament) / SONSAF and the Foreign Relations Committee of the House of Guurti met at the Guurti on October 24, 2012. The SCISEF Coordination Committee and members of the Guurti exchanged information concerning the Local Council Election. / Meeting with the President of Somaliland / On 23rd November, 2012, the SCISEF Coordination Committee met the President of Somaliland to discuss issues surrounding Local Council Election, in particular RAC’s criteria concerning which parties/associations will qualify to become national parties. The President thanked SCISEF Coordination Committee members and asked them to continue participating in election activities. / Issues discussed also included complaints from Sahil Region concerning polling stations and the need for greater coordination between the government and civil society on election issues. The President stated his commitment to the on-going electoral reform process of Somaliland. As a government, they had contributed to the election budget and that they had increased this in comparison to previous elections. The President also stated that they had provided transportation expenses to the local observers. He stated that he would do his best to ensure that fair and free elections are held. In return, the President requested that civil society/NSAs should undertake public awareness activities with regard to elections in the days leading up to the election. As a result of these meetings, the President’s Office issued a Communiqué, which was broadcast on radio and television. The communiqué covered the meeting between the President and SONSAF and the two sides discussed issues concerning Local Council Election and an acknowledgement of the important role that SONSAF would play with respect to democratisation issues. / Recommendations: / These activities will continue until March 2013. Further support will continue to be required by civil society (and political) actors in Somaliland in the post-election period, particularly in building awareness and consensus around political inclusivity (other agencies have planned to work, post-election, on political party development). A key need is for senior level international; political engagement with the democratisation process (largely undertaken by the Democratisation Steering Committee to date). / Impact Weighting (%): / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? N/A

Output 2: Broader and more informed involvement of Somaliland NSAs and citizens in democratisation processes
Output 2 score and performance description: A / Awareness-raising by SCISEF generated an increased appreciation of electoral and democratisation issues amongst its 58 non-state actor member agencies and led to a more informed involvement in the monitoring of the elections and the broader political process. The training and fielding of the 800 domestic election monitors – and their involvement in the process – is significant.
Progress against expected results: / SCISEF held a range of awareness-raising workshops and activities for its member agencies and peer agencies thereby informing Somaliland NSAs and citizens about wider democratisation issues. SCISEF also engaged Domestic Election Observers in context monitoring on the day of the election through its partnership with the telecommunications company Shaqodoon. SCISEF also raised awareness of the key issues that emerged during the local council elections through a number of widely circulated press releases. / Key milestones achieved to date include: / Three SCISEF Coordination Committee meetings held with peer agencies, such as the NEC Monitoring and Disciplinary Committee, engaged in election-related programming providing an effective platform for discussing and taking action on particular issues. / Wide dissemination of a press statement following the elections / Partnership with the telecommunications company Shaqodoon in which an SMS message system used on Election Day to get real-time updates on events received 6500 messages from polling stations in different regions allowing it to monitor election related incidents, assisting SCISEF in its assessment overall of the election. / Awareness raising workshop for 58 SONSAF member organisations on key issues relating to the Local Council Elections. / Detailed description of activities implemented during the project period : / SCISEF Coordination Committee Meetings / The SCISEF Coordination committee held meetings on 7, 14, and 23 November 2012. The Committee discussed wide-ranging issues concerning the election campaigns and complaints from different communities regarding the way in which polling stations were distributed. The aim of the meetings was to sensitize stakeholders including Progressio, Oxfam, Interpeace, NEC, RAC and local civil society organisations to contribute to, and if possible to influence, the Local Council Elections. In addition, SONSAF developed the TOR for the Coordination Committee and the duties and responsibilities of the SCISEF Coordination Committee and the availability of committee members were discussed. / Issues discussed prior to the elections included: / Complaints from constituencies in the Togdheer regions that the number of polling stations had been reduced to a greater extent than other regions. Similar complaints came from the Sanaag region, particularly in Eastern, Southern, and North Sanaag areas. / The Justice and Welfare Party of Somaliland (UCID) and the Ummadda Political Associations made complaints about interference by the Government. Both parties claimed that their officials have been promised jobs and monetary rewards to defect. / Accusations that Government officials and civil servants had been involved in election campaigning / The debate regarding RAC’s criteria that determined which three political parties/associations would qualify to become national parties was the subject of extensive debate. / Confusion as to who would announce the election results (either the RAC or NEC). / As a result of the discussions above, the following developments took place: / A SCISEF delegation met with the NEC and RAC to discuss issues concerning the Local Council Election. It was agreed that the RAC would announce the result. / Two days after the meeting, the NEC announced that it would abandon its plan to reduce the number of polling stations. / One day after the meeting, the Election Monitoring Board issued a Press Statement denouncing officials in government institutions who claimed that they had the right to participate in election campaigns. / On 24th November 2012, the SCISEF Coordination Committee and RAC met and discussed the criteria that RAC is to employ to determine which three parties will become national parties. The SCISEF Coordination Committee suggested that the RAC undertake awareness activities concerning the ranking system. As a result, the RAC began undertaking awareness meetings targeting political parties/associations, NEC, and the Guurti. / Partnership with Shaqodoon / It was agreed that the telecommunications provider, Shaqadoon would assist SCISEF in its observation activity on the Election Day by allowing SCISEF to send and receive messages from all domestic observers. Known as info-match (SMS mobile phone text messaging), this mechanism enabled observers to send and receive messages and pre-recorded voices from SONSAF’s Election Monitoring Centre. The info-match system facilitated real time reporting on voting-related events in polling stations. SONSAF and Shaqodoon agreed upon the following points: / To work with Shaqodoon to run communication coverage between SONSAF head office and SCISEF observers in the regions during the upcoming Local Council Elections. / SCISEF would establish an information centre and would send the names of observers and their contact address to Shaqadoon, which would in turn send and receive info-match SMS and Voice messages. / SCISEF would also assign key staff to provide training on info-match SMS and Voice messaging service so that SCISEF could benefit from using the service during the run up to the Election Day. / Equally, SONAF would identify and assign to Shaqodoon, a key contact person to receive and approve voter education content on behalf of SONSAF. / During the election, 6,500 messages were received by SCISEF, ensuring real-time monitoring of election events including the times that polling stations opened and closed and updates on ballot counting. This information enabled SCISEF to build up a picture across Somaliland and to assess the overall degree to which the elections were free and fair. / Awareness raising Workshop for SONSAF members / On 16th-17th October 2012, SONSAF conducted a two-day awareness workshop for 58 SONSAF member organisations on domestic election observation. / Recommendations: / This activity will continue until March 2013. Support will continue to be required by civil society actors in Somaliland in the post-election period, particularly in supporting them to build awareness and consensus around fundamental democratic processes and to support their attempts to hold the government to account in its support for the democratisation process. / An internal non-state actor needs assessment should be undertaken in to assess their role and what preparatory steps are required for the next rounds of elections (Parliamentary and Presidential). / Impact Weighting (%): / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A / The project succeeded in delivering as per its plans, and met all expectations, the short time frame notwithstanding. / 1.3 Direct feedback from beneficiaries / It was not possible to collect, systematically, direct feedback from beneficiaries (SONSAF, SCISEF, its component non-state actors and the peer agencies). A Saferworld democratisation consultant is currently – mid-December – in Somaliland and will collect feedback.
1.4 Summary of overall progress / Significant progress was achieved in a short period of time. SCISEF has been able successfully to influence policy and legislative change, gaining both access to and the respect of a number of state actors with an election mandate; and has been able to influence the policy debate through use of the media. SCISEF has emerged as an effective and legitimate representative of civil society on elections issues. SCISEF successfully trained and deployed large numbers of election observers, thereby ensuring that civil society played an informed, direct and important role in overseeing the electoral process.
Key challenges / Short timeframe for project implementation (due to the early calling of the elections) / The absence of a lead-in time/inception period presented Saferworld with recruitment difficulties. They initially envisaged that a Democratisation Consultant could be hired to support pre-election activities though this was not possible in the timeframe (a suitable candidate was subsequently identified and will lead the report writing and reflection process in late 2012/early 2013).
1.6 Annual Outcome Assessment / The specific outcome of the project is that Somaliland citizens and NSAs influence the policies and behaviour of targeted decision-makers by systematically engaging in policy dialogue on issues related to democratisation with Somaliland government and international actors via SONSAF/SCISEF. The project will not be completed until March 2013, and has only been running for ten weeks as of December 2012. That said, it is clear that SCISEF – established on 3rd October, seven weeks prior to the election date - did manage to successfully influence a number of state actors, namely the NEC and RAC, prior to the elections, as well directly contribute to legislative change. Whilst there were many negative issues associated with the elections, these were mitigated in many respects by the work of Somaliland civil society which had been supported, and whose resilience had been enhanced, through this project. A fuller outcome assessment will be undertaken at the end of the project.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / In this project period key cost drivers were: staffing (Saferworld), staff and operating costs for SONSAF and SCISEF, costs associated with the formation of SCISEF (venue hire and media) and, significantly, local transportation. Costs were at standard NGO rates. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence / 3.2 Where an evaluation is planned what progress has been made? / This project will be evaluated externally as part of the mid-term review planned for a broader programme of work funded by European Commission for the period 2012 – 2014 entitled “Strengthening the participation of Somali Non-State Actors in decision-making on peace, security and development: towards sustainability”. Saferworld will recruit for an external consultant during the next reporting period.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Risks: / Political: As identified in the proposal there were two key political risks to activities of this nature. / Firstly, that local partners/Saferworld act or are perceived to act in a non-neutral manner when engaging with state authorities or political associations. No indication was given that SCISEF were deemed to be partial or to have been co-opted by state authorities and every effort was made to ensure that this perception did not materialise. SCISEF maintained a good reputation for impartiality and credibility among political spheres largely due to its diverse range of membership which ensured that many different interests were represented (private and non-profit entities, different sectors, regions, clans and districts). SONSAF is registered under the NGO Act and often clarifies externally that it is not a mandated institution of the election and sometimes formally articulates this with state institutions directly. / Secondly, that SONSAF/SCISEF are civil society structures that they are side-lined from processes as they are not perceived to be legitimate actors in regards to electoral reform and oversight. SCISEF also has substantial knowledge of electoral systems and laws and used this expertise when working with state authorities and political associations. The NEC and RAC, declared that civil society actors are only the neutral institutions who can play a vital role conflict management and resolution role both during and in the post-election period. / Security: Whilst Somaliland remains relatively stable, any programme operating in the broader Somali region is subject to security risks. SCISEF deployed domestic observers in some volatile parts of the Sool and Sanaag region. In order to mitigate these security risks, SCISEF recruited and trained domestic observers emanating from these regions and particular districts and so were more likely to understand the local context and be accepted by local communities.
4.3 Risk of funds not being used as intended / This risk was assessed as low, and Saferworld’s internal financial processes have not raised any concerns. SONSAF has been a longstanding partner of Saferworld and has well established financial systems in place. / 4.4 Climate and Environment Risk / The greatest environmental impact of this project comes from internal working practices (for example, use of transport and specifically air travel; paper use; energy efficiency of premises etc). Saferworld reports that all the printers it uses adhere to sound environmental principles including the use of recycled paper, FSC certification (environmentally and socially responsible forestry) and the use of vegetable inks. The project has been implemented predominantly by partners based in the project implementation area reducing the need for extensive international travel.

5. Value for Money
5.1 Performance on VfM measures / The VfM indicators need to be further reviewed. / 5.2 Commercial Improvement and Value for Money / This has been reviewed. Saferworld and SONSAF are committed to minimising costs by seeking competitive rates for project inputs and recently carried out a cost-mapping exercise to align project costs (i.e. the prices of hotel rooms, meals, refreshments, local transport, and communication) to current market rates. The purpose was to agree on standard rates in line with current actual costs to facilitate easier budgeting processes; ease of referral for future proposals; and the monitoring of expenditure and value for money. Saferworld and SONSAF are also committed cost sharing. This project makes a contribution to a larger programme of work funded by the European Commission allowing for resources to be utilised that compliment both programmes of work, saving time and money on setting up resources for short-term projects. / 5.3 Role of project partners / The project has been designed and implemented by long-term partners of Saferworld’s based in Hargeisa which have a reputation for their knowledge on democratisation issues and knowledge of the local context. Implementation has been carried out locally reducing the need for international travel costs. The project also builds on SONSAF’s previous experience working on the elections. / 5.4 Does the project still represent Value for Money: Yes? The ability to analyse VfM is limited given the difficulty of assessing the value of the outcome (strengthening democracy) – given, however, the assessment that this project has contributed to this outcome, and the relatively limited inputs, it is felt that this is an appropriate investment and one which represents VfM. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / No conditionality was linked to this project

7. Conclusions and actions
In summary, whilst there has been less than three months of implementation, the establishment of SCISEF has succeeded in effectively influencing policy and legislative change with respect to the Local Council Elections. Through doing so, it has successfully created a platform for broad civil society engagement which has been both welcomed and respected by those state institutions which have an election mandate. The remaining four months of implementation will focus on the analysis of key election issues that emerged during the Local Council Elections and assessing the contribution that civil society oversight can achieve in encouraging free and fair elections in the future.

8. Review Process
Discussions were held with Saferworld in November – prior to the election – and in early December and written submissions were made by Saferworld. The short time frame – the project had only run for three months by the time of this review, thereby limiting the amount of work to be reviewed – and the fact that no field monitoring took place, have limited the comprehensiveness of the review. A full review will be undertaken in 2013.

Type of Review: Annual Review

Project Title: Somaliland Election Programme – Centre for Humanitarian Dialogue (CHD)

Date started:	11/09/2012	Date review undertaken: 19/12/12
Introduction and Context

What support is the UK providing?
The UK is providing support on the Somaliland District Council Elections / The UK provided £150,000 to the Centre for Humanitarian Dialogue (CHD) to undertake a number of activities in Somaliland prior to and during the Local Council Elections. These included the establishment of a regular consultative forum on election management; an agreement on the procedures and code of conduct between the National Electoral Commission (NEC) and the Political Parties/Associations; an agreement on the management and conduct of the elections between the Political Parties/Associations; and the establishment of an official election dispute resolution mechanism.

What are the expected results?
The intended outcome of this intervention is: democracy strengthened in Somaliland. / The expected output is: the process for election dispute resolution developed and in place. / How will we determine whether the expected results have been achieved? / The programme was monitored by the implementing partners throughout the programme period, and an Annual Review was undertaken in December 2012. An independent evaluation, to be commissioned by DFID, will take place of all Somaliland Election Programme (SEP) components at the end of the programme (it was envisaged that this would help inform decision making on possible future support to democratisation activities in Somaliland).

What is the context in which UK support is provided?
Over the past two decades Somaliland has emerged as an area of stability in an otherwise volatile region. It has made impressive progress in its democratisation including holding four relatively free and fair elections in 2002, 2003, 2005, and 2010. The November 2012 local council elections had the dual purpose of determining the three national parties for the coming ten years - i.e. the three parties which would be eligible to can contest the parliamentary and presidential elections over this period – and were thus highly significant and the focus of intense competition. Acute internal political splits, largely determined by clan affiliations, have characterised Somaliland politics since its establishment, and their management is key to stability. Somaliland politics remains fragile and there is a very real potential for democracy to be undermined and to generate conflict if electoral processes are not managed in a fair, transparent and inclusive manner. / A key contextual issue affecting support to these elections was a highly constrained time frame. It was generally expected that the elections would be held in the spring of 2013. In September 2012 it was announced that they would be held on 28th November 2012. This significantly shortened the amount of time available for the implementation of UK- and other donor-supported programmes, and resulted in the revision of previously discussed, and at times already agreed, plans, and often less support being provided than might otherwise have been the case.

Section A: Detailed Output Scoring

Output 1: Consultative forum on election management established
Output 1 score and performance description: A – met expectation / CHD provided advice which led to the formation of an Inter-Party Advisory Committee (IPAC) which served as a formal consultative mechanism between the parties and the NEC.
Progress against expected results: / CHD engaged with the NEC, the Registration and Approvals Commission (RAC), the Electoral Monitoring Committee and all the political parties and associations prior to the elections and an intensive working relationship was established. Meetings with members of NEC - including its Director of Organisation - took place on an almost daily basis. The IPAC was established and served as a consultative forum prior to the election. / CHD also facilitated bilateral meetings for the RAC. Of particular importance was a meeting with the Supreme Court – with which the RAC had not had any contact – at which the ranking formula was explained and discussed, and subsequently endorsed (thereby ensuring that the Supreme Court was on-side in the event of challenges being referred to it). / Recommendations: / Whilst the NEC performed well, significant work will be required to develop capacities and mechanisms to manage all aspects of the next rounds of elections (Parliamentary and Presidential). Further work is required to institutionalise a structure such as the IPAC. / Impact Weighting (%): 30% / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A

Output 2: Political parties/associations procedures and code of conduct
Output 2 score and performance description: A / CHD provided guidance on the formation and substance of the code of conduct between parties, and then worked with the NEC and political parties and associations to sensitise them to the content of the political party/association electoral guidelines and code of conduct. In parallel to this they undertook a number of ad hoc initiatives to assist with clarifying issues, pre-empt problems or resolve them.
Progress against expected results: / CHD held discussions with the RAC and NEC to offer them advice on the clarification of Article 26 of Law No. 14, which gave RAC the authority to give regulations and code of conduct and directives. This authority informed the formalisation of the Article 6 formula – the ranking mechanism for parties – which enhanced its legality. / CHD facilitated discussions between the RAC and the dissatisfied political parties i.e. Ucid, to clarify a legal misunderstanding of Article 6, and to convince that party not to issue negative statements about RAC and the electoral process / CHD acted in reducing the tensions between the Political parties – specifically Ucid and Wadani - which were in contention. This led to an agreement between the political parties and RAC on their conduct in the lead up to the elections. / Through discussions with the chairs of the Kulmiye and Haqsoor political parties, CHD succeeded in securing their understanding and acceptance of Article 6 and their participation in the election. / Recommendations: / Engagement with the parties and the NEC needs to be maintained post-election. It would have been desirable to have international political engagement on the ground in Somaliland after the elections to support the resolution of disputes. / Impact Weighting (%): 30% / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A
Output 3: Establishment of an Election Dispute Resolution (EDR) mechanism
Output 3 score and performance description: A – met expectation / Based on work undertaken for the 2010 Presidential elections, CHD produced a list of options for formal and informal Election Dispute Resolution (EDR) mechanisms for Somaliland, and then worked on the establishment of a mechanism.
Progress against expected results: / CHD developed a complaints form system on how to process electoral complaints during the Local Council Elections. CHD was responsible for the printing of 20,000 copies of the Complaints forms which were distributed across all the polling stations in all the districts. Each polling station received 10 copies of the complaints form. Integral to the complaints form system, CHD participated in the Training of Trainers (TOT) for the polling staff, and explained the relevance of the complaints form and the processing of the complaints form at the polling level, and procedures to be followed after that. The Complaints form system component was also included in the polling and counting manual which would be used by the polling staff. CHD developed a registry for complaints to ensure NEC has a record of all the complaints from all the districts. The registry was tasked with ensuring follow up of all complaints in Somaliland, recording all the complaints, analysing them, etc. CHD also developed a reports form in collaboration with NEC, this would provide daily information on the development of the complaints processing and the number of complaints received. A decision form was developed for use in all districts which details the dispute in question, as well as outlining the decision reached. This entire process aimed to help generate a consistent and unified election dispute system across Somaliland. CHD also developed an investigation and instruction form which would serve to guide the investigation process of complaints raised. / Recommendations: / Further refinement of the system based on the experience of the elections. / Impact Weighting (%): 30% / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A
Output 4: Scenario planning and progress monitoring
Output 3 score and performance description: A – met expectation / A scenario planning exercise was undertaken as a means of identifying possible scenarios and, if required, possible ways of mitigating any negative impacts.
Progress against expected results: / CHD facilitated a scenario-building meeting for the Democratisation Steering Committee members in Nairobi. The session analysed the situation in Somaliland in the lead up to the elections and looked at the possible scenarios that could impact the electoral process negatively. It was a shared analysis of the situation and took into account the contributing and mitigating factors and actions as well as the financial/technical and political implications of the local council elections. An analysis of the security situation and flash points was undertaken, and of the political leadership, the legal framework, elections facts and figures, civil society and the media. Of concern in the scenarios discussion was the lack of resolution of Article 6, the withdrawal of one of the parties (called UDUP), potential chaos at the polling stations, large scale fraud, close results because of the high contested outcomes and challenges in relaying results in to the district and national levels. / Recommendations: / A similar process should have been undertaken in Somaliland with the NEC and RAC / Impact Weighting (%): 10% / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A

Section B: Results and Value for Money.

1. Progress and results

1.1 Has the log frame been updated since last review? Y/N / Yes. The Log frame was update in October 2012 to incorporate the Scenarios Planning and Monitoring process. / 1.2 Overall Output Score and Description: A – met expectation / All outputs were successfully attained. CHD was successful at engaging with all key stakeholders – NEC, political parties/associations, RAC, - and in developing their capacity to manage possible disputes arising from the elections. / 1.3 Direct feedback from beneficiaries / The development of a proper EDR mechanism was received positively by a range of stakeholders, including the RAC, the NEC and regional judges who were trained on its application by CHD. The RAC, and the political parties/associations, were also very positive about CHD support in assisting with the interpretation of Article 6 of the Electoral Law.
1.4 Summary of overall progress / The project was successful in both establishing the EDR mechanism and, through its various political dialogues, managing and defusing the tensions then mounting. This was a significant contribution to the actual conduct of the election.
1.5 Key challenges / CHD highlighted the political challenges and technical complex nature of the issues which the project was addressing – Article 6, and reaching consensus on it; the high level of political contestation; issues of the distribution of polling stations; clan splits; etc.
1.6 Annual Outcome Assessment / The project outcome was that democracy is strengthened in Somaliland. CHD contributed significantly to this outcome through undertaking dialogue and consensus building and enhancing the capacity of the electoral management bodies to manage disputes. The ability of the system to manage the post-election issues – in particular the political brinksmanship by Haqsoor, the party which took to the streets after losing -, was in many ways a result of the capacity building undertaken by CHD and SEP.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / Key drivers are the costs associated with holding workshops and dialogues (principally staff costs and travel) / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes / 3.2 Where an evaluation is planned what progress has been made? / The activities of this project will be evaluated in 2013.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Low / 4.2 Assessment of the risk level / This project was primarily focused on the pre-election period during which some tension did, as was inevitable, emerge. The risk presented was low. This tension was in part addressed by this project – thereby enhancing the general operating environment for this and other SEP projects -, and it did not have a significant adverse impact on the project (apart for introducing delays in undertaking some activities).
Risk of funds not being used as intended / This is limited as CHD’s internal and systems and controls are accepted as being strong. There are no sub-grants within this project. / 4.4 Climate and Environment Risk / The main climate/environmental impact related to air travel to/from Somaliland – this was all on scheduled EC and UN flights. / For any future grant with CHD close attention will be paid to ensure that they minimise any adverse environmental and climate impact (by reviewing e.g. their including internal working practices, travel policies, energy use, use of paper, recycling policy, etc.).

5. Value for Money
5.1 Performance on VfM measures / It is not possible to quantify the costs and benefits of this activity – its role in setting-up mechanisms which would mitigate electoral disputes was significant, and therefore its value needs to be viewed as contributing to a (relatively) peaceful election. This value was not quantified at the outset of the project. / The inputs were delivered efficiently – costs were within the norms associated with this type of activity, and were minimised. / 5.2 Commercial Improvement and Value for Money / No assessment of this has been undertaken / 5.3 Role of project partners / CHD has collaborated closely with Interpeace (under IRI) and the NEC. It noted that a closer relationship with Saferworld and Oxfam would have been desirable (intra-SEP coordination was noted by other SEP partners). / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / None

7. Conclusions and actions
This was an important and effective project which helped to reduce and mitigate actual post-election discord. The shortened time frame militated against it being able to deepen and consolidate some of the processes which it established, deepen political buy-in and broaden public understanding. That said its achievements in the short time available were critical and commendable. / CHD will undertake further discussions with the RAC, NEC and political parties on the management of subsequent elections as preparations for these needs to commence soon.

8. Review Process
Discussions were held with CHD in November – prior to the election – and in early December. CHD staff met with DFID in Nairobi, and written submissions were made by CHD. The short time frame – the project had only run for two months by the time of this review, thereby limiting the amount of work to be reviewed – and the fact that no field monitoring took place, have limited the comprehensiveness of the review. A full review will be undertaken in 2013.

Type of Review: Annual Review

Project Title: Somaliland Election Programme - OXFAM

Date started:	01/11/2012	Date review undertaken: 19/12/2012
## Introduction and Context

What support is the UK providing?
The UK is providing support to a number of aspects of the Somaliland district council electoral process and the broader democratisation process. It is supporting Oxfam with £570,000 to develop a pilot project for citizen and youth participation in the electoral and democratic process. This aims to strengthen community participation in local government affairs by creating and opening spaces for citizens, particularly women and youth, to engage effectively with the political process, and also to promote institutional accountability.

What are the expected results?
The intended outcome of this intervention is: democracy strengthened in Somaliland. / The expected outputs are as follows: / The promises and community commitments of 267 political candidates tracked; / 216,000 voters in 6 districts (targeting marginalised groups such as pastoralists, rural, youth and minorities) are aware of political candidates and their agendas; / 2,600 youth are empowered and active in seeking their own political solution though their participation in 26 democracy café centres. / . / How will we determine whether the expected results have been achieved? / The programme will be monitored by the implementing partners throughout the programme period, and there will be an Annual review by the end of December 2012. / Oxfam and partners will gather monitoring data as they implement the project. The project team will organise a learning review workshop three months after the start of the project to understand what is working well and what to do differently, draw lessons learned and plan for the remaining part of the project. Security monitoring and regular context analysis will also be done to inform programming and decision making. Oxfam will produce learning documentation on one learning theme identified by partner organisations in the first two months of the project, and will commission an external evaluation of the project.

What is the context in which UK support is provided?
Over the past two decades Somaliland has emerged as an area of stability in an otherwise volatile region. It has made impressive progress in its democratisation including holding four relatively free and fair elections in 2002, 2003, 2005, and 2010. The November 2012 local council elections had the dual purpose of determining the three national parties for the coming ten years - i.e. the three parties which would be eligible to can contest the parliamentary and presidential elections over this period – and were thus highly significant and the focus of intense competition. Acute internal political splits, largely determined by clan affiliations, have characterised Somaliland politics since its establishment, and their management is key to stability. Somaliland politics remains fragile and there is a very real potential for democracy to be undermined and to generate conflict if electoral processes are not managed in a fair, transparent and inclusive manner. / A key contextual issue affecting support to these elections was a highly constrained time frame. It was generally expected that the elections would be held in the spring of 2013. In September 2012 it was announced that they would be held on 28th November 2012. This significantly shortened the amount of time available for the implementation of UK- and other donor-supported programmes, and resulted in the revision of previously discussed, and at times already agreed, plans, and often less support being provided than might otherwise have been the case.

## Section A: Detailed Output Scoring

Output 1: The campaign promises and community commitments of 267 local government political candidates are tracked
Output 1 score and performance description: A – met expectation / Significant progress was achieved in documenting and tracking campaign promises, and this activity is on track to meet its targets (it will continue after the election).
Progress against expected results: / Two milestones were proposed, targeting 267 political candidates / Documentation of political promises of seven parties - reduced from nine to seven due to the failure to register of two formerly serious parties -during Sept to Nov 2012 and 170 political candidates by March 2013 / Review of the political manifestos of 267 elected councillors / A stakeholder assessment was conducted to identify potential CSOs, women’s umbrella networks and community based organizations for the election tracking process. A total of 120 women’s representatives from a range of CSOs were identified and trained. Tracking of election promises of 175 candidates was conducted and documented, and 2 out of 5 planned community discussions were convened to influence voters to articulate their demands/voices. Due to the increased reliance on the media to follow the elections Oxfam increased its engagement with the media to document, track and publicise electoral commitments, and to articulate the issue of candidates delivering on electoral commitments. / Activities for the second milestone will take place in the post election period of the project. Oxfam will continue to analyse the documented manifesto commitments and use this to support CSOs to hold elected councillors to account. / Recommendations: / Oxfam have recommended an increased use of drama – dramatized messaging – for future voter education in the context of high levels of illiteracy. / Impact Weighting (30%): / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A

Output 2: 216,000 Somaliland voters are aware of political candidates, their agenda and the electoral process
Output 2 score and performance description: B –outputs moderately did not meet expectations / Civic and voter education, which involved extensive outreach activities, performed well and contributed significantly to the level of awareness amongst the population. The use of media to target rural communities and the youth was appropriate (using national radio, national televisions, cultural dances and public circus performances).
Progress against expected results: / Milestones proposed were: / First phase of the civic education and awareness campaigns initiated by October / Civic education workshops for grassroots CSOs, communities, local government authorities and candidates undertaken / A baseline survey will be conducted during the first month of the project measuring political awareness and understanding of rights and entitlements of targeted citizens / Voter education materials were produced and disseminated in a range of various public voter education exercises. A total of ten dramatised plays and public awareness shows out of the planned 15 voter education public exercises have been conducted in ten out of the planned 15 districts, including Hargeisa, Baligubadle, Berbera,Sheikh, Gabilay, Erigavo, El-Afwayn, Borama, Ainabo and Oog. An estimated 50,000 participants attended the public voter education forums. These voter education exercises were recorded on video and aired on national satellite television. It is estimated that a total 140,000 people were reached through the national broadcast based on viewership statistics. Mobile phone messaging have been developed and disseminated through the biggest telecommunications company in Somaliland, Telsom, as part of public voter education exercises, in all the regions or Somaliland. / Additional dramatised voter education messages were developed and were aired before the elections on national television stations and national radio broadcasting station including Hargeisa radio. / Overall, nine out of thirteen planned civic education workshops were undertaken in nine districts including Hargeisa, Baligubadle, Berbera,Sheikh, Gabilay, Borama, Burao, Odwayne and Ainabo. A total of 270 participants, from local government candidates, CSOs and community representatives, of which approximately 40 % were women, attended. / The planned baseline survey did not happen as planned due to project staff turnover, though adequate monitoring data was gathered. Oxfam is proposing not to undertake an external baseline survey but will instead triangulate monitoring data collected with that collected by the NEC and other stakeholders.
Recommendations: / The shortened timeframe impacted on the project, and future activities need to start at least six months prior to any election. / Impact Weighting (45%): / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A

Output 3: 2,600 youth are empowered and actively involved in seeking their own political solution through their participation in 26 “democracy café” centres
Output 3 score and performance description: B - met expectations / This is a mixed pre- and post-election activity. Under this component, Oxfam seeks to target youth so as to facilitate their engagement in the political process. Awareness raising and civic and voter education activities are being undertaken through the establishment of “Democracy Cafes” and support provided to assist young people learns about issues of concern through peer to peer learning. This intervention encouraged the participants to document their emerging priorities and challenges facing them and to propose ways of addressing these.
Progress against expected results: / Limited progress has been made under this component since most of the planned activities were envisioned as post-election interventions. Nine youth “hot spots” have been identified (five universities, three secondary schools and the Civil Service Institute).
Recommendations: / Longer-term funding (this is a one year activity) is required to ensure that gains made through youth initiatives are not lost. / Impact Weighting (25%): / Revised since last Annual Review? / Risk: High / Revised since last Annual Review? N/A

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description : A: Outputs are in line with expectations / The proposed interventions under this programme have an aim of providing evidence and lessons to inform the design of a longer-term three year Somaliland Democratisation Programme. In this pilot phase of the programme, the proposed interventions aim to address two key interrelated problems that are: low participation in various governance structures; in terms of awareness of rights, entitlements and responsibilities; and weak institutional accountability to citizens within governance systems. This programme is endeavouring to capitalise on a potential window of change created by the opening of political space to new political associations and the reduction in the age limit for political candidates from 35 to 25 years. / Within the short time period of the project under review, an increased level of interest amongst the youth and women to participate in the democratic process has been widely noted. This has been developed and channelled by this project, and there has been significant and active participation in the public voter education exercises. The identification and tracking of the promises of political candidates who were seeking elected positions has been concluded and will form a basis on which, subsequently, the electorate can engage with their elected leaders. This will provide an opportunity for the voters to track the performance of elected public officials which is hoped will translate to greater transparency and accountability and greater responsiveness to the needs of the electorate. / 1.3 Direct feedback from beneficiaries / The feedback received from target groups has been positive. Public voter education exercises have been assessed, by participants, as having provided relevant and timely information to the general electorate. Most of the respondents have indicated that the mode of delivery, using dramatised plays, was effective and that it appealed to audiences of different demographic groups. The voter education exercises received very large turnouts – public feedback attributed this to the diverse and entertaining approaches applied in reaching the electorate. Workshops - for key stakeholders – generated positive evaluations. A number of people interviewed also expressed that the messages passed through the public forum have had a positive influence on peace dialogue ongoing in the country through other activities. The idea of working with youth in various hotspots has also been warmly welcomed.
1.4 Summary of overall progress / The overall progress of the project can be scored as A – the project met expectations, and is on track to continue to meet these.
1.5 Key challenges / The short time-frame due to the decision to hold the elections earlier than was anticipated – this led to the fast-tracking of some activities.
1.6 Annual Outcome Assessment / The project has made an important contribution to the outcome – the strengthening of democracy in Somaliland – and is expected to continue to do so during the remainder of the project period.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes. There was an underspent in the third quarter of the 2012-13 FY of £125,035 but this has been carried forward into the fourth quarter and will be utilised. / 2.2 Key cost drivers / The key cost drivers for this period were the costs associated with the provision of training and voter civic education – principally travel and staff costs – and the cost the production of materials produced. / 2.3 Is the project on-track against original timescale: Y/N / Yes / The SEP programme for Somaliland was designed as a 12 month action ending in September 2013. Oxfam is currently working against this timeframe and the project is currently achieving the targets set against the milestones set within the log-frame.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / A project baseline survey is planned and will be undertaken as per work plan / 3.2 Where an evaluation is planned what progress has been made? / An evaluation will be carried-out at the end of the project

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Low / 4.2 Assessment of the risk level / Tension was widespread prior to, during and immediately after the elections. General election-related concerns were experienced and these did present risks to the implementation of the project. In a number of areas there were complaints and discontent by some clans about the distribution of polling stations and the elders of these clans threatened to boycott the election. These issues were resolved. Whilst this did represent a risk, had a boycott occurred it would have had only a minimal impact on the project.
Risk of funds not being used as intended / This is limited as Oxfam’s internal and systems and controls are accepted as being strong. Oxfam has a long-standing relationship with its implementing partner HAVOYOCO over which it exercises financial control. There are no sub-grants within this project. / 4.4 Climate and Environment Risk / The main environmental impact related to travel within Somaliland undertaken by Oxfam’s local partner which was minimised to the extent possible. Travel to-from Somaliland was limited and utilised scheduled EC or UN flights. / Oxfam have a solid reputation on climate and environmental issues but, this notwithstanding, efforts will be made to ensure that, at the Hargeisa and Nairobi levels, they review their efforts to minimise adverse environmental and climate impact (e.g. by examining their local including internal working practices, energy use, use of paper, etc.).

5. Value for Money
5.1 Performance on VfM measures / The value for money will be calculated from the cost per output against the number for beneficiaries that will be targeted. Each of the outputs will have measurable indicators that would be monitored regularly. The minimum baselines would be used to gauge the performance of the project in attaining projected impact against international benchmarks for free and fair elections in terms of citizen’s participation / 5.2 Commercial Improvement and Value for Money / Not assessed / 5.3 Role of project partners / No significant role undertaken by other partners. / 5.4 Does the project still represent Value for Money : Y/N / Yes. The ability to analyse VfM is limited given the difficulty of assessing the value of the outcome (strengthening democracy) – given, however, the assessment that this project has contributed to this outcome, and the relatively limited inputs, it is felt that this is an appropriate investment and one which represents VfM. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / None

7. Conclusions and actions
The project, which commenced only in September, has performed well, and is on track to continue to do so. The fast tracking of pre-election stage an activity was unavoidable though has not negatively impacted on the project’s performance. The project will now focus on post-election activities including monitoring of election promises of elected candidates following the conclusion of the elections processes. / Oxfam raised the need for inter-SEP coordination and this has been noted.

8. Review Process
Discussions were held with Oxfam in November – prior to the election – and in early December. Oxfam staff – including one who travelled specifically from Somaliland – met with DFID, and written submissions were made by Oxfam, The short time frame – the project had only run for two months by the time of this review, thereby limiting the amount of work to be reviewed – and the fact that no field monitoring took place, have limited the comprehensiveness of the review. A full review will be undertaken in 2013.