Type of Review: Annual Review

Project Title: Kolkata Urban Services for the Poor (KUSP) Programme

Date started: 11/03/2004	Date review undertaken: 15/02/2013
## Introduction and Context

What support is the UK providing?
DFID is providing a £102.7 million support (£94.06 million FA and £8.64 TA) to Government of West Bengal to improve the quality of life of poor people in Kolkata Metropolitan Area (KMA). The project started in 2004 and FA support to the project came to a close on 31 March 2011 as part of DFID’s graduation from West Bengal; by then, a 100% FA utilisation and a TA savings of £5.5 million was noted. An agreement to continue the TA support from April 2011 to March 2015 with a commitment of £5.5m was agreed with GOI in April 2012. Under this support a Project Management Unit (PMU) and a Technical Assistance Support Unit (TASU) will be set-up.

What are the expected results?
What will change as a result of our support? / Through the FA and TA support (2004-2011), the following was targeted and achieved: / 70% proportion of poor (1.45 million) reporting satisfaction on inclusion of their ‘voice’ in urban local governments decision making and functioning (compared to no intervention); / 80% target slum dwellers (600,000 poor people) reporting improvement in access and coverage to basic services disaggregated by social groups (compared to no intervention); / Over 25% increase in household expenditure (compared to no intervention) (per capita daily expenditure up from $1.15/day to $1.44/day – World Bank has identified $1.25 per capita (income) per day as the poverty line. / Through the TA-only support (2012-2015), the following change is expected: / GoWB able to leverage central funding of Rs.200 crore (£22 million) directly benefitting 45,000 poor and slum residents access security of tenure under Rajiv Aawas Yojana (RAY). / GoWB able to avail the central incentive fund set up under the 13th Central Finance Commission directly benefitting 100,000 additional poor people by providing access to improved sanitation. / What are the planned Outputs attributable to UK support? / Through the FA and TA support (2004-2011), the following outputs are attributable to UK support: / Improved urban planning and governance in Kolkata Metropolitan Area Urban Local Bodies; / Improved access to urban basic services in target slums and convergence with national programmes; / Local economic development promoted; / Service delivery mechanisms improved in Kolkata Municipal Corporation / Through the TA-only support (2012-2015), the following change is expected: / Improved urban planning and governance in Kolkata Metropolitan Area urban local bodies; / Improved access to central plan and non-plan funds (centrally sponsored schemes); / Improved security of tenure to poor people; / Service delivery mechanisms adopted in Kolkata Metropolitan Area urban local bodies. / How will we determine whether the expected results have been achieved? / Robust monitoring and evaluation systems are in place to determine the achievement of the expected results.

What is the context in which UK support is provided?
What need are we trying to address? / The Kolkata Metropolitan Area (KMA) consists of 41 urban local governments. Around 35% of total population of KMA lives in slums and informal settlements largely constituting of Scheduled Castes and Muslims. They live in a degraded environment and lack basic services. Strained state fiscal resources and lack of capacities within state institutions were acting as a barrier to take forward this new approach of testing new models of innovative inclusive planning and governance, and providing access to basic services to the poor in an inclusive manner. / What will we do to tackle this problem? / The UK support upto 2011 (FA and TA) looked to fill this critical gap by taking a three-pronged approach. Firstly, KUSP introduced inclusive urban planning and governance; secondly, KUSP provided basic services in the worst-off slums as well as fill in critical infrastructure gaps at the town-level and inter-municipal level that directly benefits the poor; and thirdly, KUSP supported a process of local economic development aimed towards skill building and micro-credit development among the poor. Intrinsic to all three approaches was capacity building of targeted at state and local governments, non-government organisation (NGOs) and community groups (comprising of slum residents). / The TA-only (2012-15) support will look at improving access to sanitation and security of tenure for urban population residing in slums and informal settlements. This will be done by positioning a DFID project management unit (PMU) within the Change Management Unit (CMU) to support GOWB access and implement the slum-free cities programme, as well as a DFID TA Support Unit within CMU to help sustain second generation KUSP reforms and to create improved access to sanitation among the urban poor. / Who will be implementing the support we provide? / The Municipal Affairs Department is the lead department for this project. A Change Management Unit (CMU) has been set up under the Municipal Affairs Department to oversee the implementation of the programme. Till 2011, the CMU was being funded jointly by GoWB and DFID; in the TA-only phase (2012-15), CMU is being completely funded by GOWB.

## Section A: Detailed Output Scoring

Output 1: Improved Urban Planning and Governance in KMA urban local bodies (ULBs)
Output 1 score and performance description: / Output score: A / Performance Description: The progress described here is attributable mainly to the momentum from the earlier FA+TA intervention but can also be ascribed to some of the activities of the TA only intervention. Overall, the output has met expectations. Own-source revenue increase has primarily been led by substantial growth (almost doubling) of non-tax revenues, thus demonstrating ULBs’ increased capacity to leverage resources beyond the traditional tax methods. E-governance has shown substantial progress in the last reporting year with the six key modules that have a direct citizen interface being prioritised by GoWB and scaled up across the 85 additional ULBs in the state; in addition the e-procurement portal has been established. Staffing rules are close to being finalised which mean that ULBs will be able to recruit permanent staff against the 381 positions created through KUSP (across 125 ULBs) which is better than the yearly contract renewal process currently undertaken.
Progress against expected results: / Indicator 1.1: aggregated own source revenue collection of KMA ULBs / Baseline: Rs.14,25 lakh (2005-06); 2012 target: Rs.27.98 lakh / An average annual own-source revenue growth of 24.3% was registered for KMA ULBs (excluding Kolkata Municipal Corporation) in 2011-12. The bulk of this increase on account of a more than two-fold growth in non-tax revenues demonstrating increased capacities within ULBs to raise revenues beyond traditional tax avenues. / Indicator 1.2: number of ULBs in which e-governance system fully operationalised with satisfied slum customers / Baseline: nil (2005-06); 2012 target: 40 ULBs / The six priority modules of e-governance have been rolled out to all 40 KMA ULBs. GoWB support to e-governance reforms initiated by KUSP continues strongly with roll out done in non-KMA ULBs. E-procurement has also been initiated in Jan 2013 wherein all procurement above Rs.20,000 under ambit of the Municipal Affairs Department, ULBs and all para-statals falling under its jurisdiction will be put up. / Indicator 1.3: proportion of ULB expenditure spent on pro-poor service delivery and related operation and maintenance (O&M) and proportion of O&M costs met through own sources of revenue. / ULBs are spending around 30% of their earmarked budget for pro-poor development in KMA ULBs; this is higher than the 25% mandated by GoWB. DFID/KUSP has already put in place a project management unit (PMU) within CMU that has been appointed as the state level nodal agency (SLNA) for West Bengal for Rajiv Aawas Yojana (RAY). The DFID PMU was made operational in October 2012. Since mandatory earmarking of municipal budgets for pro-poor development is a reform requirement under RAY, KUSP will continue to support ULBs in meeting this target as well as monitoring the same. / Other Relevant Information: / Recruitment rules for municipal cadres, including cadres introduced by KUSP, are close to being finalised. This will ensure institutionalisation of the three positions introduced by KUSP in the ULBs, as well as help GoWB respond to reform challenges set by the 13th Central Finance Commission. / Policy/Strategy studies undertaken as part of the pre-2011 support are currently being reviewed. These will be discussed afresh in the current political environment, and based on inputs received during consultation, the same will be formalised. The West Bengal Urbanisation Strategy, Land Tenure Note, and the Roadmap for KMA Municipalities for Action on Climate Change are the two studies that will be targeted initially. / Recommendations: / The DFID Technical Assistance Support Unit (TASU) proposed for KUSP should be mobilised by August 2013. / It should provide technical support to the e-governance roll out, as well as to support implementation of other reforms that have been prescribed by the 13th Central Finance Commission to access its Incentive Funds; these reforms include setting up of property tax valuation board, move to unit area based taxation, among others. / It should support Municipal Affairs (MA) Department’s endeavour to review policy and strategy documents prepared under KUSP, adapt them to current priorities, and implement these. / CMU and DFID to follow-up with GoWB to ensure that Recruitment Rules for ULB positions are adopted by May 2013. / Both DFID TASU and DFID project management unit (PMU) support should ensure capacity building of CMU staff, as well as identified champions in MA Department. The two DFID units should also support MA Department and CMU structure capacity building for ULBs towards effective implementation on centrally sponsored schemes. / Logframe revision: based on the outputs agreed for the proposed DFID TASU at end of its inception phase (September 2013), the project logframe should be revised in consultation with GOWB by October 2013. / Impact Weighting (%): 45% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Improved access to urban basic services in target slums and convergence with national programmes
Output 2 score and performance description: / Output score: A / Performance Description: this output was supported by DFID FA upto March 2011. With no FA capital available now, it is difficult to report on progress directly attributable to KUSP. However, there is evidence that GoWB is sustaining this output and reforms; a positive ripple effect of KUSP interventions is being felt in terms of improved performance of slum improvement projects taken up under centrally sponsored schemes such as JNNURM. CMU has been identified as the state level nodal agency for implementation of RAY in West Bengal. KUSP/DFID has positioned a project management unit (PMU) inside CMU to provide capacity augmentation required for accessing the extremely complex yet critically important RAY project.
Progress against expected results: / Indicator 2.1: number of poor getting access to basic services, and proportion of satisfaction of O&M / Baseline: nil (2005-06); target: 1.2 million (2012) / KUSP has so far directly benefited 1.32 million slum dwellers by providing access to improved water and sanitation; an additional 55,000 urban poor have benefited this reporting year from intra-municipal infrastructure (water, sanitation, drainage, low-income housing) from West Bengal Municipal Development Fund (WBMDF). / Indicator 2.2: number of households taken out of poverty through coordinated Mission approach. / Baseline: nil (2005-06); target: 7000 (2011) / Till date, about 26,000 households have benefited from coordinated Mission approach against the 7,000 household target through the Mission for Elimination of Poverty in Municipal Areas (MEPMA). However, since CMU was appointed the state level nodal agency (SLNA) for RAY, coordinated mission approach for urban poverty reduction in the state is being ensured by CMU. Consequently. MEPMA has become non-operational unit for now. However, a coordinated approach to pro-poor development in ULBs in the state is being led by CMU, primarily on account of the legacy built by KUSP. CMU is also expected to play a leading role in accessing of the proposed National Urban Livelihoods Mission (NULM); it is already playing the pivotal role on taking forward urban health projects in the state in association with State Urban Development Authority. Urban sanitation remains the only area where a coordinated approach does not exist in the state in spite of the West Bengal Urban Sanitation Strategy being developed under KUSP and adopted by GoWB. / Target 2.3: proportion of target slum dwellers reporting Honorary Health Workers (HHW) as first point of contact for RCH and immunization purposes / Baseline: nil (2005-06); target: 60% (2012) / An independent evaluation (2011) indicated that 79% slum households reported HHW as the first point of contact for RCH and immunisation. Due to limited resource availability, KUSP TA is not being used directly for urban health related activities although CMU remains at the centre of GoWB’s policy/strategy formulation on urban health, and has taken a number of initiatives that were originally introduced through KUSP. This includes scaling up work on vaccination/immunisation in urban areas, setting up health clinics in urban areas, and setting up of reproductive child heath (RCH) centres in each ULB. / Other Relevant Information / West Bengal Municipal Development Fund (WBMDF): As part of the KUSP FA support (upto 2011) a municipal development fund for West Bengal was set-up with a corpus contribution of Rs.82.6 crore from DFID and Rs.37.83 from state government, ULBs and urban para-statals. WBMDF primarily funds intra-municipal infrastructure projects and has been instrumental for ULBs to access central schemes such as JNNURM where the ULB component is usually raised from the Fund. In 2012-13 reporting period, projects of Rs.5.58 crores (£0.65 million) have been approved by WBMDF. However, loan sanction under WBMDF has been reducing over the last two years, primarily on account of JNNURM coming to a close (see figure below). / Recommendations: / Coordinated mission approach on sanitation: the proposed DFID TASU should look at taking up a coordinated approach towards improving urban sanitation in West Bengal. / It should support preparation of city sanitation plans for upto five ULBs, / It should support adoption of service level benchmarks (water, sanitation, solid waste management) for urban areas of West Bengal, and preparation of performance improvement plans and institutions strengthening improvement plans. / The logframe amendment exercise should discard outputs that are no longer directly supported by DFID, and being sustained entirely by GoWB funding. / DFID needs to consider if it is useful to have a membership on the Board of Trustees of municipal development funds set-up by DFID. While on one hand this provides opportunities to engage at state-level beyond DFID FA support, on the other hand the decision needs to be balanced with risks posed with this approach. / Impact Weighting (%): 40% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No / Disbursement in Rs. lakh

Output 3: Economic Development Promoted
Output 3 score and performance description: / Output score: A / Performance Description: Performance around Innovative/Challenge Fund (I/CF), skill-based training and mobilisation of self-help groups (SHGs) has been satisfactory and met expectations in spite of FA funds not being available to directly support the last two activities. GoWB and Jamsetji Tata Trust have agreed to extend the Trust support on I/CF for 30 months, although some concerns remain on rate of utilisation of I/CF corpus. Like Output 2, this output is being sustained by GoWB funding.
Progress against expected results: / Indicator 3.1: number of poor accessing I/CF whose income have increased / Baseline: nil (2006); Target: 200,000 (2012) / An additional 10,000 poor people benefited from activities under I/CF in this reporting year taking the number of total beneficiaries to 252,000. Jamshetji Tata Trust has in principle agreed to continue their support to I/CF for an additional 30 months sustaining the support upto 2014. The Trust is also exploring allocating additional funds to I/CF and a decision on this is to be taken by their Board soon. New areas to be supported have also been identified including promotion of micro-enterprises, support to disabled persons, and reduction of domestic violence. There are concerns on slower utilisation of corpus funds with Rs.2.58 crore still available for spending. DFID and CMU agreed to review this closely. / Indicator 3.2: Number of additional poor youth trained and proportion of these provided work placements / Baseline: nil (2006); Target: 3000 (2011) / No activities were undertaken under wage employment training in this reporting year through CMU as no FA was available to support this; GoWB is independently taking this ahead by linking this to ongoing state/central programs. Under KUSP, till 2011, 18,738 poor youth have received wage employment training under KUSP. CMU is now providing technical support to GoWB on this aspect by helping the state expand on the range of self-employment and job-employment training in urban areas, based on learning from KUSP. / Indicator 3.3: Number of additional self-help groups (SHGs) mobilised and proportion of these linked to banks / Baseline: 17,400 (2008); Target: 100,000 (2011) / Additional 828 SHGs were mobilised in this reporting year. Although FA funds are not available, GoWB is taking ahead this initiative linked through Swarn Jayanti Shehri Rojgaar Yojana (SJSRY) – a centrally sponsored scheme on self employment, and other similar state schemes. A total of 38,232 thrift and credit groups (SHGs) have been mobilised with 56% accessing loans from SJSRY revolving funds. / Recommendations: / DFID and CMU to ensure that I/CF corpus is completely spent by 2015, and also explore avenues for accessing support from other institutions for corpus contribution to I/CF. / Impact Weighting (%): 15 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
KUSP was originally developed for a seven year period (2004-2011). However, as part of the DFID updated strategy for partnership with West Bengal, theTA support under KUSP has been extended till March 2015. The formal agreement and amendment of memorandum of understanding with Government of India on extension of the TA support to KUSP was received in April 2012. Consequently, the project logical framework will need to be amended to reflect this changing nature of support based on recommendations of this Annual Review.
1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: / The program receives an overall output score of A. / It has met expectations in most outputs and exceeded expectations in a few areas as GoWB has taken up the challenge of sustaining the KUSP-introduced reforms agenda even after no FA is available to the project. Staffing Rules are being issued for all three positions introduced by KUSP at ULB level which means that recruitment for the 381 new positions will happen over this reporting period. This will be a critical factor in ensuring sustainability of the KUSP change initiation agenda. CMU is rolling out second generation reforms in planning and financial management across all ULBs in the state. E-governance reforms are also being rolled out to all ULBs across the state, and an e-procurement portal has been set up. Support from DFID PMU to CMU for accessing RAY would ensure that slum dwellers and residents in poor pockets of the city continue to access improved urban basic services, thus sustaining the in-situ slum improvement approach supported by DFID through KUSP and its predecessor DFID projects. I/CF continues to deliver on the livelihood agenda in the urban sector in the state, and with the proposed National Urban Livelihoods Mission (NULM) likely to be set-up shortly, CMU may be appointed the state nodal agency for the same considering the KUSP legacy on this subject. However, as both DFID support agencies are mobilised (PMU mobilised in October 2012 and TASU likely to be mobilised in August 2013), the project logframe needs to be amended so that it reflects the outputs achieved directly by the DFID TA support, and is attributable completely to DFID. / 1.3 Direct feedback from beneficiaries / Meetings were held with government partners, including those representing the West Bengal Municipal Development Fund and the Innovative/Challenge Fund. Government partners have strongly appreciated continuing support of KUSP and the TA support that has been initiated in October 2012. TA support for accessing RAY is critical to enable West Bengal access substantial central grant funding under the programme.
1.4 Summary of overall progress / The overall progress has been satisfactory and met expectations of a TA-only relationship. KUSP, and more particularly CMU, continues to influence policy/strategy making around urban poverty alleviation in West Bengal and is now serving as the state level nodal institution for the state on the RAY programme. Since FA support closed down in March 2011, GoWB has taken considerable efforts to ensure sustainability of most KUSP interventions either dedicating resources from their own funds or linking these with ongoing state/central programs. Reforms continue getting political support with focus on e-governance, including e-tendering, development planning, catalysing private sector financing for urban infrastructure and low-cost housing, among others. DFID TA is supporting GoWB achieving these reform priorities; a project management unit (PMU) support for accessing funding under the slum-free cities programme of national government (Rajiv Aawas Yojana) has already been mobilised, while a technical assistance support unit to facilitate GoWB take ahead policy priorities around improved urban governance and service delivery is in the process of being structured and likely to be in place by July 2013.
1.5 Key challenges / Going ahead, the key challenge will be to ensure that the KUSP reforms agenda remains high on the priority of GoWB. This will ensure sustainability of the reforms agenda as well as the inclusive approaches adopted by KUSP towards achieving project outcomes.
1.6 Annual Outcome Assessment / KUSP continues to influence improvement of quality of life of the poor, particularly slum population in KMA ULBs. It is taking ahead the strategic/policy reforms that were initiated under this program, as well as supporting GoWB in accessing RAY. The second generation DDPs and e-governance initiatives are likely to increase effective service delivery in urban areas. Accessing RAY will allow GoWB to continue with its legacy of in-situ slum upgradation focusing on improved basic service provision. With the proposed TA support for developing city-wide sanitation improvements through KUSP, access to sanitation in non-slum poor pockets of urban areas is also likely to improve.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: As mentioned, there has been a 12 month delay in start-up due to a delay in getting government approvals. The first year of operation has therefore practically shifted from 2001 to 2012. Since then the PMU has been operationalized and the procurement process for hiring an agency as a technical support unit has been initiated. Overall the TA only project will complete its activities and meet the spend forecast by the project end date of March 2015. / 2.2 Key cost drivers / The key cost drivers are expected to be the TA contract agencies. DFID has already positioned a project management unit (PMU) within the Change Management Unit, KUSP. This PMU contract includes 63% cost for services/fees, 27% cost for administration/out of pocket expenses, and 10% for a resource pool. A Technical Assistance Support Unit (TASU) is proposed to be mobilised by August 2013. It is expected that this contract would include around 45% cost for services/fees, 23% cost for out of pocket expenses, and 32% for resource pool. / 2.3 Is the project on-track against original timescale: Yes / Yes. The program has now been extended to 31 March 2015; only TA support is now available under this project. However, substantial delays in approval from GOI end meant that the memorandum of understanding for the project was amended to accommodate a TA-only relationship in April 2012 only, thereby leading to an almost 12-month start-up delay.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence are noted and thus, no implications are qualified. Evidence is generated from central and state government published data sources, and project management information system that is managed by CMU. / 3.2 Where an evaluation is planned what progress has been made? / A third-party impact assessment was undertaken in March 2011 primarily focusing on impacts of FA; an independent end-of-project evaluation will be initiated to feed into the project completion reporting exercise. This study will be commissioned in Sep 2014 based on a ToR jointly prepared by DFID and GoWB (in Aug 2014). The Research and Evaluation Department (RED) has recently commissioned a meta-review of DFID urban programs that covers KUSP as one of the detailed case study projects. Findings from this review will also feed into understanding the impact and sustainability of KUSP interventions.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The original output risk rating of ‘medium’ continues, primarily on account of concerns of time lag in getting TA support mobilised. Assumptions taken into account while preparing the project (political support for sustained poverty reduction, effective leadership at KUSP, capacities built at ULB level to undertake poverty mainstreamed development agenda, etc.) still remain qualified.
Risk of funds not being used as intended / Low. Since the program only provides for TA support upto March 2015 (which is directly managed by DFID), risks of funds not being used as intended is very low. / 4.4 Climate and Environment Risk / No present climate and environment risk identified from ongoing activities.

5. Value for Money
5.1 Performance on VfM measures / A £5.5 million TA support is likely to help GOWB leverage £22 million of central funding under Rajiv Aawas Yojana, and an additional £14 million from the 13th Central Finance Commission incentive fund. / A more detailed VFM study for urban TAs can be commissioned in 2014. / 5.2 Commercial Improvement and Value for Money / Towards ensuring VfM through TA consultants, it has been proposed that the entire set of TA support areas agreed between DFID and GoWB be split into two large umbrella contracts, rather than a series of medium-sized contracts. This will ensure saving of administration time within DFID, and make it easier for both GoWB and DFID to monitor progress of the TA support, and ensure overall quality control in delivery of the projects. The first TA exclusively looks at the slum free cities under RAY and the second TA will look at Governance and Sanitation. Skill sets and ways of working for both the TAs are very different. / 5.3 Role of project partners / Role of project partners remains strong. GoWB has agreed to sustain CMU until March 2015, Staffing Rules are close to being finalised, e-governance reforms that could not be initiated completely within the FA life of KUSP is being taken ahead by GoWB, among others. / 5.4 Does the project still represent Value for Money: Yes. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / None.

7. Conclusions and actions
The DFID Technical Assistance Support Unit (TASU) proposed for KUSP should be mobilised by August 2013. / It should provide technical support to the e-governance roll out, as well as to support implementation of other reforms that have been prescribed by the 13th Central Finance Commission to access its Incentive Funds; these reforms include setting up of property tax valuation board, move to unit area based taxation, among others. / It should support Municipal Affairs (MA) Department’s endeavour to review policy and strategy documents prepared under KUSP, adapt them to current priorities, and implement these. / CMU and DFID to follow-up with GoWB to ensure that Recruitment Rules for ULB positions are adopted by May 2013. / Both DFID TASU and DFID project management unit (PMU) support should ensure capacity building of CMU staff, as well as identified champions in MA Department. The two DFID units should also support MA Department and CMU structure capacity building for ULBs towards effective implementation on centrally sponsored schemes. / Logframe revision: based on the outputs agreed for the proposed DFID TASU at end of its inception phase (September 2013), the project logframe should be revised in consultation with GOWB by October 2013. / The logframe amendment exercise should discard outputs that are no longer directly supported by DFID, and being sustained entirely by GoWB funding. / Coordinated mission approach on sanitation: the proposed DFID TASU should look at taking up a coordinated approach towards improving urban sanitation in West Bengal. / It should support preparation of city sanitation plans for upto five ULBs, / It should support adoption of service level benchmarks (water, sanitation, solid waste management) for urban areas of West Bengal, and preparation of performance improvement plans and institutions strengthening improvement plans. / DFID needs to consider if it is useful to have a membership on the Board of Trustees of municipal development funds set-up by DFID. While on one hand this provides opportunities to engage at state-level beyond DFID FA support, on the other hand the decision needs to be balanced with risks posed with this approach. / DFID and CMU to ensure that I/CF corpus is completely spent by 2015, and also explore avenues for accessing support from other institutions for corpus contribution to I/CF. / A value for money exercise of the TA support being provided through KUSP could be initiated in 2014.

8. Review Process
The joint annual review was led by Secretary, Municipal Administration, GoWB and supported by Project Director CMU, Managing Trustee WBMDF, the DFID-sponsored Project Management Unit (PMU) team. DFID was represented by the Urban Advisor and the Economic Advisor. The entire CMU team and concerned nodal officers from the MA Department and the West Bengal Municipal Development Fund were present. The team reviewed progress over the last reporting year through a series of presentations and discussions. / A meeting was also held with Principal Secretary, Urban Development Department. / Project scoring has been done by DFID.