Type of Review: Annual Review

Project Title: Support for the European Bank for Reconstruction and Development (EBRD) to provide technical assistance to Middle East and North Africa reform countries

Date started: March 2012	Date review undertaken: March 2013

ARIES Project Number: 203056

Description	Scale
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

## Introduction and Context

What support is the UK providing?
The UK is providing £5 million to the European Bank of Reconstruction and Development (EBRD) to enable it to provide technical advice and assistance to countries in the Middle East and North Africa (MENA) Region, and specifically Egypt, Tunisia, Morocco and Jordan. / The UK’s funds are contributing to the EBRD’s Multi-Donor Account for technical cooperation in (what the EBRD titles) the ‘Southern and Eastern Mediterranean’ (SEMED) region. The Multi-Donor Account, to which the UK is currently the largest bilateral donor, was established by the EBRD in 2012 to enable the Bank to employ technical experts and incur other costs to provide direct advice and training to private and public sector clients in the new countries. The Account supports activities including: strengthening business management of small and medium sized enterprises and increasing their access to finance; improving the productivity of agricultural businesses and widening their range of local input suppliers; developing projects for the financing of socially desirable and environmentally acceptable infrastructure improvements; reform of legal, social and environmental policies to achieve stronger, more inclusive and more sustainable growth. / UK funding is supporting a four year programme spanning financial years 2011/12 – 2014/15. An additional £50,000 of funding is planned to be used to carry out an independent evaluation of the intervention in the final six months (October 2014 – March 2015).

What are the expected results?
The UK’s funding is expected to contribute to an impact of ensuring inclusive and sustainable growth in the MENA region. It will do this by, in combination with contributions from other donors, delivering the outcome of increased investment and private sector growth in Egypt, Tunisia, Morocco and Jordan. It is intended to result in: / £500m of total annual EBRD investments, linked to technical cooperation, in the four SEMED countries by 2014; / A total increase in employment of 4,250 in businesses that have received direct financial and technical assistance from the EBRD by 2014, including an additional 2,125 women employed; / A cumulative increase of £400m of Public-Private Partnership (PPP) investments in infrastructure improvements as a result of donor-funded technical cooperation from the EBRD; / Significant legal, social and environmental policy reforms to promote more inclusive and sustainable growth, made by at least 6 public sector and 18 private sector clients. / The programme is expected to deliver 5 outputs: / Output 1: Strengthened ability of SMEs to grow sustainably. By end 2012, 80 enterprises, including 20 majority female managed enterprises, were expected to be receiving support through the EBRD’s Business Advisory Services programme. / Output 2: Strengthened agricultural productivity and improved food supply chains. By end 2012, 10 agribusinesses clients were expected to be receiving EBRD assistance and demonstrating a 10% increase in their input suppliers. / Output 3: Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure. By end of 2012, the EBRD was expected to have completed 3 PPP feasibility studies, with at least one of these leading to an investment agreement. 100% of studies were expected to include environmental, climate risk and social impact assessments according to best practice. / Output 4: Strengthened capacity of government and private sector entities to implement legal, social and environmental reforms to support inclusive and sustainable growth. By end of 2012, 10 sovereign clients and 30 private sector clients were expected to be receiving high quality advice from the EBRD on legal, social and environmental reforms. / Output 5: Better evidence collected and disseminated of priority policy needs and expectations for successful reform. By the end of 2012, good quality environmental and social assessments were expected to be completed for all four countries.

What is the context in which UK support is provided?
The need for more inclusive and sustainable economic growth in MENA countries / The wave of uprisings that swept across several countries in the Middle East and North Africa (MENA) in early 2011, and which became known as the ‘Arab Spring’, highlighted a number of underlying economic, political and social problems. Although the MENA region generated GDP growth of almost 5 per cent a year over the decade 2000-2010, many countries were less successful in providing widespread economic opportunities for their people. / Unemployment has remained high in many of the countries of the region. Current unemployment rates are between 12-18% in Egypt, Tunisia and Jordan, compared to a global average unemployment rate of around 6%. Unemployment is especially high among young people. According to the World Bank, average youth unemployment in the region is around 25%, and where young people do work, they are typically employed in low paid, low productivity jobs. Unemployment among women is also a key concern. In 2010, the unemployment rate for women in the region was approximately 15%, compared to 7.8% for men. And despite the middle income status of MENA countries, poverty remains a significant challenge. Based on 2005 data, more than 15% of the population live below $2 per day in Egypt and Morocco. / Achieving more inclusive economic growth is therefore fundamental to sustaining successful political transition and meeting the needs of aspirant populations, particularly young people, in the ‘Arab Spring’ countries. / Key economic reform challenges in the ‘Arab Spring’ countries / The political changes brought about by the Arab Spring have created opportunities for addressing key economic and social challenges. There are several areas of reform that are important for generating more inclusive and more sustainable economic growth, including: / strengthening conditions for private sector development, particularly for small and medium sized enterprises (SMEs). SMEs offer significant potential for employment creation in these countries but face constraints, including high regulatory barriers and lack of access to finance. / improving the functioning of agricultural markets by strengthening food production and ensuring more integrated agricultural supply chains. MENA countries import around 50% of their food consumption. / upgrading infrastructure at national and local levels, including in transport, power and water. According to the World Bank, MENA countries overall need to invest between $75 - $100 billion per year in infrastructure to grow at previous rates and to boost competitiveness. / Strengthening the ability to trade. MENA is one of the least integrated regions in the world, with a share of world non-oil exports that is under 1%. There is scope to increase growth and make it more inclusive by strengthening capacity to trade, especially of SMEs. / The UK’s role in support of economic reform in ‘Arab Spring’ countries / Despite the current opportunities countries such as Egypt, Morocco, Tunisia and Jordan face constraints in implementing key reform measures required. Aside from political constraints, there are also gaps in terms of the technical capacity and the financial resources needed. Challenging economic conditions following the Arab Spring, associated with declines in inward investment and tourism revenues, have made these constraints more binding in the short term. The UK, alongside the broader international community, has a role to play in supporting these countries in their reform efforts and in helping them to achieve greater social and economic inclusion. / Why the UK is supporting the EBRD / The amount of funding and technical expertise the UK can provide directly to support economic reform in ‘Arab Spring’ countries could not be expected, on its own, to deliver the changes on the scale required. More is likely to be achieved by working with and through other institutions that are better placed to channel more substantial financial and technical resources. The UK identified the EBRD as an institution through which it should channel support to the region: / The EBRD is expanding its geographical mandate and is a ‘new player’ in the region. The UK, including through the Deauville Partnership, has emphasised the value and importance of the EBRD becoming an additional form of support to the region, particularly given its specialised role of providing direct assistance for private sector development and its relevant experience of supporting economic transition in other contexts; / The EBRD is expected, in due course, to invest up to €2.5bn per year in the region, but will only be able to do this once full ratification of changes to its Articles has been achieved and full country presence has been established. In the meantime, donor resources can enable the Bank to start providing technical assistance to businesses and public sector clients, and help prepare the ground for substantive investments. The EBRD is drawing on donor inputs through several channels including direct contributions from the EU’s Neighbourhood Investment Fund and the Multi-Donor Account for technical cooperation. The UK’s contribution to the EBRD’s Multi-Donor Account is therefore expected to help facilitate new assistance to the region. / By making a funding contribution to the EBRD for its new operations in SEMED, the UK expects to gain opportunities to work closely with the Bank to help shape its approaches in ways that address the fundamental challenges around economic and social exclusion in the region, including for youth and women, and that incorporate strong approaches to targeting and monitoring results.

## Section A: Detailed Output Scoring

Output 1: Strengthened ability of SMEs to grow sustainably
Output 1 score and performance description: / B – Output moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2012 Achieved 2012 / Annual number of enterprises (of which majority female managed) receiving business advice under Business Advisory Services (BAS) programme 80 (20) 1 enterprise (in Jordan) is so far receiving support through the BAS programme, with 2 enterprises in the pipeline to receive support. 1 out of the 3 enterprises is majority female managed. / Annual number of enterprises (of which majority female managed) receiving business advice under Enterprise Growth programme 0 2 enterprises in Jordan (ICT and food processing sectors) are receiving support. Neither of these are majority female managed. / Annual number of enterprises (of which majority female managed) financed directly under EBRD's Local Enterprise Facility 0 Good progress is being made in establishing support for enterprises under the EBRD’s Local Enterprise Finance (LEF) initiative, for instance resulting in a LEF loan being provided to Moroccan oil and soap producer. / Percentage of business advisory projects scoring as successful or highly successful 0 It is too early for projects to have finished. / Performance against the first indicator appears to have been well below expectation. There are several reasons for this: / EU funding for business support activities in Egypt, Tunisia and Morocco and Morocco has continued for longer than expected and consequently the Multi-Donor Account has only supported activities in Jordan. Through EU support, there are 50 BAS projects in Egypt, Morocco and Tunisia (of which 16 are supporting majority female managed enterprises) and 26 EG projects (of which 5 are supporting majority female managed enterprises). At the time of review, the Multi-Donor Account was starting to take over the funding of activities in these countries. / The EBRD has encountered delays in recruiting BAS teams to work in Jordan which has slowed down progress there. / Whilst the target for the end of the programme for the first indicator is still considered to be realistic, in hindsight the level of assistance expected in the first year (when projects were being established) was a little too high. It can be noted that funding from the MDA has just been approved for a new BAS project that will target assistance at 60 female entrepreneurs in Egypt. / The Bank has been making good, and better than expected, progress against some of the other indicators being used to measure this output. / Overall, the output moderately did not meet the expectation. / Recommendations: / DFID and EBRD should re-examine the milestones and targets under this output. This should reflect the right balance between what the Multi-Donor Account for technical cooperation and what other funding sources are expected to support, allowing some flexibility for uncertainties on funding decisions. / EBRD should aim to ensure that BAS teams are fully in place and that targeted levels of support are being provided from 2013. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Strengthened agricultural productivity and improved food supply chains
Output 2 score and performance description: / B – Outputs moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2012 Achieved 2012 / Annual number of agribusiness clients receiving EBRD assistance through donor-funded technical cooperation 10 2 agribusiness clients are receiving support in Jordan – the Zalloum Group (biscuits and canned food) and the Hammoudeh Group (vertical integration of bird supply chains). 3 other agribusinesses in Jordan are in the pipeline for support. / Percentage year-on-year increase in number of input suppliers to EBRD agribusiness clients 10% There is no evidence yet to suggest that agribusiness clients have increased their numbers of input suppliers. / Percentage of projects with agribusiness clients scoring as successful or highly successful 0 No projects have yet been completed to enable assessment of project quality. / Performance against the first indicator has been below expectation so far, but as with output 1, some projects in other countries have been funded by the EU (6 projects started in 2012 in Egypt, Morocco and Tunisia) rather than the Multi-Donor Account and funding from the latter for projects in these countries has not yet started. / It is too early in the implementation of projects to expect that an increase in input suppliers has occurred, as envisaged for the second indicator. / As none of the projects have been completed, it is too early to make assessments of their quality. But those being supported by the Multi-Donor Account are progressing according to plan. / Overall, performance has been moderately below expectation. / Whilst not specifically reflected in the output indicators, the EBRD has been using the Multi-Donor Account to support a large regional project on food security costing around $1.5m. This project includes four modules: i) supporting an inter-regional forum on food security, ii) country agribusiness policy workshops to gather private stakeholder views and identify country-specific policy recommendations, iii) analysis of food chains in the four countries, iv) launch of the Med-Agri platform for knowledge exchange among public, private and IFI stakeholders across the region. The project has been making good progress, with inter-regional forum held in 2012 leading to specific follow-up in Egypt, and a value chain analysis has been carried out on the Moroccan olive oil and oil seeds sector. The Med-Agri platform has also been launched. It is not clear, however, what the actual outcomes of the project are likely to be. / Recommendations: / DFID and EBRD should re-examine the milestones and targets under this output to reflect the right balance between what is expected to be supported by the Multi-Donor Account for technical cooperation and what by other sources; / DFID and the EBRD should also reconsider the output indicators to reflect the EBRD’s broader policy work on food security, as appropriate. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure
Output 3 score and performance description: / A – Outputs met expectation.
Progress against expected results: / Indicator Milestone 2012 Achieved 2012 / Cumulative number of comprehensive PPP feasibility studies completed (of which lead to investment agreements) 3 (1) Whilst not necessarily PPP feasibility studies, the Bank has used the Multi-Donor Account to carry out several preparatory studies for investments, including a due diligence study for an electrification project in Morocco and a feasibility study for a regional investment fund in sustainable energy. 2 studies have so far been completed. / Several other assessments are being carried out including a feasibility study for investment in water infrastructure improvements in Jordan (through the Yarmouk water company), assessments of sub-sovereign frameworks for financing in Tunisia and Jordan, a market demand study for sustainable energy investments in Jordan, and sector studies of ICT in Tunisia and Morocco. / Studies have resulted in the EBRD providing a sovereign guaranteed loan of €60m to the Office National de l’Électricité (ONE) for rural electrification in Morocco, and in potential investors (e.g. Global Environmental Facility and Societe d’Investissements Energetiques) being lined up to invest in a regional energy efficiency fund. / Cumulative number of sub-sovereign investments in infrastructure resulting from EBRD technical cooperation 0 0 / Percentage of studies and projects for which environmental, climate risk and social impact assessments completed according to best practice 100% Environmental, climate and social impact assessments have been carried out according to the Bank’s practice. Looking at the environmental assessment for the Bank’s Rural Electrification and Smart Metering project in Morocco, linked to the MDA, a DFID climate adviser commented that the processes followed appeared robust. / Whilst only two feasibility studies have been completed against an initial milestone of three, the progress that has been made in initiating such studies and linking them to investments has been good. Good communications material has been produced on the activity that is being supported, particularly on water improvements in Jordan (a short film can be viewed at http://bcove.me/w3lnxdn2). Interpreting the first indicator to include all investment feasibility studies, the output can be considered to have met expectation. / Whilst the third indicator has been met, it is a mandatory requirement for EBRD projects to include environmental and social impact assessments and the Bank has good procedures in place. A better, alternative indicator would measure the extent to which MDA projects are supporting priorities identified in the EBRD’s country social and environmental assessments, once completed (see output 5). / Recommendations: / DFID and EBRD should revise the first output indicators to include a set of feasibility studies and assessments for broader potential investments, not just for PPPs. / DFID and EBRD should replace the third indicator with a measure of the extent to which projects are supporting priorities in country social and environmental assessments. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Medium/ / Revised since last Annual Review? N

Output 4: Strengthened capacity of governments and private sector entities to implement legal, social and environmental reforms to support inclusive and sustainable growth
Output 4 score and performance description: / B – Output moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2012 Achieved 2012 / Annual number of sovereign clients receiving high quality advice from EBRD on legal, social or environmental reforms 10 The EBRD, through the Multi-Donor Account, has provided advice to 8 sovereign clients. It has advised public clients on legal environments for local capital market development in each of the four countries, carried out studies on sub-sovereign financing frameworks for municipal clients in Jordan and Tunisia, advised the Yarmouk state-owned water company in Jordan on restructuring, and supported a public sector energy efficiency assessment for the government in Morocco. / Annual number of private sector clients receiving high quality advice from EBRD on social and environmental reforms 30 It has not been possible to verify how many private sector clients have been receiving advice through the Multi-Donor Account as there is lack of information on the number of SMEs receiving advice through the Bank’s industrial sector energy efficiency market study in Morocco. Other relevant activities have included providing support to a Moroccan producer of oil and soap to create energy savings, assistance to the Jordan Ahli Bank for improving access to finance for women entrepreneurs, and advice to Universal Industries Co. in Jordan helping to increase production capacity and reach a larger share of retail outlets. / Progress against this output has been difficult to assess, partly due to lack of information on the full range of EBRD advisory transactions with private sector clients and partly given difficulties in assessing the quality of advice provided by the EBRD. Future reviews, and the programme evaluation at the end of 2014, should look to collate local information and feedback on the quality of advice provided. / A new energy efficiency project for Morocco and Jordan is expected to increase considerably the number of private sector clients receiving advice (and finance for restructuring). / Overall, performance can be considered to have been moderately below expectation. / Recommendations: / EBRD should report directly the numbers of clients receiving advice on social and environmental reforms. / DFID and EBRD should build feedback on the quality of advice provided into the programme evaluation and, to a lesser extent, to future annual reviews. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Better evidence collected and disseminated of priority policy needs and expectations for successful reform
Output 5 score and performance description: / B – Output moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2012 Achieved 2012 / Comprehensive 'Life in Transition' survey carried out across Egypt, Tunisia, Morocco and Jordan with full results published. Not complete The study was rejected for funding by some donors to the Multi-Donor Account and is instead being funded from the Bank’s SEMED cooperation funds account (using net income). / Number of focus countries for which Business Environment and Enterprise Performance Surveys carried out and disseminated to practitioners 0 The study was also rejected for funding by some donors to the Multi-Donor Account and is instead being funded from the Bank’s SEMED cooperation funds account. / Good quality environmental and social impact assessments and policy reviews completed Assessments completed for all four countries. Environmental and social assessments for Morocco and Tunisia are being carried out but have not yet been finalised. Problems with consultant performance have delayed progress, and assessments for Egypt and Jordan have not yet started. / Whilst significant progress was not expected against the first two indicators under this output at this stage, the decision by some other donors to the Multi-Donor Account to reject both of the activities implies that the targets for these indicators will not be met. / Environmental and social assessments for the four countries have been delayed by poor consultant performance. The Bank needs to press ahead in ensuring good quality assessments for all four countries are completed as soon as possible as this will be important in guiding the Bank’s work to support local social and environmental priorities (as noted under output 3). / Recommendations: / EBRD should press ahead in finalising good quality environmental and social assessments for Morocco and Tunisia and in carrying out such assessments for Egypt and Jordan. / DFID and EBRD should remove this output and include an indicator on how social and environmental assessments are being used under output 3 (and possibly other outputs). / Impact Weighting (%): 10% / Revised since last Annual Review? / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / Discussions with EBRD management and other donors to the Multi-Donor Account on a possible shared results framework have taken place, with ideas presented to a Donor Assembly meeting in December 2012. There is appetite among the EBRD and a number of other donors to progress towards a shared results framework by the next donor assembly meeting in June 2013. Such a results framework will need to be consistent with EBRD’s emerging approaches to results and with DFID’s and other donors’ needs. / Recommendation: DFID and EBRD, with other donors, should aim to agree a revised, shared results framework by June 2013. / 1.2 Overall Output Score and Description: / B – Output moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / Given the early stage of implementation of the programme, direct beneficiary feedback has not yet been obtained. Informal feedback from countries has been gathered, through UK embassies, which has generally been welcoming of the EBRD’s new role in the region. As projects supported by the Multi-Donor Account reach completion, beneficiary feedback will be received by the EBRD and reported. Beneficiary feedback should be collected for the programme evaluation planned for the end of 2104. / Recommendation: DFID and EBRD should ensure that mechanisms are in place to factor beneficiary feedback into subsequent annual reviews and the evaluation.
1.4 Summary of overall progress / The EBRD has made good progress in establishing its presence in the region (e.g. recruiting staff) and in obtaining and disbursing donor funds for technical cooperation activities. The Bank is providing a range of valuable technical cooperation across the four countries to a range of private and public sector clients. Such technical cooperation is targeted towards important needs for promoting private sector development and inclusive growth, including gender priorities, and is helping to prepare for substantive EBRD and other investments. Stakeholders, including governments in the region, have welcomed the new role the EBRD is playing, supported by the UK and other donors. / Progress against logframe outputs and indicators, however, has been moderately below expectation, for several reasons: / Some logframe deliverables have been supported by other donors or funding sources rather than the Multi-Donor Account, either because such funding (e.g. from the EU) has sustained activity for longer than originally expected, or because other donors to the Multi-Donor Account have rejected relevant activities. For the future, clearer arrangements need to be put in place to decide which projects should be funded from which sources and, where possible, to encourage co-financing between instruments. Such arrangements should be agreed at the next donor assembly meeting in June 2013. / The EBRD has encountered some delays with implementation, including delays in recruiting project teams and in host countries signing agreements enabling the EBRD to operate in country. In a few cases, poor consultant performance has hindered progress. Finally, delays in the process of EBRD members ratifying the regional expansion have made it harder for the Bank to build technical cooperation around potential investment activities. / Some logframe milestones were unrealistic for the first year of the programme, whilst some outputs and indicators of the logframe have not sufficiently captured the range of EBRD’s activities (e.g. work on food security). This reflects some lack of evidence at programme inception of what the EBRD could realistically be expected to deliver in the new region and by when.
1.5 Key challenges / There are challenges in reconciling the pressures for the EBRD to be providing rapid support to the region and the need to ensure that projects are carefully formulated in ways that utilize the EBRD’s strengths, tailor approaches to the regional contexts, and complement effectively the activities of other donors. This is particularly relevant given that the EBRD is new to the region. The EBRD is responding well to these challenges. / There are challenges in specifying the expected results from the programme, given that the EBRD is new to the region, that the UK is contributing to a multi-donor instrument (with some differences in donor preferences), and that the EBRD is in the early stages of strengthening its attention to results. / There are also potential challenges in ensuring that EBRD assistance to the region is focused on promoting economic and social inclusion. The UK believes that ensuring inclusive economic participation is an integral part of successful transition to functional market-based economies and is critical for the region. But there are on-going discussions taking place among EBRD members on how the Bank’s mandate to promote transition should be interpreted. / Recommendation: DFID should continue to provide advisory inputs to the EBRD’s efforts in strengthening approaches to results. / Recommendation: DFID should work with the Bank to support its efforts to promote inclusion (especially supporting the Bank’s evolving plans on gender) and continue to make the case to other EBRD members for the importance of economic inclusion in transition.
1.6 Annual Outcome Assessment / The EBRD has made good progress in lining up several investments as a result of donor-funded technical cooperation, including a €60m loan for electrification in Morocco, €22.5m of investments through the Local Enterprise Finance initiative, and potentially €25m of investment in the Yarmouk water company in Jordan. / It is too early to identify and assess changes in employment that have resulted from direct donor-funded EBRD assistance to businesses, or the percentage of sovereign and private sector clients implementing legal, social and environmental policy reforms advised by EBRD.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Disbursements have been made to the EBRD’s Multi-Donor Account according to schedule. At the time of review there were around €6.6m of funds in the Multi-Donor Account waiting to be allocated. / Recommendation: EBRD should ensure donor resources are allocated to projects and spent in timely ways. / Recommendation: DFID should monitor EBRD spend and potentially adjust the profile of its disbursements to avoid making payments significantly in advance of need. / 2.2 Key cost drivers / The key cost drivers are: / The types of projects that are supported through the Multi-Donor Account and the kinds of consultant expertise required – some being more expensive than others. / The balance between the use of local staff and consultants and London-based (or international) staff and consultants. The latter are typically more expensive. / The extent of other costs incurred, including travel and security costs. / 2.3 Is the project on-track against original timescale: Y / Whilst the EBRD has experienced some delays, and there has been less than expected progress against some logframe indicators, the EBRD has made impressive progress in establishing its regional presence and mobilising assistance. Many of the programme targets remain realistic although, as noted above, some adjustments in some areas are needed.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are some changes in the evidence on the kinds of activities the EBRD can support in the region, resulting from the evolving expansion of the EBRD into the region. It is now somewhat clearer what support the EBRD can provide and the timeframes for doing so. This information should be used to reconsider the logframe, milestones and targets. / Where an evaluation is planned what progress has been made? / An evaluation is planned to take place between October 2014 and March 2015. / DFID and EBRD have agreed to work together in the next three months to identify a set of evaluation questions, an evaluation approach and appropriate set of arrangements to govern the evaluation. At the June donor assembly meeting, other donors will be invited to join the evaluation. By the end of 2013, DFID will develop full terms of reference for the evaluation, with input from the EBRD’s Evaluation Department and, as appropriate, from other donors.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The risk level for the programme is still considered to be medium. / One year into the programme, key risks are: / Deterioration in country conditions. Deterioration or lack of progress in building political conditions for economic reform in countries could limit the impact of the EBRD. The EBRD has demonstrated, however, its ability to operate with a range of clients in countries notwithstanding problems with the political and policy environments. / Delays in full regional expansion. EBRD’s ability to follow-up on technical cooperation activities with investments, and hence the outcomes of the Multi-Donor Account, could be constrained if there are major delays to the ratification by members of EBRD’s full regional expansion. / Delays in implementation of technical cooperation. The EBRD could experience further delays in implementation of some activities, for instance due to delays in recruitment or further problems with consultant performance. / EBRD assistance not sufficiently focused on economic and social inclusion priorities. There are risks, particularly with the pressure to implement quickly, that EBRD technical cooperation and investments will not be targeted to produce outcomes that enable full economic participation, including for women and young people. Such focus could also be affected by board level discussions on the EBRD’s mandate. / Lack of coordination. There remain risks around lack of coordination of EBRD assistance with that of other IFIs and donors, although the EBRD has played a strong role in the Deauville Partnership. / Recommendation: UK should continue to actively promote ratification of EBRD’s regional expansion, including through its chair of the Deauville Partnership in 2013. / Recommendation: EBRD should put in place management attention on activities where there are risks of implementation delays and put in place contingency planning. / Recommendation: EBRD should continue to play an active role in the Deauville Partnership IFI coordination platform and work closely with other partners to coordinate activities in country. / Recommendation: The UK should build up further engagement with partners in country to help ensure activities of the EBRD and others are well coordinated ‘on the ground’.
Risk of funds not being used as intended / The risks of funds not being used as intended are considered to be low, as EBRD has good due diligence measures in place at project level and technical cooperation projects are well supervised by the EBRD donor co-financing unit. / 4.4 Climate and Environment Risk / Climate and environment risks remain medium. / The programme is funding technical cooperation linked to investments in areas that pose environmental and climate risks: infrastructure development, business growth. Environment and climate assessments are routinely carried out to Bank standards and the process is assessed by a DFID climate adviser as being robust. / Country environmental assessments for all four countries need to be completed as soon as possible. / In several cases, EBRD activities are aimed at reducing risks of climate change and at promoting environmental sustainability. For instance, with Multi-Donor Account funds, the Bank is: advising public and private clients in Morocco on improving energy efficiency, carrying out preparatory work for a new regional energy efficiency fund, and providing technical assistance for better management of scarce water resources in Jordan.

5. Value for Money
5.1 Performance on VfM measures / Two key value for money measures were identified for this programme: / Cost per job. Given lack of evidence collected by the programme to date it is not possible to assess value for money in terms of the cost of jobs created as a result of direct, donor-funded, EBRD assistance to businesses. / Investments leveraged. There is only partial information at present to assess the amount of investment to the region being leveraged through the UK’s contribution to the Multi-Donor Account for SEMED. It is not possible to identify all EBRD and other investments likely to emanate from current technical cooperation activities. But so far, a total of €107.5m of EBRD investments are being initiated or are in the pipeline as a result of technical cooperation supported by the Multi-Donor Account. The UK’s contribution to the Multi-Donor Account up until the end of 2012 was equivalent to €3.6m, around 20% of total donor funds. The UK could claim that it has leveraged at least €21.7m of EBRD investments in the region so far, a ratio to contribution of 6:1. Whilst this is significantly below the leverage ratio expected for the lifetime of the programme of 39:1, the current ratio is considered to be an underestimate and likely to grow significantly over time (subject to ratification of expansion). / 5.2 Commercial Improvement and Value for Money / EBRD’s procurement of commercial services, including consultancy support, is still considered to be acceptable. However, some experiences with poor consultant performance suggests that there may be ways to tighten up on ensuring that consultants are selected on good ‘value for money’ grounds – with prospective quality and costs of consultants (within reasonable limits) being both taken into account in arriving at overall conclusions. / 5.3 Role of project partners / The UK is the largest bilateral donor to the EBRD’s Multi-Donor Account for SEMED, but in total there are 9 donors to the Account. This helps to ensure that the UK’s resources are combined with those of others to support a significant scale of activities, outputs and outcomes. There is good evidence that the UK’s early contribution to the Account encouraged other donors to join. / There are also challenges in contributing to a Multi-Donor Account alongside a significant number of other donors, particularly given the scope for individual donors to veto individual project proposals with a value greater than €150,000. Experience with the Multi-Donor Account so far has demonstrated the need for a common understanding of priorities among donors. In so far as agreement could be reached between the EBRD and donors on critical results that should be targeted, there would be merit in establishing a shared results framework for the Multi-Donor Account. / Recommendation: EBRD, DFID and other donors should, by June 2013, aim to agree a framework to help govern the use of the Multi-Donor Account in ways that reduce the need for individual donors to reject proposals. / 5.4 Does the project still represent Value for Money : Y / Even though it has not been possible yet to fully assess the value for money being realised through the programme, it is clear that good value for money is already being achieved in terms of investments being leveraged. Further assessment is needed in due course of the impact of such investments, and technical cooperation activities, on jobs and economic and social inclusion. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The UK’s £5m contribution to the EBRD’s Multi-Donor Account for technical cooperation is enabling a key institution with experience of promoting transition, a focus on private sector development, and potentially significant resources to invest, to start operating in reforming countries in the MENA region. During the first year of the programme the EBRD has established a strong presence in the region and, with UK and other donor funds, has initiated a number of worthwhile technical cooperation activities. A number of investment projects are being established by the Bank. The EBRD has also been playing an active role in donor coordination activities through the Deauville Partnership. / Performance against logframe outputs and indicators overall has been moderately less than expected. This has partly been due to lack of clarity at the start of the programme as to which activities would be funded from which funding sources, and for how long. In some cases, the expectations for delivery in the first year of the programme were too high. There have also been some delays that have affected progress, some within and some outside of EBRD’s control. Whilst it has not been possible to assess fully at this stage the value for money of the programme, initial indications suggest that good value will be achieved. / There are medium risks to future delivery, including risks around country conditions, delays in full regional expansion, further implementation delays, lack of focus on economic inclusion as a transition priority, and possible lack of donor coordination in country. These risks will require monitoring and management (including through the actions below). / The key actions arising from the review are: / EBRD and DFID to revise the programme logframe, reflecting an appropriate balance between the Multi-Donor Account and other funding sources, ensuring milestones are realistic, incorporating important activities not currently included, and removing output 5. / EBRD and DFID should aim to agree a shared results framework with other donors to the Multi-Donor Account by June 2013. / EBRD should put forward clear proposals to the donor assembly in June 2013 to ensure clear relationships between different funding sources and acceptable arrangements for co-financing. / EBRD should follow-up on activities affected by delays and put in place contingency arrangements if necessary. Particular effort should be placed on ensuring good quality social and environmental assessments for all four countries are completed as soon as possible. / EBRD and DFID to factor client feedback mechanisms to future Annual Reviews and the programme evaluation. / DFID and EBRD to develop questions and Terms of Reference for programme evaluation by end of 2013, inviting other donors to participate. / DFID to work with the Bank to support its efforts to promote inclusion (especially supporting the Bank’s evolving plans on gender) and continue to make the case to other EBRD members for the importance of economic inclusion in transition. / DFID to continue to provide advisory inputs to the EBRD’s efforts in strengthening approaches to results. / UK should continue to promote ratification of EBRD’s regional expansion, including through its chair of the Deauville Partnership in 2013. / EBRD should ensure donor resources are allocated to projects and spent in timely ways. DFID should monitor EBRD spend and potentially adjust the profile of its disbursements to avoid making payments significantly in advance of need. / EBRD should continue to play an active role in the Deauville Partnership IFI coordination platform and work closely with other partners to coordinate activities in country. / UK to build up further engagement with partners in country to help ensure activities of the EBRD and others are well coordinated ‘on the ground’.

8. Review Process
The review was carried out by the lead adviser for the programme, with inputs from other regional advisers in DFID (results and evaluation, private sector development, climate adviser), UK staff in country, and UK staff at the EBRD. The review involved consideration of the EBRD’s previous two semi-Annual reports (December 2012 and June 2012) and consultation with EBRD staff.