Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Political Settlements Research Programme (PSRP)
Programme Value: £4,366,612		Review Date: March 2018
Programme Code: 204326	Start Date: 01/04/2014	End Date: 30/03/2019

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A	A+	A+
Risk Rating	Medium	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review

The Political Settlements Research Programme (PSRP) has met or exceeded targets for 2017, its third year. Demand for research and expert advice from The University of Edinburgh (UoE)-led consortium is high among the international conflict policy community, including the UN, international mediators, and UK officials.

PSRP has performed well on four key areas:
- Comparative research on political settlements, such as Aisling Swaine’s book comparing violence against women and girls in 3 conflict affected countries which proposes new ways to assess and address domestic and conflict-motivated violence against women.
- Peace agreements database launched, containing over 1500 documents from over 150 peace processes over the last 50 years. New data is also being developed on amnesties.
Policy engagement with International organisations, including citations in the UN/WB report on “Conflict Prevention” which updates the World Bank Development Report on Conflict 2017, and policy papers on gender and power-sharing published by UNWomen.
Rapid expert advice provided to DFID teams working on Zimbabwe and Lebanon political transitions; and to the Syria, Yemen and Burma teams on ceasefires.

Over the next (final) year of the current programme contract, PSRP will focus on the impact and policy relevance of the research. This includes further developing policy research on the themes prioritised by a UK cross-government group last year (including Stabilisation Unit, Foreign Office Research Analysts and DFID Policy leads): power and territory sharing, sub-national arrangements, design and implementation of peace processes, and security guarantees and justice provisions. New policy papers will be developed on: ceasefires, transitional justice mechanisms, amnesties, and economic provisions. Research will also continue on the central focus of the research programme - how to support ‘inclusive’ political settlements - and on gender and peace implementation.

Follow-up on 2016-17 recommendations:
PSRP acted on the recommendations in last year’s Annual Review (AR) which included deepening engagement with DFID/FCO Country and policy teams, providing thematic research on priority policy topics, and revising logframe indicators. PSRP has organised events in London every 6 months to improve engagement with Whitehall policy and country teams, and worked hard to address DFID feedback on writing for policy makers. Progress on this will be assessed again in August 2018, and again on completion of the contract.
Summary of recommendations for the next year: (see detail below)
As part of this AR period, PSRP has focussed resources and research to meet high demand from UK officials, and partners working on complex conflicts. The main recommendations from this AR are:
Complete 4 further policy papers by August (2018). Last year PSRP was required to deliver a report on each of 4 priority policy topics (peace process design and implementation, sub-national arrangements, power/resource sharing, security guarantees and justice provisions). Draft papers were submitted by Dec 2017 and will be published by April 2018. Additional papers on ceasefires, transitional justice arrangements, economic provisions and amnesties will be delivered by August 2018.

Consolidate key facts from the database and wider research into a form that can be used by international mediators or other actors working on peace processes PSRP presented early analysis from the database at a launch event with DFID’s Permanent Secretary in February 2018. PSRP will provide an updated set of facts from the database with clear recommendations for policy makers by August 2018.

Hold significant uptake events with OECD, UN and HMG staff on the database. PSRP should continue and deepen support to HMG country teams and to international mediators working on peace processes. PSRP has committed to organising events with key international partners; the OECD in support of the UK co-chairmanship, the UN Peace Building Support Unit and/or World Bank in either New York or Washington and the EU Mediation network. PSRP will also present research to the East Africa Conflict and Governance Advisers in Nairobi on the 2nd July and will provide at least 2 workshops for HMG staff in London.

Consider Extension to the current contract. DFID and PSRP have agreed to consider an extension to the current contract to enable greater use of the database and PSRP expertise within ongoing peace processes. This would build on PSRP‘s strong record this year and meet demand from policy makers for well evidenced rapid response outputs and advice.

A. Introduction and Context

DevTracker Link to Business Case:	4429922
DevTracker Link to Log frame:	5350670

Outline of the programme
DFID is providing £4.4m over four years (2015-19) to fund research into how donors can shape political settlements - the rules that regulate the access of elites to resources and power – to reduce poverty and the risk of conflict[1]. The research programme, in an area which has many evidence gaps, will inform the content, choice and targeting of interventions on political settlements by donors, diplomats, and defence actors, especially in fragile and conflict-affected states (FCAS). The research will lead to more effective interventions that address conflict risks and promote pro-poor institutions.
[1] How power is organized in a society and the rules that regulate how elites work together is termed the ‘political settlement’. Additional characteristics of political settlements include a) a broad reflection of the underlying distribution of power between different social groups; b) that they are not static or single events, but continuous bargaining processes over these rules between different elite and non-elite groups; c) that they are expressed through formal and informal institutions which constrain and shape the underlying bargaining processes; and d) exist both at the state and the sub-state level.
The Political Settlements Research Programme (PSRP) has been running for 2 years, including a six-month inception period (to Sept 2015). This is the second AR.
This programme focusses on three broad themes:
1. How different types of political settlement emerge, and which actors, institutions, resources, and practices shape them;
2. How political settlements can be improved by internally-driven initiatives (i.e. by directly involved parties), including the impact of gender-inclusive processes and rule of law institutions;
3. How, and with what interventions, external actors can change political settlements.
The research is explicitly comparative (that is, it seeks insights by understanding examples and the differences between them). The programme uses a mix of qualitative and quantitative methods, with substantial field work. Currently, research is focussed on Afghanistan, the Democratic Republic of Congo (DRC); East Timor; Ethiopia (Ogaden); Liberia; Nepal; Nigeria; Philippines; Sierra Leone; and Somalia, with comparison with less fragile settings: Colombia and Northern Ireland.
Following a competitive procurement process, a consortium led by University of Edinburgh was selected to implement the programme. PSRP complements existing RED research programmes, notably the Effective States for Inclusive Development Consortium (ESID), the Secure Livelihoods Research Consortium (SLRC) and the Conflict Research Programme (CRP).

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment
PSRP has met or exceeded its output indicators and targets this year. This progress is translating into tangible outcomes, and policy interest has further increased following the launch of the peace agreements database in February 2018.
PSRP now needs to capitalise on this interest in the final year, and deliver a legacy of high quality policy guidance and research that can transform how the international community approaches peace processes.
Progress on outcome indicators is outlined below:
UK Policy influence:
- UK Conflict Policy: Edinburgh University Researchers involved in the PSRP programme briefed DFID’s Minister of State and Permanent Secretary this year on key findings from the research, and how it could improve HMG’s use of evidence and engagement in peace processes. The “Paper Navigating Political Inclusion” was cited in a Cabinet Office report on trends relevant to the Strategic Defence and Security Review (SDSR). These briefings, and roundtables held with DFID and FCO Heads of Office, Ambassadors, and policy teams, are making the case for longer term, evidence-based approaches to conflict resolution in countries that are high priorities for the National Security Committee (NSC) and for DFID’s ‘Strategic Direction’ work on conflict, security and justice.
- UK Country Policy; PSRP has provided flexible advice to senior officials working on peace processes during times of crisis - a service for which there is growing demand. PSRP ran advice sessions this year with FCO/DFID Libya and Lebanon teams building on last year’s successful sessions on Syria and Yemen. PSRP provided rapid reviews for FCO/DFID Zimbabwe, South Sudan and Yemen. Feedback from all teams was that the service was fast, relevant and of higher calibre than other knowledge services available to DFID advisers, enabling DFID to review clear options against comparative examples at critical moments in a political transition.
- The launch of the database has enabled HMG teams to run their own searches and analysis. An official who used the database to answer a question on resource sharing and economic provisions in peace processes gave the following feedback:
 “I found the database a really helpful source – much more so than other services available. First of all, it’s clear and easy to use. Second, it instantly provides a comprehensive set of results. That’s invaluable when we quickly need to provide concrete examples and precedents to our policy customers in the FCO.” HMG official.

International Policy influence: examples, and endorsement by the staff of international organisations, include the following:

- Multilateral Policy on Peace Processes: PSRP research is referenced throughout the UN/World Bank Conflict Prevention Study[1] which updates the World Development Report on Conflict 2011[2]. This has helped ensure that work on conflict resolution and political settlements is central to the UN Secretary General’s Sustaining Peace Agenda.
  [1] United Nations; World Bank. 2018. Pathways for Peace: Inclusive Approaches to Preventing Violent Conflict. Washington, DC: World Bank. © World Bank. https://openknowledge.worldbank.org/handle/10986/28337 License: CC BY 3.0 IGO.”
  [2] World Bank (2011) ‘World Development report on conflict’ https://siteresources.worldbank.org/INTWDRS/Resources/WDR2011_Full_Text.pdf
- UNWOMEN UN Women is examining the gendered dimensions of peace agreement implementation and drawing on the PSRP gender and peace agreement database to inform this. This follows PSRP’s input to the UN’s 15-year review of Security Council resolution 1325, and the Secretary General’s Report on Women, Peace and Security last year (2017)[3],
  [3] United Nations (2017) ‘Report of the Secretary General on Women, Peace and Security’. https://reliefweb.int/report/world/report-secretary-general-women-and-peace-and-security-s2017861-enarru
- Operational Support to Peace Processes: PSRP researchers have directly supported civic actors engaging in peace processes in the Middle East. Their engagement in workshops in Jordan, Libya and Lebanon has helped Libyan, Syrian and Yemeni women refine their engagements in peace processes and advocate for greater inclusion, according to a UN representative in the regional office.
UN Department for Political Affairs, and UNDP: staff draw on the database and research to support their teams working on mediation and constitutions around the world.
“I found the peace agreements database extremely useful. Firstly, I have found the research papers and materials of the PSRP informative in my work on constitutions and the recent sustaining peace initiatives of the UN. Secondly, I turn to the database to refer to various documents of national peace processes when I have to study the background and history of a conflict in a country that I have to focus on in my work”.
Senior Constitutions Advisor in the UNs Policy and Mediation Division.
“UNDP supports constitution-making processes around the world – in many post-conflict and transitional settings. I and colleagues, have used PSRP reports to support UNDP work on constitutions in a number of country settings, which due to the sensitivity of our work cannot be disclosed.”
UNDP Lead on Political Dialogues and Constitutional Processes.
PSRP continues to support the Columbia and Yemen peace processes, following last year’s impact examples. PSRP have been asked to provide support to a new UN mediator for Yemen who came into office last month.
Overall output score and description: A+ (Output and performance exceeds expectations)
This year PSRP has focussed resources and research to meet high demand from UK officials, and partners working on complex conflicts.

Key lessons and actions
Demand for PSRP advice and research has been highest among those working directly on peace and/or constitutional processes, often in contexts where peace negotiations are less than 5 years old. Negotiations are extremely sensitive and examples of influence and impact can’t easily be shared publically. Advice and research has most resonance where it is tailored to the specific needs of these audiences.
PSRP publications are valued most strongly by policy makers where they draw on analysis from the database, alongside case studies and wider comparative research.
PSRP’s most popular research papers so far have been “Sequencing of peace processes, 2016”[4], “Navigating Inclusion, 2017”[5] and a Special Issue on Political Settlements edited jointly with Birmingham University, 2017[6] (publications are listed in Annex 2).
[4] Bell, C & Zulueta-Fülscher, K. (2016). Sequencing Peace Agreements and Constitutions in the Political Settlement Process. Stockholm: International IDEA. http://www.politicalsettlements.org/files/2016/11/sequencing-peace-agreements-and-constitutions.pdf
[5] Bell, C (2016) Navigating Inclusion in Peace Settlements, Human Rights and the Common Good, http://blogs.sps.ed.ac.uk/politicalsettlements/files/2017/06/BRIJ5395_Peacebuilding_final_web.pdf
[6] Pospisil, J. and Menocal, A. (Eds) (2017) Special Issue Issue on Political Settlements, Journal of International Development Volume 29, Issue 5 pages 549–677, E1E1 http://onlinelibrary.wiley.com/doi/10.1002/jid.v29.5/issuetoc
While PSRP’s events, advice and publications have been well received, some publications were considered either too conceptual, technically complicated (e.g. paper on sub-national constitutions[7]) or not sufficiently focussed for policy readers. DFID has provided this feedback to PSRP. In the final year PSRP should focus on delivering a clear set of policy papers that will resonate with policy readers as a legacy of the programme.
[7] Zulueta-Fülscher, K. and Welikala, A. (DATE) Substate Constitutions in Fragile and Conflict-affected Settings, International IDEA http://www.politicalsettlements.org/files/2017/11/substate-constitutions-in-fragile-and-conflict-affected-settings.pdf

Last year PSRP was required to deliver a report on each of 4 priority policy topics (peace process design and implementation, sub-national arrangements, power/resource sharing, security guarantees and justice provisions). Draft papers were submitted by Dec 2018 but are being refined to incorporate DFID feedback. Additional papers on ceasefires, transitional justice arrangements, economic provisions and amnesties will be delivered by August 2018.

Actions:
1. Complete 4 further policy papers by August (2018)
2. Consolidate key facts from the database and wider research in a form that can be used by international mediators or other actors working on peace processes PSRP has provided early analysis and facts from the database which were presented at the launch event in January. By August 2018 PSRP will provide an updated set of facts from the database with clear recommendations for policy makers.
3. Hold significant uptake events with the OECD, UN and HMG staff. PSRP should continue and deepen support to HMG country teams this year and to international mediators working on peace processes. PSRP has committed to organising events with key international partners; the OECD in support of the UK co-chairmanship , the UN Peace Building Support Unit and/or World Bank in either New York or Washington and the EU Mediation network. PSRP will also present research to the East Africa Conflict and Governance Advisers in Nairobi on the 2nd July and will provide at least 2 workshops for HMG staff in London.
Has the logframe been updated since the last review?
The log frame was revised to align targets with other RED research measures.
Targets for publications and events have remained the same, or been made more challenging. PSRP has diversified measures of internet uptake to provide a broader range of measures than were previously tracked.
PSRP has also provided qualitative feedback from policy customers engaged in peace and political processes to triangulate other monitoring.

## C: DETAILED OUTPUT SCORING

Output Title	Research products
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 No. of high quality, policy relevant new evidence on peace and political processes.	12 articles or book chapters published in peer reviewed outlets (this year)	Achieved / PSRP has produced 16 peer-reviewed journal articles (11) and book chapters (5) this year. This is about the same as last year, when PSRP published 13 articles and chapters. Highlights this year include the Special Issue on Political Settlements published in the Journal of International Development and edited by Jan Popsil and Alina Menocal (Birmingham University). Aisling Swaine’s book “conflict-related violence against women” has been published this year and shared with DFID/FCO staff.
1.2 New datasets capable of supporting ongoing research	Peace Agreement Access Tool's complete, trainings begun and database used to generate new analysis.	Achieved / The Peace Agreements Database was launched in January 2018. New Analysis was published on the website and presented at the launch in London. DFID and FCO staff is using the database to inform their analysis and policy advice.
1.3 No. of High quality policy relevant publications published (e.g. number of policy briefs, working papers and blogs.)	2 Special editions of ACCORD magazine, 20 briefing papers, 15 research reports and 30 blogs. (cumulative)	Achieved / PSRP has delivered 21 briefing papers, 33 research reports, and 59 blog entries[2]. 7 of the briefing papers and 17 reports were delivered this year. / The ACCORD publication on Nepal was published in March 2017. / A Draft of the ACCORD on Afghanistan has been shared with DFID and is undergoing revisions for publication in May.
[2] All PSRP non-journal publications are gold open access

Key Points
PSRP has met publication targets (1.1), completed and launched the peace agreements database (1.2) and produced policy relevant publications (1.3).
Qualitative feedback from policy audiences is provided below to back up the quantitative measures in the logframe. This reflects the specialist audience of practitioners involved in mediation or direct support to peace processes that PSRP research is targeting.
1.1	Publication highlights this year include
Special Issue on Political Settlements published in the Journal of International Development and edited by Popsil and Menocal (Birmingham University) was presented by PSRP and Birmingham University at ODI, with over 10 HMG staff and key external experts such as David Booth. The papers on ‘Navigating political inclusion’ and ‘political unsettlement’ were referenced by attendees as important contributions to the global practice and have received citations in UN reports and other research (see output 2.2).

Book “Conflict-related violence against women”, Aisling Swaine’s comparative research across Liberia, Timor-Leste and Northern Ireland and new research by PSRP on violence against women and girls demonstrates the many forms of violence experienced by women before, during and after conflict. The research makes recommendations about how the international community could address these more effectively. PSRP research also finds that wider efforts to end conflict, improve security and demobilise combatants have important benefits for domestic violence.
1.2	The Peace agreements database is already being used by mediators, HMG officials and diplomats in several ongoing peace processes.

“The peace agreements database is a noteworthy accomplishment, with remarkable breadth. It will serve as an invaluable resource for scholars, groups impacted by violent conflict seeking a greater voice in peace processes, and individuals charged with mediating disputes. The knowledge the database provides may foster political settlements that are more inclusive and more sustainable.”
US Ambassador (former) Carey Cavanaugh

“I found the database a really helpful source – much more so than other resources available. First of all, it’s clear and easy to use. Second, it instantly provides a comprehensive set of results. That’s invaluable when we quickly need to provide concrete examples and precedents to our policy customers in the FCO.”
HMG official using database to answer question on resource sharing
and economic provisions in peace processes.
“This database will be an important resource, not just for high-level mediators and parties to conflicts, but also to the wider range of civic participants who seek to influence talks processes and press for greater inclusion. Having access to such a breadth of data on peace processes will mean that practitioners will have a firmer foundation for the choices they make.”
Jonathan Cohen, Executive Director, Conciliation Resources, http://www.c-r.org
Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations from last year (refine scope of research and focus on impact) have been met.
Recommendations
No further recommendations for this year.

## C: DETAILED OUTPUT SCORING

Output Title	Uptake and engagement
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1: number of workshops, briefings and engagement events involving PSRP and key stakeholders in which PSRP research is discussed substantively. (cumulative)	At least 5 workshops; at least 5 other stakeholder engagement events (cumulative)	Exceeded. / PSRP hosted 16 events workshops, seminars, conferences, stakeholder engagement forums, and 3 summer schools. / Events hosted this year included: / 2 country specific research events, on DRC and Afghanistan. / Launch of Political Settlements Special Issue at ODI. / British Academy event on Political Settlements and the “Common Good” , considering human rights in PS. / DFID/ FCO country team briefs June 2017 and roundtable and public launch of the database in February 2018.
2.2 PSRP Research taken up and referenced elsewhere (cumulative)	8 peer-reviewed articles cite PSRP work.	Exceeded / 16 outputs of PSRP work have been cited by 34 peer-reviewed journal articles not authored by PSRP or affiliated researchers. This is an increase from 5 citations last year. / Some of the most cited papers are listed below: / Bell/Popsil, ‘Navigating inclusion in transitions from conflict’ Journal of International Development, 2 citations. / Bell, Lex Pacificatoria Colombiana’, AJIL 2 citations / Bell & Zuleuta-Fuelscher, ‘Sequencing Peace Agreements and Constitutions’ 2 citations. / Bell, ‘What we talk about when we talk about political settlements’ 2 citations. / Ni Aolain, ‘The “war on terror” and extremism’, 3 citations. / Popisil/Kuhn, ‘The Resilient State’, Third World Quarterly, 4 citations.
2.3 No. of stakeholders engaging with research and policy products through website, media and publication downloads.	2 publications with 500 downloads , 5 more publications with 100 downloads.	Achieved (see section B for details). / Two publications had close to 1000 downloads. 11 publications had over 100 downloads. / The website is generating a monthly average of around 300 hits. We expect this to increase in the final year as users become more familiar with the database. / The launch of the Peace Agreements Database was the second most viewed post from DFID’s Research twitter account in February 2018 with over 10,057 views.

Key Points
PSRP has met or exceeded all output 2 targets. Uptake has been demonstrated through events (2.1), academic citations (2.2) and internet uptake.
The quote below demonstrates how other research institutions and international organisations are drawing on the PSRP data to inform peace processes:
“PSRP data has informed high level policy discussions at the United Nations and is widely used by actors in peace processes. The Constitution Building Programme of International IDEA is using PSRP data in developing a database of constitution-building processes in fragile and conflict-affected settings. Data such as this, and the analysis that results, helps meet an urgent need to transform peace and democracy building practices, which too often appear in regression.”
Yves Leterme, Secretary-General, International IDEA,
former Prime Minister Belgium, https://www.idea.int

Summary of responses to issues raised in previous annual reviews (where relevant)
PSRP refined the output indicators to make them clearer and aligned with other RED programme milestones. PSRP has improved reporting on its online engagement and uptake.
The second highest engagement for DFID research on twitter in February 2018 RED were for PSRP’s launch of the peace agreements database. Good communication and live tweeting between DFID and PSRP communications staff helped ensure a successful social media launch of the database.
Recommendations
No further recommendations this year.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
Key cost drivers and performance
This is a performance based contract with expenses paid quarterly in arrears based on actual costs. DFID retains 5% of each payment; the retained amount is then paid in the following quarter providing all performance criteria have been met.
In this reporting period delivery and performance remained on track and the 5% retention was paid in full in each subsequent quarter. Full details of key cost drivers are set out in Section 4 of the contract. The key cost drivers are staff costs making up 81% of the spend to date.
VfM performance compared to the original VFM proposition in the business case
Assessment of whether the programme continues to represent value for money
The University of Edinburgh is delivering value for money (VFM) across all indicators (i.e. economy, efficiency, effectiveness, and equity). In this reporting period the UoE continued measures to further improve VFM by securing other sources of funding or resources and reallocating PSRP funds to additional themes. The chart below has been reviewed with PSRP and remains largely the same as last year. Specific examples of additional VFM savings this year include:
Economy
- Reallocation of PSRP travel funds were utilised to support database development and work to increase reach (e.g. transcriptions and translations of peace agreements).
- The UoE School of Law contributed resources to enable the recruitment of an additional six-month position, to upgrade PSRP programme management and communications;
- Funding secured for the UoE's Global Justice Academy has been used to finance further outreach activities e.g. the PA-X launch event during the 2018 ISA annual convention in San Francisco.

Efficiency
Effective management of staff input has enabled the reallocation of staff days between partners (i.e. 77 staff days from the Transitional Justice Institute (TJI) to UoE staff working on PA-X) to accelerate the completion of the database and the production and dissemination of database outputs.

Indicator category	Indicator	Performance / Best practices
Economy	Cost saving measures	Reduced travel costs by prioritising high impact events and using skype for planning with in-country partners. / Reduced printing costs through online dissemination and in-house editing.
	Best practices in procurement	Meets fair trade and living wage requirements in line with UoE procurement guidelines. / Clear benchmarks for southern researcher fee rates.
	Financial oversight	Robust financial systems at UoE include, copy receipts for all invoices submitted by partners, with internal and external auditing in place for the PSRP Consortium.
	Financial risk management	Adoption of a risk management strategy, according to DFID policies and risk management
Efficiency	Project management strategies	‘Basecamp’ virtual technology used for continuous communication between consortium members; / Benchmarking of project output/partner commitments.
	Increase quality/quantity of output	Internal peer review process for each project output / External peer review for all reports, including in-country review; / University-independent peer review of academic outputs / Contractual commitments delivered with additional outputs.
Effectiveness	Demonstrate ability to attract further funding	Additional funding from British Academy, UN Women, and ESRC has accelerated and multiplied the programme’s core work e.g. UN Women grant on women and peace processes will produce eight country-specific briefs and topic guides, particularly on women’s inclusion and the implementation of UNSCR 1325 in Syria, Yemen, and the MENA region. The briefing papers relate to the PSRP core content of negotiating inclusion in fragile political settlements.
	Promote academic impact	17 articles in top academic journals, a further publications in edited volumes and other academic outlets; / Wide use of popular open access platforms, in particular SSRN, Academia and ResearchGate; / Active participation at leading international conferences, including the organisation of sections (EISA 2015, DSA 2016) or panels (ISA 2017, BISA 2016); / High profile reports, often in partnership with international organisations such as UN Women and International IDEA; / Launch events of reports at international key locations (such as Carnegie Endowment for International Peace, UN Headquarter); / Reception at ISA – largest international studies conference with over 5000 participants.
	Promote research uptake	Prior engagement with key stakeholders before finalising research design (questions and research design revised to reflect key stakeholder input) and prior to publication; / Hard copy circulated to key stakeholders with key publications (particularly non-academic); / Translations of reports to other languages (French, German).
	Establish research partnerships	Established key strategic partnerships with International IDEA, DLP Birmingham, ODI, LSE, Berghof Foundation, SOAS, The Graduate Institute Geneva.
Equity	Involvement of Southern Researchers	All in-country research joint with southern partners, including joint design, implementation and co-authoring research.
	Consider social inclusion	Explicit research focus on inclusion – in country partners ensures representation of different social, economic, political and gender groups. This has included indigenous women in Colombia, and gender and sexual minorities in Nepal; / Public events ensure disabled access; / Publications are designed (in terms of font and print) to comply with good practice for people with disabilities such as dyslexia; / A range of means of engagement are used to suit audience – publications, power point, online audio and video.
	Promote professional development of project staff	Management approach includes staff annual reviews and takes account of staff’ interests and career progression, / Promotes opportunities for southern based researchers by including named participants in the research and co-authors.

Quality of Financial Management
The UoE forecasting has been realistic with actual expenditure / payment requests closely aligned to their (UoE team) estimates. Invoicing and supporting documentation from the UoE is timely and of good quality.
The actual expenditure for the reporting year against that originally forecast is 98% (see table below). This reflects a small underspend of 2% this financial year.
The programme remains largely on track in terms of spending and delivery, with £1,016.447 (23%) remaining to be spent in the final year of the programme (2018/19).
 Reporting Year
£	Q1 (Mar-May)	Q2 (June-Aug)	Q3 (Sept-Nov)	Q4 (Dec – Feb)	Total
Forecast	235,129	223,350	264,315	271,930	994,724
Actual	235,129	235,816	232,507	275,775	979,227
Variance	0	12,466	(31,808)	3,845	(15,497)
% Spend	0	106%	88%	101%	98%

A full breakdown of expenditure is in Annex 2, pp 39-43 of PSRP’s Annual Report.

Date of last narrative financial report	Quest No 5707918
Date of last audited annual statement	N/A as a contract

E: RISK

Overall risk rating: Moderate
Overview of programme risk
As PSRP enters the final year of its contract, the overall programme risk is assessed as ‘moderate’, with risk on a downward trajectory as the majority of programme activities successfully completed.
The main risks in this final year of the programme will be uptake and utilisation of the PSRP research findings by policy audiences. To mitigate against these risks PSRP programme partners will continue to focus on increased uptake of research and collaboration with key policy stakeholders in the UK and internationally. A clear engagement strategy is planned for the final year, following up on the PA-X database launch, and engagement with HMG stakeholders, the UN system, and OECD. Additionally PSRP plans further enhancement of its engagement with DFID/FCO country teams.
The programme was originally assessed as ‘Medium’ risk using DFID’s earlier 3 category scale. PSRP members and organisations have continued to implement the risk management activities agreed in the original tender, to ensure that levels of risk in the programme remain at an acceptably low level. PSRP has focused risk assessment/management around four risk categories, two of them related to the outputs set out in the Logframe, the other two relating to internal factors – governance and management of the programme – and to the external environment.
A detailed risk assessment was provided in the PSRP annual report and has been discussed with DFID at several points during the year.
PSRP reviewed Duty of Care procedures in all sites of ongoing field research last year. Systems put in place by partners were found to be reliable and compliant with University of Edinburgh oversight, and DFID policy. This was tested this year when conflict escalated in one research site and PSRP and DFID subsequently agreed not to publish a research paper, to ensure researcher safety.

PSRP established ‘Guidelines on Security, Risk and Ethics’ which were endorsed by all partners. Guidelines extend beyond contractual commitments, and requirements to inform the University of Edinburgh of risks, to include risk mitigation measures. These are attached as annex four of PSRP annual report (page 66) Quest No 5707918.
The geographical areas with highest risk for PSRP research are DRC, Ogaden/Ethiopia (where the major part of field research has already been successfully conducted) and Afghanistan. Research work underway in these areas is closely monitored and allowed sufficient flexibility to take account of changes to the security situation.
PSRP’s revised Duty Of Care and risk management procedures are appropriate to implement the work.
PSRP reports on activities and publications by partner and clearly identifies transactions to partners in budget and expenditure reports. DFID officials have met with all downstream partners at least once this year to discuss progress against activities.
Outstanding actions from risk assessment	None
F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The project is on track against the planned timeframe.
Performance of partnership (s)
DFID is represented on PSRP’s Consortium Advisory Group (CAG), which met for a full day in January 2018. Regular telephone meetings are held between DFID and the UoE. Work plans, objectives, performance measures and budgets have been shared and openly discussed with DFID, all to DFID’s satisfaction.
Asset monitoring and control
There are no physical assets associated with this project.

G: CONDITIONALITY

Update on partnership principles (if relevant) Not relevant.
H: MONITORING & EVALUATION

Evidence and evaluation
Qualitative feedback has been provided by policy audiences alongside data on quantitative targets for this AR. Monitoring is targeted at the specialist policy audiences working on peace processes who are the main consumers of PSRP research, and their feedback has been used over the last year to refine the research questions; and to specify the focus of policy briefs.
An evaluation has not been included in this programme. Given the nature of the research and the relatively small size of the programme, an evaluation was not considered to offer sufficient VFM over rigorous monitoring.
Demand for research on political settlements is variable, and subject to fluctuating conflict cycles and international attention. Ongoing peace and political processes can take 20 years or more to reach conclusion. PSRP’s work to inform ongoing processes is therefore best reviewed through feedback from those involved in the processes rather than concrete signs of progress in contexts where an end to conflict may be some way off (e.g. Syria, Yemen and South Sudan). PSRP’s work on Columbia last year demonstrates the value that research can provide when the political conditions for a positive milestone emerge. While we would expect these outcomes to contribute towards reduced discrimination, fragility, deaths in conflict, and violent homicide rates (PSRP programme impact indicators), it is clear that direct attribution and measurability are unlikely during the timeframes of this research programme.
Monitoring progress throughout the review period

DFID and PSRP have formal quarterly meetings to discuss and monitor overall progress and communicate monthly on routine business. PSRP submitted their Annual review and quarterly reports.in a timely manner. Quarterly reports are detailed and rigorous for a programme of this size.
This annual review was carried out during February and March 2017 by DFID A1 Conflict Advisor, and a B2 Project Manager. Substantive feedback was also received from FCO Research Analysts. One Research Analyst joined the DFID A1 adviser at the PSRP Annual Board Meetings in January 2018.
The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners. Key research and communication outputs were also reviewed. The review team consulted with all downstream partners included in the programme and with key policy audiences (e.g. the UN, mediators and HMG officials) to verify feedback provided by PSRP. The review team has included the additional feedback and quotes provided during the review within this annual report alongside those provided by PSRP.
A project review meeting was held in Edinburgh on 15/01/2018, the Consortium Advisory Group met on 16/01/2018, and a further meeting held between the AR team and PSRP in February 2018. The Annual Review report was shared with PSRP in March 2018. Recommendations will be followed up at subsequent project meetings.
ANNEX 1: Risk Matrix

Risk category	Probability	Impact	Mitigating Action
Risk Category 1: Delivery – High quality, relevant, timely and reliable research products
Research fails to provide a broadly applicable evidence-base capable of informing policy	Low	High	Cross-consortium collaboration increased in final year through forthcoming “ACCORD” publication on inclusion and policy briefs. Working with DFID and FCO to tailor research products for policy audiences.
Research fails to achieve high/international quality standards	Low	Moderate	Research assessed against Research Excellence Framework quality standards. Internal and external peer review mechanism in place.
Non-level playing fields between resources and attention given to the various work programmes proposed	Low	Minor	Minor redistribution of funds to mitigate this risk and to ensure all projects complete on time.
Research does not have any impact on potential users	Low	Moderate	PSRP has provided expert advice into ‘live’ peace negotiations. PSRP has planned further engagement with international mediators and FCO/DFID in the final year.
Research funded does not have any discernible impact on policy makers	Low	Moderate	PSRP must improve policy products this year to ensure that research is utilised by key international stakeholders including DFID and FCO.
Overall risk assessment of risk category 1: RARE/MODERATE
Risk Category 2: Operational – Research process, impact/capacity building, programme governance
Limited interest and/or willingness for policy engagement and research uptake by key external stakeholders	Low	Moderate	PSRP has a clear engagement strategy for the final year focusing on the PA-X database launch, and engagement with HMG stakeholders, the UN system, and INCAF.
Capacity building challenges with recruited Southern researchers	Low	Minor	Outputs have been delivered.
Unstable (politically or otherwise) working environment encountered in geographical area of work	Moderate	Minor	Delays were experienced but managed in Nepal, DRC, and Afghanistan. UoE has followed Duty of Care procedures. On one occasion they decided not to publish a paper to protect researcher safety.
Significant delay in project implementation due to unforeseen reasons	Minor	Moderate	The bulk of empirical field work and the PA-X database is complete. PSRP is due to meet implementation plans.
Inability to retain key programme personnel to ensure delivery	High	Moderate	Programme staff on time-limited contracts may move on as the project enters the final year. PSRP seeks additional funding to reduce this risk.
Changing priorities from DFID and/or other donors active in this research area	Minor	Minor	Demand for PSRP expertise and research remains high as the programme enters its final year.
Overall risk assessment of risk category 2: LOW/MODERATE
Risk Category 3: Fiduciary risk
Fraud such as misuse of programme funds	Minor	Minor	Regular financial reporting includes detailed monitoring and requirements to set-up traceable expenditure systems, in compliance with the Bribery Act.
Underperformance by any sub-contractor and/or breakdown of relationship between University of Edinburgh and any of its sub-contractors	Minor	Minor	All sub-contractors have delivered or are on track to deliver. PSRP regularly monitors all sub-contracted parties who report against detailed milestone targets.
Non-compliance with legislation, e.g. Companies Act, Taxes Acts, Health & Safety Act, Bribery Act	Low	Moderate	External audits; close management of partners and support from University of Edinburgh have enabled PSRP to comply with relevant acts.
Overall risk assessment of risk category 3: RARE/MINOR
Risk Category 4: / Safeguards
Risk level due to ongoing violent conflict and physical safety concerns for researchers	Low	Moderate	PSRP monitors and reviews risk assessments with sub-contractors. UoE decided not to publish one research paper due to researcher safety concerns.
Direct impact of natural disasters on research, dissemination	Low	Minor	With research in Nepal now complete the risk of natural disasters impacting on research is low.
Overall risk assessment of risk category 4: UNLIKELY/MODERATE
Risk Category 5: External context
Unfavourable political environment hampers field research, dissemination	Moderate	Minor	All partners undertake security assessments ahead of and during field research and dissemination events.
Climate change and policy engagement	Low	Minor	Risk is low as the programme enters the final year.
Environmental risks arising from the research	Low	Minor	Research outputs and communication materials are developed to minimise waste. PSRP require partners to minimise environmental impact and use electronic dissemination where feasible.
Overall risk assessment of risk category 5: UNLIKELY/MINOR
Risk Category 6: / Reputational Risk
Public campaigning against programme activities, use of funds, usability of programme	Low	Moderate	Use of funds, particularly regarding public engagement activities, is closely monitored to mitigate this risk.
Accusations against programme/funder during case study research in contested contexts	Low	Minor	Field research teams have established systems in place for delivering in contested contexts. This includes extracting researchers where necessary or choosing not to publish if it would pose a risk to researchers.
Ownership issues regarding programme ideas and output by competing research programmes	Low	Minor	The PSRP consortium has navigated ownership of ideas and input well and is on track to deliver planned research.
Overall risk assessment of risk category 6: UNLIKELY/MINOR

ANNEX 2: PSRP Publications

All publications and the blog outputs not listed below are available on the PSRP website. www.politicalsettlements.org.

Table 1. Published Outputs

Quart.	Pro.	Type	Delivery
Q08	4.1	Article	Brown/Ni Aolain: ‘Good Fences Make Good Neighbours: Assessing the Role of Consociational Politics in Transitional Justice’, forthcoming in McCullough/McGarry: Power-Sharing: Empirical and Normative Challenges, on SSRN: https://papers.ssrn.com/sol3/papers.cfm?abstract_id=2920849
Q08	1.1	Article	Bell/Pospisil: ‘Negotiating Inclusion in Transitions from Conflict: The Formalised Political Unsettlement’, forthcoming in Journal of International Development, 29:5, on SSRN: https://papers.ssrn.com/sol3/papers2.cfm?abstract_id=2922470
Q09	1.1	Report	Bell & Pospisil: ‘Navigating Inclusion in Transitions from Conflict: The Formalised Political Unsettlement’, PSRP Briefing Paper 16, 3/17, Edinburgh: University of Edinburgh, http://www.politicalsettlements.org/publications-database/negotiating-inclusion-in-transitions-from-conflict-the-formalised-political-unsettlement-briefing/
Q09	1.1	Article	Jamar & Chappuis: ‘Conventions of Silence: Emotions and Knowledge Production in War-Affected Research Environments’, Parcours Anthropologiques (Special Issues Ethnographier l’intime, les silences et les situations de violences by Jacinthe Mazzocchetti et Emmanuelle Piccoli), https://pa.revues.org/513
Q09	1.2	Report	Higazi & Yousuf: ‘From cooperation to contention. Political unsettlement and farmer-pastoral conflicts in Nigeria’, PSRP Briefing Paper 15, 2/17, London: Conciliation Resources, http://www.politicalsettlements.org/publications-database/from-cooperation-to-contention-political-unsettlement-and-farmer-pastoralist-conflicts-in-nigeria/
Q09	3.1	Article	Bell: ‘The Fabric of Transitional Justice: Binding Local and Global Political Settlements’, in Bell (ed.), ‘Transitional Justice’ (Routledge, 2017); available as SSRN Edinburgh School of Law Research Paper No 22, https://papers.ssrn.com/sol3/papers.cfm?abstract_id=2850418
Q09	3.1	Article	Bell: ‘Contending with the Past: Transitional Justice and Political Settlements Processes’, in R. Duthie & P. Seils (Eds.), Justice Mosaics: How Context Shapes Transitional Justice in Fractured Societies. NYC: Int Center for Transitional Justice, http://www.politicalsettlements.org/files/2017/05/201705_BookChapter_Bell_Contending-with-the-Past-Transitional-Justice-and-Political-Settlements-Processes.pdf
Q09	5.1	Accord	Thapa & Ramsbotham: ‘Two steps forward, one step back: The Nepal peace process’, Accord 26, London: Conciliation Resources, http://www.c-r.org/sites/default/files/Accord-26-Nepal-WEB_0.pdf
Q09	6.1	Report	Pospisil: ‘Pathways to Post-Liberal Peace: Perspectives on the “Common Good” in Peace and Statebuilding’, British Academy/PSRP Working Paper No. 7, London: British Academy, Edinburgh: Global Justice Academy, http://www.politicalsettlements.org/publications-database/pathways-to-post-liberal-peace-perspectives-on-the-common-good-in-peace-and-statebuilding/
Q09	6.1	Report	Jaede: ‘The Concept of the Common Good’, British Academy/PSRP Working Paper No. 8, London: British Academy, Edinburgh: Global Justice Academy, http://www.politicalsettlements.org/publications-database/the-concept-of-the-common-good/
Q09	6.1	Report	Molloy: ‘Justice, Rights and Equality: In Search of the Common Good in an Era of Transition’, British Academy/PSRP Working Paper No. 9, London: British Academy, Edinburgh: Global Justice Academy, http://www.politicalsettlements.org/publications-database/justice-rights-and-equality-in-search-of-the-common-good-in-an-era-of-transition/
Q09	6.1	Report	Anderson: ‘Case Study: Nepal’, British Academy/PSRP Case Study Paper, London: British Academy, Edinburgh: Global Justice Academy, http://www.britac.ac.uk/sites/default/files/Nepal_0.pdf
Q09	6.1	Report	Forster: ‘Case Study: Egypt’, British Academy/PSRP Case Study Paper, London: British Academy, Edinburgh: Global Justice Academy, http://www.politicalsettlements.org/publications-database/egypt-case-study/
Q09	6.1	Report	Jamar: ‘Case Study: Burundi’, British Academy/PSRP Case Study Paper, London: British Academy, Edinburgh: Global Justice Academy, http://www.politicalsettlements.org/publications-database/burundi-case-study/
Q09	6.1	Report	Wise: ‘Case Study: Bosnia-Herzegovina’, British Academy/PSRP Case Study Paper, London: British Academy, Edinburgh: Global Justice Academy, http://www.politicalsettlements.org/publications-database/bosnia-herzegovina-case-study/
Q09	6.1	Report	Welikala: ‘Case Study: Sri Lanka’, British Academy/PSRP Case Study Paper, London: British Academy, Edinburgh: Global Justice Academy, http://www.britac.ac.uk/sites/default/files/Sri%20Lanka_0.pdf
Q10	1.1	Special Issue / Article	Rocha Menocal/Pospisil, editors, Special Issue: Political Settlements, Journal of International Development, 29:5, July 2017, http://onlinelibrary.wiley.com/doi/10.1002/jid.v29.5/issuetoc.
Q10	1.1	Article	Bell/Pospisil, ‘Navigating Inclusion in Transitions from Conflict: The Formalised Political Unsettlement’, Journal of International Development, 29:5, 576-593, https://papers.ssrn.com/sol3/papers.cfm?abstract_id=2922470.
Q10	1.1	Article	Pospisil/Rocha Menocal, ‘Why Political Settlements Matter: Navigating Inclusion in Processes of Institutional Transformation’, Journal of International Development, 29:5, 551-558, http://onlinelibrary.wiley.com/doi/10.1002/jid.3289/full.
Q10	4.1	Article	O’Rourke, ‘Gendering Political Settlements: Challenges and Opportunities’, Journal of International Development, 29:5, 594-612, http://onlinelibrary.wiley.com/doi/10.1002/jid.3285/full.
Q10	4.6	Article	O’Rourke/Swaine, ‘Gender, violence and reparations in Northern Ireland: a story yet to be told’, The International Journal of Human Rights, published online first, 21 August 2017, http://www.tandfonline.com/doi/full/10.1080/13642987.2017.1360029
Q10	5.2	Report	Larson, ‘Processing Peace in Afghanistan’, PSRP Report/ACCORD Spotlight, Conciliation Resources; http://www.c-r.org/downloads/Processing%20peace%20in%20Afghanistan.pdf
Q10	6.1	Report	Bell, Navigating Inclusion in Peace Settlements, Human Rights and the Creation of the Common Good, PSRP/British Academy report, http://www.politicalsettlements.org/files/2017/06/BRIJ5395_Peacebuilding_final_ web.pdf.
Q11	1.1	Article	Pospisil, Menocal (eds.), ‘Why Political Settlements Matter’, Journal of International Development (Special Issue, 29:5, 2017), http://onlinelibrary.wiley.com/doi/10.1002/jid.3289/abstract
Q11	1.1	Article	Pospisil, ‘Unsharing Sovereignty: g7+ and the politics of international statebuilding’, International Affairs, 93:6, November 2017, https://doi.org/10.1093/ia/iix188, available on SSRN: https://papers.ssrn.com/sol3/papers.cfm?abstract_id=3057419
Q11	1.1	Article	Jamar, ‘The Social Life of Policy Reports. Reporting as a Tool in the Transitional Justice Battlefield in Rwanda’, Revue internationale des études du dévelopement, 2017/4 (N° 232), p. 165-194. DOI : 10.3917/ried.232.0165. URL : https://www.cairn.info/revue-internationale-des-etudes-du-developpement-2017-4-page-165.htm
Q11	4.1	Edited Volume	Ni Aolain, Cahn, Haynes and Valji (eds.), Handbook of Gender and Conflict (Oxford University Press, 2017).
Q11	4.1	Article	Ni Aolain, ‘Gendering the Law of Occupation: The Case of Cyprus’ Minnesota Journal of International Law (2017) is on SSRN here: https://ssrn.com/abstract=3048001
Q11	4.1	Report	Rooney, ‘Justice Learning in Transition: A Grassroots Toolkit’, on SSRN and available here: http://www.politicalsettlements.org/publications-database/justice-learning-in-transition/
Q11	4.5	Report	Baniya, B., Kharel, S., Thapa, D., & Ramsbotham, A. (2017). Gender and Nepal’s transition from war (PSRP Report). Available here: http://www.politicalsettlements.org/publications-database/gender-and-nepals-transition-from-war/ Q11
Q11	3.2	Report	Mallinder, L. (2017). Atrocity, Accountability, and Amnesty in a “Post-Human Rights World”? (PSRP Working Paper). Edinburgh: Global Justice Academy, University of Edinburgh. Available here: http://www.politicalsettlements.org/publications-database/atrocity-accountability-and-amnesty-in-a-post-human-rights-world/
Q11	3.4	Report	Zulueta-Fülscher, K., & Welikala, A. (2017). Substate Constitutions in Fragile and Conflict-affected Settings. Stockholm: International IDEA. Available here: http://www.politicalsettlements.org/publications-database/substate-constitutions-in-fragile-and-conflict-affected-settings/
Q11	4.6	Report	McWilliams and Doyle, ‘Violent Conflict, political settlement, and intimate partner violence: Lessons from Northern Ireland’. PSRP Research Report available here: http://www.politicalsettlements.org/publications-database/violent-conflict-political-settlement-and-intimate-partner-violence-lessons-from-northern-ireland/
Q12	1.2	Report	Salamanca et al, ‘Indigenous women and Colombia’s peace process’, PSRP Research Report available here: http://edin.ac/2DNO8K1
Q12	4.6	Book	Swaine, Conflict-Related Violence Against Women (Cambridge, 2017).
Q12	5.5	Report	Plonski and Yousuf, Peacebuilding and transition in borderlands. PSRP research Report available here: http://edin.ac/2DNNbkV