Type of Review: Annual Review

Project Title: Scaling Up Family Planning in Zambia

Date started:	March 1, 2012
Date review undertaken: 4th to 6thFebruary, 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing up to £14.8 million over a period of four years from 2012 to 2016 to scale up family planning services in Zambia. This funding includes £2.9 million for the procurement of family planning commodities. / The programme is addressing immediate needs through the rapid scale up of family planning services for under-served areas and populations and it is building the capacity of the public sector to deliver quality comprehensive family planning services beyond the programme timeframe. The programme is being implemented by Abt Associates Inc. / The programme is working with community health workers to sensitise communities on the uptake of family planning services and to provide accurate information to address myths and misconceptions. Outreach services are being delivered in partnership with the Ministry of Health (MoH) and Ministry of Community Development Mother and Child Health (MCDMCH) working with health facilities. / DFID is working with UNFPA to procure reproductive health commodities under this programme, based on identified gaps by the MoH’s Reproductive Health Commodity Committee. Supplies will be warehoused and distributed by Medical Stores Ltd (MSL) through the public drug supply system and will help address the current commodity gap in Zambia. Abt Associates will work with health facilities and districts to streamline their systems to ensure adequate supplies are available to support delivery of expanded services.

What are the expected results?
The impact will be improved maternal health in Zambia. By 2015 the programme will: / Reduce maternal mortality from 591/100,000 to 443/100,000. / Avert 92,450 unintended pregnancies (13,868 in adolescents) / Avert 13,059 unsafe abortions (1,958 in adolescents) / Avert 298 maternal deaths (45 in adolescents) / 80% of these results will be attributable to DFID. / The outcome will be increased use of family planning in Zambia. This will be measured by: / Increase the contraceptive prevalence rate in programme intervention areas from 20.4% to 27.2%. / A decrease in the percentage of women and girls with unmet need for family planning in programme areas from 27% to 5%. / The outputs and output indicators of the programme are outlined in detail below.

What is the context in which UK support is provided?
Zambia has one the highest maternal mortality rates in the world, with 591 women dying for every 100,000 live births[1]. High maternal death rates are associated with complications of pregnancy and childbirth, unintended pregnancy and unsafe abortion. Zambia has also a high and rising fertility rate at 6.2. Although the contraceptive prevalence rate has increased to 32.7% in 2007, use of modern reliable methods of family planning remains low. An estimated 27% of married women have an unmet need for family planning, 42% of pregnancies are unintended and unsafe abortion accounts for 30% of maternal deaths[2]. / Adolescent girls are particularly vulnerable to maternal death yet are poorly served by family planning services.They are less likely to be able to choose whether and when to have a child than older women, and have a much higher unmet need for family planning[3].Pregnancy is the leading cause of death in adolescent girls in developing countries, and girls aged 15-19 are twice as likely to die in pregnancy and childbirth as older women[4]. The 2007 Demographic Health Survey (DHS) showed that only 22% of married women aged 15-19 use a modern method of contraception. In addition, 28.5% of 15-19 year old girls have been pregnant or have had a child, and a higher proportion of adolescent girls in rural areas have begun childbearing (35%) than in urban areas (20%). / Unmet need for family planning and fertility, are highest in rural areas and among poorer, less educated and young women. Women in urban areas have 4.3 children on average, compared with 7.5 children per woman in rural areas[5]. Women who have more than secondary education have an average of 2.4 children, while women with no education have almost four times as many children. The poorest women have 8.4 children on average, compared with 3.4 children per woman in the wealthiest households. If all unwanted births were prevented, women would have an average of 5.2 live births (DHS, 2007).
[1] DHS 2007 (2009).
[2] MOH (2009). Standards and guidelines for reducing unsafe abortion morbidity and mortality in Zambia.
[3] UNFPA, 2010. How universal is access to reproductive health? A review of evidence
[4] WHO (2001). The Second Decade: Improving Adolescent Health and Development. Department of Child Adolescent Health and Development, Family and Community Health. Geneva.
[5] Zambia Demographic and Health Survey 2007, Ministry of Health

## Section A: Detailed Output Scoring
Output 1: Expanded availability of choice of family planning methods
Output 1 score and performance description: A – Outputs met expectations
Progress against expected results: / Indicators Results expected by Feb 2013 Results achieved Related comments and activities / Output indicator 1.1: Number of additional women and girls using FP methods (short term (pills and Depo-provera) and long term (implants, IUDs and sterilization)) Total (6000): / (i) Short term=3500(rural=2000: age 15-19=800, age 20+=1200; urban=1500: age 15-19=500, age 20+=1000); and / (ii) Long-term=2500 (rural=1500: age 15-19=500, age 20+=1000; urban=1000: age 15-19=300, age 20+=700) Total (12,944): / (i) Short term= / 11,842 / (rural=: 8,119: age 15-19= 4,335, age 20+=3,784; urban=3,723: age 15-19=745, age 20+=2,978); / (ii) Long term= 1,102 / (rural=1,035: age 15-19=104, age 20+=931; urban=67: age 15-19=13, age 20+=54) Short term methods do not include distribution of condoms (121,865). / This milestone was reduced to 6000 from 40,000 after the inception period. This was based on more realistic estimates due to a delayed start up. This overall target for the programme has not changed. / There is an underachievement in the number of long term family planning additional users. / Programme is using an innovative ‘camping approach’ to assist fast roll out*. / Year 1 targeted 7 first phase districts. So far, roll out has happened in 5 districts. The next two will occur at the end of February. / Output indicator 1.2: % of public sector facilities covered by the programme that experienced a stock-out of the full comprehensive package of FP methods last 12 months (defined as implants, IUDs, Depo and oral contraceptives) Baseline set at 3% (2 out of 75) based on an assessment of health facilities between March 2012 to October 2012 / The baseline shows low stock out rates at one point in time during the assessment. This will be regularly monitored over the programme and, if it remains low, this indicator may be changed. Not measured again – baseline just set. Will be measured regularly through random spot checks every two to three months and an average taken as the milestone in future years. Logistics and supply chain management assessment in 75 facilities completed to assess supply chain planning, management and storage. / Strong links with MSL, who are supporting the formulation of the logistics and supply chain management training modules for health facility staff. / 40 MCH Coordinators and pharmacist trained in RH commodity management. / Tracking system established RH commodities to health facilities. / Output indicator 1.3: Couple Years of Protection (CYP) generated attributable to the programme (CYP does not include pill users) Total 10,000 CYP: / Urban=3000 / (age 15-19=500; age 20+=2500); / Rural=7000 / (age 15-19=1500; age 20+ = 5500) 6,283 CYP: / Urban=732 / (age 15-19=146; age 20+=586); / Rural=5551 / (age 15-19=1304; age 20+ = 4247) Due to time constraints in calculating this figure, data for only 4 districts has been used (data for the 5th district not yet available). / Output indicator 1.4: Percentage of national forecasted need in reproductive health commodities (RHCs) met by the programme No contributionby Feb 2013. Participation in the quantification and forecasting of RHCs for 2013 supply plan. Finalisation of mode of RHC procurement. The forecasted need for RHCs in 2013 is £7.69 million. The programme is scheduled to provide £1.39 million worth of RHCs in 2013. This will cover 18% of the gap. UNFPA chosen as most value for money option to procure RHCs. Direct agreement with DFID signed. / SUFP will monitor the implementation process of the commodities in the target districts and attend national technical working group meetings and quantifications. / *The Camping Approach isinvolves launching all family planning activities in one district over an intensive two week period. This is summarised diagrammatically below: / This is followed by: / Supportive supervision and mentoring by the districts, assisted by the programme. / Integration of FP into district plans. / Follow up by the SUFP district outreach coordinator and technical teams. / Supply chain training for relevant health centre and district staff. / A great deal has been achieved in a short space of time.The detailed breakdown of family planning methods delivered as well as corresponding couple years protection calculated is summarised below (there are no corresponding targets for each method): / Method Couple Years Protection / Implants 3602 / Intra-uterine devices 386 / Depo-provera injection 2258 / Female sterilisation 38 / Future actions and recommendations: / Further define the methods for monitoring stock outs of the comprehensive package of FP commodities on a regular basis. If stock outs remain low, consider revising indicator 1.2. / Further focus on increasing the users of long term family planning methods. / Implement and monitor closely the tracking system of commodities and implement a district specific mentorship programme on commodities and supply chain management both at district and health facility levels. Avoiding stock outs at facility level is key. / Continue and strengthen the camping approach by including messages of commodity management in the trainings for health care providers and community based distributors (CBDs). / Where they are in place, utilise community health assistants to support the programme. They can play a role in the supervision of Community Based Distributors[1] (CBDs) or as depot holders for FP commodities. / Plan the integration of nutrition messages into trainings. / Plan the detailed integration of HIV couples counselling and testing into the programme (HIV prevention business case recently approved).This will involve joint meetings between SUFP and the HIV implementing partner, ZHERP to coordinate actions, streamline trainings, ensure consistency of data collection with no double counting etc. / Strengthen district ownership through training and integration of family planning into district plans. District outreach officers will be based in district health offices. / Impact Weighting (%):25% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No / Training of health centre workers on long term methods of family planning (Implants and IUCDs) / Training of volunteer community based distributors (often traditional leaders or SMAGs) in oral contraceptives and condoms. / Training of drama groups or mass media to assist community mobilisation / Orientation of traditional and religious leaders / Discussions with in-school and out of school adolescents / Training of adolescent peer educators / Increased access to FP services – integrated into regular MNCH static and mobile services / Behaviour change communication / Adolescent Community Outreach
[1] CBDs are volunteers from the community, trained to raise awareness and distribute condoms and the oral contraceptive pill.

Output 2: Increased access to family planning services for under-served areas and populations
Output 2 score and performance description: B – outputs moderately did not meet expectations / Indicators Results expected by Feb 2013 Results achieved by Feb 2013 Comments / Percentage of target communities covered by outreach services (comprising both community mobilisation and service provision) by the programme in target districts Total: 4%: / Rural=6.4%, / Urban=1.6% Total= 3% / Urban= 0.9% / Rural= 2.1% Disaggregated data not provided. / A large number (431) of outreach activities carried out in 4 districts by the time of the review. / CBDs provided with kits containing RHCs, registers, FP cards etc. / The approach to reach adolescents needs refining (see below).
Future actions and recommendations: / Document and share best practices and lessons learnt around the camping approach with other stakeholders. / Finalise the behaviour change communication strategy. / Ensure all complete, validated orientation and training packages are in place. / Support more locally organised outreach activities. / Further examine the best approach to reaching adolescents. The field trip revealed concerns from one school administration around teaching adolescents about family planning and indirectly increasing their risk of HIV infection. This was despite obvious situations where young girls were highly vulnerable e.g. living alone in rented accommodation to be near the school. SUFP should consult with all stakeholders experienced in working with adolescents e.g. Population Council and UNFPA. A specific adolescent package should be designed with a tailored approach to this group. Suggestions include framing the discussions around a broader ‘life skills’ base. Some adolescent sessions should always be conducted in same sex groups i.e. only girls or only boys. Ages could also be divided i.e. 10 years to 14 years and 15 years to 19 years. / Formative research around adolescents may be needed if enough information does not already exist. / Impact Weighting (%):30% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Increased community support for family planning
Output 3 score and performance description: A++ - output substantially exceeded expectations / Indicators Results expected by Feb 2013 Results achieved by Feb 2013 Comments / Number of Safe Motherhood Action Group members (SMAGs) trained as CBDs Total = 75: / Urban=20, / Rural=55 Total = 165: / Urban = 24 / Rural = 141 Where possible, CBDs are trained from existing cadres of community volunteers such as SMAGs. This promotes linkages to decreasing maternal mortality as well. / Number of community leaders trained as CBDs Total = 80: / Urban = 30; / Rural = 50 Total = 271 / Urban = 42 / Rural = 229 Where possible, CBDs are also chosen from community leaders to increase their influence. / Percentage of community leaders sampled who report favourable attitudes towards family planning Baseline 59% N/A - Baseline just set. Baseline percentage is higher than expected. / District commissioner support strong in all implementation districts.
Additional relevant activities conducted: / Mapping of existing community groups and youth friendly servicesin seven first phase districts. / Five orientation workshops for 128 members of these community groups, five orientation workshops for 131 youths from existing youth groups; and five orientation workshops for 121 influential traditional leaders/religious leaders. / Over 8,500 people from hard-to-reach areas were directly reached with FP messages through community outreach activities. Almost two thirds of these were adolescents and young adults. / Drama groups, radio messages, jingles and TV documentaries have been used to assist with sensitisation activities. / Behaviour change communication assessments conducted in 5 program districts and IEC/BCC materials review workshop was conducted. / A total of number 642 CBDs has been trained out of which 64% were males. The larger proportion of males is due to a lower number of literate females in the communities. The breakdown is shown in the figure below. / Future actions and recommendations: / Make concerted efforts to have a greater percentage of females CBDs than males. / Conduct FP training for district based facilitators/teams to ensure programme sustainability. / Train the local media in Family Planning and how they can use the media to enhance Family Planning awareness. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No but could change to medium risk in the next annual review. Early indications show that the community is more supportive of family planning than expected.

Output 4: Increased public sector capacity to provide comprehensive family planning services
Output 4 score and performance description: A – output met expectations
Indicators Results expected by Feb 2013 Results achieved by Feb 2013 Comments / Number of public sector health facilities in programme districts with the capacity to provide Long Term Reversible Methods Total = 40: / Urban=5; / Rural=35 Total = 38 / Urban=; 5 / Rural= 33 112 health care providers trained in long term family planning methods (LTFP). / Kaputa has set up LTFP corners at all service delivery levels – this model may be promoted elsewhere. / Not all facilities are able to provide LTFP because of lack of equipment. / Number of public sector health facilities in programme districts providing Adolescent Friendly Health Services Total = 5; / Urban=3; / Rural=2 Total = 5 / Urban= 3; / Urban= 2; / Percentage of health workers in facilities covered by the programme trained in Long Term Reversible Methods and Adolescent Friendly Health Services Total = 3%; / Urban = 1.2%; / Rural = 4.8% Total = 3% / Urban= 1.2%; / Rural= 4.8% All CBDs and health worker trainings have modules on how to mobilise communities and how to provide youth-friendly services. / Future actions and recommendations: / Equipment and supplies are currently being procured for the facilities and this process should be facilitated as much as possible. / Centres of excellence will be established in each district zone. / Implement mentorship activities in the first phase districts as part of continuing and sustaining the capacity building program / Conduct supportive supervision to sites in order to strengthen the quality of services. / Procure more training materials to support the district programs in FP. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results andValue for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / Yes the log frame has been revised since inception.The outcome on couple years protection has been changed to an output as it can be measured annually. The output on unmet need for family planning has been changed to an outcome as it can only be measured at the end of the programme. Indicators that could not be measured have been removed and others have been made more SMART. Milestones were adjusted based on baseline survey results and feasibility. All changes were approved by the DFID results adviser. / 1.2 Overall Output Score and Description: / A – outputs met expectations. / 1.3 Direct feedback from beneficiaries / Direct beneficiary feedback was obtained during the field trip to the start of the ‘camping approach’ in Milenge district, Luapula province. The review team included a representative of the Ministry of Community Development, Mother and Child Health. The team met with the district commissioner with other district staff, the chieftainess, other traditional and religious leaders, a drama group and school children. As the programme was just beginning in Milenge, no direct feedback from women accessing services was possible. / The district commissioner, his staff and the chieftainess were highly supportive of the programme and fully understood the relationships between unplanned pregnancies and maternal deaths as well as the need for support in these areas in their district. At the formal programme launch in the district, the chieftainess gave an eloquent speech describing the challenges women face with pregnancies that are not spaced and also if pregnant at too young an age. / Traditional and religious leaders expressed their wish to learn more about family planning and to support more choice for families. The Catholic pastor expressed his wish to learn more and to at least be able to discuss options with people. It will be important to follow up with these leaders to see whether they support family planning in the longer term. / The in-school adolescents were interested in family planning although were very shy to open up. The school administration expressed some concerns that talking of family planning to young people might reverse HIV prevention messages on abstinence and lead to more sexual activity. More work should be done to orientate schools on the issues and also on how to approach the topic of family planning with young people. The programme will use youth peer educators to reach adolescents and to train as CBDs - this is one strategy that may be effective.
1.4Summary of overall progress / The camping approach is an innovative method of ensuring that demand is not created without trained providers being in place and to create some momentum around family planning among communities. All early signs suggest that it is highly successful. The approach also ensures value for money as vehicles and staff focus intensively in one district. / The SUFP team have managed to energetically implement in five of the seven first phase districts with clear dedication and good planning. / SUFP is using an integrated approach where family planning messages will be integrated into broader maternal, newborn and child health presentations. The integration of HIV is another aspect of this. / SUFP is also well engaged at the national level with the MCDMCH and the FP technical working group etc. / The inception phase of the programme was delayed due to some changes in key human resource personnel and delays in arranging the baseline study. In addition, some time was spent in deciding on priority districts with the Ministry of Health and the MCDMCH. / Once these issues were resolved, a large number of activities have been completed in a short period of time including a logistics assessment; community and youth group mapping; IEC material development workshop; and rapid needs assessment. / Certain delayed activities should be completed in the next month including developing a final BCC strategy; releasing the final baseline study report; signing the MOU with the government; and developing the year 2 workplan with budget. / The targets for additional women using family planning as a result of this programme are ambitious. The year 1 milestone was modified down (from 40,000 to 6000) due to the late start up but the efficient scale up in future years is essential.
1.5Key challenges / Financial / Slow procurement of vehicles has led to increased spending more on vehicle hiring. / Baseline survey costs were not in the original budget / Programmatic / SUFP has explicitly targeted hard to reach areas, but it is difficult to conduct outreach services in these regions / Delayed engagement of District Outreach Coordinators (DOC) making it difficult to ensure activities at district and community levels are taking place / Systemic / The MOU with the government is awaiting approval / Some staff who manage the pharmacy (store rooms) in the health facilities in programme areas are not trained in inventory and logistics management systems
1.6Annual Outcome Assessment / There are two outcome indicators to increase the contraceptive prevalence rate as well as decrease the percentage of women with an unmet need for FP. Although early, indications show that these outcomes will be achieved by the end of the programme.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Expenditures through December 31st = £1,561,299 / Cumulative forecasts through December 31st = £1,513,746 / Expenditure by output: / Output 1 - Expanded availability of choice of family planning methods £346,539 / Output 2 - Increased access to family planning services for underserved areas and populations £476,104 / Output 3 - Increased community support for family planning £421,328 / Output 4 - Increased public sector capacity to provide quality / comprehensive family planning services £265,080 / Milestone Awards £52,248 / Total £1,561,299 / 2.2 Key cost drivers / Training and workshop expenditures (participants’ costs) / Printing / Vehicle hiring / International technical assistance / Graph showing the breakdown of cost drivers / 2.3 Is the project on-track against original timescale: / Partially. The start –up of the programme was delayed but roll out into all first phase districts is now almost completed (5 out of 7 completed and 2 planned at the end of February) bringing the programme back on track.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / On increased access to family planning services for under-served areas and populations, data gathered so far shows that adolescents are a broad segment of the population which has been dramatically underserved. SUFP will ensure that adolescent friendly reproductive health services are made available both through health centre static provision and outreach activities. / 3.2 Where an evaluation is planned what progress has been made? / A baseline survey has been conducted from a sample of 8 districts from all 26 proposed implementation districts with 2 control districts. The study included both qualitative and quantitative components and the report is expected by the end of February 2013.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / If implementation continues as it has started, it is possible that the risk level will be reduced to medium at the time of the next annual review as community support seems higher than anticipated. Reaching adolescents is the highest risk activity at present and the risks of facility stock outs of commodities.
Risk of funds not being used as intended / This risk is low. Abt Associates were chosen from the pre-selected global reproductive health framework organisations. Funds are channelled through Abt Associates as quarterly reimbursements for specific activities. Abt has also been submitting quarterly financial reports to DFID and have the procurement systems in place to ensure the money is used for what it is intended. / 4.4Climate and Environment Risk / The programme has a minimal impact on carbon emissions through the use of vehicles needed to reach remote areas of Zambia. This has been minimised as much as possible through car sharing by team members, promoted through the camping approach. Travel will be further reduced when the district outreach coordinators are in place at district level. The evidence around the negative contribution of rapid population growth on climate change is still strong and overall, this programme will have a beneficial impact.

5. Value for Money
5.1 Performance on VfM measures / A measure of cost effectiveness as laid out in the business case is the cost per CYP achieved. The costs are defined as economic resource costs (including costs the go beyond the immediate programme). The aim for the programme is achieve an economic cost of £30 per CYP. / It is too early within the programme to calculate economic costs. A simple calculation to give an indication of value for money is therefore the total expenditure/CYPs and this is currently £248 per CYP. Using this calculation, by 2016, the programme should achieve a figure of £45 per CYP. This figure is higher than global averages (all less than £15 per CYP) but the cost of operations in Zambia and the rural nature of the programme are likely to contribute to this[6]. / Due to the relatively slow start up of the programme, the number of CYPs achieved in this first year has been lower than originally intended. Costs are also higher in the first year due to large numbers of start-up trainings and remote locations. As the programme scales up rapidly in year 2, it is expected that the cost effectiveness will increase dramatically. / SUFP has developed a VfM framework to generate indicators and evidence on a quarterly basis. This includes a set of 8-10 VfM measures, assessed against global standards. Some of the indicators with values are shown below. A more detailed report will be available by the end of March 2013. / Indicators / Economy Average STTA rates = £686 (international) / Average LTTA rates = £400 / Percentage of national compared to international TA = / Nat 69% - Int 31% (days) Competitive / Competitive / National TA is on track with internal trend which is expected to rise to 75% at a mid-point and 80% by end of project. / Efficiency Administration and Management % of total expenditure = 40% / Unit cost per initial training participant £125 / Unit cost of providing services to each additional user of family planning = £52 40% is higher than external benchmarks due to set up costs. It is expected to reduce to 30% then to 25% during the life of the project. / Benchmarking data and internal comparisons to be collected / Unit cost is lower than internal trend projections, and is on track to meet Year 2 target of £48 / Effectiveness Cost per Couple Year Protection = £298 / Value of government contributions to SUFP activities Unit cost is higher than internal trend projections due to inception costs. However, it is still on track to reach the business case benchmark of economic costs of £30 per CYP by the end of the project. / This data is being collected. It will be shown as a % of SUFP budget, tracked against upward trajectory. / Approaches to ensure Value for Money / Commodity Procurement and Supply Chain Management / SUFP has avoided the full costs of training participants through jointly funding training sessions with Jon Snow International. / FP Capacity Building / Training is done in the community. This avoids the cost of hiring accommodation and venue in district capitals and reduces participants travel time and expenses. All purchasing of refreshments and supplies is done locally and therefore builds communities’ acceptance of the project. / Community and Adolescents Outreach / The government has contributed to outreach activities by providing vehicles, district workers and commodities. / Behaviour Change Communication / Information, Education and Communication (IEC) materials have been developed using existing materials, avoiding costs and making good use of existing resources. These materials have been tried and tested by other partners. In addition, a concession rate has been negotiated for TV and Radio spots. / 5.2 Commercial Improvement and Value for Money / DFID Procurement awarded the contract through a competitive bidding process. This is based on competitive fee ratesand a low cost approach using existing government resources. / DFID is procuring commodities directly through UNFPA to avoid payment of management fees. SUFP considered options for the procurement of commodities and demonstrated that direct procurement through DFID would reduce the fees from 14% to 7%. / The procurement procedures of the project routinely support value for money through competitive bidding and negotiation. / 5.3 Role of project partners / SUFP is implemented in partnership with the MOH and the MCDMCH. The project has been working closely with these partners to date and, in future, will engage with district planning to make sure SUFP activities are aligned with and integrated with district plans. / Within the project, partners RTT, ACNM and PPAZ have commenced work and the contracting process ensures good value for money. Payments are linked to deliverables. / In addition, SUFP has established working relationships with existing partners working in the field on family planning includingZambian Centre for Communication Programme (ZCCP), UNFPA, PPSAZ and Society for Family Health. SUFP looks to co-ordinate with partners to avoid duplication and save resources. / 5.4 Does the project still represent Value for Money : / Too early to say. The expenditure per CYP is high at present but the programme is too early in its implementation to draw this conclusion due to considerable start-up costs and lack of time to reach maximum numbers of beneficiaries as yet. / 5.5 If not, what action will you take? / The CYP numbers should increase dramatically as the programme picks up speed and roll out begins in more districts. The resulting economies of scale will make the cost per CYP decrease as the programme progresses.
[6] J Biosoc Sci. 1997 Apr;29(2):219-33. Costs of family planning programmes in fourteen developing countries by method of service delivery.Barberis M, Harvey PD.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Year 1 has seen a strong launch of the SUFP with innovative, sound, evidence based strategies and approaches in place. SUFP has also hired a dedicated, technically strong team who have managed, in a short time, to gain respect among the government and other partners and who are playing a leading role in family planning progress at a national level. Government ownership at district and provincial level is also high. / The original log frame was reviewed after the inception phase of the programme and more realistic milestones were decided. Almost all of these have been achieved in year 1. Although there is not clear value for money demonstrated at this stage, the programme is committed to achieving this and has clear strategies in place. / Start-up delays included unexpected human resource issues as well a delay in conducting the baseline survey, however, there is a need for rapid scale up of the programme from now on. / Specific action points for the SUFP team emerging from this review are listed below: / Focus on improving value for money in year 2 (Ongoing). / Complete the baseline study report, the BCC strategy and year 2 workplan with budget (by end of March 2013). / HIV integration:Plan the detailed integration of HIV couples counselling and testing into the programme. This will involve joint meetings between SUFP and the HIV implementing partner, ZHERP to coordinate actions, streamline trainings, ensure consistency of data collection etc. (by May 2013). / Further examine the best approach to reaching adolescents. SUFP should consult with all stakeholders experienced in working with adolescents e.g. Population Council and UNFPA. A specific adolescent package should be designed with a tailored approach to this group. Suggestions include framing the discussions around a broader ‘life skills’ base. Some adolescent sessions should always be conducted in same sex groups i.e. only girls or only boys. Ages could also be divided i.e. 10 years to 14 years and 15 years to 19 years. (by the end of March 2013). / Make concerted efforts to recruit more females as CBDs.(Ongoing) / Implement and monitor closely the tracking system of commodities to district and health facility levels. Avoiding stock outs at facility level is key. (Ongoing) / Consider strategies to maximise sustainability of the programme going forward.

8. Review Process
This annual review was conducted by the Health Adviser, Health and Nutrition Adviser and Programme Officer for DFID Zambia. The field trip (4th to 6th February 2013) in Milenge district in Luapula included the Health Promotion Specialist of the MCDMCH as well as the technical officer for ZHERP. Meetings were also held with PPAZ and RTT.