Type of Review: Annual Review

Project Title:Nigeria: State Accountability and Voice Initiative (SAVI)

Date started:2008	Date review undertaken:December 2012– January 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet willcalculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meetexpectation C

## Introduction and Context

What support is the UK providing?
SAVI was originally designed as a £21 million programme covering 5 states and operating over 6 years (2008-2014). SAVI currently works in five focus states in a full-scale way (Kano, Kaduna, Jigawa, Lagos and Enugu). It was envisaged that the programme would expand and an inception phase has been conducted in the states of Katsina, Yobe and Zamfara since 2011.A business case has been approved to expand the programme to cover 10 states and to extend implementation until 2015. This will require additional funding of £10 million.

What are the expected results?
SAVI was designed as one of a suite of State Level Programmes (SLPs) to bring about improved governance, service delivery (health and education) and private sector development at state level. SAVI was set up in 2008 to start to strengthen mechanisms for Nigerian citizens to hold government to account, supporting State Houses of Assembly (SHoA), media and civil society. / The impact of the intervention is expected to be the enhanced efficiency and effectiveness of selected state level governments’ use of public resources. The programme outcome is thatState houses of assembly, civil society, media and citizens demonstrate more effectiveness in demanding better performance from government and holding government to account. / The following results are expected at output level: / Civil society demonstrates a replicable and sustainable approach to issue-based policy advocacy and monitoring. / Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes. / More open and inclusive systems of communication and improved understanding between citizens, CS, media, SHoA and government. / Improved systems of transparency, public engagement and financial oversight in state houses of assembly. / Other development partners take a more sustainable and replicable approach to strengthening voice and accountability.

What is the context in whichUK support is provided?
More than 100 million Nigerians (64% of Nigeria’s 158 million people[1]) live in poverty. Nigeria has a quarter of Africa’s extreme poor, 10% of the world’s children out of school, 10% of child and maternal deaths and 25% of global malarial cases. Nigeria’s human development indicators are worse than comparable lower middle-income countries[2].In northern Nigeria, poverty rates are 77% and the current context is one of poor service delivery and little progress towards the Millennium Development Goals. / Poor governance is a major challenge and contributes to these poor development statistics. Thirty years of military rule and dependence on oil revenues has weakened the social contract in which government is accountable and responsive to citizens. Although oil provides Nigeria with disposable income, public resources are often mismanaged and corruption remains widespread. / Within Nigeria’s Federal system, State and local government are responsible for delivery of core public services and spend around 50% of the total budget. Effective spending at state level is essential for service delivery and poverty reduction. However, the various mechanisms for Nigerian citizens to hold government to account are very weak at state level (and even more so at local government level). The state legislature is seen as a ‘rubber stamp’ for the Governor. Civil society and the media still lack both the capacity and the resources they need to truly engage with government and advocate for change. All are rarely accountable to the people themselves. These factors contribute to a generally weak state of governance with limited ability of citizens to claim rights. The result is poor service delivery and little progress towards the MDGs.
[1] See UN Population Division’s World Population Prospects: 2010 revision and Nigerian Living Standard Survey (NLSS), NBS& World Bank, 2006.
[2] All figures are from the “Gender in Nigeria Report 2012”, British Council, May 2012.

## Section A: Detailed Output Scoring

Output 1: Civil society demonstrates a replicable and sustainable approach to issue-based policy advocacy and monitoring
Output 1 score and performance description: A (output met expectation)
Progress againstexpected results: / Output 1 covers the results of SAVI’s work in supporting coalitions of civil society organisations (Advocacy Partnerships) to engage in policy advocacy and monitoring at state level on specific issues of their concern. The output is measured according to three indicators. The main results are summarised below, with more detailed state-by-state scoring reported in annex 1. / Indicator 1.1 measures the strength of civil society partnerships in terms of their internal capacity, external relations and skills in policy advocacy and monitoring. The indicator is based on a new self-assessment tool, the Partnership Capacity Assessment.The PCA is a significant improvement on the tools previously used to assess the strength of the civil society partnerships. On a five point scale the average PCA score for all output 1 advocacy partnerships was 2.5 at the end of 2012. This was just short of the target of 2.7. / Some examples of advocacy success include, in Lagos where the People With Disabilities partnership is pushing for implementation of the PWD law, and has been working with the new government implementing agency (LASODA) and the State House of Assembly. In Kaduna the MNCH partnership has strengthened its work with grassroots facility health committees and the media. In Kano there has been a high level of citizen engagement in the MNCH and Water Supply Policy Partnerships. The focus of the Advocacy Partnerships in all 5 existing states has not changed since the MTR, except that the Enugu water supply & sanitation AP has been re-oriented to fit better with SAVI partnership model, and a new Gender and Social Inclusion Advocacy Partnership has been established in Jigawa. / Indicator 1.2 measures the level of independence of the Advocacy Partnerships from SAVI using the same PCA tool as for indicator 1.1. The average score for this indicator at the end of 2012 was 2.8 out of 5.0 against a target of 2.7. / SAVI’s latest progress reports (July-October 2012) indicate that many AP’s are becoming less dependent on SAVI. / Indicator 1.3 records cases of replication where civil society partnerships that are not directly supported by SAVI have adopted aspects of the approach used by SAVI supported partners. SAVI reports 11 replication cases so far against a target of 5 (see Annex 5). / Recommendations: / Develop standard format reports for the PCA assessment (to be updated annually), including detailed justification of scoring and comments by SAVI and the Advocacy Partnerships on the findings of the assessment and priorities for action. Following the PCA, SAVI and the Advocacy Partnership should prepare capacity development plans tailored to the findings of the PCA analyses and stating the commitments of both sides. (see annex 3 – PCA data quality review). / Report more systematically the results and activities of each Advocacy Partnership in regular progress reports. / Ensure that replication events are fully documented and logged at state level (see Annex 5). In future replication events reported on the logframe should only be admissible where they are backed by a replication diary and supporting documents. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes.
Output 2 score and performance description: A+ (output moderately exceeded expectation)
Progress against expected results: / Output 2 covers the results of SAVI’s work in supporting coalitions of civil society organisations (Advocacy Partnerships) to engage in government budget and planning processes. Following the Mid Term Review recommendations, this output has been reorganised to ensure that the budget and planning advocacy partnerships work more in support of issue based, output 1 Advocacy Partnerships. / Indicator 2.1 measures the strength of output 2 Advocacy Partnerships in terms of their internal capacity, external relations and skills in policy advocacy and monitoring. The indicator is based on the Partnership Capacity Assessment tool. On a five point scale the average PCA score for all output 2 advocacy partnerships was 2.4 at the end of 2012. This was just short of the target of 2.5. / SAVI’s latest progress report noted marked improvement in output 2 results compared to last year, for all states except Enugu. The reports highlight the following results under output 2: greater sharing of budget information between MDAs and CSOs in Jigawa, a performance assessment of the 2012 budget undertaken by the Know Your Budget partnership in Kaduna, stronger monitoring of the implementation of State Government Programmes by the Kano Budget Tracking Group, joint actions by CSOs and the media in Kano to engage citizens in the budget using radio phone in programmes, and routine participation by the Lagos Civil Society Partnership (LACSOP) in budget analysis. The progress reports acknowledge continuing weaknesses in the capacity and group dynamics of the output 2 partnership in Enugu (Participatory Budgeting and Planning). / Indicator 2.2 measures the level of independence of the Advocacy Partnerships from SAVI using the same PCA tool as for indicator 1.1. The average score for this indicator at the end of 2012 was 2.9 out of 5.0 against a target of 2.5. / Indicator 1.3 records cases of replication where civil society partnerships that are not directly supported by SAVI have adopted aspects of the approach used by SAVI supported partners. SAVI reports 16 replication cases so far against a target of 14 (see annex 5). / Recommendations: / Develop standard format reports for the PCA assessment (to be updated annually), including detailed justification of scoring and comments by SAVI and the Advocacy Partnerships on the findings of the assessment and priorities for action. Following the PCA, SAVI and the Advocacy Partnership should prepare capacity development plans tailored to the findings of the PCA analyses and stating the commitments of both sides. (see annex 3 – PCA data quality review). / Review in each state the extent to which Output 2 Advocacy Partnerships are engaged across the range of budget and planning processes in operation. Assess the extent to which there is scope to strengthen CSO engagement with a wider range of information sources and policy and planning processes. / Report more systematically the results and activities of each Advocacy Partnership in regular progress reporting. Pay greater attention to documenting budget and planning analyses undertaken by output 2 partnerships including their main findings and the influence of their work on key stakeholders including MDAs and other advocacy partnerships. / Ensure that replication events are fully documented and logged at state level. In future replication events reported on the logframe should only be admissible where they are backed by a replication diary and supporting documents (see annex 5). / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: high / Revised since last Annual Review? N

Output 3: More open and inclusive systems of communication and improved understanding between citizens, CS, media, SHoA and government
Output3 score and performance description: A (Output met expectation)
Progress against expected results: / Output 3 measures the extent to improved understanding and communication between citizens, civil society, the media, State Houses of Assembly and Government. It is measured by four indicators: / Indicator 3.1 measures the cumulative number of partnerships using SAVI approaches that are supported by leadership in civil society, the media, state houses of assembly and government. SAVI reports that 10 partnerships receive a level of leadership support that is strong enough to be viewed as ‘institutionalised’. This exceeds the 2012 target (8 partnerships receiving institutionalised support). / Indicator 3.2 measures the cumulative number of partnerships using SAVI approaches that are progressively including the voice of women and other socially excluded groups. SAVI reports that 17 partnerships in 2012 had institutionalised gender and social inclusion against a target of 15. SAVI’s progress reports indicate that all states are making good progress with mainstreaming gender and social inclusion into their advocacy partnerships and platforms. Three states have advocacy partnerships focusing on gender and social inclusion, but this is lacking in Enugu and Kano. / Indicator 3.3 measures the extent of public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability. This is a new indicator for which baselines are being established in 2012, and updates will be provided in 2013. IMEP is concerned that proposed method for assessing this indicator will not generate robust or useful results. SAVI intends that its state teams will estimate the percentage of (a) local partners, and (b) state citizens, with an acceptable level of understanding of 'the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability'. In IMEP’s view, such information can only be measured objectively through surveys of citizen awareness, and there is limited value in recording the opinions of state teams on the level of citizen awareness. / Indicator 3.4 measures the level of quality of coverage of SAVI-related policy issues and government budget and planning processes by SAVI supported media partners.This is a new indicator for which baselines are being established in 2012 (using a media OCA tool), and updates will be provided in 2013. IMEP finds that indicator 3.4 is a useful addition to the monitoring framework, but that the indicator needs to be reworded because the proposed method of measurement (an OCA tool) is oriented towards assessing media capacity rather than the quality of media coverage. / SAVI appears to be making progress in stepping up its support to the media following the MTR recommendation, including recruitment of 4 new SAVI staff and the development of state strategies for engaging the media that are shifting SAVI’s focus from individual journalists to media organisations. SAVI reports that the scale up of media activities has been held up by delayed agreement on SAVI’s expansion. / Recommendations / Proceed as soon as possible with the Organisational Capacity Assessments for media partners (indicator 3.4). Following this SAVI and its media partners should prepare capacity development plans tailored to the findings of the OCA and stating the commitments of both sides. / Discuss with IMEP and DFID whether indicator 3.3 in its present form is measurable and worth retaining. Consider developing an alternative indicator assessing the extent to which different sections of tripartite platforms (media, CSOs, State Houses of Assembly, as well as MDAs) regard mutual understanding and communication. This could be based on small regularly repeated surveys or focus groups. / Provide more systematic and regular reporting on the activities and results of the tripartite platforms linking civil society, the media and State Houses of Assembly. / Impact Weighting (%): 20% / Revised since last Annual Review? Yes - Increased from 15% to reflect greater emphasis on media development / Risk: Medium / Revised since last Annual Review? No

Output 4: Improved systems of transparency, public engagement and financial oversight in state houses of assembly
Output 4 score and performance description: A (Output met expectation) / This output measures the performance of State Houses of Assembly as institutions of accountability. It is assessed using five indicators, four of which are derived from an Organisational Capacity Assessment (OCA) tool. An OCA baseline and update have been completed by the State Houses of Assembly in 2009 and 2012. More recent and intermediate scores have been provided by SAVI state teams. Further details on the OCA methodology and findings of the 2012 update are provided in Annex 4. / Indicator 4.1 measures the level of quality of systems for recruitment and retention of house support staff and aides. The average OCA score for this indicator in 2012 was 2.7 against a target of 2.4. Comparison of the 2012 results against 2009 (see annex 4) show that this indicator has risen more than the others and from a lower base (increase from 1.0 to 2.7). / Indicator 4.2 measures the level of quality of systems for induction and monitoring of compliance with house rules and procedures The average OCA score for this indicator in 2012 was 2.7 against a target of 2.4. As with indicator 4.1 there has been a substantial rise in this indicator since 2009 (increase from 1.6 to 2.7). / Indicator 4.3 measures the level of quality of systems for public access to information and processes in the house and representation of public interests by members. The average OCA score for this indicator in 2012 was 2.2 against a target of 2.2. Comparison with data from 2009 suggests that there have been improvements in this indicator, but to a lower extent than for indicators 4.1 and 4.2 (increase from 1.2 to 2.2). / Indicator 4.4 measures the level of quality of systems for scrutinising public financial documents in the house. The average OCA score for this indicator in 2012 was 2.1 against a target of 2.2. Comparison with data from 2009 suggests that there have been improvements in this indicator, but to a lower extent than for indicators 4.1 and 4.2 (increase from 1.2 to 2.1). / Indicator 4.5 is a new indicator measuring the cumulative number of house committees and state houses improving the quality of their systems based on approaches initially demonstrated with SAVI support. As of late 2012 SAVI reports improvements in 26 committees and 14 state houses against targets of 25 and 10 respectively.
The comparison of 2009 and 2012 data indicates improvement for all four indicators, but with important differences between them. More rapid progress has been made for indicators 4.1 (human resource management) and 4.2 (Induction and oversight procedures) than for 4.3 (public engagement). and 4.4 (financial oversight). The progress recorded under indicators 4.1 and 4.2 have been useful quick wins, but 4.3 and 4.4 are more strategically important for SAVI’s overall goal of strengthening voice and accountability. It is also notable that SAVI has been spending considerably more resources on indicators 4.1 and 4.2 (see annex 2). A refocusing of expenditure towards supporting public engagement and financial oversight (4.3 and 4.4) appears to be warranted. / The analysis also reveals important differences between states with the most significant improvements recorded in Lagos and Enugu, and somewhat slower change in the Northern States. / SAVI’s progress reports indicate that the Enugu State House of Assembly has made particular progress on strengthening procedures for staff recruitment, induction of new members, public access to information and constituency outreach, although the quality of its scrutiny of public financial management has declined over the past year. Broad progress against most indicators is also reported in Jigawa, Kaduna and Kano. The Lagos State House of Assembly has the highest ratings, although there has been little change in these over the past year. / Several State Houses of Assembly are developing strategic plans (including in Jigawa and Enugu) and are preparing to implement Legislative and Budget Research Offices (Lagos, Enugu, Jigawa, Kano). / SAVI reports that the main problems currently being encountered are: (1) difficulties with the recruitment and retention of aides in Kano, subsequent to passage of the house service commission bill into law, (2) extended parliamentary recesses in Lagos slowing SAVI's engagement with the house, and (3) executive interference in house procedures in Jigawa. Limited scrutiny of public finance documents is a common weakness across all five State Houses of Assembly. / SAVI has started working with federal bodies that have outreach to the State Houses of Assembly, including the National Assembly Budget and Research Office, the Conference of Speakers and the Association of Clerks. / For budgetary reasons it has not been possible for SAVI to implement the MTR recommendation of appointing a dedicated SHoA officer in each state. However, SAVI has strengthened its SHoA advisory staff, and now has three SHoA advisors working at state level, with plans to recruit a fourth. / Recommendations: / In view of the trends revealed by the OCA scores SAVI should place greater emphasis and resources on work relating to indicators 4.3 (strengthening public access to information and processes in the house and representation of public interests by members) and 4.4 (public financial oversight by the State House of Assembly). / SAVI should aim to have co-signed work plans in place with 5 State Houses of Assembly by the end of 2013 based on OCA findings. This extends the MTR recommendation that SAVI should develop and agree work programmes with (at least) 3 State Houses of Assembly by end of first quarter of 2012. SAVI has made good progress against theMTR recommendation with particularly promising results in Enugu, where it is supporting the State House of Assembly’s Legislative Term Agenda. / Impact Weighting (%): 30% / Revised since last Annual Review? Yes – reduced from 35% to accommodate increased weighting for output 3 / Risk: High / Revised since last Annual Review? No

Output 5: Other development partners take a more sustainable and replicable approach to strengthening voice and accountability
Output 5 score and performance description: A+ (Output moderately exceeded expectation)
Progress against expected results: / Because SAVI is a demonstration project, its impact will depend on whether its methods and lessons are more widely adopted by other actors working to strengthen voice and accountability. Output 5 measures uptake of elements of SAVI’s approach by other development partners and is assessed according to two indicators: / Indicator 5.1 measures the cumulative number of other development partners accessing relevant and useful lessons learnt by SAVI and its local partners. SAVI reports that in late 2012 there were 37 such instances of replication, against a target of 20. / Indicator 5.2measures the cumulative number of firm commitments by other development partners to replicate key aspects of SAVI and its local partners approaches. SAVI reports that in late 2012 there were 20 such instances of replication, against a target of 10. / This annual review assumes that the claimed instances of replication are valid. On the strength of SAVI’s own claims, it appears that the programme is achieving some success in promoting the adoption of its approach by other development partners. However, the majority of claimed replication events relate to the other State Level Programmes and other DFID projects. While replication can be expected to start amongst SAVI’s closer partners, in future it will be important to look for more wider uptake by non-DFID projects and in non-SAVI states. Evidence of such broader replication would be required to achieve an A++ rating against this output. The full list of replication events is provided in annex 5. / Following the MTR recommendations, SAVI has revised its external communications strategy, and is developing a simple website. It has produced a publicity brochure and will prepare six monthly bulletins, each including four case studies of change. Much of this work is led by a UK based team and is aimed at informing the UK debate about how to effectively support civil society through development assistance. Dissemination activities in Nigeria operate more through personal networks and strategic advocacy. / Recommendations: / Ensure that replication events are fully documented, logged and analysed. In future replication events reported on the logframe should only be admissible where they are backed by a replication diary, supporting documents, and analysis on the how SAVI’s approach influenced others and how it has been adopted. / Continue with the implementation of the external communications strategy based primarily on strategic advocacy through SAVI’s own networks. Continue preparing communications products to support this work, including products geared at both international and Nigerian audiences. / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results andValue for Money.

1. Progress and results

Has the logframe been updated since last review? Yes / There have been changes to the logframe indicators since the Mid Term Review, which has required the recalibration of targets and complicates the task of comparing this year’s results against previous years. / The main changes are as follows: / Outcome level. Inclusion of anew indicator on media functionality (yet to be scored) / Output 1. Improved methodology for calculation of indicators 1.1 and 1.2 based on the Partnership Capacity Assessments. Rewording of indicator 1.3 capturing cases of replication. / Output 2. Improved methodology for calculation of indicators 2.1 and 2.2 based on the Partnership Capacity Assessments. Rewording of indicator 2.3 capturing cases of replication. / Output 3. Changes to measurement criteria for indicators 3.1 and 3.2. Redefinition of indicator 3.3 on public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly. New indicator 3.4 on media capacity. / Output 4. New indicator 4.5 capturing cases of replication where new systems and procedures promoted by SAVI have been adopted by State Houses of Assembly and their committees / Output 5. SAVI has rephrased the indicators and adjusted the measurement methods and targets. / IMEP has been discussing logframe changes with SAVI over the past year, and is in broad agreement with most of the changes, except where indicated in the recommendations for outputs 1-5 in part A above. / 1.2 Overall Output Score and Description:A (outputs meet expectation) / 1.3 Direct feedback from beneficiaries / This review is a light touch review based on documentary evidence. The only direct feedback from beneficiaries was through a total of 7 telephone interviews with SAVI partners aimed at testing evidence on SAVI’s ability to generate demonstrable change in policy and implementation (see annex 7).
1.4Summary of overall progress / SAVI appears to have made good progress over the past year in the five existing states, and its model for promoting change is increasingly demonstrating results. SAVI has recorded a total of 50 examples where it claims that its approach has influenced changes in policy and implementation. There is increasing evidence of the replication of SAVI’s approach by other development actors. / In most cases the Civil Society Advocacy Partnerships supported by SAVI under outputs 1 and 2 appear to have matured and strengthened over the past year. Under output 2 the Advocacy Partnerships on budgets and policy planning have been strengthened in most states (except Enugu). SAVI has stepped up its engagement with media organisations under output 3. Under output 4 relationships with State Houses of Assembly have strengthened over the past year, with some notable results including SAVI’s support to the Legislative Term Agenda in Enugu. Under output 5 development partners are becoming more aware of SAVI’s approach and are actively replicating elements of its model. / SAVI has completed inception activities in three additional states (Katsina, Yobe and Zamfara) and is preparing to engage in Niger and Anambra. The proposed scale up is several months behind schedule due to delays in approval of the required contract amendment. / SAVI has been stepping up its work with federal level organisations in support of change processes at state level. Federal actors can be an additional source of pressure driving change at state level. Their engagement can also help replicate lessons and lever broader impact beyond the states where SAVI currently operates.
1.5Key challenges / Insecurity.Over the past year the security situation has deteriorated markedly in northern Nigeria withfrequent terrorist attacks by Boko Haram. Yobe, Kano and Kaduna states have been particularly affected. Following the large scale Boko Haram attacks in Kano in January 2012 SAVI estimates that its work in northern states was heavily disrupted for a period of two months. Interviews with State Team Leaders in northern states indicate disruption caused by office closures, shortening of working hours, rescheduling of activities, harassment of staff members and citizens with connections to SAVI (including threat SMSs), and lower attendance at SAVI meetings. Work with State Houses of Assembly has also been affected by security concerns, in particularly constituency outreach work where State House of Assembly members feel particularly exposed. / Expansion.SAVI has completed inception activities (mainly restricted to scoping and the governance baseline study) in Katsina, Yobe and Zamfara. It is also preparing to engage in Niger and Anambra. SAVI will be operating in 10 states where it will establish full offices. It has also been requested to engage in additional policy areas concerned with growth promotion and youth employment creation.The proposed scale up of SAVI’s work is much more ambitious that that envisaged at the time of the Mid Term Review when a limited partnership with PRRINN-MNCH was planned in Katsina, Yobe and Zamfara states. / While there are attractions to scaling up the SAVI programme, this strategy also carries important risks. Already the preparation for scale up combined with delays in securing the required contract amendment has tied up considerable management time over the past 6 months. Engagement in the new states will require SAVI to develop new models of working and partnership and to develop expertise in new sectors.These demands require considerable change in SAVI’s focus and way of working over the last two and a half years of the programme. SAVI is currently receiving change management support from GRM. This should facilitate the transition, but there is still a substantial risk that achievements in the new states will be lower than expected as SAVI takes on new activities and adapts to new ways of working. There is also a risk of loss of momentum and quality in the existing states as SAVI refocuses on the expansion challenge.
1.6Annual Outcome Assessment / SAVI has made good progress against its outcome indicators, and targets have been moderately exceeded (A+ scoring). / Outcome indicator 1 measures the level of functionality of State Houses of Assembly as agents of voice and accountability. The scores are derived from the governance baseline survey that was updated in 2012. The target score of 2.9 out of 5 was achieved in 2012. This was an increase from the 2010 measurement of 2.2. / Outcome indicator 2is also based on the governance baseline survey, and measures the level of functionality of civil society as agents of voice and accountability. The score for 2012 was3.0 out of 5.0, just above the target of 2.9. This was an increase from the 2010 measurement of 2.1. / Outcome indicator 3 is a new indicator measuring the level of functionality of the media as agents of voice and accountability. This will be scored in future using an extension of the governance baseline survey. / The significant improvements in outcome indicators 1 and 2 measured between 2010 and 2012 reflect broad improvements across a wide range of governance indicators included in the governance baseline. There are additional sources of evidence that point towards an improving trend in governance in most of the states. These include the qualitative information provided by the focus groups working on the governance baseline update, SAVI’s case studies of policy change (see annex 7) / Outcome indicator 4 measures the cumulative number of demonstrable changes in policy and implementation by state government in response to public demand where there is evidence of attribution to SAVI's approach. At the end of 2012 SAVI claimed it had achieved 50 demonstrable changes against a target of 20. 57% of these changes were reported to reflect gender and social inclusion concerns (against a target of 50%). / IMEP has sought to validate the demonstrable changes in policy and implementation reported under outcome indicator 4. It has reviewed evidence for 20 of the reported changes that are documented in SAVI case studies (see annex 7). Taken together the 20 case studies provide reasonably solid evidence that SAVI is contributing to change at the outcome level. In most cases there was evidence that SAVI (often through joint working with other actors) had made a substantial contribution to bringing about the change. In some cases financial values can be attached to the reported changes which provide strong evidence of SAVI’s value for money at effectiveness level. Examples are provided in section 5 below and in annex 7. / Recommendations: / Implement the recommendations for strengthening the governance baseline update stated in annex 6. These include: (1) establishing tighter definitions for each level in the ratings scales, (2) presenting confidence intervals alongside indicators derived from the governance baseline, (3) using independent facilitators for future baseline updates, and (4) sharing experience on the use of the governance baseline with other governance programmes. / For outcome indicator 4 SAVI’s claims of demonstrable changes in policy and implementation must in future be backed by more complete documentation. Only those changes documented by a complete case study should count towards achieving the target. / SAVI should implement the recommendations stated in annex 7 on strengthening the documentation of outcome indicator 4 case studies. These include: (1) a clearer presentation of SAVI’s contribution to bringing about the change based on a diary indicating what SAVI did, with whom and how this influenced others and contributed to the change. The methods of outcome mapping could be usefully employed, (2) more complete information on the costs and benefits of SAVI’s contribution,(3) further information on financial contributions by SAVI’s partners, and (4) exploration of a range of high- and low-end scenarios estimating SAVI’s value for money in effectiveness terms for each case study.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The approved DFID budget for SAVI is £21.5million, of which £11.38 million (53%) had been spent by the end of Year 3 (July 2012). This is an appropriate level of expenditure just beyond the project’s mid-point. Over the past year the rate of spending appears to have increased. One year ago the MTR reported a total expenditure of £7.7million. / 2.2 Key cost drivers / Since inception SAVI has expended £4.77 million on long term technical assistance, £1.02 million on short term technical assistance, and £5.82 million on other expenses. Technical assistance is therefore a major cost driver, representing 49% of the total expenditure to date, but SAVI has ensured economy by limiting short term international TA and reducing unit costs for long and short term TA. / Amongst ‘other expenses’ the main cost elements are programme activities (£2.52 million since inception), office operations (£2.08 million), living costs/daily allowances (£0.65 million) and travel (£0.29 million). / In the past year additional security requirements have raised costs, but only to a modest extent. Additional security costs over the past 12 months are estimated at £125,000. / 2.3 Is the project on-track against original timescale: Yes / The project should deliver its expected results in the original five states over the original six year time frame (2008-2014). In order to ensure adequate progress in the five new states SAVI is seeking a one year time extension, until 2015.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / SAVI’s theory of change was validated by the Mid Term Review, and its underlying assumptions appear to be holding. The increasing evidence of results at output and outcome level demonstrate the effectiveness of SAVI’s model for strengthening voice and accountability. Having demonstrated the viability of its approach, SAVI is now moving into a scale-up and replication phase. There are useful lessons from SAVI’s approach that can be applied to other DFID V&A programmes. / New evidence on programme effectiveness has become available over the past year, including: (1) the governance baseline update, (2) the partnership capacity assessments for the output 1 and output 2 advocacy partnerships, (3) the Organisational Capacity Assessment updates for State Houses of Assembly, (4) the case studies of SAVI’s contribution to changes in policy and implementation, and (5) evidence of uptake of SAVI’s approach by other development partners (replication diaries). IMEP has reviewed the quality of each of these sources as part of this annual review (see annexes 3-7). / 3.2 Where an evaluation is planned what progress has been made? / No major evaluation planned, but IMEP will continue its ongoing M&E work.

4. Risk
4.1 Output Risk Rating: medium to high / 4.2 Assessment of the risk level / SAVI’s own risk assessment appears to be broadly accurate and is reproduced below. IMEP would like to highlight the following points. / Security risks have increased and are judged to be high, particularly in the north of Nigeria, but also in Anambra (kidnapping threat) where SAVI is proposing to begin operations. So far SAVI has managed to continue operating in the north in spite of Boko Haram attacks. However, a worsening of the security situation would threaten SAVI’s ability to operate here. / Political risks will remain high even if there is a lessening of Boko Haram violence. The approach of the 2015 elections can be expected to generate increased tension and political violence. This may particularly affect SAVI’s ability to work with State Houses of Assembly. / IMEP judges the institutional risks surrounding SAVI’s expansion into new states to be medium to high. SAVI is not only expanding into insecure new states, but it will also be engaging in new sectors where it has limited experience. The broader focus and geographical spread may mean that assumed efficiency gains from economies of scale may not materialise. Synergies with other SLPs will also be weaker in the new states. Although SAVI has an expansion management plan, its implementation is likely to strain SAVI’s programme management and technical capacity. Technical knowledge on growth and employment issues will need to be brought into the programme. Steps should also be taken to avoid a loss of momentum in existing states and sectors. / Risks Likelihood Impact Mitigation strategies / 3=high 1=low 3= high 1=low / POLITICAL 3 3 Programme: SAVI will enforce recently updated security procedures (general security architecture for the programme) by hiring a full time (cost-shared) security manager. Additional security requirements are necessary given recent spread of Boko Haram attacks. / Increased insecurity DFID: State Representatives, Advisers and DFID Risk Management team to proactively address potential security risks and mitigation response. Ensure partners understand the potential delay or termination if security risk threaten programme. / Inadequate autonomy of State houses of assembly 2 2 Programme: Engagement with National Assembly, Conference of Speakers, Association of Clerks of state houses, and Nigerian Governors Forum to advocate for the adoption of required Amendments to the Constitution previously blocked by the then incumbent Governors. / DFID: Leverage opportunities through policy and programme dialogue to lobby for required changes. / Political volatility 2 2 Programme: Adaptation of advocacy strategies, identifying opportunities to influence policy under the prevailing circumstances, while also implementing above-proposed management /mitigation measures against rising insecurity greater sensitivity in the selection of issues / DFID: Maintaining close working relations programmes on political analysis and high level engagement with political office holders and security personnel as appropriate / BENEFICIARIES 2 2 Programme: The provision of a self-assessment of the House (OCA) and resulting change plan endorsed by the Legislature should provide “political cover” to individuals and minorities in the House in order to take forward the endorsed reform agenda and those supporting its implementation. Retribution levied on journalists for reporting more evidenced based reporting needs to be protected, help and guidance is expected from the Nigerian Guild of Editors. Where appropriate both formal and informal contacts will be required to establish confidence building measures through existing contacts at State Level. / Intimidation of individuals and groups supporting reform. DFID: Leverage opportunities through policy and programme dialogue to lobby for required changes and support for reform. Political engagement as required. / INSTITUTIONAL 1 3 Programme: An ‘expansion management plan’ has been developed to sequence the recruitment, induction and orientation of new staff in line with a tenable work-plan of activities in each state and as much as possible in tandem with other DFID programmes. / Lack of SLP Co-ordination DFID: Ensure SLP Core group is functional and able to coordinate activity. / Impact not sustained beyond the programme lifetime 1 3 Programme: The “Theory of Change” and approach of SAVI with its engagement with Partners emphasise diminishing dependency on SAVI resources and an exit strategy is agreed with partners from day one. / DFID Validate approach in independent Annual Reviews with low profile field reviews undertaken by DFID State Representatives. / Fraud or corruption on the Programme 1 3 Programme: Ensure good quality financial management control systems in place. Monthly monitoring of financial implementation against activities. / DFID: Regular financial audits and reviews. / OVERALL 1.75 2.5
Risk of funds not being used as intended / This risk is low as SAVI does not provide sub-grants to its partners and manages all of its funds itself according to DFID’s accounting and audit standards (as noted in the independent Audit Report and Management letter for the period April 2011 to March 2012). / 4.4Climate and Environment Risk / Environmental screening was completed as part of the original programme proposal. There is no evidence to suggest that the proposed programme will have an impact on environment and climate change. SAVI partners are engaged in advocacy work on climate change risks in Lagos State.

5. Value for Money
5.1 Performance on VfM measures / Further evidence in support of the points made below is provided in annex 2. / SAVI has made progress since the MTR towards adopting a comprehensive Value for Money approach. SAVI has a Value for Money strategy which outlines the framework for the programme to generate evidence and data for the basis of responding to the DFID VFM framework. The SAVI VFM strategy builds on the work and recommendation of a DFID Nigeria commissioned study - ‘Better Assessing VFM in DFID Nigeria Governance and Conflict Programming’ conducted by ITAD in October 2012 - which aimed to set out how value for money can best be monitored and measured in DFID Nigeria governance and conflict programming. As recommended by the MTR, SAVI has since strengthened its financial systems and has made significant progress in its ability to capture sub-output expenditure at source and allocate TA inputs to outputs and sub-outputs. / Economy (cost of inputs) / SAVI made efforts to achieve more economy during the year in review by putting in place systems and processes for more economical procurement and ensuring high value to cost ratios in TA inputs, as well as additional monetary savings.. / The overall weighted average cost per input day for long term technical assistance shows a decreasing trend from inception (£171 during inception to £149 in Yr. 3). With the exception of Abuja, Enugu and programmemanagement, all states have decreased in unit cost per LTTA input day over the past year. SAVI’s long term TA rates compare favourably with similar DFID projects (ESSPIN £182 and PATHS2 £227). / The overall weighted average cost per input day for short term technical assistance has also fallen since project inception £439 in Yr. 1 to £396 in Yr. 3), although there has been an increase in the cost of international short term TA.SAVI’s short term TA rates are between the levels of PATHS2 (£384) and ESSPIN (£548). SAVI has promoted economy by shifting from using international to national short term consultants, and replacing short term with long term TA. / Further, the proportion of expenses spent on direct outputs has increased year on year, and now accounts for 43% of total expenditure. / Efficiency (cost of outputs) / Two new data sources have become available that enable an assessment of the cost of outputs: (1) data from the Partnership Capacity Assessments (PCAs) indicating progress in strengthening the capacity and independence of Advocacy Partnerships supported under outputs 1 and 2, and (2) data from the updated Organisational Capacity Assessments showing change in the capacity of State Houses of Assembly between 2009 and 2012 (output 4). Both of these provide relatively robust measures of change and an opportunity to compare results against expenditure. The results of this analysis are presented in annex 2. / The assessment shows thatSAVI expenditure has made a strong contribution to the improved capacity of the Advocacy Partnerships(outputs 1 and 2). SAVI has been instrumental in convening the Advocacy Partnerships and providing on-going support. There is also evidence that SAVI support has contributed to better performance and capacity in State Houses of Assembly(output 1).However, there are limitations to the extent to which attribution can be assumed as the improved scores can be affected by a variety of factors, most importantly local political processes. / Effectiveness (cost of outcomes) / This review applies two methods to measure VFM at effectiveness level: (1) comparison of changes in the governance baseline scores against spending on relevant outputs, and (2) use of data on costs and benefits from the case studies of demonstrable changes in policy and implementation. The detailed results of the VFM effectiveness analysis are presented in annex 2. / Overall the analysis shows that SAVI expenditure has contributed to notable governance improvements particularly in voice and accountability in the focal states. Scores indicate that the improvements are strongest for improvement in civil society ratings (average improvement 0.7) but weaker on improving State Houses of Assembly (average improvement 0.4). / Additional evidence on VFM effectiveness can be obtained from the case studies of SAVI’s contribution to changes in policy and implementation (outcome indicator 4). IMEP has completed a review of these case studies (see annex 7), and finds that they provide evidence of value for money at effectiveness level. SAVI spent a total (to date) of £10.26 million (in the 5 States) which contributed to monetary benefits of £ 19.5 million recorded in Case Studies.Some example of how SAVI’s contribution in 2012 to bringing about policy change has generated significant benefits include: / Case Study 10: Kaduna Government Institutionalises Citizen’s Participation in Government Planning and Monitoring Process through MTSS. The case study notes a 15% increase in the education budget and a 36% increase in the health budget between 2010 and 2011 (approx. £2 million), which can in part be attributed to SAVI sponsored citizen participation in the MTSS. / Case study 13: Kano State House of Assembly Committee on Local Government responds to public demand for transparent use of Local Government Funds leading to dismissal of six LGA chiefs. Budgetary savings resulting from the discovery of misappropriated funds are estimated by SAVI to be £1.8 million. / Case study 14: Kano State Government introduces monthly disbursement of funds to improve speedy implementation of Free Maternal and Child Health Programme. As a result of more regular budgetary releases, funding for the FMNCH programme increased from £480k to £600k per month in 2012. / Case Study 18: Jigawa CSOs’ demand for accountability saved Government over £188k. SAVI supported budget tracking and project monitoring work ensured the completion of the contract and payment of compensation to land losers. / The case studies are still in draft form, and many do not yet provide estimates of financial costs and benefits. The completion of these case studies will be essential to making a more complete and evidenced judgement on value for money at the effectiveness level. Annex 7 reviews the case studies in more detail and provides suggestions on how the valuation of costs and benefits can be strengthened. / 5.2 Commercial Improvement and Value for Money / SAVI appears to be recruiting technical assistance at rates that are competitive within the industry. Large scale procurement of supplies has been carried out by Crown Agents. / 5.3 Role of project partners / For each output SAVI’s contribution has often been matched by a financial or in-kind contribution of the project partner. This makes it possible to deliver outputs at lower cost, thereby increasing value for money on efficiency grounds. SAVI has not measured the value of partners’ contributions, which makes it impossible to assess the scale of these leverage effects. However, in a few cases these contributions are referred to in the case studies of demonstrable changes in policy and implementation (see Annex 7). SAVI’s systems need to be extended to monitor partners’ contributions in a more regular and systematic manner. / 5.4 Does the project still represent Value for Money : Yes / Preliminary evidence shows that SAVI is providing Value for Money. SAVI’s LTTA and STTA rates compare favourably with similar DFID projects. SAVI also demonstrated strong evidence on Economy and Efficiency. There is emerging evidence of value for money at cost effectiveness level, but the quality of documentary evidence needs to be significantly improved. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / None for this type of project.

7. Conclusions and actions
SAVI has made good progress over the past year, and is increasingly demonstrating the value of its approach and ability to deliver results. SAVI is making good progress in implementing the MTR recommendations. A critical requirement for the next year will be for SAVI to improve the quality of its reporting and documentation, and in particular to provide more substantial narrative evidence to back up the quantitative indicators measuring programme results. / Specific recommendations are provided under the output headings in section A above. The number of new recommendations has been limited so as to enable SAVI to focus on completing implementation of the MTR recommendations, putting expansion plans into effect and addressing the data quality issues raised in annexes 3-7.

8. Review Process
This review was carried out by the Independent Monitoring and Evaluation Project (IMEP), and was led by Gareth Williams with support from Victor Adetula and Femi Adegoke. / Under instruction from DFID this review is a light touch review based mainly on documentary evidence provided by SAVI and two days of interviews with the SAVI core team in Abuja.In spite of these limitations, this review did not rely entirely on SAVI documentation. Additional evidence sources were used, including telephone interviews with SAVI State Team Leaders in eight states, and telephone interviews with seven selected SAVI partners in civil society. Furthermore, a major emphasis of this review has been to test the robustness of evidence provided by SAVI by carrying out in depth data quality reviews for all of the main output and outcome indicators (see annexes 3-7).

Annexes

Annex 1 - Detailed scoring sheets for output and outcome indicators
Annex 2 - Value for money– VFM annex
Annex 3 - Data quality review: Partnership Capacity Assessment (PCA)
Annex 4 -Data quality review: Organisational Capacity Assessment (OCA)
Annex 5 - Data quality review: Evidence on replication
Annex 6 - Data quality review: Governance baseline update
Annex 7 - Data quality review: Case studies on demonstrable changes in policy and implementation