Business Case

Rural Roads Improvement Programme (Malawi)

Prepared by:

Growth Team – DFID Malawi

February 2013

ABBREVIATIONS AND ACRONYMS

AADT	Average Annual Daily Traffic
ADC	Area Development Committee
ADMARC	Agricultural Development and Marketing Corporation
ADP	Agricultural Development Programme
ADP-SP	Agricultural Development Programme Support Project
AF	Additional Financing
AISP	Agriculture Input Subsidy Programme
ASWAp	Agricultural Sector Wide Approach
ASWAp-SP	Agricultural Sector Wide Approach Support Project
ASWG	Agricultural Sector Working Group
AWP	Annual Work Plan
AWPB	Annual Work Plan and Budget
CAS	Country Assistance Strategy
CEM	Country Economic Memorandum
CEO	Chief Executive Officer
CSO	Civil Society Organization
DA	Designated Account
DDP	District Development Plan
DFID	Department for International Development
EIA	Environmental Impact Assessment
EIRR	Economic Internal Rate of Return
EMC	ASWAp Executive Management Committee
EPA	Extension Planning Area
ESIA	Environment and Social Impact Assessment
ESMF	Environment and Social Management Framework
EU	European Union
FICA	Flanders International Cooperation Agency
FISP	Farm Input Subsidy Programme
FM	Financial Management
GIS	Geographic Information System
GoM	Government of Malawi
GPS	Global Positioning System
HDM	Highway Development and Management
HH	Household
ICB	International Competitive Bidding
IDA	International Development Association
IFMIS	Integrated Financial Management Information Systems
IFR	Interim Financial Report
IGPWG	Income Generating Public Works Programme
IMT	Intermediate Means of Transport
IPC	Internal Procurement Committee
IRI	International Roughness Index
ISP	Infrastructure Services Project
LA	Local Assembly
LDF	Local Development Fund
LVSR	Low Volume Sealed Road
MDTF	Multi-Donor Trust Fund
MAFS	Ministry of Agriculture and Food Security
MASAF	Malawi Social Action Fund
M&E	Monitoring and Evaluation
MDTF	Multi Donor Trust Fund
MF	Ministry of Finance and Development Planning
MIT	Ministry of Industry and Trade
MK	Malawi Kwacha
MLGRD	Ministry of Local Government and Rural Development
MoU	Memorandum of Understanding
MT	Metric Ton (1,000 kg)
MTPW	Ministry of Transport and Public Works
NAO	National Audit Office
NCB	National Competitive Bidding
NMT	Non-Motorised Transport
NPV	Net Present Value
NSO	National Statistics Office
ODPP	Office of the Director of Public Procurement
OP/BP	Operational Procedures/Bank Policies
ORAF	Operational Risk Assessment Framework
PAD	Project Appraisal Document
PDO	Project Development Objective
PEFA	Public Expenditure and Financial Accountability
PFM	Public Financial Management
PFMA	Public Finance Management Act
PIM	Project Implementation Manual
PMS	Performance Management System
PPP	Public-Private-Partnership
RA	Roads Authority
RAP	Resettlement Action Plan
RBM	Reserve Bank of Malawi
RED	Roads Economic Decision model
RFA	Roads Fund Administration
RFP	Request for Proposals
RPF	Resettlement Policy Framework
SBD	Standard Bidding Documents
SWG	Sector Working Group
TWG	Technical Working Group
VDC	Village Development Committee
VOC	Vehicle Operating Cost

Business Case and Intervention Summary

1.	Intervention Summary

Title: Rural Roads Improvement Programme (Malawi)

What support will the UK provide?
The UK will provide £13.17m of funding over 3 years (from January 2013 to December 2015) to improve 380 kilometres of rural unpaved roads - thus improving transport links, boosting local agriculture, and improving access to services. In addition to our support, the World Bank will provide £16m over the period, and the Government of Malawi will provide a further £1m. Our funding will be provided through a World Bank Multi-Donor Trust Fund, which will in turn disburse funds to the Roads Fund Administration of the Government of Malawi.

Why is UK support required?
What need are we trying to address? / Malawi’s economy is predominantly agricultural, with 85% of the population living in rural areas. There is an urgent need to enhance agricultural productivity and commercialisation, both to improve food security and to increase and diversify exports. The sector faces a number of barriers however, including the poor state of rural roads where Malawi’s infrastructure deficit is particularly acute[1]. 60% of villages only have access to a seasonal track, forcing farmers to transport produce at least part of the way to market by carrying it on their heads, or on bicycles[2]. This fundamentally limits farmers’ access to both markets and agricultural inputs, and makes it difficult to move beyond semi-subsistence farming. Roads are typically at their worst at the end of the rainy season – harvest time for the crucial tobacco and maize crops. And reviews of Malawi’s farm input subsidy programme have found that poor roads make it difficult for fertiliser to be distributed once the rains have started[3]. Freight transport costs on unpaved rural roads are up to 20 times more expensive per kilometre-tonne than on paved international roads – a function of the poor roads themselves, and the low levels of competition exacerbated by their poor quality[4]. And the maintenance regime on existing rural roads is often inadequate given funding constraints and the high cost of maintaining roads in their current unimproved state. / What will we do to tackle this problem? / DFID’s support will improve 380 kilometres of rural unpaved roads through spot improvements, rehabilitation, and upgrading of existing rural roads. The actual works done will depend on need, but will range from simply raising the level of road sections that are prone to rain damage (so that water runs off rather than accumulating in the road), building drains and culverts, introducing gravel surfacing, and in some cases tarmacking sections of road that have high levels of traffic or are particularly vulnerable (e.g. on steep slopes). Sustainable maintenance regimes will be put in place involving maintenance clubs made up of local people to help build local ownership of ‘their’ sections of road, and community based monitoring will be used to involve local villages in assessing progress and impact. Capacity building will be provided to the Roads Authority to enable them to implement this programme, and other programmes in the future. This programme is in the DFID Malawi Operational Plan as part of our efforts to improve rural livelihoods. Our funding will pay for upgrades in 5 districts in Malawi - the World Bank will pay for similar work in 5 more. Whilst there are other donor-funded roads projects in Malawi, those mostly involve paved roads rather than the unpaved rural roads that will be the focus of this project. Our comparative advantage here is partly funding (neither the World Bank nor the GoM have the funding available to pay for the work in the extra 5 districts), and partly due to our range of other programmes that aim to reduce vulnerability and expand opportunities in high-potential agricultural areas – these initiatives will be complementary. / Who will be implementing the support we provide? / Our contribution to this overall programme will be provided through the World Bank. Our funds will be channelled through a World Bank managed Multi-Donor Trust Fund that is being set up as part of the broader Agriculture Sector Wide Approach (ASWAp) of which this programme is part. The road works will be procured and carried out through Government of Malawi systems in order to build capacity in (rather than undermine) government institutions.UK funds will therefore be disbursed from the MDTF to the Government once work plans have been prepared and agreed for the construction works. As is normally the case with such MDTFs, the World Bank will be responsible for managing our funds, and monitoring progress of the project, including the tendering of the construction contracts. Overall responsibility for this programme will therefore lie with the Ministry of Transport and Public Works (MTPW) of the Government of Malawi, who will provide policy direction and coordination. In practice, in accordance with the governance framework for the sector, the MTPW has delegated its powers for the management of this sector to the Roads Authority, whilst the Ministry of Finance has delegated financial management of the sector to the Road Fund Administration. This programme has been set up as part of the ASWAp to ensure that it is co-ordinated with other donor and Government programmes aimed at enhancing rural and agricultural development.
[1] Country Economic Memorandum (CEM),ion of the 2006/7 Agricultural Input Subsidy Program, Malawi, Final Report, (2008) SOAS.tional Statistical Office 2006/7. 2009 (WB)
[2] National Census of Agriculture and Livestock (NACAL), Agriculture Statistics Division of the National Statistical Office 2006/7.
[3] Evaluation of the 2006/7 Agricultural Input Subsidy Program, Malawi, Final Report, (2008) SOAS.
[4] CEM (2009)

What are the expected results?
What will change as a result of our support? / Rural road accessibility and conditions in 5 districts will be improved and maintained, which is expected to lead to increased road usage, better transport services and more efficient transportation. This is expected to reduce costs, allow access to new markets and inputs, and together with the other programmes in the ASWAp, increase the competitiveness of smallholder agriculture. Improved roads are also expected to improve access to services such as health care. In one of the 5 districts in which we will operate 68% women aged between 15 and 49 cite transport issues as a serious problem in accessing health care[5]. We expect the percentage of the rural road network that is transitable in the 5 districts to increase from 58% to 70% - with a focus on improving those roads that have the greatest potential to help boost local agriculture. / What are the planned outputs attributable to UK support? / Expected outputs from this project attributable to UK support include: / 120 km of rural roads rehabilitated and upgraded / A further 260 km of rural roads made transitable year-round through spot improvements / Contributing to the setting up of maintenance clubs of local people to maintain the 380 km of newly improved roads. / 5 engineers and 1 procurement and contracting specialist to provide technical assistance to the Roads Authority of Malawi during the life of the programme. . / Financial management and procurement training provided to the Roads Authority and the Road Fund Administration. / Support to the introduction of innovative and cost efficient maintenance methods (asset conservation), training and capacity building of key stakeholders. / We also expect this programme to generate approximately 2.2 million work days of temporary employment for workers upgrading the targeted roads, with a focus on using local people and women where possible. This is a time of economic hardship in Malawi due to a poor harvest and economic instability, so the timing of this project is opportune. A number of social protection programmes are being expanded in Malawi, (including cash for work programmes) to help at this time, and this programme is expected to generate similar benefits. / How will we determine whether the expected results have been achieved? / Output level results will mostly be measured by regular Roads Authority surveys of the road conditions and by programme implementation reports from project (and independently contracted) engineers. Higher level impacts will be assessed through baseline and end-of-project surveys commissioned as part of this project, and through community based monitoring to assess views of local communities on the effectiveness of the works carried out, and the impact on social and economic life in the towns and villages that are meant to benefit from the improvements. / What is the value for money assessment of the project? / The recommended option (building 380km of roads in 5 districts) is estimated to have a positive net present value of £6.7m, and an internal rate of return of 27%. These estimates do not include the broader benefits we expect from the programme, such as the expanded opportunities for agricultural diversification, or improved access to services such as health and education. Costs would need to increase by more than 60% before the costs outweighed the benefits. We therefore believe that this programme presents strong value for money for the British taxpayer. The programme includes technical assistance for the Roads Authority, and pilots of improved road maintenance systems to ensure the sustainability of the improvements.
[5] Malawi Demographic and Health Survey 2010. Scores for the 5 districts range from 38% to 68%.

# 2. Strategic case
# 2.1 Context and need for a DFID intervention

The Malawi Growth and Development Strategy (MGDS)

The Malawi Growth and Development Strategy II (MGDS II) sets out Malawi’s strategy for achieving the goal of wealth creation through sustainable economic growth and infrastructure development. The MGDS II is built around six broad thematic areas amongst them Infrastructure Development. MGDS II will be implemented through the National Budget and it is anticipated that Development Partners align their support to the MGDS II. The support to rural roads fits in well with the medium and long term investment plans for the transport sector: the Transport Sector Investment Plan (TSIP), the long term Roads Sector Program (RSP) and the 5-year Strategic Business Plan (2011 – 2016) of the Road Authority. The aim of the Strategic Business Plan is to improve the condition of the unpaved road network to 50% in good condition (from 44%, or +6%), 30% in fair condition (from 23%, or +7%) and only 20% in poor condition (from 33%, or less 13%).

Background and rationale for supporting feeder roads within the agricultural sector

Agriculture remains the main source of growth and exports in Malawi. With 85% of the population residing in the rural areas, the sector accounts for over 80% of the country’s employment, over one-third of Gross Domestic Product (GDP), and about 80% of merchandise exports. Over 70% of all farmers in the country cultivate less than one hectare and a significant number of these farmers still struggle to produce enough food to meet their annual consumption requirements. In areas where production has been good, poor roads have often prevented the marketing of surpluses.

Malawi faces an urgent need to diversify its agricultural production and exports. This is necessary to help address Malawi’s chronic balance of payments problems, and to reduce the reliance on maize and tobacco, especially given burley tobacco’s uncertain future. This in turn will require traditional (often subsistence) smallholder farmers to engage in more market oriented agriculture through better market access and integration into agricultural value chains with the overall aim to reduce transaction cost and increase competiveness. RRIP would therefore complement a range of other DFID programmes in Malawi which also aim at least in part to help small farmers in Malawi (the Private Sector Development programme, Access to Finance, support to the seeds component of Malawi’s flagship Farm Input Subsidy Programme and support to dairy farming),

The inaccessibility and poor conditions of Malawi’s unpaved tertiary, district and community roads[6] have a direct impact on agricultural productivity and market transaction cost, and therefore affects all these programmes, as well as efforts to develop agriculture more broadly:
[6] In the context of this document the terminology rural roads, feeder roads and unpaved roads is interchangeable.

The 2006/7 Agriculture Inputs Subsidy Program (AISP) review[7] states that once the rains start, fertilizer cannot reach rural suppliers on time contributing to low levels of stocks in remote selling points. Rural people are forced to travel to more distant markets to access fertilizer. Also, harvest time for the maize and tobacco crop is soon after the rains have finished, when the roads are at their worst. In summary, access to markets and suppliers for rural people is constrained by poor roads, many of which are not accessible throughout the year;
[7] Source: Evaluation of the 2006/7 Agricultural Input Subsidy Program, Malawi, Final Report, March 2008, School of Oriental and African Studies, London

A 2009 study[8]found that the infrastructure deficit is particularly acute in the area of feeder roads. Freight transport on such roads is up to 20 times more expensive in ton per km terms than that on international routes (MK 10 per ton per km as against MK 230 per ton per km). Yet, 80% of the population of Malawi depends on the commercialization of small-scale rural agricultural production that needs to be transported on the feeder road network;
[8] Source: The World Bank’s 2009 Country Economic Memorandum (CEM, 2009)

The same study attributes the high costs of freight transport on feeder roads to i) the poor condition of feeder roads, ii) subsequently low traffic volumes that reduce the competition, and subsequently recommends that investments in feeder road improvements should be made a priority.

An agricultural census carried out in 2006/2007[9]sampling 25,000 households nationwide presents the following nationwide averages for agriculture, access and transportation:
[9] Source: TheNationalCensusofAgricultureandLivestock(NACAL), Agriculture Statistics Division of the National Statistical Office (NSO), 2006/2007

- In relation to road infrastructure, 60% of the villages had access to a seasonal track, only 30% to an all season gravel road and just 8% to a paved road;
- It further shows that 56% of those villages without access to a paved or gravel road were located 4 km or more from the nearest all season road;
- About 75% of villages without access to a paved or gravel road accessed such a road by foot, 22% on a bicycle and 3% other, (motorcycle, ox cart, etc.);
- Transportation of produce to markets shows that on average 53% of the villages transported such farm produce by head, 35% by bicycle, 6% by ox or donkey cart and only 5% by public transport or matola (9 – 16 seat minibus);
- An inquiry into the rural hinterland of Salima shows that transportation of produce by bicycle taxi cost between £1.90 – £2.60 per ton.km (MK 1,140 – 1,560 per ton.km)[10].
  [10] Source: roadside interview in Salima district: cost MK 1000 for transporting a bag of 60 kg over a distance of 20 km.

Whilst cost effective and reliable transport of people and goods is crucial to achieve the underlying agricultural development objectives, the 2009 survey data from the Road Data Management System indicates that only 67% of the 11,400 km unpaved network was in good or fair condition (see Tables 1 and 2 below. Further details are in an annex at Quest No.3851035).And it isfair to assume that the overall condition of the road network has worsened since due to the current economic hardship in Malawi, which has exacerbated the lack of funds for maintenance. Government funding for maintenance comes entirely from a levy on fuel sales, so it is more insulated than most funding from budget cuts, but it is vulnerable to fluctuations in fuel sales, the real value of the levy (which is a flat rate rather than a percentage), and to rising maintenance costs.

Table 1: Malawi Road Network

Table 2: Malawi road conditions in 2009

	Paved		Unpaved		Total
Condition	km	%	km	%	km	%
Good	2 426	60	5 000	44	7 426	48
Fair	1 361	33	2 654	23	4 015	26
Poor	286	7	3 724	33	4 010	26
Total	4 073	100	11 378	100	15 451	100

The poor condition of the unpaved road network has various interrelated causes as explained by various previous studies carried out under the preparation of the Malawi Unpaved Roads Program MURP[11]:
[11] Source: Advisory report to the Ministry of Finance, Malawi on maintenance and rehabilitation strategies for unpaved rural and urban roads guidance Note 1 – The unpaved road network asset in Malawi, by Robert Petts. The MURP was never implemented, but was instead heavily revised to form the basis of this programme.

- Poor maintenance implementation strategies and insufficient resources for routine maintenance of the entire network in combination with ever increasing cost of maintenance activities leads to accelerated deterioration of unpaved roads;
- The subsequent backlog of maintenance means that the limited available financial and physical resources end up being deployed in a ‘restorative’ maintenance using heavy equipment that is both costly to run and difficult to maintain in remote locations;
- Many roads have now reached the stage of being unmaintainable and require substantial investment;
- This reactive regime is ineffective and represents poor value for money;
- The resulting frequent impassability suffered by rural communities also drives political pressure from the public for expensive upgrading of earth roads to surface standard.

Given the need for improved rural roads set out above, the World Bank is preparing a Rural Roads Improvement Programme as part of its Agriculture Sector Wide Approach (ASWAp) Support Programme. This will focus on upgrading rural roads in 5 rural districts.

Why a DFID intervention is justified

Other donors like the World Bank, EU, AfDB, Japan and China are actively involved in transport sector interventions. Except for the World Bank however, the rest of the donors are focusing on tarred roads. Whilst the World Bank is proposing to intervene, as set out above, they do not have sufficient funds available to meet Malawi’s large investment needs in this area, hence the need for UK involvement. In addition, as set out above, there is potential for significant synergies with other existing and planned DFID interventions in the rural and agriculture sectors. The proposed support is consistent with DFID’s ambitions set out in its Operational Plan for Malawi, with a strong focus on boosting economic growth and wealth creation. Whilst the GoM will (with the support in this programme) have the technical capacity to carry out this work, Malawi’s tight fiscal situation means that they are not in a position to provide the funding. In addition, political pressures encourage GoM to focus on paved road construction in paved road areas, even though, as set out above, the need for improving the existing rural road network is much greater.

In addition, a programme to improve rural roads would be expected to reduce the transport burden on women as non-motorised trips (predominantly made by women using head loading) on previously inaccessible roads will now be substituted by motorised forms of transport due to improved roads. Improved roads will also ease access to public services such as health and education, supporting our ability to deliver results in those sectors.

2.2	Impact and Outcomes we expect to achieve

At impact level, RRIP is expected to lead to an improvement in rural incomes, livelihoods and access to services. This will be through increasing the number of smallholder households with access to markets, increasing the frequency of visits to public health facilities by women and girls and increasing the land that is planted for commercial sale. At outcome level, the programme is expected to lead to improved access to markets and inputs for smallholder farmers through improved rural feeder road networks, improved mode of transportation and reduction in the road transportation costs. Additional information is presented in the RRIP logical framework on Quest Number: 3851100.

# 3. Appraisal case
# 3.1 General Overview

The Appraisal Case explores how DFID will address the need set out in the Strategic Case, generates various alternative options for such support and identifies which best delivers value for money within the context of the development objective and outcomes.

3.2	The Theory of Change

The programme will address the problem of poverty through increased incomes for the rural poor. The majority of Malawians are poor and live in rural areas. Their major occupation is subsistence agriculture. In the event of surplus production, it is difficult for these subsistence farmers to sell the surplus due to lack of access to markets as a result of the poor conditions of rural feeder roads which perpetuates prohibitive transportation costs. The RRIP will improve the conditions of the rural feeder roads and make them passable throughout the year. This will enable subsistence smallholder farmers to engage in more market oriented agriculture through better market access and integration into agricultural value chains with the overall aim to reduce transaction costs and increase competiveness. In addition, the RRIP will improve the rural roads to a level where the cost of maintenance will be significantly reduced. This is expected to allow GoM to expand road maintenance works using the freed resources. An improved road network will, in the process, contribute to economic growth and poverty reduction.

RRIP improve maintenance systems
RRIP improves rural roads

It’s easier for vehicles to reach rural areas, and they are less damaged by doing so.

Other components of ASWAp

Easier access increases transport competition
Transport costs fall

Easier physical access to health and education services
Farmers better able to access inputs
Farmers better able to access markets to sell products

Better opportunities for farmers, including diversification and integration into value chains

More use of health and education services and reduced cost

Increased rural incomes and decreased vulnerability

16.	On selection of economically justified road interventions: A preliminary economic evaluation was carried out with the Roads Economic Decision (RED) model to quantify the economic benefits and costs for each project alternative: spot improvement, rehabilitation to gravel roads and upgrade to low volume sealed road (LVSR) and compared to the ‘without project’ scenario. For each alternative, the cost (investment and maintenance) and the road user benefits (savings in vehicle operating cost and travel time) are computed. The resulting flow of net benefits using a 10% discount rate is expressed as the Net Present Value (NPV) and Economic Internal Rate of Return (EIRR). The following table presents a guide to select road service levels and road interventions as a function of Annual Average Daily Traffic (AADT) at the start of the project:

AADT	Road accessibility / service level	Proposed intervention	Average cost £/ km[12]
< 60	All season access, IRI[13] 20 -22	Spot improvement	8,000
60 - 180	All season access, IRI 8 - 10	Rehabilitation to gravel road	32,000
> 180	All season access, IRI 3 - 4	Upgrading to sealed road	160,000
[12] Source: Market study of contract rates under the World Bank funded Infrastructure Service Project (ISP)
[13] The International Roughness Index (IRI) is the roughness index most commonly obtained from measured longitudinal road profiles. It can be measured with vehicle mounted devices or correlated to the average speed a vehicle passes the road (section). The roughness index is expressed with units of slope (m/km). It has become the road roughness index most commonly used worldwide for evaluating and managing road systems.

The resulting thresholds will guide the selection of economically justified interventions for each selected road to be improved under RRIP. If the aforementioned thresholds are consistently applied throughout the project, road interventions will be economically justifiable on the basis of savings in time and vehicle operating cost alone, without considering other benefits for agriculture.

# 3.3 Generating options for DFID support

17.	For generating options, it is assumed that DFID has the choice to support the RRIP or not. If DFID does choose to support the RRIP, 2 different options for DFID support have been generated for further assessment using a different geographical focus (see table below).

Ref.	Option	Description
0	DFID does nothing	‘Do nothing’: DFID does not have a programme to support unpaved roads improvements
1	DFID supports the RRIP	“Intensifying support”: DFID provides a scale up of £13.17 million to expand the WB RRIPin the same 5 districts in which it currently plans to operate.
2		“Widening support”: DFID provides a scale up of £13.17 million to the WB RRIP, enabling it to expand into 5 new districts.

18.	Under option 0“do nothing”, The WB’s RRIP will continue to operate in 5 districts (Chitipa, Salima, Ntcheu, Mwanza and Chikhwawa) carrying out road improvements and maintenance and providing implementation support. Asset conservation and maintenance will entirely rely on the GoM contribution.

19.	Under option 1 “intensifying support”, DFID provides £13.17 million of funding to the WB through a Multi-Donor Trust Fund (MDTF) to expand RRIP activities in the same 5 prioritised districts. Road improvements are generally of the same type and outputs are proportional to the WB financed works; however there is a greater emphasis on asset conservation and value for money activities. Asset conservation will rely on both GoM and DFID contribution. Training and TA is provided to GoM to help implementation and sustainability.

20.	Under option 2“widening support option” DFID provides £13.171 million of funding to the WB through a MDTF, and the geographical coverage is expanded to include five additional districts. It is currently proposed that these 5 districts be [14]Karonga, Kasungu, Machinga, Phalombe and Nsanje based on the same selection criteria used for the five districts supported under World Bank funding, but this is being finalised by the MoAFS. Training and TA is also provided to GoM.
[14] See Annex 1 for detailed information on beneficiary districts

21.	We have not considered any option for DFID to set up its own bilateral rural roads programme. Designing and implementing such a project ourselves is not a DFID comparative advantage, therefore we will only consider engaging in this programme with a lead partner such as the World Bank that does have such a comparative advantage. There are no other suitable partners planning similar rural roads programmes in Malawi. The World Bank RRIP programme that we are proposing contributing to is integrated into Malawi’s Agriculture SWAp (ASWAp) in order to ensure that it is effectively linked to donor and GoM efforts to develop the agricultural sector. We are not aware of any other donors who are interested in contributing to this programme, and is we do not contribute funds the WB do not plan to increase their contribution to the programme. The counterfactual in Option 0 is therefore that no further road upgrading is carried out in any of the 10 districts beyond the work already planned by the WB in the original 5 districts.

22.	DFID support would be earmarked for improvement of 380 kilometres of unpaved rural roads through: (1) Spot-improvement works on critical sections of unpaved rural road. Works will include culvert installation, building simple structures and raising the level of the road, and will focus on ensuring that the road is passable for its entire length rather than being in good condition throughout; (2) Rehabilitation and upgrading to gravel standard of unpaved roads; and (3) Sealing of low volume unpaved roads, over selected sections of road where there are significant levels of traffic, or steep gradients. Typical construction involves the placement of a nominal 150 mm layer of appropriate quality gravel on the proof-rolled and previously traffic-consolidated sub-grade. In addition, the DFID support includes TA to and training for the Roads Authority. Since the support is through the World Bank managed MDTF, a US$35,000 (approx. £22,400) set-up fee and a further administration fee of 5% of the programme amount will be paid to the World Bank in line with DFID Guidance on World Bank Managed Trust Funds.

# 3.4 Cost Benefit Analysis and the Evidence Base

23.	Estimating the incremental cost to DFID of the 3 options is easy. Option 1 costs nothing, whilst Options 1 and 2 cost £13.17m. Similarly, the incremental benefit of Option 1 is zero. In order to estimate the incremental benefits of Options 2 and 3 we have quantified 3 of the main benefits that we expect to generate through this programme: (a) increases in agricultural productivity caused by improved access to inputs and markets, (b) reduced vehicle operating costs (since improved roads do less damage to vehicles) and gains from switching to motorised transport, and (c) increased incomes of poor individuals directly involved in the work. The methodologies for these are set out below.

Increased agricultural productivity
The estimation of these benefits is based on a study by Stefan Dercon et al (2008) assessing (amongst other things), the impact of proximity to roads in Ethiopian villages[15]. This study found using longitudinal household data that in the villages studied having access to an all-weather road (defined as a road capable of supporting truck and bus traffic in both the rainy and dry seasons) reduced poverty by 6.9%, and increased consumption growth by 16.3%. We have estimated likely benefits from improved agricultural productivity if these benefits were replicated in the areas in which roads will be improved. This was done by generating 2 scenarios, one in which existing consumption (derived from district data in the 2010/11 Integrated Household Survey) grows at the rate of expected GDP growth, and the second in which that consumption growth is 16% higher annually. The difference between these 2 benefit streams is the extra consumption caused by having access to all-weather roads. We do not know what proportion of the population in the relevant districts will gain access to all-weather roads because of this project, but we do know the proportion of existing roads that we expect to become all-weather as a result of the project (11.7 percentage points in Option 1, and 10.0 in Option 2) so we have used this as a proxy for the percentage of the population that will gain access to all weather roads.
[15] ‘The Impact of Agricultural Extension and Roads on Poverty and Consumption Growth in Fifteen Ethiopian Villages’, Stefan Dercon, Daniel O. Gilligan, John Hoddinott, TassewWoldehanna, IFPRI Discussion Paper 00840, December 2008.

Reducedvehicle operating costs

These were estimated using the Roads Economic Decision model referred to earlier. Driving along rough roads damages vehicles, and there is a known relationship between these costs, speed, and the roughness of the road. Based on surveys of road conditions and traffic counts for the respective districts these costs have therefore been assessed, based on assumptions about the kinds of roads that are likely to be upgraded under the 2 options, and expected improvements in road standards. An expected annual increase in traffic of 3% was assumed, as was a shift of 50% of bicycle trips and 25% of motorcycle trips to motorised vehicles as a result of the improved vehicle access. In Option 1, DFID would be improving roads in 5 districts where the WB is also improving roads. Because of this it was assumed that some of the highest priority roads will not be available for upgrade (since the WB is upgrading them). To adjust for this, the average traffic volume on DFID-improved roads has been adjusted by taking the average traffic volume for only those traffic counts lower than the 75th percentile point on the statistical distribution.

Temporaryemployment
We estimate that 2.2 million work days will be generated by the road works on the project (there will also be employment generated on an ongoing basis for doing maintenance on the roads after the works are complete, but since these will not be paid out of our funds, they have not been included in the CBA). Assuming that the workers are paid the minimum wage of MK350 a day (59 pence at today’s exchange rate), these transfers to the poor Malawians who will be doing the (mostly manual) work on the road improvements has been counted as a benefit.

27.	The benefits to agricultural productivity and vehicle operating costs have been assumed to persist unchanged for 5 years after the end of the project and then stop, whilst the benefits from temporary employment only last until the end of the project in 2015. An exchange rate of 1.6 US$ to the pound was used. The analysis does not include any costs funded by the WB or GoM’s funding for maintenance work (since this is a core function of GoM),or benefits from the roads that the WB are improving. However GoM funding for re-settlement costs have been included, by deducting a pro rata proportion from the total incremental benefits. , All costs and benefits were discounted at 10%, the standard DFID Malawi discount rate. This gives us the results table below.

Summary Results table
Option	Cost	NPV	IRR
Option 0	0	0	-
Option 1	£13.17m	£4.99,	23.4%
Option 2	£13.17m	£6.69m	27.5%

28.	A more detailed results table is shown at Annex 1. As can be seen from that table, the majority of the benefits are generated by the reduced vehicle operating costs as generated by the RED model. Indeed, even if only these benefits are included Option 2 still has a positive NPV of £3.3m. Surprisingly, the benefits from improved agricultural productivity are fairly modest. This is in large part due to the very low consumption levels in some of the districts, and the recent depreciation in the value of the Malawi kwacha, which has reduced the pound value still further. By way of illustration, mean consumption in the poorest district, Chikhwawa, is estimated at only 13 pence per person per day at current exchange rates. Therefore even large improvements in rural incomes only translate into small benefits in pound terms.

29.	In addition to these benefits that we have quantified, we would expect this programme to generate the following qualitative benefits.

- Promoting good practice in road asset conservation including the introduction of cost efficient maintenance methods through TA and training;
- Support to the development of the private sector by providing continued work load for small and medium scale civil work contractors as well as skills training in specific areas;
- Reducing the travel and transport burden on women and girls by increased usage of efficient forms of motorized and non-motorized transport to substitute head loading – time which can be more productively used elsewhere.
- Improve competition in the transport sector by expanding the market and making rural communities more accessible.
- Improving access to services such as health and education.

30.	We expect the 2.2 million work days of work generated by this project to be particularly timely. The project will focus on trying to ensure that as many of these as possible are available to local people (particularly women) as possible. This will not only have the benefit of creating a pool of local people with experience of road improvement work who will be able to work on maintenance, and to increase local ownership of road improvements (if they physically did the work themselves), but will also act as a sizeable cash for work programme. Malawi is currently undergoing a period of macroeconomic stabilisation involving increasing prices and a depreciating currency which, combined with a poor harvest, has left large numbers of poor Malawians struggling. A range of social protection programmes (including cash for work) are being developed or expanded to meet this need, but this programme will generate similar benefits.

31.	Finally, in the longer term we expect this programme to have macroeconomic benefits for Malawi. The lower maintenance costs caused by the improved roads and improved maintenance regimes will reduce the pressure on Malawi’s tight road maintenance budget. And increased connectivity will help the improvements in agricultural productivity and diversification that are crucial for Malawi’s future food security and macroeconomic stability. Closely integrated into the ASWAp as this programme is, we expect it to increase the effectiveness of all efforts to boost agricultural productivity by easing a key constraint – access to inputs and markets. The success of these efforts to boost agricultural exports and reduce the vulnerability caused by the reliance on tobacco is fundamental to Malawi’s efforts to address its chronic current account deficit, and thus one of the root causes of macro instability.

Recommendation

32.	Based on the analysis above, we recommend Option 2. The CBA estimates that it will generate more benefits than Option 1, principally because it operates in different districts from the WB’s programme, and will not therefore be ‘crowded out’ from some of the highest priority roads. This also has the advantage of a more equal spread of the benefits around Malawi’s rural areas rather than focusing all of our combined efforts on only 5 of Malawi’s 28 districts. Option 2 is also preferable to Option 0 since the benefits are expected to substantially exceed the costs, despite the fact that we have only valued some of the likely benefits.

Sensitivity analysis

33.	The most risky variable in this analysis is the cost of construction, given Malawi’s macroeconomic uncertainty and the impact that could have on costs. The recent depreciation is likely to push down overall costs (since some of the construction costs will be in kwacha, and our funding is in pounds), but in any case, the costs will need to increase by more than 55% before the NPV of Option 2 becomes negative, and this project stops representing good value for money.

Strength of the evidence base

34.	There is strong evidence on the links between better road connectivity and agricultural productivity and output. This includes econometric analysis of the impact of roads (and other types of spending) on agricultural output, incomes, and poverty in China and India[16], and a study of household data from Madagascar and Ethiopia which found that remoteness and poor road connectivity negatively affects agricultural productivity and incomes at the household level[17][18]. A World Bank study of the relationship between transport infrastructure in Sub-Saharan Africa using data from geographical information systems[19] found that agricultural production is highly correlated with proximity (as measured by travel time) to urban markets. Likewise, adoption of high-productive/high input technology is negatively correlated with travel time to urban markets. Total crop production relative to potential production is 45% for areas within 4 hours travel time from a city of 100,000 people, compared to just 5% for areas more than 8 hours away. A 1% reduction in travel time to the nearest city of 100,000 of more people increases low-input crop production by 2.9%. And, as noted above, Dercon (2009) found in villages studied in Ethiopia that access to an all-weather road caused the rate of consumption growth to increase by 16%, and poverty to fall by 6.9%. There is also evidence to suggest that lack of competition (caused in part by the difficulty of accessing rural areas) increase transport costs in Malawi[20].
[16] ‘Fan, S, and Peter Hazell, 2001. ‘Returns to Public Investments in the Less-Favoured Areas of India and China’ American Journal of Agricultural Economics 83 (5): 1217-22
[17] Stifel, D, and Minten B, 2008, ‘Isolation and Agricultural productivity’, Agricultural Economics 39 (1): 1-15
[18] Chamberlain J et al, 2007, ‘An Atlas of the Ethiopian Rural Economy: Expanding the Range of Available Information for Development Planning.’ Information Development 23 (2-3): 181-92
[19] Dorosh, P et al, ‘Crop Production and Road Connectivity in Sub-Saharan Africa – A Spatial Analysis’, WB Policy Research Working Paper 5385, July 2010
[20] Lall, S., Wang H., and Munthali T., ‘Explaining high transport costs within Malawi – bad roads or lack of tracking competition?’, World Bank working paper 5133

35.	The evidence on the impact of roughness on vehicle operating costs that underpin the World Bank’s Roads Economic Decision model are also strong, and given the homogeneity of roads of vehicles globally, it is reasonable to assume that these figures are applicable to Malawi. The IHS3 data and road surveys on which the cost benefit appraisal are based are also relatively recent and of reasonable quality. Given the above, we believe that the evidence for Options 1 and 2 are strong, as set out in the table below.

Option	Evidence rating
1	-
2	Strong
3	Strong

# 3.5 Environmental assurance

36.	RRIP involves rehabilitation, spot improvement, low-volume sealing and maintenance of sections of the existing rural roads network. Since the RRIP is a WB-led programme, the WB’s environmental safeguards and rules will apply. The Bank safeguards policy OP 4.12 on Involuntary Resettlement is triggered. It is anticipated that this resettlement will primarily involve limited land-take stripping of vegetation, soil disturbance and creation of quarry sites and burrow pits along the roads. The main risks of the programme are climate change induced high intensity rainfall washing away the roads and increased CO2emissions from the road works machinery and increased traffic thereafter. As the exact locations of the roads to be improved are not known at this time, the project, in February2012, published a Resettlement Policy Framework (RPF)[21] to ensure effective preparation and implementation of the asset acquisition, resettlement and compensation process for the ASWAp-SP[22].
[21] Ministry of Agriculture and Food Security, Agricultural Sector Wide Approach – Support Project, Resettlement Policy Framework, Draft Report, January 2012
[22] Based on the experiences of the World Bank funded ISP project, most road improvements are expected to follow the existing road alignment and the issue of compensation will therefore be very minimal. In case occasional displacement occurs, the District Lands Officer under the Ministry of Lands Officers will assess the structures, land and crops and evaluate the same based on the standard compensation cost framework provided by the Ministry of Lands.

37.	The likely relationship between each option and climate change and the environment are categorized below using the following ratings: A - High potential risk,B - Medium / manageable potential risk, or C - Low or no potential risk. Based on the observations above, the options are classified as type B (medium level risk that is manageable). More information on the risks, impacts and opportunities is provided in the programme’s Climate & Environment Assurance Note on Quest Number 3683264.

Option	Climate change, environment risks and impact rating	Possible impact on project results
0	No DFID intervention, therefore no impact.	Climate change may have an impact on the transitability levels of the feeder road network due to more than average rains and storms. This can be mitigated through: i) hydraulic design that uses recent rainfall data and higher than normal flood return periods (e.g. instead of 1:10 years, use 1:20 or 25 years), ii) using labour based technologies well suited to provide adequate erosion protection and iii) build low level structures designed to withstand occasional overtopping.
1	The road works will involve limited land take, stripping of vegetation, soil disturbance and creation of quarry sites and burrow pits. The risks and impact on the environment has therefore been rated as medium and manageable and is therefore categorized as (B) for both options 1 and 2.
2

# 3.6 Impact on Women and Girls

38.	A study[23] carried out in 2005 concerning gender and rural transport in Ntchisi district reveals that women own fewer (and have limited access to) Intermediate Means of Transport[24] in the community. Yet, they carry the greatest burden of domestic activities; they assist with field activities in addition to domestic chores such as taking care of the family, collecting water and firewood. The women also take over a large part of harvest tasks and other post-harvest chores such as bringing maize to the grinding mill or the market. The most common mode of travel and transport is walking and head loading. As such, women bear the greatest burden of rural travel and transport in the village.
[23] Source: Rural Accessibility and Mobility in Ntchisi District, Malawi, 2005
[24] Intermediate Means of Transport (IMT) are affordable forms of transport between walking (head loading and conventional motorized transport (vehicles, buses, motorcycles) and typically constitute of (load carrying) bicycles, hand carts, and animal drawn carts.

39.	It is anticipated that support to community roads will cause a general shift in transport patterns (‘modal split’) from head loading to intermediate means of transport and subsequently to motorised forms of transport. This will reduce the travel and transport burden on women and girls especially if road interventions focus on improving roads along the initial stages of the value chain (district and community roads) closer to the farms, and allow them to use this time more productively elsewhere (school, farming etc).Women are also expected to benefit from the programme through employment in maintenance clubs. For instance, in Salima District[25] (RRIP beneficiary), maintenance clubs comprised 40: 60 ratio of men to women in some cases. Qualitative information on how the road improvements impact on women will be collected through community –based monitoring.
[25] Information gathered during DFID Malawi’s visit to Salima District Assembly in May 2012 to learn involvement of district assemblies’ including communities in roads works
# 3.7 Sustainability

40.	Under RED it is assumed that road condition remains stable during the project life. In reality this may be an unrealistic expectation in Malawi where maintenance budgets are under-resourced[26], though to compensate for this benefits are only included in the CBA for the first 5 years after project completion. Current practice puts unpaved roads under routine maintenance and an occasional grading and reshaping passage (every 3 – 4 years), which is not sufficient to keep the road in good condition. It is estimated that current maintenance is carried out at levels of less than 50% of the requirement. The project has been designed to mitigate this risk however. Works will favour road spot improvement works, which require less resources for future maintenance, and it is anticipated that the improved roads will require less maintenance than existing roads, enabling the existing roads maintenance budget to fund more effective maintenance of the network.
[26] 5-year strategic and Business Plan, Road Authority

# 3.8 Value for Money summary

41.	Based on the results of the economic analysis, option 2 with an expansion to a maximum of 5 additional districts is our recommendation. This will bring the total number of roads to be improved to 800kilometres in a maximum of 10 districts (an average of about 80 km per district); of this 380 km are attributed to DFID funding. The cost-benefit analysis finds that this option has a positive net present value of £6.7m, which makes it preferable to both Option 1, and the ‘do nothing’ Option 0. These benefits are mostly driven by the reduced vehicle operating costs caused by the expected improvements in the road surface. But we believe that we have been conservative in estimating the benefits. There are a number of benefits that we have not included in this calculation, and despite strong evidence that improved road connectivity has improved agricultural productivity in other countries, we have only included relatively small benefits from this. In part this is because rural incomes are currently so low in Malawi that very large gains are required to generate significant benefits in £ terms.

42.	The indicators, targets and means of verification are subsequently discussed at 3 levels: impact, outcome and output level. Impact level indicators include the increase in the proportion of smallholder households with improved access to markets. This will be verified through surveys to be done by the Roads Authority. Outcome indicators include percentage of feeder road network in transitable condition in each of the targeted districts. Output indicators include the kilometres of unpaved rural feeder roads rehabilitated and upgraded. More indicators, targets and means of verification, are set out in the programme log frame. The cost driver in this programme that carries the greatest risk of being more than expected are the construction costs, particularly the purchase of imported goods such as cement, given Malawi’s landlocked geography and recently depreciating currency. However this risk is mitigated by the fact that our funding is provided in sterling, the kwacha value of which will therefore increase with any further depreciation.

4	Commercial case
# 4.1 Introduction

43.	The proposed DFID contribution of £13.17 million to RRIP will be channeled through the WB MDTF that is being set up to fund activities under the ASWAp.This commercial case will therefore refer to indirect procurement.

4.2	Why DFID is funding the RRIP through World Bank led MDTF

44.	The March 2011 Multilateral Aid Review by DFID rated the World Bank as “Strong” in as far as its contribution to UK development objectives is concerned; as “Satisfactory” in as far as its organizational strength is concerned; and as “Likely” in as far as its likelihood of positive change is concerned.

45.	There are clear advantages to delivering this programme through the WB rather than another organization, or on our own:
- There are no other donors carrying out rural roads improvements on this scale in Malawi in the areas in which we wanted to work, that we could partner with.
- The World Bank have a stronger background and comparative advantage in delivering programmes in this sector corporately than DFID, and has roads expertise in its Malawi office.
- The World Bank plays a leading role in the Agriculture SWAp, and manages the ASWAp support project in which this project will be located. This means that this project will be fully integrated into donor efforts to enhance agricultural commercialisation, enabling it to take advantage of synergies with other ASWAp initiatives. In addition, the WB are considering a follow-on rural roads project starting in 2015 – delivering this project through the WB increases the likelihood of that project being integrated with this one.
- There are cost savings in terms of TA and training being delivered that supports the physical works being funded by both WB and DFID.

We believe that these factors mean that there is a clear VfM case for delivering this programme through the WB rather than bilaterally.

4.3	Value for money through procurement

46.	In accordance with the institutional framework for the sector, the Procurement Section of the RA will be responsible for coordinating the procurement activities for the project that will be carried out by the Maintenance Department of the Head Office and the 3 Regional Offices in Mzuzu, Lilongwe and Blantyre.

47.	A capacity assessment was undertaken by the World Bank of the Roads Authority (RA), which will procure and manage contracts for the RRIP. Local contractors will implement the road works. Contracts for maintenance works are to be carried out by maintenance clubs. These works are financed by the GoM through the District Councils who will award the work directly to the maintenance clubs. The roads maintenance clubs are led by committees. These villagers are trained through their involvement in the road construction, rehabilitation and repairs. These are supervised by District Public Works officers and are paid for every roads repairs work. Timely payment of their dues is essential.
# 4.4 Justification of the choice of the Roads Authority (RA) as Implementing Agency

48.	The RA is responsible for managing the road improvements under the project and supporting the District Councils in the management of the District and Community Roads. A procurement assessment was carried out by WB staff in December 2011 to assess whether the capacity of the RA would be sufficient to carry out the procurement for this programme. The assessment was meant to identify the gaps that could impede the execution of the project with a focus on the conditions surrounding the carrying out of procurement, and to determine the risks to the reputation of DFID and the WB as funders, and to assess which thresholds for different levels of WB involvement and monitoring of procurement would be crossed by the procurement under this programme.

49.	The Public Procurement Act, August 2003, governs public procurement in Malawi. The Act requires procurement regulations to provide, inter alia, thresholds for the use of various procurement methods, bidding and bid evaluation procedures and contract management. The Law further established the Office of Director of Public Procurement (ODPP) with oversight for public procurement. The ODPP became operational in 2005 with the appointment of the Director and other substantive officers. The GoM also established Internal Procurement Committees (IPCs) and Specialized Procurement Units (SPUs) in all Procuring Entities including the RA as the responsible bodies for procurement. Procurement Regulations and Desk Instructions have been distributed to all procuring entities. The ODPP has also established a dedicated website for sharing of information, placing of adverts and notification of awards to the general public.

50.	RA has an IPC, which is chaired by an appointee of the Chief Executive Officer (CEO). The current arrangements are that the Director of Finance and Administration is the Chairperson. The IPC has the responsibility for approving the award of contracts. Other members of the IPC include Directors of Construction, Maintenance, Planning and Design. The Procurement Specialist is the Secretary.

51.	The assessment of the current staff in terms of procurement requirements for the RRIP is that the current staff has adequate knowledge of World Bank procurement procedures. However, the existing procurement staff should have their skills improved through attending short courses on procurement organised by training institutions within the region. There is also a need to include in the training programme staff from the Maintenance Department - and the Regional Offices working under it - which will be closely associated with the implementation of the RRIP.

52.	The overall capacity of RA to carry out procurement under RRIPhas been assessed by the World Bank as Moderate and the risk as Medium. This is based on the fact that the RA has:

- A procurement system in place and operational which separates execution and approval;
- Procurement staff is knowledgeable about World Bank procedures;
- Standard bidding documents were reviewed and found acceptable by the World Bank.
# 4.5 Findings from other sources

53.	The RFA commissions an annual third party technical and procurement audit[27], which has been consulted for this assessment. The general impression from the 2009/2010 Independent Audit Reports commissioned by the RFA is positive showing sufficient professional capacity for implementing the procurement function. The issue of limited staff resources and high number of procurement processes may well be at the root of the majority of reported weaknesses and irregularities.
[27] Technical and procurement audit of Government of Malawi funded road projects for the financial year 2009/2010, Final Procurement Audit Reports, Aurecon, May 2011.

54.	The main issues identified in the 2009/2010 technical audit on a sample basis of 20 contracts (excluding smaller recurrent contracts such as grading, patching and routine maintenance) carried out by the auditing firm Aurecon are set out below. The frequency of these issues are set out in brackets:

- Delayed submission of designs and drawings (frequent) and inadequate (one occasion);
- File management not always well organized (frequent);
- Uniformity is lacking in site management systems and project filing procedures (frequent);
- Delayed payments due to unavailability of funds (frequent);
- Delayed proclaiming of road reserve and/or compensation of land (frequent);
- Shortage of fuel (all);
- Responsibility for finding suitable material for road construction left with Contractor (all);
- Environmental management does not seem to be high on the agenda (frequent);
- The issue of site safety appears to be generally handled in a careless manner (frequent)

55.	The main issues highlighted from the 2009/2010 procurement audit on a sample basis of 20 contracts including the smaller recurrent contracts such as grading, patching and routine maintenance (with the frequency of events set out in brackets):

- Contract documents not always complete (frequent);
- Conflicting information on requirement for pre-bid meeting (1);
- Recording inconsistencies of bid submission versus bid opening (1);
- Bid period inferior to minimum required 30 days (15);
- Use of Project Review and Evaluation Technique (PERT)[28](frequent);
  [28] Project Review and Evaluation Technique (disqualification of bidders if financial offer differs in more than 15% compared with the engineers estimate.
- Filling in of rates on Bill of Quantities, where the bidder did not specify rates (2);
- Scope of works changed after the bid period closed (1);
- Notification of bidders of any arithmetic corrections made to their bids (frequent);
- Pre-contract negotiation meeting held after contract award notice being issued (7);
- No pre-contract negotiation meeting held (1);
- Format or structure of documents not always complying with prescriptions of desk instructions to Public Procurement (frequent).

56.	The European Union carried out 2 independent audits in March 2010 covering:

1. Examination of procurement of road projects, covering the period from 01/07/2007 to 30/06/2009;
2. Examination of public arrears generated from contracts in the road sector, covering the period from 01/07/2007 to 30/06/2009.

57.	Under i) the auditors examined 8 large contracts with values in excess of £6 million and another 109 small maintenance contracts with values ranging between £3,000 (e.g. grass cutting) and £320,000 (road rehabilitation and spot improvement contracts), the latter are similar to the contract size foreseen under RRIP. The findings were generally similar to those already mentioned above. On the overall assessment whether procurement of the works contracts was carried out in accordance with national procurement system in Malawi, ensuring transparency in the procurement process, the conclusion was that: “out of the 8 development projects examined various issues and breaches were noted on all but one development project”. “Small-scale maintenance contracts however(of the kind envisioned under RRIP) were considerably less susceptible to errors, with only a small minority of maintenance contracts attracting findings concerning compliance with national procurement systems.” Concerning the latter, it was noted that inadequate filing and archiving persists and that several maintenance contracts were not awarded to the lowest compliant bidder. Other important findings are “signing contract whilst adequate funding arrangements are not in place” and “poor reporting of contractual liabilities” making it difficult if not impossible to assess financial commitments.

58.	Under ii), the Audit objective was to assess the causes of built up arrears under GoM funded contracts in preparation of the EC’s intended sector budget support. The assessment included GoM co-funded development projects and road maintenance contracts (which are funded through the RFA). The conclusion was that: “by the beginning of 2010 the identified cost overruns / additional funds needed for development projects amount to approximately 17.8 billion kwacha which was at that time approximately equal to £64 million” whilst for maintenance contracts “liabilities as at 31 July 2009 amounted to K1.1 billion and that all balances relate to current contracts. All major balances for maintenance contracts as at 31 July 2009 have been paid subsequent to financial year-end and there are no cost overruns identified. As such, there are no contractors’ arrears arising on maintenance contracts other than those that would normally be expected when signing and paying for road maintenance works.

59.	In preparation of the support to RRIP, DFID also carried out an updated Roads Fiduciary Risk Assessment (FRA) in November 2011[29] with information that was largely drawn from earlier work done in 2009 in preparation for the Malawi Unpaved Roads Programme (MURP). It should be noted that this assessment had a limited scope and did not cover the requirements of a full sector FRA. The FRA distinguishes between financial and procurement related issues at both national and sector level. This section will only cover the procurement related issues at sector level. The financial issues are discussed in the Financial Case.
[29] Government of Malawi, Roads Fiduciary Risk Assessment, Main Risks in the Roads Sector, Prepared by REPIM, On behalf of DFID Malawi, November 2011

60.	The FRA is presented in more detail in Annex 2 (Quest No.3851045) together with a response on how the procurement related concerns have been addressed in this business case through proper risk mitigation measures. In summary the main concerns raised in the FRA follow those already mentioned in the audit reports by RFA and EC.

61.	The general conclusion emerging from the audit reports and assessments confirm that:
- The procurement system, procedures and documents in itself are sound but RA implementation capacity is weak which is due to a combination of factors; the number of procurement processes being handled, insufficient staff and / or inexperienced staff, insufficient procurement oversight to detect and correct errors and irregularities;
- Whilst major development contracts - particularly those (co)funded by the GoM and not subject to international review and procurement procedures - are prone to direct political influence thereby undermining transparency, value for money principles, and resulting in large cost overruns, the relatively small and medium sized maintenance contracts (as foreseen under RRIP) and for which funding passes through the RFA are rarely prone to such issues.
# 4.6 Value for money measures and risk mitigation in procurement

62.	The RRIP procurement risk mitigation measures comprise the following instruments:

- Strengthening internal procurement oversight and control in the RA;
- Mandatory use of World Bank-approved documents and procedures, if any contracts exceed WB thresholds;
- Strengthening the procurement implementation capacity of the RA;
- Monitoring, supervision and post review procedures by World Bank staff or Independent Auditors

These risk mitigation measures are briefly discussed below.

63.	Strengtheningoversight. The IPC in the RA will continue (internal) oversight functions under the programme. The members of the IPC will benefit from training courses to increase their capacity and skills in procurement oversight. Contracts that exceed the WB thresholds set out in the table below will be required to use International Competitive Bidding (ICB). In practice this requirement is unlikely to be triggered for goods contracts, since we expect all contract values to be less than these levels, but it is likely that consultancy contracts will be above these limits, and therefore will be tendered using ICB. Therefore, we expect all goods contracts to use National Competitive Bidding (NCB). This will be done using National Standard Bidding Documents and in accordance with the Malawi Public Procurement Act. The procurement procedure to be followed for NCB shall be open tendering as set forth in the Public Procurement Act, 2003, in line with World Bank Procurement Guidelines.

Type of contract	Threshold IDA prior review
Goods	US$ 500,000 (£320,000) equivalent or more
Works	US$ 3,000,000 (£1,900,000) equivalent or more
Consultants (firms) / Consultants (individuals)	US$ 200,000 (£128,000) equivalent or more / US$ 100,000 (£64,000) equivalent or more

64.	Mandatorypreparation of a procurement plan reflecting the Annual Work Plan (AWP) of RRIP. This should include relevant information on all goods, works and consulting services to be procured, and their estimated cost; procurement or selection method as well as timing of the procurement/selection process. The overall procurement plan will be updated on an annual basis in conjunction with the preparation of the Annual Work Program and Budget in accordance with the project requirements.

65.	Priorreview of contracts is requiredfor contracts with estimated values that exceed the thresholds for ICB set out above (though as noted before, we do not expect this to happen in practice). Irrespective of these prior review thresholds, the first contracts for goods, works and consulting services will be subject to prior review. Since the ODPP has already prepared Standard Bidding Documents for procurement of works and goods under NCB, the World Bank’s Standard Bid Evaluation forms would also be used for NCB contracts with necessary modifications.

66.	Strengthening procurement implementation capacity. As a mitigating factor, procurement staff should attend refresher courses within the Region to update knowledge in the use of World Bank’s procurement guidelines, RFPs (Request for Proposals) and bidding documents and be trained in the use of Bank systems such as PROCYS and Client Connection. A training plan is to be prepared by the Roads Authority and agreed with IDA by the effectiveness date. The RA has produced an initial procurement plan covering the first 18 months of activities to be financed by IDA: this will be updated regularly and will include MDTF-funded contracts.

67.	The identified weaknesses and higher risks identified in procurement implementation will also be mitigated by strengthening the implementation capacity through recruitment of 4 Project Engineers and Technical Assistance, including a fulltime rural road engineer to support RA with the planning and design of road works and a part-time contract and procurement specialist to support RA with the procurement and contracting of goods, services and works.

68.	Post-review procedures. Contracts, which are not subject to prior review, will be selectively post-reviewed by IDA or on its behalf by an independent Procurement Auditor during project implementation and will be governed by the procedures set forth in paragraph 4 of Appendix I to the relevant World Bank Procurement Guidelines.

69.	It is also envisaged that there will be sample-based annual procurement post reviews to: (i) verify that the procurement and contracting procedures and processes followed by the project are in accordance with the agreed procedure manual; (ii) verify technical compliance, physical completion and price competitiveness of each contract in the selected representative sample; (iii) review and comment on contract administration and management issues as dealt with by executing agencies; (iv) review capacity of executing agencies in handling procurement efficiently; and (v) identify improvements in the procurement process in the light of any identified deficiencies. In case such reviews come across a serious breach, mis-procurement can be pronounced in accordance with World Bank guidelines.
# 4.7 Summary of commercial case

70.	The overall capacity of RA to carry out procurement for small to medium scale works is assessed by the WB as moderate and the risk medium on average but on some aspects it is rated as high. Generally sound procurement systems and processes are in place based on the regulations and standard GoM bidding documents from the ODPP, which were reviewed and found acceptable by the World Bank. Procurement staff in the RA are experienced and already knowledgeable in World Bank procedures and standard GoM bidding documents from the ODPP.The major risk in procurement is related to the large number of small-scale contracts that are tendered and procured by the RA and the limited staff resources, which often result in poor procurement management practices (poor record keeping, insufficient post qualification of bidders and time overrun in the procurement process). Overall the procurement implementation capacity is low.

71.	A table summarising the main fiduciary risks around procurement, and proposed risk mitigation measures, can be found at Quest No. 3851134. The identified risks will be mitigated by strengthening procurement oversight, by mandatory use of World Bank’s procurement documents and procedures (if there are any contracts above the defined threshold), contract prior review (above the defined threshold), strengthening the planning, design and procurement capacity within the RA through the provision of Project Engineers /TA and post review and supervision by the Bank team.
5	Financial case
# 5.1 Introduction

72.	This section covers the cost breakdown of the RRIP including the DFID contribution. The financial case further covers sources of funding, funding mechanism, the main results of a Fiduciary Risk Assessment (FRA) of the Road Fund Administration and proposed financial management arrangements.
# 5.2 Cost breakdown by activity and funder

73.	The summary costs break down by activity and funder is presented in the table below. It should be noted that this budget is indicative. The main costs in this programme are for the road works themselves, and we will not know the actual costs for these works until the tendering process is complete.

RRIP: Summary of Component Costs

Activity	Values in Million £					% Financed by
	Total Activity Cost	IDA	Multi-Donor-Trust Fund		GoM	World Bank	DFID	GoM
			DFID	Others
A. Unpaved Road Improvement	20.3	11.7	8.6	-	-	58%	42%	-
A1 Rehabilitation	6.3	3.2	3.1	-	-	52%	48%	-
A2 Spot Improvements	4.1	2.1	2.0	-	-	50%	50%	-
A3 Upgrading to Paved	9.5	6.4	3.1	-	-	67%	33%	-
A4 Area Based Maintenance Pilot Projects	0.4	-	0.4	-	-	-	100%	-
B. Project Implementation	4.1	1.9	2.2	-	-	46%	54%	-
B1 Formal training of stakeholders	0.7	-	0.7	-	-	-	100%	-
B2 Design and Supervision Consultants	1.9	1.9	-	-	-	100%	-	-
B3 Technical Assistance for Road Authority	1.5	-	1.5	-	-	-	100%	-
C. Maintenance Works & Resettlement Compensation	0.6	-	-	-	0.6	-	-	100%
C1 Road Maintenance	0.4	-	-	-	0.4	-	-	100%
C2 Resettlement Costs	0.2	-	-	-	0.2	-	-	100%
Total – Activities (needs)	25	13.6	10.8	-	0.6	54%	43%	2%
Physical and Price Contingencies (15%)	4.3	2.4	1.6	-	0.3	56%	37%	7%
Sub-total	29.4	16	12.4	-	1.0	54%	42%	4%
WB administration fee			0.65
Third party audits			0.1				100%
Total	30.1	16	13.171		1	53%	44%	3%

74.	Out of the total budget of £29.7 Million, IDA will finance £16 Million (53%), DFID £13.17 Million (41%) and the GoM £1.0 Million (4%). The transaction cost (overhead) on road investments is around 20% (the cost of project implementation – £4.1 million - as a percentage of the cost for unpaved road improvements of £20.6 million), which is in line with international practice (also 20%). In addition to these costs, DFID will pay the WB administration fees of $35,000 plus 5%, equivalent to £648,000, and has included a budget line of £90,000 in case we need to pay for any third party audits.
# 5.3 Funding mechanism

75.	Responsibilityfor the financial management of expenditure will rest with the RFA, an executive agency overseen by the Ministry of Finance. The obligations of the parties (DFID and other donors, the Bank and GoM) in the management of the Multi-Donor Trust Fund (MDTF) will be set out in two legal agreements: (a) the Administration Agreement signed by DFID and the World Bank, and (b) the Grant Agreement signed by the World Bank and GoM (the recipient):

The Multi-Donor Trust Fund.This MDTF will be set up to fund a number of programmes within the ASWAp. The World Bank is the trust fund administrator. A Trust Fund Management Committee (TFMC), the main oversight body for the trust fund, will be established to monitor the operation and effectiveness of the MDTF. DFID will be a member of the TFMC. The main functions of the TFMC will be to: (a) review and monitor the implementation of the MDTF in line with GoM's overall ASWAp; (b) review and approve Annual Work Plan Budgets submitted for funding out of the MDTF; (c) monitor progress on the annual MDTF work program/plan, budgetary allocation/funding commitments and disbursements and any other adjustments that may be necessary.

The Administration Agreement specifies the trust fund’s purposes and scope of activities to be financed. It also defines the nature of the World Bank‘s relationship with DFID and spells out the arrangements governing the use of funds, progress and financial reporting, fee arrangements, auditing, disclosure of information, among others. An agreed template and/or standard terms are used to prepare the agreement. In line with DFID guidelines, the agreement is not legally binding.

The Grant Agreement spells out the Grant related responsibilities of the World Bank and GoM in executing the trust fund. It includes, among other things, provisions on: (i) the objectives of the trust fund activities; (ii) activities eligible for funding (iii) the recipient‘s obligations in respect of procurement, contract administration, financial management and auditing, and progress reporting; and (iv) disclosure of information. A Disbursement Letter sets out the disbursement arrangements that apply.

76.	Banking arrangements: The RFA will open US$ Designated Accounts at the Reserve Bank of Malawi for both the IDA loan and the MDTF grant. Subsequently, the RFA will also open a Malawi Kwacha Holding Account at the Reserve Bank of Malawi and an operating account with a commercial Bank acceptable to IDA. The flow of funds will be as presented in the figure below:

77.	Funds Flow Arrangements for the project are as follows:

- MTPW (RFA) will prepare a six-month cash flow forecast based on agreed work plans then submit a withdrawal application request to the World Bank (IDA and MDTF) through the Ministry of Finance. This forecast will include funds requirements for road component activities to be implemented by RA;
- The World Bank will process the withdrawal application and the amount for RRIP activities will be disbursed into the Designated Account under RFA subject to the submission of satisfactory financial reports;
- Ministry of Finance will transfer funds from the RFA Designated Account into the RFA Holding Account as and when required in local currency;
- Project expenditures can be paid from the Designated Account (US$) or the Project Account (MK).

The disbursement schedule by which DFID will pay the WB is still being discussed with the WB, and is subject to agreement on the contents of the Administration Agreement. The current proposal however is for DFID to disburse half yearly in advance to the WB. Half yearly disbursements are proposed to reduce transaction costs, and advance payments have been justified by the WB on the basis that the RFA need to be paid in advance. Contractors will need to be paid at least part of their fees in advance due to their limited access to finance, and the RFA do not have the funds available to pay for these activities. We are discussing the documentation that the WB will provide us in advance of each payment. These details will be included in the Administration Agreement.

78.	Disbursement methodsfor IDA and MDTF funding are as below. The IDA and MDTF Disbursement Letters will provide details about each of these disbursement arrangements:

- Special Commitments and Direct Payments: Special Commitments using irrevocable letters of credit may be used as well as direct payments to suppliers for works, goods and services based upon the borrower’s request;
- Advances: the project will also receive advances into the designated account based on forecasts. The World Bank will make the initial disbursement to the project after receiving a withdrawal application with a six months cash flow forecast. This withdrawal application should be prepared within one month after project effectiveness. Thereafter, the World Bank will disburse into the respective Designated Account based on quarterly Interim Financial Reports (IFRs), which would provide actual expenditure for the preceding quarter (3 months) and cash flow projections for the next 2 quarters (6 months). The IFR will be reviewed by the World Bank’s Financial Management Specialist and approved by the Task Team Leader before the request for disbursement is processed by the World Bank’s Loan Department.
- Reimbursements: funds can be paid into the beneficiaries’ bank account as a reimbursement for pre-financed expenses. These payments will also be reported in quarterly IFRs.

79.	One of the major risks identified in the RRIP is the shortage of foreign currency and imported materials such as fuel, bitumen, cement and steel. This has proven to substantially delay works and is a high risk for the contractors who operate in a volatile contracting environment[30].The World Bank is monitoring the supply situation with the RA, and appropriate mitigating measures will be adopted. As a minimum, contractors will be permitted to request partial payment of invoices in a foreign currency.
[30] Although recent developments in Malawi may point towards a better economic outlook and higher influx of foreign currencies, which could (partially) solve this problem.
# 5.4 Fiduciary risk assessment by the World Bank

80.	A financial management assessment of the RFA (which will manage the funds under the component to be implemented by the Roads Authority) was carried out. The objective of the assessment was to determine:
- Whether the entity has adequate Financial Management (FM) arrangements in place to ensure the funds will be used for the purposes intended in an efficient and economical manner and the entity is capable of correctly and completely recording all transactions and balances related to the Project;
- The Project’s financial reports will be prepared in an accurate, reliable and timely manner;
- The entity’s assets will be safely guarded; and
- The Project will be subjected to auditing arrangements acceptable to the World Bank.

The assessment complied with the Financial Management Manual for World Bank-Financed Investment Operations that became effective on March 1, 2010 and World Bank’s Financial Management Assessment and Risk Rating Principles.

81.	At the RFA, Financial Management systems are generally in place except that the entity does not have experience in managing a World Bank funded project. As a result of this constraint, an effectiveness condition was introduced for the IDA financing that RFA FM staff should be trained in FM and Disbursement procedures for World Bank funded projects. The World Bank and RFAhave agreed on the format and content of Interim Financial Report.

82.	The Financial Management assessment further concluded that the RFA’s financial management arrangements meet the World Bank’s minimum requirements. With the implementation of the financial management action plan, the financial management arrangements for the project will be further strengthened. The residual risk rating for RFA is therefore rated as Moderate.
# 5.5 DFID Fiduciary Risk Assessment

83.	In preparation of the support to RRIP, DFID also carried out an updated Roads Fiduciary Risk Assessment (FRA) in November 2011. This section will only cover the financial related issues at both national and sector level. The procurement issues were discussed in the Commercial Case.

84.	The FRA is presented in more detail in Annex 2 (Quest No.3851045) together with a response on how the fiduciary risk (concerns) has been addressed in this business case through proper risk mitigation measures. In summary the main concerns raised by DFID follow those mentioned in the audit reports of the EC. At national level these concerns are: low budget credibility (contract cost overrun and build-up of arrears), weak policy based budgeting, lack of internal control, substandard quality of financial reporting and insufficient management follow up on the outcome of audit reports. At sector level - other than procurement related issues and build-up of arrears, concerns raised are related to the implementation capacity of RFA[31] and RA in relation to the additional work under RRIP and the fact that external auditing reports over the last 2 years have not been signed off by the Board of the RFA[32].
[31] Reportedly implementation capacity at RFA is sufficient and the additional work under ASWAp-SP would not require the recruitment of additional accountants.
[32] The RFA had been without a Board since June 2010, but a Board was appointed in November 2012

85.	The fiduciary risk mitigation under RRIP will include:

- Ring-fencing the RRIP from the overall government budget by virtue of using the RFA disbursement mechanism;
- Improvement of the Integrated Financial Management Information System (IFMIS) and Financial reporting by providing support to the Public Finance and Economic Management Reform Program (funded by DFID and other donors through a WB Trust Fund).
- Using the Sector Working Group (that Government and partners have established for the transport sector which is operating successfully) to monitor sector performance and progress on the concerns raised, in particular the build-up of arrears;
- Strengthening the implementation capacity of RA through Project Engineers, TA, road design and supervision consultants;
- Monitoring the implementation of audit report recommendations during project implementation by the World Bank’s supervision team. Failure to comply with recommendations related to major fiduciary issues may result in disbursements being withheld;
- Eligible expenditures under the project will be defined in the annual work plan and budgets, and in the annual performance agreements between the RFA and RA.
# 5.6 Financial management arrangements and audits

86.	The RFA Finance Department, through the Senior Accountant, will be responsible for the financial management and reporting for the road component of the project, in line with the new Public Finance Management Act (PFMA).

87.	Budgetingarrangements:RFA’S budgeting process is deemed by the WB to be adequate. The budgeting process will be informed by the project’s annual work plans that will be agreed between the Bank and the project. The budget will be incorporated into the Sun accounting package, which RFA uses for budgeting and accounting. The Road Authority does the costing and budget preparation for road construction, maintenance and upgrading.

88.	Accounting arrangements: The RFA will use the Sun system for project operations. The system has a chart of accounts capable of capturing project components and disbursement categories. The staffing is adequate with three qualified staff. The procedures and policies are documented in an accounting manual. While procurement and the certification of invoices are done by the RA, the accounting work relating to the recording and payment of invoices is done by the RFA. As stated under the flow of funds above, funds for roads are held by the RFA who must therefore account for their utilization.

89.	Internal control and internal auditing arrangements: The RFA has an internal audit department that is properly staffed consisting of both accounting and technical personnel. The Internal Audit Department reports to a committee of the Board of RFA. Policies, procedures and internal controls are set out in the accounting manual.

90.	External Auditing Arrangements: considering the aforementioned fiduciary risks presented for the road sector, provisions will be made in the MDTF for an external audit to be carried out by the NAO which would include the RRIP. The audited financial statements will be submitted to the World Bank within 6 months after the end of the fiscal year along with the management letter. Terms of reference for the audit will be agreed with RFA. In addition to annual audits carried out by the NAO, the RA and RFA also carry out external audits of their activities by private audit firms. This is also a condition of the EU budget support to the roads sector, which will last until 2014. If the NAO audits are not satisfactory or the RFA and RA are discontinued after 2014, DFID is planning for independent technical, procurement and financial external audits of the programme. It is estimated that this exercise would cost DFID approximately £30,000 per year. A total of £90,000 has been set aside for the whole programme. DFID Malawi is still discussing with the World Bank on the modalities and management of these audits. We hope to be able to include this arrangement within our Administrative Agreement with the WB. If this proves not to be possible we will discuss with the RFAan alternative arrangement such as an exchange of letters with them directly to ensure that we are able to do these audits if necessary.

91.	Financial Reporting Arrangement. The RFA will produce quarterly unaudited Interim Financial Reports (IFRs) for the designated accounts and the related project accounts. The IFRs are to be produced on a quarterly basis and submitted to the World Bank within 45 days after the end of the calendar quarterly period.

92.	RFA will produce an IFR for RRIP activities, which will be consolidated with the IFR produced by MAFS. The reporting requirements will be incorporated into RFA’s accounting package to enable automatic generation of the IFRs.

93.	The project will also prepare the project’s annual audited accounts/financial statements, which must be submitted to the World Bank within 6 months after the end of the accounting year i.e. not later than December 31. The project will prepare its accounts in accordance with International Public Sector Accounting Standards. The accounts/financial statements will comprise of:

- A Statement of Sources and Uses of Funds/Cash Receipts and Payments, which recognizes all cash receipts, cash payments and cash balances controlled by the entity; and separately identifies payments by third parties on behalf of the entity;
- The Accounting Policies Adopted and Explanatory Notes. The explanatory notes should be presented in a systematic manner with items on the Statement of Cash Receipts and Payments being cross-referenced to any related information in the notes. Examples of this information include a summary of fixed assets by category of assets, and a summary of the IFR Withdrawal Schedule, listing individual withdrawal applications; and
- A Management Assertion that World Bank funds have been used in accordance with the intended purposes as specified in the relevant World Bank legal agreement.

# 5.7 Summary financial case
94.	The conclusion of the assessment is that the financial management arrangements meet the World Bank’s minimum requirements. The overall residual risk rating for RFA is Moderate. The project will have on-field supervision at least twice a year and will be audited by an independent external auditor, in addition to the NAO.

95.	The DFID Support budget summary is tabulated below:-

DFID RRIP Budget Lines in Pounds

Budget Line	2013	2014	2015	Total
Rural Roads Improvements	3,225,000	4,100,000	1,300,000	8,625,000
Training	400,637	208,331	64,102	673,070
MTPW	64,102	0	0	64,102
RA	64,102	32,051	0	96,153
RFA	64,102	0	0	64,102
Local Authorities	32,051	32,051	0	64,102
Local Contractors (+Maintenance Clubs)	128,204	96,153	32,051	256,408
Community Monitoring	32,051	32,051	32,051	96,153
NCIC	16,025	16,025	0	32,050
Technical Assistance	772,109	373,074	351,279	1,496,462
4 Project Engineers for RA	96,153	76,923	76,923	249,999
4 Vehicles for RA	230,769	0	0	230,769
5 sets of equipment for Project Engineers	8,012	0	0	8,012
Running Costs	144,229	96,153	96,153	336,535
Team Leader/Senior Rural Road Engineer	144,230	115,384	115,384	374,998
Maintenance Engineer	30,769	30,769	15,384	76,922
Procurement/Contracting Specialist	30,769	30,769	15,384	76,922
Other inputs	23,076	23,076	0	46,152
Baseline and Impact Studies	64,102	0	32,051	96,153
Contingency (15%)		816,340	816,340	1,632,680
WB administration fees	215,954	215,954	215,954	647,861
Third party audits	30,000	30,000	30,000	90,000
Total	4,643,700	5,743,698	2,777,674	13,165,072

# 6 Management case
# 6.1 Introduction

96.	The role of the Management Case is to set in place the arrangements necessary for the successful delivery of the RRIP and also take into account lessons learned from similar (road) infrastructure projects in Malawi.

97.	DFID will be a member of the Trust Fund Management Committee (TFMC), Sector Working Group and (if appropriate) Technical Working Groups. These groups will provide political and technical inputs to the Executive Management Committee of the ASWAp-SP under which the RRIP will be implemented. The main functions of the TFMC are to review and monitor the implementation of the MDTF, review and approve the Annual Work Plans and Budgets, and monitor progress on the annual MDTF work programme. The TFMC retains the right to withhold approval of some or all of the AWPB. In order to effectively play this role, project monitoring, and funds disbursement, DFID will provide 10% of A2 20% of and B1/2 time throughout the project life to participate in the various programme activities.

98.	Procedures to facilitate implementation of the RRIP will be developed. A tripartite project implementation agreement has been prepared between MTPW, RA and RFA (also a ‘condition of effectiveness’ for the World Bank) with clearly defined roles, responsibilities and accountabilities, and to establish working and reporting modalities between the concerned institutions.
# 6.2 Implementation arrangements for the RRIP under ASWAp-SP

Overall sector arrangement

99.	The implementation of the RRIP will be the responsibility of MTPW, who will be responsible for the provision of policy direction, coordination and liaison with MAFS, which will play an oversight function. The MTPW will become a member of the Executive Management Committee (EMC).

100.	The MTPW delegates its powers for the management of the road network to the Roads Authority (RA). The RA, which reports to the MTPW, is an autonomous public authority, established by the Roads Authority Act No. 3 in 2006, for the purpose of ensuring “that public roads are constructed, maintained or rehabilitated at all times”. On a daily basis, the implementation of the RRIP will be done through the Maintenance Department and its 3 regional offices. The Procurement Section of the RA will be responsible for coordinating the procurement activities for the project that will be carried out by the Maintenance Department.

101.	In a similar fashion, the Ministry of Finance delegates its powers to the Roads Fund Administration (RFA), which was set up under Roads Fund Administration Act No. 4 in 2006. The main responsibility of the RFA is to raise, administer and account for funds for the construction, maintenance and rehabilitation of Malawi’s public roads. On a daily basis, the RFA Finance Department, through the Senior Accountant, will be responsible for the financial management and reporting for the road component of the project, in line with the new Public Finance Management Act (PFMA).

Roles and responsibilities of stakeholders

102.	The implementation partners for the roads components are RA, RFA, District Councils and the Private Sector. Below follows an assessment of the stakeholders.

103.	The RA is responsible for managing the road improvements under the project and supporting theDistrict Councils in the management of the District and Community Roads. The RA will be responsible for:

- A leading role in the road selection in consultation with the selected DC’s and the MAFS;
- Procurement of services for environmental screening, the preparation of Resettlement Action Plans, road design and supervision and works contracts for rehabilitation, spot improvement and maintenance;
- Monitoring contract implementation and administration;
- Collecting data for the M&E framework of the project;
- Ensuring that policies and standards are complied with and best practices are followed.

104.	The role of the RFA is to administer and account for funds under the project available for road improvements. It is also responsible for monitoring the efficient use of funds disbursed to RA, both through internal auditing and by means of contacting external auditors on an annual basis. This separates the financial and implementation functions within the road sector and minimizes the possibility of conflict of interest.

105.	The District Councils (DC’s) are responsible for the management of district and the undesignated community roads. Despite the Decentralization Act, the DC’s are still not well equipped[33] to manage the roads under their jurisdiction and for this purpose they receive technical support from the RA. Although DC’s will have a decisive role to play in the selection of project interventions on district and community roads (through established participatory planning procedures), the actual works[34] will be designed, procured and managed by the RA.
[33] Although they have produced some positive results in the construction of local infrastructure under the WB supported Malawi Social Action Fund (MASAF) / Local Development Fund (LDF) and Irrigation Rural Livelihoods and Agricultural Development Project (IRLADP)
[34] With the exception of the maintenance contract funded by the GoM and implemented through the maintenance clubs

106.	The road works will be carried out (local contractors) and supervised (local consultants) by the private sector, and wherever practicable by labor-based methods to provide employment opportunities for local communities.

107.	According to the National Construction Industry Council (NCIC), there are currently over 1,800 contractors registered of which:

- More than 90% are small and medium sized contractors. However, the small and medium sized contractors only carry out 20% of the workload;
- About 600 contractors are registered with the Malawi Contractors Association and Trade Alliances (MACBATA), which is also represented in the board of the NCIC.

108.	RRIP will ideally target larger civil works contractors for the Low Volume Sealing Upgrading works (package value of £640,000 – £1.2 million), the medium scale contractors for Rehabilitation Works (package value of £190,000 – £640,000) and small contactors for Spot Improvement Works and Maintenance (package value of between £32,000 and £190,000).

109.	The main challenge for the small and medium sized contractors is weak financial standing, difficult access to finance and equipment in combination with weak management (project, contract and financial) skills. Access to equipment could be best solved through advance payments (in addition to the mobilization advance, the project could consider to pay an additional 10-15% for the purchase of equipment and conditioned by a bank guarantee).

Prioritization of intervention areas and roads

110.	For the RRIP, MAFS has determined that roads improvements will be carried out in the districts of Chikhwawa, Chitipa, Salima, Mwanza, Ntcheu, (using WB funding)and, it is proposed, Karonga, Kasungu, Machinga, Phalombe and Nsanje using DFID funding. Extension Planning Areas (EPA) within these districts have also been identified by MAFS and the selection of individual roads will then take place by the RA in consultation with MAFS and MLGRD. These districts have been identified by the MAFS according to the following criteria[35]:
[35] For instance, in Salima, roads selection process was done by the Assembly and Ministry of Agriculture using Score Cards that considered Extension Planning Areas with more than one cash crop apart from tobacco, roads near trading centres, accessibility to ADMARC depots and Extension workers

- Agricultural production levels of priority crops (cotton, ground nuts, pulses, cassava, rice, maize, vegetables, wheat, sorghum and millet);
- Complementary agricultural interventions through ASWAp that promote marketing;
- The number of available agro input dealers operating in the districts

111.	Secondary, tertiary and district roads will be prioritized by the RA and their Regional Offices using a screening and prioritization methodology for which a proposal will be developed as part of the Project Implementation Manual using the results of economic analysis using the RED model and multi-criteria analysis. Community roads will be identified, prioritized and selected using the current local participatory district planning process working through the Village, Area and District Development Committees (ADC, VDC and DDC) who already have prioritized lists of community roads available.

112.	For this purpose, the RA will work closely with the DC’s and MAFS to ensure that the results of this prioritization procedure are compatible with the overall objectives of RRIP and ASWAp-SP. Existing platforms for consultations at local (District Consultative Meeting) and national level (ASWAp EMC and TWG) will be utilised for effective stakeholder interaction.

113.	At the high level therefore (selection of EPAs), decisions are made using a relatively clear set of technical criteria which can be monitored. This is more scope for selection decisions to be influenced at the lower level however, where District Consultative Committees choose which roads would be most effective at connecting these crops to markets (possibly with VDC and ADC involvement). There is a risk that at the DCC level, MPs or other powerful actors could influence decisions so roads with minimal agricultural benefits but positive patronage benefits (rewarding areas that voted for the MP) or even private benefits are chosen. We will pursue the possibility of oversight of these decisions perhaps by ensuring that a consultant or credible Civil Society Organisations observe the decision-making process, but this will not be possible in all cases, since at least some district lists of roads for upgrading have already been prepared. Therefore we will also pursue options for verifying the choices, e.g. through monitoring visits to discuss process and results with decision makers and/or recipients.

Planning and budgeting

114.	The RA will have overall responsibility for preparation of Annual Work Plans and Budgets based on the project approved Procurement Plan. More details on planning and budgeting procedures will be presented in the Project Implementation Manual.

Road design

115.	The majority of the works are simple in nature and the designs will be based upon line drawings, typical cross-sections, standard drawings and bills of quantities.

116.	Consultancy services will be required to i) carry out the environmental screening of project roads and prepare any environmental impact assessments or resettlement action plans; (ii); carry out road design and prepare bidding documents. A budget of £598,000 has been set-aside for this. It has been assumed that design for rehabilitation and upgrade projects will be outsourced and that the design for spot improvement works is done by the RA.

Implementation and supervision

117.	All road works financed through RRIP will be supervised by independent consultants for whom a separate budget of £1.3 million (5% of the investment works) has been set aside. We propose to hire one consultant nationwide for a period of 3 years to work with the various regional based teams. There are 2 alternatives for contracting an independent supervising consultant by the World Bank:
# 6.3 Capacity building, technical assistance and training

118.	The performance of the RA is seriously undermined by the limitations in numbers of staff, office space and operational budgets. Currently the RA has 104 staff, but according to the revised and approved establishment,[36]this is to be increased to 122. In recognition of the fact that RRIP will add some 10% to the normal workload of the RA, the project will support the capacity of the institution in the following ways:
[36] Road Authority, 5-year Strategic and Business Plan 2011 - 2016

- Purchase of 4 double cabin vehicles to be used for project related activities, 1 for the RA Headquarters and 3 for the RA Regional Offices.
- Purchase of computers, software and equipment for the Maintenance Department and Regional Offices;
- Recruitment of 4 junior project engineers with a minimum of 2 years relevant work experience paid for by the project (on a consultancy basis[37]).
  [37] With the expectation that they may eventually be incorporated in the RA as part of the revised establishment plan. This has happened in a previous donor-funded project with the RA.

Technical assistance

119.	The provision of technical assistance, capacity building and training of the RA, RFA, DC’s, Contractors and Consultants is a prerequisite for successful delivery of the roads component.

120.	A budget of £0.6 million has been set aside for the recruitment of a Technical Assistance (TA) team based on the assumption of 65person-months(p/m) input including overhead costs.

121.	The TA is required to assist RA and other stakeholders with the following tasks below. The RA will recruit the TA, which due to the threshold will trigger prior review by the World Bank. The TA is contracted on an individual basis.

- The road selection and prioritization process;
- Design, costing and packaging of the road works;
- Management of the procurement and contracting functions; including the standardization of management systems and procedures;
- Monitoring the performance of the safeguards and supervision consultants;
- Introduction of Area Based Maintenance;
- Formulation of training needs and identification of training providers;
- On-the-job training of RA staff, contractors and consultants;
- Support to training institutions (NCIC) to deliver formal tailor made courses;
- Monitoring the inclusion of cross cutting issues in the design and implementation stage.

122.	The total input of 65p/m of staff inputs includes the services of a fulltime Team Leader / Senior Rural Road Engineer(39 p/m), a Maintenance Engineer (part-time, 10 p/m), Procurement and Contracting Specialist (part-time, 10 p/m) and other short term inputs (6 p/m) for specialist inputs.

Training

123.	The institutions that are to be involved in project implementation will benefit from training activities to enhance their performance in critical areas for which a training budget of £1 million has been set aside. Some of the courses may be in Malawi while most of them will be in the region. There is a regular schedule of courses in the region on using World Bank systems on a rotational basis. Facilitators from Washington administer the courses. Regional and not country sessions have proved to be most cost-effective. A detailed training needs assessment will be carried out at the start of the project to identify training courses and providers, but initial proposals are:

- MTPW - development of standards, prioritization and management systems for rural roads and policy formulation;
- RA - contract administration and specialized technical topics, mainstreaming of cross cutting issues including HIV/ AIDS, gender and environment in road construction at national and district levels and a study tour to observe the practices of decentralization and unpaved road maintenance in the region;
- RFA - training in the disbursement and management of World Bank funds, and RFA will mentor LAs in financial management;
- MLGRD - project management and procurement procedures and appropriate road prioritization techniques;
- DC’ - Directors of Public Works and Road Supervisors from the DC’s will receive training in local level planning, road management techniques and road maintenance supervision;
- Local Contractors - management of construction activities, finance, labour based methods and facilitation in the leasing or purchasing of equipment through the NCIC; and
- Maintenance Clubs - road maintenance activities and basic financial management.
# 6.4 Cross cutting issues

124.	The RA organizational set up is weak on cross cutting issues; except for environmental issues there is no dedicated staff on issues related to Gender and Occupational Safety and Health (including HIV/AIDS), although the MTPW does have staff with responsibilities for HIV/AIDS prevention. TA will include part time specialist on Cross Cutting issues to promote mainstreaming such issues in the institutions involved.
# 6.5 Risk assessment and mitigation

125.	Overall, the implementation risk is seen as medium.The key risks are set out in the table below:-

Risk	Impact	Mitigating Actions/Factors	Residual risk
(1) Interference in the road selection process	Medium	Objective criteria used for selection of districts, EPAs, and secondary and tertiary roads. / Existing local participatory processes used to select community roads. / Measures to boost local ownership of roads (see risk 3) makes it more difficult to deprive communities of upgrading works. / External monitoring of road selection process and of community roads selection.	Medium
(2) Mis-procurement of works	High	Little history of mis-procurement in road upgrading and maintenance, plus strong background of audits in the sector to identify risks. / WB monitoring of procurement processes, including prior review of the first contracts, and subsequent selective post-procurement review during implementation and annual procurement post reviews. / Audits of RFA and RA by the NAO, plus independent external audits. We will pay for these audits to be continued if this is necessary. Currently the RFA pay for themselves to be financially audited (and in at least some years to have technical and procurement audits) annually by external auditors. This is also a condition of EU SBS to the roads sector, which will last until 2014.	Medium
(3) Sustainability reduced by effective maintenance regimes not being put in place.	High	Incentives created for local communities to demand that roads are maintained through their involvement in the selection process, community based monitoring of upgrading, and opportunities for employment in maintenance. / Upgrades reduce maintenance costs, increasingly the likelihood that the road maintenance budget will be sufficient to fund maintenance. / Road maintenance funding is entirely generated by a levy on fuel, earmarked for maintenance, insulating it to a degree from the possibility of budget cuts. We will monitor maintenance funding, and raise the need to preserve the real value of the levy with GoM as appropriate. / A second round of rural road upgrading is being considered for the next round of the ASWAp. GoM will be aware that this further funding will be jeopardized if maintenance is not carried out on these roads.	Medium
(4) VfM undermined by poor quality work by contractors.	Medium	Training provided to contractors in project management to help them to deliver effectively. / Training and TA provided to the RA to enable them to monitor contractors more effectively to identify problems early on. / Improved procurement planning and processes to reduce likelihood of poor quality work due to poor design or bunching of contracts. / Community-based monitoring involves local communities in checking work quality.	Medium
(5) Road improvements don’t contribute to agricultural productivity as other barriers, food insecurity, or poor macroeconomic conditions prevent farmers from taking advantage of the opportunities presented.	Medium	RRIP integrated within ASWAp to ensure that synergies between road improvements and other initiatives to stimulate agriculture are realized, and that other barriers to agricultural development are addressed / CBM used to gather qualitative data on impacts of road improvements. / Other DFID projects address macro and food security issues, and other constraints such as access to finance and the business environment.	Low
(6) Poor coordination between relevant GoM agencies	Low	Regular ASWAp, TWG, and SWG meetings	Low
(7) Rising prices (or lack of availability) for key imported inputs such as cement and fuel slows construction.	Medium	Malawi has a history of such shortages, which have impacted on previous roads projects. The recent devaluation and removal of exchange controls should reduce the likelihood of general forex shortages. Also, since we will provide our funds in forex, if such shortages do impact our programme then we will investigate amending the financing arrangement to address the problem. / Given the small size and illiquidity of Malawi’s market, periodic shortages of many commodities do temporarily occur. The improved procurement planning introduced through this programme should help suppliers to anticipate market needs, mitigating the problems somewhat.	Medium

# 6.6 Monitoring and evaluation

126.	The Road Authority on an annual basis will do the monitoring of project output and outcome indicators which are in the programme log frame available on Quest Number: 3851100. The responsibility for road condition surveys and traffic counts will be included in the Terms of Reference for the Design and Supervision Consultants. Data about the number of km of roads improved and maintained will be derived from the monthly and annual reports submitted by the Supervision Consultants.

127.	In addition, a number of specific road and transport related impact indicators have been proposed which are to be included in a baseline and impact study to be carried out for RRIP. A budget of £96,000 has been set aside for the studies.

128.	The project also intends to utilise community based monitoring through local NGOs using a Community Scorecard procedure. A budget of £96,000 has been set aside for this.Community satisfaction surveys, over time, could provide qualitative evidence on whether roads have made a difference to people’s distance and time measurements and this could be converted to an economic monetary measure. And in order to add the aspect of transparency and accountability, for instance, a particular district community can be told in advance how much money is being spent, what contractors are supposed to do and when they are supposed to complete the road. This could ensure that the programme has a built in process of monitoring progress and satisfaction (in addition to the formal monitoring by the Roads Authority).

129.	The details of more formal monitoring of the programme are still being agreed with the WB. But the WB will receive quarterly Interim Financial Reports and audited annual accounts from the authorities, and we will request sight of these. Approximately half yearly missions will take place, led by the WB to check on technical as well as financial programme, which DFID will have the option of taking part in. The ASWAp Secretariat will prepare consolidated quarterly progress reports and annual implementation reports which will cover all MDTF funded activities (and will therefore include activities funded by our RRIP contributions.

Evaluation

130.	This programme has undergone an evaluation appraisal using the 7 point appraisal criteria set out in the DFID Malawi Results and Evaluation strategy. The full evaluation appraisal is available on Quest Number: 3823070. A summary of the evaluation appraisal is produced below:

Rural Roads Business Case:	DFID Malawi Evaluation Appraisal
Criteria	Need for evaluation by factor
	High / (Yes)	Medium	Low / (No)
Existing Evidence Base:			X
Pilot / New Programme:			X
Risk/Contentious Programme:			X
Size:	X
Demand:			X
Strategic Importance:		X
Evaluability:			X
Overall Appraisal: Evaluation not required	1	1	5

131.	The evaluation appraisal determined that this programme does not need to be considered for formal independent evaluation. The appraisal noted that monitoring data should be sufficient to determine progress for this programme. The appraisal also noted that existing evidence base for investing in rural roads infrastructure is already strong and hence does not justify the need for a separate independent evaluation. Furthermore, World Bank monitoring arrangements for this investment are expected to provide sufficient guarantees on value for money and the efficient and effective use of DFID’s investment.