ADDENDUM TO BUSINESS CASE:
INVESTMENTS IN FORESTS AND SUSTAINABLE LAND USE
SUMMARY INFORMATION
Project Name	Investments in Forests and Sustainable Land Use
Country or region targeted	West Africa, East Africa, Southeast Asia
Type of cost extension	Cost extension to scale-up impact
Original project budget	£60m (& BEIS funding of £19.3m)
Original project start and end dates	09 December 2014 – 09 December 2020
Cost extension value (if applicable)	£33.5m
New project end date (if applicable)	09 December 2023
Business Case Quest Document No.	9107136

INFORMATION
What is the project’s purpose?
Overview / A new vision for sustainable land use needs to be at the centre of efforts to realise the Paris Climate Agreement and the Sustainable Development Goals. Neither can be achieved without a shift to more sustainable patterns of land use, which produce sufficient food for a growing population, reduce greenhouse gas emissions and protect the ecosystems and natural resources (fresh water, fertile soil, biodiversity, wildlife habitats) which sustain life. / Investments in Forests and Sustainable Land Use (IFSLU) contributes to this new vision for sustainable land use, through public-private partnerships based on sustainable business models, which support development, promote growth and livelihoods, and protect forests. / Conversion of forests to grow a small number of agricultural commodities, including palm oil, soya, beef, cocoa and coffee, is the largest single cause of deforestation in developing countries, accounting for over 70% of deforestation in recent years. Over 470 businesses have made voluntary commitments to reduce or eliminate deforestation from their supply chains and operations. This provides an important opportunity for transformational change, but realising these commitments in practice will be challenging. / IFSLU is working to accelerate this trend in key commodity markets and turn corporate commitments into improved practices on the ground. The programme began operations in 2015 and is making good progress. A strong set of partnerships has been established, with the potential to greatly exceed outcome estimates set out in the programme business case. Realising this impact is taking longer than initially anticipated. Extending the programme to allow more time to realise this potential offers major scope to increase the impact and benefits over the lifetime of the programme, will provide strong value for money and is consistent with the original programme business case. / Investments in Forests and Sustainable Land Use / Implementation takes place through two complementary interventions: / The Tropical Forest Alliance (TFA), which mobilises action by industry, governments and civil society to tackle deforestation caused by agricultural commodities. / Partnerships for Forests (P4F), which supports public-private partnerships based on new business models for sustainable land use, which support development and protect forests. / An independent evaluation and learning manager undertakes continuous evaluation of programme activities to support adaptive management. / The TFA operates globally across key commodity supply chains. P4F operates in West Africa (Ghana, Cote d’Ivoire, Liberia), East Africa (Ethiopia, Kenya, Tanzania, Mozambique) and Southeast Asia (Indonesia). BEIS also recently committed funding to extend operations to Brazil and Colombia. / Results / The programme has consistently scored A at Annual Review and is achieving strong results. P4F is currently on track to exceed outcomes, bringing 1.4m hectares of land under sustainable management (equivalent to three-quarters of the size of Wales) and mobilising £350m of private investment, against targets of 1m ha and £150m respectively. / Proof-of-concept has been achieved through grant funding to prepare a sustainable rubber project, which subsequently secured commercial ‘green’ investment of $95m across 70,000 hectares of land. A set of partnerships has been established at all levels of supply chains for palm oil and cocoa (with good progress towards achieving this for rubber) with potential to support transformational change in the production, trade and use of these commodities over the lifetime of the programme. / IFSLU also generates results in terms of livelihoods and job creation in rural areas of developing countries, while helping UK companies to secure long-term supplies of commodities which are essential to their businesses, including palm oil, timber and cocoa.
What is the objective of the cost extension or other changes?
Overview / The extension will ensure greater impact and value for money from DFID’s investment, as well as supporting UK policy objectives for climate resilience, climate finance and the mobilisation of private sector investment, trade and sustainable commodities, and protection of wildlife habitat. / Programme objectives / The programme-level objectives of the extension are to: / Secure transformational impact and maximise value-for-money; / Scale-up successful interventions; / Building momentum, generating wider buy-in and action. / Secure transformational impact and maximise value-for-money / IFSLU has established strong positions within supply chains for cocoa and palm oil. These positions cover demand (sustainable sourcing commitments by governments, encompassing approximately 75% of the European market for these commodities); enabling conditions (new industry sustainability standards, policy reform and regulation in producer countries); and partnerships with companies on the ground to develop and test new and sustainable ways of doing business. / A portfolio of work has also been established around the restoration of degraded land. This makes an important contribution to community resilience, through providing a diversified income from tree crops and through protecting farmland from erosion. It also makes an important contribution towards restoring and ensuring the long-term resilience of ecosystems. / P4F interventions include partnerships to develop sustainable business models and revenue streams for restoration concessions; and partnerships to plant trees on unproductive land working with smallholder farmers. To enable the scaling-up of this work, the programme is developing innovative financing mechanisms which provide finance at scale to small farmers and enable private sector investment in restoration. A partnership has been established with the African Forest Landscape Restoration Initiative (AFR100) to share lessons from this work and encourage replication. / There is significant potential to increase work around key supply chains and forest restoration, as well as other partnerships in the programme portfolio, to increase impact and benefits. The extension provides time and additional resources to achieve this potential. / Scale-up successful interventions / As results are consolidated in the portfolio described above, there is potential to scale-up across countries (for example, applying good practice from palm oil development in Ghana to support palm oil development in Liberia), between regions (taking approaches to forest restoration in Indonesia and applying these in West Africa), within value chains (replication of deforestation-free cocoa pilots by other cocoa companies), across value chains (transfer of best practice from cocoa into palm oil value chains, and vice versa), aggregation (bundling products from niche value chains to achieve investable scale) and leveraging greater levels of private finance. / Building momentum, generating wider buy-in and action / IFSLU has successfully developed an approach to incubating public-private partnerships for sustainable land use. This is a unique focus and fills a gap in current efforts by the international community. The post-programme strategy, which will be developed during the extension period, aims to secure the knowledge, systems, strategy, partnerships and portfolio built up through the programme, and ensure this potential makes a contribution to longer term efforts to promote private investment in sustainable land use once the programme has closed. This will support continued UK aims for climate finance, private sector engagement and resilience, and encouraging action by others public and private actors. / Policy objectives / A further set of policy objectives for the cost extension include: / Supporting UK aims for climate resilience; / Supporting UK international climate finance objectives; / Delivering UK objectives for trade and sustainable commodities; / Maintaining UK support to private sector sustainability commitments; / Protecting key wildlife habitat and contributing to UK biodiversity policy objectives. / Supporting UK aims for climate resilience / Climate resilience is an increasingly important focus for the international community, recognising the reality of a changing climate and the need to build resilience to shocks into livelihoods, economies, businesses, supply chains, ecosystems and countries. The extension will support this growing effort and support private sector action around resilient land use and supply chains, drawing on the P4F model of building public-private partnerships around climate smart agriculture, sustainable land use and commodity supply chains. / Supporting HMG international climate finance objectives / The commitment to mobilise US$100bn in climate finance annually by 2020 requires a significant increase in qualifying private investment. To achieve this, donors must develop new ways of using public funds to mobilise the private sector. Future UK commitments of climate finance are likely to focus heavily on this issue, using development capital to encourage private investment. The extension helps to meet this policy goal in the area of sustainable land use, through developing a supply of projects ready for private investment. The programme will work more closely in alignment with UK development capital investments – CDC and other platforms which may in future be established – to help design and prepare projects for investment. / Delivering UK objectives for trade and sustainable commodities / IFSLU is playing a critical role in both shaping and delivering HMG’s aims and objectives around sustainable commodity value chains. This area of work is growing rapidly in profile, through delivery of the UK’s 25-Year Environment Action Plan and through the growing importance of public-private partnerships to deliver action to tackle climate change and support economic development. / Maintaining UK support to private sector sustainability commitments / The year 2020 is the deadline by which many companies have committed to remove deforestation from their supply chains and operations. This will not be achieved, but good progress has been made and further efforts beyond 2020 need to be sustained, given the crucial influence of this issue on global deforestation rates. Partnerships for Forests is playing a key role in demonstrating how to turn commitments into practice, with successful examples emerging from palm oil, cocoa and rubber partnerships. Positive examples like these will play an important role in shaping a post-2020 narrative, showing that progress is being made and that ambitious commitments can be realised, helping to sustain support and effort around that goal. / Protecting key wildlife habitat and contributing to UK biodiversity policy objectives / Tropical forests provide habitat for many critically endangered species, including tigers, elephants, orangutan and chimpanzee. Mitigating a major driver of deforestation will help to protect key wildlife habitat. This supports the aims of the Illegal Wildlife Trade conference which the UK hosts in October 2018, through working with sustainable business to deliver long-term impact that benefits both poor people and wildlife. The extension will also anticipate future priorities relating to the Convention on Biological Diversity, through public-private partnerships which capture value in biodiversity.
What is the additional and total support the UK will provide?
The UK will provide an additional £33.5m. This will increase total UK support to £112.8m over a total period of eight years (2015-2023). The provisional allocation of additional support is as follows: / Tropical Forest Alliance Post-2020 support to the community of practice working to support an industry-wide transition to sustainable palm oi, soya, cocoa, cattle and paper & board. £2m / Partnerships for Forests Support for reforms to markets, enabling conditions to facilitate sustainable investment and grant funding and technical assistance to develop public-private partnerships for sustainable land use. £30m / Food and Land Use Alliance Support to align climate, food production and land use agendas, share lessons and scale-up sustainable land use public-private partnerships. £1m / Building momentum, generating wider buy-in and action Evaluation and assessment of needs and opportunities to institutionalise and sustain momentum for sustainable land use public-private partnerships after programme closure. £0.5m / Total £33.5m / .
What are the expected results?
The programme has the potential to bring up to 1.4m ha of land under sustainable management (equivalent to three-quarters of the size of Wales) and mobilise up to £350m of private investment, against targets of 1m ha and £150m respectively. Realising this impact is taking longer than initially anticipated. The extension will provide more time to realise these results. Projected impacts greatly exceed estimates in the programme business case and the extension offers strong value for money. / Any further increase in key performance indicators from the additional funds made available through the extension will depend on the ambition of new public-private partnerships supported under the proposed extension, as well as progress to scale-up interventions within the existing portfolio. / The extension will also secure further progress towards the transformation of agricultural commodity production. Specific results include the completion of pilot projects for deforestation-free cocoa, palm oil and rubber, generating improved livelihoods and strengthened resilience amongst large numbers of smallholder farmers associated with these interventions. / The extension will also ensure the completion of pilot projects to restore degraded land with tree cover; and generate proof-of-concept for business models and sustainable value chains to finance restoration. This will generate improved livelihoods and strengthened resilience for large numbers of smallholder farmers and communities engaged in the restoration of degraded land. / Examples of partnerships expected to generate results during the extension period include: / Ghana: Working with Touton, a French cocoa trading company, to increase sustainable cocoa production, benefiting up to 150,000 people while protecting the Bia National Park. / Ethiopia: Building a brand and higher value in wild forest coffee (Arabica coffee originates in Ethiopia), to improve livelihoods for up to 23,000 farmers, conserve the wild range of the plant and preserve genetic diversity in wild coffee varieties. / Indonesia: Support sustainable rubber plantation development, creating 16,000 jobs and improving 50,000 livelihoods while protecting key protected areas and wildlife habitat. / Further scaling-up of efforts to transform agricultural commodity production will be achieved through programme partners embedding pilot approaches within broader company operations and the replication of innovative pilot approaches by industry players throughout supply chains. The Tropical Forest Alliance, which convenes a global community of practice for sustainable supply chains, will play a key role in this process of scaling and replication. / Scaling of forest restoration will be achieved through developing innovative mechanisms to finance restoration at scale, through aggregating large numbers of smallholder farmers, integrating land restoration within existing smallholder agricultural lending platforms and enabling private sector investment in restoration; and replication through the AFR100 community of practice.
What is the approach to implementation?
Implementation arrangements / The funding will be delivered through existing implementation arrangements. Funding for the Tropical Forest Alliance is provided through an accountable grant to the World Economic Forum, under a delegated cooperation agreement with Norway. Partnerships for Forests is implemented through a service contract with Palladium. A new partnership with the Food and Land Use (FOLU) Coalition is proposed, implemented through an accountable grant (subject to due diligence and value for money), to apply lessons from P4F public-private partnerships to wider agriculture, food and land use challenges. / Value for money / The main cost driver in P4F is the need to engage the specialist expertise required to work effectively with businesses, governments, industry associations and non-government organisations, and design and structure innovative public-private partnerships, which are financially viable, and deliver social and environmental benefits, while meeting DFID’s standards for risk management. / Mobilisation of private investment through use of DFID’s grant funding ensures that the programme achieves a strong value-for-money outcome. Programme support is geared towards helping partners secure the commercial finance required to become financially viable businesses, providing the programme with an exit strategy from the partnership. To date, programme funding has secured £67m (US$95m) in commercial ‘green’ private sector investment. The projected level of investment mobilised over the lifetime of the programme is up to £350m. / Gender Equality Statement / The business case was supported by a social and gender appraisal. Both the TFA and P4F have adopted gender and inclusion strategies. Partnerships for Forests reports gender impacts through case studies. A review of partnerships has been undertaken to identify case studies and baseline data is currently being collected. The first case studies are focused on customary law for land tenure and impacts on women palm oil farmers in Ghana; women’s participation in the wild coffee value chain in Ethiopia; and participation of women and indigenous people in the forest honey value chain in Indonesia. Certain flagship partnerships are also collecting baseline gender data, including a cocoa partnership in Ghana, with a view to future reporting of disaggregated gender impacts. The case studies will allow P4F to document best practice, identify ways of delivering benefits for women and girls through sustainable land use public-private partnerships, and seek opportunities to replicate best-practice approaches. / Risk management / Partnerships for Forests applies a robust risk management strategy. Key risks are: / Risk Mitigation / Challenges aligning public funding requirements with private sector operating practices, resulting in inability to form effective partnerships and leverage required level of private capital Developing a broad portfolio with potential to exceed target level of finance. Early and sustained engagement with private sector partners to identify ‘sweet-spot’ opportunities for collaboration, aligning public and private interests. / Partnerships with private sector focused on sensitive land and resource issues, with associated environmental and social risks. Scrutiny of partnerships, detailed due diligence, close monitoring of risks, interventions to mitigate risks identified in specific partnerships. / Risk of media criticism and reputational damage through private sector partnerships Engagement of reputational risk manager, reputational risk training, establishment of crisis management protocols and procedures. / Systems have been designed to ensure that fiduciary risk is low. Programme funds are disbursed through an external service provider with strong due diligence and financial management systems. Downstream mapping of the supply chain has taken place for Tier 2 and Tier 3 partners.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The proposed extension remains in line with the original business case and overarching theory of change. / The Independent Evaluation and Learning Manager has conducted a comparative analysis of programmes focused on incubating public-private partnerships and noted that “Partnerships for Forests is a highly experimental programme wishing to achieve results in a short time frame, which comparators have only achieved after much longer periods of learning and refinement”. The set-up and mobilisation of the programme, the development of a high-impact portfolio of 27 partnerships, and the results achieved to date, has been a significant achievement. A review of secondary literature provides evidence to support the P4F theory of change, its activities and outcomes.