Project Completion Review (PCR)

Title: Education Data Research and Evaluation in Nigeria (EDOREN)
Final Programme Value £ (full life): £9,617,869.56	Review Date: June 2018
Programme Code: 202643	Start Date: March 2013	Final End Date: June 2018

Summary of Programme Performance
Year	2014	2015/16	2016/17	2017/18
Programme Score	A	A	A	A
Risk Rating	Moderate	Moderate	Minor	Minor

DevTracker Link to Business Case:	EDOREN Business Case
DevTracker Link to Log frame:	EDOREN Logframe

A. Summary and Overview

Description of programme and what it has achieved

DFID Nigeria’s Education Data Research and Evaluation Programme, EDOREN, was implemented by Oxford Policy Management (OPM). The project had two objectives – i) to embed research, evaluation and learning in DFID’s education programming in Nigeria and ii) to enhance national capacity to generate and use quality education data, research and evaluation for policy and strategy making. In 5 years, EDOREN has placed Nigeria “on the map” from an education research and evaluation perspective.

In 2013 when EDOREN began there were no rigourous evaluations on what works to support learning outcomes in Nigeria. By 2018, EDOREN had enabled 2 high quality rigourous impact evaluations for DFID Nigeria’s Teacher Development Programme (TDP) and Girls Education Project, (GEP3) including GEP3’s Reading and Numeracy Activity (RANA). EDOREN also undertook evaluations for DFID Nigeria’s innovative low cost private education programme, Developing Effective Private Education in Nigeria (DEEPEN), and also an evaluation of the outcomes associated with DFID’s support to Bridge International Academies (BIA). The findings from the evaluation surveys have informed DFID Nigeria programming and crucially have provided a stronger evidence base for DFID Nigeria’s future education programming in Nigeria.

In 2013 when EDOREN began, there was no central initiative in the Federal Ministry of Education to promote the use of evidence for policy making and impact. By 2018, EDOREN had supported the Federal Ministry of Education (FME) to routinely budget for and lead the Nigerian Annual Education Conference (NAEC) which brings together policy makers, researchers and practitioners to promote the use of evidence in education planning and implementation. EDOREN pioneered collaborative research in education in Nigeria by supporting Nigerian academics, policy makers and civil society to work together in teams to conduct thematic research. This approach was used for studies on teacher recruitment and deployment and the recommendations contributed to important teacher workforce reforms being taken forward by government in the DFID partner states of Kaduna, Jigawa and Kano. In addition to the evaluations and collaborative research, EDOREN supported thematic research in a range of areas including how to better support female teachers, attitudes to primary school attendance in the wake of the Boko Haram insurgency and on Special Educational Needs and Disability.

The high quality of work produced by EDOREN was recognised by stakeholders interviewed for this project completion review (PCR) who spoke of EDOREN’s positive contributions to improving attitudes regarding use of data and evidence in decision making. EDOREN’s work benefitted other development partners, e.g. the review of Universal Basic Education in Nigeria which provided a historical and comparative perspective of UBE reforms, contributed to the design of the World Bank’s first results based financing project on basic education in Nigeria.

The project closes having produced a critical mass of high quality data, research and knowledge products that are increasingly being accessed and used by a variety of stakeholders – all available on www.nigeria-education.org. In addition to the reports of evaluations and thematic research, the programme produced a wide range of case studies, experience papers and synthesis papers on a range of issues including data use, teacher competency, approaches to collaborative research, reflections on the EDOREN model and overall lessons learned for future education programming in Nigeria.

Overall assessment: A

EDOREN was originally planned as an 8 year programme and contracted to Oxord Policy Manageent (OPM) for 4 years (to 2017). The project began in 2013 as a component under the UNICEF implemented Girls Education Project (GEP3), to support efforts to improve data quality within the project. Work for EDOREN to undertake was included in 3 other business cases – Education Sector Support programme in Nigeria (ESSPIN) Extension Business Case (BC), DEEPEN, TDP – and a decision was subsequently taken by the Head of Office in 2015, to create EDOREN as a standalone project for accountability purposes. Following the outcome of the DFID Portfolio Quality Review in 2017 the programme contract was extended for 1 more year to close in June 2018, rather than a further 4 years. This decision was a reflection of DFID Nigeria portfolio direction, including the decision that future work to achieve EDOREN’s outcomes would be incorporated into the design of the new flagship education programme. The decision was not a reflect of the project’s performance.

EDOREN has consistently met expectations during the lifetime of the programme, delivering high quality research and evaluation outputs in an often challenging working environment. The final year of the programme has been the busiest to date as the programme grappled with the requirement to close earlier than initially planned, and the need to do as much work as possible in the time remaining. The team should be recognised for delivering a high volume of quality work in its final year.

In determing the overall assessment of A, the review team acknowledged evidence from output scoring in previous annual reviews and factored this into achievements in the final year. Based on this approach, EDOREN has been scored As across outputs 1 (evaluations and operational research), 3 (data systems and quality) and 4 (knowledge and dissemination), and scored A+ for output 2 on thematic research. There was evidence of achievement of intermediate level outcomes in that -i) EDOREN’s work was used by DFID and DFID programmes in design and implementation, ii) some outputs were used by state and federal governments to improve education policy design and service provision, and iii) education data collection and analysis in Nigeria improved in targeted states (examples discussed in Outcomes section below).

The achievements of the programme point to what more needs to be done with regard to future programming to achieve EDOREN’s objectives. This Programme Completion Review sets out lessons learned (see Output sections below), to be taken on board for future programming.

Follow up actions required following approval of this report

The actions are:

- DFID Nigeria, GEP3, TDP, DEEPEN and Bridge to ensure adequate dissemination and follow up of evaluation findings – within Nigeria (state and federal) (Oct 2018), across DFID (Dec 2018) and at external fora (ongoing).
- DFID Nigeria to share lessons learned from EDOREN PCR with DFID’s Education Resarch Team, Research and Evidence division and education research team (Dec 2018)
- DFID Nigeria to share the lessons learned from the EDOREN programme and evaluations with potential suppliers to inform approaches to supporting use of evidence for policy and programming impact in DFID Nigeria’s planned new flagship education programme, as part of Early Market Engagements events (Dec 2018) and ensure that the learnings from EDOREN are embedded in future programming (ongoing)
- DFID Nigeria to use lessons learned from EDOREN evaluations to influence the design and implementation of other programmes in country, including World Bank and Global Partnership for Education (GPE) project.
- Finalise the project audit following report from auditors which was “unqualified”: conduct the tripartite meeting with auditors, DFID Nigeria and OPM, take any required actions, ensure documents are saved on DFID systems. Following this, OPM will then present its final invoice for payment by DFID.

## B: DETAILED OUTPUT SCORING

Output Title	Evaluations, reviews and operational research studies for DFID Nigeria education programmes
Output number per LF		1	Output Score	A
Impact weighting (%)?		60%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of evaluation products signed off by DFID evaluation review processes	Review of GEP3 strategies, theory of change and logframe*; GEP3 evaluability study*; GEP3 evaluation framework; baseline report and midline report. / DEEPEN evaluation framework; DEEPEN ex ante review*; DEEPEN baseline report and midline report / TDP evaluation framework; baseline report and midline report / * = not subject to SEQAS review	All reports completed. / Strong positive feedback from SEQAS / EQUALS[1] on reviewed reports, all green/excellent rated except GEP3 evaluation framework (amber).
Number of other research studies in the context of DFID-N programmes signed off by DFID	GEP3 FTTSS Tracker Study; FTTSS OR study; GEP3 Teacher Supply and Demand study; GEP3 PEA study; ESSPIN Capacity Impact study; TDP Teacher Supply and Demand Studies; DEEPEN Public-Private Primary 4 Comparison Study; TDP Formative Research (“In-service training activities”); Bridge Research Report	All reports completed and to a high quality standard.
[1] This is DFID’s Evaluation Quality Assurance and Learning Service (EQUALS), previously known as Evaluation Quality Assurance Service (SEQAS)

Provide supporting narriative for the score

The A score for this Output under EDOREN is strongly justified because EDOREN consistently delivered research and evaluation products that are robust, rigorous and of a technically high quality. SEQAS/EQUALS has rated technical evaluation reports as green/excellent, with feedback noting that field work was well-planned and executed, agile enough to respond to issues, and that the reports were comprehensive and well-written. The past year in particular was an intense period of activity for EDOREN, which managed 3 evaluations and an observational study of Bridge International Academies (BIA) concurrently. Drafts of the evaluation reports for TDP, GEP3 and DEEPEN and the study on BIA were produced by EDOREN in advance of project closure but the final reports were not produced until afterwards in July, due to the need to properly reflect feedback from the evaluation steering committees, the projects and DFID EQUALS before finalisation. It was therefore not possible to properly disseminate the findings before the project closed and responsibility for this must now be taken up by DFID Nigeria and the projects that were evaluated (see recommendations below).

EDOREN’s evaluations are an important contribution to the evidence base on teaching and learning in Nigeria – they provide a wealth of evidence that helps DFID, programmes and policy makers better understand what is and is not working in Nigerian basic education systems – to inform future programme design, planning and implementation. Beyond the evaluation reports, the project produced policy briefs, shorter synthesis reports and presentations in critical areas – e.g. findings on teacher competency in Northern Nigeria; public and private education markets in Lagos. The raw data has been made available on open source sites, allowing researchers to conduct additional research.

EDOREN’s relationship with other DFID Nigeria education projects was largely positive. The quality of EDOREN’s outputs and their thorough technical approach was recognised by DFID Nigeria’s other education projects and projects noted that there had been collaboration between EDOREN, projects and DFID to ensure evaluations were carried out in line with plans and on time. Jointly commissioned operational research was highly valued by projects, for example - the teacher supply and demand studies undertaken with TDP, were critical in providing the evidence base for TDP to promote better coordination between supply side (pre-service Colleges of Education) and demand side (State Universal Basic Education Boards, SUBEBs) teacher agencies.

The EDOREN team produced a paper which offered reflections on the EDOREN model and sets out lessons for other DFID programmes seeking to achieve similar objectives to EDOREN.[2]
[2] “The EDOREN model: Reflections and implications for other DFID programmes”, on www.nigeria-education.org
Reflections offered in that paper include:
1. How EDOREN’s model and Theory of Change evolved over time starting from the need to provide rigourous independent evaluation of DFID projects in country (prioritised following an ICAI review in 2012) to later creating more opportunities for formative research leading to more work on thematic research and greater focus on policy impact;
2. The factors that were supportive (e.g. EDOREN specialised staff) and those that provided constraints (e.g. long lags between completion of surveys and sharing of findings), in supporting EDOREN to contribute effectively to the other projects;
3. Discussion on finding the balance between EDOREN’s DFID-facing and government- facing objectives and reflections on project structure and resourcing.

As part of the review of this output, the PCR review team had a mandate to investigate the experiences of EDOREN and the projects which were evaluated by EDOREN. The points below are summary reflections from the team on a range of issues which emerged during the course of the review and from which lessons can be drawn out for future programming.

Evaluation objectives and design: The programme’s own reflections on EDOREN’s model highlight the tension in all evaluations between their focus on generating learning outcomes data for results reporting and accountability, versus more formative research to improve programme implementation. While these objectives are not mutually exclusive, the choice of high quality rigorous impact evaluations by DFID for interventions that were not yet properly tested, suggests that more emphasis was given to the former rather than the latter. A point of learning from EDOREN that should be taken on board from future programming is that - given the myriad and systematic challenges of the contexts in which the programmes worked, greater emphasis could have been put on formative approaches in the first instance – with more focus on evaluation of processes and nimble evaluation to support testing and learning, only graduating to rigorous evaluation when there was sufficient confidence that the intervention was “worth evaluating”.

Projects reported that they did not always fully understand all the implications and trade offs associated with the evaluation design and instruments which were eventually selected. This points to the asymmetry in technical expertise sometimes encountered when high quality robust evaluations are implemented, whereby even though evaluation frameworks outline the limitations of different design options, these may not be fully internalised by the project until the effects are clearer – when baseline surveys have been carried out and implementation has commenced. The case of DEEPEN which sought to test the making markets work for the poor (M4P) approach, for the first time globally in low cost private education markets is notable in this regard. The DEEPEN Evaluation Framework required that following the baseline, a critical intervention on Rules and Standards – the Graded Assessment of Private Schools (GAPS) had to be rolled out by government for the outcomes of the programme to be robustly evaluated at endline. When it became clear that the delays to government rollout of the GAPS meant that the endline evaluation would not be able to generate sufficient evidence of DEEPEN outcomes and impact, the programme challenged the design adopted in the evaluation framework and felt that its limitations should have been made clearer before they agreed to it. While the Evaluation Framework set out the risks of the selected design, these were not fully discussed and internalised by all parties. In hindsight, EDOREN agreed that they could have better ensured that all parties understood the implications of the design. EDOREN also believed that a different design could have been adopted and that they should have engaged DFID more strongly on the final design, rather than accept the decision to hinge the evaluation’s ability to measure DEEPEN effects so strongly on GAPS rollout.

Instrument design: The PCR team found that there was some inconsistency in the level of visibility different EDOREN evaluation leads gave to the different projects with regard to the instruments used for data collection – in the case of TDP and Bridge, the projects had sight of and in the latter case, made some input into the instrument design process to ensure relevance to the operating context. However in the case of RANA, the project was not involved in the instrument design process resulting in some tension as to whether the instruments deployed were appropriate for measuring the interventions implemented by the Programme. Reviews of some of the instruments by the PCR team point to some complexities with regard to instrument design that should be better considered in future programming. For example, the instrument for the Teacher Development Needs Assessment (TDNA) required a high degree of understanding of “exam technique” for teachers to be familiar with the requirements of the test. On language - having English instructions in a teacher competency test on Hausa language which had test questions in Hausa – raised some concerns.

Evaluation governance: EDOREN, the Projects and DFID were the principal parties involved in meetings to plan and deliver the evaluations. The PCR noted that at times EDOREN did not adequately engage the Steering Committees throughout the evaluation design, implementation and dissemination process although the project did improve its management of the Steering committee in its final 2 years. There appear to have been issues with selection of suitably qualified steering committee members leading to insufficient participation by some members. Overall the PCR team believes that there was underutilisation of evaluation Steering Committees which could have better helped to mediate different interests of all stakeholders, create space for challenge, navigate design concerns and to provide communications and dissemination support.

Staffing, structure and ownership of evaluations: Having a core team who worked on multiple evaluations and other EDOREN activities allowed for contextual knowledge to be built within the UK-based evaluation teams and for lessons and tools to be transferred between evaluations, which would not have happened if DFID (or projects) had separately contracted evaluations. This is an important lesson to embed for future programming.

However, the PCR team noted some concerns with ownership of evaluations which may affect policy impact. The evaluations were perceived by a range of stakeholders as being UK-driven rather than Nigerian-driven. While capacity of individuals was built in that evaluation teams were majority Nigerian enumerators and significant capacity of individuals was built over time in enumeration for quantitative and qualitative fieldwork, the evaluation model led to limited opportunities for building the capacity of key Nigerian institutions on learning assessment. In response to DFID Nigeria’s focus on rigourous analysis, EDOREN’s evaluation approach brought in high quality expertise to design and lead on evaluations and this contributed to building the projects reputation for quality. In doing so however, less attention was paid to systematically building local institutional capacity in the conduct of assessment, an issue that will be given greater focus in future DFID Nigeria programming.

EDOREN’s dual role of independent evaluator and commissioned researcher sometimes led to challenges on EDOREN’s ways of working with the other projects. Over time these were managed well by EDOREN, supported by the introduction of workstream leads, which streamlined relationship management. However DFID could have helped manage expectations from the outset e.g. better establishing guidelines for managing the evaluations/research between programmes and EDOREN, rather than stepping in to resolve issues for example on branding and communications with state partners.

Projects use of findings from evaluation and communicating the evidence from evaluation to external stakeholders
Some difficulties were raised by projects about issues which they felt limited their engagement with the evaluation findings. These included - long time lags between survey results and reports emerging particularly in the case of the baselines therefore not having sufficient time to influence project implementation; issues following triangulation of evaluation data with other qualitative sources and project monitoring data – for example the evaluation of RANA appears to give more negative feedback about the projects outcomes than project monitoring data and stakeholder feedback from observation.

Sometimes difficult findings which EDOREN evaluations identified and nuances required in reporting led to the projects being concerned about how best to communicate the findings appropriately to audiences who were not technical experts. Rather than leave the external evaluator to disseminate the findings to stakeholders, projects were keen to work collaboratively with EDOREN in the dissemination and communication of findings. This included reviewing the communication products produced from the evaluation to ensure that they distilled the key messages and policy implications clearly for decision makers. EDOREN’s positive engagement to enable joint dissemination of evaluation findings was welcomed by projects.

Recommendations for project closure
1. DFID Nigeria should ensure EDOREN produce all pre-agreed dissemination materials (policy briefs, stand-alone executive summaries, presentations etc.) for all concluded evaluations (by end September – in progress at the time of PCR submission).
2. DFID Nigeria to ensure programme teams with OPM evaluation leads disseminate evaluation report findings broadly and support stakeholders to identify recommendations for future programming, government planning and implementation that will demonstrate engagement with the findings and recommendations from the evaluations. The TDP Evaluation Dissemination session occurred in September 2018 at the time of writing this PCR, the GEP3/ RANA Dissemination session is pending.

Lessons identified and recommendations for future programmes
1. In developing evaluations creating space early on for constructive external challenge from individuals beyond the immediate team could have helped open up dialogue on appropriateness of design, explored alternative options and help build ownership from a wider range of stakeholders from an earlier stage. In future evaluations DFID teams should help facilitate this process before evaluation questions and designs are finalised.This could include external inputs as well as more cross-office or cross-cadre challenge and crucially greater involvement from government at conception/planning stage. Sufficient evaluation expertise needs to be in place within DFID teams to support this technical debate through (in-country) Evaluation Advisers or EQUALS support and Steering Committees need to have wider membership to facilitate this approach.
2. More attention needs to be paid to instrument design particularly the extent to which instruments are accepted and understood by a range of stakeholders and how the instruments can relate to other existing/accepted instruments used by other partners and decision makers. On learning assessments, DFID Nigeria should support efforts to standardise approaches across partners and contexts and seek to adopt standard tools such as EGRA/EGMA going forward – to generate greater buy in on learning assessment, enable greater understanding of results amongst other partners and decision makers and support metrics which could contribute to SDG reporting from Nigeria. Additional studies can be commissioned where required to “get beyond” causal links and the why following the presentation of findings emerging from the use of standard tools.
3. Workplans and budgets for evaluations and research need dedicated resources allocated for communication and dissemination, with efforts made to ensure that this doesn’t get cut/reduced at the end. Evaluation teams should include dedicated communications expertise to help facilitate the distillation of key messages.
4. Having team members who worked across multiple evaluations led to more comprehensive understanding among evaluation teams of the context and EQUALS requirements, and contributed to cost and efficiency-savings – the model of having evaluation providers under one leadership should continue, although this does not preclude a lead evaluator “buying in” relevant expertise from outside its own organisation where appropriate to address the issues and evaluatiuon approaches, e.g. process evaluation, prioritised by stakeholders.
5. In areas where evidence indicates multiple factors beyond education are affecting children and the functioning of the education sector, evaluation design should incorporate elements to assess assumptions within theories of change, barriers to change and how this is affecting delivery. There should be greater focus on complementary operational research to help deepen understanding of issues and response to evaluation findings. Operational research, Process evaluation and “real time learning” should be better factored into planned work to support data and use of evidence under DFID’s new flagship programme.
6. In future programmes where a project may be expected to play dual role of evaluator and research partner DFID should take strong leadership from the outset so that mutual expectations and ways of working are established between all parties.

Output Title	Primary and secondary studies on key basic education issues in Nigeria
Output number per LF		2	Output Score	A+
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Provide supporting narriative for the score

Indicator(s)	Milestones	Progress
Number of studies signed off by DFID advisers	Thematic research proposals (initial scoping); Review of education data in household surveys (2ndary); / Completion of Thematic Research (TR): TR1: UBE literature review; TR2: Teacher management study; Analysis of wealth, gender and regional inequalities (secondary); TR3: Identifying, Recruiting, and Deploying Effective Teachers; TR4: Primary school attendance in the wake of conflict in Borno; TR5: Evidence-based Education Policy and Practice of Teacher Recruitment and Deployment in Nigeria; TR6: Special Needs Education / Disabilities; Borno Teacher tracking study (not planned in logframe)	All completed. / Dissemination and support for stakeholder follow up actions completed.

Provide supporting narriative for the score

EDOREN delivered all milestones associated with this Output and also demonstrated progress towards outcomes with regard to evidence being used to impact on teacher policy in DFID partner states. Further detail on the work done under this output is set out in the EDOREN End of Programme report, June 2018. The work under this Output in the earlier part of the programme involved thematic research designed and led by external international consultants with some input from Nigerians in qualitative field work teams, shifting - in the last 2 years a dedicated focus on Nigerian teams of academics and policy makers determining research questions and methods with the support of an international facilitator. EDOREN became less risk adverse to testing new ideas and diversifying approaches under this Output once they had become more established, gained experience working in Nigeria and had built reputation and relationships and this testing was championed by the project’s Country Director in Abuja.

Collaborative research approach: The past year has seen an intensification of the collaborative problem-driven research approach that facilitates teams of academics and policy-makers to jointly identify research needs, then design and undertake research. This has resulted in demonstrable impacts with regards to capacity development and a higher value being placed on evidence by stakeholders who have participated in the research. Momentum has built over the last two years on the benefits as findings from the studies have emerged and EDOREN fellows at state level have helped facilitate evidence-based dialogue and institutional exchange. Perhaps the most notable success under this output over the past year has been EDOREN’s role in supporting the thematic research on teacher effectiveness that informed the reforms in Kaduna state whereby the governor took a decision to relieve 21,000 teachers of their jobs due to poor competency and hire 25,000 new teachers. The process was still underway at the time of project closure and the Governor, Commissioner Budget and Planning and Commissiover of Education highlighted the findings and recommendations from EDOREN collaborative research, including better approaches to select and deploy more effective teachers, as critical to supporting the teacher workforce reforms they are implementing. The EDOREN brand has come to be synonymous with a desire to use evidence in Kaduna state and the state chose to immortalise EDOREN’s efforts in the naming of a new research library in the Ministry of Education as the EDOREN Library.

Capacity building: Under this output, EDOREN has demonstrated an ongoing commitment to involving Nigerian researchers, increasing the number of national teams carrying out research activities for the programme particularly in the context of qualitative research and its thematic research workstream. In particular, the team has attempted to expand the role of nationals beyond data collection and enumeration (a recommendation in previous annual review). State-level research capacity strengthening teams involving policymakers and academics have helped to bring different stakeholders together who have not traditionally worked together. In the case of the research on Special Education Needs and Disability, the team also included civil society and media stakeholders. The representative from SUBEB appreciated the validation workshop with stakeholders where findings were discussed in a solution-focussed way. EDOREN researchers gained information, engaged in an ongoing working-level dialogue, and achieved recognition and impact for research. In the words of the SUBEB representative:
 “…One thing that has stood them [EDOREN] out is their convening power; they are able to bring in other partners.”

Policy impact: A majority of the evidence of impact and policy changes noted by the review team related to activities completed under this output. For example in Kano government, stakeholders reported being able to talk more confidently about issues with research to back up their points. State-level teacher policy has been domesticated in Kano, informed by the thematic research on teacher effectiveness which recommended new approaches to teacher recruitment and deployment study. In Jigawa, the study was used by the Commissioner to advocate to the Governor to support changes to teacher recruitment processes. Stakeholders valued having evidence to refer to when challenged by others. To some extent the higher proportion of demonstrable examples of research influencing policy and decision-making is to be expected under this output, given the nature of the activities supported and the problem orientated approach adopted. It is also an indicator of the cost-effectiveness of the approach.

In the last year the Special Education Needs and Disability (SEND) study has been a notable addition to the thematic research portfolio, as a new area of research for EDOREN and an example of activities under this output being used to strengthen the evidence base in areas of DFID’s interest to fill data gaps and inform DFID’s decision-making. Stakeholders at all levels voiced their appreciation of the research approach and it’s robustness (with regards to consent, ethics and processes to minimise bias). The SEND research team received positive feedback from parents of children living with disabilities who felt engaged and empowered by the process due to the validaton workshops rather than just being a provider of information. They saw the research as a positive process to help reduce stigma associated with disability and increase expectations for what their children could achieve. This, coupled with dedicated media engagement from the outset, has helped build momentum around results and also led to unintended outcomes. For example there has been increased interest of parents in improved interaction with their children who are hearing impaired; one of the parents who was part of the interaction has now begun an Islamic training school for teaching those with hearing impairments. The process of bringing together multiple organisations has also provided a platform for further coordination and advocacy work. SEND stakeholders agreed that having data has strengthened their advocacy and awareness raising work on the rights of children with disability, and has helped provide a platform for policy discussions e.g. on national inclusive education policy.

The Country Director played an instrumental role in the introduction and successful delivery of the collaborative research approach. His leadership and mentoring was a critical for the dividends that are now being seen with regards to changing attitudes towards data and the emerging relationships between different stakeholder – as evidenced by testimony from research teams. A different office/team structure which empowered the Country Director to take up a more technical leadership role and balanced this with more in-country operations management support could have facilitated this approach from even earlier on in the programme.

The Fellowship programme has helped facilitate collaboration at state level as well as having personal impact on the individuals involved. Fellows gave examples of new skills that they have acquired and behaviours that they have sustained after the fellowship (for example reaching out to colleagues from different insitutions), but also greater appreciation of different ways of working across different institutions (also see Output 4 for more discussion on this). The fellowship scheme has had many secondary benefits as well, for example fellows have represented EDOREN at state level events and meetings when the central EDOREN team couldn’t travel. This has helped increased EDOREN’s visibility and exposure.

Capacity and Sustainability: There was feedback from some stakeholders that more could have been done to better support institutional capacity building. For example taking a more organisational approach with capacity development opportunities rather than the individual fellowships. Some stakeholders also queried if EDOREN could have had closer links from the outset with one or more Nigerian research institutions. On an individual level, those involved in research teams reported learning new skills around research methods that they could apply to future projects. Although most agreed that further external facilitation and funding would be needed for future studies to take place. Statekholders in DFID partner states were appreciative that other DFID programmes such as TDP and PERL were able to support follow up actions and response to research findings.

Lessons identified this year linked to this output and recommendations for future programmes
1. Investing in the collaborative research approach has led to demonstrable dividends with regards to capacity development and policy impact in the area of teacher policy in DFID partner states. Having the Country Director as a champion who set clear expectations for collaboration and who was willing to take some risks to mentor less experienced research teams has been central to this success. Future projects should be empowered by DFID to take similar risks investing both in collaborative processes as well as in the research outcomes, to better enable policy impact.
2. Having complementary mechanisms to situate thematic research, e.g. through institutions, other DFID programmes, fellows, or NGO networks, has provided a platform to support follow up and continued dialogue after research has been completed. Future programming would benefit from similar approaches while also better considering the role of media (including social media) in supporting the agenda on evidence to enable policy impact.
3. Ideas were muted both by EDOREN team and other stakeholders on the potential for EDOREN to have developed into an independent research institution and to have attracted funding from other sources to carry out it’s broader remit. If EDOREN had extended beyond this 5 year period such considerations should have been part of exit strategy options. In future, research programmes with significant individual and institutional capacity building objectives, should plan exit strategies from earlier in the programme.

Output Title	Education database, data tools, processes, and data reviews
Output number per LF		3	Output Score	A
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of data quality outputs completed (reviews, workshops with programme teams)	GEP3 community mapping survey review; ESSPIN LGA indicator database review; GEP3 survey review; DEEPEN baseline survey review; / Provision of school lists for NEDS2015; Nigeria Education Data Survey Out of School Children (OOSC) report finalised; / Support for Annual School Census (ASC) 2015/16 and 2016/17 including: 2 Zonal ASC questionnaire workshops; Support to three training workshops on UIS software; Linkage of 5 years of ASC data for EMIS states; Support for at least 3 workshops on improving quality and timeliness of 2015/16 ASC using UIS software; Support for 2015/16 joint ASC validation survey (ESSPIN/GEP); Dissemination of linked ASC data and school quality index (ISD); 2016/17 ASC support training workshops; Trial methods to improve ASC coverage of Private Schools; / Design of Schools Intervention database (SID) analysis tool; Dissemination of SID; Creation of School Quality Indices for all States; / Capacity building on use of data for Local government; State planners workshop and state planners; Kano and Jigawa EMIS workshop for LGA planners; Kano EMIS Workshop for state planners on more advanced data use; Lessons learned workshop for surveys and data gathering; Support for at least 3 workshops on Data Use for LGA Level planners; / Placement of DFID school survey microdata on NBS microdata repository. / E-Survey for factors affecting education;	All milestones delivered. / (Note: Milestones and priorities were frequently and adaptively re-prioritised; the list given here is the latest iteration from the project logframe.) / In addition, the team drafted a consolidated report on data initiatives (e.g. LEARN Nigeria, National EMIS), participated in a range of data-related workshops and stakeholders’ meetings including those called by Federal government Education MDAs, and / provided strategic support to DFID Nigeria on evidence and data to inform planning, and DFID results reporting.

Provide supporting narriative for the score

At the outset of the EDOREN programme, the education sector in Nigeria did not have a strong focus on data collection, analysis and use by academics and policymakers; the focus was more on qualitative research than using quantitative data and evidence. EDOREN was starting from a very low base and strongly contributed to the fact that there is now robust Annual School census trend data over 5+ yars across 11 states in Nigeria, there has been peer learning on data collection with other states and the Federal Ministry was able to publish a digest of data across all states in 2017, the first time in 3 years, which drew on improved data. EDOREN set out lessons learned from work done to support improved data in papers including – “Using data to improve education outcomes” and “Data on education in Nigeria: what is available and how can it be improved?”[3]
[3] See www.nigeria-education.org

EDOREN’s engagement with data quality in the Nigerian education sector leaves behind a substantially changed landscape. The data that has been collected has created awareness on the challenges of the education sector in Nigeria. A Permanent Secretary in the Ministry of Education in one of the EDOREN-supported States said:

“What is very striking about what EDOREN is doing is that it exposes the weakness of the Nigerian education system and to be specific the north-western part of Nigeria. Until the coming of EDOREN not many policy makers were aware of the problems in the education sector in terms of quality teachers, instruction materials and learning outcomes. The coming of EDOREN has opened up many of these issues.”

A stakeholder who participated in training workshops in Kano, Kaduna, Jigawa and Bauchi, Zamfara, Katsina and Niger affirms that EDOREN has institutionalised evidence-based planning saying:

“When you train a planning officer and that planning officer trains officers in a Local Government Area (LGA), the whole planning in that LGA will change”.

Quality assurance of data: EDOREN demonstrated flexibility in providing short-term strategic support to partners in providing external quality assurance in range of data areas, often at short notice. For example, EDOREN supported the finalisation of the Ministerial Strategic Plan (2016-19), including support on data, costing and monitoring and evaluation.

Collaborative work on education data systems: EDOREN worked together with UNICEF to support the external review of education data systems across Nigeria. This joint working has been an important way of demonstrating development partner collaboration on data. EDOREN also contributed to DFID’s thinking on data for the planned new education programme and to other development partners’ thinking, particularly the World Bank, on the data and monitoring and evaluation needs of future programmes. In response to broader stakeholder questions about Nigeria’s Out of School Children (OOSC) data, EDOREN produced a report getting under the skin of existing household data (the Nigerian Education Data Survey (NEDS) to be able to set out in more detail what we know about OOSC numbers and patterns and what this means for policy in these areas. In addition, a study on teacher tracking in Borno state (under output 2), was carried out under the leadership and with strong inputs from EDOREN’s data workstream over the past year. Throughout the programme, the data workstream has contributed to all evaluations (see also output 1) and a large proportion of other research (see also output 2) undertaken by EDOREN, which translates directly to the success of the programme’s higher-level outcomes.

Annual School Census (ASC) and Education Management Information System (EMIS): EDOREN has worked closely with ESSPIN and GEP3 to support the ASC, taking a leading role for coordinating on a new EMIS tool, and creating from scratch the Integrated Schools Database (ISD) as a comprehensive data resource building on ASC and geolocation data. For the first time, the ISD database provides longitudinal data on 23 core education indicators in an easily accessible format to researchers, policy makers, implementers, and donors and is linked into the UNESCO Institute for Statistics (UIS) software for education data collection and analysis. EDOREN has also made inroads advising the National Bureau of Statistics (NBS) and NEDS on data quality. EDOREN has helped demonstrate that a rich data set can be continuously developed and integrated. Over the last year, EDOREN has made a more dedicated effort to strengthen Nigerian capacities for the use and understanding of the ISD database, and ASC data. In a series of workshops for State and FME planners, the team has focused strongly on practical applications. In the process, a Nigerian specialist was trained specifically to support similar workshops as well as the continued collection of future ASC data.

Sustainability concerns: There are serious concerns about losing continuity for ASC and EMIS data; Kwara and Enugu (which no longer have DFID Nigeria bilateral funding following the end of ESSPIN in January 2017), both failed to commence their 2016/17 ASC activities due to budget constraints. Both Ministries directors of planning gave their commitment to the exercise and there was a commitment from each core EMIS team who had the necessary skills available to carry out the exercise, but adequate budgets could not be released by the respective State Governments at a time of very low oil prices. EDOREN considered supporting questionnaire printing but it was felt the two states would still have insufficient resources to carry out a quality exercise even with this catalyst. Lagos completed their ASC exercise late not allowing sufficient time before the end of EDOREN to complete ISD and ISD+ (time series data on composite indicators generated from the ASC data) roll out for 16/17 for the State.

Lessons identified this year linked to this output and recommendations for future programmes

1. Consider in future programmes, the balance in investment (and likely use by policymakers) between ASC/EMIS data and large-scale evaluations to ensure appropriate levels of investment in both.
2. Ensure strong alignment between different donor funded support programmes on data.
3. Focus future programming on stronger use of data alongside improved approaches to generating data and ensure adequate attention is paid to effective communication of findings from data in various ways and to various audiences.

Output Title	Derived knowledge and dissemination products
Output number per LF		4	Output Score	A
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Percentage of planned communication processes delivered	Two quarterly DFID N education portfolio meetings (2014); / 100% of outputs set out in agreed policy impact workplan completed on time (including agreed contributions to DFID strategy); / 10% year-on-year growth of nigeriaeducation.org website hits (2015-2018); / 80% of agreed fellowship-related communication processes delivered; / NAEC 2017 Conference held.	All milestones achieved (though not always on time) / All dissemination outputs delivered – of 70 outputs on June 2016’s plan, 25 pertained to years beyond March 2017 (in the expectation of EDOREN’s extension), 12 were obsolete due to changes in DFID programmes and DFID priorities and the remaining 33 were delivered. / Overachieved on year-on-year growth of www.Nigeria-Education.org website traffic: 61%, from 15,868 visitors in the year to March 2016 to 25,853 in the year to March 2017.
Number of individuals participating in and demonstrably benefiting from capacity enhancement activities	Number of Nigerian researchers trained on education research.Targets: / 2014 = 20; 2015 = 50, 2016 = 20; 2017 = 20; 2018 = 43 (33 TR5, 10 TR6) / Number of Nigerian government officials attending EDOREN dissemination workshops or meetings on education research. Targets / 2014 = 20; 2015 = 50; 2016 = 50; 2017 = 50	All achieved / Regularly trained numbers of researchers in excess of logframe targets and held data workshops for officials in target states in significantly greater numbers. / (e.g. 20 researchers in Teacher Study; 8 researchers trained in Conflict Study (not counting use of Girl Effect TEGAs); total number of state and local government participants at “Use of data” sessions in DFID partner states – 138 in 2017 alone).

Provide supporting narriative for the score

EDOREN delivered all milestones associated with this Output which focuses on use of knowledge and includes work done across all Outputs and with tangible products, processes and an established national education conference. Over the five years of the programme, there has been a recognition of the need to move from dissemination through to research uptake that influences policy changes. Some of the ways EDOREN has begun to demonstrate this include:

Products: EDOREN has made professionally designed outputs available in accessible and engaging ways – reports for dissemination, presentations, policy briefs, and blog posts in both hard copy (print) as well as on the website. The latter shorter presentations, policy briefs and ppts were mostly made available in the last year of the programme as a result of the May 2016 policy impact assessment.

Website: EDOREN has built, maintained and disseminated a growing database of relevant education research on the www.nigeria-education.org website which has attracted an increasing number of visitors. This website will remain accessible for three more years as a pro-bono contribution by OPM. This will ensure that a window is provided to make research products accessible to the public until DFID’s successor education programme comes onstream to further drive the use of this evidence. Despite the increasing number of visitors to the website, there was a view expressed by several stakeholders interviewed by EDOREN for the “Contribution Studies” that the website was not known about beyond the “inner circle” of stakeholders. In addition, the organisation of website and tagging could be improved to make easier navigation, especially for searching for summary reports/syntheses. EDOREN also supports http://www.naec.ng to redirect traffic pertaining to Nigeria’s Annual Education Conference (NAEC) to the relevant pages on Nigeria-Education.

Nigeria’s Annual Education Conference (NAEC): a key route for the dissemination of research has been the NAEC which took place in 2015, 2016 and 2017 and involved around 200 stakeholders each year. This involved a diverse group of stakeholders including policymakers, academics and practitioners and has taken place through a partnership involving EDOREN, the British Council, World Bank, USAID and DFID education-funded education projects, UBEC and the FME. Planning for the 2018 conference is underway by a joint planning committee led by the FME and supported by the British Council and other partners demonstrating its institutionalisation and sustainability of this conference beyond the EDOREN programme into the Nigerian education system. The NAEC has drawn high levels of engagement (e.g. the 2016 keynote address was delivered by the Vice-President of Nigeria). The FME’s commitment to continuing the conference is demonstrated in the clear role of the Planning Department in organising the conference and a new budget line created in the FME’s budget to support the conference. On this regard the FME highly valued EDOREN’s supportive approach that gradually built up ownership of the conference and ensured that the FME “remained in the driving seat”. Inputs from the NAEC have been taken by the FME to the Joint Consultative Council on Education (JCCE) and the National Council of Education (NCE) to guide implementation. In addition, EDOREN has produced a manual with step-by-step approach to preparing for this conference which will be useful future conferences.

Innovative approaches to research uptake: EDOREN’s innovative approaches to ensuring evidence uptake informed the decision to create EDOREN fellows and research teams with participants cutting across academia, private practice and government ministries, departments and agencies (see output 2 for more detail on the research teams).

Fellowship programme: The EDOREN Fellowship programme lasted for 8 months (from July 2017). Three EDOREN fellows were selected from the Kaduna State University (KSU), Kaduna State Ministry of Education (KSMoE) and the National Teachers Institute (NTI) in Kaduna and they have been instrumental in promoting EDOREN’s objectives at their respective organisations. In the case of the KSU and KSMoE fellows, this involved a job swap between a KSU lecturer and a KSMoE Assistant Director of Planning, Research and Statistics. The KSU lecturer spoke of how the KSMoE has been using the data generated through his EDOREN fellowship to influence into some of its policies. An example was that the KSMoE did not have any recruitment and development policy but when it saw the outcome of the research by EDOREN, it quickly drew on this to ensure there would be improvement in the recruitment and deployment of teachers across the State. The fellow at NTI was able to deliver the “Teachers Knowledge Fair” which brought organisations with a demand for evidence (Teachers’ Registration Council of Nigeria, National Open University of Nigeria, UBEC, National University Commission, etc.) and those who supplied evidence (donor organisations, donor-funded programmes, etc.) within education in Nigeria. The Fellowship Programme ensured collaboration between academia and the government towards ensuring that data and research feed into policymaking and that academia is able to answer research questions that will be used by the government to inform policy and service delivery. A key result of the Fellowship Programme has been that it has enabled individuals to become champions for evidence production and use within the education system of Nigeria irrespective of EDOREN’s exit. The programme would likely have produced more fellows and research if the EDOREN programme had not been curtailed.

Collaborative research: EDOREN has demonstrated an ongoing commitment to involving Nigerian researchers, increasing the number of national teams carrying out research activities for the programme particularly in the context of qualitative research and its thematic research workstream (output 2). State-level research capacity strengthening teams combined of policymakers and academics have helped to bring different stakeholders together who have not traditionally worked together. The research teams cut across five themes but worthy of mention is the Special Education Needs and Disability (SEND) research team working in three states, which also included civil society and media stakeholders as part of the team and therefore provided a platform for dissemination and research uptake from the outset.
Learning how to gather, process and use data is by far the most outstanding lesson respondents mentioned when interviewed for “Contribution Stories”. Several of the researchers particularly mentioned the way EDOREN helped them with extending their knowledge in qualitative research. They tell of how engagement with EDOREN has practically built the capacity of researchers to do what they referred to as very meaningful qualitative research that helps those involved find solutions to problems. Stakeholders highlighted the opportunity to have been exposed to step-by-step training in this regard; the development of the protocols, interview guides, collecting the data, transcribing them, printing them, and report writing.

Attitudinal and/or policy change: Through its capacity building activities and research collaboration, the EDOREN programme is beginning to see evidence of changed attitudes through increased awareness and use of data and evidence. Looking beyond dissemination to research uptake that has the potential to influence policy changes, EDOREN has increasingly engaged with State and Federal decision makers, and a policy impact workstream was created during 2016 to address this. The EDOREN “Contribution Stories” point to some examples of ways in which these studies have influenced the actions of others and in some cases, are starting to influence policy, for example:
- Increased awareness of the need for a dedicated policy for special needs education among some stakeholders
- Teacher training in some States on special needs education by the FME
- The establishment of a private college of education with separate female and male campuses to encourage women to attend by a researcher after exposure to the topic of girls’ education during EDOREN research
- Support to the Ministerial Strategic Plan in 2016
- Support to State teacher policies in 2017 and 2018 - Kaduna teacher recruitment policy drafted; Kano finished drafting and taking to State Assembly, and Jigawa has started drafting

These outcomes are quite important to note given the need to recognise the large size of Nigeria’s education system and the relatively modest size of the EDOREN programme by comparison.

Lessons identified this year linked to this output

Knowledge management and dissemination could have been stronger and more embedded in the programme from its outset: EDOREN’s “Contribution Stories” as well as previous annual reviews, demonstrate a belief that EDOREN’s knowledge management and dissemination strategy were the weakest part of an otherwise strong programme. This includes a perception that the website was not widely known about or disseminated beyond the “inner circle” of education stakeholders or outside of the EDOREN focus States. In response to last year’s Annual Review recommendations EDOREN did facilitate additional workshops, consultations and activities with stakeholders, and reached out to new media and civil society partners (e.g. BudgIT) to promote broader awareness and engage with advocacy groups. Some of the latter activities may have come too late to have had significant impact. Having a clear communications strategy and a dedicated person in the EDOREN team having responsibility for implementing the strategy could have increased awareness and uptake of the research.

EDOREN could have more consciously reflected on lessons learnt from dissemination and from DFID-N’s FOSTER and PERL projects to improve and tailor it’s approach on communications, for example recognising the power of a story to illustrate findings and that in Nigeria this is what will often be repeated after a presentation rather than a fact or figure. There are some examples of EDOREN doing this in workshops and in evaluation reports including photos of student’s work and teacher’s assessment to demonstrate what levels of competency mean in practice was powerful. With additional in-country communications capacity, even more could have been achieved in creative communicatons and tailoring of messages.

Recommendations for future programmes
1. A communications strategy should be developed during the inception phase of any new programme with dedicated in country communications expertise leading on the implementation and rollout of the strategy from early in the programme.
2. There should also be synergy between communications efforts related to use of evidence in research and evaluation programming and comms expertise in main delivery programmes
3. DFID should ensure that any successor programme further drives the use of the evidence created from EDOREN.
4. A comment on evidence uptake by the GoN was “to improve evidence uptake, technical support should be given to government personnel to ensure they can deliver the identified recommendations”. Since most of DFID’s programmes make recommendations for various institutions within the GoN, it is important that DFID gives this due consideration in looking at research update in future programmes and ensure any potential changes to policy do result in changes in practice.
5. Fellows recommended that any future fellowship lasts a full year and includes sufficient time for training/induction at the beginning of the fellowship. The fellow at NTI, having requested to stay in her institute rather than doing an exchange, reflected with hindsight that an exchange would have been more effective and allowed for a more manageable workload.
6. Research teams that include both academics/researchers and policymakers but also extend further to representatives from civil society and the media, could help to further embed evidence in policy and practice.
7. The majority of EDOREN’s overall budget was allocated to large-scale evaluations of DFID programmes; a much smaller proportion was allocated for research uptake to achieve logframe higher-level outcome 2: improving policy implementation in Nigeria’s education sector. EDOREN has started to achieve traction on policy impact in selected States with relatively modest means. Any future programme should consider both the relative budget allocation as well as the timeframe required to bring about change in policy and practice which may be quite substantial after the production of data, research and evidence.
8. Future programming should re-look at the balance of emphasis between the different outputs of EDOREN as set out in the weighting of the Programme with more weighting to be given to work involving data and communications that is currently the case under EDOREN.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The EDOREN project has two central objectives:
1. To embed research, evaluation and learning in DFID’s education sector support in Nigeria. This involves adding value to, and improving the performance of, DFID Nigeria’s (DFID-N) current basic education sector portfolio; and informing DFID-N’s education strategy by synthesising and interpreting the evidence and knowledge gained from current projects, EDOREN’s independent research, and relevant comparative research.
2. To enhance national capacities to generate and use quality educational data, research and evaluation for policy and strategy making. This requires all EDOREN activities, whether in support of the DFID-N education portfolio or separately, to apply well-articulated approaches to the development of individual and/or organisational capacity. It also entails working with stakeholders and partners to increase both the demand for and the capacity to supply high-quality educational data for policy-making. This aim is underpinned by EDOREN support and initiatives for improved data collection and management across a range of stakeholder programmes.

The EDOREN Theory of Change and logframe captures these objectives in 2 higher-level logframe outcomes – i) Improved DFID Education Portfolio Performance and ii) Improved Education Policy development and implementation and 3 intermediate outcomes - i) Outputs are used by DFID and DFID education portfolio programmes to improve portfolio design and implementation; ii) Outputs are used by state and federal governments to improve education policy design and service provision, iii) Education data collection and analysis in Nigeria is improved in key states; and 4 output areas (discussed in the Output sections above).

The programme was conceived in a data poor environment with little awareness of learning outcomes or teacher competencies and needs, and immediate needs to improve quality of data reporting and use in DFID-N’s other education programmes. There has been a shift over the last 5 years, supported by EDOREN, into an environment with better awareness of results and demand for evidence to inform decision-making. In line with this transition the balance between EDOREN’s objectives shifted from a predominantly internal focus on performance of DFID-N’s programmes (high at the outset), towards the second more external objective in improving capacity to generate and engage with evidence. This has influenced both what and the how EDOREN has delivered activities within it’s scope, with an increasing focus on sustainability, capacity building and facilitating attitudinal and behaviour change on the use of data and evidence over the course of the project. EDOREN has also sought to capitalise on it’s convening power and dedicated time to build networks and relationships to continue collaboration. This is most notably seen in the recent thematic research approach, but also in another aspects of EDOREN’s activities such as Nigeria’s Annual Education Conference.

The project was initially conceived as an 8 year programme and evidence from similar programmes working on these issues demonstrates that it takes significant time to embed the kinds of achievements expected at the highest levels of the logframe. On higher level logframe outcome 1, while the DFID Nigeria bilateral education portfolio has scored well in Annual reviews and support to systems in areas such as SBMCs and teacher development in the North and access to finance in private education markets are improving, overall learning outcomes in areas supported by DFID Nigeria programmes remain static in the time EDOREN has supported evaluation efforts. With regard to higher-level logframe outcome 2, while there were “green shoots” emerging in relation to recognition amongst DFID partners states as to the importance of teacher workforce issues and in Lagos with regard to the importance of rules and standards, by the time of project closure, these changes are not fully embedded in the target states. EDOREN’s achievements are strong at Output level (as discussed above). There is solid evidence on the achievement of each of the 3 intermediate outcomes e.g.
1. Outputs used by DFID and DFID education programmes – Somewhat achieved. EDOREN outputs influenced some aspects of programme implemention. For example, the TDP baseline and midline provided evidence that led to TDP doing more work on Hausa language, greater focus on training all teachers at school level not just some teachers as previously planned, greater focus on reading competencies, going beyond broader support to teaching the subject curricular. In DEEPEN, EDOREN’s work influenced DEEPEN to drop planned Access to Finance interventions on mobile money and parents savings. In GEP3, EDOREN’s work contributed greatly to improved data systems, evidence to redesign the programme and an evaluability assessment – all of which put the project on a stronger footing following Minister’s decision to redesign the project. However, EDOREN and the projects own reflections highlight that EDOREN’s influence was perhaps not as deep as it should have been, partly due to the fact that there was often a significant time lag between when surveys for the quasi-experimental evaluations were conducted and when results became available to feed into programme implementation. Greater focus on other types of research and evaluation for the programmes such as operational research, process evaluation and real time learning would have provided better opportunities for ongoing testing, learning and influencing for programming impact. This learning on approaches towards evidence generation for programming has been fed into the design of the planned new flagship education programme and EDOREN outputs have strongly influenced the overall design of DFID’s planned new flagship education programme.
2. Outputs are used by state and federal governments to improve education policy design and service provision – Somewhat achieved, with evidence on teacher policy emerging from the collaborative research. It is less clear how other thematic and comparative studies have influenced policy design and service provision.
3. Education data collection and analysis is improved in key states – Somewhat achieved with evidence in use of Annual School census and ISD data to support planning and implementation in states (see discussion on Output 3 above).

The review team was of the view that more time and greater focus on dissemination and communications if the programme were continued, would have yielded greater achievement of outcomes. The value of EDOREN therefore, goes beyond project closure and these efforts will now be taken forward by DFID Nigeria, including under the planned new flagship education programme.

Summarise the programme’s theory of change and major changes to it in the past year

EDOREN’s theory of change is set out in the diagram below. The ToC and logframe were significantly revised in 2015/16, with a reduction in output areas from 6 to 4 and clearer articulation of capacity development and policy impact as cross-cutting. No subsequent changes were made to the ToC, except the agreement of key milestones to the end of the programme following the contract extension from April 2017 to June 2018.

Explain major changes to the logframe in the past year

N/A

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

EDOREN did not have an original business case - it began as a component under GEP3 in 2013 and was created as a standalone project in ARIES in 2015 with funds from all DFID Nigeria education projects - so direct comparison with the proposition in the business case cannot be made. EDOREN had a VfM strategy in place from 2015. A VfM assessment was undertaken during 2018 towards the end of the programme which limited the ability to fully reflect and improve VfM throughout the programme.

One area which should be taken on board for a future programme working on data, research and evaluation, is the impact of such work on the VFM of other projects. DFID Nigeria education projects (TDP, DEEPEN) have consistently met expectations at output level, mainly scoring A at Annual Reviews. Most notable is the case of GEP3 which had significant challenges with data. EDOREN’s efforts to support the data, redesign and evaluability of GEP3 from 2013-2015/16 contributed to the project scoring improving from a C in 2014 to a B in 2015 then As in 2016 and 2017[4]. These efforts were not quantified in the final VFM assessment of the programme but should not be underestimated.
[4] More recent challenges faced in results delivery by GEP3 in 2018 have occurred because of a slow down in results delivery, partly linked to staffing challenges and not because of problems with the project design.

The final VfM self-assessment rated EDOREN’s overall VfM as good[5]. Economy was ranked as excellent, with efficiency, effectiveness and cost-effectiveness all being ranked as good. The basis for these judgements, taken from the VfM assessment, is summarised below.
[5] EDOREN – Final VFM report, June 2018

VfM criterion	Evaluative judgement	Basis for judgement
Economy	Excellent	Previous Annual reviews demonstrate that the project has done well with regard to economy indicators. There has consistently been good practice to manage key cost drivers, secure savings, and keep costs down. These efforts ensured that key input unit costs were consistently below agreed benchmarks. For example, the average costs of key inputs such as fees for national and international personnel, remained flat over the 5 year period, despite general inflation over the period. The project actively sought savings such as cost sharing with other DFID Nigeria programmes, altering the scheduling of activities to help reduce costs and increasing use of Nigerian nationals (rather than internationals) over time, e.g. in thematic research.
Efficiency	Good	EDOREN deliverables generally met the required quality and timeliness within budget, and the programme has been managed adaptively; but there was a small shortfall against targets and some internal delays, some reports received the amber rating from EQUALS, and the ratio of national to international consultants dropped off in Years 4 and 5.
Effectiveness	Good	EDOREN has documented many examples of ways in which the DFID-N portfolio and federal and state governments have used its outputs to guide decision-making, has adapted and improved in response to learning, and has generated learning for future education programmes; but uptake has been limited by questions about evaluation design and time taken to disseminate findings, and limited engagement, reach and visibility at policy level.
Cost-effectiveness	Good	EDOREN has made significant progress towards its intended higher-level outcomes, particularly given contextual difficulties and challenges, and has helped to enhance the VfM of other DFID and governmental initiatives; but there are deep concerns over the sustainability of EDOREN’s work stemming from the early curtailment of EDOREN’s timeframe, which is outside of EDOREN’s control.
Equity	No judgement	As EDOREN does not directly target specific groups, an evaluative judgement has not been made against the equity criterion.
Overall programme VfM	Good

Regarding equity, the VfM assessment outlined how EDOREN evidence called attention to equity issues for DFID-N education programmes and for wider use by Nigerian policymakers:

- Providing gender-disaggregated data and gender analysis of issues of access, the school environment, teacher behaviour and learning outcomes (e.g. in the GEP3 mid-line study);
- Providing analysis on the capacity of the programmes to reach poor and very poor children (e.g. in the TDP end-line study);
- Providing analysis of other characteristics which may affect learning outcomes, such as language spoken at home (e.g. study on BRIDGE schools in Lagos);
- Highlighting demand-side barriers to uptake of schooling among vulnerable groups in several studies (e.g. social norms and household responsibilities which affect girls’ ability to go to school, and the need for the poorest children to work during the harvest);
- Recommending how the DEEPEN challenge funding could be used by DFID to optimise teaching quality in low-fee private schools in Lagos state (in the study on BRIDGE schools);
- Recommending ways to improve access of people with disability to basic education in Nigeria through better management and implementation of the policy on special needs and disability (SEND study); and
- Recommending ways to increase primary school attendance and the quality of basic education in the state of Borno in the wake of violent conflict.

A summary of other key findings from the VfM assessment is provided here:

VfM assessments are of most use when they meet the dual purposes of programme learning and accountability. Under EDOREN, only one VfM assessment was undertaken towards the end of the programme limiting any ability to improve VfM over the programme’s life. For future programmes, scheduling VfM assessments throughout the programme’s life can help to provide early and regular diagnostics on economy and efficiency ratios and drivers, and later checks on the likely achievement of results commensurate with the level of investment.

Anticipated outcomes should be realistic and in line with a programme’s timeframe and level of investment. If the timeframe and/or budget change during implementation, outcomes should be revised accordingly. EDOREN was originally established as an 8-year programme and was then shortened to 5 years. The outcomes were not revised which makes it difficult to determine at what level EDOREN has achieved VfM.

There are VfM questions and potential trade-offs linked to the changes in the design of evaluations that took place during the EDOREN programme. For example, a decision was made to cancel the DEEPEN mid-line and end-line studies and replace them with smaller-scale and less expensive qualitative studies. Whilst this created substantial savings and produced studies that were better aligned with the needs of the programme, this made the baseline study obsolete (beyond its value as a situation analysis) and therefore a potentially unnecessary expense. This raises a question about the trade-offs in VfM (absolute v relative and how to quantify these) during a programme that is adaptable and flexible.

EDOREN has demonstrated some examples of research uptake that has started to influence policy and practice in both the FME and in focus States. Key examples are the continuation of the NAEC by the FME and the development and implementation of teacher policies related to the identification, recruitment, deployment, training and retention of teachers in several states. During the final year of the programme, EDOREN has strengthened efforts to disseminate its findings widely to policymakers in tailored accessible formats, to increase traffic to its website, to engage key government stakeholders in the application of findings and conducted useful research on the factors which facilitate evidence uptake.

EDOREN’s “Contribution Stories” nevertheless indicate that visibility and reach have been low. This is important, as the VfM of research and evaluation is reduced if key stakeholders do not use (or only use in a limited way) the findings to influence changes in policy and practice. This has potentially resulted in a reduced contribution to EDOREN’s higher level outcomes (but see caveat under point 2 above). Deliberate attention and detailed planning for research uptake from the beginning of the programme could have helped to ensure greater VfM in this respect.

These learnings will need to be taken forward by DFID Nigeria into planned new programming.

E: RISK

Overview of programme risk
The risk for this programme was originally assessed as medium. In the last two years, the risk assessment has been updated using the new DFID risk rating system, and is now assessed as minor. This revision is in consideration that EDOREN is a research programme and not involved in day to day delivery of programming in states and local governments. A good amount of the work of the programme including the conduct of research and evaluation is within the control of the programme although the project does work with other projects and government partners and sometimes there have been delays in delivery of specific tasks due to issues outside the control of the project.

Risk management over the life of the programme has been robust. Risk was managed through reviewing the programme risk matrix at DFID’s quarterly programme meetings. The programme risk register was updated following quarterly meetings and mitigation strategies were implemented. No major issues arose during the year. EDOREN should be noted for the level of attention given to Safeguarding risks. When a Safeguarding issue was identified during a survey, OPM flagged it up with DFID and the project concerned and the risk was addressed in ways which are providing learning on how projects can handle safeguarding risks which arise in contexts not directly controlled by them (in government schools). As EDOREN has reached its end, there are no remaining programme management or delivery risks.

However, it should be noted that the risks of sustainability of programme efforts and risks associated with limited delivery of higher level outcomes remain. EDOREN set out mitigations for these risks to the extent it was able as set out in the EDOREN Sustainability strategy and the review team judged EDOREN’s efforts in this regard as good. There will be a need for DFID Nigeria to pick up the need to address these risks by adequately taking on board the work done and lessons learned from EDOREN in future programming, under the planned new flagship education programme currently going through DFID Quality Assurance and approval processes.

Update on partnership principles

The Partnership Principles were not considered within the project business case. In September 2014, DFID Nigeria conducted an assessment of the Federal Government of Nigeria commitment to the Partnership Principles which reconfirmed the UK’s declared policy that no UK aid money should go directly to the Government of Nigeria: as an anti-corruption measure and to avoid substituting for the country’s own resources. TDP is consistent with this policy. As the programme is delivered directly by an implementing partner with no funding through government channels, the Partnership Principles are not relevant for the direct management and monitoring of this project. However to attain impact and sustainability, TDP will need to leverage government resources and ensure that project interventions are scaled up through government systems.

There may be a role for the partnership principles to inform project implementation in future years. In particular State Government commitment to reducing poverty and attaining the MDGs, to strengthening financial management and minimizing corruption, and to strengthening domestic accountability may be considered when determining the level of investment the project makes in each State, with greater resources directed to those States that demonstrate greater commitment to the partnership principles. Hence the role that the partnership principles should play in project design, management and monitoring will be reconsidered in future reviews.

Asset monitoring and control

All items belonging to the project are listed in an asset register, which is regularly checked and updated. Asset reports are created by a non-EDOREN OPM staff member in Abuja and verified by Country Director. DFID conducted an annual comprehensive financial audit of OPM’s management of EDOREN, including a review of the asset register, and reported no “material findings”, i.e. no substantial problems of discrepancies.

As part of project closure activities, the assets disposal process included putting together a robust assets disposal plan which was approved by DFID Nigeria and assets disposal conducted in line with DFID’s asset disposal guidance.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
EDOREN has now completed 5 years implementation phase (September 2013 - June 2018), during which time the project delivery plan has been adjusted in close cooperation with DFID. Adjustments have been made to take into account changed circumstances, emerging priorities and the new project structure, for example, EDOREN had been conceived as an eight year programme; the second phase after the initial four years was curtailed to a single year, ending in June 2018.
EDOREN had quarterly milestones. These were agreed with DFID at the beginning of each project year and aimed to cover all output activities and significant deliveries in the workplan. The project plan as well as planned budgets and payment milestones were reviewed each quarter, with a mid-quarter review on progress towards milestones. Deliverables were generally delivered on time and to a high quality.
At the end of year four of project implementation, EDOREN underwent a contract and budget extension until March 2018 to formalise the outcome of the Portfolio Quality Review (PQR) and a subsequent zero-cost extension to June 2018. This took the overall project budget from £6,788,336 (as agreed in the previous budget extension in May 2016) to £9,638,268.25. The decision to only extend EDOREN by one more year rather than the 4 years initially envisioned was a reflection of DFID Nigeria portfolio direction, including the decision that future work to achieve EDOREN’s outcomes would be incorporated into the design of the new flagship education programme. The decision was not a reflect of the project’s performance.

OPM’s consortium partner for EDOREN is the Institute of Development Studies (IDS) of the University of Sussex. IDS’s role has included knowledge management and dissemination aspects, but since 2016, has been re-defined more narrowly to focus on a core competence that OPM and the EDOREN office in Abuja cannot perform themselves, which is the technical maintenance of the EDOREN and Nigeria-Education.org website. By increasingly using OPM’s own expertise and communication teams, as well as a further shift of activities towards Abuja, and local service providers, EDOREN has kept communication and dissemination costs down, and moved responsibility for dissemination closer to key stakeholders in Abuja. However, there are recommendations for how communicatinos could have been better in the Project (see discussion under Output 4 above).

DFID’s partnership with EDOREN is positive and DFID finds the programme to have been flexible and responsive, particularly in dealing with the uncertainty associated with the Programme’s future and the need to reprioritise activities and reduce budgets in the last year of programme implementation. Working relationships between EDOREN and other DFID Nigeria projects are positive and EDOREN proactively engaged well with the PERL(Governance) programme to support greater roll out of its research and policy impact agenda and as part of broader sustainability efforts. Protocols for ways of working between EDOREN and other programmes over the course of the programme life and the Organisation structure recognising the role of Workstream leads responsible for interactions with Programmes, were fit for purpose. Partnerships with the wider research community, varied in intensity but were also productive. EDOREN intensified its relationships with State Ministries and SUBEBs and with Academic institutions over the past year and stakeholders judged these to be productive relationships.

The EDOREN Theory of Change was updated in 2015/16 to reflect greater focus on policy impact. While the use of workstream leads was generally fit for purpose, in hindsight, more could have been done to review staffing and team structure so that the project had a stronger Abuja based presence. The importance of on the ground staffing for projects of this nature should be taken on board in future programming.

FINANCIAL PERFORMANCE
EDOREN worked well with DFID to respond to the requirements from DFID Nigeria to provide highly reliable accurate forecasting and financial data.
Expenditure on the programme was monitored and reported quarterly and in annual reports. Expenditure over the lifetime of the project has been close to the budgeted figures; budgets and forecasts were continually adjusted in collaboration with DFID, to enable adaptive management and flexibility, while staying within the overall contracted value. Savings were dynamically re-allocated towards additional activities, to enable maximal impact and value for money.

Overall EDOREN has responded well to DFID’s instruction to maintain monthly variances in expenditure against budget within a 5% margin in Q1 – Q3 and 2% margin in Q4, as well as the directive to spend 90% of annual budgets by end of the third quarter, which has influenced the timing of key activities including survey work. Issues of concerns related to delayed invoicing at some point in the project year was responded to positively.

The Programme audit cycle is annual, in line with the project closure and to provide audit opinions on financial transactions and assurances on the use of funds for intended purposes. Baker Tilly was commissioned in May 2018 to conduct full and satisfactory independent financial and programme closure audit of the Education Data Research and Evaluation in Nigeria (EDOREN) for the period 1 April, 2017 to 30th June 2018.

The draft audit report, received on 14th September 2018 suggested that the Statement of Receipts and Payments, showing the receipts and payments made by EDOREN for the period 1 April, 2017 to 30th June 2018 was presented fairly in all material respects, and in conformity with the basis of sound accounting policies and practices. The audit opinion expressed in the draft seen by the AR team at the time of submission of this Annual Review is an unqualified one, which implies that no material weaknesses that could impact adversely on delivery of programme objectives were observed.

The draft audit report found that OPM-EDOREN complied with recommendations from the last audit exercise which implies that OPM-EDOREN is committed to improving its systems of internal control. A Management Action Plan has been drawn up by the external auditor and this will be finalised in a tripartite closeout meeting between the auditors, OPM and DFID.

Date of last narrative financial report	June 2018
Date of last audited annual statement	September 2017

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Progress was well monitored throughout the programme with the Lead Adviser and SRO having adequate oversight via quarterly reports and milestone reportings. There were also intermittent check-ins to resolve burning issues during the lifetime of the programme. Given other DFID projects were some of EDOREN’s primary beneficiaries, feedback was obtained regularly through Adviser’s engagement with other projects, including quarterly meetings and were used to respond to issues.

EDOREN’s logframe was comprehensive and was the key vehicle to monitor progress on achievements with new targets set where necessary annually up to final year of the programme. Due to the peculiarity of the programme which was aimed at addressing DFID changing needs, programme’s flexibility was also essential to its success. Quarterly payment milestones were linked to logframe milestones. Particular monitoring processes were also developed for the outputs focused on thematic research and fellows as regards their capacity development. Learning was incorporated from DFID’s research and evidence team on research uptake and best practice of monitoring within research programmes in developing the logframe.

The PCR field visit was conducted from 25 – 29 June by a team including a results/statistics officer, DFID Education adviser, an external consultant and a DFID programme manager. The review involved engagement with and input from DFID Education advisers, the EDOREN team, meetings and interviews with a wide range of stakeholders including federal, state and local government officials in addition to research team members and fellows who were instrumental to the success of certain aspects of the programme. The review also included a critical review of a large number of documents and reports as well as the ARIES self assessment report. EDOREN had its end of programme dissemination event during this week as well which was also useful and helped facilitate the meetings.

Evidence

One of EDOREN’s objectives was to focus on evidence supply; to this end, it has produced databases (State Intervention Database) and presentations – studies, research reports, evaluation reports (baseline, midline and endline), etc. most of which have been included on the www.nigeria-education.org to ensure uptake by relevant stakeholders even after programme closure. EDOREN has also had a commitment to open data for example ensuring that microdata has been made available through National Bureau of Statistics for further use by others, and a state and LGA level building significant capacity to access and use available ASC data.

Contribution stories and case studies became the primary vehicle to monitor policy impact and capacity development. Signficant efforts were made at the end of EDOREN to capture these examples and learn lessons, with dedicated resources brought in to facilitate this. In addition when there was an in-country Research Officer in post this role was used to develop tools for stakeholder feedback and support write up of case studies. Yet through interviews with stakeholders many additional individual stories and anecdotes emerged, particularly on the individual impact of mentoring or workshops. More systematic efforts and allocated resources could have been made through the lifetime of the project to more routinely capture this evidence of research uptake, use and capacity development e.g. synthesising feedback that was obtained after workshops or events and capturing this withing quarterly reports or case studies.

## Smart Guide
## The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.
The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (eg related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the logframe. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Signifcant changes to logframe indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.