Type of Review: Annual Review 2012

Project Title: Consolidating Science Journalism in Africa and the Arab World: SjCOOP-II

Date started:	SjCOOP II: 1st January, 2010
Date review undertaken: 4th – 7TH Feb, 2013

Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID contributes £1,900,000 from 1st January 2010 to 31st December 2013 to the World Federation of Science Journalists for SjCOOP II, the second phase of this programme. Joint financiers include: Directorate-General for International Development, Dutch Ministry of Foreign Affairs (DGIS); and the International Development Research Centre (IDRC). / SjCOOP I was undertaken between July 2006 and August 2009, and the DFID contribution to that phase was £481,452.96.

What are the expected results?
This project will help to improve the reporting of science and development issues such as health, climate change and environment, by journalists in Africa and the Arab World. The programme will also help establish national and regional associations of science journalists to ensure ongoing support of science journalists at national or regional level after the programme completes. / People in developing countries will have access to accurate and understandable scientific information that could improve their lives. More science journalists will write more stories about science, which in turn will develop better public understanding for science, and increase pressure on developing country governments to base their policies and decisions on scientific evidence. In particular the programme is tracking impact stories where articles or media pieces have had a specific impact on policy or government decision making. / Specific outputs of the programme will include: / 1: Experienced journalists trained as trainers in science journalism in African and Arab contexts / 2: Journalists trained in science journalism and accurate reporting of science / 3: Establishment and reinforcement of national and regional associations of science journalists enabled to manage local and regional training activities and ongoing support in science journalism / 4: Evidence of journalists influencing policy-making in health, environment, technology and science / 5. Methodology to evaluate impact of media on policy and decision-making

What is the context in which UK support is provided?
Scientific reports are often too technical and difficult for non-specialists to understand. Media such as newspapers, radio and television are particularly well placed to popularize scientific information, and for science journalists to be taken seriously, science needs to be reported accurately. In the developing world in particular, journalists that specialize in science are few and far between, and the quality of their reporting is rarely of a comparable standard to science reporting in developed country media. This project is training experienced journalists in Africa and the Arab World to become science journalists, so they can accurately report on scientific issues.

## Section A: Detailed Output Scoring

Output 1: Fully trained body of science journalism trainers/mentors
Output 1 score and performance description: A, achieved the target (Possible A+)
Progress against expected results: / Indicator 1 Professional level of mentors. A / Target (August 2012) 15 mentors (all mentors) will have proved their proficiency by the end of the project. / Achieved: 15 mentors who are all experienced and practicing journalists (8 women, 7 men in Africa – Anglophone and Francophone and in MENA region) have remained with the project for the three years, and have mentored (58 graduates) which has proved their proficiency. It is of great credit to the programme that journalists involved with it in many roles want to stay informally linked. / A Malawi based mentee, interviewed for this review, said that SjCOOP has made an enormous contrition to demystifying science in Africa and that scientists have become more active in wanting to get their work into the public. ‘Scientists now contact me’. / All people interviewed for this review (12 in all) have said that the main strength of SjCOOP is the mentoring, and ex-mentors and ex-mentees all want to stay in touch with each other and with the WFSJ. This was a priority activity in 2011. / Indicator 2 Coordinators and Mentors supporting targeted research activities. / Target (August 2012) 7 mentors and 3 coordinators actively involved in supporting their mentees in targeted reporting activities. A+. / Achieved: Exceeded target as all 15 mentors and the 3 Coordinators have been actively involved in working with and encouraging their mentees. / They encouraged mentees to write impact stories, undertake investigative journalism and in writing cross border stories in which they encourage their mentees to collaborate on articles that impact more than one country. All mentors have set up internships which enabled the mentees to experience the mentor’s newsroom and to have the mentor involved in their newsroom and to jointly cover science conferences. / Impact Weighting (45%): 15% / Revised since last Annual Review? Yes. Because this has been achieved in the first year of the project, and has continued but has not been the major focus of attention in this year. / Risk: High / Revised since last Annual Review? No. / Output recommendations / It is recommended that Coordinators and Mentors are managed with greater supervision (as noted in the last annual review) and that payments are not excessive. The rejection of leadership training by many of this group points to considerable lack of being managed and an unwillingness to be managed. This should be reviewed. / It is recommended that the SjCOOP mentoring experience should be documented for learning – as it has been a strong success; it is now time to analyse this success and to make this learning available to others in the development sector through accessible outputs such as a journal article.

Output 2: Increased capability in science journalism
Output 2 score and performance description: A+
Progress against expected results: / Indicator 1. Analysis of journalists-scientist interactions show that journalists (SjCOOP-II-mentees) are recognized as professionals by scientists. A (A+) / Target (August 2012). 30% of all SjCOOP-II-mentees are judged positively by scientists - after having interviewed the scientist for an article/broadcast. / Achieved: There is evidence from the interviews that we held for this review that scientists are becoming more interested in getting their work into the public domain and that in some countries (Anglophone) scientists are now contacting the journalists to do that. Internal evaluation assessment interviewed a range of scientists (28) and concluded that 34.4% (9 mentees) of mentees have been judged by this group positively in regard to behaviour and proficiency. (See July – Sept. report for more details). / Indicator 2. Analysis of achievements of mentees as working journalists (awards won, career steps made, new media outlets free-lanced for, new areas in science journalism covered, writing skills improved) shows an increasing level of journalistic proficiency in the SjCOOP-network. A+ / * For the ratings - High, Medium, Deficient - an aggregated variable was used containing the following data: number of mentees that have won awards, number of mentees that have made a career step, number of mentees who publish in outlets that are new to them (freelance work), writing skills assessed by mentors, and the number of mentees that have started to cover areas in science that are new to them. / The target* (August 2012): High: 32 journalists (11 SjCOOP I mentees + 21 SjCOOP II mentees), Medium: 45 journalists (13 SjCOOP I mentees + 32 SjCOOP II mentees), and Deficient: 43 journalists (36 SjCOOP I mentees + 7 SjCOOP II mentees). / Achieved: High: 39 journalists (13 SjCOOP I mentees +26 SjCOOP-II mentees); Medium: 41 journalists (11 SjCOOP I mentees +30 SjCOOP-II mentees); Deficient/Low: 58 (36 SjCOOP I mentees +22 SjCOOP-II mentees, with 10 leaving in the first year). [See July-September 2012 Technical Report for more detail]. / The lack of advancement by some appears due to various contextual and personal reasons, and also to weakness in the initial selection process, accepting some weak candidates, that was highlighted by mentors and mentees in the interviews for this review. / Qualitative assessment of mentees career progression (by mentors and coordinators and through the internal evaluation) has also shown that many have advanced in their careers due to increased skills and confidence. Interviews undertaken for this review echo this assessment. / There have been significant achievements by mentees; 40 mentees started freelancing for new media; 30 mentees and 1 mentor won 63 prizes; 17 Mentees are now in charge of 17 New science beats. (Please see Annex for detail of achievements). / Impact Weighting (20%): 30% / Revised since last Annual Review? Yes this has been increased because it was a focus area for this year / Risk: High / Revised since last Annual Review? No / Output recommendations / It is recommended in any future training that the selection of mentees is more systematic and quality controlled. This was an area of weakness noted by both mentees and mentors. The quality of applicants needs to be assessed through quality criteria and testing it is essential that they are committed and that they emphasise the importance of impact from the inset and this is clear in their contracts. There is a need to involve greater use associations to select mentees and verify their references. / It is recommended that WFSJ keep in touch with SjCOOP I & II people to maintain the opportunity to network and learn from their graduation experience. We recommend that an alumni group is set up to maintain contacts with graduates.

Output 3: capacity built in national and regional associations of science journalists to manage local and regional trainings in science journalism
Output 3 score and performance description: A
Progress against expected results: / Indicator 1. Associations with a charter, elected board and regular meetings A+ / Target (October 2012). 10 new associations in Africa and the Middle East set up; to become members of the World Federation of Science Journalists (WFSJ). / Achieved: Exceeded target with12 associations set-up and supported. Two in Kenya but 9 in other African countries and one regional Arab one have been set up over the SjCOOP period. Five new associations were created in SjCOOP II and have joined WFSJ, in addition to the 7 associations’ set-up in SjCOOP I period. There were challenges of setting up associations in the Arab world because of unsupportive government regulations. / Arab Association of Science Journalists (ASJA). President: Ms. Nehal Lasheen / SciLife: Cameroon. President: Ms. Dora Shey / Ghana Association of Science Journalists (GASJ) / Rwanda Association of Science journalists (RASJ) President: Mr. Patrick Nyiridandi / South Africa Science Journalists Association (SASJA). President: Ms. Lynne Smit / Soudan Association for Science Journalists (SASJ) / Uganda Science Journalists Association (USJA) President : Mr. William Odinga / Science Journalists and Communicators of Togo (JCS-Togo). President: Ms. Andréa Dagawa / Kenya Science Journalists Association (KENSJA). President: Mr. Ochieng Ogodo / Association des Journalistes et Communicateurs Scientifiques du Benin (AJCSB). President : Mr. Christoph Assogba / Association des Journalistes Scientifiques du Niger (AJSN). President : Mr. Alhassane Abdou Mahamane / Association des Journalistes et Communicateurs Scientifiques du Burkina Faso (AJSC/BF). President : Ms. Fatouma Ouatara / Indicator 2. Associations with a range of dedicated activities: A / Target (September 2012) 4 associations / Achieved: Seven associations already meeting this requirement with a range of dedicated activities such as websites, training, science cafes, funded staff and encouraging networking. They also have local and international partnerships with Scientists and organisations like local and international donors. /  Associations who have used the SjCOOP-funding and met the expectations: South Africa (SASJA), Kenya (MESHA) and Uganda (USJA) /  Associations who have used the SjCOOP-funding and did engage in some activities but who still have to prove that they have achieved something that will last beyond the funding period: While the Cameroonian association (Scilife) did the minimum of what was expected of them, the African Federation (AFSJ) still has to prove that the support it received was a good investment. / At least three associations funded proved that they can now run their own activities and training workshops. / Impact Weighting (20%): 30% / Revised since last Annual Review? Yes because this is more an area of activity this year. / Risk: Medium / Revised since last Annual Review? No / Output recommendations / It is recommended that more engagement and support is given to new national and regional associations; those with strong potential should be in line for grant funding for some activities, and they should be invited to WFSJ meetings and twinned with other associations. / Key consideration should be given in supporting sustainability; it was noted that by having a bank account they are in a good position to be the route for journalist training provided by other development organisations.

Output 4: evaluation methodology for quality of science journalism and impact stories
Output 4 score and performance description: A+
Progress against expected results: / Indicator 1. (Scholarly) Peer-reviewed publications produced; A+ / Target (November 2012). 2 (scholarly) peer-reviewed publications submitted / Achieved: Exceeded target. Three peer reviewed publications submitted and published with two others in the pipeline. In addition Africa STI was partly created with support of SjCOOP with core funding the African Federation of Science Journals (which was set up under SjCOOPI). Science Africa is a journali founded by a former SCOOP members, the Arabic Nature was launched in 2012 by a former SCOOP mentor as a result of his experience with SjCOOP. He is the editor in chief. All of these new journals give opportunities for SCOOP mentees and associations to showcase their work. The cross border stories have been a great success- for example 3 mentees collaborating on water, and there is demand for more than this. / Indicator 2. Conference talks on SjCOOP evaluation methodology A+ / Target (November 2012). 3 conference talks given / Achieved: Exceeded target; five talks have been given in total and these have generated interest in evaluating the impact of science journalism and the individuals involved receive invitations to speak at conferences, which further publicises the WFSJ and SjCOOP work on the evaluation methodology. / Impact Weighting (15%):25% / Revised since last Annual Review? Yes this has been a key activity. / Risk: Medium / Revised since last Annual Review? No / Output recommendations / It is recommended that a summary of evaluation findings is produced, as well as a one page summary of the methodology used for the external and internal evaluation. / It is recommended that the no-cost extension period should be utilized for the development of more peer reviewed publications and learning products.

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No. Only with reporting data. / 1.2 Overall Output Score and Description: A+ / 1.3 Direct feedback from beneficiaries / During the annual review period we interviewed by telephone a random sample of 12 people who were programme beneficiaries – mentees – as well as a sample of mentors and coordinators who have worked on the programme and been secondary beneficiaries of the programme in so far as they have been contracted and engaged in capacity development of mentees and of themselves as leaders. / Interviewees included: 1 coordinator, 2 mentors and 9 mentees. The consistent headline messages from this interview sample include: / * Mentoring; people like the mentor system and it is a main strength especially the networking. Mentors cited it as the main strength and appeared to have a positive experience, and mentees likewise praised it as the main strength of the programme. Some mentees complained that mentors were not always as available as they should be. One said there was a long period before linking up with the mentor and it took a long time to get feedback, although another said; ‘I had a great mentor who really empowered me’. / * Networking: this is a key output from the programme and highly valued by participants. However there should be more linking between the language groups and some way of keeping in touch after graduation ; currently some people feel abandoned. One mentor said informally that she was staying in touch with her mentees ‘because it is heart-breaking to let them go and forget about them’ (mentor from Canada). It was noted that many of the mentors and mentees get very close; it is an intense relationship. / * Opportunities: interviewees are very positive about the range of opportunities that the programme has brought for them in their varied contexts; however mentees also feel strongly that they want more opportunities to free-lance to use their new talents and training. Those who are engaged with the Virtual Newsroom initiative (and only some are, which is also a bone of contention for excluded mentees) are both optimistic and frustrated about the lack of publishing opportunities despite this process. Others in general want more writing opportunities and require more support, they do not necessarily know how to sell science stories outside (‘not everyone can write for SciDev’ as one mentee commented). They want to participate in a news agency or the Virtual Newsroom to continue their access to a larger market. A key learning for SjCOOP is that people they train still require support to make that investment worthwhile, many mentees are located within print or broadcast jobs where opportunities are limited for putting into practice their learning and so the primary outlet for them is in the freelance market. They want a bigger market, some kind of brokerage news agency that is more than pitching stories; ideally it should be an exchange point where there is more formal engagement with researchers giving the information and finding science journalists in various countries who are available to write about new research and developments. SjCOOP has been very successful in supporting new journals for Africa, and this is an area that should be further developed; possibly WFSJ developing its own journal and a better website; and more opportunities for programme stakeholders to place their stories online via the programme site even if they are not picked up by other media. / * Learning; the programme has resulted in a growth in confidence of many mentees and this in turn has appeared to foster a context of increased trust and engagement between them and scientists/ researchers and also editors who are in the market for good freelancers. Mentees have learned skills but also have gained professional and social skills that have aided their careers. The impact of the programme on the mentees has been to open up horizons and ambitions. It has created confidence between scientists and the media, for example one mentee from Malawi, said; ‘there is regular sharing of information and scientists now call me’. / * Quality of recruitment; both mentees and mentors are saying that there is a problem in the selection of mentees with some mentees feeling that poorer quality mentees are dragging down the quality and all would like to see more testing of science as well as of journalism to improve the quality of the mentees in the scheme. This has been a repeated theme from most of the interviews and clearly is a major weakness is an otherwise robust process. A much more selective quality controlled and tested process needs to be developed for any future mentoring programme. A theme around difficulties in recruiting high quality staff emerged during the interviews. This includes some of the mentors and coordinators, the person who provided the leadership training and the recent director of the WFSJ. / * Story Development: People observe that money is being spent on the meetings but not in investing in stories so mentees have no money to travel to key areas to report on. It would be good to have a fund for this, and would improve VFM, especially pertinent when they see the money spent on conferences.
1.4 Summary of overall progress; A+ Exceeding expectations / WFSJ has flourished in this period, with 4-6 new members joining the Federation. It has become a well-established and well regarded institution with an impressive Board of leading journalists. It attracts about 800 people to its conferences and a range of countries (Brazil, Kenya, South Africa, and Korea) all keen to host the 2015 conference. / The technical side of the review suggests that WFSJ is likely to fulfil a key role in promoting science across all three regions. The programme was reported by some Anglophone mentors as creating a cultural change in parts of Africa by succeeding in popularising science in Africa. This is a major outcome. / Improvements continue to need to be made to governance systems; in particular a new WSFJ Director and possibly new staff with strong skills in management and delivery. However current management and financial systems are good although we recommend that WSFJ apply project management principles to manage the grants passed onto associations and to ensure that best practice of similar international organisations (for example in recruitment of a new director) is adhered to.
1.5 Key challenges / The key challenge for the last months of this programme are; / i) to consolidate progress made and set out a road map to get the Federation onto a self-financing sustainable basis. / ii) recruit a strong, international, professional Director for the WFSJ. This is ‘mission critical’ to the future of the organisation. It is important that this recruitment is successful and the new Director given the remit to take the organisation to the next level (see recommendations for more on this). / iii) review salary levels. This review recommends that the salaries paid to coordinators and mentors are reviewed as these are excessive and not in line with local salaries paid by similar organisations. Continuation to pay high salaries will threaten the sustainability of the WFSJ in the long term. / iv) The ‘Arab spring’ was unforeseen and has understandably focused that region on politics rather than science which may reduce the impact of the programme. / v) closing the gap between the external evaluation (which many on the scheme thought was tough) and the internal evaluation of the mentors who thought the participants of the programme had done better.
1.6 Annual Outcome Assessment; A+ / The programme continues to perform above the expectations set out in its logframe. It was noted by the Review Team that women are strongly represented in the programme; the majority of mentees were women. The top impact stories were done by women mentees. / What is now needed is better understanding of the link between those outputs and the purpose and goal of the programme; to contribute to ‘poverty reduction through better science reporting in Africa and the Middle East’ and its purpose is to ensure that ‘quality science reporting and expertise inform public debate’. For example how the systematic and high-quality reporting of science leads to improved use of evidence by policy makers and eventually, outcomes on poverty reduction. / A recent evaluation has identified at least 12 impact studies demonstrating how better science reporting, fostered by this programme, has led to policy discussion and in some cases policy change or development which is extremely encouraging. We recommend that impact continues to be a major focus of the final months of the programme so a better understanding of the theory of change between science journalism and public outcomes is established.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Yes £1.9mil at approval (converted to CA$3,344,280.23) / Left in purchase order as of 1st Feb: CA$224,599.47 / No cost extension agreed to 31st May 2013. / Anticipated expenditure: / Jan – March: $127 911.00 / April – May: $96,688.49 / (Please see annex for budget and work plan Feb-May 2013; to include travel, publications, salaries, coordinators fees, some consultants, NewsRoom (5k), and the board members trip to Boston). / 2.2 Key cost drivers / The key cost drivers of this project are salaries of staff, coordinators, mentors and evaluators, and the cost of the annual conference. / We are concerned that excessive payment expectations have been built up by Coordinators and Mentors and have raised this with the WFSJ. (Rates have been high - CA$30k per year for Coordinators, and CA$10K per year for a mentor, with an expectation of CA$13K if a next phase.) / 2.3 Is the project on-track against original timescale: Y / Yes. A no-cost extension has been approved until end of May 2013 to assist the Federation to get itself on a more sustainable (less donor dependent) basis in the near future and to document the learning from the second phase.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / None / 3.2 Where an evaluation is planned what progress has been made? / There has been significant activity in the evaluation area. (See annex for one page summary of evaluation activity, and a brief summary of findings.) / In general terms these evaluations are capturing useful lessons, strengths and weakness of the programme which can further improve it. They are also demonstrating that where the programme is active there is generally (but not universally) a strengthening of science reporting and in some cases a clear link to policy debate and decision making. / The evaluation reports deliver a lot of primary data with no analysis or conclusions. We recommend that a crisp analysis of what the data means is added to these reports using journalistic norms of concise, clear language and unbiased fair reporting of the different indicators. This would greatly improve the quality of the evaluation. (See recommendations).

4. Risk
4.1 Output Risk Rating: Low/Medium/High: / Change from Medium to High because the implications of the Arab spring are very likely to reduce the impact of the programme in that area. / 4.2 Assessment of the risk level / The programme has a risk register (in separate new proposal document pages 66 – 74) which was reviewed as part of the review. / This was a useful exercise which covered the main risks that could knock the results of the programme off course. We recommend that these are presented in a matrix (so the likelihood and impact of the different categories of risk can be compared – see below) and that the risks are made as explicit as possible rather than be summarised into general categories like ‘political risk’: for example; Journalists being arrested or intimidated, Journalists trying to operate in difficult situations, Low quality work, Plagiarism, Loss of key donors, Weak internet access. / Risk table / The risk Probability / (High, medium, low) Impact / (High, medium, low) The mitigation action / comments (incl. managed off)
Risk of funds not being used as intended / The review included a meeting with the independent auditor of the WFSJ to discuss the financial integrity of the organisation and use of DFID funds. The Auditor found their accounts generally correct and thought they were doing very well. Her personal confidence in the WFSJ is 90% which (she said) is very good. The WFSJ has no contingency budget in their Accounts. The WFSJ Accounts closed at the end of December and are currently being examined by the Auditor. / The risk of funds not being used as intended was assessed by the review team to be low risk because the funds are managed centrally by the WFSJ Secretariat, which has robust financial systems, and clear accounting procedures that are audited annually by an external accountant. The WFSJ accountant has identified only one area of risk of loss of money which is from per diems, and local travel costs (although the review team found that this is handled according to good practice and all international travel has clear receipts and vouchers). / The following activities are routinely undertaken to prevent the loss of funds: / Two signatories for any expenditure. / Per diems require a signed voucher. / Expenditure is against receipts. / Mentors only get paid on the production of two annual reports (every 6 months) which are quality assured before payment. / Annual audited accounts / Quarterly coordinator reports. / Independent accounting procedures check by IDRC on 28 October 2011 which results in minor procedural recommendations to verify accounting instructions. / Grants to associations are via a written contract which requests both a technical and financial report. Follow up payments are only made when previous payments have been accounted for. / One area of concern is the area of payment rates, as there is no systematic approach to this, and some rates may be in excess of national norms. [DFID to send WFSJ information about consultancy rates for reference, inquiries made internally about costs for consultants in Nigeria for comparative example as this is the location of one of the SjCOOP Coordinators). / Risk of Corruption / The review team held a discussion about corruption; and it was noted that the WFSJ does not have a formal corruption or anti-fraud policy. This led IDRC to undertake a review and consultation regarding the organisation’s systems and processes which recommended that the WFSJ Director (Jean-Marc Fleury) must sign off all international transfers. / SjCOOP ll WFSJ made visits to DEVCOM (a conference partner for one year) to check its processes; and monitor their financial system. / All monies go through the HQ. / Monies to the Associations – are accounted for in regular reports, and no money is sent before reporting on previous funding is received and approved. / We recommend that WFSJ develop a simple (and proportionate) written document of their financial systems and anti-fraud measures, many of these are in place and just need to be set out. [DFID to send an example from Crown Agents of how this could be done.] / 4.4 Climate and Environment Risk / There is a good story on mitigating climate and environment risk. The mentees include stories on climate change as a focus, and contribute to improved public awareness and policymaker awareness in developing countries. For example see Annex on Cameroon case study on weather forecasting. [Send to Ivan as example of potential Insight article]. / The programme has an Environmental Screening Note (ESN). (See Quest) which remains relevant and has been applied. / The programme has mitigation systems to reduce impact of its own operations; for example reducing travel – by tying events to each other; and the majority of meetings are done via Skype rather than travel (interviews for this review done by Skype).

5. Value for Money
5.1 Performance on VfM measures / The programme has been successful in delivering to target in all output areas, however this has not been without cost. / The main cost drivers have been salaries for Programme Staff and sub-contractor fees for Coordinators, Mentors and Evaluators. There is some concern within the annual review team that the salaries for coordinators and mentors are not in line with other equitable professionals in developing countries, and this needs to be reviewed further by the programme, particularly as there appears to be elevated expectations of fees from coordinators in particular. (As mentioned in 2.2 rates have been high - CA$30k per year for Coordinators, and CA$10K per year for a mentor, with an expectation of CA$13K if a next phase.) / Travel has been the second major area of expenditure, with the programme including large-scale conferences of participants, and exchange visits to media outlets in different countries for mentee groups hosted by mentors. We are content that the management of travel expenditure is according to lowest-cost principles. / The value for money of the £1.9 million funding has been in the development of a strong community of trained developing country journalists with a specialisation in development science and research. This has been an investment in the potential of this community to further grow and develop as intermediaries between researchers and media gatekeepers such as editors and media owners. / This intermediary role has an impact on public awareness and public discourse on vital issues such as environmental economics or climate change and adaptability. This also has an impact on policy and decision-makers’ knowledge, attitudes and behaviour; which impacts on citizen’s livelihoods, quality of life, access to services and other common goods within a context of alleviation of poverty. / In addition to the core focus on developing science journalist’s knowledge, skills and professionalism - which impact positive within their own societies - the programme has also had more unintended outcomes that prove value for money in the area of developing WFSJ as an institution, and in the support of national science journalism associations in Africa. / The programme has been successful in creating a buzz around science journalism in Africa; as evidences by the keenness of national associations such as those in Kenya and South Africa to bid for hosting the global WFSJ gathering; and also evidenced by the development of the Africa magazine about Science, and the establishment of the Arabic version of Nature magazine. While not all of these developments can be directly attributed to the programme, it is clear that the programme has contributed to a more enabling environment in regard to the acceptance and profile of science journalism as a valid area of focus for developing country media. / 5.2 Commercial Improvement and Value for Money / We were convinced that the programme manager Olfa Labassi has a strong grip on commercial issues and value for money and implements this throughout the Federation’s transactions. / An example of getting value for money is paying for travel of all participants by Visa which gives free insurance. This was called upon and worked well in Doha. / A policy of using the cheapest route of travel is in place and always (even for Board members) using economy class travels / All conference costings are kept down due to negotiating for special rates for all events. Local partners and associations help broker good deals. / We are concerned that salaries to coordinators and mentors are too high and are not in line with salaries in those regions see recommendations below. / 5.3 Role of project partners / There are no formal project partners. WFSJ gives grants and supports the development of science journalist associations, and it contracts coordinators and other consultants who may come from other organisations, however the relationships is not a partnership, it is a sub-contacting relationship. / There are a range of informal relationships with other organisations, universities and other stakeholders. There are fledgling partnerships with media such as the engagement of editors in the Virtual News Room, this should be developed further. / There are good potential partnerships with publications such as Nature Magazine, and with content producers such as SciDev. WFSJ should consider a partnership strategy to make better use of these synergies and relationships in a more formal manner. WFSJ has shown undue modesty in not noting as achievements the publication of articles in peer reviewed journals and international magazines and outlets such as the above. These should be more clearly included in reporting. / WFSJ and SjCOOP have partnerships with Nature, Nature Middle East, and SciDev. Nineteen mentees freelance for SciDev and the SciDev editor for francophone Africa, Theodore Kouadio, was from SjCOOP and introduced to SciDev. Four African mentees/mentor have published in Nature and another three in Nature Middle East. Philip Campbell, Nature’s editor-in-chief, is a member of a WFSJ committee on the Future of Science Journalism. / On 13th February 2013, Nature published an article that mentions SjCOOP: http://www.nature.com/naturejobs/science/articles/10.1038/nj7436-271a / SciDev has also published several articles that mention SjCOOP: / Rise of African Science Journalism: http://www.scidev.net/en/science-communication/science-journalism/features/the-rise-of-african-science-journalism-1.html / First Science Virtual Newsroom launched: http://www.scidev.net/en/science-communication/science-journalism/news/first-virtual-science-newsroom-launched.html / And others: http://www.scidev.net/en/search/results/?term=SjCOOP / Other donors funding the WFSJ include the Canadian International Development Research Centre IDRC (who were contacted during this review) the Directorate-General for International Development, Dutch Ministry of Foreign Affairs (DGIS), and the Adessium Foundation, with additional funds in Phase 1 including SIDA, Robert Bosch Foundation and the Qatar Foundation / It should be noted that the Dutch Foundation Adessium is already funding the salary of the WFSJ Director for three years, including a travel budget. / The full programme budget provided by WFSJ itemises expenditure according to DFID and other funders (collectively), this ensures some transparency as to accurate apportioning of funds for specific areas. The coding of expenditure in the accounts is also clearly related to each funder. / 5.4 Does the project still represent Value for Money : Y / Yes. We believe that the objectives of the programme and means of achieving them represent value for money. In addition the Project Manager continues to find ways of getting best value for money. (See 5.2) / 5.5 If not, what action will you take? / NA

6. Conditionality
6.1 Update on specific conditions / NA

7. Conclusions and actions
RECOMMENDATIONS / General recommendations / Recommendation about consolidation and sustainability planning / We recommend that WFSJ use the period Feb – May 31st for consolidating learning and experience so far, and for setting the WFSJ onto a more sustainable financial footing in the next 3-5 years. / This would include activities such as; Lesson learning, Mentor manual, papers, short concise and informative final report, creative presentation of the case studies. The Federation should also assess its staff’s skills and experience to check it has the right mix of skills and capabilities for its next phase (for example we question the need for four days of expert technical assistance for the next 3 years). / We recommend that a sustainability plan for the future of the Federation is written and discussed by the Board. This should include financial sustainability such as charges to Associations in developed countries to join the Federation being in line with similar organisations / Recommendation about senior management and management systems / It is recommended that more planning is done to define adequate management structures, between WFSJ and SjCOOP management. There was a discussion regarding the succession planning for the current Executive Director who has retirement plans and the recruitment of a new director for WFSJ. / The Review Team felt that the recruitment of a ‘world class’ Director for the WFSJ to take the organisation to the next level is now mission critical and it was with concern that we heard about the previous recruitment process which involved just one candidate being interviewed and only by the Board (the candidate was later found to be inadequate and moved out). We recommend that an open and transparent international recruitment process is set up in line with similar organisations. We would expect for at least 3 and probably more , international candidates are selected for the recruitment process which should include for example a leadership assessment, a Board interview, a written assessment, a staff interview/engagement exercise and a management exercise. WFSJ should consider including a representative from IDRC or DFID on the leadership interview. A thorough induction and clear remit are also necessary for success. / We were surprised that WFSJ staff have no individual work plans and formal performance assessment interviews with their line manager and recommend that these are established in line with normal good practice. / Recommendation about financial management / We recommend that WFSJ develop a simple (and proportionate) written document of their financial integrity systems and anti-fraud measures, many of these are in place and just need to be set out. Action- DFID to send an example from Crown Agents of how this could be done. / This review recommends that the salaries paid to coordinators and mentors are reviewed as these are excessive and not in line with local salaries paid by similar organisations. Continuation to pay high salaries will threaten the sustainability of the WFSJ in the long term. / It is recommended that the programme establish a more robust process for the management of assets; taking into account that all computers and other assets remain the property of DFID throughout the lifespan of the programme and need to be return to DFID unless written agreement for distribution/sale/scrappage is secured. / Recommendation about the WFSJ Board / It is recommendation that serious consideration is give at the board level regarding the diversity of Board members of WFSJ and consider including a small number of (for example as non-executive directors), management experts or donor representatives who will add a challenge function and a wider range of skills, good practice and experience from other sectors. / Recommendations about presentation of information / The Review Team struggled throughout this review with the large amount of unanalysed information that was provided by the Programme’s evaluators and in the WFSJ reports. Reports plunged into primary data reporting on indicators or outputs with no overall executive summary or conclusions of what this information means or context. We found this very surprising for a World Federation of Journalists. / We strongly recommend packaging the learning of the case studies using journalistic skills to present the conclusions of this information in an unbiased and clear manner. We recommend all reports to DFID are in future limited to 10 pages with annexes to back up the conclusions and analysis. / Furthermore the WFSJ may like to consider checking these reports with an editor as key meaning is being lost in poor translation and prose. / Recommendation about use of social media / The Virtual Newsroom project is a welcome project that goes some way to using online media to link and engage graduates, it is recommended that this is advanced and trialed further in the no cost extension period and a report made about learning from this phase. / It is recommended that the WFSJ as a whole and the SjCOOP programme specifically improves its web presence and use of online facilities. This should include integration with Facebook, Twitter and other social media. It was noted in the review that WFSJ does not use social media to the degree that would be anticipated for a leading media focused organisation. It is recommended that it makes better use of digital media and innovations (in line with similar international organisations including DFID and IDRC) to report on progress and outcomes. / It is also recommendation that digital media is utilized for the improved presentation of information and learning from the programme, in accessible ways for different audiences. This could include for example the use of YouTube to report on evaluation findings and case studies. / Recommendation about continued engagement / It is recommended that the WFSJ considers setting up an alumni group for networking and information sharing.an online network; and to establish an online network - so graduates of the programme and other stakeholders (such as mentors and other science journalists) can continue to be in contact and synergize opportunities and learning through a networked community. There was a strong desire amongst both mentors and mentees interviewed to stay in touch with the programme and not to lose those participants that were not invited to join in the news rooms. / Output recommendations / Recommendations - Output 1: Fully trained body of science journalism trainers/mentors / It is recommended that Coordinators and Mentors are managed with greater supervision (as noted in the last annual review) and that payments are not excessive. The rejection of leadership training by many of this group points to considerable lack of being managed and willingness to be managed. This should be reviewed. / It is recommended that the SjCOOP mentoring experience should be documented for learning – as it has been a strong success; it is now time to analyse this success and the make this learning available to others in the development sector through accessible outputs such as a journal article. / Recommendations - Output 2: Increased capability in science journalism / It is recommended in any future training that the selection of mentees is more systematic and quality controlled. This was an area of weakness noted by both mentees and mentors. / It is recommended that WFSJ keep in touch with SjCOOP I and II people to maintain the opportunity to network and learn from their graduation experience. We recommend that an alumni group is set up to maintain contacts with graduates. The regional coordinators should have a key role in this, leading for their region on newsletters etc. / Recommendations - Output 3: capacity built in national and regional associations of science journalists to manage local and regional trainings in science journalism / It is recommended that more engagement and support is given to new national and regional associations; those with strong potential should be in line for grant funding for some activities, and they should be invited to WFSJ meetings and twinned with other associations. / Key consideration should be given in supporting sustainability; it was noted that by having a bank account they are in a good position to be the route for journalist training provided by other development organisations. / Recommendations - Output 4: evaluation methodology for quality of science journalism and impact stories / It is recommended that a summary analysing evaluation findings is produced, as well as a one page summary of the methodology used for the external and internal evaluation. / It is recommended that the no-cost extension period should be utilized for the development of more peer reviewed publications and learning products. / Action against recommendations from last annual review: / Progress against recommendations from the last review was checked although the WFSJ did not recall having been sent a copy of the last annual review with these recommendations; however they did as it is documented in Quest. However despite not acting on the recommendations formally they have acted on them in the course of SjCOOP II’s delivery. / Recommendation - Leadership training / This was organised but it was not well received by all the coordinators and mentors (who felt they either did not need leadership training or that the course leader was not satisfactory) so it remains an issue. / Recommendation – supervisory arrangements / These are in place and were demonstrated by for example removing a mentor who would not conform to requirements. Related to this we recommend an transparent recruitment process for the positions of coordinators for any future phase and salaries more aligned to local norms. Liz and Olfa reviewed Coordinator reporting process. We recommend reporting is made monthly, and a clear work plan is set for each employee. / Recommendations – small grants for associations / This recommendation has been implemented Three new grants were given to existing Associations during 2012. This was funded by IDRC. / Recommendations – theory of change / The programme needs a clearer theory of change (ToC) and guidance on how to design this was given in the margins of the Jordan conference in September. Further theory of change support from the DFID Programme Manager is recommended. / Recommendations – evaluation / This has been undertaken but needs a crisp and clear analysis of what the information gathered in the evaluation means written to normal journalistic standards. DFID sending WFSJ the DFID form for submitting case studies and information to R4D. / Recommendations – papers / These are being written and it is important to share information about what is being published with DFID / Recommendations – strengthened financial forecasting / The Project Manager in collaboration with DFID continues to work together on this to ensure the forecasting becomes more accurate. / Recommendations – academic accreditation / This issue has been discussed, but there are no formal agreements with universities yet. / Recommendations – case studies / The Impact Case Study template has not been created. RED is about to create an Impact Case Study template from scratch. DFID to send WFSJ the template as soon as it has been approved. / Recommendations – body of literature / WFSJ directed to Research to Action portal (www.research2action.org) for information and analysis about media as intermediaries. Including such references as: / How research brokers and intermediaries support evidence-based pro-poor policy and practice: an analysis of the Locating the Power of In-between Conference, Human Sciences Research Council & Institute of Development Studies (2010) / Fisher, C., Vogel, I. (2008) Locating the power of in-between: how research brokers and intermediaries support evidence-based pro-poor policy and practice (PDF), Working Paper, Strategic Learning Initiative, Institute of Development Studies, Brighton. / Vogel, I., Wendt, D. and Wolfe, R. (2007) In the Know: Conceptualising information interventions in international development (PDF), Working Paper, Strategic Learning Initiative, Institute of Development Studies, Brighton. / Wolfe R. (2006) Changing conceptions of intermediaries in development processes: challenging the modernist view of knowledge, communication and social change (PDF), Strategic Learning Initiative (SLI), Institute of Development Studies, Brighton.

8. Review Process
The review was undertaken by Gail Marzetti (Deputy Director of RED), Jackie Davies (Research Uptake Manager and Project Manager) and Liz Harmer (Deputy Programme Manager, Evidence Into Action team) – see TOR in Annex. The team reviewed all available documentation, including Programme Proposal, Logframe, quarterly progress and financial reports relevant to the review period. See document list attached as appendix 1. The annual review included a focus on gender, revisiting the gender stocktake template that was distributed in June. / The review included a team visit to the headquarters of the WFSJ between 4 February 2013 – 7 February 2013. The team met the programme team to discuss the logframe and outputs in person. 12 interviews with a random sample of mentors, mentees and coordinators were held by Skype based on a SWOT analysis of the programme, as was a phone discussion with Jan Lublinski (Monitoring and Evaluation Consultant). / The review included a meeting between the independent accountant and the DFID EiA team finance officer to discuss the financial integrity of the WFSJ and use of DFID funds. A meeting was also held with IDRC directors who partly fund WFSJ and was joined for one morning by Fernando Perini, the IDRC Programme Manager responsible for this project / The Review Team piloted the Research and Evidence Annual Review checklist throughout this review and found it a useful tool to check the discussion against. We also used the RED ‘expectations of partners’ document in this review to structure a discussion around value for money best practice. / We also discussed gender, which was found to be useful; using the reference of the gender stocktake exercise that the programme participated in (See WFSJ Gender Stocktake response document in Annex).

# Annex

## Annex: Terms of Reference for 2012 Annual Review - Consolidating science journalism in the developing world (Sjcoop II - Aries Project code 112150)

Introduction
DFID carries out Annual Reviews of all of its programmes to assess progress against the objectives contained in the logframe, and to check if the programme is on track, and if any adjustments need to be made. At the end of a project, DFID undertakes a Project Completion Report to confirm the progress made and the success of the project.
This second phase of the ‘Consolidating Science Journalism in the Developing World’ (SjCOOP II) runs from 1st January 2010 to 31st December 2012, with a no-cost extension until 31st May 2013 agreed.
This programme aims to build the capacity of science journalists in Africa and the Middle East, helps establish national and regional science journalists associations and builds relationships between scientists and the media for more effective reporting of science and research in developing countries. This phase of the programme builds on phase I of the programme (funded by DFID from 2006 to 2009). In addition to training, it provides opportunities for mentees to immediately put training into practice on specific health, environmental and scientific key issues. The impact of articles developed during the course of the programme on policy and decision making will also be captured to produce lessons on how the media can influence policy in Africa and in the Arab World. The project will also consolidate the new burgeoning relationships between a corps of journalists dedicated to reporting scientific issues and scientific communities.
DFID Research Uptake Team is contributing £1.9 million to this phase of the programme (in addition to £365,000 for phase I). The programme is also currently funded by Directorate-General for International Development, Dutch Ministry of Foreign Affairs (DGIS), the Canadian International Development Research Centre (IDRC), and the Adessium Foundation. With additional funds in Phase 1 including SIDA,Robert Bosh Foundation and Qatar Foundation. The programme is delivered by the World Federation of Science Journalists based in Gatineau, Canada.
The programme is nearing completion of year 3 (of phase II). A proposal for a phase III has been received in January 2013 and is being considered.
An independent evaluation was undertaken for Phase I in May 2009, and an in-depth Annual Review was conducted by DFID staff in December 2010, which consulted World Federation of Science Journalist staff, partners, mentors and mentees; and an Annual Review was completed in December (undertaken 30th November and 1st December) 2011 concentrating l primarily on assessing progress made since the last Annual Review. The programme has also worked with DFID Evaluation advisor Andrew Shaw in piloting in-depth evaluation methodology.

Background
The goal of this programme is to contribute to ‘poverty reduction through better science reporting in Africa and the Middle East’ and its purpose is to ensure that ‘quality science reporting and expertise inform public debate’. To achieve these, the programme will put in place networks of journalists throughout Africa and the Arab World competent at reporting scientific issues. Their reporting will in turn increase the use of scientific evidence in policy making and decision-making in these regions.
In practice, the SjCOOP Project aims to train 60 journalists (mentees) in the reporting of science. It will also train another 15 experienced science journalists as trainers in science journalism (mentors). Simultaneously, SjCOOP will put in place and reinforce 10 associations of science journalists, which will provide sustainable support to these 60 journalists and 15 trainers.
Over three years, the trained journalists will be engaged in a series of investigative reporting activities aimed at influencing policy and decision making in the areas of health, environment, climate change, agriculture and science in Africa and the Arab World. Once equipped with skills in reporting science, journalists will work in teams including experts, scientists and NGO activists where appropriate to form ad hoc ‘journalists/scientists coalitions’, established for the duration of the issue-specific reporting activity. These coalitions will be aimed at producing media reports that will influence policy and decision making.
SjCOOP II will also document how the stories that influence policy will have been constructed. The impact of the stories on policy and decision making will also be captured, to produce lessons on how the media can influence policy in Africa and the Arab World.

The specific outputs of the programme (as detailed in the logframe 2010-2013) are:
- Output 1: Fully trained body of science journalism trainers/mentors
- Output 2: Increased capability in science journalism (mentees)
- Output 3: Capacity built in national and regional associations of science journalists to manage training in science journalism
- Output 4: Evaluation methodology for quality of science journalism and impact stories

From quarterly monitoring reports sent by the WFSJ, the programme appears to be on track as per the milestones identified in the logframe. The SjCOOP phase 2 network consisting of 3 Regional Coordinators, 15 mentors and 60 mentees is now well established and groups have met regionally as well as collectively during the World Conference of Science Journalists in Doha in Qatar in June 2011, and in Amman, Jordan in September 2012, attended by DFID Research Uptake Manager Jackie Davies. Monitoring and evaluation work is also well established in the programme. The Annual Review will provide an opportunity to review achievements and areas of potential concern in more detail.

Objective of the Review
The review will:
- Assess progress achieved since the last Annual Review conducted in December 2011, including an assessment of the quality of progress and follow-up on previous recommendations.
- Make recommendations and identify action points regarding any major technical or financial issues and problems affecting progress.
- Assess and score the project’s progress during the last year against the Outputs in the logframe, including a consideration of Assumptions and Risks, and determine whether and what changes are required;
- Assess and score progress towards achieving the logframe Purpose by the end of the project;
- Identify priorities and work plans for the coming period;
- Assess the programme’s performance in relation to implementing Gender Analysis;
- Review the programme’s partnerships, including its relationship with DFID
- Revisit and update the value for money and risk assessment sections of the business case and risk register
- Undertake an assessment of corruption and fraud risk and financial management practices

Scope of the Work
The review team will examine progress of the project against the Purpose and Outputs set out in the Project Document approved in January 2010 and based on the logframe updated following the last meeting with the Programme.
The review team will normally check not just progress made against the logframe, but also test the logframe itself: for example, in practice, are the Outputs still the right ones in order to achieve the Purpose, and are the Indicators still the right ones to monitor progress?

Methodology
Review tasks will include:
- A review of available documentation, including Programme Proposal, Logframe, quarterly progress and financial reports produced covering the review period, and any other reports relevant to the review period. See document list attached as appendix 1.
- The review team will meet with as many as the programme team as feasible such as in person Jean-Marc Fleury (Programme Director), Olfa Labassi (Project Manager), and Jan Lublinski (Monitoring and Evaluation Consultant) by telephone. A full list of Mentees and Mentors from the life of the programme has been prepared and the team will interview a sample of people from this list. See draft schedule attached as appendix 2.
The duration of the review will be 4.5 days which will include (½ day for preparation of the review including reading background documents, 3 days for meetings with project team, and 1 day for reporting once back in the UK).

Reporting
The main output of the review will be the completed Annual Review template, which will highlight main issues and constraints, and summarise recommendations, action points, owners and time-frames.
The Annual Review template report will be completed at the very latest three weeks before report deadline (31st March, 2013), to enable internal review and to share with WFSJ prior to input into the DFID system.
A short review report (maximum 10 pages) summarising the visit will also be collated and shared with WFSJ by end of March 2013. A list of recipients of the review report will be agreed with WFSJ.
The review team will endeavour to have the reports drafted by 8th March 2013.

Timeframe
The review will take place in Gatineau, Canada, on the 5th, 6th and 7th of February, 2013.

Team Composition
The review team will comprise:
- Jackie Davies, Research Uptake Manager, Evidence Into Action Team jackie-davies@dfid.gov.uk Gail Marzetti. Deputy Director Research & Evidence Division gail-marzetti@dfid.gov.uk
- Elizabeth Harmer. Deputy Programme Manager, Evidence Into Action team l-harmer@dfid.gov.uk
 Document list
SjCOOP Phase 3 (proposed):
SjCOOP Phase III Proposal (Final, 17 Jan, 2013)
SjCOOP Phase 2:
General Information
- Technical Proposal, August 2009 (Quest n. 2480288)
- Submission, November 2009 (Quest n. 2544277)
- Accountable Grant Letter, January 2010 (Quest n. 2595829)
- Logframe, updated August 2011 (Quest n. 3199867)
- Budget (Quest n. 2573632)
Year 3 Documents
- Endline Final Results
- Draft Report Impacts
- Mentees List
- Mentors List
- WFSJ Staff List
- WFSJ Board list
- Brief technical report Jan-March 2012 (Quest n. x)
- Financial Report Jan- March 2012 (Quest n.
- Brief technical report April-June 2012 (Quest n. x)
- Financial report April – June 2012(Quest n.3602830)
- Brief technical report Jul – Sep 2012 (Quest n. 3841197)
- Financial report Jul-Sept 2012 (Quest no 3841197)
- Brief technical report Oct – Dec 2012 (Quest n. x) – awaiting from WFSJ
- Financial report Oct – Dec 2012 (Quest n.x – awaiting from WFSJ
Year 2 Documents
- Brief technical report Jan-March 2011 (Quest n. 3047733)
- Brief technical report April-June 2011 (Quest n. 3292591)
- Brief technical report Jul – Sep 2011 (Quest n.3310739)
- Brief technical report Oct- Dec 2011 (Quest n. 3492841)
- WFSJ Phase 2 Logframe Achievements November 2011 (Quest n. 3310733)
- Expenditure Jan-Sep (Quest n. XXXXX)
- Comments DFID Oct-Dec 2012 (Quest n. XXXXX)
Year 1 Documents
- Expenditure Jul-Sep 2010 (Quest n. 2850831)
- Brief technical report Jan-March 2010 (Quest n. 2728977)
- Brief technical report April-June 2010 (Quest n. 2729000)
- Brief technical report July-September 2010 (Quest n. 2480288)
- SjCOOP Mentees Initial Achievements, November 2010 (Quest n. 2873955)
- Structural setting Editors in Chief perspective, November 2010 (Quest n. 2873955)
- WFSJ Phase 2 Logframe Achievements November 2010 (Quest n. 2873955)
SjCOOP Phase 1:
- Programme Completion Report, November 2009 (Quest n. 2431653)
- External Evaluation Report, May 2009 (Quest. n. 2260958)

## Annex: The Journal Article
1. Journal of African Media Studies, Volume 4, Issue 2: http://www.intellectbooks.co.uk/journals/view-journal,id=166/
2. Les Cahiers du Journalisme, No 22/23, Autumn 2011, pp. 242 – 259 : http://www.cahiersdujournalisme.net/cdj/pdf/22_23/16_MBARGA.pdf
3. Les Cahiers du Journalism, No 24, Autumn 2012, pp. 150 – 168 : http://www.cahiersdujournalisme.net/cdj/24.htm

## Annex: Evaluation summary

SjCOOP Evaluation

SjCOOP was simultaneously assessed by an independent external consultant (external evaluation) and another consultant that was part of the team (internal evaluation).

Internal Monitoring and Evaluation

Internal Evaluation focused on monitoring and measuring:
1. efficiency of the mentors (Output Indicator 1a);
2. progress of the mentees as assessed by:
  1. their mentors (Purpose indicator b), their editors (Purpose Indicator a), and scientists (Output Indicator 2a); and by recording
  2. career progress (promotions, prizes) (Output Indicator 2b);
3. success in establishing associations and associations that were actively contributing to the development of science journalism (Output Indicators 3); and
4. improvements in the work environment of the journalists favorable to science journalism (Purpose Indicator a).
External Evaluation

The external evaluator (and his team) was tasked with evaluating:
1. quality of the mentees’ reporting using 9 indicators (Purpose Indicator b); and
2. influence of journalistic stories in making governments adopt policies and decisions that improve the life of people (Goal).
SjCOOP also promised to publish three articles in peer-reviewed journals as well as present at three scientific meetings and conferences: it did three and five. The external evaluation of the quality of mentees’ reporting was also to see if mentoring was a good approach to train science journalism. Both, the external and evaluation teams also provided baseline information on gender, education, goals, challenges, and work environments of the journalists. Additional data on how the journalists collaborated and networked was also collected towards the end of the project.

Did SjCOOP achieve research uptake (Goal)?

The wording of the SjCOOP Goal – captured in the Logframe – concerned documenting cases of linkages between journalistic reporting with decisions taken to improve the life of people. Research uptake was not clearly indicated as the goal.

SjCOOP’s external evaluator analysed in depth 15 journalistic productions claimed to have influenced government decisions and policies. Of these, 12 were had an impact on governments. Amongst these 12 stories, two showed “potential of having latest scientific knowledge taken up”[1] (to fight striga weed and prevent Buruli Ulcer) while one achieved “uptake of science and technology” by making weather forecasts available to farmers.
[1] All quotes are directly taken for the reports of the External Evaluator.

A 4-page story on the state of science in Africa published in Nature (30 June 2011) was written with three SjCOOP journalists. No impact could be measured but the sole production of this story with African journalists shows the SjCOOP potential.

At least, SjCOOP provided clear lessons on how to achieve research uptake through the media:
IF African and Arab journalists specialize in science reporting they become informed by research, ally on an ad hoc basis with researchers, activists, and bureaucrats; and then give politicians the favorable media environment needed to make palatable uptake of research in some government policies and decisions.

SjCOOP evaluation describes in details how these ad hoc alliances influence government. It also describes how media, through ‘media echo’, can act as an amplifier for stories that lead to research uptake.

SjCOOP achieved minimal research uptake but proved that media in Africa and in Arab countries impacts governments and indicated how the media can bring more science and evidence in government decisions and policies.

Did the quality of the reporting improve (Purpose)?

In hindsight, it might have been overkill to task an external evaluator to measure the quality of the mentees’ articles according to 3 general indicators and 6 specific indicators (with three indicators broken down in three sub-indicators).

Overall, the quality of the production of the mentees “has slightly improved in quality, from an average mark of 1.69 to 1.84, a 9% increase”.

There were puzzling contradictions ‘within’ the external evaluator’s reports. For example: marked improvement in ‘scientific argumentation’ is accompanied by a decline in “scientific affinity’ (articles giving scientific background). There were even stronger contradictions between the evaluations performed by (1) mentors, (2) the external evaluator, and (3) the success at achieving research uptake. For example, the two strongest cases of research uptake were achieved by two mentees who were deemed not good and, in one case, not even good enough to graduate according to her mentor.

A superb contribution of the external evaluator was to confirm that in order to improve the quality of the reporting, mentors need to work on drafts of articles or outlines and storyboards of radio and television programs.

		Baseline 2010	Endline 2012
Average of indicators (54 mentees)		1.69		1.84
Number of mentees in the low, medium, and high categories		no. mentees		no. mentees
LOW (1.0 -1.57) / MEDIUM (1.58 – 1.92) / HIGH (1.93 to highest)	Low	18 (33.3%)		10 (18.5 %)
	Medium	26 (48.2%)		24 (44.4%)
	High	10 (18.5%)		20 (37.0%)

Did mentors become good at mentoring (Output 1)?

Of the 16 mentors that participated in SjCOOP, 15 become good at mentoring. One mentor was let go.

Did mentees become professional science journalists (Output 2)?

The strongest criteria that can confirm a journalist as a career science journalist is for that journalist to become responsible for a ‘science beat’, i.e. either asked to regularly cover science and science related issues by the editor-in-chief or put in charge of a science section in print media or science program in radio and television. By the end of SjCOOP, 17 mentees were in charge of 17 new science beats; 30 mentees and 1 mentor had won a total of 63 prizes; and 40 mentees were freelancing for new media (including several for Nature, the most renowned scientific journal in the world).

SjCOOP also achieved its targets regarding the number of journalists recognized as good science journalists by editors and scientists.

We believe that the SjCOOP approach is particularly appropriate for a journalist who wants to become a professional science journalist and we proved it.

Did SjCOOP establish active associations of science journalists (Output 3)?

SjCOOP makes individual journalists better at reporting science and puts in place supportive networks of colleagues. At the end of this second phase, there are 12 established associations of which 8 implement training activities, with some implementing membership fees (equivalent of $30 in Cameroon), and are also successful at fundraising. Three African associations, Kenya (joint bid of 2 associations) and South Africa, are bidding to host the 2015 World Conference of Science Journalists.

Did SjCOOP publish journal articles and present at conferences (Output 4)?

Well before the end of the project three articles had been published in peer-reviewed journals (2 were the lead author is African) and 5 presentations had been made at as many scientific conferences. Two more articles are presently being written for peer-reviewed journals.
## Annex: Achievements

Mentees (30) and Mentors(1) Prizes (63)
First name	Family name	Country	Prizes
Ola	Al-Ghazawy	Egypt	Participated in a media tour in the Netherlands funded by the Dutch government; / Participated to Rio+20 as part of the SciDev.net team to cover the conference sessions; / Attended the European Science Open Forum, ESOF2012 in Dublin, in July 2012
Suzanne	Baaklini	Lebanon	Scholarship with UNESCO to cover the climate change conference held in Qatar
Duraid	Ibrahim	Irak	Received a letter of thanks from the Central Agency for Standardization and Quality Control & another letter of thanks from the Ministry of Planning in Iraq.
Tariq	Alhmaidi	Jordan	Visited Egypt and the USA as a trainee for his excellence in reporting for science journalism. / Selected to participate to an international journalism training In the USA, from January 30th to February 13th, 2012. / Second price from the Jordanian association for environment for his distinguished reporting related the environmental issues
Adel	Alsaadi	Irak	3 local prices for his science articles that helped improve the daily life of Iraqis / Prize of the best investigative report on his story about health care of elders from the World Health Organization in April 2012 / Prize from the Ministry of Industry, Commerce, and Trade (MICT) for his distinguished reporting about lack of health conditions in popular restaurants that affects health and economy.
Fatima	Yassine	Morocco	Fatima received a scholarship for a training session on investigating journalism by ARIJ. The training was in Jordan in December 2011.
Mohamed	Baqer Awal	Kingdom of Bahrain.	Nominated for a course in writing for environmental journalism in Beirut. / Nominated for a course in investigative journalism in Bahrain. / Nominated for the green economy forum held in October 2012 in Beirut. / Participated for the first time in the competition of the Health Press of the Gulf Cooperation Council countries with his newspaper the health page. / Participated in the competition Journalism Award Gulf in Dubai
Farah	Atyyat	Jordan	Scholarship to attend the UN climate conference held December / Award from the Jordanian association for environment. / Award from the United Nations Environment Programme (UNEP) for the best ozone and climate change reporting by end 2010.
Eshraga	Abbas Abda-Rahman	Sudan	Selected for a training session on the environment and the economy organized by the World Bank office in Khartoum / Eshraga gained confidence in herself and she recently applied for the Lorenzo Natali Journalism Prize organized by the European Union (http://lorenzonataliprize.eu/)
Sara	Mattar	Lebanon	Award from Agence France-Presse (AFP).
Deborah-Fay	Ndhlovu	South Africa	Deborah-Fay won a MIT Brain Science Workshop, in Boston.
Godwin	Haruna	Nigeria	Award on Maternal and Child Health.
Cosmas	Butunyi	Kenya	FitzGerald Prize that comes with a one year post graduate BA at University of the Witwatersrand / 6 months internship at a Reuters newsroom: http://uk.reuters.com/
Kingsley	Hope Elijah	Ghana	Cambridge UK-run Biosciences for farming in Africa (6-month fellowship) / Selected to attend Reuters Women’s Health Reporting Course in 2012
Bibi-Ayesha	Wadvalla	South Africa	International Women’s Media Foundation (IWMF) HIV/AIDS Reporting Fellowship. / Selected to attend Reuters Women’s Health Reporting Course(2012) / More confident in her journalistic skills, Bibi applied for different fellowships. She applied for the Knight Science Fellowship at MIT and the Logan Science Journalism Fellowship.
Benedict	K. Tembo	Zambia	“AVAC”-fellowship in Doha 2011
Vivienne	Irikefe	Nigeria	Grant sponsored by the Ford Foundation to investigate issues of maternal and child health in Nigeria. / Science-broadcast journalist of the year award by end 2010. / MDGs Award 2010 for a story on exposing a quack doctor in a rural area across the seas in Lagos. / Thompson-Reuters scholarship in 2011
Violet	Nakamba-Mengo	Zambia	Scholarship for COP17-Summit / She wrote a special story that won her an award on sanitation. / Best media coverage for the Zambia Federation of Employers (November 2010)
Arsénio	Manhice	Mozambique	Award in sanitation in Mozambique. / Main award on Print media in Mozambique on December 2010. (The story was on Science. He received a certificate and 3000 USD)
Divine Junior Ramzi	Ntaryike	Cameroon	US International Visitor Leadership Program scholarship dedicated to giving greater insight into investigative journalism. (Scholarships 2012)
Violet	Otindo	Kenya	Fellowship for two months on Internews Heath Journalism Fellowship program.
Lominda	Afedraru	Uganda	Winner in the Uganda Media Science Biotechnology Award in 2010 / Uganda Science Biotech Media Award in 2011 / Best Journalists award in the print Category from the Nation Media Group At the USJA 2nd Science Journalism Forum 2012
Rosalia	Omungo	Kenya	Award from the Kenya Media Network on Population and Development for her TV reports on clean water.
Chinyere	Opia	Nigeria	Award “worthy promoter of journalism” Award by the Institute for Journalism in Imo State Chapter.
Jennifer	Dube	Zimbabwe	Internews/Panos fellowship. / Rotary International Humanitarian Reporting Award in 2011 / Award by the African Youth Society for her Climate Change reporting.
Théodore	Kouadio	Ivory Coast	Winner 2nd Place Lorenzo Natali Award (2500 euros)
Fatouma	Ouattara	Burkina Faso	Won a journalist fellowship to attend agriculture research meeting in South Africa.
Boureima	Sanga	Burkina Faso	Science journalism prize awarded by the French Foundation Varenne for 2011 / West Africa Prize from the Centre technique pour la coopération agricole et rurale 2011 / Special prize “Galian" for the best journalistic production / First Prize from the West African Pharmacists Corporation for an article on fake drugs, written during his participation in SjCOOP.
Claire Stéphane	Sacramento	Benin	1st Prize Radio Category Best productions of the Benin Media ``concours des meilleures productions de la presse béninoise 2012`` (article : Mal de dos, que caches-tu?)
Line Renée	Anaba Batongue	Cameroun	Winner of the Top Prize of the Ozone Africa Media Award. / Winner of the Journalists’ / Media Competition on Making the connection (Value Chains for transforming smallholder agriculture http://makingtheconnection.cta.int/awards)
Christophe T. E.	Assogba D.	Benin	Laureate of Daniel Pearl Award 2011 / Received an award on covering Tuberculosis

Freelancers(40)
	First name	Family name	Country	Freelance
Ms.	Ola	Al-Ghazawy	Egypt	Nature Middle East, OnIslam.net, UNESCO’s Arab Women Health blog, and became the Website and Social Media Editor at Zewail City of Science and Technology, Cairo
Ms.	Nehal	Lasheen	Egypt	Scidev.net; OnIslam.net
Mr.	Duraid	Ibrahim	Irak	SciDev.net, Al-Hayat newspaper; and the English weekly Kurdish Globe
Mr.	Hyder	Abdelhafeez Mohammed Abdelhafeez	Sudan	Al Muharrir (The Liberator) newspaper
Ms.	Nadia	AL Dakroury	Egypt	Al-Hayat newspaper
Mr.	Adel	Alsaadi	Irak	Al Hayat Newspaper, Scidev.net and Nature Middle-East
Ms.	Farah	Atyyat	Jordan	SciDev.net
Ms.	Eshraga	Abbas Abda-Rahman	Sudan	SciDev.net, Al-Bia Wal-Tanmia magazine and Al-Hayat newspaper.
Mr.	Zeke	AlDroubi	Syria	Scidev.net
Mrs.	Jihène	Dhayaa	Tunisia	Al Wasat newspaper and Al Wafd newspaper
Mr.	Mohamed	Assyed Ali	Egypt	SciDev.net.
Ms.	Sara	Mattar	Lebanon	Al Wafd newspaper
Mr.	OMAR	ALHAYANI	Yemen	Al-Bia Wal Tanmia magazine and Al-Hayat newspaper
Ms.	Deborah-Fay	Ndhlovu	South Africa	Nature
Mr	Cosmas	Butunyi	Kenya	Nature
Mr.	Aregu Balleh	Wondimuneh	Ethiopia	Scidev.net
Mr.	Kingsley	Hope Elijah	Ghana	ScienceAfrica
Ms.	Bibi-Ayesha	Wadvalla	South Africa	Nature Middle East, Al-Jazeera, SciDev.net and IPS
Ms.	Hope	Mafaranga	Uganda	Malaria World, Scidev.net and Plus News
Ms.	Esther	Nakkazi	Uganda	Nature, Nature Middle East, The Ecologist, SciDev.net, and many other publications.
Ms.	Vivienne	Irikefe	Nigeria	AfricaSTI and Nature
Ms.	Violet	Nakamba-Mengo	Zambia	Health Development Network and IPS
Mr.	Arsénio	Manhice	Mozambique	SciDev.net, Gemini Network, and AlertNet
Mr.	Maxwell	Awumah	Ghana	SciDev.net and Panos
Mr.	Divine Junior Ramzi	Ntaryike	Cameroon	SciDev.net, Voice of America, Associated Press, and The Post newspaper
Ms.	Sipokazi	Fokazi	South Africa	freelancing for local newspapers
Ms.	Lominda	Afedraru	Uganda	BioVision newsletter and the Science Times
Ms.	Jisi	Bongben Leocadia	Cameroon	ScienceAfrica, Malaria World, and Panos.
Ms.	Rosalia	Omungo	Kenya	ScienceAfrica
Ms	Jennifer	Dube	Zimbabwe	IPS News
Mr.	Alhassane	Abdou Mahamane	Niger	SciDev.net and local radio
Ms.	Ghislaine	Atta	Côte d'Ivoire	Scidev.net and for the NGO Akendewa
Ms.	Fatouma	Ouattara	Burkina Faso	Scidev.net and Défis du Sud
Ms.	Adrienne	Engono Moussang	Cameroon	Pan-African News Agency Panapress
Mr.	Boureima	Sanga	Burkina Faso	Scidev.net and the Belgium magazine Défis du Sud
Ms.	Line Renée	Anaba Batongue	Cameroun	Mutations newspaper
Mr.	Paul	Avougou Ndila	Gabon	Golf FM, CRTV-Radio, InfosGabon
Mr.	Harouna	Fomba	Mali	Daily newspaper in Bamako
Mr.	Christophe T. E.	Assogba D.	Benin	SciDev.net
Ms.	Diéneba	Dème	Mali	Mali correspondent of “Afrique TV” in France

New Science Beats (17)
	First name	Family name	Country	New Science Beats (17)	Media	Link
Ms.	Nadia	AL Dakroury	Egypt	Became Science editor	Al-Dostour newspaper, a tabloid owned by a Christian businessman that has been fiercely critical of Egyptian President Mursi and the Muslim Brotherhood while showing strong support for the military council (according to Al Arabya news).	http://dostor.org/
Mr.	Tariq	Alhmaidi	Jordan	Now in charge of environmental segments for TV-station	Al Rai newspaper, government controlled / Roya TV	http://alrai.com/ / http://www.roya.tv/
Ms.	Fatima	Yassine	Morocco	Now in charge of science and environmental section	Al-Marghribya Newspaper	http://ar.yabiladi.com
Mr.	Mohamed	Baqer Awal	Bahrain	Now in charge of the newspaper science section	Al-Wasat is the main opposition newspaper in Bahrain and has been shut down a few times by the government. It the most popular and most credible newspaper of the Kingdom.	http://www.alwasatnews.com/
Mr.	Kingsley	Hope Elijah	Ghana	Now responsible for new science page	The Ghanaian Times	http://newtimes.com.gh
Mr	Patrick	Dambula	Malawi	New head of science news	Malawi Broadcasting Corporation:	http://www.mbc.starmediamw.com/
Mr.	Benedict	K. Tembo	Zambia	Now in charge of the health page.	Daily Mail	http://www.daily-mail.co.zm/
Ms.	Jennifer	Igwe	Nigeria	Now in charge of environment desk	Nigerian Television Authority- NTA	http://www.nta.com.ng/
Mr.	Arsénio	Manhice	Mozambique	New head of new science page in his newspaper	Jornal Noticias:	http://www.jn.pt/
Ms.	Rosalia	Omungo	Kenya	Head of new science desk, KBC	Kenya Broadcasting Corporation	http://www.kbc.co.ke
Ms	Chinyere	Opia	Nigeria	Head of new science beat in her radio station	HOT-FM	http://www.hotfmnigeria.com/
Mr.	Joseph Leger	Ngueme Ntiga	Cameroon	Now head of science desk, Canal 2	Mutations Newspaper, the main independent newspaper of Cameroon	http://quotidienmutations.info/
Ms.	Ghislaine	Atta	Côte d'Ivoire	Now in charge of a rubrique science et technology	State-controlled newspaper, Fraternité-Matin	http://www.fratmat.info
Mr.	Boureima	Sanga	Burkina Faso	Now responsible for new health column	State-controlled newspaper Sidwaya	http://www.sidwaya.bf/
Ms.	Claire Stéphane	Sacramento	Benin	Now science editor at her station	Golfe FM radio	http://www.eit.bj/golfefm.htm
Mr.	Christophe T. E.	Assogba D.	Benin	Promoted editor-in-chief; started a new weekly science page	La Nouvelle Gazette
Mr.	Lazare	Pouya	Burkina faso	New Head Education and Health Desk	State Radio & Television of Burkina Faso	http://www.rtb.bf

## Annex: WFSJ Gender Stocktake response (prepared for DFID June 2012)

SjCOOP and Gender Analysis

Does the programme INTEND to mainstream gender analysis in its research? / Yes

Has the programme MAINSTREAMED gender analysis in its research? / Yes

In what ways does this programme implement, or intend to implement, gender analysis? Select all that apply
Is there a capacity building (not necessarily gendered) element to the programme in the logframe? / Yes.

Does the output include male/female ratios in the capacity building indicator AND/OR specifically target women researchers? / Indicators in the logframe do not include male/female ratios but gender was taken into account right at the outset. For example, we recruited equal numbers of male and female coordinators, mentors and mentees. Initially, we included 75 journalists to be trained in the program (half women and half men), in the end we graduated 58 (26 men and 32 women) and we tracked their individual accomplishments regarding: / quality of their writing; / professional achievements (promotions, prizes); / work environment and gender: how do editors perceive female VS male staff journalists and how female journalists say they are perceived in the newsroom; and / associations: how do associations take into account the different needs of women and men journalists? How many associations have a female president? / We tracked all these criteria according to gender, but we will provide results on only a few selected criteria and characteristics.

Does this output or activities under the output include building the capacity of researchers to undertake gender analysis? / SjCOOP did not have as a specific goal to train researchers in evaluation or gender analysis, but the monitoring and evaluation consultants used local partners that gained some expertise and experience in evaluation and gender analysis.

Can you please comment on how well you think the capacity building elements of this programme are working? Why do you think this is the case? (OPTIONAL) / The overall goal of capacity building in science journalism aiming at training as many women as men while influencing associations of science journalists to take into account the special needs of women worked rather well. / Do women science journalists face particular difficulties? / A minority of women (one out of six) and men (one out of four) said that women faced particular difficulties as science journalists. However, women were adamant that there was discrimination against women to access managerial positions in media. / F M / No problem. “No, not to the best of my knowledge.” 14 19 / In general. It may be a problem. “We do not have many women as journalists, so everything goes well.” “Ours is a newsroom with females so there are no gender issues.” 3 6 / Women work more. They are better. They are more productive. They are less paid. They are not to cover “strong” areas. “Women in management positions are rare. In my media, no woman has a management position. We do the same work, but women cannot make decisions.” 13 2 / “Science reporting is a specialty to be practiced by men.” “There is a real problem. First, they (the women) feel neglected. They do not want to move in science journalism because complicated things require patience and courage.” 3 6 / Total 33 34 / As in most countries, the number of women in managerial positions is rather weak. What was surprising was that a few women saw science journalism as a specialty practiced by men even though we had as many women mentors as men and that, at least in North America, the majority of science journalists are women. / Newsroom environment not favorable to women / Mentees worked in newsrooms that included on average 25 journalists. These newsrooms were dominated by men; the ratio was one woman/ two men. Editors and newsroom environments were not favorable to women. The difficulties for women to become bosses in the newsroom is illustrated by the fact that – during our program -- although women won more prizes (37) than men (26), a smaller number of women mentees became in charge of science beats (7) compared to men (10). / But , the future of science journalism in Africa and in the Arab World might be female / As indicated previously, our program graduated 26 men and 32 women as science journalists and 7 men and 8 women as trainers in science journalism. On average woman mentees are younger, men mentees are older. Our external evaluator concluded: “the future of science journalism in African and Arabian States may be female”, which would repeat what has been observed in North America where the majority of science journalists are women. Our women mentees won more prizes (37) than men (26) and a greater number of women started freelancing (23) than men (17). / We also analysed the relationships between the participants in the SjCOOP community. In the anglophone group, the center of the communication graph (higher communication) is occupied almost exclusively by women (4 women and only one man).
	Has gender research or evidence products from this programme influenced policy and practice? / Women as presidents of associations of science journalists / By the end of our project (beginning of 2013), seven women had been president of the 15 associations of science journalists created by SjCOOP: Nadia el-Awady and Nehal Lasheen (Arab Association), Dora Shey (Cameroon), Violet Otindo (Kenya – MESHA), Andréa A. Dagawa (Togo), and Anso Thom and Lynne Smit (South Africa). We have found that women play an important role in associations, even if they are outnumbered by men, and they are more active and responsible than the men. At least in one case, we were told that men adapted to the needs of women. In Uganda the meetings of the association were set on Fridays instead of Saturdays, as originally intended, following a request of women who said that they needed their Saturdays for domestic chores. / According to a survey sent to associations in late 2012, women represent between 20% and 43% of associations members (this exclude Rwanda and South Africa for which we do not have confirmed gender membership ratio). / So it looks like the associations – as opposed to newsrooms - are places were women can be supported and strengthened as science journalists. / Women make impact on governments / Of the 12 stories that had an impact on governments, 9 were written by women. Two women each had two impact stories to their credit. / It was interesting that these two women were not deemed good science journalists by their mentors (one female and one male). The female mentor thought that her woman mentee journalist should not even graduate. Both of these women had very strong personalities and very problematic relationships with their mentors, never acknowledging their weaknesses. On the other hand, it seems they both had a ‘killer instinct’ for stories with a potential for research uptake or impact on government. It seems that the editor-in-chief of these two women supports them; providing means to cover stories and even rewriting their stories before publication (we have confirmation of this for one of them). / This is another example of contradictions between some of the collected data, in this case finding that newsrooms are generally adverse to women while finding two women who benefit from strong support from their editors.
	If yes, please describe the policy, practice or other outcomes/impacts you feel this programme has had? / The program is making scientists and the Arab and African scientific establishments begin to respect and see some journalists as professionals. This is to a certain extent already leading to more positive interaction between scientists and journalists. We have several examples of scientists developing respect for journalists; ministers (Jordan, Mali, Nigeria and Uganda) and academic political, and research institutions meeting, discussing and looking at ways of supporting science journalism (Unesco, UN Economic Commission for Africa, and African Union).
	What are the success factors that enabled these outcomes/impacts to be achieved? (OPTIONAL) / See above.

	Has gender has been well integrated into the programme, given the overall goals and methods employed? / We took particular care to involve and graduate as many women as men and we collect lots of data that allow gender analysis, see above.

	What worked well in mainstreaming gender across this programme? / Staff that includes women and consultants in monitoring and evaluation that constantly remind us and collect the gender data.

	Please elaborate on why this happened and worked well. / See above

	What DID NOT work well in mainstreaming gender across this programme? / As with so many aspect of this program, we discovered all the time more things that we should be doing! / In the first phase (2006 – 2009), we lost many women trainees, particularly in the francophone group. Since we were not collecting so much data about the work environment and not asking as many questions related to gender, we could see clearly why we lost so many. / Now, with so much data collected, we are able to make correlations between the progress of the journalists and their education, work environment … and gender.