Annual Review
Title: Bihar Agricultural Growth and Reform Initiative (BAGRI)
Programme Value £ (full life): £10 Million		Review Date: 08 August 2018
Programme Code: 204135	Start Date: 29/06/2015	End Date: 28/06/2020

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium/Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4158341.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/26655551.xlsx

A. Summary and Overview (1-2 pages)

Description of programme
DFID India is providing £10m Technical Assistance (TA) support to the Department of Agriculture (DoA), Government of Bihar (GoB), under the Bihar Agriculture Growth and Reforms Initiative (BAGRI) programme. The programme targets small and marginal farmers (men and women) in the second-most poor state in India, Bihar, to enhance their income, bargaining power, market access and elevate them from subsistence to a sustainable level. The programme complements GoB in the implementation of its Agricultural Road Map (2017-22). The main programme components include collectivizing farmers into Farmer Producer Groups (PGs) and subsequently into Farmer Producer Companies (FPCs), helps create forward and backward linkages, assists in developing market value chains and contributes to key agriculture sector reforms in the state. Through these interventions the programme BAGRI interventions focus on horticulture products (fruits and vegetables) and cover 11 districts in Bihar.
Summary supporting narrative for the overall score in this review
This is BAGRI’s fifth Annual Review. Following last year’s Annual Review (AR) and Internal Audit Department’s (IAD) recommendations, the programme has been streamlined. A greater focus was given to creating market linkages, tapping in to financing options for the farmer collectives, reaching out to more women farmers, developing the market value chain and more inclusive development in Bihar’s agriculture sector. The logframe, delivery plan and risk register were significantly revised to better reflect weightings, activities and measurable indicators of partner activities and their work plans.
During the review year, the programme has assisted GoB in achieving the following targets:
- Mobilised and collectivized 37,885 farmers (vis-à-vis a target of 31,500), of which 16% are women. Formed 1620 PGs and 10 FPCs.
- The FPCs have started raising share capital from within their members, without any initial external support.
- Facilitated 8 new market linkages. 45% of the PGs have now been facilitated with better market linkages (against this year’s target of 10%).
- Developed a mobile application to collect and disseminate market price information to PGs and FPCs across the 11 BAGRI districts.
- BAGRI’s work on policy reforms has been well acknowledged by GoB. The following initiatives from BAGRI have been adopted by GoB as part of the Agricultural Road Map (2017-22) and also by the DoA for scaling up:
  - Seed Production promotion policy
  - Strengthening Action Plan (SAP) for Bihar Rajya Beej Nigam (BRBN)
  - Piloting an e- kiosk for improved agricultural technology transfer
  - Suggestion that there is a strong need for an institution for development of agriculture marketing
  - Action plan for strengthening Bihar Agriculture Management and Extension Training Institute (BAMETI)
  - Operating Mobile Soil testing Laboratories (MSTL) in Public-Private partnership (PPP) mode
- In addition, during the review year, the team has been entrusted by the Honourable Minister of Agriculture to assist on the following at a strategy level:
  - Prepare plan for upgradation of Agricultural Education in Bihar
  - Prepare roadmap for establishment of Agri- machinery/ implements manufacturing units in Bihar
  - Ways to increase efficacy of trainings done by DoA, GoB
  - Strategy plan for strengthening State Seed Farms (SSF)
  - Action plan on increasing the reach of schemes in Bihar
  - Roadmap for Developing Plant Protection Centres (PPCs) in Bihar

The key lessons learnt during the review period are:
- While GoB remains a committed partner and highly values BAGRI’s contribution in the state’s agriculture sector, there is a need to lift the dialogue on sustainability of farmer collectives – which is a key aspect in GoB and Government of India (GoI)’s endeavour to double farmers’ income. A key element of this dialogue will be to brainstorm on how to finance the FPCs and bring in sustained private sector participation for value chain development. This will also involve new thinking on potential options for how DFID India might want to take its partnership with GoB forward by using new and innovative financing instruments (development capital) and synergizing with GoB’s new strategy of agricultural product aggregation.
- Bringing in private sector players in to Bihar for agriculture value chain development has been challenging.
- Effective delivery of BAGRI interventions and regular and close consultations with GoB counterparts has helped develop a strong trusted relation between the BAGRI team and GoB. There has been a high demand for Technical Assistance including for support which goes beyond BAGRI’s scope.

Main Recommendations for the year ahead:
- Next year, the programme will focus on ensuring sustainability of its interventions. This would include strengthening the FPCs as businesses, aggressively developing forward linkages, developing the value chain by bringing in more private sector presence and pursue implementation of policies adopted in the Agriculture Road-Map.
- DFID will enhance its dialogue with GoB and other development partners on identifying financing options for farmer collectives.
- DFID would explore, in consultation with GoB, the possibility of initiating interventions (whether through BAGRI or through a new programme) – to foster private investment in agribusiness that would help increase farmer incomes and sustainability.
- The implementation team will continue to focus on women farmers – by forming women-only FPCs, engaging women farmers and farm labourers in agriculture-allied livelihood development opportunities, capacity building and gender-mainstreaming behavioural trainings.
- The team will revise the logframe and Value for Money (VfM) indicators – in light of this year’s progress – by November 2018.
- DFID will commission an independent Mid Term review of the programme by December 2018.

List of Abbreviations
Acronym	Full form
AIFD	Agri Investment Facilitation Desk
AMP	Aid Management Platform
AR	Annual Review
ATMA	Agriculture Technology Management Agency
BAGRI	Bihar Agricultural Growth and Reform Initiative
BAMDA	Bihar Agriculture Market Development Authority
BAMETI	Bihar Agricultural Management Extension and Training Institute
BAMIIS	Bihar Agriculture Market Information and Intelligence System
BAU	Bihar Agriculture University
BKB	BAGRI Kisan Bazar
BKSK	BAGRI Kisan Sewa Kendra
BRBN	Bihar Rajya Beej Nigam
CHS	Custom Hiring Services
CRPs	Community Resource Person
DFID	Department For International Development
DoA	Department of Agriculture
eKB	e-Kisan Bhavan
FPCs	Farmer Producer Company
FPOs	Farmer Producer Organizations
GoB	Government of Bihar
GoI	Government of India
IAD	Internal Audit Department
ICT	Information & Communication Technology
IT	Information Technology
LF	Log Frame
M&E	Monitoring & Evaluation
MFIs	Micro-Finance Institutions
MSTL	Mobile Soil Testing Laboratories
NABARD	National Bank for Agriculture and Rural Development
NBFCs	Non-Banking Financial Corporations
NRI	Natural Resources Institute
PGs	Producer Groups
PPCs	Plant Protection Centres
PPP	Public-Private-Partnership
PPPIAD	Public Private Partnership Initiatives for Integrated Agriculture Development
PPs	Partnership Principles
SAP	Strengthening Action Plan
SFAC	Small Farmers’ Agribusiness Consortium
SFI-AE	Syngenta Foundation India- Agri Entrepreneurship
SRO	Senior Responsibility Officer
SSF	State Seed Farms
TAST	Technical Assistance Support Team
ToC	Theory of Change
VfM	Value for Money
WGs	Working Groups

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Enabling Formation of Producer Group/Companies for Maximizing Profits to Farmers and Strengthening their Bargaining Power
Output number per LF		1	Output Score	A
Impact weighting (%):		50%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 No. of farmers mobilised into Producer Groups (PG)	31500	37885 (Exceeded)
1.2 No. of Producers Groups (PG) formed	1050	1620 (Exceeded)
1.3 No. of women farmers mobilised through PGs	5000	6009 (Exceeded)
1.4 Farmers Producer Companies (FPC) registered	10	10 (Met)
1.5 No. of FPC achieved threshold shareholder capital of INR 3 lakh	3	1 (Partially met) / 2 (in range of INR 2-3 lakh)
1.6 Number of farmers provided training on agriculture credit & insurance	2000 {Male (1700); Female (300)}	1047 (Partially met)
1.7 Number of beneficiaries (farmers and farm labourers) provided trainings on improved agronomical practices, technology (seed variety, fertilizers, pesticides etc.)	31250 {Male (26250); Female (5000)}	32224 {Male (29564); Female (2660)} (Exceeded)
1.8 Number of farmers provided trainings on PG/FPC planning, management, governance etc.	6000 Male {(5000); Female (1000)}	25982 {Male (22494); Female (3488)} (Exceeded)
1.9 % of farmers adopting at least one of interventions demonstrated/ proposed under BAGRI	Male (10%); Female (5%)	NA
1.10 % of PGs accessing agricultural inputs at reduced cost	10%	46% (Exceeded)

For output 1.1, BAGRI assisted GoB to mobilize 37,885 farmers (against a target of 31,500). This has been possible through aggressive village sensitization as well as effective planning and generation of strong enthusiasm among the target groups. Demonstration effect of project interventions with older PGs in project area has also been a catalyst for higher degree of mobilization.

For output 1.2, through BAGRI’s assistance, 1,620 PGs have been formed against a target of 1,050. Meticulous, time bound planning and targeted sensitization meetings have led to higher achievement. Formation of PGs has been followed by selection of office bearers, PG norm setting, bank account opening and Agriculture Technology Management Agency (ATMA) registration. The PGs are provided hand-holding support in issues of governance, operations, management – facilitating their gradual federation into FPCs. Community Resource Person (CRPs) of respective project geographies, who work at the block level and intently with the farmers, have played a critical role in this processes.

For output 1.3, during the review period, BAGRI interventions helped mobilize 6,009 women farmers through exclusive women PGs against this year’s target of 5,000. To enhance the participation of women, BAGRI provided targeted support to women farmers/farm labourers and their groups in the form of mandatory board position, reducing the requirement of share capital contribution to half etc. Such measures have worked as additional motivator for women farmers to join PGs/FPCs within the BAGRI project. Continuing its efforts toward ensuring better gender inclusiveness, BAGRI has planned to form women majority FPCs in the next year.

For output 1.4, 10 FPCs were registered as planned. Until September 2017, registration of the first 4 FPCs was completed in the districts of Buxar, Bihar Sharif, Vaishali and Muzaffarpur. Incorporation of 6 new FPCs in the districts of Begusarai, Vaishali, Gaya, Rohtas and Samastipur was also completed. The team has been able to generate interest among the wider small and marginal farmers community, to come under the fold of BAGRI.

For output 1.5, FPCs established through BAGRI have a target of mobilising a critical amount (INR 3, 00,000) as share capital. This share capital helps the FPCs to become functional business entities and is expected to be deployed as working capital to facilitate FPCs conducting their business with individual farmers and PGs. During last year, 1 FPC has been able to achieve this threshold share capital of Rs. 3, 00,000 (against a target of 3 FPCs). 2 other FPCs have been able to raise more than INR 2, 00,000 as share capital. Since the share-capital is an out-of-pocket expenditure for the FPC members, delays are caused due to their vulnerable economic status. This is further exacerbated by the delay in issuance of licenses by district agriculture offices which allows FPCs to initiate their agriculture input distribution business. The team has been working towards strengthening its relationship with key government officials further and is confident of achieving all targets related to this indicator next year. As a pilot, the team engaged with Samunnati, a Non-Banking Finance Company (NBFC), to provide working capital finance for one of BAGRI’s FPCs. The members paid the loan on their own within the stipulated tenure, which has encouraged Samunnati to provide further working capital loans to other BAGRI FPCs.

For output 1.6, 949 male and 98 female farmers were provided training on agriculture credit and insurance against a target of 1700 male and 300 female farmers respectively. Shortfall in this category is attributable to non-deployment of a specialised third party agency to work on this component within the BAGRI project. However, the process of on-boarding is at its final stages and it is expected that all the targets related to this indicator will be achieved next year.

For output 1.7, 32,224 farmers have been provided trainings on improved agronomical practices, technology (seed variety, fertilizers, pesticides etc.) against a target of 31250 during review period. This includes 29,564 male farmers and 2,660 female farmers. BAGRI has started focused training and capacity building activities for women farmers which are more relevant to their daily on farm and off farm activities.

For output 1.8, BAGRI has assisted in training and capacity building of 25,982 farmers (against a target of 6,000). This includes training on planning, management, governance etc. of PGs/FPCs. Experts from PGs/FPCs have been utilized as master trainers to improve the impact of training on larger farmer community as well as for institutional planning, management and governance.

For Output 1.9, the achievement against the target could not be quantified due to lack of adequate data. It was realized during the course of data collection that the time lapse between providing training on new techniques and that of data collection was too short. Farmers would typically need a few months’ lag in adopting new techniques. Therefore, the team currently do not have adequate data to measure achievement of the milestone target. This year it is collecting appropriate systematic data and will be able to account for it in subsequent reports.

For output 1.10, 46% PGs (against a target of 10%) have been accessing agricultural inputs at reduced cost due to BAGRI interventions. Direct procurement of quality agriculture inputs from manufacturers/big traders have led to direct savings in procurement. It is to be noted that the FPC/PG led collective marketing of agriculture inputs has also led to reduction in prices of such inputs by other retailers in the zone of influence of the FPCs/PGs. This demonstration effect has led to significant gain not only for members of BAGRI PGs/FPCs but for non-members alike.

Lessons identified this year, and recommendations for the year ahead linked to this output
Mobilization of farmers is not evenly split across project districts. For instance, it has been a challenge to mobilize farmers in Darbhanga district. Due to reasons such as a regular inflow of remittances from family members staying outside the district/state/country, lower production of vegetables and lower dependence on agriculture as a source of income, farmers in Darbhanga are, on average, better off than those in other districts and not easily attracted to the PG/FPC model. Consequently, the the pace of PG formation is relatively slow in the district.
While the programme will keep its line of sight firmly on poor farmers, it will not exit Darbhanga in the immediate future because of the reputational risks involved. Part of BAGRI resources has been diverted away from Darbhanga to a new block in another BAGRI district to undertake additional famer mobilization. A final assessment will be done in the next 5-6 months, exploring ways to adjust the PG/FPC model to better suit the circumstances, attitudes and needs of farmers in Darbhanga.
- For farmers to remain motivated and for the programme to achieve high impact, it is important to focus on building profitable and long-term market linkages. While both forward and backward integration into the market is important, creating opportunities for famer collectives to sell their produce in the local and external markets will be crucial in the future. In the absence of such linkages, there is clear risk of declining farmer interest in the FPCs. The programme has already achieved some success in this regard but will focus on scaling them up in the coming years.
- Some of the trainings listed under indicator 1.6 do not have a direct line of sight to the output. These trainings are part of overall awareness creation of the member farmers about farming as a business, government schemes and the agriculture insurance market. To ensure all trainings are directly linked to the output (and outcome), it is recommended that either some of these trainings are phased out or a clear set of output indicators be developed to capture their role in the success of the overall programme. For the trainings that continue, the programme will build and strengthen relationships with GoB officials with an aim to secure institutional and financial support. This will create ownership within government, integrate and mould the training agenda in line with GoB priorities and create sustainability.
- The team will enhance its outreach to Non-Banking Financial Corporations (NBFCs), Micro-Finance Institutions (MFIs) etc. and enhance sensitization towards functioning of PGs/FPCs.

Output Title	Strengthening the Marketing Chain and Market, wherein Small/Marginal & Poor Farmers are Effective Partners
Output number per LF		2	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of new market linkages developed	8	8 (Met)
2.2 % of PGs facilitated with better market linkages	10%	46% (Exceeded)
2.3 Market linkages turnover facilitated through FPCs/PGs	£0.25m	£0.58m (Exceeded)

For output 2.1, Better market linkages through FPCs and PGs are the most critical interventions and carriers of various project benefits envisaged within the project design. The BAGRI project has lived up to the challenge of creating remunerative market linkages in its project geographies by providing potential of commercial viability for FPCs through better implementation and replication of such models. 8 market linkages have been created, as per target, until year 2017-18. Introducing high value products like papaya and strawberry and marketing scale up in Buxar, launch of the BAGRI Kisan Bazar or farmer markets (BKB) and the BAGRI Kisan Sewa Kendra or farmer facility centres (BKSK) models are few achievements in this regard. Going forward, in addition to implementing new market linkage models, the programme will continue to devise strategies for replicating models like BKBs and BKSK to increase market penetration, scale up volume and increase footfalls. The team has successfully facilitated forward linkage of 2 FPCs with ITC for supply of about 500 Metric Ton (MT) of wheat. These FPCs are now enrolled as direct vendors for ITC – rendering the linkage sustainable in the long term.

For output 2.2, 46% of BAGRI PGs have been facilitated with better market linkages against a target of 10%. 730 PGs have been facilitated for collective input and output marketing. The programme would continue such facilitation process for the next year to achieve the intended targets.

For output 2.3, BAGRI has facilitated £0.58m of market linkage turnover against target of £0.25m. It has facilitated market linkages across all project districts with PGs/FPCs. Such market facilitation includes £0.32 m in input transaction and £ 0.26 m in output transactions during the review period. CRPs deployed in the project have been playing a critical role in facilitating the market linkages. BAGRI has also been training CRPs on various aspects of input and output market linkages preparing them for future challenges and replication.

Lessons identified this year, and recommendations for the year ahead linked to this output
- While the team will focus on increasing market linkages, there will also be a strong focus on sustaining the existing linkages. The programme will explore facilitating market linkages with big agri-processors (like Pepsico etc.).The upcoming MTR will also compare the effectiveness of building market linkages at PG versus FPC levels and help the programme streamline its efforts.
- BAGRI has helped FPCs open their own agribusiness centres in three districts. Such agribusiness centres have been receiving good response from catchment area farmers including non-members. There is need to implement an IT based comprehensive solution with proper accounting system for such agribusiness centres to ensure better record keeping and transparency.
- External funding support from the Small Farmers’ Agribusiness Consortium (SFAC) and NBFCs will be explored to strengthen the capital base of FPCs who have completed one year of operation and have generated a credible credit history.
- In order to support small and marginal farmers increase the crop yields through efficient farm operations, the team has planned to facilitate linkage between FPCs and farm machinery suppliers by piloting IT enabled Custom Hiring Services (CHS) in the project districts.
- With sustainability of FPCs being the focus for the next two years, the team will enhance the weightage of this output appropriately in the logframe.

Output Title	Enabling Accessibility to Clear, Reliable and Dynamic Agricultural Information
Output number per LF		3	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of districts facilitated with mechanism to collect agricultural market price from BAGRI project areas	5	11 (Exceeded)
3.2 No. of farmers getting access to BAGRI facilitated real time market information	5000	2003 (Partially met)
3.3 No of farmers getting access to better knowledge and technology inputs through e/m- services, one stop shops/other improved models facilitated by BAGRI	5000	More than 5000 (Met )
3.4 No. of farmers facilitated for improved soil testing infrastructure through MSTL and advisory services facilitated by BAGRI	12500	(Not Met)

For output 3.1, at present there is no institutional set up in the state to collect real time agricultural market price in Bihar. BAGRI has been able to innovate in this space by funding the development of a mobile application to collect and disseminate market price information to farmers associated with BAGRI PGs and FPCs. In the improvised system, CRPs deployed in different project districts are being leveraged to collect market price information as additional responsibility. The team has also been training farmers on how to install the app in their phones and use the same.
However, to ensure sustainability of this initiative and institutionalizing it, the team is finding it difficult to convince local agencies to create a network for collection of price, without long-term commitment. The team has submitted a concept note to GoB, detailing requirement of a Bihar Agriculture Market Information and Intelligence (BAMIIS) application for collection and dissemination of market information to farmers to facilitate them take informed marketing decisions. This note also contains techno-functional requirement of BAMIIS proposed as ICT solution. In the next review year the team will be following up on this with GoB on a priority basis.

For output 3.2, 2003 farmers are getting access to BAGRI facilitated real time market information against a target of 5000. Market prices collected through the mobile application with the support of CRPs are being disseminated to the farmers. BAGRI team will start expanding the reach of the mobile application in the upcoming year by engaging a local service provider and seek appropriate GoB support for outreach. Discussions on this have been initiated with the relevant stakeholders.

For output 3.3, More than 5010 farmers (against a target of 5000) are getting access to better technology and technology inputs through mobile and internet services, one stop shops and other innovative models – facilitated by BAGRI. An e-kiosk machine has been installed at Masaudhi e-Kisan Bhawan for knowledge dissemination. The kiosk has been designed by Hewlett Packard (HP) and the content has been developed in collaboration with Bihar Agriculture University. HP has provided this service pro-bono. In addition, 3 FPCs have been facilitated to open one-stop-shops in the form of BKSKs for knowledge and technology dissemination. Although, the scale of services offered through e-kiosk and BKSK is limited so far, the aim is to scale them up in the next years.

For output 3.4, the selection process of a private entity for operating Mobile Soil Testing Laboratory (MSTL) vans through Public-Private-Partnership (PPP) mode has been delayed due to changes made in contract clauses by GoB. This has resulted in non-achievement of this milestone. The contracting is expected to be completed within the next quarter.

Lessons identified this year, and recommendations for the year ahead linked to this output
- There is need to engage a suitable agency for collection of real time market price and its dissemination. Furthermore, the team, in consultation with GoB, could devise ways to ensure necessary institutional and extension support for collection and validation of market and price information with registered FPCs.
- The existing mobile application could be further developed on functionality and dedicated resource and effort should be channelized to increase the outreach of this high impact intervention. Also going forward team will track how much of the total subscribers are active users.
- The market for innovative technologies disseminating market prices to farmers has been increasing. There is however dearth of systematic evidence on the extent of impact these innovations have on farmers’ income and profitability enhancement. DFID will explore ways of monitoring the impact of availability of price information through ICT innovations on farmers’ profitability and overall income, for example using a randomized control trial model. This will also contribute towards creating a scientific evidence base on effectiveness of such innovations and help identify criteria for success.

Output Title	Strengthening institutional capacity, introduction of regulatory reforms and facilitating private sector investment in agribusiness in the state
Output number per LF		4	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
4.1 No of policy & institutional reforms initiated by BAGRI	2	14 (Exceeded)
4.2 No of proposed reforms adopted by Agri Department and/or Roadmap	1	6 (Exceeded)
4.3 Number of reforms implemented	NA	NA
4.4 E-Kisan Bhawans operationalised through BAGRI facilitation as pilot	1	1 (Met)
4.5 Capacity building of agricultural universities through UK linkages in agricultural research	1	1 (Met)

For output 4.1, in the past year, the team has worked closely with GoB on the following policy and institutional reforms:
1. Introducing Public Private Partnership Initiatives for Integrated Agriculture Development (PPP-IAD) schemes in Bihar for increased private sector participation and increased impact of schemes in Agriculture and Working Group formation
2. Roadmap for introduction of PPP-IAD scheme in Bihar
3. Strengthening Action Plan (SAP) for Bihar Rajya Beej Nigam (BRBN) or State Seed Policy
4. Strengthening agriculture research capacity of the Bihar Agriculture University
5. Bihar Seed Production Promotion Policy
6. Farm Mechanisation & Promoting Custom Hiring services Policy
7. Strategy Action plan for operationalization of e- Kisan Bhawans in Bihar
8. Action plan for Agriculture Investment Facility Desk (AIFD) in Bihar
9. Strengthening Action Plan for BAMETI

On GoB’s request, the team has also worked on the following: prepared a note on agricultural warehousing need in Bihar, Bihar Scheme Access Facilitation unit (BiSAFU), Bihar e-Scheme Monitoring System (BeSMS), Bihar Agriculture Market Development Authority (BAMDA), Bihar Agriculture Marketing Administrative System (BAMAS) and prepared the Strengthening Action Plan for BAMETI.

A national level stakeholder consultation workshop, along with GoB’s DoA, was conducted during the assessment year, to identify the implementation modalities of PPP-IAD. A Working Group on PPP-IAD has been constituted to expedite the implementation. GoB is in the process of notifying the final PPP-IAD scheme guidelines. Under BRBN policy initiative, necessary consultations were made with GoB to get the proposed intervention incorporated in the Agriculture Road Map (2017-22).

For output 4.2, the programme has had strong achievements in this output category. The policy reforms initiated by BAGRI were incorporated in GoB’s Agriculture Road Map (2017-22). The Road Map is the key policy document of GoB that will be followed through to enhance farmers’ income and overall agricultural productivity – for the next five years. To have BAGRI’s inputs incorporated in this document in 6 key areas is a major achievement in terms of the programme having sustainable impact on Bihar’s agriculture sector.

Against a target of 1, 6 of the policies that have significant contribution from the BAGRI team has been adopted by the agriculture department in its operations and as part of the Roadmap:
1. Seed Production promotion policy
2. Strengthening Action Plan (SAP) for Bihar Rajya Beej Nigam
3. Piloting an e- kiosk for improved Agricultural technology transfer
4. Need and role of an institution for development of agriculture marketing
5. Action plan for strengthening BAMETI
6. Operating MSTL under PPP mode

This year there was no milestone to be reached under output 4.3. However, next year, pursuing the implementation of the policies that were incorporated in the Agriculture Road Map – will be key focus of BAGRI.

Under output 4.4, as planned, an e-Kiosk has been deployed at 1 e-Kisan Bhawan to promote their ICT enablement and thereby operationalize them effectively for agriculture extension. The e-Kiosk has an in-built response form which captures the feedback of the viewers regarding the services provided. The functions of the kiosk have been developed in collaboration with Bihar Agriculture University.

For output 4.5, 3 key activities have been undertaken during the review period:
1. A 2-day University level consultation workshop at Bihar Agriculture University (BAU), Sabour to structure the capacity building workshop.
2. A 3-day workshop in collaboration with the Natural Resources Institute (NRI), University of Greenwich, UK on capacity building of faculties and researchers for strengthening agriculture research in Bihar.
3. Drafted MoU between NRI, UK and BAU, Sabour for partnership in academic and educational research and facilitating the MoU execution.

The programme team has facilitated investment worth £4.05 million in the food processing and agri-infrastructure sector. Some of the key enterprises are Vishal Food & Snacks Pvt. Ltd., Maa Vindhyasni Agro Processing Pvt Ltd, Maa Chhinmastika Food Processor Pvt Ltd, Jai Mata Di Agro Products Pvt Ltd and Md. Israil Cold Storage.
Lessons identified this year, and recommendations for the year ahead linked to this output
- Frequent transfers of senior government officials and associated delays often defer the programme’s progress on policy reforms. In order to expedite the process, last year, the team in consultation with DoA, GoB had three specific Working Groups (WGs) created, with technical and advisory committees, for steering policy reforms. This helped fast track policy reforms and timely adoption of some of the BAGRI assisted policy recommendations in the Agriculture Roadmap.
- With a change in political ecosystem in the state in July 2017, wherein there was a renewed central government focus on doubling farmers’ income, BAGRI was asked to start delivering on multiple policy reforms and related activities on short notice, directly from the Honourable Agriculture Minister’s office. While this has helped BAGRI interventions get a higher level of attention from GoB, it was a strain on the limited human resource of the team. In consultations with DFID and DoA, the team streamlined some of the crucial asks within its scope of delivery for the review year. The team, going forward, would ensure that need for additional activities are posited through the programme’s Steering Committee and are taken up based on their alignment with BAGRI’s scope of work.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year

Department of Agriculture, GoB supervision and support

Techno-managerial support by BAGRI TAST

Thematic experts

DFID’s financial and technical inputs

Performance of agriculture sector in Bihar improves significantly to reflect higher private sector investment, higher production and price realisation by farmers

- Additional private sector investment in agriculture sector in Bihar
- Average increase in production/productivity of select horticulture crops in project districts
- Average increase in income of farmers for select horticulture crops in project districts
- Improvement in Agricultural Orientation index (AOI) for the state of Bihar

Output 3: Enabling Accessibility to Clear, Reliable and Dynamic agricultural Information
- Facilitating agriculture price dissemination across programme districts
- Enabling farmers with IT enabled techniques
- Providing farmers improved soil testing and advisory services
Output 1: Enabling Formation of Farmers Producer Group / Co-operatives for Maximizing Profits to Farmers and Strengthening their Bargaining Power
- Mobilizing men and women farmers for formation of farmer collectives (PGs/FPCs
- FPCs raise share capital internally for sustainability
- PGs have effective backward linkage
- All member farmers are provided holistic training
Output 4: Strengthening institutional capacity, introduction of regulatory reforms and facilitating private sector investment in agribusiness in the state
- Policy and institutional reforms initiated
- Number of reforms adopted by state government
- Capacity building of Bihar’s agricultural University

Increase in agricultural growth rate between 2016-17 and 2019-20
Inputs
Outputs

Outcome
Impact
Output 2: Strengthening the Marketing Chain and Market, wherein Small / Marginal & Poor Farmers are Effective Partners
Develop and strengthen market linkages at PG and FPC level

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

	Output	Broad Interventions	Status	Linkage with Outcome/Impact
1	Enabling Formation of Farmers Producer Group / Co-operatives for Maximizing Profits to Farmers and Strengthening their Bargaining Power	Creation of PGs and FPCs	On track	Outcome indicators 2, 3 and 4
		FPCs have share-capital	Partly on Track
		PGs have effective backward linkages	On Track
		Member farmers provided trainings	On Track
2	Strengthening the Marketing Chain and Market, wherein Small / Marginal & Poor Farmers are Effective Partners	Develop and strengthen market linkages at PG and FPC level	On Track	Outcome indicator 1, 3 and 4
3	Enabling Accessibility to Clear, Reliable and Dynamic agricultural Information	Facilitating agriculture price dissemination across programme districts	On track	Outcome indicators 1, 2, 3 and 4
		Enabling farmers with IT enabled techniques	Off track
		Providing farmers improved soil testing and advisory services	Off Track
4	Strengthening institutional capacity, introduction of regulatory reforms and facilitating private sector investment in agribusiness in the state	Policy and institutional reforms initiated	On Track	Outcome indicators 1, 2, 3 and 4
		Number of reforms adopted by state government	On Track
		Capacity building of Bihar’s agricultural University	On Track

Explain major changes to the logframe in the past year
In response to changes in the context and recommendations of previous reviews (AR and IAD), the team revised the Logframe indicators in September 2017 to better reflect weightings, activities and measurables of partner activities and their work plans. The logframe was restructured around the four outputs reflected in the ToC, output indicators and relevant milestones were rationalized around what the team, considered the most impactful partner activities, rather than seeking to capture the full range of activity being undertaken.

Describe any planned changes to the logframe as a result of this review
After substantive review in the last review period, no major changes are planned in the logframe. The milestones will however be updated based on the current review period’s performance on specific output indicators. For example, with the focus of BAGRI shifting primarily to sustainability of the FPC, creation of sustainable market linkages will take centre stage. Therefore, in the next year, the weightage of output 2 will be enhanced. The milestone indicators will also be revised to ensure the programme thrives to create successful market linkages covering all PGs and FPCs in the next two years.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year
Economy: The programme has made sufficient economy gains in terms of the inputs invested into the Technical Assistance. Economies have been achieved in using Community Resource Persons to form Producer Groups instead of District-based teams. This alone has had an estimated gain of about £400,000. As pointed out earlier, premises of the office are given free of any charges by the Government of Bihar resulting a saving of another £40,000 each year. Also the economy gains in this programme have been high in comparison with another similar programme run by the National Bank for Agriculture and Rural Development (NABARD)[1]. Given that most of the outputs have been achieved the Economy gains for the programmes are well settled.
[1] http://sfacindia.com/UploadFile/Statistics/Farmer%20Producer%20Organizations%20Scheme.pdf page 26

Efficiency: In the ability to convert inputs to outputs, while comparable programmes have used more than INR 145,000 (£1600) in establishing an FPC, BAGRI has been successful in completing the same in half the cost, without compromising on the milestone. With most of the output milestones either met or exceeded the targets, the efficiency gains have also been realized through faster achievement of targets, not only in comparison with the programme milestone but also with other comparable programmes. The total efficiency gains calculated through lesser time taken for creating each Producer Group and for federating each FPC, higher training hour per farmer, higher turnover in million GBP per PG/ FPC, higher farmers footfalls / usage facilitated through one stop shops/ models, lesser turnaround time for reform initiative, lesser turnaround time for strengthening activities and lower facilitation time per million GBP investment adds up to a total of £ 790,734. With an input cost of £1.3 million in the year, the economy and efficiency gains demonstrated have been to the tune of £2.8 million, which is commendable for a primarily Technical Assistance programme.

Effectiveness: While the programme is still on its way to attain all its outcome targets, effectiveness has already been demonstrated in realizing gains for the farmers through three ways: (a) reduction in input costs, (b) higher price realization and (c) increased productivity. Evidence also suggests that this has also led to reduction in overall input prices in the surrounding areas where BAGRI operates, thereby resulting in gains to non-members too. Moreover, on the policy reform front, 6 reforms suggested by BAGRI have already found place in the Agriculture Road Map of the state. The programme has facilitated investments worth £4.05 million in the food processing and agri-infrastructure sector. The overall cost effectiveness has been found to be more than 1 for almost all indicators like PG level business turnover, FPC level business turnover and production by shareholders through adoption of improved practices. With more outcome performance data becoming available in the coming years, this can be demonstrated better.

Equity: BAGRI works in one of the poorest states of the country. While the beneficiaries are mostly small and marginal farmers, landless farmers also benefit from this programme. The conscious effort put in reaching women farmers is demonstrated by the over-achievement of targets specific to women. The programme is also on its way in establishing a FPC specifically for women. People from all castes belong in the Farmer Producer groups without any discrimination. Through partnerships with UK universities like University of Greenwich and research organisations like Syngenta Foundation, efforts have been made to bring cutting-edge technology to the remotest farming lands, so that farmers benefit from increased produce. Thus the programme seeks to ensure equity through these various means.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
As explained above, the programme has demonstrated Value for Money on all 4 counts of Economy, Efficiency, Effectiveness and Equity. Thus it should continue on its own merits. This programme sits in the Inclusive Growth and Investments portfolio of DFID India. This is the only programme that directly addresses farm productivity in the portfolio. In a country that is still largely agrarian and with a looming agrarian crisis and farmer suicides hitting the headlines every day, the success of this programme in terms of ensuring Value for Money is integral in the DFID India narrative. While the spend is still on Technical Assistance only, huge gains have been demonstrated with the concept of federating farmer groups. Going forward, BAGRI will develop more systematic coordination, information exchange and cross-learning with ongoing comparable programmes in Bihar, to ensure continued efficiency.

Each of the 6 policy reforms adopted by the Government of Bihar is expected to yield significant gains for the farmer in terms of seed quality, technology transfer, agricultural marketing and Public Private Partnerships. While assigning a monetary value would be difficult at this stage, in the language of the Business Case, even if 50% of these were achieved, the Value for money for DFID investment in this programme would have been realised.

E: RISK (½ to 1 page)

Overall risk rating: Moderate
Key Risks (and Residual Risk Rating post Mitigation)	Mitigation measures
Delivery: Proposed policy and institutional reforms may be delayed due to long drawn government processes [Major]	The team closely engages with key stakeholders and decision makers to speed up the process of approval. This is further ensured via monthly meetings and Programme Steering Committee Meeting (quarterly)
Delivery: Inadequate response from private sector investors due to external business environment in the state. [Major]	TAST has extensive relationships with private sector – both within and outside Bihar which is being leveraged. In addition, the TAST’s experience in implementation of agribusiness specific investment promotion activities and greater coordination and linkage with the Industries Department is being used to create greater awareness about government’s intent to promote private investment in the state. Greater coordination is being forged with other DFID India programmes for better synergy in attracting private sector investment.
Delivery: Frequent transfer of senior GoB officials involved in project may delay interventions that require government approvals [Moderate]	DFID project Team meets with partners once in every two months, such close coordination is expected to ensure a smooth transition and minimize delays. The TAST regularly monitors government counterpart movements and takes measures for smooth handover process for such transitions.
Delivery: Risk of programme deliverables not achieving intended impact. [Moderate]	The team works in close consultation with GoB. All activities are formally agreed and tracked with partner department at the quarterly Programme Steering Committee meetings. There is scope for the PSC to deliberate on priority areas and change deliverables, if the latter does not have the desired impact. The Mid Term Review will also capture the extent of impact of the programme’s activities systematically.
Delivery: Institutions (FPCs) created through the programme fail to be sustainable after the programme ends. [Major]	In the next two years of implementation the programme will have strong focus on ensuring sustainability of the institutions created. This will include extensive discussions with GoB and other development partners on – linking the institutions with sustainable sources of finance, creating long term market linkages and streamlining the programme activities with GoB’s priorities in the agriculture sector (like GoB’s new focus on product aggregation). As the FPCs are being created, the next year will focus on training them on developing viable risk mitigation plans – to avoid undue reliance on single cropping, identify and mitigate fraud and corruption while running the FPCs as business entities.
Safeguards: The programme might not reach many potential women beneficiaries, leading to unintended exclusion. [Moderate]	The programme's focus on women farmers has been revived (with new targets). An external partnership (with SEWA) has been forged specifically to bringing more women farmers in to the fold of the programme. In the next two years, the focus will be retained and capacity of women farmers will be further developed.
Reputational: Failure to deliver intended development objectives as per GoB expectations. [Moderate]	Review with GoB to ensure programme and expectations are on track - once every two months. Quarterly review of project progress with supplier – not only in terms of money disbursed against milestones but also in terms of development impact assessment

Update on partnership principles
DFID India’s Partnership Principles state that DFID India’s support is based on a shared commitment to the following four principles:
- Helping India reduce poverty and leave no one behind
- A commitment to respecting human rights and other international obligations
- A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
- A commitment to strengthening domestic accountability
In line with the partnership principles, BAGRI complies with the partnership principles and where funding is channelled through partner organizations, this is done in accordance with these principles. Compliance to these principles is ensured through processes like Due Diligence, Financial Audits and Technical Reviews in close collaboration with GoB.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues
Programme progress is on track for all four outputs except few interventions of output 3, where the pace is relatively slow owing to some procedural delays. Delivery against the agreed targets is monitored and reported on quarterly basis. The TAST has been sensitive and aware of the importance of adhering to timelines in terms of overall deliverables and related commercial performance. The quality of financial management was good for the year 2017-18. The team has ensured the budgeted spend as per the agreed forecast and delivery plan. The detailed snapshot of deliverable plan, targeted and actual submission period is captured below:

S. N.	Quarter	Deliverables	­Targeted Quarter	Actual delivery Quarter
1	Quarter-1 (April-June)'17	Action plan on Strengthening & Restructuring plan for BRBN (Bihar Rajya Beej Nigam)	Q-1	Q-2
		Pilot of SFI-AE (Syngenta Foundation India- Agri Entrepreneurship Model) (First batch of AEs sent for training)	Q-1	Q-2
		Roll out of PPP - MSTL (Mobile Soil Testing Lab)	Q-1	Q-4
		1 eKB (e-Kisan Bhavan) pilot implemented	Q-1	Q-4
		Formation of new 180 producer group (out of total 720) (0.675% for every 180 producer group)	Q-1	Q-1
		Formation of 4 FPOs ( Farmer Producer Organizations) (out of total 10 FPOs) (0.5% per FPO formation)	Q-1	Q-1
		Quarterly Progress Report –Q1 FY’18	Q-1	Q-1
	Quarter-2 (Jul-Sep)'17	Strategic Action Plan for 6 eKBs (for 6 districts)	Q-2	Q-2
		Formation of 180 new producer group	Q-2	Q-2
		Formation of 2 new FPOs ( Farmer Producer Organizations)	Q-2	Q-2
		1 Market Linkage Project implemented	Q-2	Q-1
		Quarterly Progress Report Q2- FY’18	Q-2	Q-2
3	Quarter-3 (Oct-Dec)'17	Capacity Building for select faculty of BAU (Bihar Agricultural University) by NRI (Natural Resources Institute), London.	Q-3	Q-3
		PPP-IAD (Public Private Partnership for Integrated Agriculture Development) Workshop & roadmap preparation for implementation	Q-3	Q-3
		Roadmap preparation for creating Federation of FPOs and Setting up PMU for handholding FPOs	Q-3	Q-4
		Formation of new 180 producer group	Q-3	Q-3
		Formation of 3 new FPOs (Farmer Producer Organizations)	Q-3	Q-3
		Quarterly Progress Report Q-3 FY’18	Q-3	Q-3
4	Quarter-4 (Jan-Mar)'18	Formation of 180 new producer group	Q-4	Q-3
		Formation of new 2 FPOs ( Farmer Producer Organizations)	Q-4	Q-3
		2 Market Linkage Project implemented	Q-4	Q-4
		Quarterly Progress Report Q4- FY’18 (with detailing of no. of women farmers reached)	Q-4	Q-3
		Quarterly Progress Report Q-4 FY’18	Q-4	Q-4

Date of last narrative financial report(s)	NA
Date of last audited annual statement (s)	16/04/2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring
The logframe has been the basis for monitoring. The following are used a monitoring and evaluation methods to track BAGRI’s progress:
- Quarterly progress Reports with output wise information update, key achievements and challenges faced.
- Programme Steering Committee meeting held every quarter and chaired by the Development Commissioner – to assess progress, address bottlenecks and identify emerging needs/priorities.
- Regular visit by DFID task team including site visits, discussion with beneficiaries, key government counterparts and TAST.
- Deliverable linked payments are agreed between DFID and TAST at the beginning of the programme year. The Programme Steering Committee vets the same.
- In this review period, the DFID task team exposed the programme to multiple scrutinies by other officials from within DFID India. This included visits by DFID India’s Head of Office and Team Leader of DFID India’s Inclusive Growth and Investment team. The goal was to gather dispassionate views about BAGRI’s progress, its strategic fit in DFID’s India partnership and looking at long term sustainability and methods of enhancing value add, going forward.
- The market for innovative technologies disseminating market prices to farmers has been increasing. There is however dearth of systematic evidence on the extent of impact these innovations have on farmers’ income and profitability enhancement. DFID will explore ways of monitoring the impact of availability of price information through ICT innovations on farmers’ profitability and overall income, for example using a randomized control trial model. This will also contribute towards creating a scientific evidence base on effectiveness of such innovations and help identify criteria for success.

Evidence
The programme lays significant impetus on evidence guided planning and implementation. Best practices within the country are being used to design and implement the interventions. Stringent measures are put in place to establish baselines and realistic milestones are arrived at, which are tracked and monitored throughout the programme cycle. Case studies are collected periodically to understand the programme’s progress. A third party mid-term evaluation is to be commissioned that aims to undertake a thorough stocktake and provide recommendations for course correction. A third party impact evaluation is also planned at the end of the programme. The monitoring and evaluation activities entail participation from of all programme stakeholders.

Learning
- While GoB remains a committed partner and highly values BAGRI’s contribution in the state’s agriculture sector, there is a need to lift the dialogue on sustainability of farmer collectives – which is a key aspect in GoB and Government of India (GoI)’s endeavour to double farmers’ income. A key element of this dialogue will be to brainstorm on how to finance the FPCs and bring in sustained private sector participation for value chain development. This will also involve new thinking on how DFID India might want to take its partnership with GoB forward by using new and innovative financing instruments (development capital) and synergizing with GoB’s new strategy of agricultural product aggregation.
- Bringing in private sector players in to Bihar for agriculture value chain development has been very challenging. This is exacerbated by the programme’s limitation of not being able to fund hard infrastructure.
- Effective delivery of BAGRI interventions and regular and close consultations with GoB counterparts has helped develop a strong trusted relation between the BAGRI team and GoB. There has been a high demand for Technical Assistance even for support which goes beyond BAGRI’s scope.

Progress on recommendations from previous reviews
Update as per last year’s AR and IAD recommendations:
- The logframe, VfM indicators, Delivery Plan have been reviewed for adequacy, accuracy and relevance – in consultation with TAST.
- BAGRI has enhanced its focus on reaching out to women farmers and bringing them under the fold of the programme. This is visible in 16% of its current members being women farmers (as compared to 5% in 2016-17).
- BAGRI has been coordinating with other DFID India programmes namely Infrastructure loan (for bringing in private players for cold chain piloting in its programme districts) and the Poorest State Inclusive Growth programme (PSIG) for digital finance literacy and access to micro-finance institutions.
- A Programme Steering Committee has been formed that is chaired by the Development Commissioner. This has significantly improved programme coordination, intra-departmental coordination and eased decision making within GoB on key issues affecting BAGRI’s progress.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided