Type of Review: Annual Review
Project Title: Public Financial Management Reform Programme
Date started: 1st July 2012
Date review undertaken: 15th Sep – 15th Oct 2013

Scoring used in this Review / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is investing £15.9 million over the period of 5 years (2012/13-2016/17) to improve Tanzania’s Public Financial Management (PFM). This is composed of the following three components: i) £10 million to support Phase IV of the Government’s Public Financial Management Reform Programme (PFMRP IV) ii) £5 million to support Local Government Level PFM Reforms and iii) £0.9 million for Technical Assistance to provide strategic advice for the implementation of Tanzania’s PFM agenda.

What are the expected results?
The UK’s support is contributing to i) public resources being allocated more strategically (in line with priorities) and used more efficiently and effectively to support service delivery ii) improvements in fiscal discipline and iii) reduced opportunities for corruption and fraud. / To achieve such impacts, the UK support is helping strengthen PFM systems as evidenced by: / Improved revenue management: For example, total revenue collection is expected to increase from 16.5% of GDP in 2010/11 to at least 17.8% of GDP in 2013/14; Tax exemptions as a % of GDP are expected to decrease from 2.2% of GDP in 2010/11 to1.2% in 2014/15. More resources will better support service delivery and help Tanzania to graduate from international aid; / Improved budgeting and planning: For example, a more orderly and participatory approach to the budget preparation process to ensure that the budget is credible as a financial and operational plan; strengthened linkages between the Government’s stated strategic policy objectives and their budgets to ensure that they are properly funded; / Improved budget execution, transparency and accountability: For example, increases in, and more timely releases of development funding for local governments to better support service delivery; improvements in the level of compliance to procurement legislation from 68% in 2011 to a target to be agreed later in 2012 to ensure better value-for-money and reduced opportunities for corruption in procurement processes; improved integrity and content in financial statements to ensure that there is a solid picture and understanding of the Government’s finances; / Improved budget control and oversight: For example, increases in the percentage of unqualified audit opinions for central and local Government accounts as evidence of improved compliance to internal controls and accounting standards; improved implementation of external audit funds and recommendations; strengthened oversight capacity of the parliamentary accounts committees. / Other issues: Improved inter-governmental fiscal transfer system to increase the amount, and speed up the transfer of financial resources to support public service delivery / To achieve these results, UK funding is, alongside funding from other donors, support the i) updating of laws, rules and procedures to ensure robustness and clarity in standards ii) strengthening of skills of those engaged in the PFM activities, both within the Government and for those performing oversight roles (e.g. the National Audit Office and Parliamentarians) and iii) improvements to software systems to support the implementation of PFM activities. / The process to determine whether expected results have been achieved will include annual performance reviews and independent evaluations in 2013 (a Public Expenditure and Financial Accountability – PEFA assessment), in 2014 (mid-term) and 2017 (end-term).

What is the context in which UK support is provided?
Tanzania’s public expenditure has expanded sharply over the past decade to reach 27% of GDP (approx. Tsh 9.4 trillion /GBP 3.7 billion) by the end of 2010/11. Meanwhile, revenue collection currently amounts to around Tsh 5.7 trillion/GBP 2.3 billion, approximately 16% of GDP. Ensuring that these substantial resources are managed in a way that promotes economic growth, enables the poor to participate in economic activity and enables the achievement of development goals whilst achieving maximum value-for-money is at the heart of Tanzania’s PFM agenda. Sound PFM is also an imperative for curbing corruption in the public service. / However, whilst Tanzania has made substantial improvements in its PFM systems over the last 10-15 years resulting in a mid to high ranking when compared to other Sub-Saharan Africa countries, significant weaknesses remain. These result in the following challenges: / Financial resources not reaching service delivery points in the amounts budgeted for, or in a timely and predictable manner; / Financial resources being inefficiently and inequitably distributed resulting in poor value-for-money and the exclusion of groups and districts in under-served remote areas from the delivery of quality basic services; / Financial resources not being strategically allocated to maximise value-for-money; / A growing fiscal deficit and rising public debt; / Weaknesses in internal controls giving rise to opportunities for corruption. / As a result, a Fiduciary Risk Assessment conducted by the UK and African Development Bank in late 2011 concluded that on a scale of high, substantial, moderate and low, the overall level of fiduciary risk in Tanzania is substantial. / What will be done to tackle these challenges? / To address these challenges, alongside other donors the UK is supporting the new Phase IV of the Government’s PFM Reform Programme (PFMRP IV); the implementation of PFM reforms at the Local Government level and; technical and strategic dialogue and analysis across Tanzania’s PFM agenda. / PFMRP IV: The Government’s strategy aims to improve PFM in the following areas: i) Revenue Management; ii) Budgeting and Planning; iii) Budget Execution, Transparency and Accountability iv) Budget Control and Oversight. UK support to PFMRP IV will be implemented by central and local Government, the National Audit Office and Parliament and will be provided in a pooled funding arrangement with other donor money. / Local Government Level PFM Support: PFM weaknesses are more pronounced at the local compared to the central government level, and local governments are responsible for the delivery of basic services. To ensure that UK funding supports an intervention that is sustainable and achieves value-for-money, a local government PFM component is currently being designed based on the emerging evidence base. / Technical Assistance: Given its breadth and complexity of the PFM agenda and the need to ensure effective sequencing and linkages across multiple stakeholders, the UK has enhanced its technical expertise by recruiting a specialist PFM Adviser. This Adviser is responsible for providing technical and strategic advice to better inform and thereby improve PFM policy dialogue. The UK will also provide funding for supportive diagnostic and analytical work.

## Section A: Detailed Output Scoring

Output 1: Laws, rules and procedures are amended to improve revenue policy and administration at central and local government levels
Output 1 score and performance description: B Outputs moderately did not meet expectation / Indicator 1.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Bills/Acts submitted and approved on tax revenue policy and collection for central and local government levels Bill submitted to Parliament to enact the Tax Administration Act for the purpose of establishing a common tax procedure among different taxes collected by the Tanzanian Revenue Authority Bill has been framed and submitted to AG for vetting. Likely to be submitted to Parliament in February 2014.
Progress against expected results: / The proposed Tax Administration Act, which targets a common tax collection procedure among different taxes collected by Tax Revenue Authority (TRA), was submitted to the Cabinet and Attorney General (AG) for verification in June 2013. With the Parliament due to discuss the draft Constitutional Review in November 2013, the bill is unlikely to be tabled until February 2014. Additionally, Government is currently revising the VAT Act with support from IMF due to the numerous exemptions from it that impact on the tax base and reduce its efficiency while making it more distortive. The PER secretariat has commissioned a study on tax exemptions and the findings from which will be examined for the revised VAT Act. / Recommendations: / These are among the many pieces of legislation that have been delayed. Higher level dialogue is required with GoT to push through important pending Bills. / Impact Weighting (5%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 2: Appropriate capacity at Local Government level to implement improved policies and administration procedures
Output 2 score and performance description: A Outputs met expectation / Indicator 2.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Appropriate capacity at Local Government level to implement improved policies and administration procedures Sufficiently trained staff in PMO-RALG and RSs in tax revenue plans and budgets to spearhead reforms PMO-RALG conducted training for 50 planners across LGAs during 2012-13 and 65 planners in 2013-14 for improving planning & budgeting capacity, including revenue planning. In addition, 30 planners have been trained on financial management in 2013-14 in the newly created LGAs. However, a comprehensive training programme on revenue management for LGAs has been delayed and is currently being designed.
Progress against expected results: / Capacity building at local level is recognised as a key issue and extends beyond revenue management. Particular emphasis has been given to the implementation of EPICOR. Staff across all LGAs, included Heads of Departments, have been trained on EPICOR and regular follow-up has been extended to accountants. Training on financial management is currently being extended to cover newly created LGAs. In 2012-13 and 2013-14 (till date), PMO-RALG has trained 869 personnel on different PFM aspects. / Recommendations: / The proposed PFM reform support to LGAs should provide dedicated capacity building support across different PFM areas to PMO-RALG, Regional Secretariats and local governments. / Impact Weighting (15%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Laws, rules and procedures are amended improve budget preparation and planning at central and local government levels and improve budget transparency
Output 3 score and performance description: A Outputs met expectation / Indicator 3.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Rules and procedures approved on budget preparation and planning Chart of Accounts modified to accommodate Programme Based Budgeting (PBB) Chart of Accounts has been modified to accommodate Programme Based Budgeting (PBB) / Indicator 3.2 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Public access to key fiscal information Approved budget and year-end budget execution report is published on MoF's website by September of each year; a year-end (budget outturn) comparing the budget execution to the enacted budget is published on MoF's website by October of each year; Citizen's budget is published by November of each year. Approved budgets (Vol II-VI) have been published – Vol I which contains revenue estimates is yet to be published due to changes in tax proposals. End-of-year budget execution report is planned to be published on MoF website by Mid-November. Citizen’s budget 2012-13 was published in November 2012 and this year’s citizens’ budget is expected to be published soon.
Progress against expected results: / Although modification of the Chart of Accounts has been done, it will be implemented as and when programme based budgeting is rolled out across MDAs and LGAs. Additionally the MTEF has been reviewed to make it compatible with program based budgeting. However timeline has been deferred to September 2016 given the planned rollout to all MDAs and LGAs in a gradual manner. / Good progress has been made on budget transparency and access to key fiscal information – the PEFA notes that 4 out of 6 requirements are being currently met. This aspect has been further strengthened under PFMRP based on the PEFA report findings. / Recommendations: / There is need to continuously monitor progress on this aspect, including timely publication of quarterly budget execution reports. / Impact Weighting (5%): / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? N

Output 4: Appropriate capacity at central and local government levels to implement improved budget preparation and planning
Output 4 score and performance description: A+ Outputs moderately exceeded expectation / Indicator 4.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / % of staff in MDAs and RSs trained with the necessary skills to effectively implement programme-based budgeting Interim milestones to be derived from the agreed PBB Action Plan / Suggestion: PBB pilot commenced in selected Ministries Good progress has been made based on the milestones included in agreed PFMRP milestone matrix (details provided below).
Progress against expected results: / PBB template developed and MoF organised a working session end of August 2013 with 8 pilot Ministries (Ministries of Finance, Water, Works, Transports, Education, Health, Community Development and Agriculture). Training has been provided to technical staff in these pilot ministries. Existing PBB Action Plan will be reviewed after the October working session with pilot Ministries. It will include a Policy Paper in order for the Cabinet to formally authorise the use of PBB. PBB will be implemented in a stepwise fashion starting with a number of Pilot ministries and then move to other MDAs, regions and LGAs. All MDAs and LGAs to be compatible by September 2016. / Recommendations: / It is recommended that suitable milestones are included in the logframe based on the PBB action plan. There is need to continuously monitor progress on the implementation of the PBB Action plan. / Impact Weighting (15%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 5: Laws, rules and procedures are amended to improve the inter-governmental fiscal transfer system
Output 5 score and performance description: A Outputs met expectation / Indicator 5.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Ease of use and speed of the inter-governmental fiscal transfer system Agreed cross-governmental policy approach to address the problem as reflected by a comprehensive and sequenced two-year work-plan, including a time bound M&E framework with roles and responsibilities to address shortcomings of the systems and processes of inter-governmental transfers is finalised by June 2013. Key actions starting to be implemented by October 2013. A comprehensive and sequenced action plan has been developed, based on the inter-governmental fund transfer study conducted by the Ministry of Finance. Implementation of the action plan will commence from December 2013. However, some of the actions have already been initiated – this includes review of the allocation formulae for LGAs.
Progress against expected results: / The study on intergovernmental fund transfers was completed and submitted to Government in Sep 2013. The action plan was developed through a workshop held in October 2013 involving Ministry of Finance, PMO-RALG, sector Ministries and development partners. This group deliberated and discussed proposed actions for taking the recommendations forward and came up with realistic and practical actions for implementation, with clearly outlined responsibility between different GoT components – Commissioner of Budget, ACCGEN and PMO-RALG. / Recommendations: / It may be appropriate for DFID to consider financing some of the agreed action points through the local government PFM component, which is currently under design. / Impact Weighting (10%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 6: Laws, rules and procedures are amended to improve procurement practices
Output 6 score and performance description: B Outputs moderately did not meet expectation / Indicator 6.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Procurement policies and legislation revised New Public Procurement Act 2011, regulations prepared and issued by June 2013; Revised procurement implementation and monitoring tools issued Regulations under PPA 2011 are yet to be gazetted. Draft new regulations were submitted to Inter-Ministerial Technical Committee (IMTC). It is currently waiting for AG’s verification and subsequent Ministerial approval. Procurement implementation tools in line with the PPA 2011 and new regulations are under development.
Progress against expected results: / Even though the PPA 2011 regulations haven’t been made effective so far, the PPA 2011 has been disseminated in June and July 2013 to 85 Board of Directors and 189 Accounting officers of Public Entities. The procurement management information system (PMIS) is being developed and has 610 registered users from 299 PEs. The 2011/12 Annual procurement performance evaluation report was published on PPRA Journal and Website. The 2012/13 is expected to ready in October 2013 and published by Feb 2014. / Recommendations: / To continue engagement with key stakeholders for enabling notification of the PPA 2011 regulations given that many there are many follow-up activities linked to this milestone. / Impact Weighting (5%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 7: Laws, rules and procedures are amended to improve cash management and debt management
Output 7 score and performance description: B Outputs moderately did not meet expectation / Indicator 7.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Cash management and banking arrangements revised Future milestones to be devised after agreement on the recommendations from the IMF East AFRITAC Cash Management mission / (New suggestion – Cash flow management strengthened and payment arrears are monitored on a monthly basis) Significant improvement has been in streamlining banking arrangements – between 2009 and 2012. GoT has closed 31,441 bank accounts since 2009 and the balances were transferred to GoT’s accounts in Bank of Tanzania (BoT) (approximately TSH 12bn). / For the six main bank account categories and its sub-accounts, bank reconciliation is conducted monthly within two weeks after the end of the end. For those in commercial banks, ACCGEN receives quarterly bank statement after one month following the end of the quarter.
Indicator 7.2 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Debt management arrangements revised Debt management policy developed and shared (May be supplemented by additional milestones after agreement on recommendations from the World Bank Debt Management mission) MOF has conducted a debt sustainability analysis (DSA), which covers both domestic and external debt. The DSA output is expected to serve as key inputs for the country’s new Public Debt Management (PDM) Strategy that will guide the government borrowing policy. / Progress against expected results: / The PEFA notes that more than 29,000 bank accounts remain in commercial bank with deposits amounting to more than Tz 800 billion. New accounts continue to be opened in commercial banks, mainly at the request of donors. The ACGEN still does not have regular and systemic knowledge of the balances held in these accounts. / Cash flow management has been identified as a key weakness by the PEFA assessment. With the prescription of monthly cash ceilings, MDAs tend to accumulate payment arrears, often recorded outside the IFMIS. / On debt management, work is underway on the draft of this new PDM Strategy, which MOF expects to finalize by the by November 2013. Several other interventions have been undertaken by GoT on debt management. A single external debt data base has been enabled by consolidating the database maintained by Bank of Tanzania with that maintained in AccGEN. The AccGEN routinely prepares monthly and quarterly debt reports mainly for management purposes. The President’s office has agreed to establish a centralized Debt Management Office (DMO) within MoF. MoF has been working on the revision of the current Loans and Guaranteed Act to incorporate provisions that will insure a greater control of public indebtedness and limit fiscal risks stemming from contingent liabilities. / Recommendations: / Support on cash flow management should be strengthened in PFMRP and agreed milestones implemented after dialogue with CPAD and ACCGEN by December 2013. / There is need to support GoT to complete the institutional modalities for establishing a single debt management office that will integrate the back office and front office debt operations. / Impact Weighting (6%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 8: Laws, rules and procedures are amended to improve internal audit functions
Output 8 score and performance description: A+ Outputs moderately exceeded expectation / Indicator 8.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Effectiveness of internal audit function Operational Plan for MoF's new Internal Audit Department is developed and approved by June 2013; internal audit manual/guidelines, standards and quality assurance improvement programme, which complies with international standards and best practices is in place by June 2013 IAGD Operation Plan has been developed. Internal audit manual has been developed and finalised along with a quality assurance improvement manual. Draft audit committee guidelines have been developed and are currently under review. All MDAs, LGAs and RSs have established Internal Audit Units (IAU) and their planning is approved by Audit Committees.
Progress against expected results: / PEFA report indicates significant improvement in effectiveness of internal audit – improved from C rating in 2010 to B rating in 2013. This year, a new milestone has been added to ensure that corrective actions as identified by the IAGD reports are taken by accounting officers, although evidence contained in the IAG’s and MDA’s reports indicates that management response has improved considerably and corrective measures are increasingly being taken. / Recommendations: / Continue engagement with IAGD to strengthen institutional capacity. / Impact Weighting (13%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 9: Appropriate operational capacity within the NAO to perform an oversight function
Output 9 score and performance description: B Outputs moderately did not meet expectation / Indicator 9.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / Number of staff trained and systems to track outstanding audit matters established Database that will separate findings (monetary and non-monetary) and recommendations, including by age, and record follow-up actions is established Progress on the establishment of a database on audit recommendations has been slow, although manual consolidation of past audit queries and recommendations from resident auditors is on-going. NAO is looking for alternative options for developing appropriate software for tracking outstanding audit queries.
Progress against expected results: / This was a very ambitious milestone. Developing a database and software to track audit queries generated each year requires consolidation of the data currently residing with the resident auditors scattered across the country and subsequent development of an ICT solution to digitise the data to be able to generate consolidated reports. The entire work cycle requires 2-3 years to be completed. / However, there are other significant areas on which the NAO has delivered. The quality and coverage provided by the Central Auditor General (CAG) in statutory audits have achieved AFROSAI-E level 3 standards. Audit coverage of expenditures of all government MDAs, public entities and corporations increased to 100% in 2011/12. The development of performance and technical audit capacity continues to receive focus with external support – CAG got acclaim for the quality of performance audit it conducted in 2012-13. NAO has carried out extensive staff training in areas such as risk based auditing and IT audit. To foster greater transparency and to make its reports user-friendly NAO produced and disseminated its first Citizen’s Audit Report (2011-12) in July 2013. / Recommendations: / Support NAO to identify and assess suitable software options and provide technical assistance in developing an audit tracking system. / Impact Weighting (7%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 10: Laws, rules and procedures are amended to provide a more supportive ICT infrastructure environment for PFM
Output 10 score and performance description: B Outputs moderately did not meet expectation / Indicator 10.1 Milestone (End of 2013) : Target Milestone (End of 2013) : Actual / ICT infrastructure (PAF KPA) Costed action plan to bring all GoT financial and peri-financial software under 1 common architecture with technical support structures is approved by GoT The final draft report on ICT Mapping was submitted by consultant in October 2013. This was discussed and approved by a joint government-DP group. The final report will be the basis for the action plan development.
Progress against expected results: / Progress on this issue has been significantly delayed. The action plan is now expected to be prepared by March 2014, taking into account the recommendations of the ICT mapping study. / Recommendations: / Continue to be engaged with GoT on this issue. / Impact Weighting (10%): / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the log frame been updated since last review? N / This is the first annual review. No changes made to the logframe. However, based on the findings from the recent PEFA assessment, several new milestones have been incorporated while some others have been revised. In addition, some output indicators in the logframe were yet to be defined. Hence, it is proposed that the logframe will be reviewed and updated in the near future to reflect these changes. / 1.2 Overall Output Score and Description: A Outputs met expectation / Overall the programme is rated A. On two outputs it has been rated `A+’ (28%), on three outputs it has been rated `A’ (34%), on 5 outputs it has been `B’ (38%). / The outputs on which the programme has achieved or exceeded the milestone relate to orderliness and participation in budget preparation, progress towards programme based budgeting, inter-governmental fiscal transfers, budget transparency and effectiveness of internal audit. The outputs on which the programme has moderately not achieved expectations include legislations on tax revenue, cash management, procurement oversight, debt management, audit tracking system and IT integration of financial systems. / 1.3 Direct feedback from beneficiaries / This annual review is based on the findings from the Annual Joint Supervision Mission undertaken by a team which comprised of development partners and government counterparts. Feedback on the programme implementation was obtained from all key stakeholders including Ministry of Finance (Planning Division, Commissioner of Budget, Accountant General, Procurement Division, HRM division, Financial Information Systems), Office of Internal-Auditor General, National Audit Office, Public Procurement Regulatory Authority, Treasury Registrar, President’s Office – Public Service Management and Prime Minister’s Office – Regional Administration and Local Government among others. / Apart from the direct participating departments and agencies, the mission also held discussions with other key stakeholders such as Bank of Tanzania, Tax Revenue Authority, select ministries (MoHSW, MoE and MEM). These meetings provided the opportunity for discussions that focused on the impact of reforms, status of reform implementation and challenges that spending and income generating entities face given the reform environment.
1.4 Summary of overall progress / In the first year of its implementation, the programme has done well to ensure that all reform components are largely on track. The joint supervision mission has highlighted in its findings that there has been good progress on the core reform components that include planning and budgeting, budget execution and external oversight and control. However, it has also noted limited progress in the areas of revenue forecasting and change management. / The gradual improvement in PFM systems in Tanzania is also corroborated by the 2013 PEFA assessment. Out of 31 PEFA Indicators (PIs), 12 ratings improved, 5 are in process of improving, 9 PIs have not changed and 2 have fallen. However, it was apparent that the PFMRP programme, in its original form, did not address some of the weaknesses identified by the PEFA assessment. Hence, during the joint supervision mission, PFMRP milestones were reviewed to ensure that the key issues highlighted in the PEFA assessment were being addressed by the programme. / DFID is currently undertaking scoping work for designing an additional programme component for supporting PFM reforms in local governments.
1.5 Key challenges / Significant challenges remain which hinder the PFM reform process. These include the following: / Some of the temporal blockages in the PFM process are linked to pending legislative procedures for a host of legislations. / Although PFMRPIV addresses many areas highlighted in PEFA 2013, there were several gaps which are now being addressed through new & revised milestones. There is need for active engagement on these new/revised milestones. / Several non-technical factors impede progress, most of which are beyond the control of MoF – such as extraneous factors influencing budget execution. / Programme coordination is critical for effective implementation. This aspect needs to be further strengthened.
1.6 Annual Outcome Assessment / At the outcome level, there has been good progress in many areas although significant weaknesses remain. / Significant improvement has been made on orderliness and participation in the annual budget process including a new budget cycle from 2013-14 / Tanzania has made significant progress on revenue mobilisation year after year. However, tax exemptions have continued to increase significantly. / Several weaknesses persist in budget execution. High level of reallocations and lack of predictability in fund flow distort the execution of the budget. This affects the overall credibility of the budget. However, there has been improvement in compliance on procurement regulations, in payroll controls and in debt management. / Tanzania continues to show improvement in the functioning of its oversight institutions such as IAGD, NAO, PPRA. / Outcome Indicator Milestone (June 2013) : Target Milestone (June 2013) : Actual / 1 Improved Revenue Management (Primary economic benefit: domestic revenue, other economic benefits include fiscal discipline) Domestic tax revenue and non- tax revenue collection as a % of GDP o/w [Indicator 1b] 17.8% 17.6% (based on RBA 2013) / Tax exemptions as a % of GDP 1.6% (2012/13 FY) 3.1% (2012-13) – source RBA 2012-13 / 2 Improved Budgeting and Planning (Primary economic benefit: Allocative efficiency. Other economic benefits include fiscal discipline) Orderliness and participation in the annual budget process (PEFA Indicator) Recommendations and an action plan submitted on adjustments to the budget legal framework Significant improvement as noted in the PEFA. New budget calendar in place. / % of MTEF Budgets meeting the Medium Term Strategic Planning and Budgeting Manual Requirements (To be measured from end of 2014) Not applicable / 3 Improved budget execution, transparency and accountability (Primary economic benefit: Allocative efficiency and reduced leakages/wastage) Non-salary releases (development funds) to RSs and LGAs by the end of Q3 of the FY, as a % of available resources for the year. (Also a Budget Support PAF Indicator) 65% 59% (2012-13 budget) / Level of compliance to procurement legislation (Budget Support PAF Indicator) - Also a Budget Support PAF Indicator Target being defined to be consistent with the new 2011 Public Procurement Act Average level of compliance for MDAs increased from 65% in 2010-11 to 77% in 2011-12. For LGAs, during the same period it increased from 56% to 67%. / Integrity and content of government financial statements and the migration from IPSAS cash to IPSAS accrual accounting for all government accounts. Completed plan to migrate to IPSAS accrual accounting Achieved. 5 year action plan developed and approved. / 4 Improved Budget Control and Oversight (Primary economic benefit: reduced leakages/wastages) Unqualified audit opinions as a % of the total for MDAs and LGAs Unqualified audit reports for MDAs increased from 85% in 2010-11 to 95% in 2011-12. For LGAs, during the same period it increased from 54% to 78%. / Level of outstanding audit matters (Budget Support PAF Indicator) tbd: Improved performance and reduction in value from the baseline Cannot be rated – NAO has enabled manual consolidation of the audit queries – there is no software database to provide a consolidated tracking of audit matters. / Quality of the External Audit Function (NAO) Future milestones may be derived from the contents of the Committee Report NAO achieved level 3 standard based on AFROSAI-E peer review / Quality of Parliamentary Accounts Committees oversight to be defined As noted by the PEFA, the coverage of hearings by PAC is extensive. However, it takes more than a year for the PAC to review the CAG reports. The recent amendment to the Public Audit Act could further delay this process.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / The programme spending is on track, we are on second year of spending and we have spent, a total of 4, 089,755.21 so far out of planned amount of 5,525,000. Also a total of 1,500,000 planned to be spent before end of this financial year / 2012/13 2013/14 2014/15 2015/16 2016/2017 / Planned Disbursement 2,075,000 3,450,000 3,450,000 3,450,000 3,450,000 / Actual Disbursement 2,002,126.51 2,087,628.79 / 2.2 Key cost drivers / Two key cost drivers were identified in the business case – consultancy services and procurement of goods. DFID T has strived to achieve value for money on these key cost drivers. DPs, including DFID, have exercised close scrutiny of all Terms of References and all deliverables to ensure that outputs meet the agreed objectives, and clear justification is obtained on consultant inputs. DFID has sought to ensure that all procurement guidelines are adhered to, whether initiated by government of by DFID. / 2.3 Is the project on-track against original timescale: Y / We are expecting that the project will achieve its objectives and completed as planned

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The PEFA 2013 assessment provides fresh evidence on the PFM system in the country. By comparing the findings of the PEFA 2013 to the earlier PEFA 2010, the programme has been able to examine the trajectory of PFM reform. PFMRPIV has examined the existing M&E framework in light of the PEFA findings and several milestones have been added and/or revised across different KRAs to make the reform programme more credible and stronger. / 3.2 Where an evaluation is planned what progress has been made? / A mid-term evaluation of the programme is scheduled to be undertaken in the next financial year 2014-15. This will be facilitated by the PFMRP Secretariat. / Apart from the recent independent PEFA assessment of PFM reform in Tanzania, a local government PEFA assessment will be undertaken in 2013-14.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / The programme is judged to be of high risk with the potential of high return. / 4.2 Assessment of the risk level / As indicated in the business case, the overall output risk rating was high – and it continues to remain high. Political and institutional risks are significant and pose key challenges to the achievement of outputs and results. This is also evident from the fact that key legislative changes envisaged during project conception are yet to fructify. / Financial risks are also significant. Currently expenditure commitments are not reported and this makes it difficult to monitor budget execution. To mitigate this risk, a detailed template for financial and procurement reporting has been agreed with GoT. An additional risk pertains to untimely disbursement to components mandated to implement the reforms. Last year, it was evident that some components could not take up or complete activities due to late disbursal of project funds. It is important both for donors and GOT to commit and release funds on time so that components receive funds early in the financial year. / With the proposed expansion of the programme to enable support for PFM reforms at the local level, the risks are likely to increase. However, a detailed risk management action plan will also be developed to enable that appropriate actions are taken to manage and mitigate the risks.
4.3 Risk of funds not being used as intended / The risk of funds not being used as intended is moderate. Approval for each spending proposal is approved by the Joint Steering Committee, which is chaired by the Permanent Secretary and co-chaired by DPs. Programme allocations are then included in the next year’s budget under the PFMRP basket fund and is categorised into local (GoT) spend and foreign (DP) spend. To ensure effective utilisation of programme funds, several agreed risk mitigation measures are being implemented such as random sampling procurement audits on an annual basis (the post-procurement audit for the first year is being designed currently), the Annual Procurement Plan is compliant with the procurement legislation and DP’s are actively involved in scrutinising ToRs before procurement processes are launched. / Audit of project funds is done annually by the CAG. A separate procurement audit is also planned in FY 2013-14. / 4.4 Climate and Environment Risk / The climate & environmental risk is judged to be low for the programme. / On the other hand, improvements in PFM are likely to have a positive impact on how the revenues from natural resources are used, effective expenditure on delivery environmental services (water, sanitation) and Tanzania’s ability to leverage climate finance if it has effective PFM in place. Tanzania’s climate finance has increased (from $50m to over $194m) however most of it remains off budget and this is possibly due to lack of confidence in the financial management systems and lack of clear priorities and investment plans.

5. Value for Money
5.1 Performance on VfM measures / Progress against VfM metrics set out in the Business Case is as follows:-. / Economy / Secretariat costs: - The cost of the GoT Coordination Secretariat (funded from the donor basket) was Tsh124 million in 2012/13 against a budgeted figure of Tsh 700 million. This underspend was because 3 out of 6 posts have been filled so far, one position (PFM advisor) has been cancelled in FY2013/14 and workloads adjusted. The performance of the Secretariat has reached a good standard though there is more to be done to raise the transparency of financial reporting. / Efficiency / Budget execution: -The execution rate of GoT’s development budget improved from 76% in 2011/12 to 85% in 2012/13. Nevertheless significant challenges remain with over-budgeting in the development budget and under-budgeting in some areas of recurrent expenditure, cash rationing, by passing of commitment controls and accumulation of expenditure arrears. The programme is at too early a stage of implementation to asses cost per beneficiary for capacity building activities / Effectiveness / Reduced leakage/wastage:- There have been significant improvements in compliance with procurement legislation. The level of compliance of the top 20 procuring entities (which account for 80% of GoT spend) reached 71.9% in 2012/13 compared with a target of 71.1% in. This is a good result since it is before adjusting for changes in measurement methodology which would have added an additional 5 to 6 percentage points to the level of performance. / Reduced leakage/wastage: - There is evidence that internal controls are improving. The percentage of unqualified audit opinions has generally increased, with minor exception, as shown below. New milestones for IAGD have been agreed to track and ensure action is taken to follow up on compliance with CAG recommendations. / Unqualified audit opinions. / 2010/11 2011/12 / MDAs 85% 95% / LGAs 54% 78% / PAOBs 90% 89% / Reduced leakage/wastage: The level of outstanding audit matter for LGAs improved from 4.5% of total spend in 2010/11 to 3.1% in 2011/12. Aggregate data is not yet available for MDAs. / Domestic revenue: GoT`s revenue yield increased from 15.7% GDP in 2011/12 to 16.1% GDP in 2012/13 and is on a consistent upward trend. Performance was, however, below an ambitious target set by the government to reach 20.3% in 2012/13. / Allocative Efficiency: Data is expected to be available in 2013/14 on the share of MTEF budgets that meet the standards of the Medium-Term Strategic Planning and Budgeting Manual. / Accountability: Tanzania’s Open Budget Index score indicates that fiscal transparency is on an improving trend, as shown below. / Open Budget Index / 2008 2010 2012 / OBI score 36 45 47 / Note: data published every two years / Trigger points / The BC sets out the following criteria for assessing whether VfM should be re-evaluated: / The majority of programme results in the DFID log-frame are being achieved more than 12 months behind schedule; / Budget execution rate stays below 55%; / There are deteriorating trends in quantified targets at the effectiveness level, for example on procurement compliance and audit opinions. / None of the three criteria apply, hence re-evaluation of VfM is not required. / 5.2 Commercial Improvement and Value for Money / All procurement undertaken through the basket funding is compliant with the applicable public procurement regulations and the terms of reference for every procurement is reviewed by the development partners. A post-procurement audit will be undertaken in 2013-14 for auditing procurement undertaken in 2012-13 and findings from the audit will inform the procurement process. Last FY there was a delay in fund disbursal and this impacted several activities adversely – this FY, stronger systems have been put in place to monitor fund disbursal to programme components. DFID has, alongside other DPs, continued to press VfM messages and GoT has shown a fair degree of receptivity. / 5.3 Role of project partners / The role of component partners is critical for achieving VFM. While most government component partners agree with and subscribe to basic procurement regulations, there is need to inculcate among component managers better standards of financial scrutiny and VFM. / Donor partners exercise strong oversight on project financing and clearly drive the VFM agenda. / 5.4 Does the project still represent Value for Money : Y/N / The programme continues to represents very good VfM judged on the basis of performance metrics set out in the BC. / 5.5 If not, what action will you take?

6. Conditionality
No specific conditions for this project

7. Conclusions and actions
The review of progress against the M&E framework suggests that PFMRP Phase IV has progressed well. Over the last year, there has been significant progress on KRA 4 (Budget control and oversight), good progress on KRA 2 (Planning & Budgeting) and KRA 3 (Budget Execution), and limited progress on KRA 1 (Revenue management) and KRA 5 (Change Management). / The TWG discussions also confirmed that component managers are engaged, activities are implemented and developed further. There is also a visible improvement in coordination of efforts by the donor community and their engagement with GoT counterparts. / The following key actions will be undertaken: / Continue to strengthen engagement with different programme components in order to sustain pace and quality of implementation / Pursue actions undertaken by GoT to address the temporal blockages in the PFM process that are linked to pending legislative procedures. / Monitor progress on PEFA related milestones in PFMRPIV on a quarterly basis / Strengthen program coordination with different stakeholders and early identification of emerging challenges to ensure that the momentum of the major cross cutting initiatives is maintained. / Maintain strong oversight on financial reporting on PFMRPIV, along with monitoring of procurement of goods and services. / Update programme logframe in light of new information and action plans by January 2014.

8. Review Process
The Annual Review of PFMRP was undertaken along with the Joint Supervision Mission during Sep 15 – Oct 15, 2013. The primary methodology used during the mission was the Technical Working Groups (TWG) consisting of the key PFMRP Component Managers and DP representatives where extensive discussions were undertaken to jointly assess progress and examine key priorities going forward. Apart from the direct participating departments and agencies, the mission also held discussions with other key stakeholders such as BoT, TRA and select ministries. / The detailed findings from this exercise are contained in the Aide Memoire of the supervision mission 2013. The key findings were also presented to all stakeholders at the wrap-up meeting of the supervision mission on Oct 31, 2013. Changes to milestones, budget allocations and financial reporting were approved by the Programme Management Committee and Joint Steering Committee on Oct 31, 2013.