Business Case

Summary Sheet

Title: Support to the United Nations Relief and Works Agency for Palestine Refugees in the Near East (UNRWA) Syria Emergency Appeals 2017-2020
Programme Summary: To provide essential humanitarian support to Palestine Refugees in Syria (PRS) affected by the ongoing Syrian crisis
Programme Value: £36,000,000		Country/Region: Syria/Middle East
Programme Code: 300389	Start Date: 01 August 2017	End Date: 31 March 2020
Overall programme risk rating:	High
Vault Number:	12989679

Intervention Summary

Narrative summary including why UK support is needed:
DFID will provide £36 million over three years to the United Nations Relief and Works Agency for Palestine Refugees in the Near East (UNRWA) Syria Emergency Appeal.[1] Of the estimated 438,000 Palestine refugees that remain inside Syria (PRS)[2], 418,000 (over 95%) are in acute need of sustained humanitarian assistance in order to survive, including tens of thousands trapped in areas of active conflict or recently reconciled areas.[3] UNRWA is the only organisation mandated to provide protection and assistance for PRS. Without DFID’s continued support to UNRWA there is a high risk that the needs of this extremely vulnerable group will not be met. DFID have identified PRS as a target group in the Humanitarian Approach for Syria. Amongst the PRS population, DFID support will focus on those with the most acute needs, including those living in besieged and hard to reach areas, and collective shelters; the disabled; pregnant and lactating women; and those at risk of sexual and gender based violence.
[1] This funding will be targeted towards the Syria-specific elements of the Emergency Appeal, not Jordan, Lebanon or Regional components
[2] UNRWA’s 2016 verification survey released in June 2017 documents there are 438,000 PRS remaining in Syria.
[3] Humanitarian Needs Overview (December 2016)

The programme will contribute to DFID’s overarching goal to save lives, protect civilians, reduce suffering and build resilience by providing essential humanitarian support to PRS, who reside in official and unofficial camps located in both government- and opposition-held areas across five governorates.[4] This will include the provision of cash, food and emergency relief items, livelihood support, protection assistance and basic services, such as education and healthcare. Since the start of the Syrian crisis, UNRWA has a strong track record in providing humanitarian assistance.[5] Through a network of 219 facilities and 4,000 staff in Syria, nearly all of whom are PRS themselves; UNRWA directly implements its programmes. UNRWA manages the end-to-end supply chain where goods remain in UNRWA’s custody from delivery at the port/airport of arrival until distribution directly to beneficiaries, or via UNRWA health clinics and schools.
[4] A Palestine refugee camp is a plot of land where the host government has given UNRWA permission to accommodate Palestine refugees and set up facilities that address their needs
[5] UNGA resolution 302 (IV) of 8 December 1949 - http://unispal.un.org/UNISPAL.NSF/0/AF5F909791DE7FB0852560E500687282

Results will be based on DFID’s share of UNRWA’s Syria Emergency Appeal each year. DFID’s funding will support UNRWA in 2017 to provide: [6][7]
[6] £12m in 2017 will equate to 4.7% of these results from UNRWA’s 2017 Syria Appeal ($15,600,400 as of 23.05.2017 oanda).
[7] UNRWA’s 2016 verification survey released in June 2017 documents there are 438,000 Palestine refugees remaining in Syria, 418,000 of which are in acute need of humanitarian assistance including approximately 254,000 displaced at least once within Syria. The targets listed here are as noted in UNRWA’s 2017 Syria Appeal (released early 2017), although we have updated cash, food and NFI targets to reflect latest caseload data. Any changes over 2017 and results achieved against 2017 Appeal targets will be described in UNRWA narrative reporting and DFID Reviews.
- 418,000 PRS with cash and in-kind food assistance
- 254,000 PRS with non-food items, such as blankets, mattresses and hygiene kits
- 2,600 PRS with shelter assistance, including the provision of daily hot meals
- 1,400 students to complete short term technical and vocational education and training
- 1,000,000 PRS visits to UNRWA health facilities
- 3,500 PRS students graduating from basic education
- 30,000 children with psychosocial support
- 39,750 PRS with microfinance loans to enable households to cover unforeseen expenditures and to start up small businesses.

Does the programme fit with DFID’s strategic architecture?
Yes. This programme is a key deliverable under the 2015 UK Aid Strategy which commits the UK to respond to humanitarian emergencies. [8] By providing cash and food assistance, microfinance loans and vocational training, UNRWA will improve the resilience of thousands of PRS in the first year; delivering on Objective 2 (strengthening resilience and response to crisis); and Objective 4 (helping the world’s most vulnerable). The programme goals align with the National Security Strategy and Strategic Defence and Security Review 2015 which note the consequences of conflict and instability overseas for UK peace, security and prosperity.[9] It complies with the International Development Act by contributing to poverty reduction and protection of the most vulnerable, contributes directly to all DFID Syria Business Plan objectives (protection, resilience and conflict reduction), and is in line with Grand Bargain commitments, and the DFID Syria Humanitarian Approach of supporting those most acutely in need.
[8] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
[9] http://webarchive.nationalarchives.gov.uk/20121015000000.pdf

What percentage of DFID’s Single Departmental Plan (SDP) results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
This programme will make a very small contribution to the SDP targets. It is aligned to all SDP 2015-2020 objectives: (1) strengthening global peace, security and governance; (2) strengthening resilience and response to crisis; (3) promoting global prosperity; (4) tackling extreme poverty and helping the world’s most vulnerable.

Is the programme coherent with the wider international community and partner government response?
Yes. It is aligned with the international Syria Humanitarian Response Plan (HRP) and UNRWA participates in the cluster system to coordinate the assistance provided to PRS with the international community’s support to Syrians. The UK has consistently been one of UNRWA’s top five donors. Other top donors of UNRWA for the Syria Appeal include the US, the EU, Sweden and Germany.[10]
[10] https://www.unrwa.org/syria-crisis

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Yes. DFID Syria will continue to work closely with the FCO to advocate for improved humanitarian access and protection of civilians inside Syria. Accessing cross-HMG funds is not appropriate for the delivery of this humanitarian assistance.

How does the programme relate to other UK aid within the specific sector?
This business case is part of a package of UK support to UN agencies and INGOs to address the protracted crisis in Syria and meet humanitarian needs. DFID Syria’s multi-year funding will align with DFID’s Occupied Palestinian Territories (OPTs) core funding to UNRWA’s Programme Budget and will be used to further incentivise UNRWA to progress UK reform priorities.

Is there sufficient flexibility to learn and adjust to changes in the context?
Yes. DFID Syria’s Humanitarian Approach commits DFID to maintain a flexible programmatic approach and regular scenario planning, to allow DFID support to respond to the changing dynamics of the conflict, delivering large volumes of life-saving assistance with real impact. DFID will provide an unearmarked commitment of £36 million to enable UNRWA Syria to flexibly respond to the rapidly changing context. The scale and multi-sectoral coverage of UNRWA’s work enables them to flexibly meet evolving PRS needs.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. This is a severe risk programme, given the Syrian context, but this should be weighed against the high return of intervening to save lives and provide basic services for PRS. Mitigation actions are set out in the Management Case and include third party monitoring, due diligence and quarterly review meetings.

Is there a clear communications strategy and use of UK aid logo?
DFID Syria will liaise with DFID’s Communications Division and DFID OPTs to identify opportunities for announcements of this funding in line with DFID guidelines. UNRWA does not use the UK aid logo in Syria given the Syrian regime’s prohibition of donor logo branding as conditionality to operate, however UNRWA ensures that both international and local stakeholders are made aware of donor contributions through media coverage and public information materials.

Has the programme been quality assured and is it able to deliver?
This programme has been quality assured by DFID including humanitarian, education, health, livelihoods, conflict and social development advisers and monitoring, commercial, finance, value for money and risk specialists. Given UNRWA’s track record in providing humanitarian assistance since the start of the Syria crisis, and knowledge of the region since 1949[11], we are confident that it is the right organisation to deliver a programme of this size to support vulnerable PRS in an unstable environment. DFID’s 2017 UNRWA Syria Due Diligence Assessment concluded that UNRWA Syria’s capacity and capability is sufficiently robust to respond to the risks associated with operating in Syria and to deliver the programme (see Management Case C).
[11] UNGA resolution 302 (IV) of 8 December 1949 - http://unispal.un.org/UNISPAL.NSF/0/AF5F909791DE7FB0852560E500687282

Does the SRO and team have the capability and resources to deliver this programme?
Yes. The SRO is the A2 Syria UN Team Leader and is supported by a Programme Manager and Humanitarian Adviser. Further support comes from a wider Advisory team as listed above.
Strategic Case

Context
The 1948 Arab-Israeli conflict and formation of the State of Israel resulted in over 700,000 Palestinians leaving their homes and becoming refugees, including to Syria.[12] Prior to 2011, there were approximately 560,000 Palestine refugees living in official and unofficial camps in Syria. The environment within PRS camps was generally poor, with high population density, cramped living conditions and inadequate basic infrastructure such as roads and sewers. Despite having access to social services provided by the Syrian Government, Palestine refugees have lagged behind the Syrian host population in key development indicators. For example, Palestine Refugees in Syria (PRS) had higher rates of infant mortality and lower rates of school enrolment, and their long-term future was uncertain.[13]
[12] 726,000 according to the United Nations Conciliation Commission. UNRWA’s defines Palestine refugees as “persons whose normal place of residence was Palestine during the period 1 June 1946 to 15 May 1948, and who lost both home and means of livelihood as a result of the 1948 conflict.”
[13] https://www.unrwa.org/where-we-work/syria

Since 2011, the world’s most complex crisis has taken hold in Syria. Political, security and humanitarian implications of this conflict are not limited to Syria but have regional and global impact, with the involvement of multiple international and regional actors. Humanitarian access is routinely denied, despite Security Council interventions, and starvation used as a weapon of war. Sexual and gender based violence (SGBV) and forced conscription are commonplace. Civilian infrastructure has been purposely targeted, seriously depleting essential services. The violence and brutality – which represent significant violations of international humanitarian law (IHL) and international human rights law (IHRL) – have set a new and disturbing precedent internationally, and are conducted with impunity. This may be contributing to the rise of extremism and sectarian division, allowing extremist groups to expand.

6.3 million people have been internally displaced within Syria (approximately 35% of the total population), including 254,000 PRS (58% of the PRS population).[14][15][16] As of May 2017, there are 4.35 million people living in areas where humanitarian access is extremely restricted in besieged and hard to reach areas, including 28,900 PRS (7% of the PRS population). It is estimated that 438,000 Palestine refugees remain in Syria today, while an additional 122,000 have fled the country in search of safety.[17] Since 2014, PRS have been prevented from entering Jordan and Lebanon, severely limiting their options to escape violence and presenting PRS fewer coping mechanisms than their Syrian counterparts.[18]
[14] Evaluation of OCHA response to the Syria crisis, Sida et al, March 2016
[15] http://www.unocha.org/syrian-arab-republic/syria-country-profile/about-crisis
[16] UNRWA’s 2016 verification survey released in June 2017 documents that 254,000 PRS have been displaced at least once within Syria.
[17] UNRWA’s 2016 verification survey released in June 2017 documents there are 438,000 PRS remaining against the 560,000 individuals registered with UNRWA in Syria.
[18] UNRWA Syria Regional Crisis 2016 Emergency Appeal Progress Report

The protracted conflict has caused further socioeconomic deterioration and vulnerability for PRS due to the proximity of camps to conflict areas, particularly in Rural Damascus and Aleppo governorates. Approximately 80% of PRS reside in Damascus, including in areas with restricted humanitarian access.[19] All 12 Palestine refugee camps in Syria have been severely affected by violence and many remain battlegrounds with limited access. Reports note that PRS are particularly vulnerable and are “uniquely in peril as a population”.[20][21]
[19] UNRWA Syria Regional Crisis 2016 Emergency Appeal Progress Report
[20] Evaluation Synthesis and Gap Analysis – A synthesis and analysis of 24 publicly available evaluative studies concerning the international response to the Syria crisis, James Darcy, May 2016
[21] Evaluation of OCHA response to the Syria crisis, Sida et al, March 2016

The majority of Palestine refugees living in Syria will remain displaced in 2017.[22] Mass displacement and exposure to conflict has stripped Palestine refugees of their livelihood assets. 418,000 (over 95%) are in acute need of sustained humanitarian assistance in order to survive, [23] including tens of thousands of PRS trapped in areas of active conflict or recently reconciled areas such as Yarmouk, Khan Elshieh and Dar’a.[24]
[22] UNRWA Syria Regional Emergency Appeal 2017
[23] UNRWA Syria Regional Emergency Appeal 2017 (p.17)
[24] Humanitarian Needs Overview (December 2016)

Unemployment has risen rapidly, while the loss of businesses and a contracting economy have left families without a source of income. PRS are not permitted to own farmland in Syria (nor do they own the land upon which their houses are built).[25] As a result, food insecurity among PRS has risen significantly and remains one of the most critical humanitarian concerns for PRS[26]. Increasing prices and constrained access to markets has prevented families from meeting their minimum nutritional requirements. Food insecurity has had a particularly negative effect on the elderly, people with disabilities, female-headed households and children. 418,000 PRS are in need of regular food assistance.[27] The protracted nature of the crisis has pushed many to the brink of survival, forcing families to resort to harmful coping mechanisms, including reducing expenditure on food by skipping meals or reducing the nutritional value of meals.
[25] As official camps are set up on state land or land leased by the host government from local landowners, PRS only have the right to ‘use’ land for a residence. They are not land owners themselves.
[26] UNRWA 2016 Annual Operational Report
[27] UNRWA Syria Regional Emergency Appeal 2017

The protection needs of PRS remain acute, primarily as a result of continued exposure to armed conflict. Shifting conflict lines mean that a significant proportion have been forced into a pattern of repeated displacement, as episodes of intense fighting erupt in previously safe areas. It is estimated that 254,000 Palestine refugees (58%) have been displaced at least once within Syria.[28] The majority of PRS live in inadequate and crowded collective shelters, or expensive private accommodation.
[28] UNRWA Syria Humanitarian Snapshot April 2017

Widespread fighting has not only forced massive population displacements but also trapped tens of thousands in areas such as Yarmouk, Khan Elshieh and Dar’a governorate. Significant protection risks and vulnerabilities have emerged, including: psychosocial trauma and disorders, particularly among children; kidnappings and forced detention; increased rates of GBV, substance abuse, sexual exploitation and abuse; exposure to crime; and exclusion and discrimination, particularly for people with disabilities, the elderly, women and girls.

Major damage to health facilities over six years of conflict has had a significant impact on the Syrian public health system and capacities to provide healthcare to PRS. The flight of qualified health staff, higher costs for medical supplies and hospitalisation services, and reduced options for referral, also impact on delivery capacity. The number of PRS accessing maternal care and non-communicable disease services remains significantly lower than pre-crisis levels, as are vaccination rates for Palestinian children, suggesting ongoing difficulties to access services. A recent survey of the socioeconomic status of PRS concluded that, amongst children under 5 years of age, nearly 20% were suspected to have had pneumonia and 17% suffered from diarrhea during the two weeks preceding the survey.[29]
[29] Situation Assessment of Palestinian Refugees in the Syrian Arab Republic (2016), General Administration for Palestine Arab Refugees (GAPAR)

The conflict in Syria has also resulted in the deterioration of water, sanitation and hygiene (WASH) services, in particular water supply and sewage networks. [30] The combination of limited personal and domestic hygiene, reduced access to potable water, poor environmental conditions and lack of basic sanitation increase the risk of disease (including water-borne) outbreaks amongst PRS. Less than 40% of PRS living in camps have water piped directly to their shelter.[31]
[30] UNRWA 2016 Annual Operational Report
[31] Situation Assessment of Palestinian Refugees in the Syrian Arab Republic (2016), General Administration for Palestine Arab Refugees (GAPAR)

Palestine refugee children continue to be severely affected by the protracted crisis in Syria, with at least 86,000 forced to flee from their homes and many more exposed to the trauma of armed conflict and the loss or separation of family members. A critical component of this ongoing trauma has been the inability to access regular education, depriving children of the opportunity to learn, socialise and grow, while forcing them to remain unoccupied at home, often in highly insecure environments. In September 2016, 44,597 Palestine refugee children started the new school year, compared with a pre-crisis population of 67,000 in 2010.[32] Within this context, there is an ongoing need for investments in sustaining and rehabilitating direct education services, while continuing to develop innovative and new ways of reaching students who are unable to attend as a result of the surrounding conflict.
[32] UNRWA Syria Regional Emergency Appeal 2017

How does DFID propose to address these needs?
UNRWA has a unique mandate to provide basic services, humanitarian assistance and protection for Palestine refugees.[33] Since 1950, UNRWA has worked with PRS and the Syrian Government[34] to provide free education, health, relief and social service programmes to meet the needs of PRS. Inside Syria, UNRWA is often the only organisation with the access, permission and capacity required to assist Palestine refugees.
[33] UNGA resolution 302 (IV) of 8 December 1949 - http://unispal.un.org/UNISPAL.NSF/0/AF5F909791DE7FB0852560E500687282
[34] General Administration for Palestine Arab Refugees (GAPAR)

UNRWA manages 219 facilities across Syria, established over 60 years. UNRWA employs a network of 4,000 frontline delivery staff, including doctors and teachers, almost all of which are PRS themselves (see Figure 7). Given this considerable operational capacity, extensive network inside Syria and PRS-focused mandate, UNRWA’s comparative advantage allows for the direct delivery of basic services and humanitarian assistance that meet the extensive, multi-sectoral needs of Palestine refugees. To continue meeting PRS needs as the conflict has evolved, UNRWA has adopted a highly flexible approach of providing life-saving humanitarian assistance, supporting livelihoods and rehabilitating existing facilities, alongside continuing to deliver the basic services available prior to the conflict.

UNRWA remains, and will continue to be, the main provider of humanitarian assistance, protection and basic services to PRS. No other humanitarian organisation within the UN, Red Cross/Crescent Movement or international NGO community specifically targets PRS. Recognising the specific needs of PRS and their inability to directly access this vulnerable group, some UN agencies support PRS through direct funding to UNRWA. For example, OCHA provides UNRWA with pooled funds to rehabilitate and maintain PRS shelters; UNESCO funds UNRWA to undertake small-scale training activities; and UNICEF funds youth programmes. UNRWA also participates in overall Whole of Syria coordination mechanisms and is an active partner in clusters for food security, education, health, NFIs, shelter, early recovery and protection. UNRWA’s cluster participation and channelling of other UN funding ensures that humanitarian assistance offered to PRS is of a similar standard and quantity received by vulnerable Syrians from other organisations.

Since before the Syrian conflict, DFID’s Occupied Palestinian Territories team (OPTs) has, and continues, to support UNRWA’s core Programme Budget, delivering basic services across UNRWA’s five fields of operation – Gaza, West Bank, Lebanon, Jordan and Syria. However, the scale of increased humanitarian need for PRS and level of destruction sustained by the health and education systems has put additional pressure on already strained UNRWA services. Since 2012, eight out of 23 UNRWA health centres have become unusable or inaccessible, and only 24 out of the original 58 UNRWA school buildings remain accessible for education purposes.[35] UNRWA has become the sole provider of all services for most PRS and, in response, launches an additional annual UNRWA Syria Appeal to ensure these increased needs can be met. The funding from this Business Case proposes to directly support UNRWA’s Syria Emergency Appeal in 2017, 2018 and 2019.

Why should DFID provide additional humanitarian aid?
The rationale for this investment is three-fold. It ensures vital humanitarian needs are met, supports wider HMG objectives and contributes towards the UK’s international commitments.

Meeting humanitarian needs
Syria is the world’s largest and most complex humanitarian crisis. Inside Syria, over 400,000 lives have been lost and 6.3 million people are estimated to be internally displaced (approximately 35% of the total population) [36], including 254,000 PRS (58% of the PRS population).[37] 13.5 million people (80% of Syrians) live in poverty and are unable to meet their basic needs without humanitarian assistance, including 95% of the PRS population.[38] More than 60% of the labour force is estimated to be unemployed.[39]
[36] The UN stopped counting this figure in 2014. UN Special Envoy Staffan de Mistura provided this estimate in a media conference on 22/4/16. This number is much higher
[37] Evaluation of OCHA response to the Syria crisis, Sida et al, March 2016; UNRWA 2016 verification survey released in June 2017
[38] Syria Humanitarian Response Plan 2016
[39] IMF, June 2016, Syria Centre for Policy Research, March 2015

Despite $1.6 billion funding received against the UN-coordinated Syria Humanitarian Response Plan (HRP) 2016, it was only 49.2% funded.[40] It is clear that all needs in Syria are not being met. Additional support is required to provide urgently needed assistance to millions in dire need of protection, food, water, medicine, shelter, education and livelihoods. The 2017 HRP seeks $3.4 billion to assist 13.5 million people in Syria this year, with the UNRWA Emergency Appeal for Syria calling for $329 million to support PRS alone.
[40] https://fts.unocha.org/appeals/501/summary as of 25.01.2017

Delivering broader UK objectives
The UK Aid Strategy 2015 commits the UK to responding to humanitarian emergencies as the root causes of instability and conflict. Such crises, if unaddressed, often have direct impact on the UK, for example by contributing to irregular migration, transitional crime and terrorism.

HMG’s vision for Syria – as set out in the UK’s National Security Council strategy – is that we see progress towards ending the Syria conflict through an inclusive political settlement, with Syria presenting a reduced threat to UK national security, and better meeting the needs of its own people.[41] This is achieved through political, security and resilience objectives.
[41] http://webarchive.nationalarchives.gov.uk/20121015000000/http://www.direct.gov.uk/prod_consum_dg/groups/dg_digitalassets/@dg/@en/documents/digitalasset/dg_191639.pdf

DFID’s approach to Syria is fully aligned behind these objectives and is informed by analysis of possible scenarios. It has three key strands: i) protection and relief to meet the most pressing humanitarian needs; ii) resilience building to strengthen the capacity of individuals, households and communities to deal with the impact of conflict where they are, and; iii) conflict reduction/peace-building to support Syrian communities, including moderate voices, to mitigate local conflict, build dialogue, lay the foundations for a future political settlement and offer an alternative to extremist groups. This is underpinned by DFID engagement with the international system to ensure that UK and international resources are used efficiently and effectively, offer the best possible value for money and are well coordinated.

This intervention supports the delivery of all three DFID strands:
1. Protection and relief: By providing cash, food and NFI assistance, and supporting livelihoods, this programme will help to reduce the risk of vulnerable PRS households relying on negative coping strategies and exposing themselves to protection risks (see Strategic Case A). UNRWA collective shelters will continue contributing to the protection, health and well-being of displaced PRS.
2. Building resilience: This programme will protect and restore livelihoods, improve the food security of PRS and strengthen resilience to ongoing and future conflict-related shocks.[42] Specific activities include provision of microfinance loans, in particular women and youth, to start-up small businesses and cover unforeseen basic living expenses, thereby restoring livelihoods and revitalising local economies. Young PRS will also receive vocational training and support to find longer-term job placements.
  [42] Syria Regional Crisis, UNRWA Emergency Appeal, 2017
3. Conflict reduction/peacebuilding and extremism, violent extremism and terrorism (EVET): While not a direct objective of UNRWA’s programme, several activities are expected to have a positive impact on mitigating local conflict and the drivers of extremism and support conflict reduction and peacebuilding. Individuals and households with a reliable source of income are less likely to engage in negative coping strategies, such as joining armed groups to engage actively in the conflict. By providing timely and reliable information on rights, social and legal services and access to legal aid, communities are able to make better informed choices and improve access to life-saving services, which in turn reduces community tensions.

Delivering DFID Syria Commitments
DFID Syria’s Humanitarian Approach recognises that the key constraint on reaching the most severely in need is access and, whilst understanding the risks and encouraging the international community to do the same, aims to (1) focus UK humanitarian aid on the most acutely in need, including particularly vulnerable groups such as PRS; (2) ensure the international response is fit for purpose, and; (3) future-proof our humanitarian response. This programme is aligned with this approach through: flexibility; targeting funding to the vulnerable Palestine refugee population group, and within that the subset of PRS most acutely in need, and; alignment with DFID OPTs and CHASE to ensure our response in Syria complements the reform of the humanitarian system and DFID and UNRWA Grand Bargain commitments.

Realising international commitments and UN reform
On 4-5 April 2017 the UK co-hosted the Brussels Conference on “Supporting the Future of Syria and the Region”, building on the unprecedented outcomes of the UK-hosted London Conference in February 2016. The Conference resulted in the pledging of $6 billion for 2017 and $3.7 billion for 2018-20 for Syria and the region. This programme (and the other Syria humanitarian Business Cases which are being submitted to Ministers) will ensure that the UK is able to meet its own commitments made at the Brussels Conference to spend £1 billion between 2017-2019, addressing the Syria crisis in the region.

This three-year commitment is aligned with the Grand Bargain commitments made by the international community including UNRWA and the UK at the World Humanitarian Summit including: the increased use of cash; accountability to affected populations; multi-year planning; and harmonised and simplified reports (see Commercial Case C). The benefits are multiple and include respecting the dignity and greater choice for affected populations and better Value for Money (see Appraisal Case J).

Working across the UK government
We will continue to work across the UK government and use our technical, policy and diplomatic instruments to allow partners to deliver aid effectively and promptly to all those in need, including in besieged and hard to reach locations. Close collaboration with the Foreign Office across the Syria Overseas Network, London, Geneva and New York has been critical so far and helped put pressure on conflict parties to comply with International Humanitarian Law, allow safe and unimpended access to populations in need and protect civilian populations and humanitarian personnel and assets.

Impact and Outcome expected
The impact of this programme is to save lives, protect civilians, reduce suffering and build resilience, and will be achieved by alleviating the critical needs of 418,000 Palestine refugees affected by the conflict in Syria. Figure 1 below shows the results chain for this programme. UK-attributable results will be calculated according to DFID’s share of UNRWA’s Syria Appeal each year (at this stage the indicative DFID percentage share is 4.7%).[43]
[43] DFID’s guaranteed contribution of £12m in 2017 equates to 4.7% of UNRWA’s 2017 Syria Appeal ($15,600,400 as of 23.05.2017 oanda)

Figure 1: Results Chain
OUTPUTS				OUTCOME		IMPACT
	PRS are provided with safe and timely access to quality assistance, services and support networks (food, cash, NFIs, shelter, health, education and protection) / PRS reduce reliance on negative/irreversible coping mechanisms and build their resilience (microfinance and vocational training)			PRS are able to meet their essential life-saving needs and cope with sudden crisis		Lives saved, civilians protected, suffering reduced and resilience built

Outputs
In order to achieve these changes, DFID will support the following key activities:

1. Palestine refugees in Syria are provided with safe and timely access to quality assistance, services and support networks, by:

Providing relief assistance (cash, food, non-food items and shelter)
UNRWA implements the largest cash-based programme in Syria, helping PRS meet their humanitarian needs with the dignity of choice. In 2017, cash assistance (for both food and non-food items) will remain the largest and most critical element of UNRWA’s humanitarian response, accounting for approximately 60% of expenditure.

UNRWA plans to distribute cash grants of US$35 per month to 418,000 refugees identified with acute needs, through six distribution rounds in 2017.[44] Each distribution will cover two months (i.e. US$70). Through a network of commercial banks and financial institutions, UNRWA is able to provide cash assistance in a flexible and timely manner with minimal distribution costs and financial risk (see Financial Case). The number of beneficiaries is updated after each distribution round. An annual verification exercise ensures all eligible Palestine refugees remaining in Syria are assisted. Cash assistance has proven an efficient and effective means of responding to needs, allowing UNRWA to support Palestine refugees across the country, including in areas of active conflict.[45]
[44] UNRWA Syria Regional Emergency Appeal 2017
[45] UNRWA 2016 Annual Operational Report

In a context of dysfunctional and sometimes hard to reach markets combined with rising prices for staple commodities, in-kind food assistance remains a priority for UNRWA Syria.[46] 95% of PRS registered with UNRWA rely on food assistance. UNRWA will provide in-kind food assistance to meet immediate, life-saving needs of up to 418,000 critically food insecure PRS. Food parcels will meet approximately one third of daily caloric needs (almost 700 kcal per person, per day) and are adapted to the specific needs of beneficiaries (e.g. size of the household, people living in collective shelters and hard-to-reach areas). It is expected that PRS will use a portion of their cash grants to meet remaining food needs.
[46] UNRWA 2016 Annual Operational Report

UNRWA will provide non-food items (NFIs), such as blankets, clothes, mattresses and hygiene kits to 254,000 internally displaced and other vulnerable PRS, including pregnant women, people living in hard-to-reach and besieged areas, and those in collective shelters. The distribution of NFIs will help PRS meet their minimum needs, especially during winter.

UNRWA will continue providing assistance for approximately 2,600 internally displaced PRS living in collective shelters (such as garbage collection, rehabilitation of sewage systems infrastructure, provision of equipment, spare parts and fuel). In addition to receiving cash assistance, food parcels and NFIs, these beneficiaries will also benefit from the provision of daily hot meals, access to WASH facilities, protection services and education.

To deliver humanitarian assistance to Palestine refugees living in hard-to-reach and besieged areas (estimated to be 43,000 people), UNRWA runs five mobile and 13 fixed distribution centres close to these locations and also participates in inter-agency convoy missions.

Improving access to health care services
Looking beyond emergency response operations; health and education services are central pillars to Palestine refugee resilience in Syria. UNRWA will continue delivering primary health care to all PRS (438,000 people), with a focus on people living with disabilities, pregnant and nursing women, and those living in hard to reach and besieged areas. This assistance will be provided through 15 health centres and 11 health points throughout the country, and support for referrals for hospital care.

UNRWA health centres and health points provide a range of primary medical services, including out-patient consultations, vaccinations, growth monitoring, provision of medicines, gynaecology consultations, laboratory services, non-communicable disease care, maternal and child health, and dental services. Due to ongoing conflict, the risk of disease outbreaks has increased, especially in hard-to-reach and besieged areas where humanitarian responders have limited access. UNRWA maintains the capacity to deploy emergency health teams to areas of active conflict and displacement, in the event of localised crises. In 2017, UNRWA will roll-out a new electronic medical records system (e-Health) in a number of facilities and reposition two existing health centres, with the aim of maximising its reach for all PRS.

Supporting education
Access to education provides stability and protection and contributes to building new opportunities and bringing hope amidst crisis. Providing high-quality and inclusive education for 45,000 Palestine refugee students in Syria remains a key priority. Through the Education in Emergencies programme, UNRWA will build the capacity of over 1,700 teaching staff throughout the country and expand the number of safe learning spaces in order to support a larger number of children with specific educational needs. UNRWA will continue to expand psychosocial support to 30,000 Palestine refugee students by increasing the number of counsellors located in UNRWA-managed schools to 47 (one for each school). With UNRWA support, students and school personnel will build their essential survival skills in a context where schools are frequently exposed to violence. To support children who cannot regularly access schooling, UNRWA has developed self-learning materials (SLM), such as textbooks, online interactive learning and educational games, and DVDs, across the core subjects of Arabic, English, science and mathematics.[47]
[47] UNRWA Education in Emergencies in Syria https://www.unrwa.org/sites/default/files/eie_in_syria.pdf

Strengthening protection services
UNRWA will maintain its strong focus on providing service referrals for all PRS identified as experiencing a protection risk and requiring psychosocial support. Area Support Officers will provide legal, social and psychosocial support, enhance protection mainstreaming, case tracking and referrals, and protection capacity building of staff across the country. Group and individual therapy sessions for children will be implemented in 15 UNRWA-managed schools. Through training initiatives, UNRWA will build its capacity to strengthen internal and external referral processes for high-risk protection cases, including those (children and women) affected by violence, GBV, abuse and neglect. In 2017, UNRWA will expand its partnerships with external service providers, including for specialised services persons with disabilities.

2. Palestine refugees reduce reliance on negative/irreversible coping mechanisms and build their resilience, by:

Supporting employment opportunities:
Livelihood interventions are crucial for improving the resilience of PRS, who continue to face multiple shocks, including exposure to violence, lack of income and prolonged displacement. Alongside the direct employment of PRS by UNRWA, livelihoods interventions will focus on microfinance and Technical and Vocational Education and Training (TVET).

UNRWA’s microfinance programme will provide loans to both internally displaced Syrians and Palestine refugees. Analysis of current activities suggests that consumer loans are the most requested, which enable households to cover unforeseen expenditures such as the purchase of assets. In 2017, UNRWA will continue providing inclusive financial services through the direct disbursement of 39,750 loans. As the Syrian Pound continues to steeply depreciate, this programme reflects growing demand for financial products amongst conflict-affected PRS.

UNRWA will provide 600 young PRS with long-term vocational training and job placement support so as to improve their future employment opportunities. TVET technical staff have reviewed the courses on offer based on feedback received from employers and students, and regular market assessments. This ensures the continued relevance and effectiveness of the TVET programme, particularly as the socioeconomic situation in Syria remains fluid and restrictive. In 2017, UNRWA will expand the number of courses provided to students, particularly through satellite centres in Homs, Dar’a and Lattakia.

F. Gender Equality Act
This programme meets the requirements of the International Development Gender Equality Act 2014. UNRWA helps promote gender equality and empower women and girls (Global Goal 5) by ensuring equal access to services for girls, boys, women and men, and through providing specific services targeted at female-headed households and girls and women experiencing gender-based protection threats (see Appraisal Case F).

G. Counter Terrorist Financing
UN agencies are not legally subject to UK counter terrorism legislation or Member State sanctions regimes, but DFID mandates all partners to ensure funds do not support terrorist activity. UNRWA has confirmed that it complies with all applicable UN anti-terrorism resolutions and sanctions. A clause banning the financing of any terrorist activity or individuals will be included in the signed Memorandum of Understanding citing UN Security Council Resolutions S/RES/1269 (1999), S/RES/1368 (2001), and S/RES/1373 (2001). Although UNRWA does not implement activities through downstream partners, they do contract suppliers. DFID will request UNRWA provides a list of suppliers contracted in Syria and DFID will check these against European Union sanctions to ensure UK funds are not used to support them.

## Appraisal Case

What are the feasible options that address the needs set out in the Strategic Case?
In 2016 DFID Syria conducted a portfolio review to consider which Agencies were best able to deliver strategic objectives outlined in the DFID Syria-Turkey Business Plan. Options for reaching PRS are limited. UNRWA is the only humanitarian organisation, amongst the UN, Red Cross/Crescent movement and international NGOs, to focus on PRS, and often the only organisation with the access, permission and capacity required to provide assistance. Since its establishment in 1949, UNRWA has been uniquely mandated to provide basic services, humanitarian assistance and protection to Palestine refugees worldwide.[48] UNRWA has consistently demonstrated its capacity to address PRS’ needs, including in besieged and hard-to-reach locations, through its existing infrastructure, cluster system participation and extensive Syrian networks (including 219 facilities and 4,000 staff across the country). Supporting other UN agencies or NGOs to meet PRS needs is not a feasible option.
[48] UNGA resolution 302 (IV) of 8 December 1949 - http://unispal.un.org/UNISPAL.NSF/0/AF5F909791DE7FB0852560E500687282

The Strategic Case identifies the scale of need. Four options have been considered:
Option 1:	Do nothing
Option 2:	Provide unearmarked funding to the UNRWA Syria Appeal
Option 3:	Provide earmarked funding to specific activities under the UNRWA Syria Appeal
Option 4:	Provide core funding to UNRWA’s overall Programme Budget

Option 1: Do nothing
Not funding UNRWA Syria would allow DFID to prioritise both budget and staff time towards other programmes, but would result in DFID not being able to reach a uniquely vulnerable target group, given UNRWA’s exclusive mandate. As the second largest donor to UNRWA’s Syria Appeal this would severely impact on the scale of UNRWA’s activities in 2017 and on the lives of PRS. Previous appeals have been underfunded, including only 54% of required funds secured in 2016. As a result, the number of cash rounds was halved. Without the predictability of UK support, UNRWA has limited ability to formulate longer-term plans, resulting in significant gaps in the overall Syria response.

Option 2: Provide unearmarked funding to the UNRWA Syria Appeal
Successful delivery of this programme, while ensuring value for money, will require significant procurement and logistical capacity, an ability to rapidly assess changing needs and capacity to coordinate delivery at scale. Unearmarked DFID support allocated to UNRWA’s Syria Appeal would allow UNRWA to flexibly prioritise funding according to severity of needs.

Option 3: Provide earmarked funding to specific activities under the UNRWA Syria Appeal
While earmarked funding would provide DFID increased control over how support is allocated under the Syria Appeal, this option would also prevent UNRWA from rapidly responding to changing conflict contexts and needs.

Option 4: Additional DFID OPTs core funding to UNRWA’s Programme Budget
Providing additional core funding to UNRWA’s Programme Budget would signal the UK’s continued commitment to UNRWA and could be delivered through DFID OPTs’ existing financing arrangement (see Management Case A).[49] Additional core funding would ensure UNRWA has greater resource flexibility when implementing basic health and education services across all fields of operation. However, there is no guarantee that additional UK funds would be allocated to the Syrian crisis since UNRWA use a separate funding stream to respond to this emergency.
[49] DFID OPTs has allocated up to £167.5m to UNRWA’s Programme Budget over 2016-2021 (yet to be announced).

Costs and benefits
Figure 2 considers the different ways DFID could support UNRWA Syria 2017-2020.

Figure 2: Appraisal Options
	Option 1	Option 2	Option 3	Option 4
Mechanism	Do nothing	Unearmarked Syria-specific funding to support the UNRWA Syria Appeal	Earmarked funding to specific activities under the UNRWA Syria Appeal	Additional core funding to UNRWA’s Programme Budget
Cost	£0 million	£36 million	£36 million	£36 million
MENAD management time	Low: some time required to respond to enquiries on why DFID is not funding UNRWA’s Syria response	Medium: Administration time for management, monitoring and evaluation, including: / 0.3 FTE Deputy Programme Manager; 0.2 FTE Humanitarian Adviser; 0.1 FTE Senior Responsible Owner, and; contributions from wider Advisory team and monitoring, finance, risk and due diligence staff.	Medium: Administration time for management, monitoring and evaluation, including: 0.3 FTE Deputy Programme Manager; 0.2 FTE Humanitarian Adviser; 0.1 FTE Senior Responsible Owner, and; contributions from wider Advisory team and monitoring, finance and due diligence staff. Additional time required initially to establish priorities and earmarking arrangements.	Low: Reduced administration time with 0.1 FTE DFID Syria Deputy Programme Manager and no Senior Responsible Owner or Humanitarian Adviser in DFID Syria. It would initially require management time from both DFID OPTs and Syria to establish modalities.
Dialogue and alignment with DFID priorities	None. Not supporting the UK’s Syria Conference commitments or DFID Syria Humanitarian Approach of supporting those most acutely in need.	Dialogue with UNRWA will be around PRS-specific humanitarian issues. Aligned with the UK Aid Strategy, the Syria-Turkey Business Plan, DFID Syria Humanitarian Approach, the Grand Bargain, Syria Conference commitments and wider UN reform priorities. DFID teams will work collaboratively to ensure maximum influence through the UK’s membership of UNRWA’s Advisory Commission and Sub-Committee.	Dialogue with UNRWA will be around PRS-specific humanitarian issues and service provision for DFID-prioritised activities. Aligned with the UK Aid Strategy, the Syria-Turkey Business Plan, DFID Syria Humanitarian Approach and Syria Conference commitments but not in line with Grand Bargain commitments or donorship principles, potentially impacting on relationship and reputation.	Dialogue would be on issues relating to all field offices rather than Syria specific. Increasing overall core funding would increase DFID’s leverage with UNRWA. Aligned with the UK Aid Strategy, but it would not incentivise delivery against the Syria-Turkey Business Plan, DFID Syria Humanitarian Approach or Syria Conference commitments as DFID could not prioritise funding to Syria.
Results	None. Humanitarian situation worsens. Without DFID support to UNRWA, PRS would lack vital support.	Coherent coverage of humanitarian assistance and access to services for all PRS that would not otherwise be covered by DFID’s programme portfolio in Syria. Allows for Syria-specific results.	Coherent coverage of humanitarian assistance and access to services for all PRS that would not otherwise be covered by DFID’s programme portfolio in Syria. Allows for Syria-specific results across earmarked activities.	DFID-attributable results to UNRWA’s basic services provision in Syria, but no Syria humanitarian results as DFID would not be supporting the Appeal.

Evidence of delivery	None.	Strong: MENAD has been supporting UNRWA inside Syria since 2012. The Annual Review score for 2015/16 was A+.	Strong: MENAD has been supporting UNRWA inside Syria since 2012. The Annual Review score for 2015/16 was A+.	Limited: Core funding modalities are rarely used in high-risk fragile state environments.

Conclusion of Appraisal Case
UNRWA has consistently demonstrated its capacity to serve the needs of PRS. By contributing to UNRWA’s Syria Appeal, DFID would be supporting the only UN agency mandated to provide assistance to PRS. Option 2 will deliver the full package of assistance and services to PRS at scale, with the ability to flexibly prioritise funding according to severity of needs and rapidly respond to changing conflict contexts and needs across sectors, which Option 3 would prevent. This will complement DFID OPTs’ funding and DFID Syria’s support to other UN agencies and INGOs with different mandates/target groups.
Option 2 is strongly aligned to DFID Syria’s Humanitarian Approach, directing funding to a vulnerable population group, alongside the UK Aid Strategy, Grand Bargain commitments of unearmarked multi-year funding and increased use of cash, and DFID’s Syria Business Plan, including emergency relief, protection and resilience activities. Option 2 would deliver a significant set of PRS-specific results across all sectors which would not otherwise be covered by DFID’s programme portfolio in Syria. Furthermore, DFID will ensure (through the MoU, quarterly reports and meetings, and logframe/indicators) that UNRWA targets PRS with the most acute needs: those living in besieged and hard to reach areas, and collective shelters; the disabled; pregnant and lactating women; children; and those at risk of sexual and gender based violence; targeting those with the most acute needs within this already vulnerable population group.

Theory of Change (ToC) for preferred option
The Theory of Change is based on the argument that providing PRS with humanitarian assistance, access to basic services and livelihood support will meet immediate, life-saving needs while also building longer-term capacity to cope with sudden crisis. For example, improved access to food and cash will address essential nutritional needs as PRS become increasingly food secure. Improved access to health care will save lives, prevent future disease outbreaks and contribute to building a health system for vulnerable populations. Alongside vocational training and microfinance loans, lives will be saved, PRS will be protected and resilience built.

The causal linkages between outputs, outcomes and impact are listed at Figure 3 below.

Figure 3: Theory of Change
OUTPUTS
ACTIVITIES
Maintained and enhanced access to food, non-food items and shelter assistance
Improved access to livelihood opportunities
Reduced impact on health services (including meeting public health needs)
Continued access to education
Strengthened protection of vulnerable Palestine refugees
Improving access to health services and supplies
Supporting education
Strengthening protection services
Supporting employment opportunities
Vocational Training
Setting up health points and mobile clinics
Protection assistance
Microfinance Loans
Providing Relief Assistance
Food
Cash
Shelter
NFIs
Legal advice
Hygiene kits
Medical supplies
Distributing Learning materials
Psycho-social support
Protection training
Rehabilitating WASH networks
Teacher training
Creating safe spaces
IMPACT
Palestine refugees are able to meet their essential life-saving needs and cope with sudden crisis
Lives saved, civilians protected, suffering reduced and resilience built
OUTCOMES
PRS provided with safe and timely access to quality assistance, services and support networks
PRS reduce reliance on negative/irreversible coping mechanisms and build their resilience
INPUTS
NEEDS
Unemploy-ment
Food insecurity
Protection risks
Damaged health facilities
Deteriora-tion of WASH
Lack of access to regular education
Displace-ment
Donor Funding
DFID and UNRWA Staffing
UNRWA facilities
Direct procurement

ASSUMPTIONS
- Security and humanitarian assistance is maintained and improved to allow access to PRS and safe delivery
- Interventions take into account PRS dietary needs and cultural habits
- Education increases a child’s ability to make appropriate and informed choices
- Operating environments remain similarly challenging and needs continue
- Regular monitoring identifies changing needs of PRS
- Continued donor funding of the UNRWA Syria Appeal
- Procurement pipeline is uninterrupted
- Capacity of PRS to implement activities is available and adequate
- Decline in purchasing power, exchange rate fluctuation and inflation is manageable
- The UN, including the UK, renews UNRWA’s mandate in 2017 in the absence of a Middle East Peace Process political situation

Strength of Evidence Base

Food Security Support
There is very strong evidence that delivering food, livelihoods support and nutrition will meet critical food needs, reduce suffering and save lives.[50] For this to happen, interventions need to take into account the dietary needs and cultural habits of the population, and be influenced by community and household needs. Food security interventions must be fair, accountable, transparent and gender sensitive. Distribution to women is recommended for two main reasons: first, women often have the primary role in household food management; second, because women are more likely to use food aid for nutritional purposes (as opposed to selling or exchanging for other goods). UNRWA has identified 248 female-headed families in its collective shelters – a number that has increased due to conflict. To ensure its interventions comply with the above principles and approaches, and deliver the expected outcomes, UNRWA will draw on its extensive experience of delivering food assistance to Palestine refugees across Syria, including directly to female-headed households, and adapting food parcels to the specific needs of beneficiaries (e.g. size of the household, people living in collective shelters and hard-to-reach areas).
[50] E.g. ICRC Nutrition Manual for Humanitarian Action: https://www.icrc.org/eng/assets/files/other/icrc_002_0820.pdf

Cash-Based Programmes
A significant and growing body of evidence demonstrates that cash-based interventions can act as a viable and safe alternative, or complement, to in-kind assistance. Cash-based interventions support local business and markets. People often prefer receiving cash as it provides choice and control over how best to meet individual needs, and a greater sense of dignity. Cash programmes usually cost less to implement than in-kind assistance. Aid agencies do not need to transport and store relief goods, which makes limited humanitarian resources go further.[51]
[51] ODI Report of the High Level Panel on Humanitarian Cash Transfers. September 2015

A 2014 UNRWA cash evaluation[52] found that over 71% of all cash provided to PRS was used for basic needs: food and rent. Nearly all PRS indicated their preference for cash over other forms of aid as it provides flexibility in meeting needs. The evaluation also found that the provision of cash was relevant and particularly cost effective in the context of Syria despite limitations on movement and functioning markets in some areas. UNRWA is planning another evaluation of its cash programming in 2017.
[52] UNRWA Department of Internal Oversight Services’ Evaluation of the Emergency Cash Assistance Component of the Syria Emergency Response Programme of UNRWA, November 2014

Multi-year financing
There is some evidence that operational costs may be lower under multi-year funding arrangements as agencies are able to negotiate longer term contracts with implementing partners and suppliers, at reduced costs. There is strong evidence that predictable funding can allow agencies to procure inputs, such as food, with significant savings. There is strong evidence that response times can be decreased by half through flexible funding, as proposed under this Business Case. Limited evidence suggests that this time saving can result in reduced food deficits, though there is a good deal of variation.

A 2015 CHASE review concluded that DFID reduces process and transaction costs by supporting multi-year programmes. This leaves staff more time for meaningful engagement to monitor programmes, and advocate for changes and improvements with partners. The review also found that multi-year arrangements strengthen humanitarian systems in-country by providing predictable financing. A greater focus on delivery is also possible as less time is required for annual programme design and fundraising, resulting in better preparedness and early action. By providing predictable UK commitments to future UNRWA Syria Appeals in advance, UNRWA can better plan cash and food rounds at the start of each year.

Multi-sector financing
The needs of PRS are significant and varied – from food insecurity and increasing unemployment to mass displacement and associated protection risks. By delivering multi-sector assistance, UNRWA is able to bridge the divide from emergency relief to early recovery, and implement a flexible approach that provides both life-saving assistance and supports longer-term resilience for PRS. UNRWA ensures that PRS have access to a full range of opportunities that meet their specific needs via this integrated approach. With limited humanitarian resources available, UNRWA’s multi-sector response ensures efficient coordination and cohesion, and reduces DFID management time (implementing through one agency versus several).

Building Resilience
The multi-year approach will enable DFID to increase focus on preventing the reliance of Palestine refugees on negative and irreversible coping mechanisms. There is clear evidence that benefit to cost ratios of investing in resilience range between $2.30 and $13.20 of benefit for every $1 spent.[53]
[53] Value For Money of multi-year approaches to humanitarian funding, Cabot-Venton, April 2013, https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/204946/Cost_Effectiveness_of_Multi-year_Humanitarian_Funding_-_Final_Report.pdf , accessed June 2015

Vulnerability, Disability and Gender

The Humanitarian Needs Overview recognises Palestine refugees, along with newly displaced and female-headed households, as among the most vulnerable groups in Syria. UNRWA is responsible for protecting and promoting PRS rights through, for example, the provision of legal advice or upholding the right of children to access quality, inclusive and equitable education. UNRWA helps promote gender equality and empower women and girls by ensuring equal access to services for girls, boys, women and men, and specific services targeted at female-headed households and girls and women experiencing gender-based protection threats. In addition, when assessing needs, UNRWA pays particular attention to determining whether a household includes those who have been internally displaced, those living with disabilities, the elderly, women and children.

UNRWA considers accountability to vulnerable populations as a cornerstone of quality programming, meeting changing PRS needs and delivering more sustainable outcomes. A number of formal and informal mechanisms are in place to ensure meaningful participation of PRS at various stages of the programme cycle. For example, student councils in UNRWA-operated schools facilitate student and parent engagement with school management and curriculum development. UNRWA’s focus on Palestine children is emphasised through its Child Protection Framework, which supports the creation of safe learning and recreational spaces for children most at risk from violence. UNRWA is deploying an additional 47 psychosocial counsellors in 2017 in its schools to build resilience among children and their families.

In combatting SGBV, UNRWA has developed community-based structures and initiatives to promote Palestine refugee participation (see Management Case). Inputs provided by women, men, boys and girls guide SGBV programming and have informed the development of UNRWA’s Gender Equality Strategy 2016-2021. UNRWA gender action plans prioritise women and girls for emergency assistance and provide a framework to address cases of gender-based and domestic violence through direct intervention and referral to specialised service providers.[54] In the shelter and health components of the programme, UNRWA has included specific indicators to measure female access to primary healthcare services and shelter assistance received by female headed households.[55]
[54] UNRWA Experience in GBV programming: lessons from the first five years https://www.unrwa.org/resources/reports/unrwa-experience-gbv-programming-lessons-first-five-years
[55] UNRWA Syria Emergency Appeal, 2017

DFID will continue engaging with UNRWA on its gender and protection strategies. Response to gender-specific needs, promotion of gender equality and consideration of opportunities to empower women and girls, based on best practice and lessons learned, are mainstreamed into all UNRWA programming. UNRWA has a dedicated team of Area Support Officers to ensure the protection needs of all PRS are met. DFID has seconded a part-time Social Development Adviser to UNRWA Jerusalem headquarters to provide operational support to UNRWA’s reform agenda. As required by Grand Bargain commitments, UNRWA will disaggregated a number of key indicators by sex, age and disability, which will allow for greater transparency (see Management Case E).

In addition, UNRWA has an extensive network of area offices, camp service offices, schools, health centres and other installations across Syria. This ensures that PRS have direct and regular access to UNRWA staff. UNRWA have approximately 4,000 staff employed inside Syria, with the vast majority being engaged in the direct delivery of operations and drawn from the Palestine refugee communities being assisted. Direct access to PRS allows UNRWA to target relief activities, including life-saving food, cash, health and education interventions, as well as livelihoods assistance, that are based solely on need and account for different vulnerabilities, as identified through assessments, monitoring data and engagement with beneficiaries. UNRWA’s approach of targeting the most vulnerable PRS is further guided by the priorities identified in its Mid-Term Strategy (2016-2021), which includes a commitment to focus on people living with disabilities, the elderly and those chronically ill or injured.

G. Conflict and EVET Sensitivity
Without UNRWA’s support, identified needs among the PRS population would be unmet, with a destabilising impact on extremely vulnerable communities. PRS camps are often sites of conflict and any reduction in UNRWA’s activity would likely exacerbate violence in these locations. Through its broad network of staff and services, UNRWA is in a unique position to understand and foresee the effects of conflict on its operations. All UNRWA programmes are developed according to the Do No Harm principle. UNRWA recognises that conflict affects groups of people differently, particularly children, people with disabilities and displaced PRS.

UNRWA is conscious of tensions between PRS, IDPs and host communities, and aims to prioritise interventions that have a positive effect on community relations. Participating in the cluster system allows UNRWA to coordinate its assistance to PRS with that provided to other Syrians. For example, there are currently 12,413 people, both PRS and other Syrians, with limited movement in Yarmouk camp.[56] While other UN agencies are unable to reach this population, UNRWA has established a system where those in need are able to travel out of the camp to collect humanitarian assistance. In this way, UNRWA coordinates identical food, medical supplies and NFIs for PRS, IDPs and host communities. UNRWA is also able to meet the health and education needs of both groups through its staff and facilities already established in Yarmouk, in a way that is sensitive to the environment of violent extremist groups.
[56] UNRWA 2016 verification survey released in June 2017

UNRWA designs its programmes in a conflict sensitive way by:
- Ensuring that humanitarian assistance offered to PRS is of a similar standard and quantity received by vulnerable Syrians from other organisations, including through cluster participation and coordinating procurement with other UN agencies (i.e. WFP and UNHCR).
- Participating in inter-agency convoys to ensure both PRS and Syrian civilians are served on behalf of the UN.
- Undertaking measures to analyse and monitor the context, operating environment and conflict dynamics and impact. For example, UNRWA monitors and reports on specific vulnerabilities through its Area Support Offices.
- Recruiting four Area Support Officers in 2016 to the Central Area, Damascus, Aleppo and Dar’a for protection mainstreaming, case tracking and referral, as well as protection and neutrality capacity building.
- Ensuring neutrality commitments are included in all supplier contractual documents, obligating compliance with UNRWA General Conditions of Contract including specific provisions on anti-terrorism, mines, child labour and the fundamental rights of works.

The DFID Syria Team has developed a set of standards to assess the conflict and EVET sensitivity of partner programmes. These require partners to a) undertake ongoing and participatory conflict analysis and ensure conflict sensitive implementation; b) build staff capacity on conflict sensitivity; c) have conflict sensitive polices in place regarding recruitment, communications and procurement; and d) monitor conflict related risks. DFID requires UNRWA Syria to further systematise the way it undertakes conflict analysis and monitors conflict-related risk. To that end, UNRWA Syria has expressed its commitment to develop a conflict and EVET sensitivity plan and meet DFID Syria standards. DFID Syria will lead and monitor progress through quarterly meetings and Annual Reviews.

H. Resilience
This programme recognises the need to strengthen household and community capacity and resilience to cope with the protracted crisis in Syria, while also acknowledging the importance of life-saving emergency assistance for those continually and directly affected by ongoing violence. Conflict in Syria is punctuated by spikes in violence that cause major displacement, damage vital infrastructure and increase the population’s vulnerability and poverty levels. Syria has lost four decades of human development gains and poverty levels have now increased to 80% of the population. As the crisis becomes increasingly protracted, its multi-dimensional consequences are severely felt by individuals and communities throughout the country, particularly by PRS.

UNRWA will implement activities that reduce Palestine refugees’ exposure to immediate risks. The ability of people to cope with and mitigate immediate risks (such as SGBV, inadequate food supply, inappropriate shelter and water-borne diseases) is increased by an awareness of rights and access to assistance such as cash, food, housing and NFIs. UNRWA staff will provide services related to psychosocial wellbeing, safe spaces for women and children, and training for skills development. By also improving the quality of available shelter and access to NFIs, the protective environment and ability of PRS to mitigate health and safety risks will be enhanced.

Food and cash assistance allows PRS to improve their food and nutrition security, and absorb the shock of food scarcity/inaccessibility without skipping or reducing meals. These interventions also discourage negative coping strategies such as selling productive assets, accumulating debt, removing children from school, child labour and others that could cause permanent and negative impacts for families over time.

A lack of education decreases a child’s ability to make appropriate and informed short, medium and long-term choices; and limits their access to livelihoods and future economic opportunities. By providing access to education and safe spaces, and improving the quality of teaching, UNRWA will promote coping strategies that enhance individual and community resilience.

Loss of livelihoods and income erodes economic resilience and the ability of individuals and communities to cope with conflict and displacement. Cash assistance, vocational training, improved access to employment opportunities and distribution of microfinance, will enable UNRWA to build a supportive environment and individual capacity that restores livelihoods and increases resilience.

I. Likely impact on climate change and environment
Overall, this programme should not have a significant impact on the climate or environment. Through its Environmental Health programme, UNRWA ensures that garbage produced in camps is collected and processed appropriately, and sewage systems are rehabilitated and regularly maintained to ensure the health of PRS and reduce environmental impacts. UNRWA will continually monitor and assess the potential for any environmental impact.

J. Value for Money (VfM)
UNRWA represents good VfM. Its long-established presence and reach in Syria and the region provides a hard to replicate comparative advantage in terms of local knowledge, and extensive and highly capable group of staff. VfM is embedded within UNRWA Syria’s daily operations. For example, UNRWA's move to cash assistance is in line with international best practice and is cost effective. While UNRWA continues to provide in-kind assistance where markets mean high prices or unavailability of certain goods, cash assistance has significantly lowered operational costs while simultaneously increasing the ability of PRS to prioritise their own needs.

However, UNRWA needs to formalise their approach to VfM across the organisation, particularly regarding the systems used to assess and analyse whether expenditure represents good VfM, and donor reporting. DFID OPTs will lead this work. DFID Syria will monitor this progress at quarterly meetings and through Annual Reviews.

Economy
UNRWA identify their key cost drivers as staffing and supplies. UNRWA offers universal health and education services to all Palestine refugees, including through the provision of salaries for teachers, health professionals and other frontline service delivery staff. UNRWA Syria staff salaries and entitlements are lower than national staff salaries paid by other UN Syria agencies, and take pay levels of the Syrian regime into account. Making additional cost savings on salaries is difficult; UNRWA’s staff unions are strong and well organised.

UNRWA makes cost savings in Syria primarily through their procurement, including by[57]:
[57] UNRWA Procurement Manual v.3 (p.7)
- Enabling economies of scale: consolidating procurement requirements across all field offices for items such as rice, sugar, oil, pharmaceuticals and vehicles. All other items which are available locally in Syria are procured through competitive tendering.
- Establishing Long Term Agreement (LTA) contracts for items procured on a recurring basis to fix costs (e.g. blankets, hygiene kits, food items and mattresses.)
- Launching local tenders in both Syria and Lebanon to increase market reach/competition.
- Working with other UN Syria agencies, including through the Logistics Cluster, to launch tenders to compare quoted prices and utilise existing UN contracts.
- Introducing an Enterprise Resource Planning (ERP) system in March 2015 to minimise excess stock levels: saving warehousing costs and reducing the scope for theft.
- Moving to cash assistance, and reducing transportation and storage costs.

Efficiency
UNRWA’s operating model of delivering regular services and emergency assistance directly through its 4,000 staff and 219 facilities in Syria demonstrates an efficient response to the needs of PRS across all sectors. The majority of staff are PRS themselves, directly contributing to programme outcomes. By contracting goods and services, with no downstream partners, UNRWA minimises administration costs and risks. Direct access to PRS allows UNRWA to target emergency relief activities and livelihoods assistance based solely on needs, through vulnerability assessments, monitoring data and beneficiary engagement.

Where possible, UNRWA provides cash assistance, allowing PRS the flexibility and choice to prioritise their own needs. A 2014 evaluation found UNRWA’s cash programme to be efficient and relevant, with overheads between 0.64–2.5%, despite limitations on movement and market functionality in some areas.[58] Over 71% of all cash provided to PRS is used for basic needs: food and rent. Nearly all PRS indicated their preference for cash over other forms of aid, although, where food prices remain extremely high, in-kind distributions are necessary. This evaluation and DFID’s recent Due Diligence Assessment note that distributing cash to all 418,000 PRS deemed in need of humanitarian assistance is cost-efficient in the current context. However, in the longer-term, UNRWA should implement a more targeted approach to ensure the needs of the most vulnerable are fully met.
[58] UNRWA Department of Internal Oversight Services’ Evaluation of the Emergency Cash Assistance Component of the Syria Emergency Response Programme of UNRWA, November 2014

Where possible, UNRWA collaborates with other agencies to ensure a more efficient response. For example, participating in UN inter-agency convoys in instances where only UNRWA can access specific areas to ensure both PRS and Syrian civilians are served, and collaborating with other UN agencies to perform assessments such as socio-economic surveys of PRS[59].
[59] 2016 Situation Assessment of Palestinian Refugees in the Syrian Arab Republic – GAPAR, UNICEF, UNRWA

Effectiveness
PRS are almost entirely reliant on UNRWA for their basic requirements as well as humanitarian needs. By directly employing nearly 4,000 PRS and reaching over 97% of PRS deemed in acute need with one or more emergency assistance interventions in 2016, UNRWA has proven effective.[60]
[60] 2016 UNRWA Annual Operational Report

In 2014, an external evaluation by the European Union confirmed UNRWA’s capacity to deliver and generate impact in the areas of education, health and social relief. A study undertaken by the Independent Commission for Aid Impact (ICAI) 2013 noted that services delivered by UNRWA are efficient given the context and constraints within which UNRWA operates. It was concluded that DFID was making a positive impact on the lives of PRS through its contributions to UNRWA, despite the challenging operating environment.[61] ICAI reported that DFID’s support to UNRWA is an effective way of supporting both organisations’ aim to improve the human development outcomes of Palestine refugees and contribute to regional stability.
[61] http://icai.independent.gov.uk/2013/09/13/independent-commission-for-aid-impact-publishes-report-on-dfids-support-for-palestine-refugees-through-unrwa/

Commercial Case

A. Funding Mechanism
The proposed funding mechanism is through a Memorandum of Understanding (MoU) agreed between DFID Syria and UNRWA. DFID’s voluntary contribution of £36 million over three years will be used exclusively to support the Syria component of UNRWA’s Syria Regional Emergency Appeal. The MoU will outline the value and timing of each planned payment, reporting requirements and specify clauses on anti-terrorist financing and DFID’s zero tolerance for fraud and corruption (see Financial Case). Should there be any evidence of either poor performance or that funds are not being used for the purposes intended, DFID reserves the ability to terminate the programme and/or seek the return of funds.

B. Partner Assurance
DFID has a long-standing partnership with UNRWA and is active in driving greater efficiency, leadership, transparency and financial accountability through UNRWA’s reform processes. DFID OPTs conduct regular reviews on UNRWA’s core policies, capacity, risk and performance, and DFID Syria will undertake quarterly meetings and Annual Reviews of the programme with UNRWA Syria. DFID’s most recent funding to UNRWA Syria (April 2015 – December 2016) scored an A+ in 2015. The Project Completion Review (PCR) will be due in July 2017. DFID OPTs’ 2015/16 UNRWA programme PCR also scored an A+.

DFID OPTs and Syria teams are subject to regular reviews by the Internal Audit Department and UK National Audit Office. An internal audit of UNRWA is undertaken each year in addition to an external audit conducted by the UN Board of Auditors (UNBOA). In the last five years, UNRWA has also been reviewed by the Independent Commission for Aid Impact (in 2013) and the UK International Development Committee (in 2014). Due Diligence Assessments were undertaken by DFID Syria and DFID OPTs in 2015. A new Syria Due Diligence Assessment was conducted in January 2017 and reviewed whether UNRWA’s capacity and capability is sufficiently robust to respond to the risks of operating in Syria (see Management Case C). Several of the findings will be incorporated in the DFID OPTs core funding Due Diligence Assessment as they have bearing Agency-wide. DFID Syria will re-assess the due diligence risks and recommendations during quarterly meetings and at each Annual Review.

C. UN Reform
The Secretary of State has identified UN reform as a top priority. DFID OPTs have agreed a Mutual Accountability Framework documenting the UK’s reform agenda with UNRWA and holds UNRWA and DFID accountable for key partnership commitments over 2016-2021, including through tying core Programme Budget funding to reform-based indicators. Reform priorities focus on improving UNRWA’s financial stability and safeguarding the provision of services for Palestine refugees. DFID OPTs will lead coordination with DFID Syria and DFID’s Conflict Humanitarian and Security Department (CHASE) to include Grand Bargain commitment indicators in the Mutual Accountability Framework for 2017 and use all available technical, policy and diplomatic mechanisms to ensure UNRWA deliver their humanitarian assistance effectively and promptly.

The UK is a member of the Advisory Commission. This provides us with the opportunity to influence UNRWA programmes and raise any concerns, in addition to bilateral discussions. The internal DFID Steering Committee on UNRWA will ensure effective alignment on programme management and oversight across all DFID funding streams. Providing funding directly to the Syria Appeal maintains DFID’s influence over the humanitarian response for PRS, and for approaches agreed at country-level to feed into wider institutional reform.

D. Procurement Approach and Capability
UNRWA Syria will conduct large scale procurement with DFID funding. All procurement will be undertaken in accordance with UNRWA’s Procurement Manual, policies and guidelines that document limits and delegations of authority. UNRWA’s principle of ‘Best Value for Money’ ensures spending decisions take into account relevant costs and benefits over the full life-cycle of a product and determines where single source rules can be used for procurement.

E. Delivery Chain
UNRWA directly implements programmes, employing 4,000 staff to deliver education, health and relief services in Syria through 219 facilities (See Figures 4 and 5). With a workforce predominantly comprised of Palestine refugees (and only 15 international staff), UNRWA has a large service delivery presence. UNRWA’s supply chain is managed internally, operating an end-to-end supply chain where goods remain in UNRWA’s custody from delivery at the port/airport of arrival until direct distribution or issue to beneficiaries or via UNRWA clinics and schools. Procedures governing the delivery chain include clear segregation of duties; a framework that governs authority and decision-making delegations; and an independent review methodology based on contract valuations. The introduction of an Enterprise Resource Planning (ERP) system in March 2015 ensures that logistics and procurement transactions are captured electronically with an auditable electronic document trail.

Figure 4 – UNRWA Syria Management Structure
Director of UNRWA Affairs, Syria
Syria Field Office, Damascus (including 15 international staff)
Chief Area Officer
Area Field Office,
Lattakia
Chief Area Officer
Area Field Office,
Hama
Chief Area Officer
Area Field Office,
Homs
Chief Area Officer
Area Field Office,
Dar’a
Chief Area Officer
Area Field Office,
Aleppo
Chief Area Officer
Area Field Office,
Damascus
219 facilities including: 101 schools, 15 health centres, 11 health posts, 4 large warehouses, 14 distribution centres, 12 vocational training centres, 11 community centres and 2 microfinance offices.

Figure 5: UNRWA Syria Presence

F. Flexibility
Within this complex and challenging operating environment, UNRWA will draw upon existing structures, supply chains and capacities to ensure an effective and agile response to ongoing and evolving needs.[62] Preparedness activities, in anticipation of new displacements, include prepositioning of humanitarian supplies (food and NFIs) and identification of potential shelters in key locations (for example in the case of Aleppo in September-October 2016). Should there be an increase in PRS seeking to return home, UNRWA are ready to engage in early recovery activities. For example, in 2015, following the return of PRS to Husseiniyeh, UNRWA re-established core services (including rebuilding community infrastructure such as schools) and addressed urgent humanitarian and protection needs.
[62] UNRWA 2017 Syria Regional Emergency Appeal (p.15)

DFID Syria will monitor the context and UNRWA’s performance, funding and PRS needs at quarterly meetings and Annual Reviews. This will involve ensuring that UNRWA is responding to the evolving humanitarian needs of PRS, and enable DFID to review its support and explore options to flexbily respond.

## Financial Case

A. UNRWA Budget
UNRWA has three main sources of income:
1. Regular Budget of the UN – UNRWA receives a limited subsidy from the Regular Budget of the UN, used exclusively for administrative costs. This includes less than $1 million to cover the key managerial Syria field staff costs, including international staff. In 2016, UNRWA Syria received $2 million from OCHA, and a US$33,000 grant from UNESCO to cover minor education activities against its normal programmes.
2. Government Partners – sustained contributions from the European Union, state and regional governments, representing 90% of all contributions in 2015.
3. Private Partners – NGOs, Business and Foundations, and Individuals.

Aside from core contributions to their Programme Budget, UNRWA seeks new funding for their Syria Appeal on an annual basis, in line with the annual Syria Humanitarian Response Plan (HRP). The 2017 Appeal requests US$329m to cover the needs of Palestine Refugees inside Syria. UNRWA have set a minimum requirement of US$166m for Syria to run their basic operations. It is assumed that the number and needs of PRS are going to continue and therefore that UNRWA will request similar levels of funding in 2018 and 2019.

B. UNRWA Donors
UNRWA relies almost entirely on donor contributions to fund its operations in Syria. In 2016, the US contributed 54% of total funds received, and the UK 18% (Figure 6).

Figure 6: Top UNRWA Syria donors in 2016

Donor	2016 funding (US$)	Percentage
1. USA	86,306,509.98	54.37%
2. DFID	27,930,522.02	17.59%
3. Germany	12,401,352.88	7.81%
4. Sweden	4,842,146.23	3.05%
5. Norway	4,239,992.31	2.67%
Others	23,025,327.35	14.51%
Total	158,745,850.77

UNRWA has a chronic Programme Budget deficit, as well as under-funded Appeals. For example, in 2016 UNRWA only secured 54% of funds required, resulting in a reduction of the number of cash rounds over the year from six to three and food from six to four. Without the predictability of donor funding, UNRWA is limited in its ability to plan for the longer-term, resulting in significant gaps in the overall Syrian response.

To date only 22% of the 2017 UNRWA Syria Appeal has been funded. No major commitments have yet been announced. There is a strong indication that the US will continue to cap their contribution at 25% of the UNRWA Syria Appeal request. UNRWA Syria had to carry approximately US$28m into 2017 to cover January-March 2017 procurement of food commodities, NFIs and staffing.

C. DFID Budget

Financial Year	Planned funding
2017/18	£12 million
2018/19	£12 million
2019/20	£12 million
Total	£36 million

DFID provided £15 million in 2015 and £20 million in 2016 to UNRWA Syria. This Business Case proposes an annual contribution over 2017/18 to 2019/20 of £12 million predictable multi-year support to UNRWA’s Syria Appeal. This would maintain DFID’s position as the second largest UNRWA Syria donor.

To maintain flexibility, DFID Syria will review funding levels through quarterly meetings and Annual Reviews on the basis of developments on the ground and the level of need set out in appeals and needs assessments, alongside UNRWA’s performance within Syria and the Mutual Accountability Framework, including Grand Bargain commitments.

D. Payments
DFID will agree a MoU with UNRWA Syria documenting allocation amounts and tranches over 2017-2020. It is intended that funding tranches will be transferred to UNRWA in August and November of 2017, and June and November of subsequent years following receipt of six-monthly results reports (by 31 May and 31 October of each year).

The funds will be committed and transferred to UNRWA in GBP sterling, and will support the UK in meeting Official Development Assistance (ODA) targets. Should there be any significant change to the conflict, DFID may change the planned contribution. To ensure the UK does not pay in advance of need, DFID Syria will continue to monitor UNRWA Syria’s cash levels and operational reserves at quarterly meetings and Annual Reviews and adjust the schedule accordingly. UNRWA will assume the risk of currency fluctuations, including any fall or benefit in the value of pound sterling relative to the local currency.

E. Affordability
This programme will be funded from DFID Syria’s programme budget (£162 million in FY17/18). The planned allocation of £12 million per annum will be profiled on DFID’s ARIES financial system. Total operating costs for DFID to manage this programme are already included in the workforce planning and do not represent any increase in overall expenditure.

F. Assets
UNRWA maintains an Asset Register on the ERP. As this is a contribution to an Appeal of a multilateral organisation, any assets purchased would not be directly attributable to DFID.

G. Administrative Costs
Unlike other UN agencies, UNRWA implements all projects itself. Given nearly all 4,000 staff are PRS themselves, directly contributing to the outcomes of the programme, and through contracting goods and services, with no downstream partners, UNRWA minimises administration costs and risks throughout the delivery chain. There are three elements to UNRWA Syria’s administrative costs:

1. Assessed contirubtions from the UN regular budget. This covers the salaries of 155 international staff agency-wide.
2. Indirect Support costs. Across all fields of operation UNRWA incurs 11% Indirect Support Costs (ISC) associated with the delivery of emergency activities at field and headquarters which cannot be allocated to individual activities. This includes systems, structures and support functions such as finance, IT, offices, security, and oversight to ensure proper management and delivery of emergency operations.[63] The 11% standard ISC rate was established after a comparison of practices across UN agencies where the standard ISC rate varies from 7-13% with some exceptions with even higher rates.
  [63] UNRWA Indirect Support Cost briefing 09.06.2016.
3. Capacity and management budget lines. The Syria Appeal includes a budget line for Capacity and Management support to UNRWA’s response to the Syria Crisis, relating to 4.6% of the Appeal. This covers costs for staff directly involved in management, coordination and response, related equipment, travel and training costs.

H. Assessment of financial risk and fraud
UNRWA’s financial systems and controls are well established. In such a large programme with 4,000 staff, a cash assistance expenditure of $77m and procurement caseload of approximately $30m per annum in a volatile conflict situation, there is however inevitably high fiduciary and financial risk (see Figure 8). UNRWA has a range of robust procedures in place to combat these risks. Given that UNRWA’s supply chain is managed in-house, with no downstream partners, no DFID funds, either directly or indirectly, will be channelled through or to support any Syrian Ministries or the Syrian Arab Red Crescent (SARC).

Aid diversion
There is a risk that procurement, distribution and delivery are subject to aid diversion (including loss, theft, fraud, damage or misuse). DFID Syria works closely with partners to mitigate the risk of fraud through strengthened programme due diligence (including Counter Terrorism legislation compliance) and independent monitoring. Partners are required to report all instances of aid diversion to DFID.

DFID has carried out checks that UNRWA has policies and procedures in place to reduce the risks of fraud and corruption and is taking appropriate measures to prevent diversion taking place (see Management Case). UNRWA’s mitigation measures include:
- A zero tolerance approach to fraud, issuing an anti-fraud and anti-corruption policy at the end of 2015, with respective whistleblowing policies.
- All beneficiaries receiving cash and food assistance have to be registered with UNRWA and must be present and holding three forms of identification to receive their distribution.
- Weekly cash distribution reports.
- Introducing an ERP information management system to track who received what assistance and from where and tracking the movement of goods.
- Random calls to beneficiaries, spot checks and complaints and appeals processes.
- Transferring funds into Syria by US$ bank transfer from headquarters. Such bank accounts require two designated signatories, and are reconciled every month.
- Performing a quarterly stocktake to independently check 100% of stock.
- Working closely with the Governmental Delivery Mechanism, involving signed facilitation letters and the sealing of trucks by government representatives to reduce tampering.

Given that UNRWA directly implements most of its programmes, there is a lower risk of diversion of funds, as UNRWA does not rely on any downstream partners, with greater control.

Terrorist financing
As this programme operates inside Syria, it carries with it a risk of aid being diverted to armed and terrorist groups. As in the Strategic Case, UNRWA has confirmed that it complies with all applicable UN anti-terrorism resolutions and sanctions; vetting all partners and suppliers, and six-monthly checking staff members, personnel, supplier names and other payees against relevant UN lists, including the UN Suspended Vendor reports and the New Consolidated List established and maintained by the UN Security Council Committee. A clause banning the financing of any terrorist activity or individuals will be included in the MoU and UNRWA will provide a list of suppliers contracted in Syria for DFID to check against European Union sanctions to ensure UK funds are not used to support them.

Insufficient finance from other donors
The emergency services provided by UNRWA constitute the minimum support necessary to meet the critical needs of Palestine refugees affected by the conflict in Syria. Underfunding presents a significant risk to UNRWA’s provision and quality of assistance and in turn meeting the needs of PRS. Any reduction in planned assistance could have profound repercussions in eroding household resilience and coping capacities. UNRWA relies almost entirely on donor contributions to fund its Syrian operations. Previous UNRWA Syria Appeals have been significantly underfunded. In 2016, the US contributed 54% of total funds received, and the UK 18%. To date neither have announced their 2017 commitments, and only 22% of the Appeal has been funded. Without any additional commitments, some basic services such as health and education would be partially covered by UNRWA’s Programme Budget, although UNRWA may be forced to appeal for emergency funding from OCHA to cover emergency relief. Multi-year funding from DFID and the implementation of UNRWA’s 2016-18 Resource Mobilisation Strategy[64] will mitigate this risk, although it remains severe. DFID Syria will monitor UNRWA’s Syria Appeal funding levels quarterly and assess whether UNRWA performance and PRS needs warrant a budget increase.
[64] UNRWA Resource Mobilisation Strategy (RMS) 2016-2018 https://www.unrwa.org/resources/strategy-policy/resource-mobilization-strategy

Double counting
A small proportion of UNRWA’s Syria Appeal is to provide access to emergency health and education for PRS (7% and 3% respectively in 2016). Staff who work in education (teachers) and health (doctors) are usually charged to the Programme Budget (DFID OPT-funded) whereas staff who work on the delivery of services either under cash or food assistance are charged to the Emergency Appeal (DFID Syria-funded). There is therefore a risk of DFID ‘double counting’ activities funded through our contributions to the core Programme Budget and Syria Appeals. To mitigate this risk, DFID OPTs and Syria will report on attributed rather than actual results. UNRWA’s Annual Operational Report shows how activities funded through different funding streams contribute to the overall UNRWA Medium-Term Strategy (MTS).

Exchange rate fluctuation
DFID contributions to UNRWA are made in GBP, yet UNRWA transactions into Syria are made in US$ and then converted into Syrian Pounds upon withdrawal. Given that 60% of UNRWA Syria’s activities is cash assistance, exchange rate fluctuations pose a financial risk to UNRWA Syria’s operations. UNRWA has technical instructions, policy statements and procedural steps in place to manage UNRWA’s foreign exchange and currency conversion transactions. To mitigate this risk, UNRWA hedges the exposure of Non-US$ donor contributions in order to reduce the risk and UNRWA Headquarters Amman only transfers money to UNRWA Syria when requested for operations, ensuring that funding levels in Syrian bank accounts is kept to a minimum.

Management Case

A. Management arrangements for implementing the intervention

DFID management
DFID’s Occupied Palestinian Territories (OPTs) team provide core funding to UNRWA’s Programme Budget. Responsible for DFID’s institutional relationship with UNRWA, DFID OPTs engage closely through the UNRWA Advisory Commission and Sub Committee, and at working level via the Harmonised Results Working Group. DFID’s Conflict, Humanitarian and Security (CHASE) Department will oversee the UN’s progress against the Grand Bargain commitments. DFID OPTs will work closely with DFID Syria and CHASE to ensure consistency with wider objectives and maximise leverage in driving reform.

This UNRWA Syria programme will be managed by DFID Syria, with the following resources:
- A2 Syria UN Team Leader (10%): Senior Responsible Owner and responsible for effective delivery of the programme and compliance with the SMART Rules.
- A2 Humanitarian Advisor (20%): provide technical oversight of the programme and lead DFID Syria engagement with UNRWA in-country.
- B1 Deputy Programme Manager (DPM) (30%): day-to-day management of the programme including monitoring, evaluation and financial management.
- Specialist advice from DFID Syria sector advisers and Risk and Results team.

The essential elements of the oversight arrangements will be:
- Regular engagement between DFID and UNRWA operations teams on any issues;
- Quarterly meetings between DFID Syria and UNRWA to discuss progress (including financial spend), changes in context and need, risk, aid diversion and conflict sensitivity.
- Annual Reviews through the programme lifecycle and a Project Completion Review at the end of the programme to assess achievements against Appeal targets.
- Programme Delivery Plan and Risk Register developed and regularly updated.
- DFID-contracted third party monitoring to undertake spot checks at least once year to ensure controls are in place for effective delivery.

UNRWA management
UNRWA is headed by Commissioner General and Chief Executive Pierre Krähenbühl, responsible for overall management, oversight and administration of the organisation across UNRWA’s five fields of operation: Gaza, West Bank, Syria, Jordan and Lebanon. Through a decentralised model, UNRWA coordinates delivery of assistance in Syria via an UNRWA Syria Field Office in Damascus and six Area Offices headed by local Chiefs in Aleppo, Latakia, Hama, Homs, Dera’a and Damascus. As a direct service provider, UNRWA employs approximately 4,000 PRS and national staff working across 219 facilities (see Figure 4).

B. Risks to Programme and how these will be managed

DFID Syria risk strategy
The risks inside Syria are severe as DFID partners are delivering in an active conflict zone. As DFID staff are currently not able to travel to Syria there is no direct oversight of what is happening on the ground. However DFID has assessed these risks, and through a Due Diligence Assessment, including short visits to UNRWA’s regional offices and documenting follow up actions (see Management Case C).

The key risks to the DFID portfolio in Syria, all of which include reputational risks, are:

- Conflict and violence lead to greater need and constrain delivery: There is a risk that the ongoing conflict and violence leads to increased displacement and greater levels of need amongst PRS. Operational risks associated with the conflict include security risks and constrained access, both of which limit UNRWA’s ability to operate effectively within Syria.
- Aid Diversion: As in the Financial Case, there is a risk that procurement, distribution and delivery of humanitarian assistance are subject to aid diversion (including loss, theft, fraud damage or misuse).

UNRWA Syria programme risks
The most severe risks to this DFID programme are captured in the register at Figure 7.

Figure 7 – Risk Register

Risk	Prob.	Impact	Severity	Mitigation measures
DELIVERY: A deterioration in the security situation means that UNRWA is unable to deliver basic services or maintain humanitarian access, leading to increased humanitarian need and/or threats to stability.	Likely	Severe	Severe	DFID to continue to work across HMG including through advocacy with the FCO and UN to call for political and peaceful resolutions to conflicts in the region and for the need for humanitarian access in line with international humanitarian law. Whilst aware of the limitations of advocacy efforts, DFID to continue monitoring incidences of conflict and building conflict sensitivity, flexibility and scenario and contingency planning into all programmes. DFID to coordinate core and humanitarian funding to UNRWA to maintain basic service delivery in conflict-affected areas. Through its network of 4,000 staff UNRWA to continue strengthening community engagement and advocacy, to coordinate with partners through clusters and the UNCT to ensure flexibility in modes of delivery and alternative supply routes and coordinate with authorities, the Office of the Special Envoy and other parties controlling access. UNRWA pre-positioning core relief items allows for the continuity of operations in case of access restrictions.
DELIVERY: UNRWA’s budget deficit and underfunded Syria Appeal causes an interruption to service provision, leading to unmet need and threats to regional stability	Likely	Severe	Severe	DFID Syria to provide predictable multi-year funding and quarterly assess UNRWA funding levels. DFID to encourage UNRWA to diversify its donor base, and for others to provide predictable funding where possible. DFID to engage closely with UNRWA and other donors on the need for reforms to safeguard core service delivery. UNRWA to continue to enhance partnerships with national and international organisations for efficiency and effectiveness and implement the 2016-18 Resource Mobilisation Strategy
DELIVERY: Reduction in adequate human resources and capacity given security situation and delays/ rejections of international visas for UNRWA staff	Likely	Major	Major	UNRWA to maintain emergency roster of international members of staff prepared for deployment to the Syria crisis response if needed, and multiple rosters of national candidates allowing rapid recruitment in case of vacancies.
FIDUCIARY Aid Diversion, including aid items confiscated or stolen at checkpoints	Possible	Major	Major	DFID to continue to strengthen programme due diligence and undertake third party monitoring over 2017-2020. UNRWA to continue to monthly report to DFID on aid diversion, including sampling and confiscations, and continue quarterly stocktakes and close engagement with the Syrian regime regarding the sealing of deliveries to reduce tampering (see Financial Case H).

UNRWA Syria’s 2017 Appeal includes a Risk Register, identifying the risks faced by the Agency due to challenges in the operating environment, and the mechanisms followed to mitigate those risks. These are updated six-monthly as part of the reporting cycle. This is however a Syria portfolio risk matrix, compiled by Amman headquarters and shared with donors, not specific to the activities delivered under the Appeal. UNRWA Syria staff assess and manage risk as part of day-to-day activities due to the operating environment.

DFID Syria will monitor progress at regular quarterly meetings with UNRWA and through Annual Reviews, alongside discussing any changes to the key risks and need for any additional mitigating actions. In discussion with DFID OPTs, if any of these risks materialised and were outside our risk appetite, DFID would consider what action to take, including consulting with Ministers and introducing new measures to reduce the risks or suspend/close the programme.

The residual risk of this programme is severe due to the ongoing conflict in Syria. Even if the situation in Syria improves, the context will remain fragile and require a flexible approach that responds to operational risks by allowing partners to scale operations up or down, change location or carry out different activities. Within the significantly challenging operating environment, UNRWA has consistently demonstrated that it can operate at tremendous scale and meet the needs of PRS, including those in besieged and hard to reach areas. The severe risk of operating in Syria is therefore outweighed by the high return of providing life-saving humanitarian assistance to PRS and supporting governance and service delivery that work towards longer term, post conflict recovery and development.

C. Due Diligence

In January 2017 DFID undertook a Due Diligence Assessment of UNRWA Syria via short site visits to UNRWA in Amman. It concluded that UNRWA Syria’s capacity and capability is sufficiently robust to respond to the risks associated with operating in Syria and to deliver this programme.

DFID have shared the Due Diligence Assessment with UNRWA and will discuss control weaknesses identified and agree mitigating actions. These will be formally documented within an improvement plan, noting UNRWA, DFID OPTs and DFID Syria responsibilities and attached to the MoU, prior to the programme start date of 01 August 2017. DFID Syria will monitor UNRWA’s progress against the improvement plan at quarterly meetings, and formally document in the Annual Review.

D. How will progress and results be monitored, measured and evaluated?
DFID has devised the logical framework at Annex 1 using a subset of indicators presented in the Syria Appeal and Medium Term Strategy, to assess performance of the programme each year. This includes an output on UNRWA’s effective management and implementation of its Syria programme. This framework will be reviewed by DFID each year to reflect changes in UNRWA Syria’s plans and reflect changes in the operating environment.

Each year, DFID will take a percentage share of the results reported by UNRWA in their annual operational report, based on the percentage that our funding has covered of UNRWA’s total annual appeal expenditure. At this stage the indicative DFID percentage share of results for 2017 is 4.7%.[65] At the end of the implementation period there may be a requirement to adjust our percentage share of UNRWA’s results if UNRWA over or under achieve their appeal funding or UNRWA changes the proportion of funding allocated against each activity, in which case DFID’s percentage share will increase or decrease proportionately.
[65] DFID’s guaranteed contribution of £12m in 2017 equates to 4.7% of UNRWA’s 2017 Syria Appeal ($15,600,400 as of 23.05.2017 oanda)

E. Reporting
DFID receives a half-year and annual Harmonised Operational Reports as the principal means through which UNRWA informs donors how Appeal contributions have been used and results obtained. In addition, through the Advisory Commission (AdCom) upon which DFID OPTs sit, DFID is able to monitor any substantial changes to UNRWA’s rate of expenditure and global operational reserves through the provision of the following reports:
- Monthly financial report – providing detail on budget received and disbursed resources
- UN Board of Auditors report issued annually. This provides an overview of financial and management issues, and recommendations to improve UNRWA’s performance.
- Annual report of UNRWA’s Department of Internal Oversight Services (DIOS) which covers UNRWA’s internal audit, investigations, ethics and evaluations findings.
- UNRWA Syria has agreed to immediately report fraud cases to DFID via a bespoke fraud reporting mechanism.
- Annual harmonised donor reporting matrix showing what UNRWA spends its money on in terms of service delivery.
- Annual report from the Commissioner General of UNRWA to the UN General Assembly. The report includes political, economic, operational and organisational development, as well as a financial overview of income and expenditure.
- AdCom periodic updates on progress against reform and Grand Bargain workstreams

In addition to this, and in line with the DFID Data Disaggregation Action Plan, for a set of key indicators DFID will receive from UNRWA a complementary quarterly breakdown of associated results disaggregated by governorate, district and sub-district in Syria, sex and age group. This will ensure that DFID continues to build on the evidence base of what works in Syria, helps us to identify gaps in our response and ensure greater programme transparency. UNRWA will also report to DFID how many people with disabilities they have supported in Syria each year (see Annex 1).

F. Monitoring

UNRWA Monitoring
UNRWA uses a Results Based Monitoring (RBM) system to monitor the achievement of strategic results and key performance indicators, with data reviewed on a monthly basis by UNRWA Syria and quarterly internal review meetings. In addition, UNRWA reports against targets on a monthly basis through the 4Ws inter-agency cluster system, tracking what, where, when and who conducted activities. Data from the RBM feeds into Results Reports on a semi-annual basis and the donor Harmonised Results Report on an annual basis.

DFID monitoring
Alongside monitoring progress through the project’s logframe, DFID Syria will meet with UNRWA Syria quarterly to discuss and monitor the areas of progress, context, needs, risk and aid diversion. In lieu of DFID staff being unable to visit projects in Syria, DFID has contracted an independent supplier to conduct and document: (1) a one-day field monitoring visit to UNRWA Syria operations each year, and (2) an independent assessment of UNRWA’s monitoring and evaluation (M&E) systems and processes.
1. Field monitoring visits will be conducted by local Syrian field monitors each year and will seek to: verify partner reporting; develop DFID’s qualitative understanding of projects; inform programme management; improve DFID’s response over time, and; document that DFID is performing its accountability function. The outcome of each field monitoring visit will be a report rating the project against a set of 12 standard questions, and a set of recommendations for improvement to be agreed and prioritised between DFID and UNRWA Syria.
2. The M&E Assessment of UNRWA Syria is to provide assurance to DFID that UNRWA has appropriate systems and procedures to monitor and evaluate its response and document areas for improvement, including associated recommendations. Fieldwork was undertaken between November 2016 to April 2017. DFID will work with UNRWA Syria to agree and ensure implementation of the recommendations to support improvements in M&E going forward.

G. Accountability to Beneficiaries
As the main provider of basic services to PRS, it is essential that UNRWA demonstrates accountability and transparency in its delivery of basic services and humanitarian assistance to PRS. The participation of Palestine refugees is one of UNRWA’s minimum protection standards, including the proactive involvement of vulnerable groups such as women, children, older people and persons with disabilities. As part of the 2016-21 MTS, UNRWA has published a Framework for Accountability to Affected Populations (AAP)[66] committing UNRWA to:
[66] UNRWA Framework for Accountability to Affected Populations (p.1)

Information sharing:	Refugee communities are provided with adequate information about UNRWA policies, processes, eligibility and rights to services and relevant targeting criteria
Information gathering:	Use of participatory methods to obtain information from different communities and groups through focus group discussions, inclusion of refugee communities in project coordination teams etc.
Consultation:	Active solicitation of the views of refugee communities in assessing, prioritising, monitoring and evaluating service delivery.
Participation of vulnerable groups:	Use of targeted mechanisms and strategies to enable the participation of people who are marginalised and excluded throughout the programme management cycle.
Complaints and feedback mechanisms:	Systems to provide individuals and communities with access to safe and confidential ways to make complaints, pose queries or comment about programmes, providing refugee communities with information about these processes and feedback on the results achieved.

AAP compliance will be monitored by UNRWA senior staff, reporting against results, formal programme evaluations and annual protection audits. DFID Syria will monitor AAP compliance at quarterly meetings and Annual Reviews.

H. Annual Review
An Annual Review of the UNRWA Syria programme will be carried out by DFID Syria by July each year, starting in 2018, following the receipt of UNRWA Annual Operational Reports. This will be done in close consultation with DFID OPTs team so that UNRWA performance and delivery in Syria feeds into DFID’s broader review of UNRWA’s institutional performance and progress against the UN reform agenda.

I. Evaluation
UNRWA’s medium term evaluation plan is associated with the current MTS 2016-21 and is refreshed annually to reflect the situation in UNRWA, new initiatives, donor interests and risks associated with programme delivery and approved by the Harmonised Results Working Group. Evaluation findings and recommendations are recorded in the DIOS annual report and responded to by management. UNRWA has decentralised some evaluation functions to field offices, providing training and quality assurance manuals to guide the process of contracting evaluations to external consultants. In 2017 UNRWA Syria plans to commission the following:
- Evaluation of cash assistance 2017
- Evaluation of Engaging Youth 2017
- Vulnerability Assessment of Palestine Refugees in Syria

There will not be a separate evaluation for this programme as it is a well-tested humanitarian intervention with a strong evidence base. The risks of carrying out an evaluation inside Syria do not outweigh the benefits the findings could provide. DFID OPTs in liaison with DFID Syria will continue to seek opportunities to feed into wider DFID evaluations, such as CHASE’s independent review of the operational performance of humanitarian agencies, and UNRWA Syria evaluation opportunities through DFID OPTs UNRWA Technical Assistance budget and seats on the Sub-Committee and Harmonised Results Working Group. The Multilateral Organisation Performance Assessment Network (MOPAN) is to conduct a performance assessment of UNRWA in 2017.
Annex 1 Draft programme logframe including indicators and targets

Outcome/ / Output	Indicators		2016 / Baseline	2017 Target[67]
Impact: Lives saved, civilians protected, suffering reduced and resilience built
Outcome: Palestine refugees are able to meet their essential life-saving needs and cope with sudden crisis		1. Number of PRS receiving one or more UNRWA emergency assistance interventions / 2. Number of primary, secondary or tertiary health care visits and/or consultations supported by UNRWA / 3. Number of water-borne disease outbreaks in refugee camps / 4. Percentage of PRS students graduating from basic education (as a proportion of those enrolled) / 5. Percentage of PRS whose livelihoods have improved from accessing microfinance services (disaggregated by sex) / 6. Extent to which PRS consider UNRWA to be protecting and promoting their rights (disaggregated by SSN, Sex, age and disability) / 7. Percentage of UNRWA Syria Appeal funded / 8. Number of persons with disabilities supported by UNRWA’s response in Syria	419,000 / 855,000	418,000 / 1,017,000
Output 1: Palestine refugees in Syria are provided with relief assistance (cash, food, NFIs and shelter assistance)		1.1 Number of PRS provided with cash assistance during the latest distribution round / 1.2 Number of PRS individuals provided with in-kind food assistance during the latest distribution round / 1.3 Number of PRS individuals receiving NFIs / 1.4 Number of displaced people receiving shelter at UNRWA facilities / 1.5 Percentage of shelters in PRS camps connected to adequate water supply services and sewerage networks (both official/UNRWA-managed and others) / 1.6 Beneficiary satisfaction with social safety net programme	414,000 / 406,000 / 254,000	418,000 / 418,000 / 254,000
Output 2: Palestine refugees’ public health needs are met		2.1 Number of PRS visits to UNRWA health facilities (disaggregated by sex) / 2.2 Number of operational UNRWA health centres, health points and mobile clinics / 2.3 Number of UNRWA hospitals accessed by PRS patients / 2.4 Percentage of health centres (HCs) with no stock-out of 12 tracer items / 2.5 Percentage of IDPs receiving potable water during displacement in UNRWA collective shelters / 2.6 Percentage of accessible Palestine refugee camps receiving repair, rehabilitation or reconstruction of water and sanitation networks by UNRWA / 2.7 Number of PRS (women, men and children) provided with hygiene kits to maintain their health, dignity and well-being	1,000,000 / 27 / 13,338 / 88.5% / 100% / 100% / 254,000	1,000,000 / 27 / 13,000 / 100% / 100% / 100% / 254,000
Output 3: PRS children are able to access quality, equitable and inclusive basic education, recreational activities and psychosocial support		3.1 Number of school-age children enrolled in regular classes in UNRWA schools / 3.2 Number of PRS students provided with educational and recreational materials (self-learning materials (SLM), back-to-school kits, PSS/recreational kits, stationery) / 3.3 Number of school-age children receiving psychosocial support / 3.4 Number of students identified with a disability receiving support meeting their specific requirements / 3.5 Percentage of students benefiting from improved teacher quality (based on numbers of teachers with a degree) / 3.6 Number of SLM reviewed against the UNRWA Curriculum Framework / 3.7 Percentage of students meeting required levels in MLA tests (a) Grade 8 Arabic, disaggregated by sex; (b) Grade 8 Maths disaggregated by sex	44,186 / 43,017 / 22,509 / 12,000 / 0	44,900 / 44,900 / 30,000 / 12,000 / 50
Output 4: Vulnerable and at-risk PRS’ rights under international law are protected and promoted		4.1 Number of individuals identified as experiencing a protection risk (general protection, GBV and child protection) provided with assistance (disaggregated by sex, age and disability) / 4.2 Number of PRS provided with legal advice / 4.3 Number of UNRWA staff members trained on protection / 4.4 Number of protection incidents of alleged violations of international law documented by UNRWA (disaggregated by sex and disability)	100% / 964 / 744	100% / 1,000 / 200
Output 5: PRS capabilities are strengthened for increased livelihoods opportunities		5.1 Number of students completing long-term vocational training courses (disaggregated by sex) / 5.2 Number of students completing short-term courses (disaggregated by sex) / 5.3 Number of PRS and Syrians who receive microfinance loans (including women and youth) / 5.4 Degree of employer satisfaction with UNRWA graduates / 5.5 Number of partnerships established in support of livelihood activities for vulnerable Palestine refugees (disaggregated by sex, age and disability)	754 / 1,353 / 9,334	828 / 1,400 / 39,750
Output 6: UNRWA effectively manages and implements its Syria programme		6.1 Multilateral Organisation Performance Assessment Network rating / 6.2 Percentage of PRS who report being satisfied with UNRWA services / 6.3 Resolved case ratio for complaint mechanism brought forward by PRS / 6.4 Percentage implementation rate of DIOS audit, evaluation and investigation recommendations
[67] UNRWA’s 2016 verification survey released in June 2017 documents there are 438,000 Palestine refugees remaining in Syria, 418,000 of which are in acute need of humanitarian assistance including approximately 254,000 displaced at least once within Syria. The targets listed here are as noted in UNRWA’s 2017 Syria Appeal (released early 2017), although we have updated cash, food and NFI targets to reflect latest caseload data. Any changes over 2017 and results achieved against 2017 Appeal targets will be described in UNRWA narrative reporting and DFID Reviews.