Type of Review: Project Completion Review

Project Title: South Sudan Peace Fund

Date started: March 2009	Date review undertaken: March 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
Between March 2009 and March 2012 DFID provided £5,503,111 of funding to Pact’s South Sudan Peace Fund. / The fund was originally established in 2008 with support from the Norwegian Ministry of Foreign Affairs, Canadian DFAIT and Danida. It was part of a larger peace-building programme run by Pact Sudan that including a project on the Transitional Areas and a Water for Recovery and Peace Project (WRAPP). Pact has been working in Sudan and South Sudan since 2002 and its peace-building efforts have historically focused on grassroots initiatives.

What were the expected results?
The SSPF project sought to build local, regional and national capacities in order to foster a peaceful and secure environment for recovery and development. / According to the project’s Logical Framework, the goal of the SSPF is ‘a peaceful and secure environment for recovery and sustainable development in Sudan’. The same document defines the SSPF’s purpose as ‘to improve local, regional and national capacities to mitigate conflict and foster peace and security in Southern Sudan’. / The SSPF aims to build local, regional and national capacities in South Sudan to respond to and resolve community conflict whilst increasing understanding of conflict triggers. / From the outset the programme design was based around two pillars; support for nascent government institutions with the intention of building their capacity so that they would become the focal points for peace-building in South Sudan and support for CBOs that would promote peace-building at a grassroots level. / The South Sudan Peace Fund program (SSPF) supported rapid response to conflict, peace building, conflict mitigation and conflict transformation, civic-voter education, Conflict Early Warning Systems, demobilization, disarmament and reintegration (DDR) and community security and small arms control (CSSAC) and support to key government institutions including the Peace Commission, the CSSAC Bureau, the Legislative Assembly’s Peace and Reconciliation Committee and the DDR Commission.

What was the context in which UK support was provided?
In early 2009 there was a crucial requirement for peace-building initiatives in the then Southern Sudan. / Since 2005 the country had been in an “interim period” following almost half a century of civil war. The Comprehensive Peace Agreement (CPA) guaranteed the southerners the right to self-determination and was marked by a series of milestones including a census and national elections. Should the referendum succeed in taking place independence was inevitable however grave concerns existed about Southern Sudan’s ability to successfully undertake the CPA milestones peacefully. / Alongside the north-south dynamics numerous communal conflicts existed within South Sudan itself. Although there was a brief hiatus in violence in the post-CPA period the instances of communal fighting were increasing on a yearly basis. / Against this background the institutions for tackling the task of peacebuilding were weak. Few active and effective civil society groups existed and the government institutions were nascent. SSPF was designed to bridge the gap between the high demand for peace-building and the low capacity for carrying it out. / Pact had been working in Southern Sudan since 2002 and had established a presence at grassroots level, unparalleled by any other organisation. Its peace-building fund was already established and active.

## Section A: Detailed Output Scoring

Output 1: Increased understanding and awareness of key government officials (GoSS and state level), other partners, and the wider community of the root causes of conflict and triggers in South Sudan and the negative impact of these on longer-term development of the country. Conflict assessments influencing policy and practice of GoSS, institutional donors, Pact and other development agencies. / Over 3000 people directly made aware of the root causes of conflict in Southern Sudan through the dissemination (print, website, presentations) of the reports.
Output 1: final score and performance description: / Final Score: A / The activities of Output 1 consisted of two separate research organisations – London School of Economics (LSE) and International Alert (IA) – carrying out conflict assessments in the first and final years of the project respectively, and disseminating their findings. / Research for the LSE report took place in October and November 2009. Three teams of researchers from LSE, the Peace Commission and Juba University’s Centre for Peace and Development Studies conducted more than 300 extended qualitative interviews and 354 survey questionnaires throughout Upper Nile, Eastern Equatoria and Greater Bahr El Ghazal. 150 hard copies of the first draft assessment were distributed to government officials, CSOs and other stakeholders. In early 2010 a completed version of the 122-page report was produced and circulated to government officials, CSOs and other stakeholders. In total over 300 soft copies and 100 hard copies were distributed. Two dissemination forums were arranged, the report was published on the LSE website and media groups within South Sudan published extracts in print and on their websites. / The second conflict assessment was planned to take place in 2010 however the tender process did not take place until early 2011 and the contract was not finalised with International Alert until mid-2011. At the time of the PCR a final draft is almost completed. Pact and International Alert have plans to disseminate the report and its findings in May 2012 (with additional not DFID funds).
Final results: / Both assessments were of a sound academic and practitioner standard. The LSE report is routinely referred to as a reliable secondary source in literature on South Sudan and has underpinned numerous donor assessments. While the first assessment was carried out at a time when many international organisations had a weak understanding of the conflict dynamics in South Sudan, by the time the International Alert assessment was undertaken the results yielded little information that was particularly new. / Through no fault of International Alert or Pact, the second assessment was lacking almost as soon as it was produced due to the rapidly shifting dynamics of the oil negotiations between Sudan and South Sudan. / Pact succeeded in meeting almost all the tangible outputs of the first activity in Output 1.The only activity that will fall outside of the funding period is the dissemination of the International Alert study. / Pact reported that the first assessment had influenced the Peace Commission’s understanding of conflict dynamics, informed the NGO secretariat and its members on conflict issues and influenced its own strategy. / Activities undertaken by Saferworld in Output 3 may also be regarded as having contributed to Output 1 in that they influenced policy and practice. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N / This activity was rated as medium risk. Arguably the risk of undertaking two research exercises and disseminating findings was low. However, the conflict context throughout the period constituted an ongoing, unpredictable risk to access by researchers.

Output 2: In partnership with key government institutions, develop and operationalise early warning and early response systems to enable government and other agencies respond to early warning of conflict in a timely and effective manner.
Output 2: final score and performance description: / Final Score: A (the original Output did not define the geographic scope of DFID’s expectations. That the system is up and running in three states is therefore assumed to constitute meeting expectations for a one year subgrant) / Output 2 was entirely subcontracted to Catholic Relief Services (CRS) to design and operationalise a Conflict Early Warning and Early Response System (CEWERS). The activities funded by SSPF ran between April 2010 and June 2011. / By June 2011 the CEWERS was operational in Eastern Equatoria and Northern Bahr El Ghazal and in implementation stages in Western Equatoria and Upper Nile State. / Other partners supporting CRS in the project have included UNDP, Danish Demining Group, Nonviolent Peace Force, UNMIS (now UNMISS), the UN Resident Coordinator’s Support Office, the South Sudan Community Security and Small Arms Control Bureau (CSSAC) of the Ministry of Internal Affairs, and CEWARN/IGAD. / The success of the project lies not only in conflict mitigation but also in the process oriented outcomes. The process of setting up a CEWERS is now fully developed as well as the tools and training materials. However the mid-term evaluation noted that the impact from training of Peace Commission staff may have been lost as a result of high turnover. / County Peace Response Mechanisms (CPRMs) have been established throughout Eastern Equatoria and Northern Bahr El Ghazal and the State Government in Eastern Equatoria has endorsed the model where some of the CPRMs are now running autonomously.
Final results: / By the end of the project the CEWERS was fully established and functional in Eastern Equatoria with almost 200 incidents reported in the database. The system is apparently also established in Northern Bahr El Ghazal although CRS did not provide any information on the results in that state. A number of other donors are now contributing to further roll out of CEWERS. / The CEWERS model is sound and replicable in other states. However in a country where illiteracy is so high, the heavy reliance on IT solutions makes implementation a slow process. / CRS claims half a dozen incidents in Eastern Equatoria where the CEWERS has already proved useful, however to date the emphasis appears to have been on early warning and more effort is required to develop the response aspect of the mechanism. This is a common weakness of early warning initiatives. It will also take time to see CEWERS fully integrated into mainstream state security structures rather than established as a semi-parallel system (which it is now though efforts are ongoing to redress this with some success e.g. in Eastern Equatoria). Ultimately, CEWERS remains highly contingent on political will to make the system work (i.e. there is no real accountability or sanction for lack of response). But again this is a recurring problem with early warning internationally and given the starting point for development of early warning in South Sudan progress can be judged as reasonable overall. / Impact Weighting (%): 25% / Revised since last Annual Review? N / The Impact Weighting of this output should have been revised as it was disproportionately large compared its impact on the total SSPF project. / Risk: High / Revised since last Annual Review? N

Output 3: Ministry of Peace and CPA Implementation and South Sudan Legislative Assembly (SSLA) formulate conflict- sensitive policy and legislation that foster community cohesion.
Output 3: final score and performance description: / Final Score: B / The planned key activity under Output 3 was the provision of advisers to the Peace Commission (which, during the life of the project became the Ministry for Peace and CPA Implementation and then reverted back to the status of Commission) and the South Sudan Legislative Assembly’s Peace and Reconciliation Committee (SSLA/PRC). The advisers were to focus on formulating conflict sensitive legislation and providing training. / Very little occurred under this output in the first year of the project as Pact struggled to identify and recruit an appropriate adviser. An adviser was eventually recruited at the beginning of the second year of the project to support the SSLA/PRC. Since UNDP already had an adviser in the Peace Commission, Pact decided that it would be unnecessary and possibly confusing to provide another. Instead the SSLA adviser aimed to fulfil a coordinating role between the two institutions. The adviser remained for eighteen months and a second adviser was brought in towards the end of 2011. / The planned activity of reviewing legislation and providing conflict sensitive recommendations had to be adapted as no legislation was put before parliament during the period that the adviser was in position. This was largely due to the post-election wrangling preventing parliamentary activity, as well as long recesses. The adviser instead shifted his efforts towards providing training in areas such as conflict-sensitivity and budgetary oversight. / The adviser developed training modules and provided training on conflict sensitive legislation, budgeting and budget oversight. The adviser also undertook activities to support a peaceful referendum, arranging a “peace mission” for the SSLA/PRC to meet their counterparts in Khartoum in advance of the referendum where discussions were held on how to ensure a peaceful vote. The adviser also supported the SSLA/PRC members create a Parliamentary Ad Hoc Committee for the Referendum, assisting with drawing up the budget, committee structure, activities and drafting motions. The adviser also organized an exchange trip to Kenya for MPs from the Referendum Committee to learn about early-warning hotlines and voter education. / The adviser and the Referendum Committee developed a framework to strengthen the capacity of legislators to oversee referendum related peace and security activities. The adviser trained MPs in voter education and peaceful electoral processes and they were provided with voter education materials to be used in training their constituents. / With regard to the Peace Commission, the adviser provided support to the strategic planning process as it was elevated from the position of commission to ministry. He also provided training to Ministry headquarters staff and state directors on an overview of the Referendum Act and statutory and non-statutory dispute resolution processes available during the referendum. / In addition to supporting the SSLA/PRC the adviser presented options on peaceful resolution options under the CPA, regional and international law in the event of a delay to the referendum as well as producing a monthly tracking report detailing violence across the region for Pact’s internal use. / The adviser also provided support at the state level by facilitating a session on a peaceful referendum for a Women Leaders workshop in Bor, Jonglei. / Work was also carried out on the Peace Commission’s budget to ensure conflict sensitivity and sound budgeting principles. The adviser reviewed the budget and submitted a report that resulted in the Ministry’s budget being increased for SDG 8 million to SDG 10 million. This was followed up with a workshop on gender sensitive budgeting. / In addition to the work with the SSLA/PRC the Adviser supervised research into oil-related conflict resolution methods. / Six MPs went on a Democracy, Peace and Reconciliation tour of South Africa that was organized by the adviser. The MPs met with South African counterparts as well as civil society organizations, providing them with an opportunity to critically analyze the issues of peace and reconciliation for an extended period, outside of the context of South Sudan. The participants on the trip subsequently elaborated a list of learning points from the tour, on the subject of constitutional development, the role of former rebel movements, decentralization, democracy, human rights, the role and perception of government as well as truth, reconciliation and amnesties. / The adviser also worked with the SSLA to conduct conflict sensitive analysis of the transitional constitution. / A second adviser was provided to the SSLA/PRC in the latter part of 2011.
Final results: / The final score for this output does not reflect the achievements that were made because, regrettably, Pact failed to alter the logframe in response to the changed conditions (though DFID AR process should also have identified this). Therefore, while wise adjustments were made to the activities, these were not reflected in the project planning. / The activities deviated significantly from the original plan and logframe that focused on formulating conflict sensitive policies and legislation. At the time that the main adviser to the SSLA/PRC was in position there was little space in the political sphere for development of legislation as South Sudan undertook its first national election as a semi-autonomous state. Furthermore the SSLA/PRC, with an ill-defined mandate, was inactive and demotivated. / The SSLA/PRC and the Peace Commission have been a disappointment in their lack of achievements in the past year. Changes in South Sudan’s political and conflict context were primarily responsible for this rather than any specific issue with the quality of support provided by the SSPF. Though with the benefit of hindsight, deployment of advisors does not appear to have been guided by any defined strategy for strengthening institutional capacity and to have been somewhat ad hoc. / Pact decided not to provide an adviser to the Peace Commission because UNDP already had an adviser in place. It was hoped that the relationship would be cooperative but Pact reported that the relationship between the two organizations was difficult throughout the project – again this was an issue that DFID should have identified through AR. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: Increased coordination amongst key institutions (Ministry of Peace & CPA Implementation, South Sudan Legislative Assembly, South Sudan DDRCommission, Community Security and Arms Control and South Sudan Human Rights Commission) in support of peacebuilding.
Output 4: final score and performance description: / Final Score: C / At the beginning of the project, in mid 2009, Pact established a Steering Committee comprised of the GOSS key institutions including the Peace Commission (chair), SSLA/PRC, SSDDRC, CSSAC Bureau, SSHRC; INGOs like CRS, DED, Saferworld; and UN bodies like UNDP and UNMIS. However the activities of the Committee were limited when many key members joined politics in advance of the March 2010 elections. The Committee only met 6 times during the life of the project and eventually fell by the wayside. / When the Peace Commission became a ministry Pact supported and encouraged the establishment of an initiative by the ministry for a Peacebuilidng Coordination Forum, that sought to bring the ministry’s peace partners and other government entities together to share information on activities, analysis of the context and support mapping of priorities and opportunities for future peace activities. The first meeting was attended by MoPCPAI, World Vision, Pact, CRS CEWERS Management Team, Saferworld, National Council of Churches, UNMIS Civil Affairs, UNDP, USAID, EU colleagues and staff members from the South Sudan Bureau of Community Security and Small Arms Control (SSBCSAC). A second meeting took place three months later that was attended by 20 individuals from various government and NGOs. However with the Ministry once again being relegated to the status of Commission momentum was lost on the Coordination Forum. / The Pact Advisers to the SSLA/PRC and DDR Commission undertook many of the activities under outputs 3 and 6 respectively.
Final results: / Output 4 undoubtedly had the poorest results of the entire project. It was plagued by the ever-shifting nature of the key institutions – particularly the Peace Commission – as well as the high turnover of staff in both the government institutions and the international organisations. This situation greatly hindered Pact in being able to establish a routine and schedule for coordination meetings. / Very few results are visible from this output, indeed many of the key figures in the relevant institutions, when questioned, were unaware of any organised coordination. One Pact staff member noted that when the institutions did send a representative to coordination meetings it was often a junior member of staff with little traction or authority within their organisation. Indeed there is little evidence of coordinated activity between the respective institutions today. / The exceptions in this output were when the Pact Advisers made efforts at bi-lateral coordination, as the Pact Adviser to the SSLA/PRC did with the Peace Commission. / According to Pact, coordination with the Peace Commission was made more difficult by the lack of cooperation from UNDP and its adviser to the Peace Commission. / The project would have been better served if Pact had re-assessed this output partway through the project and integrated it into Outputs 3 and 6. As with Output 3, the low final score is more of a reflection of Pact’s failure to record changes in circumstance and adjust the logframe accordingly (and DFID’s failure to identify these issues proactively through AR), than it is an indication of a poor performance. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 5: Increased capacity of communities (including local administration and civil society) to respond to threats to community stability in a timely and effective manner.
Output 5: final score and performance description: / Final score: B / This output was supported mainly through small grants provided to CBOs in local areas. Pact’s grants database shows that it provided 93 grants to a total of 73 organisations with grants. Of these, 55 were funded by DFID. The vast majority of these organisations were local organisations. / The grants database shows that investments were spread thinly. Programming was undertaken in all states of South Sudan. The median total value of grants received by small organisations was USD 28,000, with for a period of less than four months. During field visits, beneficiaries and project implementers praise Pact’s ability to quickly respond to needs; however it is unlikely that the investments have made a substantial difference in the capacity of community organisations to respond to threats. / Available documentation about activities is scant, but field visits suggest that the results of initiatives themselves were mixed. A number of livelihoods projects were undertaken. The intention of these is usually to train people in skills they can use to earn income, but the income generation activity is also seen as a way for projects to build connections between people from different groups. Such projects are highly relevant to peace building in South Sudan, but a number of problems are evident in how the activities themselves were implemented under SSPF: / Connection to conflict reduction is often weak: The connection between the livelihood activity and how it will lead to conflict reduction is often poorly described. In some cases it appears that the problem may simply be one of “framing” the project properly. But conversations with field staff and implementers leave the impression that the connection really is often not well-understood by Pact field staff or project implementers. In one project that was visited (Omeo Women - a women’s enterprise harvesting nuts and making the oil into soap) the aim of conflict reduction was altogether left behind. / Unsustainable: the viability of enterprises that are set up through the projects is often highly questionable. The Omeo Women project set out to train women how to process Lulu nuts into oil and soap which could be sold. In addition to having no connection to conflict reduction, the cooperative enterprise was no where near to providing a viable income for the women involved, primarily because the project did not provide the right equipment. The implementing partner judged their own success in terms of delivering training, and that women were showing up to work. / The problems appear to have their roots in the lack of experience of Pact field staff. Field staff are overwhelmingly South Sudanese, and are a great asset in terms of providing understanding of context and local conflict dynamics. When asked about their work in developing projects, they describe that proposals received by proponents are extremely weak and a great deal of effort is required to help partners put their proposals into a form that can be considered. They spend significant amounts of time writing a comprehensible narrative, listing anticipated outputs and making a reasonable budget. Identifying anticipated developmental benefits receives much less attention, and there is no follow-up to ensure that benefits are occurring. / Pact’s performance appears to be best in carrying out peace conferences. Pact has supported many of these and has a well-rehearsed approach. This involves supporting a local organisation to coordinate and make all the arrangements in terms of getting people and supplies to and from the venue (in Eastern Equatoria, government organisations have played this role). The local organisation will also recruit a peace committee - consisting of chiefs, youth and women - to mobilise and engage communities on the different sides of a given conflict. Peace committees are important for “cooling down” those at the centre of the dispute and convincing them to participate in the process, and for raising awareness within communities about the conference and getting people to come. Pact also hires outside expert facilitators to train the peace committee and run the peace conference itself. Conferences provide space for all affected parties to voice their concerns and propose solutions. Outputs of peace conferences are typically resolutions that all sides of disputes publicly commit to, and which local/state governments endorse.
Final results: / Pact’s work under this objectives have left behind a few lasting results: / Resolutions agreed: peace conferences have resulted in resolutions which all sides publicly agree to. These list commitments by all sides to undertake certain actions, and describe actions that different parties will undertake if subsequent events occur that have the potential to spark escalating conflict. / Continued collaboration between communities: field visits showed that several communities are still working together after peace conferences to contain violence. In Nasir for example, the county commissioner keeps in touch with commissioners from Ulang and other counties when there are reports of cattle raids. Each commissioner commits to arresting and punishing youths from their communities who are caught stealing cattle. / Peace committees still active: in Upper Nile, where local authorities are weak, peace committees that were set up for peace conferences are still active. The peace committee in Nasir and Ulang meet irregularly but every month or so, when new issues emerge. In Baliet, the peace committee that was assembled as part of the resolution of the Baliet-Akoka dispute is meeting every two weeks. that and continue to meet and act to avert conflict despite no resources or support. / Network of local organisations: although SSPF funds were distributed too thinly, a positive aspect of this is that Pact has positive relationships with a large number of local organisations in remote villages. These networks provide a platform for future programming. / Impact Weighting (%): 15% / Revised since last Annual Review? N / This output should have had a higher impact rating. / Risk: High / Revised since last Annual Review? N

Output 6: Provide technical support to SSDDRC to implement their community-based reintegration strategy to ensure returnees are fully re-integrated into society in 3 states.
Output 6: final score and performance description: / Final score: B / The SSPF provided support to the SSDDRC in the form of two technical advisors;a Public Information Adviser whose key role was to strengthen communications between different government entities engaged in DDR, DDR participants, and communities supporting reintegration; and a Gender Advisor. The advisors worked together to ensure that community led approaches were adopted by the SSDDRC and other DDR actors and efforts to connect DDR to other areas of peace-building. In addition both advisers contributed to the development of the draft DDR policy paper for 2012-2018. Only the public information adviser was funded by DFID, the gender adviser was funded by Norway. Both advisers were supplied in response to requests from the SSDDRC who identified these as key areas needing support. / Activities undertaken by the Public Information Advisor included: / Rapid assessments to develop a baseline of public information needs for the new DDR program; / Development of guiding plans and toolkit to support SSDDRC Public Information and Communication department to implement community sensitization around demobilization and reintegration of ex-combatants; / Finalization of the SSDDRC website and key national DDR material including multi-language flyers, comic book strips, posters and radio broadcasts; / Facilitated design of a DDR planning event to finalize approaches and timeframes for the new DDR strategy;
Final results: / This output is problematic because it was poorly phrased in the first place and never revised subsequently. “Community-based reintegration” was superseded in the DDR programme by a more individualistic approach. The participants were not “returnees” but rather were supposed to be ex-combatants. The programme took place throughout South Sudan not just in three states. / The contribution of the SSPF to the SSDDRC must be understood within the wider context of the achievements of the DDR programme. The DDR programme in South Sudan has had no discernible impact on conflict mitigation and peace building in South Sudan therefore, despite the best efforts of Pact, and regardless of the quality of support provided, Output 6 cannot be considered to have contributed to a peaceful and secure environment. Between 2009-2011 the DDR programme succeeded in enrolling 12,525 people into the programme (just 14% of the planned caseload), of these, only two thirds completed the programme. Furthermore serious questions were raised as to whether the programme participants were genuine ex-combatants according to the programme’s own criteria. / The public information element of the programme was unsuccessful. Today it would be difficult to find anyone in the South Sudanese public, in the SPLA, or in the DDR programme itself, who could explain the purpose of the programme. With regard to Pact’s input, the adviser and the DDR Commission had diverging views of the role the adviser should play and the relationship was difficult. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 7: Strengthen capacity of GOSS to address community security and Small Arms & Light Weapons (SALW) control in Southern Sudan
Output 7: final score and performance description: / Final Score: B / Output 7 was undertaken in its entirety by the international NGO, Saferworld.Due to the size of the sub-grant to Saferworld (£835,297) a comprehensive logframe was designed that broke down the project into 5 outcomes, each with dozens of activities over the three-year period. / The outcomes, along with some of the key activities were as follows: / 1. Strengthened capacity of key Government of Southern Sudan and security and law enforcement authorities to respond to community security and Small Arms and Light Weapons (SALW) control concerns. / Saferworld’s efforts to strengthen the capacity of GoSS have mostly been focused on support for and capacity building of the Bureau for Community Security and Small Arms Control (CSSAC). Saferworld was key to the establishment of the Bureau prior the start of the SSPF and the sustained support throughout the three years has included the development of the Bureau’s policy and strategic plan, training of staff, public awareness-raising, the making of a documentary film on cattle raiding and assistance in drafting small arms legislation. Most other elements of Saferworld’s programme in South Sudan have involved the Bureau at some level. / One of the most significant activities undertaken by Saferworld as part of this outcome was the tri-state conference involving security actors from Lakes, Unity and Warrap states, to address issues of community security – particularly around cattle raiding and tribal violence. The conference was led by the CSSAC Bureau and was followed up by subsequent meetings including one in Juba that was chaired by the Vice President. As a result the Security Committees of the three states agreed to hold meetings every two months to address potential security issues. / Strengthened capacity of Southern Sudanese civil society to influence and coordinate action to address community security and SALW control concerns. / The majority of Saferworld’s support was provided to the South Sudan Action Network on Small Arms (SSANSA). State-level networks were also supported including in Eastern Equatoria (EEANSA), Warrap (WANSA) and Jonglei (JOANSA). Saferworld supported SSANSA and the state-level ANSAs with numerous activities including a newsletter, organizing radio talk shows, supporting rallies for peaceful referendums in Kwajok, Pibor and Jonglei, Raising awareness on women and SALW through local women’s organizations on International Women’s Day in Morobo and Bor. / In partnership with Pax Christi Saferworld supported a three-day workshop for the EEANSA. A separate workshop on proposal writing, budgeting and report writing was conducted for civil society representatives in Juba. Several workshops were conducted on SALW control awareness and community / Community-level approaches to SALW control that contribute to community stability and peace building are developed and promoted. / Saferworld assisted the CSSAC Bureau to establish a pilot Community Protection Committee initiative in Nyang Payam, EES. Four community consultations were held between July 2010 and April 2011 to identify sources of community insecurity and to develop an Action Plan to tackle them. Local staff were trained to carry out assessments in other areas, with a view to expanding the pilot into Warrap and Jonglei States.According to Saferworld, the forum has proven to be an effective mechanism in discussing and resolving threats to community safety and security. / Saferworld has worked to strengthen community security information in Jonglei State. It has provided support to the student NGO Jonglei State Students for Peace Network (JSSPN) throughout most of the three years including funding JSSPN to undertake research throughout Jonglei and publish and present its findings. Saferworld also supported the Upper Nile Youth Mobilization for Peace and Development Agency (UNYMPDA) on the community security work in Akobo and Pibor, counties of Jonglei State. This included supporting Murle and Lou Nuer communities to establish community security committees. / Saferworld conducted a community security assessment in Warrap and conducted follow-up workshops with peace actors in the state. It also conducted an assessment in advance of the civilian disarmament to identify areas of concern. / The Government of Southern Sudan and international agencies integrate SALW control and community security into policies and program related to security and justice sector development and peace building. / In collaboration with the UK-funded Safety and Access to Justice Program (SAJP) Saferworld conducted a survey and wrote an analytical report on community perceptions of policing. The recommendations were presented to the CSSAC Bureau and the South Sudan Police Service. / Two papers were researched and written analyzing civilian disarmament campaigns undertaken in South Sudan aiming to set out lessons learned from the experiences. / Halfway through the project Saferworld began publishing the South Sudan Monitor, a monthly newsletter to highlight, analyze and discuss key critical issues including analysis of community policing, oil and conflict, security sector reform, the constitutional process, Abyei and independence. / Southern Sudan develops strengthened cooperation with the region to address cross-border SALW control and insecurity. / Saferworld arranged numerous research trips during the three years of the project principally for the CSSAC Bureau staff and SSANSA members, and also for police and members of the DDR Commission. These included: / Supporting the CSSAC Bureau director and deputy to meet with counterparts in Khartoum and in neighbouring countries in order to enhance the Bureau’s engagement in dialogue, cooperation and information exchange across the region. / Saferworld organised and accompanied a group of SSANSA representatives on a study tour to Nairobi to expose them to a different security environment and help enhance their understanding the relationship between community security and arms control; methods of fundraising; independent operations and interventions; and ways of interacting with government and other partners. / Saferworld organised and accompanied an exchange visit by EEANSA and SSANSA to Uganda enabling the exchange of information and ideas with Ugandan civil society counterparts and learning from Saferworld Uganda’s security and conflict assessment in the insecurity and SALW affected region of Karamoja. / In the final year of the project Saferworld organised a visit to Bujumbura, Burundi, to meet with local stakeholders involved in civilian disarmament, community security and DDR. The delegation also met with the Burundi National Focal Point on more ‘technical’ institutional topics like law reform, the computerization of data, communications planning, administration and finance, and the planning of SALW control activities. / These trips served a secondary purpose of bringing together staff from South Sudan’s different government and civil society security institutions. / Saferworld also facilitated the relationship between the CSSAC Bureau and the Regional Centre for Small Arms (RECSA) that resulted in RECSA providing the Bureau with two weapons marking machines.
Final results: / As with most of the other outputs, the results of this output do not reflect the original intention and it would have been advisable for Pact to alter the output accordingly. / The Saferworld project suffered from a slow start in the first year of the project with a high turnover of staff, insufficient operational capacity and a poor sense of strategic direction. This situation was rectified considerably in the subsequent two years. / The support that Saferworld has provided to the CSSAC Bureau has been invaluable in terms of building the Bureau’s capacity. The “software” provided by Saferworld’s technical support has been complemented by UNDP’s support in the form of “hardware”. Whether the Bureau itself has had significant impact on community security in South Sudan, or represents “the Government of South Sudan”, remains in question. Dogged by leadership struggles and with little traction among the other key security institutions, its ability to influence arms control or community security policy remains in doubt. The most striking example of this is the failure to have any significant impact on the March 2012 civilian disarmament campaign. This raises the question of whether Saferworld’s support was most effectively targeted. / Saferworld’s reporting of its activities is detailed and highly competent. However, subsequent to the many workshops, rallies and assessments, and the official statements that were made, it is often difficult to identify any discernible impact of many of the activities. Too often reports of activities comprised of statements such as “the recommendations were very well received”. Furthermore, on more than one occasion papers were written simply because they were activities in the logframe but without any sense of who the audience would be or what was the purpose. / Although not specified as an activity in the logframe for the project, Saferworld’s contribution to international advocacy on the issue of community security in South Sudan has been significant. This is one of the organisation’s core strengths and the ability to transfer grassroots information and experience to advocacy in Europe has been a success of the project. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? N / The logframe has remained the same throughout the project. / This is a significant failing on the part of Pact since the final score reflects achievements against the logframe. DFID should also have picked up on the need to revise the logframe through routine AR, / 1.2 Final Output score and description: B / The seven different outputs of the SSPF, the diverse methodologies for achieving them and how they have variously performed over the past three years cannot be adequately reflected in a single Output score. At least one output failed entirely, others have under-performed, and some have had a degree of success but that success is hard to measure because of the very poor evaluation methodologies within the project.
Direct feedback from beneficiaries / The beneficiaries of SSPF comprise many different stakeholder groups. The people of South Sudan are the ultimate beneficiaries of the project, however it is impractical to have appropriate representation in this review, for the purposes of this review, the beneficiaries are more appropriately understood as the community based organizations – funded under output 5, the government institutions supported under outputs 3, 4, 6 and 7, and the two large sub-grantees, CRS and Saferworld funded under outputs 2 and 7 respectively. / CBOs - Pact provided sub grants to over 40 CBOs through the SSPF. Although it is not possible to get feedback from all of these organizations, the general feedback from the sample visited by PACT’s independent Final Evaluator was extremely positive. Grassroots NGOs in South Sudan rarely have the opportunity to access international donor funds and when they do they usually lack the skills to provide the requisite documentation and accountability. Pact worked closely with its CBO sub-grantees and provided enough support and oversight to enable the CBOs to access funding that would otherwise have been out of their reach. / Government Institutions – The government institutions that were beneficiaries under this project were the Peace Commission, SSLA/PRC, CSSAC Bureau and the DDR Commission. During the course of this DFID PCR, all of these institutions agreed that the support from the SSPF was appreciated and the majority acknowledged that, in view of their low capacity in 2009, technical support was more valuable and suitable than financial support. The institutions gave different reports on the quality of the technical advisers that were provided. While the SSLA/PRC spoke very highly of the work done by the SSPF adviser, the SSDDRC were less impressed. The CSSAC Bureau went so far as to claim it would not still be in existence if not for the support provided by the SSPF via Saferworld. Somewhat inevitably, all of the government institutions stated that in future “hardware” should be provided in the form of vehicles, communications equipment etc. in addition to the “software” of advisers. / CRS and Saferworld – CRS was very positive about the support provided by Pact and the networking opportunities afforded by being part of the SSPF. It should be noted that the CRS programme manger for CEWERS was a former long-serving Pact staff member who was able to positively utilize the SSPF network. Saferworld’s reported a more negative experience and made clear that a direct relationship with DFID would have been preferable and more productive for their project than having Pact as an intermediary.
1.4 Overall Outcome score and description: B / According to the project’s logical framework, the goal of the SSPF is ‘a peaceful and secure environment for recovery and sustainable development in Sudan’. The same document defines the SSPF’s purpose as ‘to improve local, regional and national capacities to mitigate conflict and foster peace and security in Southern Sudan’. It is interesting to note that in subsequent project documents the outcomes of the project are almost never mentioned. This is telling because the project has been characterized by a lack of well-defined theory of change. / One of the major flaws of the SSPF is that the logframe was badly designed with some of the outputs not being coherent and too much reliance on quantitative indicators for activities. Furthermore, as the project progressed, and it became clear that changes needed to be made to the logframe, there was still a failure to alter it accordingly. In addition a baseline assessment was never conducted and key terms such as “peace” and “security” were never defined, making it impossible to judge whether sub-grants that were made within the project genuinely contributed to peace and if so why. Such failure not only means that the SSPF necessarily receives a low final score but it also implies a lack of strategic direction on the part of Pact. DFID should also have identified these project failings at an earlier point in the SSPF’s life-cycle. / Undoubtedly individual successes have been made. The LSE conflict assessment opened up discussion among peace actors in South Sudan at a time when there was a dearth of good information available, support provided to the SSLA/PRC was of a high standard, Saferworld’s support to the CSSAC Bureau has been key to its institutional development, more than 40 CBOs have received direct support both directly from Pact and via Saferworld’s support to SSANSA members. / Of particular note has been the support that the SSPF has provided to women through output 5 – the support to CBOs. The SSPF provided training to women in the DDR programme who had been associated with the SPLA as well as supporting women in Eastern Equatoria to start up their own soap producing business. It should be noted that women of South Sudan are “the marginalised of the marginalised” and any initiatives to assist them is an improvement on human security in the country. / In particular the success of a peaceful election and referendum should not be underestimated. Civil society in South Sudan played a key role in the success of these two potentially volatile events by disseminating information and providing oversight. The SSPF provided invaluable support in these activities. / The seven different outputs of the SSPF and the methodologies for achieving them are so diverse that it is almost impossible to accurately reflect the performance of the project in singular score. As noted above, at least one output failed entirely, others have under-performed, and some have had a degree of success but that success is hard to measure because of the very poor evaluation methodologies within the project. / As the project draws to an end South Sudan may look back on the achievements of successfully attaining independence through a peaceful referendum, yet in the past 6 months the country has experienced the highest levels of inter-communal violence since the signing of the Comprehensive Peace Agreement. In such circumstances it is not possible to claim that the goal of ‘a peaceful and secure environment for recovery and sustainable development in Sudan’ has been achieved, indeed by some measures the country is further from peace than when the project started. / Impact and Sustainability / It may be several more years before the full impact of the SSPF is realized. Through the various outputs hundreds of South Sudanese people have been trained by Pact, Saferworld and project consultants in a variety of skills and knowledge that will equip them to work towards a peaceful and secure environment. While the individuals may move on from the original institutions where they received the training, the knowledge and skills will likely remain with many of them and within South Sudan. Additionally, over 40 CBOs have had their capacity built and provided at least temporary livelihoods opportunities to hundreds of individuals. / Pact plans to continue with a new peace programme that will concentrate its resources geographically in South Sudan on conflict clusters. The new programme has already secured funding of $6.4 million for 2012-2014 from Danida. It is also targeting its support for CBOs at a more select group via its “CBO of Excellence Initiative” which will see nine CBOs supported with mentoring and training as well as financially over a sustained period.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / Towards the end of the project there was an underspend which resulted in a flurry of hastily-planned activities being undertaken, primarily by Saferworld. / 2.2 Key cost drivers / The changing rate of exchange in South Sudan throughout the life of the project has worked in its favour. At the start of the project the rate of Sudanese pounds to dollars was 2.5 whereas by the end was 4.0. / This advantage was mitigated by the weakened rate of the British pound against the dollar in the same period and also by the rising costs of commodities in South Sudan since May 2011. / 2.3 Was the project completed within the expected timescale: N / A no-cost-extension of two months was required to allow Pact to complete its final evaluation.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / Two thirds of the way through the project South Sudan attained independence from the north. This had a significant impact on the project aims. The project was initially conceived as a means of consolidating the peace brought about by the Comprehensive Peace Agreement in the context of north-south tensions. While there was a clear focus on the mitigation of intra-south conflicts, which maintained relevance in both the pre- and post- independence contexts, in the final third of the project the focus shifted solely to southern conflicts. The LSE Conflict Assessment produced as part of the SSPF in 2009 provided a sound evidence base for this. / A large aspect of the project was predicated on support for the Peace Commission. However, during the life of the project the Commission changed status to a ministry and back to a commission, as well as under-going numerous changes of key staff and leadership. These frequent changes, compounded by the already weak capacity of the nascent institution considerably impacted on the planned model of using the Peace Commission as the principle vehicle for undertaking the project. / If Pact had a theory of change it was not clearly elaborated or documented. From looking at the project activities over the three years it is clear that Pact responded to the changes in evidence but the process by which this took place is unclear. / 3.2 Set out what plans are in place for an evaluation. / Pact has contracted the consultancy Integrity Research to carry out an evaluation which is due for completion by early May An independent mid-term evaluation of the SSPF was also completed March/April 2011.

4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? N / 4.2 Risk funds not used for purposes intended / There were two levels at which there may have been risks to the funds; in the provision of funding to Pact itself and in Pact’s provision of funding to sub-grantees. / With regard to Pact, throughout the SSPF it has submitted a full suite of financial management documents to DFID. At the time of this PCR, Pact has contracted McGladrey & Pullen, LLP, Certified Public Accountants to conduct an annual audit. / With regard to financial risk at the CBO-level of the SSPF, Pact is highly experienced in working with CBOs and typically issues cost-reimbursable awards, which allow it to carefully monitor sub grantees’ expenses. Any questioned costs are discussed with the sub grantee and either allowed or disallowed based on the explanation provided. / For some partners who have not demonstrated significant evidence of being able to reliably manage funds, Pact may include special award conditions that require additional reporting (ex. evidence of having obtained three quotes prior to specified procurements) or set milestones that the partner must meet before funds are disbursed (ex. setting up a project-specific bank account with three signatories). In some cases Pact may issue a cost-reimbursable award. / The determination about whether to issue an in-kind or cost-reimbursable award and which conditions to include in each is based on the capacity assessment that every partner completes prior to receiving an award from Pact. / 4.3 Climate and Environment Impact / The SSPF was designed before climate and environmental impact were part of the considerations in the planning process. However the impact of the project on both these factors was low.

5. Value for Money
5.1 Performance on VfM measures / No VfM measures were established as there was no business case when the project was developed. / 5.2 Commercial Improvement and Value for Money / Pact ensures value for money in its projects by three measures: / Working with local partners. These CBOs have lower overheads than international organizations. / Investing in people and institutions. By working consistently to build the capacity of CBOs Pact generates behavior change which reaps benefits throughout the project and beyond. / Economies of scale. Pact has a long-term, full-time presence in South Sudan, including technical leads, programmatic and financial management, and administrative support. Because they have many other donors and projects running concurrently, they have been able to distribute the costs of maintaining a presence and integrate activities for greater effectiveness and impact. / 5.3 Role of project partners / Implementing partners in the SSPF were CRS, Saferworld, International Alert, LSE and over 40 CBOs. The funding provided to Saferworld represented 30% of the funding spent on programme outputs, the CRS funding was 6%, the two reports undertaken by LSE and International Alert accounted for 14% of funding spent on programme activities, whereas the sub-grants to over 40 CBOs represented 29%. / See individual outputs above for comments on performance. / 5.4 Did the project represent Value for Money : / The total project cost was £5,503,111 over three years. / 83% of costs were direct programme costs / 53% of funding was spent on programme activities / £816,665 was spent funding 55 projects undertaken by CBOs / Given the very different outputs it is difficult to give an overall assessment of the project’s value for money. / Output 5, the funding of peace-building activities by CBOs represented good value for money with 55 individual projects being implemented by over 40 CBOs throughout South Sudan at relatively low operational cost (vis a vis INGOs or UN agencies). / Output 6 represented very poor value for money. Support to the DDR Commission in the form of a public information adviser cost £102,574 yet there was very little public awareness of the DDR programme and the DDR programme itself made no impact on security in South Sudan. / Output 7 was the most expensive and consisted of funding to Saferworld at a cost of £835,297. Output 7 had mixed results. Some individual activities were wasteful, such as the commissioning of expensive reports that were never published or utilized, whereas other activities, such as those providing support to the CSSAC Bureau have resulted in the strengthening of the Bureau’s capacity. / Overall it can be said that, although no clear theory or change is evident, the SSPF has directly and positively impacted dozens of CBOs and hundreds of individuals. Even if a small percentage of these organizations and individuals have succeeded in mitigating conflict in South Sudan as a result of the support that they received from SSPF it must be regarded as value for money (it is estimated that £1 spent on effective conflict mitigation can save £4 in later conflict response).

6. Conditionality
6.1 Update on specific conditions / N/A. No Financial Aid was given directly to a partner government.

7. Conclusions
The outcome planned by the SSPF - ‘a peaceful and secure environment for recovery and sustainable development in Sudan’ – was overly ambitious and relied on innumerable socio-political factors that were outside of the control of Pact. Furthermore the project relied heavily on the strategy of supporting formal government institutions as a means of attaining its outcome. These institutions have, over the past three years, under-performed due to a variety of factors. Regardless of the quality of support that SSPF provided to these institutions, their failings mean that the project has also underperformed. / The project has been characterized by a lack of any apparent theory of change and decisions, particularly on the funding of sub-grants, appear to have been taken via an organic approach rather than with the direction of a clear strategy. This has been compounded by a weak logframe, a lack of a robust M&E system and poor institutional documentation processes. / Despite these reservations it is important to acknowledge the successes in of the past three years. The active involvement of civil society in information dissemination throughout the election and referendum periods undoubtedly played a role in securing the peaceful undertaking of both these potentially volatile events. Furthermore, a strong civil society is key to improved security in South Sudan, and as a vehicle for supporting the development of CBOs the SSPF has been crucial in building the capacity of civil society. Pact’s geographic spread throughout South Sudan and its excellent reputation in some of the farthest reaches of the country mean that it was the ideal organization to undertake this task. / Lessons learned from the SSPF are as follows: / DFID’s decision to fund the SSPF for three years provided Pact with sustained support that is unusual in the context of South Sudan where most other donors are providing a maximum of one year’s funding on peace. The duration of the funding was crucial in enabling the SSPF to provide sustained support to both nascent government institutions and CBOs that likely significantly strengthened resilience to conflict during the uncertainties of the CPA period. / Robust monitoring and evaluation mechanisms that were lacking in the SSPF need to be in place for future peace-building projects. The mechanisms must utilize both quantitative and qualitative indicators and prioritize measurement of outcomes and impact over inputs/outputs. A baseline assessment, which was never conducted in the case of the SSPF, is crucial for assessing peace-building progress. / Information sharing with the other major peace-building actors in South Sudan such as UNDP, AECOM and Saferworld is crucial. Among the major peace-building institutions in South Sudan there needs to be honest and regular evaluation of the initiatives that have succeeded and those which have failed in order to build effective and coherent strategies that diversify from the current strategies which are proving inadequate. / The failure to establish and document the nature of the key relationships and project governance at the start of the project led to misunderstandings and frustrations. In an environment where turnover of staff is high and in a project with such a long duration rigorous documentation is essential to ensure that relationships are well defined. / Pact wisely chose to adjust certain activities within the project in response to evolving circumstances. Although the changes were discussed with DFID they were not documented or reflected in the logframe, this resulted in the appearance of Pact having failed on some activities. Documentation of project changes is key to providing reassurance and direction. / Future peace-building projects need to be more targeted both geographically and thematically i.e. to have clear theories of change from the outset. Conflict dynamics differ throughout South Sudan and no model or study of the entire country is sufficient. / The original project design was based on the premise that peace-building could, in part, be accomplished via key government institutions. Unfortunately these institutions did not develop and perform as anticipated. The money and effort that was put into building the capacity of these institutions was not commensurate with the results yielded.

8. Review Process
This review was conducted by Lydia Stone, an independent consultant with final revisions and input from HMG’s Juba based Conflict and Stabilisation Advisor, Helen Lewis. / The review and write-up was conducted over 10 days, as provided for in the Terms of Reference, during March and April 2012. / A literature review was conducted that included a wide range of Pact documents. The key documents that influenced the content of the PCR included: / Annual reports of SSPF / Quarterly narrative progress reports to DFID / Mid-term evaluation / Conflict assessments / Inception Report / Budgets / Logframes / Pact’s South Sudan Country Strategy / CRS’s end of project report / Pact was unable to provide some documents that the consultant requested, for example annual reports from Saferworld. Much of the documentation that was provided was delivered late and was disorganized despite intervention from Helen Lewis. / Interviews were conducted with the following individuals: / Dina Parmer Pact Conflict and Policy Adviser / Emmanuel Gumbiri Pact SSPF Programme Manager / Mauro Tadiwe Pact Country Director / Rachel Beck Pact Monitoring and Evaluation Manager / Stephanie Marienau Turpin Pact Grants Manager / Richard Reeves International Alert Head of Research and New Initiatives / Hesta Groenewald Saferworld Head of Sudan and Great Lakes Programme / Brigadier Christo Fataki CSSAC Bureau Director of Small Arms Control / Dr Riak Gok CSSAC Bureau Deputy Chairperson / Ngong Deng Gum SSLA/PRC Former Deputy Chairperson / Alex Dowling Independent Consultant Author – SSPF mid-term evaluation / Rosa Weet SSDDRC Gender Adviser / William Deng Deng SSDDRC Chairperson / Alfred Okech CRS CEWERS Programme Manger / Peter Cross Saferworld Former South Sudan Programme Manager / Within the timeframe allowed for this PCR there was not opportunity to fully and fairly reflect on the achievements of Outcome 5 that comprised of support to 55 CBOs. It should be noted that a Pact-contracted evaluation was undertaken concurrently by the consultancy Integrity Research that provides more detailed information on the support provided by the SSPF to the CBOs. This will be available early May 2012.