Inception Review of the project Reducing Maternal and Child Mortality through Strengthening Primary Health Care (RMCH) and Annual Review of the project Essential Steps in Managing Obstetric Emergencies (ESMOE)

Narrative Report, 19 October 2012

This inception review of the project ‘Reducing Maternal and Child Mortality through Strengthening Primary Health Care’ (RMCH) and annual review of project ‘Essential Steps in Managing Obstetric Emergencies’ (ESMOE). The review was undertaken by Dr. Neil Squires and Ms. Nothemba Kula, between 15 and 18 October 2012, and consisted of a document review, stakeholder interviews and a field visit to an ESMOE saturation training course.

Rating of Progress
Overall progress is rated against DFIDs 5 point rating scale (A++, A+, A, B, C)

Progress is rated as A.

The outputs specified in the logframe are in line with (but do not exceed) the expected achievements at this early stage in project implementation.

Although the logframe for the project is not yet finalised, indicators are near final, and the timing of this inception review means that its recommendations can feed in to the finalisation process.

Background to Review

DFID is providing a total of £17m over 4 years in support including ESMOE at £2m, which started a year ago contracted separately through the Liverpool School of Tropical Medicine, and the new three year 13,527,294 m RMCH programme which is managed by a consortium of agencies led by the Futures Group.
The RMCH programme has been running for 5 months since June 2012 and is now at the end of its inception phase. The programme has met expectations in terms of planned activities, however an agreed final logframe, with indicators for measuring outputs is one of the deliverables for the end of the inception phase and has not yet been agreed and signed off with the National Department of Health (NDOH) and this is now a priority as the inception phase is coming to a close at the end of October.

A number of recommendations on the logframe and indicators have been made as a result of the review and delayed finalisation of the logframe is therefore an opportunity to strengthen the indicators against which project progress will be monitored over the next 2½ years.

The ESMOE programme has been running for one year. For the purpose of this review ESMOE was assessed as a component of RMCH under output 2, however ESMOE is managed under a separate contract and future reviews will need to assess progress against the agreed logframe for ESMOE, as well against an agreed set of indicators that should be nested in the RMCH logframe. This review makes recommendations about the need to strengthen the working relationship and management structures between RMCH and ESMOE.

Contextual factors which impact on the likely success of the project

Political Commitment: Changes in the political leadership in South Africa in 2009 created new opportunities to tackle unacceptably high maternal, neonatal and child mortality in South Africa (mortality levels are particularly striking given RSA’s GDP/capita). There has also been a significant shift in policies towards HIV/AIDS treatment since 2009, and for treatment to prevent mother to child transmission from 2004, and this is having significant impact on HIV related maternal and child mortality.

The impact of HIV: The Confidential enquiry into Maternal deaths 2008-2010 indicates that 80% of maternal deaths in SA had had an HIV test and that of those deaths, 70% were HIV positive. Chweneyagae D. et al[1] estimate the Maternal Mortality Ration (MMR) for HIV+ve women is 430/100,000, and for HIV–ve women is 75/100,000. The major cause of death in HIV+ve women is non-pregnancy related infections, however it should also be noted that HIV+ve women also have a higher rate of death from pregnancy related causes, such as haemorrhage. This means that in assessing the impact of the RMCH/ESMOE on maternal, neonatal and child health, the impact will need to be distinguished from HIV specific interventions. Data can be disaggregated by cause in order to allow this distinction.
[1] The impact of HIV infection on Maternal Deaths in South Africa. Chweneyagae D. et al: S.Afr J OG 2012;18(3)

The Rapid Mortality Surveillance Report 2011 (published August 2012) indicates the following life expectancy and mortality statistics and trends:

Table 1: Life expectancy and morality trends and targets 2009 – 2014.
Indicator	Target 2014	2009	2010	2011
Male life expectancy at birth	56	54	55.5	57.2
Female life expectancy at birth	61	59	60.8	62.8
U5MR per 1000 live births	50	56	53	42
IMR per 1000 live births	36	40	37	30
NNMR per 1000 live births	12	14	13	14
MMR per 100,000 live births	270	310	333	…..

The project is operating in a context of increasing life expectancy and decreasing infant and under 5 mortality, which is largely contributed to by the impact of ARV treatment for HIV/AIDS. It is notable that there has been little change in neonatal mortality and the trend for maternal mortality is complex (related to the delayed impact of scale up in HIV treatment). It is expected that maternal mortality as a result of HIV should begin to decline from 2011 onwards.

The Negotiated Service Delivery Agreement: High level political commitment to reduce maternal, neonatal and child mortality create a highly supportive context for this project, which should facilitate implementation. The Negotiated Service Delivery Agreement (NSDA) includes a commitment to achieve the targets specified table 1 above, in the context of the following objectives:

- To increase life expectancy at birth
- To reduce maternal and child mortality rates
- To combat HIV/AIDS and TB
- To strengthen the effectiveness of the health system

The Confidential Enquiry into Maternal Deaths: There is also a high level commitment to the ESMOE component of this programme, which will facilitate its implementation. The 5th report on the Confidential Enquiries into Maternal Deaths in South Africa (Saving Mothers 2008-2010) recommends training all health care workers in maternity care in the ESMOE programme; supports the idea of targeting the districts with the greatest problems first (the 12 districts out of 52 nationally selected for ESMOE support account for 50% of maternal deaths); and recommends National and Provincial directors provide support for the training of doctors and midwives in ESMOE. This recommendation is also made to Provincial and District managers – emphasising the importance of CEOs allowing staff time for training.

A number of positive supportive actions to reinforce the training element are already in place, with ESMOE training being accredited for CPD. All doctors need to demonstrate completion of 30 hours CPD per year for continuing registration.

Reform and Restructuring: Other key components of the programme are also well established national priorities. The District Clinical Specialist Teams in South Africa, Ministerial Task Team report to the Minister of Health sets out the roles and functions of the DCSTs, with job descriptions for each of the team members. The project is therefore supporting an initiative for which there is a strong national commitment, both in policy and resource terms. This will help minimise risk to the project, although not remove the challenges related to recruitment and retention of key personnel.

The national commitment to re-engineer primary health care is also strong, and there is already evidence of its impact. Salary differentials introduced to encourage staff to move from the centre to district level have already led to a movement of staff.

Other factors, outside of the project may also impact on future maternal mortality. For example, the Occupation Specific Dispensation Act may, inadvertently, have had negative impact on maternal mortality with the failure to provide dispensation for nurses involved in termination services leading to an exit of nurses from the service. This may have increased the risk of unsafe abortion with a negative impact on maternal mortality. In contrast to this, an increasing commitment to increasing contraceptive choice (no contraceptive implants are currently licenced in South Africa), may have a positive impact on contraceptive prevalence with resulting reductions in maternal mortality.

Expanding the scope of the Project may impact on Equity: The scope of the project has expanded, from an original focus on 15 districts (selected on the basis of their poor maternal, neonatal and child health indicators), to 25 districts, also prioritised on the basis of need. However there is a national commitment to roll out DCSTs nationally to all 52 districts, and it will therefore be important to track the added value that is brought to the 15, then 25 districts by the project, if we are to be able to attribute success to project funding and also ensure that the 15 most poorly performing districts have a chance of narrowing the inequality gap on maternal and neonatal mortality.
Review of Progress by Output

Output 1: Districts able to oversee improvement of reproductive, maternal and child health services

There is a planned roll out of District Clinical Specialist Teams nationally. Currently only 2 out of the 52 Districts have the full complement of 7 DCST members.
The purpose of the RMCH project was in part to address inequity in maternal and neonatal morbidity and mortality in South Africa, and 12 of the 15 target districts identified by ESMOE for the first phase of the project account for 50% of maternal mortality. If the project is to demonstrate added value, it needs to ensure that the capacity of the DCSTs in the districts with greatest need is built up more rapidly than the creation of teams nationally. In discussions with NDOH, it was indicated that all districts in South Africa face problems – however the purpose of having a project which addresses inequality is to prioritize the districts in greatest need first. It will be important to compare the priority districts with others and to demonstrate relatively faster progress in order to justify the prioritisation process. It will therefore be important to raise the issue at the National Health Council that the 25 districts be prioritized the same as NHI districts in the establishment of teams to improve maternal and child health services in SA
In terms of measuring progress against output 1, the logframe indicator currently looks at numbers trained. Important that the programme to orientate DCSTs ensures that once recruited they are provided with the tools to function. However teams formed or partially formed is also an important measure of functionality but recruitments are the responsibility of the NDOH. Key to the success of this output will be the extent to which DCSTs are considered fully or partially functional. A more nuanced indicator of DCST functionality will be needed if team capacity is to be assessed and monitored.
Recommendation: It is recommended that the project monitors levels of DCST functionality by measuring both the establishment of minimum teams (dyads) in the 25 districts, and monitors progress building team strength through numbers trained as per the comprehensive orientation and mentorship support manual that is being developed and implemented through the programme. It will be critical to ensure that DCSTs are strengthened in the priority districts, as a priority. Without this emphasis, the equity dimension of the project inputs will be lost.

Output 2: Strengthened delivery of school health services, ward level PHC teams and obstetric and neonatal emergency services

This is a complex output, with three quite distinct sub-components on school health, PHC teams and emergency services. One of these sub-components includes the ESMOE project, which has a distinct set of outputs. Each component is discussed briefly below:

School Health:
A key challenging in evaluating the impact of the project on School Health will be to separate out changes and interventions that are already underway with NDOH and Ministry of Basic Education support, in order to determine how the project is adding value.

The project potentially adds greatest value in strengthening health promotion and health education through the Integrated School Health programme, as it can draw down technical expertise in the development of health education programmes. However, one of the indicators selected for measuring project performance originally, was not considered useful for the demand creation role that will be played by the programme must align with the national indicators. The annual performance plan for 2012/13 – 2014/15 (p 64) has an indicator of the percentage of quintile 1 schools visited by the school health team to provide integrated school health programme services – the target for 2012/13 is that 80% or 6454 schools should be visited. Providing that there is a clear template for a visit, and some evidence that visits are an effective mechanism for improving school health delivery, then this is a useful indicator. However, if we want to determine the impact of the project on strengthening health education through School health, then impact indicators of improved health outcome will be needed.

Recommendation: The project needs to define a health education outcome, for students targeted with sexual health messages, in order to demonstrate that its technical inputs are adding value.

Community Health Workers:
On CHWs, the original logframe indicated the number of CHWs undergoing orientation training. However, as the programme is not directly responsible for training CHWs, and training on its own may not make a difference to practice, this is not a useful indicator. The programme is seeking to ensure that trained CHWs effectively refer client groups to appropriate services, therefore the newly proposed indicators of referral of women and children are more appropriate.
Calculating the added value of the project will be a challenge, given that training of CHWs is not a direct project responsibility and is happening nationally, not just in the project target districts. There are about 72,000 CHWs nationally, trained in a variety of different ways for different purposes. Of these, 5000 have been trained (prior to the project) on RMCH and there are plans to train a further 5000, and to include orientation within this training. What the project seeks to do is to increase women and neonates referred in to health facilities for care and to increase the number of women who have an antenatal visit in the first trimester (or rather the first 20 weeks -currently less than 30% of pregnant women have an ANC visit in the first 20 weeks).
Improvements in early ANC attendance would reflect improved referral but this will require a comparison of intervention districts with no-intervention districts. This should be considered as part of on-going monitoring and evaluation, as a way of assessing the impact of CHW orientation.
Another potential benefit of CHW training would be to increase postnatal follow up within 6 days of delivery. Trends could be compared between intervention and no intervention districts. However, recognising that DCST and CHW programmes are being rolled out across the country, not just in the 15/25 project districts, the challenge will be to identify the added value that the project is bringing.
Recommendation: It is recommended that project evaluation considers how best to quantify the benefit of CHW orientation in terms of effective referral and how to compare intervention and non intervention sites.

Outputs related to ESMOE:
One of the indicators under output 2 makes reference to the ESMOE programme. However the indicator only captures a small component of what ESMOE does. The indicator is ‘Number of DCST specialists trained in ESMOE’. This is an activity measure which does not capture the intent of ESMOE to provide saturation training (training over 80% of health workers who deal with maternal health) or the intent to use simulations (Fire Drills) to train and improve/maintain quality of ESMOE, nor the evaluation component that will allow Fire Drill only ESMOE to be compared with saturation training and assess relative cost effectiveness of the two approaches.
Since a number of the ESMOE outputs could have a significant impact in terms of shaping national efforts to strengthen maternal health, it is important that they be reflected in the RMCH logframe. More importantly, RMCH should actively draw on the ESMOE outputs and build links to other outputs of the RMCH programme (for example, publicising the quality standards promoted by ESMOE could be vehicle for increased accountability and linked to demand side interventions under output 3).
Recommendation: The links and interactions between ESMOE and RMCH have started through the DCST programme but should be strengthened further to show linkages in other technical outputs of the RMCH programme. Currently there are 5 people who are on the ESMOE Board, who are also on the steering committee for RMCH (Jack Moodley (chair ESMOE Board) Nat Khaole (NDOH), Bob Fryatt (DFID), Yogan Pillay (NDOH) and Robert Pattinson (ESMOE). However, the Futures group (RMCH consortium) is not on the ESMOE board, this should be corrected.
A progress review of ESMOE
ESMOE type training has been delivered by LSTM under the DFID funded Making it Happen Programme and shown to be effective in five demonstration countries (India, Bangladesh, Kenya, Zimbabwe and Sierra Leone). Lessons learnt and experience gained are being used to inform the programme of implementation and evaluation in RSA. Progress has been good, with high level endorsement of the ESMOE approach (see context section above and references to ESMOE in confidential enquiry report).
Baseline data for the intervention districts has been completed and all districts have received mannequins. Saturation training has begun, and we visited a training which was well organised and getting a positive feedback from participants. Trainers trained as master trainers indicated that they had had initial training and refresher training and there was evidence presented that the quality assurance process of training had been used to good effect, identifying and correcting dips in training practice. Good materials including aide memoires had been developed.
The design for the evaluation of ESMOE with comparison of fire drill only versus fire drill plus saturation training was underway, and there is good prospect of a robust evaluation and costing which should help inform both national policy and practice (and be of international interest). The training is recognised for Continuing professional development accreditation and satisfies over 20 hours of the needed 30 hours of training per year. The possibility of hospitals getting fire drill training accredited for CPD on a facility by facility basis means that resistance due to the time commitment of regular fire drills should reduce.
Recommendations:
- In order to adequately capture the ESMOE contribution to RMCH, then a nested logframe approach should be used in order to ensure that RMCH partners are aware of the objectives and outputs of the ESMOE component. This should be reinforced by having RMCH representation on the board of ESMOE.
- A forum for technical dialogue and exchange between ESMOE and RMCH needs to be established, to ensure that the projects are mutually supporting. As an initial step it is suggested that the ESMOE data monitoring team, and administrative team (i.e. Dr Jenny Makin, and Mrs Cathy Beziudenhout) should meet with Prof. Pattinson, Dr Ngubane, Petro Rousseau, and those involved with their data monitoring to discuss how the DCST programme linkages with ESMOE can be supported and how the benefits of this might be monitored.

Output 3: Improved demand and accountability for RMCH services
The original project documents specify civil society organisations should lead the development of social compacts which enhance accountability of services to clients. However, this assumes a top down specification of what a compact is, and does not allow for communities to lead in the development of an appropriate accountability mechanism. The RMCH team have been working to identify ways of engaging with civil society to strengthen bottom up engagement to enhance accountability.
At the time of the review, a meeting was being organised between RMCH and NDOH to discuss a ‘Framework for Demand and Accountability Activities – prepared by SDDirect (October 2012), this sets out a detailed, evidence based framework for engagement and will be designed to form a solid foundation for the demand and accountability activities.

Recommendations:
- The project should develop models for scaling up evidence based demand and accountability approaches that can be adapted by the department of health and used by districts to improve demand and accountability for RMCH services – it is agreed, as proposed by the NDOH, that these be piloted in 3 districts at different levels of service delivery, while other demand and accountability activities are implemented in the rest of the priority districts
- The Project should work with NDoH to develop a Demand and Accountability Strategy for Reproductive, Maternal and Child health services, which will include a communication strategy and support campaigns (such as contraceptive choice campaigns) to increase awareness of national priorities.
- The project should develop tools to support PHC teams to engage with communities and civil society.

Output 4: New knowledge to remove barriers to uptake and access of RMCH services
Two indicators were identified in the original logframe. The first of these was to establish RMCH baselines – and to have conducted these in the 15 districts by the end of the first phase and in 25 by the end of the second phase, this work is underway, as planned. The second indicator to establish an operational research programme has been removed at the suggestion of the steering committee, the focus will be on establishing robust project monitoring.
An external evaluation of the programme was envisaged under this output, however, it has been decided to allocate the budget for this to an external mid-term evaluation of the national Maternal, neonatal and child and Women’s Health Strategy (2012-2016), co-funded with other partners, ensuring that the RMCH component is evaluated as part of this wider evaluation. This approach makes good sense, as it will allow a clearer idea of the contribution of the RMCH to the national effort to be assessed. However the TOR for this have not yet been developed to review.

Overall Conclusions and Recommendations

The project is performing well, with the RMCH having achieved the majority of the milestones expected for the inception phase and ESMOE having achieved its milestones for the end of the first year of funding.

Finalisation of the logframe is needed by the end of October 2012, with a view to it being signed off with NDOH by December 2012, project implementers think this can be achieved.

The expansion of the project coverage from the initial 15 districts, selected on the basis of their maternal and neonatal mortality rates, to 25 districts, alongside national efforts to expand ESMOE and DCSTs nationally, mean that there is a risk that the equity objective of the project may be undermined.

The expansion of districts will have cost implications, and DFID has already indicated that it cannot increase its funding. The project will need to identify the funding gap that results from taking on 10 extra districts and present these to NDOH for consideration.

Project success depends on the project addressing the inequalities which lead to the target districts current poor maternal and neonatal health outcomes. If resources are spread thinly, by trying to achieve national coverage too quickly, this will undermine the equity focus. This risk needs to be managed. Dialogue in the RMCH Steering Committee needs to regularly emphasis the equity focus of the project and to ensure that resources remain focused on the project objectives.

There are large potential synergies between RMCH and ESMOE, which are not yet being fully captured or exploited by the project. Establishment of a technical working group between the two projects will be mutually beneficial, ensuring ESMOE results inform RMCH and RMCH outputs reinforce and champion ESMOE roll out. RMCH should have representation on ESMOE board.

There are a number of indicators in the proposed RMCH logframe which are not completely within the projects control. For example, DCST training will be supported by the project, but the formation of teams at District level will depend upon recruitment and posting, which is outside the projects control. However, it remains important that the functionality of DCSTs is an indicator or success, rather than just the training of individuals, since it is the teams that will deliver the impact. RMCH should report both numbers trained and also record team functionality. If, in spite of training individuals for DCSTs, functional teams are not deployed in the priority districts, then the project should raise this as a concern and this should prompt a dialogue between the project, DFID and NDOH.

There are some areas of policy where greater clarity on objectives is needed at the national level, as well as through the project. For example, there are a number of functions for school health (screening, health education, school nurse service) for which outcome indicators are not defined. It is not clear how the success of the school health programme will be measured in terms of outcomes and impact. Current indicators which focus on numbers of visits, focus on activity. The project should work closely with NDOH to better define indicators for measuring the impact of school health.