Department for International Development

Nigeria

Costed extension of the DFID Support to National Malaria Programme (SUNMAP)

Business Case

        May 2013

Contents	Page number
Intervention Summary	4-5
Strategic Case	6-17
Need and context for DFID intervention	7-16
Impact and Outcome that we expect to achieve	16-17
Appraisal Case	18-46
What are the feasible options that address the need set out in the Strategic case?	18-27
Theory of change and evidence base / Impact on local capacity / Impact on climate change and the environment / Impact on social development / Impact on conflict and fragility	28-32 / 32-37 / 37-39 / 39-41 / 41
What are the costs and benefits of each feasible option?	41-43
What measures can be used to assess Value for Money for the intervention?	43-46
Summary Value for Money Statement for the preferred option	46
Commercial Case – Direct Procurement	47-51
Clearly state the procurement/commercial requirements for intervention	47
How do we expect the market place will respond to this opportunity? / How does the intervention design use competition to drive commercial advantage for DFID? / What are the key underlying cost drivers? How is value added and how will we measure and improve this?	47 / 48 / 48-50
How will the contract be structured and contract & supplier performance be managed through the life of the intervention?	50-51
Financial Case	51-56
Who are the recipients of all proposed payments? / What are the costs to be incurred directly by DFID?	51 / 52
Is the required funding available?	52
What is the profile of estimated costs?	52-54
What is the assessment of financial risk and fraud? / How will expenditure be monitored, reported, and accounted for?	54-56 / 56
Management Case	57-61
What are the Management Arrangements for implementing the intervention?	57
What are the risks and how will these be managed?	57-60
What conditions apply?	60
How will progress and results be monitored, measured and evaluated? / References	60-61 / 61-63
Annex / SUNMAP Logframe

Glossary

ACT	Artemisinin-based Combination Therapy
APR	Annual Programme Review
CM	Case Management
DALY	Disability Adjusted Life Year
DFID	Department for International Development
DFID-N	Department for International Development - Nigeria
FMoH	Federal Ministry of Health
GBP	Great British Pound
GFATM	Global Fund to Fight AIDS, Tuberculosis and Malaria
HPI	Health Partners International
IEC	Information, Education and Communication
IPT	Intermittent Preventive Treatment
IRS	Indoor Residual Spraying
ITN	Insecticide Treated Net
LLIN	Long Lasting Insecticidal Net
M4P	Making markets work for the Poor
M&E	Monitoring & Evaluation
MDG	Millennium Development Goals
MoH	Ministry of Health
NMCP	National Malaria Control Programme
OPR	Output to Purpose Review
PATHS 2	Partnership for Transforming Health Systems – Phase 2
RDT	Rapid Diagnostic Test
SMoH	State Ministry of Health
SMCP	State Malaria Control Programme
SP	Sulphadoxine pyrimethamine
SPARC	State Partnerships for Accountability, Responsiveness and Capability
SuNMaP	Support to National Malaria Programme
USD	United States Dollar
VfM	Value for Money

Intervention Summary
Title: Support to National Malaria Programme

What support will the UK provide?
The UK will provide the sum of £39 million for a costed extension to the DFID Support to National Malaria Programme (SUNMAP), which will increase the programme funding from £50 million to £89 million, and extend the programme by an additional two years from 2008 – 2013 to 2008 – 2015. The SUNMAP programme was originally approved by Ministers in 2008. Additional funding for the extension period will consist of: / £18 million to support the management, coordination and delivery of malaria control services in 10 Nigerian States with a population of 60 million. / £21 million for the procurement of additional commodities for malaria control.

Why is UK support required?
What need are we trying to address? / Nigeria has 25% of the world’s disease burden for malaria. 97% of Nigeria’s 170 million population are at risk from malaria, with an estimated 50% of the adult population suffering from at least one case of the disease a year.[1] Malaria cases account for 60% of outpatient visits and 30% of hospitalisations, and kill an estimated 300,000 children every year. Malaria is a major cause of ill health, mortality and poverty in Nigeria. / Effective tools are now available to fight malaria, and are being aggressively scaled up in Nigeria. Coverage of key malaria control interventions have increased dramatically in recent years, leading to the saving of an estimated 136,000 lives of children under five between 2009 and 2010. Many more lives could be saved and illness prevented if the current level of progress is maintained and increased. Currently available funding for malaria control will not be sufficient to meet Nigeria’s malaria control needs and additional financing will be required. / What will we do to tackle this problem? / The UK Government has committed to help halve malaria deaths in at least ten of the worst affected countries by 2015. Though it is unlikely Nigeria will meet this target due to insufficient resources, DFID Nigeria’s operational plan 2011 to 2015 targets a scale up delivery of malaria interventions in Nigeria, including a “we will” target to distribute 10 million long lasting insecticide treated nets to Nigerian families by 2015. To achieve this DFID Nigeria frontloaded the existing DFID funded Support to National Malaria Programme (SUNMAP), expanding its scope of operation from 6 to 10 States and covering more malaria intervention areas. However the existing SUNMAP programme will be insufficient to meet DFID’s OP targets (for instance it will distribute just 5.5m LLINs out of the 10m OP target) and will end in August 2013. In order to meet DFID’s OP and malaria control commitments for the period 2013 - 2015, DFID will provide the sum of £39 million for a costed extension to the SUNMAP project, which will increase the programme funding from £50 million to £89 million, and extend the programme by an additional two years from 2008 – 2013 to 2008 – 2015. The additional funding is divided into two components: / A technical cooperation component which will: / Improve the management, coordination and delivery of malaria control activities in Nigeria. / Improve the availability of insecticide treated nets, rapid diagnostic testing and effective malaria treatment in 10 Nigerian States. / Improve the ability of health workers in 10 Nigerian States to prevent, diagnose and treat malaria. / Expand the delivery of malaria control interventions through the private sector. / Increase demand and appropriate usage of malaria control commodities by the public. / Conduct relevant research to inform malaria control policy and strategy in Nigeria and beyond. / This component will be funded through an £18 million extension of the existing contract of Malaria Consortium, the current service provider for the project. / A procurement component which will meet additional commodity requirements for the scale up in the 10 States during the extension period. This will be used to procure the following commodities: / 4.6 million long lasting insecticide treated nets. / 3.3 million doses of artemisinin combination therapy, the recommended treatment for malaria. / 4 million rapid diagnostic tests kits for malaria. / These commodities, which will cost £21 million, will be procured through DFID Nigeria’s existing procurement core country agreement with Crown Agents.
[1] Federal Ministry of Health. National Malaria Control Program Strategic Plan 2009 – 2013. Abuja: Federal Ministry of Health; 2009.

What are the expected results?
This intervention will contribute to sustained reductions in death and illness due to malaria in Nigeria, particularly in the ten States supported by the programme. The programme outcome is “Delivery of Nigeria’s malaria control effort strengthened in up to ten supported States”. / With additional funding and a 2 year extension SUNMAP will achieve the following additional outputs: / Output 1: National, State and LGA capacity for policy development, planning and coordination are improved. / Output 2: All agencies’ support for the malaria sub-sector at federal, state and local levels are effectively harmonised. / Output 3: Population coverage of effective measures for the prevention of malaria is increased. / Output 4: Access of the population to effective treatment of malaria is improved. / Output 5: Community awareness and demand for effective malaria treatment and prevention are improved. / Output 6: Operational research into key areas of prevention and treatment provides the basis for more effective strategies. / Programme results will be monitored by the DFID programme team against the programme logframe. SUNMAP’s performance will also be assessed by internal monitoring of the programme; by independent monitoring through annual and mid-term reviews; and by an independent end-of-programme review. / The SUNMAP costed extension will accelerate the delivery of highly cost-effective malaria control through a tested and successful existing programme which has consistently been assessed as delivering value for money. The cost effectiveness of the interventions to be delivered in the SUNMAP extension are well established. Excluding non-quantifiable and non-health impacts, the SUNMAP extension will improve the overall cost effectiveness of the SUNMAP programme from $52 per DALY over five years to $30 per DALY over seven years.

Business Case

Strategic Case

A. Context and need for a DFID intervention / The Health context / Nigeria has poor health indicators including: higher than Sub-Saharan average rates of under-five mortality, the highest number of maternal deaths in Sub-Saharan Africa / Nigeria, Sub Saharan Africa’s second largest economy, has a population of more than 158 million, large reserves of oil and gas resources and a growing economy. Despite this progress, average life expectancy at birth is 44 years[2] and more than 100 million people live on less than £1 per day[3]. / Most health indicators remain below national and internationally recognised standards. The under 5 mortality rate is 157 per 1000 live births and maternal mortality ratio in Nigeria is 545 per 100,000 live births. Thirty three thousand women (10% of the world’s total) die of childbirth related causes and the country has one of the world’s highest rates of all-cause mortality for children under five: approximately one in six children (or one million children every year) die before their fifth birthday in Nigeria. / Malaria is a major cause of ill health, mortality and poverty in Nigeria / Nigeria has 25% of the world’s disease burden for malaria. 97% of Nigeria’s 160 million population are at risk from malaria, with an estimated 50% of the adult population suffering from at least one case of the disease a year.[4] Malarial cases account for 60% of outpatient visits and 30% of hospitalisations, and kill an estimated 300,000 children every year.[5] / In 2008, malaria was considered responsible for 11% of Nigeria’s maternal mortality, 25% of infant mortality and 30% of under-five mortality[6] / Malaria ill health is estimated to slow economic growth by 1.3% (PPP $4.4 billion lost in Nigeria) each year[7]. Indirect costs may be much higher.[8] / Climatic factors and a weak health system account for the high burden of malaria in Nigeria / Situated between 4˚ and 13˚ Northern Latitude Nigeria has a suitable climate for malaria transmission throughout the country. 97% of the population live in areas of malaria transmission and are therefore at high risk of infection. The only exception is the area south of Jos in Plateau State where some mountain peaks reach 1600 meters and the altitude of settlements lies between 1200 and 1400 meters. This area can be considered of relatively low malaria risk. / Figure 1 / The duration of the transmission season decreases from South to North (Figure 1) from perennial in most of the South to only 3 months or less in the border region with Chad. / Figure 2: / The health system in Nigeria is still suffering from the decline in performance that occurred during the 1990s, and which has left infrastructure dilapidated, staff morale low and confidence in public provision amongst the population seriously lacking. The situation is compounded by the persistence of vertical programmes, the absence of appropriate skilled health workers, particularly at the community-level and in rural areas, poor inter-sectoral collaboration, weak managerial capacity and a poor health information system. Furthermore, the commodity procurement, storage and distribution systems are uncoordinated and thus hinder health care provision.[9] Low funding is a big problem that has contributed to the state of the public healthcare system and which hinders its improvement. Just 5% of government spending is directed to health and government spending on public health interventions is inadequate. / .According to the 2008 Nigeria Demographic and Health survey, only 10% of married women used any modern method of family planning[10], 58% of pregnant women received antenatal care from a skilled provider, and 39% of deliveries were assisted by a skilled provider. Access to basic child health services is similarly poor. Only 20% of children 6 – 11 months old received antibiotics for acute respiratory infection, and 6% of children with fever received recommended treatment for malaria[11]. / but effective tools are now available to combat malaria / A number of interventions are now available to limit the spread of malaria and reduce the human impact of the disease. There is strong evidence that preventive measures such as insecticide treated nets (ITNs) and indoor residual spraying (IRS) with insecticides are highly effective in preventing malaria in settings similar to Nigeria. ITNs, and the newer version, LLINs, are the most prominent malaria preventive measure for large-scale deployment in endemic areas; the evidence for their efficacy is strong. A systematic review of 22 randomised controlled trials (13 in SSA, five in Latin America, two in Thailand and one each in Pakistan and Iran) concluded that the use of ITNs reduced under-five mortality in malaria-endemic areas in sub-Saharan Africa by about a fifth and halved clinical episodes of uncomplicated malaria in areas of stable malaria transmission in Africa[12]. There is also evidence that IRS is effective in reducing the incidence of malaria, particularly in areas with unstable transmission. / Similarly, improvements in diagnosis of malaria using rapid diagnostic tests (RDTs) and highly effective drug treatment (known as artemisinin combination therapy – ACT) are also available to reduce illness and death due to malaria. However, in many low income settings such as Nigeria, several barriers continue to limit the effective coverage and usage of these interventions by the public – such as inadequate funding to purchase malaria control commodities, ineffective systems to deliver them to the people who need them, and improper use due to widespread ignorance. / …and Nigeria is aggressively scaling them up / In 2008, Nigeria launched a new Strategic Plan for Malaria Control (2009 – 2013)[13], which called for an unprecedented scale up in coverage of malaria interventions to combat malaria. This plan attracted a range of new partners and growing resources. Between 2004 and 2010, nearly US$600 million in external funding was allocated to scale up the country’s malaria control programme. Between 2008 and 2010, at least $80 million of Nigerian Federal Government resources was also spent on malaria control[14] / Figure 3 / The amount of external funding reached a peak of US$ 325 million in 2009 (this included massive procurement of LLINS that were distributed over the following two years). Still, this represented roughly US$ 2 per person at risk for malaria when current estimates show that 2 to 2.5 times this amount is needed to tackle the disease[15]. / …with some success / This funding made possible a massive scale up in interventions to prevent and treat malaria across the country, including a plan to distribute 2 insecticide treated bednets to each of the country’s 32 million households. Between 2007 and 2010, the Nigerian Government and partners procured and distributed more than 50 million ITNs and large numbers of other commodities to millions of households[16]. / Figure 4 / This scale-up has, in turn, led to large increases in the coverage and use of key malaria control interventions across the country. By 2010, Nigerian States which had benefitted from the 2 nets per household universal net campaign (at that time this was 18 States, but has since increased to 30 States) had shown remarkably higher coverage of key malaria control interventions. For instance, States which had received this support showed an increase in the proportion of households owning at least one LLIN from 8% in 2008 to more than 70% in 2010. During the same period, ITN usage in the same States increased from 6% to 50%. States which had not yet received this support showed much more modest coverage[17],[18] / Figure 5 / Nationally, the proportion of children under five using nets increased five-fold from 6% in 2008 to 29% in 2010 (this is expected to be much higher now given the increase in the number of States where universal campaigns have taken place since 2010). / Figure 6: National trends in net use among children under age 5[19] / The 2010 Malaria Indicator Survey showed much more modest increases in the proportion of children under five with fever who received effective malaria treatment (ACTs). 6% received an ACT in 2010, compared with 2% in 2008 – reflecting the relative emphasis placed by the national programme on scale up of preventive measures in the first two years of the plan. However, the DFID backed Affordable Medicines Facility for malaria (AMFm) has been launched since then, and has already led to marked improvements in the availability and affordability of ACTs in Nigeria – since the launch, retail prices for ACTs have reduced by 80%, and usage has dramatically increased.[20] This should contribute to an expected increase in the proportion of children who receive recommended malaria treatment from 2% in 2008 to 60% by 2015. / These sharp increases in coverage are likely to have led to reductions in disease burden for malaria and lives saved, but it is considered too early to detect comprehensive evidence of impact. The national prevalence of malaria parasites in the blood of children under five was still high in 2010: 42% as measured by using microscopy (MIS 2010)[21]. However, a DFID funded malaria monitoring site in Kano State showed a substantial drop in malaria prevalence among children under five from 29- 43% in June 2009 to 14-17% in June 2010. / According to estimates using the Lives Saved Tool (LiST model), the lives of 166,000 children under-five have been saved by malaria control interventions in Nigeria since 2001. Approximately 136,000 (or 82%) of the lives saved occurred in 2009 and 2010 alone. The current LiST model does not account for the lives saved through early diagnosis and effective treatment or for the indirect effects of malaria on child mortality. It is therefore reasonable to assume that the actual number of lives saved by all malaria control interventions is much higher.[22] / Figure 7 / It is estimated that the malaria-related mortality rate in children under five for 2010 is 15% lower than it would have been, had the Government of Nigeria not expanded malaria control intervention coverage[23]. / Why should DFID intervene? / A lot has been achieved in Nigeria, but much more could be accomplished / Modelling using the Lives Saved Tool (LiST) has already demonstrated the considerable impact likely to have been generated from scale up of malaria interventions in Nigeria to current levels. However, projections using the tool have also shown that impact could actually be doubled by scaling up malaria interventions beyond their current coverage rates over the next few years. / Figure 8[24] / Key strategies identified by Nigeria’s National Malaria Control Programme to expand coverage and further reduce malaria related morbidity and mortality over the next few years include: / Expansion of mass LLIN campaigns to all States. / Routine LLIN distribution through child welfare and antenatal clinics. / Improvement of malaria diagnosis and expansion of rapid diagnostic testing to all public health facilities. / Expansion of indoor residual spraying. / Extension of behaviour change and communication activities / Improving monitoring and evaluation, including monitoring of drug resistance and strengthening routine surveillance. / Expanding sustainable access to effective malaria interventions through the private sector. / It is likely that the level of funding required for maintaining and scaling up coverage of malaria interventions in Nigeria is likely to outstrip available Government resources, at least over the medium term. External funding for malaria control will therefore be required for the foreseeable future; at least until the disease burden is reduced to a more manageable level. Besides DFID, the main external funding partners for malaria in Nigeria are The Global Fund, the World Bank, and the USAID – President’s Malaria Initiative. However, currently committed funding from these partners will not be sufficient to meet Nigeria’s external financial requirements for malaria control. / The UK is committed to combating malaria, particularly in the worst hit countries / Addressing malaria is one of the main priorities of the UK government. In “Breaking the Cycle: Saving Lives and Protecting the Future: The UK’s Framework for Results for malaria in the developing world” DFID sets out the UK’s commitment to helping halve malaria deaths in at least ten of the worst affected countries by 2015. This commitment will contribute directly to reaching international targets set out in the Roll Back Malaria Partnership’s 2008 Global Malaria Action Plan and the Millennium Development Goals. / With a focus on the poor and vulnerable populations in high-burden countries in Africa and Asia, the framework prioritizes the following pillars of action: / Improve the quality of services / Support the implementation of evidence based and context appropriate mixes of cost effective malaria prevention and treatment interventions that are part of broader programmes. Ensure that they deliver maximum health benefits and value for money. / Expand access and increase demand / Support approaches to ensure all men, women and children are able to access responsive malaria and related health services irrespective of where they live or their ability to pay. / Support innovation and global public goods / Support strong global technical leadership and effective international organisations that support countries to achieve malaria and broader health goals / Support coordinated action to address important global needs including tackling resistance, building and sharing evidence and supporting market efficiencies / Support the development of new prevention, diagnosis and treatment tools and delivery approaches. / Focus on impact and results / Improve the quality and availability of data on malaria so that results are measurable, transparent and strengthen accountability to communities and the UK public. / Improve the effectiveness and efficiency of the global response through international institutions, partnerships and global civil society. / To help meet these commitments, DFID Nigeria’s 2011 – 2015 operational plan and results framework sets out an ambitious scale up of malaria results over the period, including the delivery of an additional 8 million insecticide treated nets to households, contributing to 9 million children under five sleeping under nets, and scaling up access to malaria diagnosis and effective treatment for millions of people who are ill. However, the resources required to achieve the target of halving malaria deaths in Nigeria far exceed that currently available through DFID and other donors, so it is unlikely that Nigeria will meet the target during this period. The National Malaria Control Programme currently estimates a funding gap of $1.7 billion for malaria control in Nigeria from 2013 to 2016. / Additional DFID assistance will build on a successful existing programme, and enable achievement of DFID’s operational plan targets. / In 2008, DFID Nigeria launched the £50m Support to National Malaria Programme (SuNMaP) to help support the delivery of Nigeria’s malaria programme. Repeated annual reviews of this programme have affirmed its excellent contribution to Nigeria’s malaria response, and the progress that has been made so far.[25] Important achievements of this programme since its start include: / Establishing a harmonisation mechanism whereby ministry, institutions, organisations, partners and people develop a common approach to strategic areas. / Capacity building resulting in the development of effective national and state malaria control plans. / Development of management, planning and malaria case management training modules that have shown impact (and that have been used across the health sector). / A key role in orchestrating and coordinating the successful nationwide distribution of insecticide treated nets to every household. / Developed and implemented the first large scale routine distributions of insecticide treated nets through ante-natal clinics. / Distribution of 5 million insecticide treated nets to Nigerian households, 50% of operational plan targets. / Good operational research that is helping to inform national policy. / Following the programme’s mid-term review in 2011, DFID agreed the following adjustments to the programme – to enable the achievement of DFID’s operational plan commitments for malaria: / Expansion of the programme operations from the existing 6 States to an additional 4 States – totalling 10 States with a total population of more than 60 million people. / The expansion of more malaria control interventions (besides prevention using bednets and IPTp), such as diagnosis using rapid diagnostic tests (RDTs), and treatment using artemisinin combination therapy (ACTs). / Changes in the programme approach to working with the private sector – using the Making Markets Work for the Poor (M4P) approach. / The SUNMAP programme works closely with DFID Nigeria’s 2 health systems programmes – the Partnership for Transforming Health Systems phase 2 (PATHS2) and the Partnership for Reviving Routine Immunization in Northern Nigeria – Maternal, Neonatal and Child Health (PRRINN-MNCH), which work in a total of eight Nigerian states to improve the coverage and delivery of basic lifesaving health services, as well as health sector governance. SUNMAP engagement with these programmes is targeted at integrating malaria control more closely within the health care delivery systems, to improve the efficiency and sustainability of malaria interventions. / The existing SUNMAP programme will end in August 2013. Two options were considered to help ensure the achievement of DFID Nigeria’s operational plan malaria commitments to 2015: / Design and develop a new malaria programme which will take over the implementation of DFID’s malaria interventions from August 2013. This option has the advantage of enabling the development of a longer term programme of support beyond the operational plan period – possibly to 2018 or 2019. However, this option would also mean the current programme would have to be wound down rather than expanded as is currently the case. There is also a serious risk of a disruption to existing project engagement with partners, loss of continuity of project interventions, and loss of experienced personnel during the transition between both projects. These would effectively render the achievement of DFID Nigeria’s operational plan 2015 targets impracticable and unlikely. In addition, the timeframe for the new programme would be poorly aligned to DFID’s existing malaria framework, as well as international and national MDG milestones for 2015, and would mean further adjustments might be required to align the programme with the emerging post 2015 agenda. / This option is considered not suited to the objective of achieving DFID Nigeria’s operational plan commitments. / Extend the successful SUNMAP project for an additional two years to 2015, and secure funding for procurement of additional quantities of malaria commodities during the period. This option has the advantage of supporting the on-going expansion of the existing programme which is required if operational plan targets are to be achieved. The existing programme has a strong track record of delivery, scoring a “2” (all reviews before 2012 using the old scoring system) or an “A” (latest review 2012) at independent reviews. In addition, this would bring the programme timelines into closer alignment with DFID’s malaria framework and allow the later development of a new programme better aligned to the post 2015 agenda. / Given this option will not require a new procurement process, more evidence would be required that it secures value for money for DFID. This will be developed further in other sections of the business case. / This option is considered better suited to the objective of achieving DFID Nigeria’s operational plan targets, and will be developed further. / Consequences of not intervening / If DFID does not intervene, it is unlikely that the Nigerian Government and other donors supporting malaria control in Nigeria will be able to cover the shortfall in support. The outlook for improving malaria control in the worst affected country in the world will worsen. The UK’s commitment to “helping halve malaria deaths in at least ten of the worst affected countries by 2015” will not be met. Coverage rates for malaria interventions in the ten Nigerian States to be supported by DFID, are likely to reduce over time, and the number of lives saved by these interventions are likely to shrink.
B. Impact and Outcome that we expect to achieve / This intervention will contribute to sustained reductions in death and illness due to malaria in Nigeria, particularly in the ten States supported by the programme, measured by / Impact: / Reduction in all cause under-five mortality rate (the number of children who die by the age of five, per thousand live births) from 157 in 2008 to 100 by 2015. / Reduction in Malaria-specific deaths in 10 supported States. Using the Lives Saved Tool[26], we estimate that the lives of 95,000 (16,000 attributable to DFID) children under five were saved from malaria deaths in the 10 States between 2008 and 2013. The SUNMAP extension will contribute to the saving of a total of 168,000 (60,000 attributable to DFID) lives of children in the 10 States between 2008 and 2015 / Outcome: To strengthen delivery of Nigeria’s malaria control effort in up to ten supported States. / Between 2008 and 2010, the proportion of children under five sleeping under insecticide treated nets in SUNMAP supported States increased from 3% to 49%. The extension will enable a further increase to 65% (9 million children sleeping under nets – leading to a total of 121,000 lives saved) by 2015. / Between 2008 and 2010, the proportion of pregnant women in SUNMAP supported States who used intermittent preventive treatment increased from 2% to 16%. The extension will enable a further increase to 35% by 2015. / Between 2008 and 2010, the proportion of children under five with a fever who received treatment with recommended malaria treatment increased from 3% to 6.5%. The extension will enable a further increase to 25% (leading to a total of 47,000 lives saved) by 2015.
[2] UNICEF: State of the World’s Children
[3] TP Ogun, Infrastructure and Poverty Reduction: implications for Urban Development in Nigeria. UNU, May
[4] Federal Ministry of Health. National Malaria Control Program Strategic Plan 2009 – 2013. Abuja: Federal Ministry of Health; 2009.
[5] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[6] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[7] Gallup JL and Sachs J. The economic burden of malaria. American Journal of Tropical Medicine and Hygiene, 2001, 64:85-96.
[8] Jimoh et al 2007. Quantifying the economic burden of malaria in Nigeria using the willingness to pay approach. Cost Effectiveness and Resource Allocation 2007, 5:6doi:10.1186/1478-7547-5-6
[9] The Global Fund. Round 8 Funding Application: Nigeria; 2008. Available at: http://portfolio.theglobalfund.org/Country/Index/NGA?lang=en#.
[10] Nigeria Demographic and Health Survey, 2008
[11] Nigeria Malaria Indicator Survey 2010
[12] UK Department for International Development, 2010. Malaria Framework for Results. Breaking the Cycle. Evidence Paper
[13] Federal Ministry of Health. National Malaria Control Program Strategic Plan 2009 – 2013. Abuja: Federal Ministry of Health; 2009
[14] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[15] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[16] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[17] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[18] National Population Commission (NPC) [Nigeria], National Malaria Control Programme (NMCP) [Nigeria], and ICF International. 2012. Nigeria Malaria Indicator Survey 2010. Abuja, Nigeria: NPC, NMCP, and ICF International.
[19] National Population Commission (NPC) [Nigeria], National Malaria Control Programme (NMCP) [Nigeria], and ICF International. 2012. Nigeria Malaria Indicator Survey 2010. Abuja, Nigeria: NPC, NMCP, and ICF International.
[20] AMFm Country Updates Oct – Nov 2011. Global Fund.
[21] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[22] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[23] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[24] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[25] DFID. 2011. Mid Term Review of the Support to National Malaria Programme SUNMAP.
[26] http://www.jhsph.edu/departments/international-health/centers-and-institutes/institute-for-international-programs/list/index.html

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / As previously mentioned in the strategic case, DFID Nigeria’s 2011 - 2015 operational plan set out an ambitious scale up of malaria results in Nigeria in order to help meet DFID’s global malaria commitments. At the time the DFID SUNMAP programme had been active for three years, and was making significant contributions to malaria control in Nigeria. Prominent achievements included improved National and State malaria planning, harmonisation and management; as well as orchestrating a massive scale up in malaria prevention interventions (bednets) nationwide. In selecting a viable means of delivering DFID Nigeria’s operational plan commitments, the following options were considered at the time (2010): / Continue the SUNMAP programme as planned (business as usual): This option would involve no changes to DFID malaria programming. / Merits: No additional costs and time required. / Demerits: Existing malaria programming would be insufficient to meet DFID’s malaria commitments. / Deepen the work of SUNMAP in its existing 6 States: This option would involve increasing the level of coverage of SUNMAP work in its existing States, and scaling up additional interventions such as malaria case management using Rapid Diagnostic Tests (RDTs) and Artemisinin Combination Therapy (ACTs). / Merits: This option could be rolled out relatively rapidly, with minimal additional transaction and setup costs. It would help address malaria control more comprehensively than the existing programme. / Demerits: Though this option could contribute towards meeting DFID’s malaria commitments, it would be insufficient to meet the targets that had been set. In addition, some of the work on new interventions was likely to be at an early stage by SUNMAP’s close in March 2013. Significant momentum could be could be lost if these interventions were stopped or handed over to a new programme at that stage. / Expand SUNMAP to 4 additional States: This would involve expanding the programme to 4 DFID focus States – Jigawa, Kaduna, Enugu and Yobe. Each of these States had longstanding DFID health systems and governance programmes, as well as high level engagement with DFID. / Merits: This option could be rolled out rapidly, would complement the existing DFID investments in those States, and would enable stronger DFID – State engagement given the high level political interest in malaria control. / Demerits: This option would incur some setup costs (for programme engagement in the new States), though this would be expected to be limited given the existing DFID engagement with the States, and the potential to share resources with other DFID programmes in those States. In addition, there would be insufficient time for the programme to consolidate its work and demonstrate results in the new States by its expected close in March 2013. Significant momentum could be could be lost if this work were stopped or handed over to a new programme at that stage. / Start a separate malaria programme to cover the 4 additional States: This would involve the design of a new programme to implement malaria interventions in the additional States for at least the duration of the operational plan period. It is likely that the management of this programme would be contracted to a suitable service provider. / Merits: This option would have the advantage of ensuring that the work in the additional States could be continued uninterrupted for a period sufficient to demonstrate results. / Demerits: This option could not be rapidly rolled out, requiring considerable time for design, setup and engagement of the new programme in the new States. There would also be significant additional transactional, management and setup costs. This option would also mean there would be two separate DFID malaria programmes running at the same time, which could to lead to some confusion and incoherence between the two programmes and with other partners. In addition, some of the work on new interventions in the 6 existing States is likely to be incomplete by SUNMAP’s close in March 2013. Significant momentum could be could be lost if these interventions were stopped or transitioned to a new programme at that stage. / Channel additional DFID resources for malaria through a partner organization: This would involve the transfer of DFID resources to help expand existing malaria work being conducted in Nigeria by a partner organization. The partners that were considered included the World Bank, which has a $280m Malaria Booster Project active in several Nigerian States; the Global Fund, which has existing malaria grants in Nigeria totalling up to $600m; UNICEF, which has supported bednet distributions in several States; and the Nigerian National Malaria Control Programme (NMCP), which implements the Nigerian Government’s malaria control programme. / Merits: This option could be quickly rolled out, and would require limited additional transaction and setup costs. / Demerits: None of the potential partners for this option were in a position to benefit from this opportunity. The World Bank malaria booster programme was already experiencing significant difficulties, and did not have the spare management capacity to handle the extra responsibilities (indeed the World Bank had requested DFID help in managing its existing malaria programme). The Global Fund mechanisms were unable to earmark any additional donor funds to a specific country, and their Nigeria malaria grants were facing serious difficulties occasioned by an audit. The existing UNICEF malaria work did not have the capacity to deliver the comprehensive range of interventions required by DFID. Channelling DFID funds to the NMCP would require their entry into Nigerian Government financial systems. This is currently not possible because these systems do not meet DFID fiduciary standards. In addition, this option was unlikely to maximise coherence with other DFID programmes or contribute significantly to DFID engagement with the States. / The options were assessed according to the following criteria (1 – low score; 5 – high score) / Criteria Option 1 Option 2 Option 3 Option 4 Option 5 / Can be rolled out quickly enough to meet DFID operational plan targets 5 5 5 2 5 / Can be implemented at sufficient scale to meet DFID operational plan targets 1 3 5 4 5 / Interventions can be scaled up throughout the operational plan period without interruptions 3 3 3 3 3 / Addresses a comprehensive range of malaria interventions 2 5 3 3 4 / Minimises transaction, setup and engagement costs 5 5 5 2 4 / Delivery partner capable of implementing programme 5 5 5 4 1 / Coherent with other DFID programming 5 5 5 3 2 / Contributes to improved DFID engagement with new partner States 1 1 5 4 2 / Total score 27 32 36 25 26 / The combination of options 2 and 3 were selected as the most likely to meet DFID’s requirements. On this basis DFID Nigeria’s operational plan proposed a deepening of the SUNMAP programme in existing States, as well as an expansion of the programme to four additional States. Either an extension or a new programme would be required to cover commitments after the end of the programme in 2013. The operational plan was approved by Ministers in early 2011. / The SUNMAP programme has now established operations to three of the four additional States (expansion to the fourth State, Yobe, was slowed down due to deteriorating security conditions). Programme interventions are now being implemented in all 9 States, and additional interventions such as malaria rapid diagnostic tests and antimalarial treatment are being delivered. Its 2012 annual review concluded: “Overall the review found that SuNMaP is making good progress in achieving the purpose and outputs of the programme. It is highly regarded among stakeholders as a key leading partner in malaria control in Nigeria whose contributions are greatly valued”. / The SUNMAP programme will now end in August 2013. The following options were considered to continue to meet DFID’s malaria commitments after the end of the programme: / Develop a new malaria programme which will implement DFID’s malaria work from 2013. / Merits: This option will enable the development of a longer programme of support, possibly up to 2018 or 2019. This would have the advantage of securing greater predictability of DFID support beyond 2015, which would be useful to Nigerian Government and other partners. The new programme would also have more scope to make significant changes in design based on learning from the current programme. In addition, this option could, in theory, offer the possibility to generate value for money through a competitive tender for the new programme / Demerits: A significant part of the work of the existing SUNMAP programme, particularly its new interventions and activities in the new States, is currently at an early, scale up stage. It is unlikely that this work could be transitioned to a new programme without a substantial loss of momentum, There is also a serious risk of a disruption to existing project engagement with partners and loss of experienced personnel during the transition between both projects. These would effectively render the achievement of DFID Nigeria’s operational plan 2015 targets unlikely. / In addition, Nigeria’s malaria control strategy is currently in transition from its current phase, characterized by massive investment in one-off prevention interventions such as bednet distribution campaigns, to a new, more difficult phase involving recurrent investment in interventions (such as nets, rapid diagnostic tests and malaria treatment) delivered routinely through the health system and private sector. SUNMAP is currently leading efforts to develop Nigeria’s new malaria strategy based on learning from the initial phase and changes in the malaria landscape. An interruption of the programme at this point is likely to significantly set back this effort. No other partner currently has the capacity to take this on, and a new DFID programme is likely, at this time, to lack the necessary experience and credibility. / Furthermore, the timing is not conducive to the design of a new, longer term malaria programme. Key information requirements for the design are currently unavailable, such as suitable baseline data (expected in 2014 from the DHS and MIS surveys); a new national malaria strategy covering the 2014 to 2019 period (expected in early 2014), clarity around the workings of major malaria funders such as the Global Fund and the Affordable Medicines Facility for Malaria after existing grants expire in 2014; and a DFID malaria strategy beyond 2015 linked to the post 2015 agenda. This would mean the design of any new programme would have to include substantial strategic risks, and is likely to need significant changes by 2015. This would be less than ideal. / Any theoretical opportunity to derive more value for money through a fresh competition at this stage could be outweighed by the costs of the escalating security risks of delivering a new programme in Northern Nigeria. In order to manage this risk, bidders would be likely to factor in significant risk premiums into their bids, which would increase costs to DFID. / Extend the SUNMAP programme to 2015 through a no cost extension. / Merits: This option would allow the interventions currently being scaled up under the SUNMAP programme to continue uninterrupted throughout the operational plan period. This would offer the best chance of meeting DFID’s operational plan targets. The programme could continue to support the national malaria partnership through the difficult transition between malaria control phases. This option would also allow the later design, if required, of a new, better informed DFID malaria programme for the post 2015 period. In addition, an existing programme is likely to be better able to manage, at lower cost, the recently increased security risks of working in Northern Nigeria. / Demerits: This option would have less scope to make substantial changes in the design of the malaria programme (in practice, such large changes would be unlikely – SUNMAP has often been described as a model malaria project[27], its design has received praise from such quarters as the National Audit Office, and appears to have even inspired the design of a USAID malaria programme). In addition this option would provide less predictability of DFID funding beyond 2015. / Close SUNMAP in 2013 as scheduled, and do not start a new programme (“Do Nothing” counterfactual) / Merits: No additional costs to DFID / Demerits: DFID’s malaria commitments could not possibly be met. A significant part of the work of the existing SUNMAP programme is at an early stage and would be lost if the programme were to close at this point. The transition to a new malaria strategy could be more difficult, and this could make it more challenging for Nigeria to secure additional malaria resources from large donors such as the Global Fund. / If DFID did not intervene, Nigeria would rely on three existing programmes – the GFATM, World Bank Booster Programme and MAPS, which is USAID funded and geographically specific. / The first two of these programmes are due to finish in 2013 and 2014 respectively, and it is likely there will be a considerable discontinuity of support to the malaria subsector in Nigeria by external partners. However in 2012 the Nigerian authorities, led by the Federal Ministry of Health, has announced a campaign to Save one Million Lives, through low cost health measures, aimed in particular at reducing the incidence of childhood diseases including malaria. / Whilst there are is increasing Government momentum, the loss of DFID’s support at this crucial stage would be a major setback to efforts to reduce morbidity and mortality levels from malaria in Nigeria. SUNMAP provides significant capacity building support that is highly valued, and its loss at this stage, before gains are consolidated, could undermine progress made to date. / Preferred option / Options 1 and 3 were rejected as being unlikely to deliver DFID’s operational plan commitments. Option 2 was selected as the preferred and only remaining feasible option. This option was put to our Director in the strategic case, and the decision was made to develop a business case for a two year extension of the SUNMAP project. / As previously mentioned, given this is a two year extension to a successful existing programme (which has already undergone changes as outlined above), option 2 has limited scope to make any further significant changes in design. For this reason, it will not be useful to attempt to generate further design or delivery choices to deliver this option. This option will therefore be appraised further. / Description of Option 2 / Option 2 is a £39 million costed extension of the SUNMAP programme from 1st September 2013 to 31st August 2015. The programme will consolidate the successes of the existing SUNMAP programme, and contribute to further reductions in illness and death due to malaria in Nigeria. / Outputs: / Capacity strengthening: National, State and LGA capacity for policy development, planning and coordination are improved / SUNMAP has made significant progress working at the national and State level to improve the ability for planning and managing malaria control activities. At National level, SUNMAP supported the development of the 2009 – 2013 malaria strategic plan which helped attract at least $900m of donor and government funding for malaria control. The programme also provided technical support enabling six States to develop and implement malaria annual operational plans, as well as implement a number of programme management frameworks (such as integrated supportive supervision and procurement and supply management). The extension will enable SUNMAP to support the development of the 2014 – 2019 National Strategic Plan for Malaria Control, which will form the basis for continued programming by donors and the Federal Government during the period. In addition, the extension will enable the programme consolidate its support to malaria annual operational planning and programme management in the four additional States. / Harmonisation: All agencies’ support for the malaria sub-sector at federal, state and local levels are effectively harmonised. / Stakeholders widely recognise and credit SuNMaP for playing a key role in the harmonisation of methodologies and tools for standardising the efforts of all malaria control partners in Nigeria. These tools are currently being used by major malaria control partners in Nigeria including the USAID funded MAPS project as well as the World Bank booster project. Methodologies and tools developed with other partners to-date are: / NMCP coordination framework: framework revision, endorsed by partners and supporting implementation / LLIN universal coverage distribution campaigns: resource mapping, national plan, implementation guidelines and tools, training materials, management structure / Advocacy, Communication and Social Mobilization (ACSM): national strategic framework, joint partners implementation plan, tool kit for adaptation at state level / National malaria Operational Research agenda setting: SuNMaP has provided technical and financial support to a NMCP led process of setting priorities and mapping of resources for OR in malaria (May 2010 and Feb 2012) / Malaria control capacity building package (Service delivery and Programme Management): training approach, training materials and training roll-out planning guide / tools (training planning guide to be finalised). The programme management aspects include Annual Operational Plan and Procurement and Supply Management. A total of 13 programme management and service delivery training modules developed, and endorsed by partners. The training modules are being used by other partners, including the World Bank. / Survey Methodology: SUNMAP developed methodology and tools for net retention and use surveys. These have now been adopted by other partners. / The extension will enable SUNMAP support the harmonisation of one additional and the revision of four existing strategic areas for malaria control. / Prevention: Population coverage of effective measures for the prevention of malaria is increased. / The two main interventions supported by SuNMaP for the prevention of malaria include the distribution of long lasting insecticidal nets (LLINs) and Sulphadoxine – Pyrimethamine (SP) for Intermittent Preventive Treatment (IPT) in pregnant women. The main element has been through SuNMaP support of the universal coverage campaign of over 60 million LLINs (SuNMaP provided commodities and supported the campaign directly in Kano, Anambra and Ondo states, and provided technical assistance in the form of State Support Teams (SSTs) for the rest of the country). SuNMaP played a critical role in the planning and design of the campaign as noted in Outputs 1 and 2. / Eight months after the campaign, SuNMaP undertook post-campaign net retention surveys in the six supported states. These surveys show a considerable increase in the number of households (HHs) with at least 1 ITN. / Figure 1: Households owning at least one ITN 8 months post campaign. Note: Sokoto is not a SUNMAP State, but was supported by the SUNMAP led State Support Team. / As the first States to be covered by the universal coverage campaign received LLINs in 2009 we know that those nets are coming to an end in their life span and are due to be replaced. As part of the strategy to keep up coverage, SuNMaP have been supporting the routine distribution of LLINs through Ante natal care (ANC) and immunisation clinics to target the most vulnerable groups; pregnant women and children under-5 years. This has been going to plan with the milestones for 2012 being achieved. By the current end of the project in August 2013, SUNMAP will have distributed a total of 5.5 million LLINS to Nigerian families. The extension will enable the distribution of an additional 5.2 million nets by 2015, which will exceed DFID’s OP target of 10 million nets distributed by 2015. / In recognition of the sustainability problems posed by the heavy dependence of malaria prevention on donor funded LLIN supplies, SUNMAP has also been working with the commercial sector to develop sustainable retail markets for LLINs. Using a facilitative “Making Markets work for the Poor (M4P)” approach, the project is helping address key constraints to the bednet retail market. Important interventions include improving access to finance for net distributors; improving branding, marketing and distribution of net products; interventions to improve the desirability of nets and generate demand, and supporting the development of new products which better meet the needs of the population. An important part of this work includes efforts to improve the targeting of free net distributions in order to create more space for the commercial sector. Initial successes include agreements by the national malaria partnership to target routine net distributions to vulnerable groups such as children and pregnant women, and to target universal net campaigns to areas where net coverage falls below certain thresholds. By the current end of the project in August 2013, SUNMAP will have facilitated the sale of 1 million nets through the commercial retail sector. The extension will enable the project facilitate the sale of an additional 1.5 million nets by 2015. This is not included in DFID’s operational plan target because the net sales are not fully attributable to DFID. / SuNMaP has also been providing support to prevent malaria in pregnancy by providing commodities, alongside training, for the use of sulphadoxine-pyrimethamine (SP) as IPT (intermittent preventive therapy) for pregnant women. To date, the programme has distributed 3.4 million doses of SP for IPT, enough to protect 1.7 million pregnant women. The extension will enable the distribution of an additional 1.5 million doses by 2015, enough to protect 750,000 pregnant women. / The extension will also enable SUNMAP implement a pilot of seasonal malaria chemoprophylaxis (SMC), a new intervention which involves the intermittent administration of full treatment courses of an antimalarial treatment combination to children under five during the malaria season in areas with highly seasonal malaria transmission. This promising intervention has been shown to significantly and cost effectively prevent malaria illness among children under five in other countries. It is proposed to be implemented in Jigawa State in Nigeria’s Sahel region, in partnership with the Bill and Melinda Gates Foundation. This pilot will aim to establish the effectiveness, cost effectiveness and feasibility of the intervention in the Northern Nigerian context, with a view to developing good practice guidelines and plans for possible scale up to other suitable parts of the North. / Indoor Residual Spraying (IRS), either alone or in combination with LLINs, is an intervention that has been shown to be effective in reducing the burden of malaria in many countries. It is currently being implemented in Nigeria by the World bank, USAID, as well as a number of State Governments. However, this intervention is not included in the existing SUNMAP project, and it will not be feasible to implement it during the two year extension. In addition the cost-effectiveness and operational feasibility of this intervention is yet to be established in the Nigerian context. We will examine evidence from IRS implementations by other malaria partners in Nigeria to guide decisions on any future DFID malaria project beyond 2015 / Treatment: Access of the population to effective treatment of malaria is improved. / WHO recommends the use of artemisinin-based combination therapies (ACTs) for first-line treatment of uncomplicated malaria and since 2009 also recommends confirmed diagnosis prior to treatment with ACTs. The signs and symptoms of malaria are nonspecific and malaria is clinically suspected mostly on the basis of fever or a history of fever. The changing epidemiology of malaria due to scale up of interventions and the introduction of ACTs have increased the urgency of improving the specificity of malaria diagnosis. Thus, clinical suspicion of malaria should be confirmed with a parasitological diagnosis prior to treatment with ACTs. / SUNMAP was initially designed to support improvement in case management of malaria by providing support for the sale and promotion of subsidised artemisinin combination therapy (ACT) for children through the commercial sector. However, this could not be implemented due to the development and implementation of the Affordable Medicines Facility for Malaria (AMFm), which is a similar, but much larger scale intervention. In addition, the initial design did not include substantial support for malaria diagnosis because Nigeria’s malaria treatment policy at that time did not recommend parasitological diagnosis of malaria before treatment in children. The current policy now stipulates parasitological diagnosis prior to treatment in all age groups. / A revised SUNMAP strategy for this output is now being implemented. It includes support for the following interventions: / Training and support of health workers, including informal health workers such as patent medicine vendors (PMVs) who account for the bulk of malaria treatment in Nigeria, in the appropriate treatment of fever and malaria. As at September 2012, SUNMAP had trained health workers from 5,400 service delivery points. The extension will enable the programme increase this number to 10,500 by 2015. / Procurement and distribution of ACTs and RDTs to health facilities to enable the appropriate treatment of malaria after prior parasitological diagnosis. 1.6 million ACT and 1.6 million RDT are expected to be distributed by SUNMAP by August 2013. The extension will enable the programme to increase this number to 4.2 million ACT and 4.8 million RDT by 2015. The quantification of ACT and RDT requirements is based on programme assessment of realistic commodity requirements for scale up, and current gaps in supply of these commodities, taking into account quantities expected from Government and other partners. / Support to the commercial sector for the sale through retail channels of subsidised ACTs and RDTs. This intervention will help address some of the constraints in the market for malaria diagnosis and treatment that have hindered the scale up of appropriate treatment for malaria. Specifically, SUNMAP is facilitating mutually beneficial partnerships between AMFm first line buyers and networks of rural patent medicine vendors, which will help ensure that commodity supplies are adequately targeted to the poor, and that commodity prices are kept at an affordable level. In addition, SUNMAP will help address constraints that currently severely limit the scale up of RDT diagnosis in the informal private sector. The extension will enable the programme facilitate the sale of 4 million doses of subsidized ACTs and 1 million subsidized RDT kits through retail channels. This is based on the assumption that subsidies for ACTs and RDTs will be sustained through the lifetime of the extension (see page 51, Risks). / Behaviour change: Community awareness and demand for effective malaria treatment and prevention are improved. / While there has been substantial progress in the availability of key malaria control interventions such as LLINs, IPT and ACTs; a lack of awareness about the benefits and use of these measures by the population has limited the extent to which they are being used. SUNMAP has carried out extensive awareness campaigns at household and community level to increase population knowledge and awareness about the best ways of controlling malaria, with a view to increasing demand and appropriate usage of effective malaria control measures. This work will be intensified during the extension period to maintain and increase awareness levels to support sustainable malaria control. Between 2010 and 2012, the proportion of women of child bearing age in the initial 6 SUNMAP States who know the benefits of LLINs increased from 52% to 94%, and the proportion who know the benefits of IPT increased from 29% to 50%. The extension will enable SUNMAP maintain or increase these levels in the 6 States and scale up this work in the 4 additional States by 2015. As a result of this work, the gap between the proportion of people in SUNMAP States who have LLINs and those who use them (use gap) will be expected to reduce from 36% in 2010 to 5% in 2015. The improvements in intervention usage are expected to lead to increases in cost effectiveness of the intervention. / Operational research: Operational research into key areas of prevention and treatment provides the basis for more effective strategies. / SuNMaP’s approach to evidence based implementation has included close engagement with NMCP and Nigerian research community. This has allowed the NMCP to be introduced to the process of evidence based policy development. In this regard SuNMaP can be perceived to have succeeded in working in a fashion that enables ownership and allows for better opportunities of sustainability within the system[28]. / One operational research study that has been completed and results disseminated. It is titled ‘Comparing the implementation of integrated and stand-alone campaigns within the context of achieving Universal Coverage of LLINs in Nigeria by end 2010’. The results of this study were influential in resolving disagreements within the partnership regarding the best way of attaining universal coverage in Nigeria, and establishing good practice for further implementation of the universal net campaigns. / Other studies in the pipeline include: / ‘Assessing SP sensitivity and effectiveness of Intermittent Preventive Treatment in pregnant women in Nigeria’ / ‘Assessing the effect of the SuNMaP capacity building programme for malaria control in Nigeria’ / ‘How are rapid diagnostic tests for malaria integrated into the case management of febrile children in Niger State, Nigeria’ / ‘Causes of non-malarial febrile illness and health outcomes of treatment of febrile illness based on malaria rapid diagnostic tests’ / For a number of reasons these studies will not be fully completed and disseminated by the current end of SUNMAP in August 2013. The extension will enable SUNMAP not only to fully complete and disseminate the results of these studies, but also to ensure that the results are used in evidence based malaria policy development. In addition, a further 7 operational research questions will be investigated and answered during the extension period. / Outcome: To strengthen delivery of Nigeria’s malaria control effort in up to ten supported States. / Between 2008 and 2010, the proportion of children under five sleeping under insecticide treated nets in SUNMAP supported States increased from 3% to 49%. The extension will enable a further increase to 65% by 2015. / Between 2008 and 2010, the proportion of pregnant women in SUNMAP supported States who used intermittent preventive treatment in SUNMAP supported States increased from 2% to 16%. The extension will enable a further increase to 35% by 2015. / Between 2008 and 2010, the proportion of children under five with a fever who received treatment with recommended malaria treatment increased from 3% to 6.5%. The extension will enable a further increase to 25%.
B. Theory of change and evidence / The programme will impact upon the mortality and morbidity attributable to malaria, through the delivery of preventative and curative commodities); and through capacity building, harmonisation of activities and interests, advocacy and social mobilisation and operational research. / Evidence summary[29] / Project performance / Repeated annual reviews of SUNMAP have affirmed its excellent contribution to Nigeria’s malaria response, and the progress that has been made so far. The last (2012) annual review of the project concluded “Overall the review found that SuNMaP is making good progress in achieving the purpose and outputs of the programme. It is highly regarded among stakeholders as a key leading partner in malaria control in Nigeria whose contributions are greatly valued.” The project scored an “A” at its last annual review in 2012. / Epidemiology and Burden / The majority of human clinical malaria is caused by Plasmodium falciparum and the great majority of deaths are caused by this species. Plasmodium vivax malaria remains a significant health problem in much of Asia and Latin America. Quoted evidence of the rate of transmission of malaria around the world depends on direct observation and modelling. Using these two approaches there are now a number of maps of malaria, at a global and country level. These demonstrate the very wide range of transmission of malaria from areas where clinical cases are only occasional to those, particularly in West and Central Africa, where unprotected people can receive several infected bites a night and have several clinical episodes of malaria a year. There is therefore a wide divergence between population at risk, and burden of disease. The majority of the deaths occur in Africa, particularly West and Central Africa, due to a combination of very high transmission and weaker health services. There is considerable variation in transmission even within countries with many countries in Africa and Asia having areas of very high transmission and low or no transmission within short distances of one another. Data quality on which existing maps and graphs of malaria transmission are based is variable however, and in particular in many of the poorest areas reliable evidence of malaria transmission is hard to come by. / Recent trends in malaria show that malaria burden has dropped substantially both in terms of transmission and clinical burden in a number of countries in Africa which have effective malaria programmes. Evidence for this is strong, although mainly from health service data. / Malaria is a significant burden on health systems and on the wider economy and, particularly in Africa, represents a substantial economic burden on households having to pay for prevention and treatment. Community, age, nutritional status and some aspects of economic socio-economic status have an impact on the probability of individuals both acquiring malaria and dying from it. / In fragile/conflict affected states where malaria control and other public health services break down malaria can often have a significant resurgence. Examples of this include Afghanistan and Burundi. / There is an on-going debate on the effects of climate change on malaria. Malaria is likely to be transmitted higher up in highland areas and may spread into some areas it was previously not found due to global warming, but this effect is probably modest and it is changes in rainfall patterns that are likely to be the main driver of changes in transmission; the effects of climate change on rainfall are currently unpredictable in most malaria-endemic countries. Climate change will therefore move malaria around. It is unclear whether this will lead to an overall increase (or decrease) in malaria all other things being equal. Changes in water management and sanitation, agricultural practices, urbanisation and deforestation all have significant impact on malaria transmission. / Interventions and Delivery / Vector control. / There is strong evidence for the use of insecticide treated bednets (ITNs), long lasting insecticide treated nets (LLINs) and indoor residual spraying (IRS) in areas where the predominant mosquito species bite and rest indoors. This is in the majority of Africa and a number of other areas in Asia, although in areas of Asia and Latin America much or most transmission is outdoors. Evidence that ITNs, LLINs and IRS work under trial conditions is very clear. Evidence to what is the best delivery mechanism for insecticide treated bed nets is less strong and more context specific. There is a long standing debate around the role of free net distribution vs vouchers vs subsidy to increase coverage levels from their current low rates particularly in Africa. A mixed delivery method is probably appropriate in most settings. IRS has generally had to be delivered by vertical programmes. A number of novel methods of delivering insecticides such as curtains or blankets and tarpaulins in emergencies have been shown to work. / There are a number of non-insecticide based approaches to vector control including larvae control, changed water management and building out malaria. These have an established place in certain environments although they are generally less useful across Africa where major vectors have many breeding sites. Novel methods including genetically modified mosquitoes are being considered but are a long way from deployment. / Case Management: Diagnosis and Treatment / Diagnostic Tests for Malaria / Whilst light microscopy remains the most widely used form of malaria diagnosis, rapid diagnostic tests (RDTs) are becoming increasingly used. These are sensitive and specific and increasingly heat stable. They have advantages in certain situations particularly where there is low throughput of tests and where electricity is not available, for example peripheral areas. Deploying tests without training however does not lead to improve diagnosis as the results are often ignored. There is good evidence that malaria is significantly over-diagnosed in formal health care settings in Africa and possibly in Asia. At the same time malaria is often not diagnosed because people do not reach formal health care. Improving diagnostic tests and training can help with the first but not second of these. The role of rapid diagnostic tests in the private sector is currently unclear. / Drugs for malaria / There are a wide range of potential drugs for malaria. A major limitation of available drugs is drug resistance. There is now some drug resistance to almost all the older anti-malarial drugs used either alone or increasingly in combination. / Broadly there is extensive drug resistance throughout South East Asia and to the lesser extent the rest of Asia. In this area artemisinin combination drugs (ACTs) are the only realistic option. Early evidence of artemisinin resistance exists in South East Asia. There is however a need for new drug classes since drug resistance to malaria is a matter when, not if. New and more effective drugs including ACTs cost more than older drugs and this causes significant problems of willingness to pay in areas where the majority of care is through the informal private sector (shops and drug-sellers); the informal private sector is the predominant source for antimalarials in much of Africa and Asia. / The recommended ACTs for treatment of uncomplicated malaria in Nigeria are Artemether-Lumefantrine and Artesunate-Amodiaquine. The 2009 Drug Therapeutic Efficacy Tests carried out on these medicines in the country have confirmed that they remain efficacious[30]. Nigeria is currently rolling out RDTs nationally in line with WHO recommendations for confirmed diagnosis prior to treatment. / Whilst evidence for which drugs work under control trials is a very strong, evidence on what is the most effective ways to get drugs to those who need them is much more variable. Highly effective drugs that reach only a fraction of those who need them have relatively limited operational impact. There are multiple steps along the pathway between a child or adult first having symptoms and their receiving effective drugs where they can fall off. This includes: failure to seek care of any kind; physical barriers to access to formal health care (e.g. distance, mountains); poor diagnosis in the private, informal or formal sector; absent drugs; unaffordable drugs; poor quality and fake drugs; and failure to take a course completely. Each of these requires different possible solutions, and testing of these is only beginning in many areas. Solutions to failure to seek care are likely to be largely around education and awareness campaigns. Reducing the impact of physical access to antimalarials includes community health workers, home base delivery of care, and improving transport in rural areas. All of these have some evidence but it is mixed and likely to be locally specific. For those seeking care in the private sector there is reasonable evidence from a very limited range of studies that interventions with shops and other drug providers can significantly improve the quality of care provided. Improving adherence to drugs is likely to revolve around drug packaging and training of health care workers and other providers. Management of the epidemic of fake drugs is likely to require a combination of improved detection and law enforcement but in particular it is likely to involve reducing the cost of effective drugs to end users (although formal evidence that this works is so far limited). / Drugs can be used to prevent malaria. There is now strong evidence to support intermittent preventive treatment in pregnancy (IPTp), intermittent preventive treatment in infancy (IPTi) and intermittence preventive treatment in children (IPTc). There are however operational questions with all of these. In particular the level of transmission at which they cease to be effective is currently unclear. Which drugs to use, particularly in pregnancy, remains a difficult question on which evidence is limited. / Different methods of delivery also have to be considered, particularly in areas where malaria is seasonal. WHO has recently issued a new policy recommendation for Seasonal Malaria Chemoprevention (SMC) involving the intermittent administration of full treatment courses of an antimalarial treatment combination during the malaria season to prevent malaria illness among children under five, in areas with highly seasonal malaria transmission. While the potential benefits of SMC are substantial, more research is needed to determine if and how this can be a practical approach to malaria control. Northern Nigeria is in a geographical area where SMC could potentially be a powerful intervention. A Cochrane review of trials that evaluated the impact of SMC in preventing malaria in pre-school children living in endemic areas with seasonal transmission showed that SMC prevented approximately three quarters of all clinical malaria episodes and a similar proportion of severe malaria episodes and that these effects remained even where insecticide treated net usage is high[31]. Other studies have also shown the beneficial additive effect of SMC given during the transmission season alongside other malaria control interventions such as the distribution and promotion of use of LLINs[32],[33] / Whilst evidence that vector control methods and drugs work is very strong under ideal conditions, evidence around delivery channels and how cost effective these are is much more variable and context specific. This applies to drugs, diagnostics, insecticide treated bed nets, and other vector control measures. Sustainability and affordability in particular are unclear for several of these, and evidence of how best to engage the private sector is in most areas sketchy. / Whilst nutrition does appear to be associated with increased severity of malaria, evidence that nutrition interventions have a significant impact on malaria is limited or absent. / Interventions in high-risk groups: pregnancy / Malaria in pregnancy requires specific interventions. Evidence for providing insecticide treated bed nets for pregnant women in high malaria transmission settings is very strong. Evidence for intermittent preventive treatment is also strong with the caveats mentioned above. / Behaviour change approaches / Advocacy and behaviour change communications have been a key component of Nigeria’s fight against malaria since 2004[34],[35],[36]. Malaria awareness-raising, advocacy, case management, and prevention efforts have reaped the benefits of social science research and as a result, many programs are implemented and evaluated in a more effective manner than in the past[37]. There is empirical evidence to show that communication plays a vital role in changing knowledge, creating positive attitudes and improving practice of positive health behaviour[38],[39]. / Approaches to health systems / In much of Africa and Asia the problem is not that there are no preventive measures and drugs which are proven to work, but rather that they do not get to the people who need them. This is a failure of health systems which in many countries is extreme. Usually this is due to multiple stages. Evidence suggests that independent activities need to be undertaken to address each of the individual steps rather than assuming that a single intervention will achieve significantly stronger health systems. Research on this area has been variable and sometimes context specific. Areas where there is some evidence of interventions under operational deployment include: improved physical access; supply chain management; quality drug formulation and packaging; training in case management and rational treatment; community case management and home management of malaria; health worker and work force planning; human resource management; and information systems and health worker motivation. Involving both public and private health care for malaria is in many countries essential since much health care is currently provided by the informal private sector (mainly shops) especially for the poorest. Reducing the cost of antimalarials, and possibly diagnostic tests, is likely to be a necessary but not sufficient part of the response to this. Initial studies of subsidised antimalarials through the private sector are encouraging. / Evidence underpinning theory of change / The evidence outlined above, as well as the strong track record of delivery of programme outputs and outcomes by the programme, supports the assertion that the programme inputs and interventions will lead to the desired outcomes. This is summarised below: / Causative links International evidence SUNMAP programme experience / That there is a link between the problem and the causes Very strong Very strong / That the inputs will lead to the outputs Strong Strong / That the outputs will lead to the outcomes Strong Strong / That the outcomes will lead to the impact Very strong Too early to say. Key survey data due in 2014 will provide more evidence. / Assessing the strength of the evidence base for each feasible option including delivery routes / In the table below the quality of evidence for each option is rated as either Very Strong, Strong, Medium, Limited (or No Evidence) / Option Evidence rating / 2 Strong
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / Rapid baseline capacity building needs assessment for malaria control were conducted in Anambra, Kano and Lagos States during November/December 2008 and in Katsina, Niger and Ogun States during December 2009 to February 2010. Each state that the program covers is different in terms of institutional arrangements, capacity to manage malaria control, pattern of disease and State plans etc. The assessment helped to establish a baseline and inform the design of the capacity development program to be rolled out at the Federal level and in each State and contributed to preparing them for the rapid scale up of interventions to achieve the ambitious targets for Malaria control in the country. The participatory nature of the assessment process was also important as part of the engagement with the States and is itself a capacity building activity. / The assessments indicated a number of areas of concern and provided recommendations for future capacity building interventions across the 6 output areas and for national, state, LGA and service delivery levels. One of the outcomes of the baseline assessments was the realisation that while there was a wide range of training materials on malaria control in Nigeria, these were not standardised and there were still gaps, particularly around management of malaria programmes. Other areas of concerns highlighted included weakness in existing coordination, operational planning and supply chain systems. At service delivery points there appeared to be poor perception and adherence to policy recommendation on malaria diagnosis and treatment. / Consequently, a capacity building package was developed with NMCP to address two overarching themes of programme management and service delivery. In the course of development, it was noted that many training aides had been produced by the NMCP/FMoH (Federal Ministry of Health) with support from development partners, however further discussions with NMCP identified that materials related to the management of malaria control did not exist and needed to be developed. Thus SuNMaP supported NMCP to develop and produce a standard set of materials appropriate for Nigeria, consistent with national policies to ensure that all involved in the management of malaria control at Federal, State, LGA or service delivery points understand their roles and responsibilities to improve programme management and service delivery. The output is 1 curriculum and 14 modules for trainers and trainees (as outlined in the table below) developed through utilising, re-aligning, re-working and updating existing materials and developing new ones where necessary. / SuNMaP’s capacity building approach is “a people-centred, pragmatic and focused approach that goes beyond training to improve the knowledge, skills and practices of programme managers and health care providers. It strengthens organisational capacity to implement effective and sustained malaria control within the health system”. The approach recognises and focuses on the vital role of effective teams at federal, state and LGA level in managing malaria control. / SuNMaP’s capacity building work has five key objectives: / I. Improved capacity for policy development, planning and coordination at National, State and LGA level / II. Capacity building technical support customised to respond to the context, divergences, peculiarities and priorities of the intended beneficiaries / III. Effective, efficient Malaria Control Programme Teams providing leadership for all key players and working together in a synergistic manner at National, State and LGA level / IV. Well established systems for mobilising, harmonising, distributing, utilizing and sustaining resources for malaria control / V. Health managers and providers in the public and private sector who know their roles in the prevention, delivery of services and management of malaria control / SuNMaP’s capacity building initiative is based on three basic principles:- / Consistency with National Policies – capacity building at all levels must be consistent with national policies for malaria control. / Stakeholder engagement - stakeholder participation and ownership of capacity building is imperative for sustainability and achieving the programme’s objectives, including: / Joint assessment of needs / Planning by Stakeholders, with SuNMaP support / Implementation by Stakeholders, with SuNMaP support / Harmonisation – all agencies, organisations, projects and programmes supporting malaria control working together under national/state government leadership, with “three ones”:- one malaria control policy; one set of capacity building procedures and guidelines; and one operational plan (at the national level and for each state and LGA) / SUNMAP’s support for planning and policy development can be summarised by the following matrix: / SuNMaP’s capacity building support revolves around five major components as follows: / I. Participatory Appraisal/ Assessments / II. Building Individual & Team Capabilities / III. Strengthening of systems (line systems) / IV. Institutional Strengthening (central systems) / V. Exit & Sustainability / SuNMaP’s capacity building effort recognizes sustainability planning as an integral part of its planning process. For capacity building to be considered a success, there must be an inbuilt mechanism for exit that ensures that gains achieved are not only sustained but improved upon; for this reason all aspects of the programme activities take into cognisance the vital role of stakeholder participation and ownership across the programme outputs. / This is particularly important as it relates to the operational planning support and capacity building package. It is anticipated that the programme shall continue to support the hand over process of continuous improvement for capacity building in the short run through technical assistance and hand holding as NMCP and SMCP coordination and technical capacity improves. / The active involvement of the personnel from SMCPs and NMCP in the planning and implementation of programme activities such as the capacity building roll out and other technical areas has provided the opportunity for learning by doing with a resultant rise in confidence level of key health staff, the establishment of a pool of technical resource at state and national level in the process of the capacity building roll out is already being exploited by the SMCPs and NMCP outside the frame of SuNMaP supported activities, this technical resource is likely to sustain the current effort outside the geographical scope and lifetime of the programme . / The SUNMAP project scored an A+ for its capacity building work at its most recent independent annual review (2012). The following lessons have been learned from SUNMAP’s capacity building work and are being applied in ongoing and future work: / At the commencement of the Programme, capacity building was perceived to be limited to Output 1, which is Improved National, State, and LGA level capacity for policy development, planning and coordination. Cumulative experience has shown that capacity building is a cross-cutting issue which transcends each and all of the six Programme outputs. / To be effective, capacity building efforts must go beyond the traditional methods of organising training events and employ multi-pronged techniques and approaches including coaching, mentoring, on-the-job training, in-depth training, the use of job aids and readily available guidelines and hands-on support through Integrated Supportive Supervision. / Capacity building strategies must take cognisance of the context, divergences, peculiarities and priorities of the intended beneficiaries. This means that there cannot be a one-size-fit-all approach. This makes stakeholder participation and ownership of the process imperative for the achievement of programme objectives and sustainability. / Financial sustainability of malaria control / Funding for malaria control in Nigeria is still largely donor dependent. Precise data on Government expenditure on malaria control, particularly at subnational levels, is difficult to come by. Between 2008 and 2010 the Federal Government expended at least $80m on malaria control, which suggests a significant increase from previous levels[40], and does not include expenditure at State and local Government levels. During this period, external donor expenditure on malaria control in Nigeria totalled $491m, indicating the sector is still a long way from being financially independent of external funding. The majority of the funding from government and donor sources during this period was expended on procurement of LLINs for the universal net campaigns. During this two year costed extension, SUNMAP will continue to pursue opportunities for increasing financial contributions from the Government of Nigeria, as detailed below. / The Government of Nigeria has recently launched a new “Saving One Million Lives” strategy to save the lives of one million women and children by 2015 through scaling up coverage of key lifesaving interventions, including those that address malaria. Although precise financial allocations for this programme have not yet been released, it is likely that it will involve significant increases in the allocations for malaria control. However, this is unlikely to significantly address the massive malaria financing gap of $1.7 billion currently estimated between 2013 and 2016. / The Global Fund’s new funding model stipulates that recipient countries now have to meet counterpart funding requirements based on their level of income per capita. Under the model, Nigeria is classified as a “lower lower middle income country”, and will therefore have to ensure that the Nigerian Government provides at least 20% of the total of government and Global Fund financing. Given the large share of malaria financing in Nigeria currently provided by the Global Fund, this 20% will translate into a significant increase in Government of Nigeria spending on malaria. / SUNMAP is encouraging greater financial sustainability through the following ways: / Improved planning, budgeting and management of malaria control by government health authorities: Better planning and implementation of malaria programming at Federal and State levels, linked with reforms of State budgeting systems supported by DFID’s health systems (PATHS2) and governance (SPARC) programmes, strengthens the case for improved budgetary allocations to malaria at Federal and State levels. / Leveraging additional government funding through the demonstration effect: SUNMAP developed and demonstrated the first universal net campaigns in Nigeria, in Kano and Anambra States, back in 2009. The success of these campaigns, and the political interest they generated, leveraged unprecedented levels of Government funding for additional nets and other costs to replicate the campaign in other States. In the same way, SUNMAP’s support for routine net distributions is designed to stimulate increasing levels of domestic funding for this activity through formal MOUs signed with each of the supported States. Government is also showing interest in scaling up the Seasonal Malaria Chemoprophylaxis (SMC) intervention if the SUNMAP SMC pilot is successful. / Improving value for money in malaria programming: SUNMAP’s efforts at improving harmonisation and coordination of malaria programming among multiple donors has been shown to reduce duplication and waste, enabling limited resources to be used more efficiently. In addition, its high level of credibility within the malaria control environment offers the opportunity to replicate SUNMAP’s value for money approach across other malaria partners. Recent VFM analysis performed by SUNMAP (and commended by the UK NAO) indicated unit costs, particularly in capacity building activities, that appear well below those of other partners. SUNMAP is currently carrying out operational research to demonstrate the cost effectiveness of the approach and generate lessons for government and other partners. / Advocacy: SUNMAP’s approach prioritises engagement with and advocacy to decision makers and policy makers at national, state and community levels. Advocacy efforts are primarily targeted at promoting the widespread use of effective malaria control measures, and increased government funding for malaria programming. Recent successes include a commitment, facilitated by SUNMAP and DFID, of the Kano State Governor to provide £2.5m in additional funding for malaria activities in 2013. / Facilitating sustainable market systems for LLINs: In recognition of the sustainability problems posed by the heavy dependence of malaria prevention on donor funded LLIN supplies, SUNMAP has also been working with the commercial sector to develop sustainable retail markets for LLINs. Using a facilitative “Making Markets work for the Poor (M4P)” approach, the project is helping address key constraints to the bednet retail market. Important interventions include improving access to finance for net distributors; improving branding, marketing and distribution of net products; interventions to improve the desirability of nets and generate demand; and supporting the development of new products which better meet the needs of the population. / Improving the health system / Malaria is estimated to be responsible for 60% of health facility visits in Nigeria. Given the massive impact of malaria on health services, effective delivery of malaria control will require significant improvements in the building blocks of the health system. Such building blocks include: / Health system leadership and governance / Health financing / Human resources for health. / Health commodities and logistics systems. / Monitoring and evaluation, including health management information systems. / Service delivery. / SUNMAP is a malaria focused programme. It is designed to work in partnership with DFID’s health systems programmes, PATHS2 and PRRINN-MNCH, which are focused on transforming the health delivery systems in each of the focus States. SUNMAP engagement with these programmes is targeted at integrating malaria control more closely within the health care delivery systems, to improve the efficiency and sustainability of malaria interventions. Key objectives of PATHS2 and PRRINN-MNCH include: / Improved governance of health delivery systems at National and subnational levels, including facilitating fundamental reforms of the way health services are organized and managed. / Improved management of the health workforce in focus States. / Improved systems for raising revenue for health services, managing the health budget and purchasing health services, in order to improve equity and ensure protection of the poor and vulnerable. / Improved systems to ensure the availability of drugs and commodities. / Improved health facility infrastructure and service delivery. / Improved ability of households and communities to manage their own health problems and hold health services to account. / Progress in all these areas is measured through the logframes and monitoring and evaluation arrangements for PATHS2 and PRRINN-MNCH. These programmes due to end in 2014 but the successor MNCH programme will continue to work on the above areas in partnership with SUNMAP.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 2 B B / Possible effects of SUNMAP on climate and the environment / Research is still ongoing with regards to the environmental impacts of used LLINs and how to go about managing their growing numbers following mass campaigns. It is worth mentioning that an LLIN that has reached the end of its useful life still contains insecticides, whether it is still being used to sleep under, is being re-used for another domestic purpose, or has been discarded as waste. LLINs are not, however, considered as hazardous waste under the Basel Convention on the Control of Transboundary Movement of Hazardous Waste and their Disposal. It has been proposed that LLINs that have reached their EOL should be considered as “pesticide containers”, and managed using the same principles, in order to minimize the environmental risk. / There are some concerns that there may be environmental (toxicity to terrestrial and aquatic life) and human health risks related to net usage and local LLIN waste management, i.e. when burned, buried or left in the environment (see figure below). When an LLIN is used as a net to sleep under, the risk for the environment is low. However the risks arising from the re-use of old LLIN material for other domestic “non-design” purposes have not been comprehensively assessed. To quantify these risks, one would need a greater understanding of the different uses. / Figure 1: Flowchart of used LLINs, WHO Report 2010 / It has been argued that there may be a public health benefit from leaving the LLINs in the community. If an LLIN in good condition is not available, then sleeping under a used or worn out LLIN is certainly better than not using a net at all. The protection given by an old LLIN presumably depends on (a) the size and number of holes and (b) on insecticide levels. LLINs used as eave curtains or window coverings may contribute to malaria vector control[41]. Common domestic reuses for economic activities, including covering of crops and enclosure of livestock, may improve economic outputs and hence the livelihood and health of the household. For example, treated netting has been shown to be effective at improving cabbage production in smallholdings in Benin[42]. There is anecdotal evidence that old netting is being re-used for purposes other than sleeping, however the range and frequency of such forms of domestic reuse have not been fully documented. Studies have shown nets being used for a range of outdoor purposes, including: fishing and drying fish in Kenya[43]; prawn fishing in the Solomon Islands[44], protecting seedlings and garden crops, as the walls of a chicken coop, plaited into string to tie cattle in Ethiopia[45], and as washing sponges in Liberia[46]. A range of indoor uses have also been reported, with netting being used as a ceiling, a room-divider, curtains on window, door or eave, bed covers, padding under a sleeping mat, tablecloths, and even as garments in Sudan[47]. / There is a need to further characterize and document such alternative uses and to clarify to what extent and in what condition nets are being put to such alternative purposes and the environmental and human health risks they pose. WHO recently undertook a preliminary research study[48] focusing on identifying preferred options for LLIN End of Life management, and provide evidence to make policy recommendations. The main recommendations[49] of this study include the following: / Proper disposal of LLIN packaging material to reduce their environmental impact. / Net distribution should be accompanied by education on the proper use and disposal of LLINs. / Net distribution workers should wear Personal Protective Equipment. / LLINs should not be retrieved from the community at their end of life. / There is no immediate impact on climate change anticipated. / Possible effects of climate change on SUNMAP / Global temperature and precipitation changes alter the location, rate of breeding and the migration range of disease-bearing vectors including mosquitoes. In fact while many infectious diseases are affected by changes in the climate, vector-borne diseases, such as malaria and dengue fever are known to be particularly sensitive to climatic variations. Available research indicates that the combined effects of changing temperatures, precipitation and humidity are in most cases likely to lead to a more suitable environment for the spread of malaria. Analysis of malaria morbidity data in a number of other tropical countries, e.g. Ethiopia, indicates that higher minimum temperatures correlate with increased instances of malaria outbreaks (Confalonieri et al., 2007). The effects of increased temperature can be further multiplied by a simultaneous increase in precipitation (Confalonieri et al., 2007). Climate changes also affect the density of vectors in a particular area and increases the likelihood of infection up to significant thresholds (WHO, 2004). Bite frequency generally rises with temperature and atmospheric CO2 content (DeLucia, 2008). If climatic changes increase the rate of spread of malaria in Nigeria to new significant level, the obvious implication will be that a far greater percentage of the population than anticipated by SUNMAP will be at risk of malaria infection. However, such significant changes are highly unlikely during the life of the 2 year SUNMAP extension. / Opportunities / Some opportunities exist to make SUNMAP more resilient. Firstly, SUNMAP managers would need to be sensitive to the possible ways through which climate changes can impact the epidemiology of malaria in Nigeria. Future malaria modelling in SUNMAP active states and indeed the country will need to involve a prediction of the scope, geographical distribution and characteristics of malaria over a period of time. These models must incorporate a variety of factors including projected changes in temperature, precipitation, and humidity as well as other environmental factors such as drought and deforestation. For example some existing models suggest that people living in developing countries at the risk of malaria will increase 5-15% by 2100 due to climate change. In Africa alone, according to the MARA Project (Mapping Malaria Risk in Africa) there is a projected increase of 16-28% in person-month exposures to malaria by 2100. These models are crucial in preparing an effective public health response to future disease outbreaks. In 2012, SUNMAP funded the most recent mapping of trends in malaria epidemiology and climate in Nigeria, and will support the NMCP to continue to update the model and improve environmental targeting of malaria interventions. / There are additional opportunities to minimise the impact of SUNMAP’s activities, particularly the distribution of large numbers of long–lasting insecticide treated nets, on the environment. During the extension, the project will: / Continue to promote the use of pre-treated LLINs rather than other types of nets which require treatment by the user, and have much higher environmental risks. / Continue to ensure proper disposal of LLIN packaging according to WHO guidelines, including specifying the use of biodegradable packaging materials in net procurement. / Continue to provide information to consumers and communities regarding the use and safe disposal of long lasting insecticide treated nets. / Encourage practices (e.g. appropriate washing, drying and stitching of holes) to extend the useful life of LLINs. / Collect data from programme beneficiaries and other users regarding net preferences, alternative uses and net disposal practices to enable better targeting of net types and information, as well as inform policy. Share the data collected with WHO and other relevant organisation which are conducting studies in this area. / Ensure net distribution workers wear personal protective equipment. / Measure the implementation of the above measures as part of its monitoring and evaluation processes.
E. If any, what are the likely major impacts on social development? / Malaria accounts for 25-30% of infant mortality in Nigeria. This rate however represents the national aggregate. There exist significant differentials in infant mortality at national and state levels, between rural and urban, and even city-wide differences between the rich and poor. / Malaria is responsible for poor pregnancy outcomes such as low birth weight, pre-term deliveries, stillbirths, abortions, and anaemia in pregnancy. Malaria is known to contribute to 11% of maternal mortality in Nigeria. / Indirect and social costs of the disease are enormous. It leads to an increased sickness absence rate in children with consequent low educational attainment and to absenteeism from work in adults leading to low capacity to earn. The resulting loss of income aggravates poverty and contributes substantially to maternal mortality and reduced life expectancy. / Characteristics of the poor include low income, poor access to health services, poor housing conditions and high incidence of under-nutrition and parasitic diseases. In the urban areas by contrast, there is increased general awareness on health issues, access to primary education and a source of income of some sort. However, poor sanitation and increased environmental degradation lead to increased vector breeding sites, increased malaria transmission, increased frequency of malaria episodes and its sequelae on the household. / As in many developing countries, women in Nigeria are more likely to be poor. They also have fewer options than men for escaping poverty. Women are the primary caregivers in Nigeria and should be targeted for education in malaria prevention and treatment especially as it affects children. Women are unable to contribute to the household income when they fall ill, as they have to stay away from work. They also have to sacrifice their time and stay away from work when any member of the household falls ill - be it the husband or the children. / Social conditions in Nigeria present a startling paradox: despite a rich endowment of natural and human resources, most of the country is poor. The growing incidence and the dynamics of poverty in Nigeria have stratified and polarised Nigerian society between the ‘haves’ and ‘have-nots’ resulting in tensions and social conflicts that have eroded the fabric that has held the society together. The challenge is not only to reform the economy in order to boost economic growth but also to empower people as a means of revitalizing the weakened social support systems. This will require a human rights approach to development planning that places people at the centre of development efforts. The added value provided by this approach is that the norms and values enshrined in it have the potential to empower the poor. / SUNMAP has contributed to ensuring a positive social impact by supporting improvements in the quality of service delivery, particularly among rural primary facilities and informal health workers used primarily by the poor. The provision of preventative commodities such as LLINs and SP are expected to have a substantial effect on reducing malaria incidence. The distribution of these commodities has been carried out in such a manner as to ensure access by the poorest and vulnerable groups. A recent study investigating the effects of the SUNMAP 2009 net distribution campaign in Kano State[50] concluded that “The campaign had a significant impact by increasing ITN coverage and reducing inequity in ownership and use”. The programme’s focus on approaches which address equity will continue during the extension period. / Routine distribution of LLINs through ANC and EPI channels will target the most vulnerable groups – women and children under five - thus reducing the risks of malaria related mortality and increased opportunities for income generation and reduced number of school days missed. Provision of case management commodities, will not only assist health facilities in improved treatment relating to malaria, but enable the opportunity for prompt and effective treatment of malaria and, it is anticipated, reduce malaria related mortality. / Behaviour change interventions will also work towards developing a more knowledgeable community with particular regards to malaria prevention who know how to protect themselves and generate a demand for quality services. Relevant approaches that have been implemented, with some success, in the project include: / Advocacy - Religious, political, commercial, traditional and community leaders, through their positions of power and respect, can make malaria a public issue and support recommended prevention and control practices, helping to overcome barriers to adoption, acting as role models, and changing community norms around treatment seeking and prevention. Advocacy efforts will equip these influential individuals with malaria information and create opportunities for them to address their constituencies, whether through mass media or group fora. / Social Mobilization - Social mobilization activities target Non-Governmental Organizations, CBOs, Faith-Based Organizations, Civil Society Organizations and other networks of stakeholders and captive populations including youths, boarding schools, media and market population to empower them as change agents within their communities. / Behaviour Change Communication - BCC targets mothers, caregivers, fathers and other secondary audiences through the development, production and implementation of IEC and BCC messages adapted to local needs. Relatively poor access to mass media, erratic power supply in the rural areas have meant that the project has had to develop innovative ways to target behavioural change messages to rural populations.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / In spite of steady economic growth, Nigeria has witnessed an increasing trend towards rising conflict and fragility, particularly in the last few years. Key hotspots include Northern Nigeria, where a religious insurgency has disrupted families, economic activities and social services. Environmental degradation in the Niger delta, as well as dispute over the control of oil resources has also fuelled conflict in that region. / The roots of conflict appear to lie in widening social inequality, exacerbated by poor governance, high levels of impunity and unresolved ethnic and religious differences. Low levels of accountability and delivery of public services have weakened the government’s ability to successfully address these issues. DFID’s strategy for helping address this challenge in Nigeria includes (1) helping improve the capability, accountability and responsiveness of Nigerian governance at all levels; (2) working with communities to develop sustainable and peaceful means of resolving conflict, including police and justice reforms; (3) helping to address poverty, improve employment, and foster inclusive economic growth; and (4) helping improve institutional means of citizen participation in governance, such as fair elections and legislative representation. / 97% of Nigeria’s population are at risk of malaria, and it is a condition that affects nearly every household in the country. Interventions, such as bednets and treatment that help address malaria are highly valued by families and political leaders. The universal bednet campaigns (2 nets for each household) between 2009 and 2013 were seen by many rural poor as probably one of the few tangible benefits they have received from public services. / SUNMAP works in some of the areas heavily affected by conflict – six out of the ten SUNMAP States are in Northern Nigeria. It will contribute to reductions in conflict and fragility in Nigeria by helping address some of the root causes, for instance, by improving the capacity of public health services to plan and deliver malaria interventions in equitable ways; helping reduce the burden of malaria which is expected to improve household incomes; and improving the ability of households to protect themselves from malaria and other diseases.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / Costs / Existing programme Costed extension (additional amount requested) / April 2008 – August 2013 (£) September 2013 – August 2014 (£) September 2014 – August 2015 (£) Total extension (£) Grand Total (£) / Total fees and project expenses 36,056,468 8,987,554 9,014,517 18,002,071 54,058,539 / Commodity procurement 10,746,100 21,000,000 21,000,000 31,746,100 / Independent monitoring, Procurement agent fees and contingencies 3,197,432 0 0 / 50,000,000 39,002,071 89,002,071 / Benefits / Benefits Existing programme 2008 - 2013 Costed extension 2014 -2015 Total / Quantifiable health benefits LLINs delivered – this excludes 4.1 million nets provided by DFID from 2009 -2012 through the PATHS2 project, but distributed by SUNMAP 2,500,000[51] 4,617,090 7,117,090 / DALYs[52] averted by LLINs[53] 1,210,427 2,235,460 3,445,888 / ACTs delivered 1,726,000 3,318,326 5,044,326 / DALYS averted by ACTs[54] 183,395 352,587 535,982 / RDTs delivered 1,410,000 4,031,632 5,441,632 / DALYS averted by RDTs[55] 110,248 315,233 425,481 / Total DALYs averted 1,504,070 2,903,281 4,407,351 / Benefits Existing programme Costed extension Total / Other benefits Improved capacity for malaria planning and delivery Federal and 6 States 4 additional States Federal and 10 States / Improved harmonisation of malaria strategic areas 6 Malaria strategic areas harmonised 1 additional malaria strategic area harmonised. 4 existing updated in line with recent evidence 7 malaria strategic areas harmonised. 4 existing areas updated / Service delivery points with health workers trained in malaria prevention, diagnosis and treatment 8,500 service delivery points Additional 2,000 service delivery points 10,500 service delivery points / Improved household income and school attendance 6 States 4 additional States 10 States / Reduced potential for conflict and fragility 6 States 4 additional States 10 States / Cost effectiveness (discounting all non DALY benefits) £33 per DALY ($52 per DALY) £13 per DALY ($20 per DALY) £20 per DALY ($30 per DALY) / The SUNMAP extension will improve the overall cost effectiveness (excluding non-quantifiable impact) of the SUNMAP programme from $52 per DALY over five years to $30 per DALY over seven years. The World Health Organization has defined interventions that cost less than a country’s GDP per capita as “highly cost effective”; interventions that cost between one and three times GDP per capita as “cost effective”; and interventions that cost more than three times GDP per capita as “not cost effective”[56]. According to the World Bank, Nigeria’s GDP per capita in 2011 was $1,502[57]. / Sensitivity analysis / Using the cost effectiveness benchmarks above, the interventions delivered by SUNMAP are highly cost-effective. The project would have to be 50 times less cost effective to be classified as “cost effective” and 150 times less cost effective to be classified as “not cost effective”. Given the large relative impact generated by the delivery of nets, this scenario is only likely to be produced by a catastrophic degradation in both the effectiveness (possibly caused by mosquitoes rapidly developing resistance to the insecticide) and usage levels of the nets. This scenario is considered highly unlikely within the 2 year duration of the SUNMAP extension.
H. Theory of Change for Preferred Option / See section B above
I. What measures can be used to monitor Value for Money for the intervention? / We will carefully track SUNMAP’s progress against results and milestones in the logframe as an overall guide to whether expected benefits are being achieved. Value for Money measures that will continue to be tracked include: / Economy / Unit costs of procuring malaria commodities such as nets, RDTs and malaria treatment. Project data as outlined in the 2012 annual review reveals that the costs have fallen through successive procurements when expressed in £ sterling. A key variable has been the £ to US$ exchange rate, given that most nets are procured in US$. Costs falling somewhat but less dramatically when presented in US$, as is shown below: / DFID LLIN procurement / Quantities / (Million) UNIT PRICE / £ UNIT PRICE / US$ / 2008/09 0.5m £ 3.19 US$ 4.53 / 2009/10 1.0m £ 3.13 US$ 4.67 / 2010/11 0.7m £2.69 US$4.31 / 2011/12 2.1m £2.60 US$4.08 / GFATM Voluntary Pooled Procurement has cited prices of: US$4.00 per LLIN and a further US$0.80 for distribution, and this is worth using for benchmarking in future. However there are caveats around whether this represents the full cost of procurement as it may not factor in the cost of HQ procurement and clearing costs. / Efficiency / Unit costs for the delivery of key SUNMAP outputs such as trained health workers and distribution of commodities. This can be disaggregated by State and mode of delivery. Capacity building costs by State are presented below: / Unit Costs of Capacity Building/Training by State / Year 3 Year 4 / State Workers trained Total cost (£) Unit cost (£) Workers trained Total cost (£) Unit cost (£) / Anambra 2,207 152,918.00 69.29 - 6,185 - / Kano 1,154 100,274.00 86.89 2,217.00 85,630 38.62 / Katsina 756 75,614.00 100.02 961.00 38,155 39.70 / Lagos 1,513 184,727.00 122.09 129.00 5,467 42.38 / Niger 798 90,312.00 113.17 1,908.00 89,666 46.99 / Ogun 626 94,069.00 150.27 690.00 141,668 205.32 / To assess the efficiency of capacity building as a major strategy for improving malaria control, the unit cost of training activities was measured by the number of workers trained at all levels of healthcare for malaria control services, from the original six SuNMaP supported states. / Unit costs per trained worker varied significantly between the states for both year 3 and 4, showing significant differences in the efficiency of training across the states. The significant decline in the unit costs from a cumulative average of £94 in year 3 to £61 demonstrated vastly improved efficiency in the delivery of capacity building activities. However it is noteworthy the consistent high unit cost recorded for Ogun state for both years as having the most expensive capacity building activities. This data has been useful for identifying the contributing factors and applying corrective action for instance seeking lower cost accommodation for training and seminars in Ogun State, and better scaling of net distribution capacity in Anambra State. / Contributing to the efficiency of capacity building is the SuNMaP procurement system which shows clear procedures for recruiting STTAs with ToRs and delivery of training programme for health workers. The procedure is applied in all the supported states. / Similarly to reduce cost while training more workers, SuNMaP makes use of Training of Trainers (ToT) for training more workers, reducing the effective cost of training per worker. Moreover not captured in the unit cost of trained worker was the use of SuNMaP ToTs by other partners for training more health workers in the different states, releasing money for other uses. This adds value to the programme and if captured will further reduce the unit cost of capacity building. / Unit costs (of output) of key interventions (Yr 3&4) / Intervention Volume Program cost Total cost (£) Unit cost (£) $ / A LLIN delivery / 1 Mass Campaign delivery 1,843,496 784,010.12 5,713,518.42 3.10 4.85 / 2 Routine delivery wt ANC 1,455,383 2,800,332 6,692,026.42 4.60 7.19 / 3 Commercial sector 1,362,769 2,898,144.08 6,542,188.39 4.80 7.51 / Total LLIN intervention 4,661,648 6,482,486 18,947,733 4.06 6.36 / B IPTp (SP) intervention 520,000 256,274 313,474 0.60 0.94 / The unit costs include the costs of all input resources (LLIN and SPs costs) expended in generating outputs in key interventions such as in LLIN delivery channels, IPTp preventive interventions (with SPs to pregnant women), and case management with ACTs. The unit costs of preventive and treatment interventions (outputs 3&4) also include expenditures of all the other outputs (1, 2, 5 and 6 as well the cost of M&E and management fees), which were adjusted for each of the interventions based on criteria that reflected the level of activities. Information on unit cost of ACT intervention was not complete during the period of assessment. / Unit costs of prevention interventions (LLIN and SPs) compared to international benchmarks. At $6.36 per LLIN delivered in Year 4, through routine delivery the unit costs fall below international benchmark which range between $9 - $13 [ ] per net distributed. Distribution through mass campaign as one the major channels appear to have the lowest delivery cost at $4.85 but information is limited on the actual costs of delivery due to contribution of other partners. It is expected that scale of delivery and cost sharing opportunities will lower the unit costs of delivery, increasing the efficiency of resource utilisation. / Commercial sector channel of distribution generates the highest unit cost of LLIN delivery at $7.51 apparently due to increased cost of communication and advertisement as part of demand creation activities. However, the efficiency of the channel will be better measured by the expected outcome/ impact based on utilisation, which will justify the high cost of the input resources. The value of the commercial sector will be better measured by the issue of sustainability and improved utilisation of nets. It is expected that where consumers have purchased a net they will be more likely to use it. / Cost effectiveness: / Cost effectiveness measures to be monitored include cost per malaria case averted, cost per DALY averted and cost per death averted of the various SUNMAP interventions,
J. Summary Value for Money Statement for the preferred option / The SUNMAP costed extension will accelerate the delivery of highly cost-effective malaria control through a tested and successful existing programme which has consistently been assessed as delivering value for money. The cost effectiveness of the interventions to be delivered in the SUNMAP extension is well established. Excluding non-quantifiable and non-health impacts, the SUNMAP extension will improve the overall cost effectiveness of the SUNMAP programme from $52 per DALY over five years to $30 per DALY over seven years.
[27] SUNMAP 2009, 2010 and 2011 independent annual reviews
[28] SUNMAP 2012 annual review report
[29] Largely copied from: Department for International Development, 2010. Malaria: Burden and Interventions. Evidence Overview
[30] National Guidelines for diagnosis and treatment of malaria. NMCP, FMoH, Nigeria. 2011
[31] Intermittent preventive treatment for malaria in children living in areas with seasonal transmission (Review) (2012) The Cochrane Collaboration. John Wiley & Sons, Ltd.
[32] Dicko A. et al. Intermittent Preventive Treatment of Malaria Provides Substantial Protection of Malaria in Children Already Protected by an Insecticide-Treated Bednet in Mali
[33] Konate A. et al. Intermittent Preventive Treatment of Malaria Provides Substantial Protection of Malaria in Children Already Protected by an Insecticide-Treated Bednet in Burkina Faso – A Randomised, Double-Blind, Placebo-Controlled Trial (2011). PLoS Medicine. Vol. 8 Issue 2.
[34] A Strategy for Behaviour Change Communication in the Roll Back Malaria Programme 2008-2012, Nigeria. FMoH, Dec 2008.
[35] Advocacy, Communication, and Social Mobilisation Strategic Framework and Implementation Plan, FMoH 2010
[36] National Malaria Strategic Plan 2009 – 2013, FMoH 2009
[37] Mwenesi HA. Social science research in malaria prevention, management and control in the last two decades: An overview. Acta Tropica Vol 93, Issue 3, 2005
[38] Hornick R. Public Health Communication – Evidence for behaviour change. 2002
[39] Seidel R. Behaviour change perspectives and communications guidelines on six child survival interventions. JHU/CCP and UNICEF, 2005
[40] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[41] Lengeler C. Insecticide-treated bednets and curtains for preventing malaria. Cochrane Database Syst Rev., 2004.
[42] Martin, F et al. Efficacy of Mosquito Netting for Sustainable Small Holders’ Cabbage Production in Africa. Journal of Economic Entomology 99(2):450-454. 2006
[43] Minakawa N et al. Unforeseen misuses of bednets in fishing villages along Lake Victoria. Malaria Journal, 2008, 7(1):165.
[44] Atkinson J et al. A qualitative study on the acceptability and preference of three types of long-lasting insecticide-treated bednets in Solomon Islands: implications for malaria elimination.
[45] Baume C et al. Factors associated with use and non-use of mosquito nets owned in Oromia and Amhara
[46] Banek K et al. Evaluation of Interceptor long-lasting insecticidal nets in eight communities in Liberia. Malaria Journal, 2010, 9(1):84.
[47] The MENTOR Initiative. Malaria control in humanitarian crisis training. Photo and PPT presentation, 2010
[48] World Health Organization, 2010. Inception meeting for the pilot-study project on sustainable management of long-lasting insecticidal nets throughout their life-cycle: REPORT
[49] Aurelie Bottelin. Sustainable Lifecycle Management of LLINs: Project findings and recommendations. World Health Organisation Global Malaria Programme.
[50] Ye et al.: Can universal insecticide-treated net campaigns achieve equity in coverage and use? The case of northern Nigeria. Malaria Journal 2012 11:32
[51] Excludes 4.1 million nets funded through the DFID PATHS2 programme but distributed by SUNMAP.
[52] Disability adjusted life year. A DALY is defined as one healthy year of life lost (YLL) due to premature death and/or disability from a disease. It measures the gap between current health status and an ideal situation where everyone lives into old age free from disease and disability.
[53] DALYs calculated using Stevens W and Jeffries D (2011). PSI Malaria Health Impact Estimation Model. Washington, DC: Population Services International. Available at: http://www.psi.org/resources/publications.
[54] DALYs calculated using Stevens W and Jeffries D (2011). PSI Malaria Health Impact Estimation Model. Washington, DC: Population Services International. Available at: http://www.psi.org/resources/publications.
[55] DALYs calculated from RDT DALY coefficient for Tanzania in 0-4 year olds using Stevens W and Jeffries D (2011). PSI Malaria Health Impact Estimation Model. Washington, DC: Population Services International. Available at: http://www.psi.org/resources/publications.
[56] www.who.int/choice/costs/CER_thresholds/en/index.html. Accessed 11 February 2013.
[57] data.worldbank.org/indicator/NY.GDP.PCAP.CD. Accessed 11 February 2013.

Commercial Case

Direct procurement through a contracted supplier

A. Clearly state the procurement/commercial requirements for intervention / The procurement process for management of the existing SUNMAP project has already been undertaken through competitive open tendering in accordance with the EU Public Procurement Directives. Contractually the preferred option would require a slight revision of the initial tender Terms of Reference to reflect an increase in duration. However, this would not necessarily require an increase in scope as the extension does not envisage major changes in methodology or broad approach. / The scale-up of the technical cooperation contract with Malaria Consortium (current value: £36,056,468) is within EU rules which specify that contracts awarded can be increased by up to 50% (additional proposed: £18,002,071) before they need to go out to tender again. In these circumstances, a direct single tender route with the existing supplier is justified unless poor performance or failure to agree on terms of engagement indicates that fresh market advertisement and a change of supplier is required. However, further negotiations at contract amendment stage with input from the DFID Procurement Group will further ensure economy and efficiency of proposed additional funding. / The commodity procurement component of the project will continue to be undertaken under the existing DFID Nigeria procurement agency core country framework agreement with Crown Agents. This will require effective engagement with manufacturers by Crown Agents, and issue by DFID Nigeria of a call down contract from the main framework.
B. How do we expect the market place will respond to this opportunity? / Programme management / We assume the Malaria Consortium, who implements this programme, will welcome an opportunity to extend their service provision to SUNMAP, and that they will wish to at least maintain the value of current prices for services and goods. / We will propose to offer a single tender route. This means that for the Malaria Consortium, the significant cost of bidding and use of unproductive time is now a sunk cost reclaimed in fees over the first year of the project, and this project is now a part of the Malaria Consortium’s portfolio. In these circumstances, we will wish to negotiate revised prices for fees and expenses that represent a reasonable incentive for the Malaria Consortium in exchange for a single tender opportunity, free of competition. We will also make it clear that the extension should not be an opportunity for the company to renegotiate in the time scales and resources necessary for the existing programme. In negotiation we trust that they will see the sense of our position. / Commodity Procurement / The procurement component of the extension is worth £21 million. Two thirds of this will be used to buy bed nets. Most of the rest is for anti-malarial drugs. There are eight registered bed nets manufacturers whose operations have been accredited by the World Health organisation. Three more may shortly obtain registration. Unfortunately, none are in Nigeria. There are several antimalarial manufacturers and four testing kit manufacturers accredited by the World Health Organisation and the local drug regulator. We have established through consultation and research that our new business will be large enough to interest the markets, although not significant enough to distort availability or interest any other potential new suppliers.
C. How does the intervention design use competition to drive commercial advantage for DFID? / Programme Management: / The intervention design anticipates that better value would be obtained by negotiating an extension to the current supplier’s contract. This judgement is based on: / the supplier’s performance so far; / the real and opportunity costs that would be incurred in returning to the market and potentially “changing horses in mid-stream”; / and the reality that unless it were common knowledge within the relevant market that the Malaria Consortium’s performance was below par, few if any other potential service providers would not judge the cost of bidding to be worth it, because we would be unlikely to make a change at this juncture in the life of the project and ultimately to do this would be at significant additional cost to DFID (e.g. set up costs and time, procurement). / Commodity Procurement / We have assessed our market position, applying the Kraljik Matrix. This is a cruciform that plots in four boxes a purchaser’s degree of market difficulty, and the purchaser’s importance to the market. The cruciform is like this: / HIGH / Degree of market difficulty? Do it ourselves or give up Strategic partnership: / Work together / LOW Non critical items: / Shopping; / Oral quotes Leverage / Competition and negotiation / LOW Importance of DFID to the market? HIGH / So the worst box to be in is High:Low. This means that DFID has a high degree of market difficulty, because there are few suppliers of what we need, and we are low in importance to that market. The best box is High: High, when we are important to the market, and there are plenty of suppliers. / Our assessment of the bed nets, ACT and RDT markets is High: High. We have noted above that there are a number of pre-qualified manufacturers. Our agents will seek to use competition among them to ensure high quality, at fully acceptable prices. If thought desirable, we could split orders between two manufacturers. This potentially increases delivery time, and reduces the risk of non-performance-if a supplier is in difficulties we could transfer our order to the performing supplier-but does carry risks of increased contract management time and cost, and miss volume discounts.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Programme Management: / These are: / Consultancy fee rates, where the specific factors are levels of responsibility, duration of engagement, difficulty of the post, credentials and CV ands past performance, unique issues related to the market position of each professional group, and regional or local market factors for national consultants; / Direct consultant overhead costs relating to the provision of a consultant (e.g. medical insurance, visas, etc.) / Indirect overhead costs. These will include amounts within each fee to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, Nigerian office, etc.) / The profit margin. / Our ability to influence the cost drivers is limited, although we have made progress in the past year in strengthening our negotiating position with our key suppliers. But living costs in Nigeria are high, and while insecurity continues, these become higher factors and a major driver of consultancy costs, as is the perception of Nigeria as a difficult environment to operate in. However, the project has been successful in adapting to difficult conditions, including by maximising the use of local staff and consultants. / Many of the results expected in the extension period involve leveraging the efforts of the Nigerian Government and other donors. In this context the experience and effectiveness of key consultants is paramount, value for money is not driven simply by least cost, but by the best ratio of effectiveness to cost, and this has to be assessed on a case by case basis. Whenever interventions are not delivering the expected results, and we assess that this is due to the limited effectiveness of individual consultants, we will either agree personnel changes or discontinue the intervention. / Commodity Procurement / Commodity procurement costs are largely dependent on international market conditions, with limited ability for DFID to influence this. However, measures that have been applied in the project include consolidating procurement volumes to achieve economies of scale, and ensuring, as much as possible, that standard product specifications are ordered. Project data (particularly for LLINs) reveals that costs have fallen through successive procurements when expressed in £ sterling. A key variable has been the £ to US$ exchange rate, given that most nets are procured in US$. Costs falling somewhat but less dramatically when presented in US$, as is shown in the table below: / DFID LLIN procurement / Quantities / (Million) UNIT PRICE / £ UNIT PRICE / US$ / 2008/09 0.5 £ 3.19 US$ 4.53 / 2009/10 1.0 £ 3.13 US$ 4.67 / 2010/11 0.7 £2.69 US$4.31 / 2011/12 2.1 £2.60 US$4.08 / GFATM Voluntary Pooled Procurement has cited prices of: US$4.00 per LLIN and a further US$0.80 for distribution, and this is worth using for benchmarking in future. However there are caveats around whether this represents the full cost of procurement as it may not factor in the cost of HQ procurement and clearing cost. / DFID RDT Procurement / Quantities / (Million) UNIT PRICE (excluding freight and delivery costs) / £ UNIT PRICE / US$ (excluding freight and delivery costs) / 2011/12 1.4 £ 0.21 US$ 0.33 / GFATM voluntary pooled procurement has cited weighted average unit prices ranging from $0.39 (for an order of 18.9 million tests) to $0.78 (for an order of 1.28 million tests). / DFID ACT Procurement / Quantities / (Million) UNSUBSIDISED UNIT PRICE / £ (excluding freight and delivery costs) UNSUBSIDISED UNIT PRICE / US$ (excluding freight and delivery costs) / 2011/12 1.2 £ 0.26 – 0.93, depending on the age group. US$ 0.4 – 1.45, depending on the age group. / The 2011/12 DFID ACTs were procured through the Global Fund’s Affordable Medicines Facility for malaria (AMFm) programme, which negotiated deep discounts with ACT manufacturers on a global basis. However, the AMFm programme is undergoing funding challenges, and there have been issues with order rationing and long delivery timelines for delivery of AMFm commodities. There is considerable uncertainty as to whether SUNMAP will be able to procure ACTs using the AMFm mechanism during the extension period. For this reason, we have budgeted for ACTs using a mean unit price of £1.6 (including all delivery costs), obtained through market testing of non AMFm ACT suppliers. However, we expect the large orders required and the competitive process will help secure better prices. If we are able to secure AMFm prices again, we will explore what additional opportunities that presents for commodity provision through this programme. / Market prices are generally driven by spare manufacturing capacity and competition among the registered suppliers. We are confident that prices would stay constant or even reduce during the life of the project, although we accept that if full commitment to the world wide supply of commodities materialised, prices might increase. / We will continue to assess the benefits and risks of various ordering approaches, from one order with agreed hedged prices and split delivery times, to separate orders, paying the price at the time of delivery. / On the anti-malarial drugs and test kits, we aim to procure in two or more batches.
E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention? / Programme management / We will liaise with the Procurement Group to write to the Malaria Consortium seeking a proposal for an extension to the existing contract, and emphasise that we are looking for a revision that reflects the factors set out above in section B. Once we have this we will meet to negotiate an outcome. Our emphasis will be on obtaining improved value for money for both parties (including proportional overhead costs, fee rates and expenses), without delaying the process of the next phase of work. / Annual audits of the SUNMAP programme currently present no issues on procurement. These audits also provide DFID assurance that SUNMAP follow the terms of conditions of the signed contract. / We will continue the quality-focussed approach so far deployed, but will seek the Malaria Consortium’s interest in an increased focus on payment by results, possibly by payment of higher fees for over-performance a mid-level fee range for standard delivery, and means to reduce fees in the event of under-performance and failure to meet the programme’s log frame targets. / Commodity Procurement / The commodities will be purchased though DFID Nigeria letting a call down contract from the core country framework with Crown agents. This would be underpinned by a memorandum of understanding between the Malaria Consortia and Crown Agents, setting out their requirements, quality needs, and timescales. Our assessment has assured us that Crown Agents has the capacity and capability to deliver a high quality service, although their across-the-board performance in 2011/12 was poor, and there were delays with delivery of ACTs and RDTs (though it appears that the problems with the ACT procurement may have been due to issues with the AMFm rather than Crown Agents). / The normal period from request to contract placement is two months. For LLINs, production normally takes six-eight weeks, shipping six weeks and clearing and distribution six-eight 6-8 weeks. Delivery times for ACTs are likely to be 8 – 12 weeks. Delivery times for RDTs, which have to be tested by WHO and the University of Lagos before delivery, are likely to be 12 -15 weeks. / The purchase is only part of the procurement life cycle. Logistics must be excellent. We will ensure that the Malaria Consortium and Crown Agents arrange effective distribution and storage at state level. For example, a contract for 5 million bed nets ordered in one shipment would require about 250 x 40 foot containers. We will learn from previous experiences of overstocking, and encourage strategic planning of distribution.

Financial Case

A. Who are the recipients of all proposed payments? / The lead service provider (Malaria Consortium) is the recipient of proposed payments under the technical cooperation component of the project. / Crown Agents is the recipient of proposed payments under the commodity procurement component of the project. Procurement agent fees will be as specified in the current core country agreement with Crown Agents.
B. What are the costs to be incurred directly by DFID? / The SUNMAP extension will require the sum of £39,002,071, consisting of / £18,002,071 for the technical cooperation component. / £21,000,000 for commodity procurement. / This will increase the cost of the SUNMAP programme from the current £50,000,000 over five years to £89,002,071 over seven years.
C. What are the costs to be incurred by third party organisations? / None
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / No
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / The programme will be funded from programme resources and has been budgeted for in the Operational Plan for DFID Nigeria. / There are no contingent or actual liabilities.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / Total 2008 - 2013 Sep 13 - Aug 14 Sep 14 - Aug 15 Total extension requested Grand total 2008 - 2015 / £ £ £ £ £ / PERSONNEL COSTS / Long term personnel 8,442,715 2,175,933 2,182,461 4,358,394 12,801,109 / Short term Capacity development 1,608,124 378,132 379,266 757,398 2,365,522 / ST Harmonisation 124,437 23,875 23,947 47,822 172,259 / ST Prevention of malaria 984,697 229,008 229,695 458,703 1,443,400 / ST Treatment of malaria 648,454 195,595 196,182 391,777 1,040,231 / ST Community awareness & demand 1,350,334 180,818 181,360 362,178 1,712,512 / ST Operational research 243,167 31,865 31,961 63,826 306,993 / ST M&E 211,766 43,595 43,726 87,321 299,087 / ST Technical Advisory Group 95,757 9,497 9,525 19,022 114,779 / TOTAL PERSONNEL COSTS 13,709,451 3,268,318 3,278,123 6,546,441 20,255,892 / PROJECT EXPENSES / Operations 4,370,848 1,117,712 1,121,065 2,238,777 6,609,625 / Activities 14,822,995 3,849,810 3,861,359 7,711,169 22,534,164 / TOTAL PROJECT EXPENSES 19,193,843 4,967,522 4,982,425 9,949,947 29,143,790 / TOTAL COSTS / Personnel 13,709,451 3,268,318 3,278,123 6,546,441 20,255,892 / Expenses 19,193,843 4,967,522 4,982,425 9,949,947 29,143,790 / 32,903,294 8,235,840 8,260,548 16,496,388 49,399,682 / Management Fee - ON PERSONNEL COSTS 23% 3,153,174 751,713 753,968 1,505,681 4,658,855 / TOTAL TECHNICAL COOPERATION COSTS 36,056,468 8,987,554 9,014,517 18,002,071 54,058,539 / PROCUREMENT Total 2008 - 2013 £ Sep 13 - Aug 14 £ Sep 14 - Aug 15 £ Total extension requested £ Grand total £ / LLINs (procurement) 7,254,000 13,851,270 13,851,270 21,105,270 / Sulphadoxine pyrimethamine (SP) 497,582 100,424 100,424 598,006 / Artemisinin combination therapy 1,058,043 5,309,322 5,309,322 6,367,365 / Rapid diagnostic test kits 460,674 1,612,653 1,612,653 2,073,327 / Other procurement 1,475,801 126,331 126,331 1,602,132 / TOTAL PROCUREMENT COSTS 10,746,100 21,000,000 21,000,000 31,746,100 / DFID RETAINED COSTS Total 2008 - 2013 £ Sep 13 - Aug 14 £ Sep 14 - Aug 15 £ Total extension requested £ Grand total £ / Independent reviews and audits, Procurement agent fees, port clearance costs and contingencies 3,197,432 0 0 0 3,197,432 / GRAND TOTAL COSTS Total 2008 - 2013 £ Sep 13 - Aug 14 £ Sep 14 - Aug 15 £ Total extension requested £ Grand total £ / GRAND TOTAL 50,000,000 29,987,554 9,014,517 39,002,071 89,002,071 / Prior to award of the amended contract, SUNMAP will produce a detailed budget covering the additional two years which includes, at a minimum: / Monthly estimates of costs expected within the current financial year. / Quarterly estimates of costs expected for the remainder of the current spend review period beyond the current financial year. / At the beginning of each financial year, SUNMAP will provide monthly estimate of costs expected within that financial year. Every quarter, SUNMAP will provide revised monthly estimates that take account of any contextual changes which are impacting on the ability of the project to meet previous forecasts. / Accurate forecasting will be ensured through monthly review of SUNMAP invoicing to assess the degree of variance from forecasts. The DFID Nigeria health programme officer will meet monthly with the project staff to ensure variances remain within a maximum of 5% of forecast.
G. What is the assessment of financial risk and fraud? / There are four key financial and fraud risks: / Risk of funds being misappropriated or not being used as intended. / Risk of diversion of DFID funded commodities. / Risk of loss due to reduced financial management and oversight in conflict areas. / Risk that expenditure does not represent value for money for DFID. / The following is an assessment of the key risks: / Risk Probability Basis for assessment Mitigation / Risk of funds being misappropriated or not being used as intended. Low Government systems in Nigeria do not currently meet DFID’s fiduciary standards. Consequently, no SUNMAP funds are passed through government systems. All technical support provided to government are directly managed by the service provider. / DFID commissions regular independent audits of the SUNMAP programme, and has conducted two audits since inception. The audit findings did not indicate any instance of deliberate fraud or misappropriation, but highlighted a number of internal control issues, which were subsequently addressed. For example, agreements with supported State governments (see below on commodities). / As part of processes leading to the award of a Programme Partnership Agreement (PPA) grant, DFID HQ in 2011 commissioned a Due Diligence Assessment of Malaria Consortium, the service provider for this project. The DDA did not reveal any critical issues, and the grant was subsequently awarded. No SUNMAP funds will be passed through government systems. / DFID will continue to commission regular independent audits of the SUNMAP programme. A new audit is planned in 2013. / Risk of diversion of DFID funded commodities. Low - medium The service provider has signed agreements with supported State governments, which stipulate some SUNMAP oversight over commodities provided by the project, allowing their use to be managed and monitored jointly with State health authorities. / DFID has provided assistance to improve inventory control and logistics management information systems for health commodities in the supported States. / DFID’s independent audits of SUNMAP include detailed verification and reconciliation of commodity utilisation and stock. Audits to date have not revealed any significant instances of diversion, but highlighted control issues which were subsequently addressed. SUNMAP will continue joint management and independent monitoring of the use of commodities. / DFID will continue providing assistance to improve the management of health commodities in supported States. / Independent audits will continue performing verification and reconciliation of commodity utilisation and stock. / Where inventory control and commodity management systems remain inadequate, DFID will consider the use of private storage providers. / Risk of loss due to reduced financial management and oversight in conflict areas. Medium SUNMAP, as with other DFID and donor programmes, has experienced some limitations with travel, particularly by international staff, to conflict zones. If security conditions in the conflict areas worsen, it could become more difficult to exercise sufficient oversight over operations in the conflict areas. However, SUNMAP’s head office is located in Abuja where majority of management and financial systems coordination takes place. Develop the ability of local staff, particularly in the conflict zones, to monitor SUNMAP financial operations in their areas. / DFID will continue to ensure, as much as possible, that independent audit teams visit all SUNMAP locations, including those in conflict locations. / Risk that expenditure does not represent value for money for DFID. Low All commodity procurement under the SUNMAP project is conducted using DFID’s contracted procurement agent using EU procedures. Assessment of procurement costs so far indicates unit costs are competitive relative to international benchmarks. / SUNMAP’s value for money analysis, which, according to the NAO, is the most advanced of any malaria programme in DFID, is enabling the programme (and DFID) identify value for money issues and address them. / The cost effectiveness of SUNMAP’s major interventions are well established. / Value for money assessments of the project, conducted as part of its annual reviews, indicate that project interventions represent value for money. DFID will continue to conduct value for money assessments of the SUNMAP project as part of its annual review processes.
H. How will expenditure be monitored, reported and accounted for? / Monitoring and accounting of expenditure will take place using the DFID’s ARIES financial management system and standard DFID Nigeria procedures for inspecting invoices to ensure VfM and compliance with agreed fees and reimbursement costs. DFID will rely on: / • Quarterly progress reports covering programme and financial issues / • Year-end statement of actual expenditure / • Independent annual audits of the programme / • Monthly invoice checks before payment. / Quarterly narrative and financial progress reports to DFID will include reports against the logical framework and agreed results. Expenditure will be monitored/validated against quarterly financial and progress reports. Progress and financial reports will be submitted within 30 calendar days of the end of each quarter. / DFID will conduct independent financial audits of the programme and ensure that SUNMAP maintain up to date asset registers. DFID will decide on the disposal of assets at the end of the programme.
I. Are there any accounting considerations arising from the project? / None

Management Case

A. What are the Management Arrangements for implementing the intervention? / Project management is primarily the responsibility of SUNMAP and the service providers, but with close collaboration between them and the DFID Health Adviser. Technical coordination and direction of the programme will be provided by DFID Nigeria’s Health Adviser. Project management support is provided by a Programme Officer within the Human Development (HD) Team. / DFID State Representatives liaise closely with SUNMAP at state level. DFID State Representatives have been appointed since late 2011 to represent DFID in DFID focus states, to ensure robust political dialogue and engagement with state governments and other counterparts; as well as to coordinate and assist DFID programmes in their work. / The project is managed by a management team led by an Abuja based Programme Director. The Programme Director, supported by a Deputy Programme Director and a Technical Director, leads the project’s engagement with DFID, the managing consortium, the project’s local partners and key stakeholders in Nigeria’s malaria control environment. State Team Leaders (STLs) in each SUNMAP supported State oversee project implementation in their respective States, report to the project management team, and lead engagement with DFID State Representatives, other DFID programmes in the State, and key malaria stakeholders. There are quarterly meetings of all STLs at state level to ensure coordination between the different programmes. / A programme management board, chaired by the DFID health adviser and comprising the DFID programme officer as well as the SUNMAP project management team, meets on a monthly basis to review progress and provide strategic direction. A commercial sector management board, which includes the above individuals as well as DFID Nigeria’s private sector adviser and the project’s commercial sector management team, meets on a quarterly basis to review progress with the commercial sector interventions. / Crown Agents will continue to be responsible for the procurement of commodities as agreed through the extension period. SUNMAP will continue to work closely with Crown Agents to ensure commodity requirements and specifications are agreed in time to meet delivery timelines. DFID Nigeria’s Procurement Adviser will also continue to work closely with Crown Agents and SUNMAP to ensure procurement processes use best practice and secure value for money for DFID. / The National Audit Office (NAO) recently carried out a value for money audit of DFID’s malaria control work. A case study of the SUNMAP project was included as part of the audit. A final report of the audit is not yet available, however the NAO team provided preliminary feedback on the SUNMAP case study. The preliminary feedback commended the design of the SUNMAP programme, its responsiveness to changing malaria priorities in Nigeria, its efforts on capacity building and harmonisation, and the value for money efforts within the project, but raised concerns regarding limited progress in areas such as the commercial sector and operational research. There was also more general feedback (regarding malaria control in Nigeria and not specific to SUNMAP or DFID) regarding insufficient usage of nets, the provision of malaria treatment without prior diagnosis, and the sustainability of malaria control efforts. The SUNMAP extension includes interventions targeted at all these issues to the extent feasible within the two year extension period. The 2013 annual review of the SUNMAP project will study the final report of the NAO audit, and consider implications for further adjustment of the programme design or interventions to address any outstanding issues.
B. What are the risks and how these will be managed? / The risk assessment from SuNMaP’s original Programme Memorandum has been comprehensively reviewed and updated for this Business Case. Risk mitigation measures have been identified with a particular focus on risks that have become prominent during the last five years since SuNMaP was designed. These include: / Political Risks (and Opportunities) / SUNMAP performance was impacted by a year-long public health worker strike in Anambra State in 2011-12. This was partially mitigated by additional work through faith based facilities. In other states the quality of engagement with state governments has varied: in Enugu, for example, low degree of commitment to reforming state health systems has been a cause of concern. Dynamic state leadership in Lagos is encouraging but has, on occasion, led to operational challenges. / There is an increased interest among African (including Nigeria) political circles around the scale up of malaria interventions, such as larviciding, that according to the World Health Organization, do not appear to be appropriate for the climatic and epidemiological context. There is a risk that limited Government funding could be spent on such interventions which may not provide value for money. / Given that SuNMaP is a technical programme, the extension will link more closely to PATHS2, SPARC and other state programmes especially around issues of financial management (including PFM reforms). / An intensified focus on opportunities for high level engagement (on model of DFID’s successful Family Planning leveraging) to attract national funds to fighting malaria, given malaria is a “unifying” disease in Nigeria due to its universality. Nigeria’s strong fiscal position, as evidenced by the 2011 IMF Article IV Consultation, highlights that funding is largely an issue of priorities. There is an on-going fungibility risk that DFID’s interventions in malaria simply enable the Government to reallocate necessary resources to other activities. However, the increased Government spending on malaria in Nigeria over the last few years, and plans for more funding going forward, do not bear this out. / Security Risks / Since the original risk framework security in Northern Nigeria has deteriorated, DFID Nigeria highlights the importance of maintaining and improving service provision in the North. Three out of four new states are located in the North. The 2012 annual review found that: / Roll-out to new states has been rationally planned in terms of linking to existing programmes; / Proposals about “SuNMaP Lite” to provide some support, (e.g. working where necessarily remotely in Yobe State) appear sensible, providing the risk of product and/or reputation dilution is minimized. / It is challenging to measure VfM implications of insecurity. Lessons from Afghanistan is that: i) Programmes take longer to deliver; and ii) Risks from patronage, financial irregularities etc increase as oversight deteriorates. SuNMaP will therefore avoid being over-ambitious and strengthen safeguards, including independent programme quality assurance and financial verification. / These important risks have been included in the completed risk assessment below. / Identified Risk Probability Impact Mitigation Measures Residual risk / Malaria fails to gain traction as an issue at a political level Medium Medium Potential to mitigate through high level advocacy, as DFID has successfully done regarding family planning. Explore scope to engage at Presidential / bilateral political level to raise malaria as a potential political issue. This has had some success, for instance in Kano State which has agreed to commit £25m for malaria this year. Stronger monitoring of SUNMAP MOUs with State Governments using DFID State engagement mechanisms. Medium / Political interest in inappropriate interventions diverts resources from more cost effective measures Medium Medium Continue high level advocacy, particularly through encouraging WHO to provide more technical evidence and advice. SUNMAP is also supporting better malaria epidemiological mapping to enable better targeting of interventions to epidemiological and climatic patterns Medium / Over-reliance on GFATM and World Bank inputs Medium Medium The World Bank Booster project is due to finish in 2013 and GFATM Phase 2 support in 2014. Highlights need for continued close engagement at HQ levels with Washington and Geneva to clarify follow-on proposals. There is a high probability of a funding gap from both programmes, justifying an expansion of commodity supply under SuNMaP extension. Low / Increased insecurity affects ability to implement the project. High (in some states) High i) Monitor closely; / ii) Avoid overloading programmes in insecure States; / iii) Develop low profile but frequent programme monitoring to ensure checks and balances are maintained in fragile states. / (iv) Encourage effective recruitment and training of local project staff with high local credibility. / (iv) DFID State representatives, advisers and DFID risk management office (RMO) proactively address potential security risks and mitigation responses. High / 7. Commodity quality is not adequately assured. Low Medium Reduce time pressure by avoiding procurement at the end of the financial year. / Ensure independent testing. / Procure from WHO prequalified suppliers. Low / 8. LLINs cannot be marketed in the face of competition from untreated nets and publicly funded LLINs Medium Medium i) Address inherent contradiction between free public nets and development of the private sector which undermines sustainability; / ii) Strengthen M4P approach especially regarding demand generation Medium / 9. Malaria parasites develop resistance to SP and ACTs Low Medium i) Reinforce steps to improve rational drug use and SuNMaP Operational Research components. Low
C. What conditions apply (for financial aid only)? / Not applicable
D. How will progress and results be monitored, measured and evaluated? / Programme results will be monitored by the DFID programme team against the programme logframe. SUNMAP’s performance will also be assessed by internal monitoring of the programme; by independent monitoring through annual reviews; and by an independent end-of-programme review. / The monitoring and evaluation strategy through the extension period will build on the strategy in place under the current SuNMaP programme and will comprise the following: / Routine monitoring as stand-alone programme workstream will continue as under the current programme. Monitoring will as far as possible be integrated into routine national health monitoring being conducted by the Federal Ministry of Health and State Ministries of Health. SuNMaP will submit quarterly summary reports to DFID documenting progress against the annual workplan, M&E framework and log frame in a template agreed with DFID. Key data sources include / The Demographic and Health Surveys (DHS), funded by USAID, Government of Nigeria, and several donors including DFID (through the PATHS2 project). / The Multiple indicator Cluster Surveys, funded by UNICEF, Government of Nigeria, and several donors including DFID (through the PATHS2 project). / The Malaria Indicator Surveys, funded by USAID and Government of Nigeria / Health Management Information System data obtained from the Federal Ministry of Health. / Special surveys, such as net retention surveys, consumer surveys and ACT watch funded by SUNMAP and other malaria implementation partners. / . . / Testing approaches to delivery in the Nigerian context through operational research as is currently ongoing. Given that, for the most part, the interventions themselves have strong evidence base (as outlined in the evidence section), SuNMaP will continue to invest in the series of operational research studies agreed to-date as some of these studies are likely to be ongoing into the extension period. New studies will also be conducted during the extension period. / The Seasonal Malaria Chemoprophylaxis pilot will seek to improve child health outcomes in Jigawa state through increased access to seasonal malaria chemoprophylaxis, most notably among the nomadic populations of Northern Nigeria. This pilot will aim to establish the effectiveness, cost effectiveness and feasibility of the intervention in the Northern Nigerian context, with a view to developing good practice guidelines and plans for possible scale up to other suitable parts of the North. / The pilot has four objectives: / To design, in consultation with key local stakeholders, an appropriate community-based delivery system for SMC in Jigawa state based on formative research which will review aspects relating to feasibility, community acceptability, effectiveness and cost / To launch and execute SMC delivery according to the selected delivery system and collect data on process indicators and costs / To evaluate community acceptability, costs and effectiveness of the delivery system for SMC / To inform future national and state plans for SMC continuation/scale up by disseminating findings and sharing experiences with key stakeholders. / The key audience for this pilot include local stakeholders, Nigerian state governments, particularly in the North, Nigeria’s Federal health authorities, health authorities in other countries with similar conditions, particularly the Sahel region, and the global malaria community. / Four Local Government Areas supported by SUNMAP in Jigawa State will be selected as the site for this assessment of SMC delivery with a target population of around 700,000-800,000. / Assessment methods to be used include: / Incidence (confirmed and suspected cases of malaria) to be measured via passive surveillance through the HMIS system / Reduction in parasite prevalence will be measured by cross-sectional surveys / Case control study will measure effectiveness of SMC treatment doses / An SMC delivery system will be assessed through a series of two cross-sectional surveys, review of HMIS data and qualitative reviews / A formal impact evaluation of the entire SUNMAP programme will not be undertaken in this instance as the evidence base for current SuNMaP interventions is strong as outlined in the evidence section.
Logframe / Quest No of logframe for this intervention: 3875151

References