Type of Review: Project Completion Review

Project Title: Apparel Lesotho Alliance to Fight AIDS (ALAFA)

Date started: 01/09/2008	Date review undertaken: 5-7 November 2012

## Introduction and Context
What support did the UK provide?
The UK provided a total of £4,475,000 over the period 2009-2012 to the Apparel Lesotho Alliance to Fight AIDS (“ALAFA”). The ALAFA programme, which has been operational since 2006, was initiated with seed funding from DFID and grew out of the Making Commodity and Service Markets Work for the Poor (ComMark) programme in Lesotho.[1] ALAFA addresses the impact of HIV and TB in Lesotho’s textile industry, a major employer in Lesotho, particularly of women. The programme provides prevention and treatment services for factory workers and their partners through a work-based scheme, thereby removing access barriers to healthcare. / ALAFA is a registered NGO and operates as a public private partnership. The alliance includes Government of Lesotho, donors, international brands, employee and employer associations and health service providers. The programme is delivered by non-government and private sector providers. Factory workers also play an important role in delivery. ALAFA services include: / Policy Development Support for factories, / Prevention (peer education, condom distribution, mobilisations) / Voluntary Counselling and Testing Prevention of Mother To Child Transmission, / Care and Treatment (Registrations, pre-HAART and HAART, TB and STI treatment, Medical Monitoring). / In 2010 DFID’s Bilateral Aid Review resulted in the decision to close the bilateral programme in Lesotho. DFID agreed to continue funding up to the point where ALAFA could secure medium-term core funding. In early 2012 GiZ agreed to support ALAFA with €2m until 2014 (this is administered through delegated cooperation with the EU). DFID provided £925,000 to cover the gap prior to GiZ funding. This bridging funding ended in October 2012 prompting a Project Completion Review.
[1] This programme aimed to support policy, institutional and operational initiatives that facilitate the development and improved operation of commodity and service markets for the benefit of the poor in Southern Africa. It included a focus on job creation in the textile and apparel industry.

What were the expected results?
This programme was designed prior to DFID’s new business case template. Expected results are drawn from the logical framework. The original project purpose statement was to: / Reduce absenteeism, morbidity and mortality among the workforce of Lesotho’s apparel industry by ensuring a comprehensive prevention, treatment, care and support programme within the workplace, especially for HIV positive employees and their dependents. / Expected Impact: Poor men and women remain healthy, productive and sustain their jobs and Lesotho’s apparel industry remains competitive. / Expected Outcome: To reduce absenteeism, morbidity and mortality among the workforce of Lesotho’s apparel industry by ensuring a comprehensive prevention, treatment and care and support programme within the workplace, especially for HIV positive employees and their dependents. / Output 1: A comprehensive prevention programme across the Lesotho apparel industry is established. / Output 2: A comprehensive treatment, care and support programme within the workplace for HIV positive employees and their dependents that is aligned to national policy frameworks and guidelines is operational. / Output 3: Constructive partnerships with stakeholders strengthened (movement towards increased local financial sustainability). / Output 4: Effective mechanisms to manage ALAFA established.

What was the context in which UK support was provided?
It was a key assumption in the original Project Memorandum that ALAFA would raise sufficient funds to ensure its long-term viability. ALAFA is truly an alliance – an innovative public-private partnership that has received funding from other donors, the Government of Lesotho and the private sector including 'brand' garment companies. Factories increasingly take social responsibility and welfare for their workers seriously and contribute in kind; some also pay for primary healthcare clinics. But this has so far not been at the level required to enable long-term financial sustainability. / The global economic downturn has impacted negatively on donor funding opportunities and other bilateral donors have left Lesotho. In light of the DFID’s withdrawal of bilateral funding from Lesotho the issue of financial viability is critical. The ALAFA team is making considerable efforts to leverage private and public funds in a tough financial climate.

## Section A: Detailed Output Scoring

Output 1: A comprehensive prevention programme across the Lesotho apparel industry is established.
Output score: A+ Output moderately exceeded expectation / Overall, the programme is comprehensive in its reach across the target population. This was around 40,000 at the start of the programme; however, numbers in the industry fluctuate. Of the 37,000 employees currently employed, 86% were covered by the ALAFA’s prevention activities by November 2012. ALAFA has exceeded three of its original targets on Output 1 (1.1, 1.3 and 1.4). Targets 1.2 and 1.5 have not been met but are subject to some measurement complications as discussed below. / Final results / 1.1: 20% increase in workers who are potentially willing to disclose their HIV positive status from a baseline of 50% to the target of 70% / Exceeded target: final result is 81%. Qualitative research also showed that stigmatising attitudes were virtually absent in the factories (2012 KAP survey). / 1.2: Increase in reported regular condom use with extra partner in multiple partner relationships to 90% from a baseline of 80%. / The KAP survey worded this indicator differently to the original baseline in order to conform with UNAIDS best practice on measurement of multiple concurrent partnerships. It is important to also note that this type of indicator has limited precision because it is self-reported by respondents. By way of context, a large proportion of women working at the factories are the head of household, being either widowed or having partners who are migrant workers. This may increase the likelihood of multiple partnerships. / In this instance a direct comparison with the baseline cannot be undertaken. However the KAP survey showed that just over a fifth (21%) of respondents had two or more sexual partners in the past year. Of those who reported more than one partner: / With partner 1: 68% normally use a condom / With partner 2: 80% normally use a condom / With partner 3: 69% normally use a condom. / The variance between the second and third partner is not statistically significant. The average rate of condom use for those with two or more partners would be around 76%. According to the consultants who conducted the analysis (Epicentre), a figure above 70% for condom use is high given that those having two or more partners are more likely to be in risky sexual encounters. Thus the original target of 90% was very ambitious. Also, the target in the log frame focuses on the behaviour of factory workers with multiple partners and therefore does not account for a reduction in the overall number of partners / In relation to the wider issue of condom use it is interesting to note that “Male and female condoms were noted to be widely available in factories and there was a high demand for condoms by both male and female employees” (KAP survey report p.29). Annual condom distribution numbers have also increased. In 2010 distribution was 2.08 male condoms per worker per month and 0.15 female condoms per worker per month. While distribution does not necessarily equal use, it is certainly a positive trend and these figures exceed South African targets on condom uptake. When asked about the main ways to prevent HIV 95% of respondents mentioned condoms and “three quarters of employees agreed that they had taken steps to prevent HIV during their most recent intercourse…the main strategy was condom use” (p.7). The KAP survey report concluded that “the sense that behavioural changes were happening among employees in general was perceived to be occurring and this is encouraging, as it suggests a change in social norms in relation to HIV risk” (p.34). / 1.3: Maintain KAP 2009 survey result of 75% of workforce having tested at least once for HIV. / Exceeded target: the final result is 88%. 67% of this group had tested in the past year and 41% of this group tested most recently in the factory. Of the 88% who have ever tested, most just wanted to know their status (66%) while 15% tested because they felt ill. / 1.4: 75% of pregnant HIV positive mothers complete Prevention of Mother To Child Transmission programme / Exceeded target: 98% of mothers on treatment completed the course successfully (ALAFA medical monitoring data October 2012). This refers to the number of HIV positive women who fall pregnant; who finish the course of prophylactic treatment and continue to formula feed the infant for nine months. / 1.5: 95% of employees report correct knowledge about HIV transmission and its prevention, answering at least 7 out of 10 KAP survey questions correctly from a baseline of 92%. / This question was also phrased differently in the 2012 KAP survey compared with the original baseline and so the final results are not directly comparable. Respondents were asked 12 questions of which six were easy to answer. Of the six harder questions, the question on male circumcision was excluded from the analysis as the subject is not covered by ALAFA. 88% of the six harder questions (excluding the one on male circumcision) were answered correctly. The KAP survey research concluded that “knowledge of HIV prevention among employees was overall high, considering that a fairly large proportion had low levels of education” and that “it is a credit to the work of ALAFA that a main source of HIV and AIDS information in the past years is derived from education in the factory” (p.32). The KAP also noted that general HIV knowledge was adequate, although some myths still prevail.
Impact Weighting (30%) / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N – not since June 2009

Output 2: A comprehensive treatment, care and support programme within the workplace for HIV positive employees and their dependents that is aligned to national policy frameworks and guidelines is operational.
Output score: A - Output met expectation / Good progress has been made against all targets in Output 2. The scheme is comprehensive, providing treatment for TB, STIs and family planning services for HIV-affected employees and also addressing prevention and stigma issues. According to the KAP survey report, “in factories where ALAFA is active, many of the key ingredients for an effective workplace programme are in place” (p.7). ALAFA has also been held up as a best practice example: / Lauded as best practice in the UNGASS 2008 report / Won the South African Trust Drivers of Change Award for the Business Category / Commended in the 2009 Business Excellence Awards of the US-based Global Business Coalition on HIV/AIDS, Tuberculosis and Malaria / Won the 2011 International Health Promotion Award in the workplace category. / ALAFA has strong government ownership: Government of Lesotho’s Ministry of Health plays a key role in delivery of the treatment and prevention component through providing ARV drugs and laboratory testing services. Government has also seconded and pays for two senior counsellors working directly with doctors on the ALAFA programme and provided training for nurses and counsellors. Primary health clinics are based in factories where private doctors and nurses employed by ALAFA team up with factory-based peer educators, counsellors and “expert”[2] patients. The programme provides a much more accessible service than would otherwise be available to factory workers through the public healthcare system, who would otherwise risk losing a day’s wages queuing at a government clinic. / Relations with Ministry of Trade have been positive, although the project advisory council has not met since February prior to the general election in July 2012. Civil society organisations interviewed expressed concern over lack of government coordination on HIV/AIDS since the National Aids Council shut down. It was considered to be “top heavy” with little presence in the districts and did not appear to have a clear mandate. However the recommendation of the present Prime Minister is that the National Aids Council will re-open and is likely to focus on monitoring and evaluation, resource mobilisation and development of national policies. Although it was not possible to interview a government representative for this review, the KAP survey report indicated that “the work of ALAFA was seen as complementing and adding to the efforts of government” (p.29). / Final results: / 2.1 % of registered patients lost to follow up (death/drop out/ confirmed defaulter/ transfer) does not exceed 12%. / ALAFA currently loses 16% of clients to follow up. Although the target of 12% has not been met, this result should be considered in light of the fact that in Lesotho 37% of patients are typically lost to follow up. The original target was adopted from the World Health Organisation’s international standard. Contract workers in Lesotho’s factories may return to rural areas or pass over the border in to South Africa where they do not seek, or cannot access, treatment. This context makes the target particularly difficult to meet. (The issue of HIV and migration is itself an important issue for regional programmes to address). Losing track of people on first-line HIV treatment is problematic as poor adherence dilutes the efficacy of ARV drugs and second-line treatment is considerably more costly. ALAFA is forging relationships to help tackle this problem, for example through the organisation Lesotho Network of Aids Services Organisations (LENSAO) which has been tasked by the Ministry of Health to follow up on patients lost to follow up. This target has not been achieved although good progress has been made in comparison to the Lesotho national average. / 2.2 25% of employees are members of support groups and regularly attend support group meetings at the workplace / Notwithstanding the original target, good progress has been made in this area as support groups are active in all factories. According to the ALAFA team, such a large support group population is not needed and smaller groups are more effective in providing support to HIV positive people. 25% was thus an ambitious, and arguably inappropriate, target. Support groups have been formalised and registered in all factories. There are currently 1,200 support group members in factories that have care and treatment programmes covering a population of around 34,000 workers. / 2.3 Referral systems between different caregivers and to home-based care established. Target: ALAFA patients are linked with Government of Lesotho system: / This target has been met. ALAFA routinely issues clients with medical documents when they are transferred to government, and vice versa. Patients do not always continue with treatment at their destination and the ALAFA team working with government on ways to close this loop. / ALAFA follows the national guidelines for HIV care and ALAFA’s Medical Director also sits on the government technical working group. ALAFA operates customised electronic patient monitoring that provides tools for patient follow-up and most doctors in the network of service providers are linked to ALAFA’s central database. Referral systems linking ALAFA and the public healthcare sector are also operational. In 2012 ALAFA commissioned an M&E Audit Report to assess medical data quality. This confirmed that ALAFA doctors were familiar and knowledgeable about the Ministry of Health policy guidelines on the testing and treatment of HIV and AIDS and have adhered to statutory requirements (p.23). Thus, in terms of policy and practice the programme can be said to operate to a good standard. The picture on data was more mixed. The report found that “generally ALAFA service providers regularly and consistently produced HTC, STI, TB/HIV integration and PMTCT programme data during the period under review. However the same could not be said about the [data for] the Care and Treatment facet”. ALAFA is working with service providers to further improve data systems. / Other issues arising / The issue of equity for HIV negative factory workers arose during the review. HIV negative individuals cannot access health services at work free of charge, unless the factory is one which provides primary health care. This observation is supported by the KAP survey report which notes that “the clinical services provided to support PLW HIV were valued by employees; although there were concerns that general medication was not available to those who were HIV negative” (p.30). Although it is not the purpose of ALAFA to treat HIV negative employees, some are still affected for example through caring for family members. Others are affected by health complications following illegal abortions linked to lack of family planning access, or insufficient resources for the care of infants who fall sick. As concluded in the KAP survey report “employees who are presently HIV negative have different needs in relation to HIV and AIDS in comparison to those who are living with HIV” (p.7) and furthermore that “attending the clinic might also create an association with being HIV positive.” ALAFA recognises the potential risks of these stigma equity issues. These are also important lessons which could be more widely shared with other HIV treatment and care programmes.
Impact Weighting (30%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N (not since June 2009, prior to which it was low risk)
[2] Patients who have the skills and confidence to manage a medical condition in partnership with health professionals and can provide support to recently diagnosed patients in how to live with the condition or illness.

Output 3: Constructive partnerships with stakeholders strengthened (movement towards increased local financial sustainability).
Output score: B – Outputs moderately did not exceed expectation / ALAFA is an innovative and successful public private partnership. It has potential to be replicated in other contexts; and indeed many of those interviewed emphasised the need for a similar scheme in other sectors. The model is an effective delivery model for HIV prevention and treatment services in the workplace. However, the issue of financial sustainability would need to be resolved before considering wider replication. ALAFA needs to become a locally embedded, rather than donor funded programme. Although future partnerships are being explored by ALAFA this has not yet resulted in any concrete commitments from industry or government. / It is critical that a decision around the future of the programme is taken soon to allow time for transfer of patients on HIV treatment to the public system as a last resort. The wider picture (at present) looks reasonably good with 61% of eligible people on treatment, death rates dropping and increased funding[[1]]. However, the transition of financing from international to national sources is fraught with difficulties. While Lesotho provides healthcare to all its citizens, the critical issue is making such services accessible to factory workers as this population, while the most at risk, is also the least likely to seek health care in the public sector. The possibility of losing the most vulnerable to treatment is high and this would need careful monitoring. Furthermore, according to the EU, the public healthcare system doesn’t currently have the capacity to absorb factory workers and offloading them from ALAFA could adversely impact on the wider healthcare system.
Final results: / 3.1 Project Advisory Council (PAC) revitalised with meeting in August and December 2011 / This target has been met. The December 2011 meeting was moved to February 2012 (Hilary Nkulu, former Deputy Programme Manager at DFID Southern Africa, attended this workshop). Historically, the Project Advisory Council has been chaired by the Ministry of Trade and Industries, Cooperatives and Marketing. PAC meetings were held in 2011 however no further meetings were held in 2012 due to the elections. ALAFA has asked the new Minister of Trade to continue to hold the post but has not yet received confirmation of this. / 3.2 Wage levy agreement operationalized by January 2011 / The milestone of broad and in principle support by March 2011 has been met in the sense that industry is very supportive of ALAFA. But beyond this, no concrete progress has been secured despite best efforts of the ALAFA team. Although the garment industry is keen for the programme to continue it is not yet willing to pay a levy. / Cost-benefit analysis commissioned by ALAFA covering the period 2008-13 showed that if the Lesotho apparel industry as a whole contributed up to 60% of the total programme costs, this would still create a net saving to the industry. Industry is cooperative and already contributes in kind by allowing staff time off to participate in the programme and providing basic clinic facilities. 5 out of the 29 factories that have a clinic on site employ a nurse to provide primary healthcare at the factory clinic. The KAP survey report noted that “most employees agreed that management at the factory cared about preventing HIV among employees” (p.6). ALAFA is now trying to persuade the industry to contribute 15% (9 Maloti per worker per month). Those factories that have been in Lesotho for longer are generally prepared to invest more. However, at factory level there is increasing focus on cost reduction due to competition and the factory manager interviewed explained that the apparel industry does not expect to own ALAFA as it views HIV prevention and treatment as a government responsibility. / One possible option would be to shift some of the primary healthcare resource that around a third of factories already fund in to the ALAFA programme i.e. to combine factory-funded clinic funds with ALAFA resources. The ALAFA team is currently scoping out different delivery models that would enhance the cost-effectiveness of the programme (see section 5). / 3.3 Principle agreement on partnership towards sustainability of programmes created with Ministry of Health and Social Welfare. / Since the July 2012 election in Lesotho, health and social welfare functions have split and the main actor involved with ALAFA is the Ministry of Health. Although it was not possible to meet with any government ministers or officials during the PCR visit, the ALAFA team feels that the political climate is ripe for increase government support towards ALAFA. However, government is reluctant to commit additional funds until the industry associations agree to shoulder some of the cost of ALAFA. ALAFA is seeking to convene talks between government and industry although since the election securing meetings with government has not been possible. Ten garment brands appear in the original log frame; however only three have actually contributed to ALAFA (Gap, Levi-Strauss, Walmart).The contribution of brands is necessary but not sufficient to fund the programme. / It should also be noted that ALAFA’s Memorandum of Understanding with the Department of Health has expired and the the ALAFA team is working on its renewal. Although this issue is not currently affecting ALAFA’s operations, it provides the necessary permissions, access and tax exemptions for the programme. / Impact Weighting (20%): / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N
[[1]] Lesotho Global Aids Country Progress Report Jan 2010 – Dec 2011, pg. 74

Output 4: Effective mechanisms to manage ALAFA established
Output Score: A - Output met expectation / ALAFA is managed by a core of staff under the oversight of a management board. An advisory council brings together the interests of the Ministry of Health and Ministry of Trade, labour and industry association, donors, the National AIDS Commission, international brands, employees and employer representatives and service providers. Over the funding period ALAFA has developed a strong alliance and the organisation also has an active board of trustees. The governance of ALAFA is strong, although could perhaps be further strengthened by greater representation of beneficiaries in programme governance, for example through the opportunity to join the board of trustees or observe meetings. Currently Peer Educators and HIV coordinators (who are also factory workers) have opportunities to provide feedback directly to ALAFA staff on behalf of colleauges and ALAFA also meets regularly with union officials.
Final results: / 4.1 Repeat KAP survey by March 2012 and preliminary results available: / This target has been achieved. The KAP survey was undertaken and findings have been used to inform this project completion review. Section 3.2 contains further detail. / 4.2 % of private service providers using “bookwise” invoicing system increases to 30% / Bookwise is a medical electronic record system that collects patient level data. The proportion of private service providers using it has not increased as ALAFA is expanding the system to include more data e.g. the PMTCT programme. New modules were installed by the end of November 2012 as anticipated and users are being trained on the new system before it is rolled out. Thus while the target has not yet been met it is well on track. / 4.3 Main administrative financial is shifted to the European in transition to sustainability phase / This target has been achieved. GIZ is now providing €2 million until 2014. / Figures show that DFID has funded just under half of annual ALAFA expenditure over the period 2009-2012[3], where the total budget takes in to account cash and in kind contributions. Thus Government of Lesotho funds 42% of the programme with the remaining 9-11% coming from other sources. DFID funding has been used for all programme components (prevention, care and treatment and core funding) with a higher proportion used for core funding. ALAFA’s figures for 2012, where the budget totals ML48 million, show that the programme is currently 55% donor funded. ALAFA’s vision is to rebalance this to reduce dependence on donors by increasing public sector funding up to 79% with a private sector cash contribution of 15%. / 4.4. ALAFA programming and administrative costs are maintained at a minimal yet effective level. / ALAFA has kept costs within approved budget for each year. Staff salary costs have been benchmarked to be competitive yet comparable with similar organisations. Programming costs – in particular HIV treatment - are relatively high as private doctors are employed by ALAFA. This does however need to be seen in light of the fact that there are very few public sector doctors in Lesotho (45 Basotho doctors on the medical registers or around 160 including expatriates). A cost-effectiveness study which aims to compare different delivery models (e.g. different ratios of doctor/nurse inputs and different ways of contracting doctors) has been commissioned, with the expectation of reviewing and reducing programme costs. This is discussed further in section 5. / Impact Weighting (20%): / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[3] Note that some in kind contributions are based on estimates as ALAFA has only recently costed the in kind contribution.

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the log frame been changed since the last review? Y/N / No. / 1.2 Final Output score and description: / Final Output Score: A - Output met expectation / The ALAFA programme has exceeded expectations in many areas of its work. A comprehensive and effective treatment and prevention programme is now operational in Lesotho’s apparel industry. However, until financial sustainability has been achieved a higher output score cannot be justified.
Direct feedback from beneficiaries / The 2012 KAP survey included qualitative research which has been used to support the findings of this project completion review. The Results and Evaluation Adviser talked to staff (nurses, counsellors, doctors) and beneficiaries (peer educators, support group members, recipients of treatment) during Project Completion Review visit (sampling was purposive and two factories were visited). Respondents were asked to describe their roles, what they enjoyed about their job and what they found challenging; what support they received and their hopes for the future. The following themes featured prominently in the discussions and these findings have been triangulated with the KAP survey. / The interviews and focus groups revealed strong engagement of ALAFA staff and beneficiaries with the programme: / [I became a peer educator] to increase my own knowledge, enjoy teaching people, to help people who don’t know their status because I enjoy it” [female peer educator] / I enjoy listening to people. Seeing progress in someone [female counsellor] / My role is to assist those who have infection. A pool [of people] is moving around to support others e.g. person with TB, helping them wash clothes and with cooking. The support group has 30-40 members and meets weekly [male support group member] / Benefits of the programme ranged from knowledge acquisition to treatment for and reduced absenteeism: / Helped me as gained knowledge without paying. Very good training [male peer educator] / Before ALAFA people were sick and dying…some people were afraid to talk about their status….the programme has helped to control absenteeism [factory HR Manager] / I have gained so much knowledge about how to protect myself… In August 2011 I had a baby while taking prophylaxis and treatment during labour. The baby also received treatment. My child tested HIV negative after two months. I have been open with co-workers, told them about my status, encouraging others [to be open]. I have not come across stigma – others say I look “fat” [i.e. healthy]. [female client receiving PMCTC treatment] / Challenges faced related to overcoming traditional beliefs, working with specific groups (men, older people) and lack of health services for HIV negative people. / We still have challenges. Very little time with co-workers. Working with elders is also challenging [male peer educator] / An ongoing problem is that men are reluctant to talk. They want to be seen as strong and withstand the pressure [Factory HR Manager] / Most people don’t believe in ARVs. They prefer to use herbs. [male support group member] / A problem with the service relates to HIV negative clients. They have to pay a small charge for medicines [e.g. for family planning, STI treatment]...This distinction could leave to reverse stigma [female doctor] / There was considerable demand for expansion of the programme: / To extend the programme as people’s lives are in danger [female peer educator] / [I hope] To educate younger people and expand [the programme] to the whole nation. Very happy with the programme [female counsellor] / I want to see ALAFA covering the whole country. I want to thank ALAFA: if it wasn’t for the project, some people could have died [female client on the PMCTC programme] / These interviews and focus group discussion support findings from the KAP survey that employees do not hold stigmatizing attitudes; that peer educators are able to answer people’s questions; and perceptions that the death rates of employees had decreased as a result of ALAFA (p.29). They also confirm that knowledge around HIV is good but misunderstanding still occur and concerns exist that healthcare is not available to HIV negative people (p.30).
Overall Outcome score and description: / Expected Outcome: To reduce absenteeism, morbidity and mortality among the workforce of Lesotho’s apparel industry by ensuring a comprehensive prevention, treatment and care and support programme within the workplace, especially for HIV positive employees and their dependents. / Final outcome score : A+ - Outcome moderately exceeded expectation / This programme has demonstrated strong performance at outcome level and exceeded the original expectations, as demonstrated through performance against the outcome indicators. / Outcome indicator 1: % of employees in factories with legally compliant and active HIV & AIDS workplace programmes reaches 70% by March 2012. / This target was exceeded. The target was reset in 2011 to take in to account the fact that some factories had policies which were not up to date. By the end of October 2012 81% of employees within factories that the project works in met this target (this had increased to 95% by January 2013). It should however be noted that factories that the project works with cover only 86% of total employees in the apparel industry. / Outcome indicator 2: The annual survival rate of patients is 90% and above. / This target was exceeded. Survival rates are consistently exceed 98% (ALAFA medical monitoring data). / Outcome indicator 3: Increase in the number of workers accessing medical services for HIV (including HAART) reaches 7,150 by March 2012. / Total number of workers ever registered: 8,000 (March 2012 figure) 9,000 (October 2012 figure). / Current patient numbers with constant follow up: 5,507 (March 2012) and 5,800 (October 2012) Note: these figures includes both HAART and pre-HAART patients. / This indicator does not however account for the mobility of the worker population. In terms of total numbers of patients ever registered, the target has been reached. If migration and other reasons for losing patients to follow up are taken in to account, the target has arguably not been reached. As the programme has put significant numbers of patients on to treatment it is judged to be successful against this outcome target. / Outcome indicator 4: 10% annual increase in uptake of HIV treatment from 50% in 2007 to 70% by 2010[4]. / The level of uptake is 90% and so this target has been exceeded. It refers to the percentage of people eligible for treatment who access treatment (i.e. those with a CD4 count above the recommended level at which treatment should begin). Around one in ten clients refuse treatment: reasons include being in denial, using herbs instead or consulting ancestors. / Outcome indicator 5: % of HIV infected infants born to HIV positive mothers on the PMTCT programme does not exceed 10%. / The target has been exceeded as this figure is consistently below 2%. / Impact and Sustainability / Expected Impact: Poor men and women remain healthy, productive and sustain their jobs; and Lesotho’s apparel industry remains competitive. / Despite some problems with the impact indicators, overall this project can be described as impactful. Although the KAP survey research did not build in direct comparison of factories with and without the programme or a longitudinal cohort study, it is a fair assumption that the positive impacts on health and absenteeism at individual and factory level have occurred due to the programme. The evidence base around the effectiveness of properly administered HIV treatment at reducing mortality and morbidity is very strong. In a context where HIV treatment is not readily accessible to factory employees (although around 10% of HIV positive factory workers still use the public healthcare system to preserve their anonymity) it is reasonable to assume that the results were achieved through this intervention. / Impact indicator 1: HIV prevalence for factory workers reduced by 10% to 31% by March 2012. / This was not an appropriate indicator to measure the impact of this project. Any treatment programme is unlikely to reduce prevalence because as people access treatment they live longer. Thus prevalence rates can even rise due to effective treatment. Furthermore, the factory population is constantly changing as employees leave and new workers – some of them HIV positive – join. The figures show that HIV prevalence in the factory populations has remained high but stable at 42% in 2012, peaking amongst women aged 35-39 (n=2,800). / Impact Indicator 2: Absenteeism due to medical reasons is reduced by 30% cumulatively by 2011 / There is a lack of quantitative data in factories on this indicator. However, anecdotal evidence from factory managers indicates that absenteeism is much lower since the introduction of ALAFA having previous been around one quarter or one fifth of workers. According to the KAP survey qualitative research “there was a general perception that death rates of employees had decreased as a product of the ALAFA programme, with employees testing for HIV and receiving ARV timeously” (p.29). A sophisticated system would be required to identify absenteeism (e.g. for different illnesses and to record time off to attend funerals or when a child is sick) and there are limits as to what could be accessed from factory records. This could however be an area of measurement for ALAFA to build in to new agreements with factories to provide more robust evidence around reducing absenteeism and morbidity.
[4] It is unclear why this indicator stopped at 2010 in the log frame

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y/N / Project costs have stayed within the expected DFID budget and any monthly variance on costs has been closely monitored by ALAFA. This project will continue even though DFID is not continuing to fund it. / 2.2 Key cost drivers / The man cost driver is the direct medical costs of care and treatment component of ALAFA which employs private doctors to provide services. This is discussed in section 5 below. / 2.3 Was the project completed within the expected timescale: / As discussed in earlier sections, good results have been achieved against most of the targets in the DFID project log frame. The project is continuing with core funding from GiZ and expecting to transition to a long-term delivery model.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / There are no major changes in evidence which had implications for the project. There is still a lack of robust evidence on what is effective in preventing new HIV infections. ALAFA was arguably ahead of its time in combining prevention activities with treatment and care in one comprehensive programme, which is now considered to be best practice. / 3.2 Set out what plans are in place for an evaluation. / A comprehensive outcomes report was produced in June 2012. A quantitative Knowledge, Attitude and Practice (KAP) study provided robust evidence about the effects of the project to date. This included an HIV seroprevalence survey, a KAP questionnaire and qualitative focus groups in 15 factories which were sampled in 2007, 2009 and 2012. This survey was robust, however it should be noted that some of the measures are self-reported (for example around behaviour change) which limits the overall validity of some findings.

4. Risk
4.1 Risk Rating (overall project risk): Low / Did the Risk Rating change over the life of the project? N / 4.2 Risk funds not used for purposes intended / Good financial controls and supporting documentation are in place for this project. Annual audits are undertaken by external auditors and no irregularities have been reported. / 4.3 Climate and Environment Impact / The prevention component of the programme includes guidance on appropriate condom disposal. ALAFA trains peer educators to discuss disposal of condoms in their demonstrations. Follow up with peer educators takes place and at times they are also observed in their work so ALAFA is confident that they communicate condom disposal. It is not possible however for ALAFA to know whether people do actually dispose correctly of condoms following use. / All medical waste generated by the programme is disposed of properly in hospital incinerators. Medical waste is disposed of in a standard way. All procedures in ALAFA clinics strictly follow the national guidelines on what instruments, tools and disposables must be used in each treatment or test. / No new structures have been built through this programme – all clinics are within existing factor premises. / Carbon emissions from running a small office and two project vehicles. ALAFA encourages staff to use vehicles efficiently, for example through coordinating travel schedules ahead of time wherever possible. To date no carbon or environmental audit has been conducted.

5. Value for Money
5.1 Performance on VfM measures / 11% of ALAFA’s total budget is used for cross-cutting activities[5] (including administration) and the remainder covers prevention or treatment/care organisations. This compares favourably with other civil society organisations (where 15-20% overheads is the norm in South Africa). Value for money measures were not tracked as this programme which predates DFID’s focus on value for money. If the ALAFA team are able to develop any retrospective metrics e.g. average cost per beneficiary treated this would be valuable. ALAFA has meanwhile commissioned some costing analysis which is discussed below in section 5.4. / 5.2 Commercial Improvement and Value for Money / Staff salaries are benchmarked to be comparable with similar organisations. Doctors’ fees are also benchmarked to similar private sector rates to remain in line with market rates. ALAFA invoices most delivery partners on an activity basis and good practices are in place around procurement e.g. obtaining three quotes for goods and services. / 5.3 Role of project partners / A wide range of project partners are involved in delivery of ALAFA. These include garment factories themselves, Government of Lesotho (health services as well as ministries), Population Services International (PSI) which supplies condoms, other donors (public and private sector), and civil society organisations supporting prevention activities. / 5.4 Did the project represent Value for Money : Y/N / It is difficult to make an overall judgement on value for money where metrics have not been tracked throughout the programme. Overall it the programme has clearly demonstrated its effectiveness and administrative costs have also been well managed. However, due to the costs of contracting private doctors it is not clear that the current model delivery model is the most efficient way of delivering services. Programme costs have delivered strong results and, with a modified delivery model, could be potentially stretched further. ALAFA has commissioned costing analysis to explore alternative models “Cost effective study on model of health care service delivery” ( this is in inception phase). Models being costed include: / Factory employed nurses and private doctors / Factory employed nurses and ALAFA employed doctors / Factory employed nurses and MoH supported doctors / MoH supported nurses and ALAFA employed doctors / MoH supported nurses and rotating private doctors paid by ALAFA/MoH / ALAFA employed nurses and private doctors / ALAFA employed nurses and doctors / ALAFA employed nurses and MoH employed doctors. / Either factory employed nurses and ALAFA employed doctors OR ALAFA employed nurses and doctors is likely to be the most cost-effective delivery models. Outcomes at society level (i.e. how the chosen delivery model could affect distribution of already scarce medical skills in Lesotho) should also be a consideration. ALAFA had looked at placing nurses (provided by Ministry of Health and managed by ALAFA) in all of the factories. However the team is cautious about reducing availability of healthcare workers in the public sector. To date, using private sector doctors has not been problematic as they support ALAFA’s work while also maintaining private practices. Another option is to staff clinics with nurses, provide them with more training and work with the three rotating doctors to consult on difficult cases to avoid taking doctors away from other work.
[5] Activities included under cross cutting are: fixed assets; operating costs (rent, insurance, communications etc.);admin salaries; marketing and fundraising; and monitoring and evaluation (e.g. KAP study).

6. Conditionality
6.1 Update on specific conditions / Not applicable to this project

7. Conclusions
This is a highly successful project, combining factory policies on HIV and prevention and treatment in one comprehensive package. The pivotal role of the peer educators, healthcare provision in the work place and the broad partnership comprising private sector, government and civil society characterise ALAFA’s innovate approach. ALAFA is now well established and is highly regarded by partners and beneficiaries. The programme also has a strong governance structure which could be further strengthened by greater beneficiary participation. / However working out a model for financial sustainability, and in particular agreeing greater financial support from the private sector, remains a challenge. During an interview for this PCR, the EU representative was uncertain about the EU’s investment in HIV/AIDS in Lesotho beyond 2014 as the new European Development Fund is very rigorously defined to support other sectors. On the other hand, the EU is currently funding increasing investments in HIV/ADS health systems in Lesotho. Furthermore, now that GiZ (through delegated cooperation with the EU) has taken on direct funding of ALAFA’s HIV treatment and care programme they will be obliged to continue this until such time as they have agreed a robust plan for transitioning care to institutions with secured long term funding. Adequate monitoring and backup arrangements (e.g. through CSOs) will also be required to ensure that the most vulnerable continue to access quality treatment. This is critical to enable the achievements of the project to be continued and possibly replicated elsewhere. (Through the Foreign Office connection, DFID could provide lobbying or brokering support for example by writing to potential funders, should this be required). / ALAFA could benefit from a more robust evidence base on programme effectiveness and cost-effectiveness to help convince the garment industry to increase its financial contribution. One option could be to seek research funding from an academic partner to further test the effectiveness of ALAFA, for example through testing and comparing different delivery models in factories. Including cost benefit analysis as part of this could help make the case to factory management and other stakeholders to increase investment in programme.

8. Review Process
Esme Gaussen, Results and Evaluation Adviser for DFID Southern Africa conducted a desk review of documentation and travelled to Maseru to carry out this review. She interviewed ALAFA staff, clinic staff, factory managers and employees in two factories and also discussed the project with key stakeholders in country (EU delegation, GiZ, USAID and the NGO Phela).