Type of Review: Annual Review

Project Title: DIÁLOGO – Democratic Governance Support Programme

Date started: 14/10/2010	Date review undertaken: Feb – Mar 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK provides financial and technical support to a range of non-governmental organisations and groups, including urban communities, civil society organisations, policy orientated think-tanks and the media. The support will help these groups to improve the accountability and responsiveness of government at municipal and central level. Through the support received the groups will be able to aggregate, articulate and press the issues that are the priorities for the women, men and youth of urban Mozambique. UK support will help improve communication in focal urban municipalities, namely Maputo, Beira, Quelimane, Tete and Nampula, to ensure that local priorities and concerns are incorporated into government planning at the municipal level, and become a part of the agenda at the national level. Women, men and the youth in target cities will be able to establish channels through which the locally identified priorities for their development can be represented in municipal planning processes and documents. The support provided by the UK will facilitate the space, skills, and human, technical and financial resources for this process to gain traction. This is done through the DIALOGO Programme (the Democratic Governance Support Programme).

What are the expected results?
The overall vision and mandate of the program is that regular, mutually-productive interactions between citizens and local governments will improve governance and strengthen democracy at the local level, while increased awareness of these interactions through increased media coverage and independent research on these same local issues will be reflected in national policy on issues that matter to citizens. / As a result of the activities under this programme, women, young people and men will increasingly participate in a meaningful way in the decision-making and political processes at a local level in the target municipalities. They will have a better understanding of the possibilities and limitations of municipal level government, and will have established processes and channels for discussion and communication between citizens and decision-makers. These will act as a decompression chamber for social and economic frustration. Citizens’ priorities will begin to be a part of the municipal agenda. In the target municipalities, the project will see up to a 10% increase in the quality of citizen participation in municipal governance (from 22.4% in the Baseline Survey), and an increase to 24% (from 17% in Baseline Survey) of survey respondents who say that information accessed about Municipal Council business (such as solid waste collection) was easy to both find and understand, and an increase to 13% (from 4% in the Baseline Survey) of survey respondents who say that information accessed about Municipal Assembly (the legislative body) was easy to both find and understand. / The program will also improve the level of citizens’ knowledge of municipal governance from 18% (Baseline survey) to 30%, and increase the capability of CSOs to enable citizens to represent their interests from 0.6% to 8%. These improvements will contribute to strengthened democratic decision-making processes in the project sites, with at least 2.3 million Mozambicans supported to have choice and control over their own development and to hold decision-makers to account.

What is the context in which UK support is provided?
The programme and approach were developed to respond to the findings of targeted analysis and design work. This preparatory work showed that democratic institutions in Mozambique have little incentive to be more proactive in providing and promoting the rights and freedoms of citizens. Such institutions are not being held accountable for their actions and omissions. This will not happen without effective demand from society, but the demand also needs to be listened to. The programme aims to facilitate a process that will identify and constructively channel such demand in a manner that is responsive to the needs of the poor, and inclusive of all relevant stakeholders. / Mozambique’s formal commitment to democracy is apparent in its legal and planning framework. The Constitution of the Republic establishes a democratic system of government, with a strong bias in favour of Presidential power. The consolidation of democracy and good governance are central themes of the Government of Mozambique’s current five-year plan (PQG). Paragraph 4 of the PQG Introduction highlights a commitment to continuing with a people-focussed process of decentralisation, promoting good practice in governance in order to combat poverty and promote social, economic and cultural development. Priority actions include the promotion of peace, dialogue and national reconciliation leading to the consolidation of democracy and reinforcing civil society participation in local development, with particular focus on the involvement of local consultative councils. In its action plan based on the recent African Peer Review Mechanism (APRM) report, the Government included a thematic area of democracy and political governance. / However, the overall conclusion of recent political economy analysis is that Mozambique faces great economic and political challenges. There are indications of a growing democratic deficit, in that the government’s formal commitment to democracy is not backed by corresponding action. In 2013, Mozambique was scored as “partly free” by Freedom House in its well-regarded global index. At the same time, the country faces uneven poverty reduction with slow progress or even worsening results in the centre of the country. There is also a strong perception of increasing inequity in the distribution of wealth and services, with women suffering disproportionately. / At the municipal level, democratic governance is a work in progress. Municipal governments were relatively recently created, with the first municipal officials elected in 1998. DIÁLOGO research during the inception phase confirmed that citizens and municipal governments are not effectively communicating or partnering to solve local issues. At the municipal level, the baseline study confirmed that there is limited interaction between municipal institutions and civil society, media or research institutions, resulting in a lack of engagement with the issues facing citizens, and little accountability for the policies and programmes funded or executed by the municipal government. Some platforms or structures exist for public engagement, but these are not being used as intended, with weak awareness of their existence and the apparent politicization of their leadership and activities. In particular, participation by women and youth seems disproportionately low.

## Section A: Detailed Output Scoring

Output 1: Enhanced knowledge of democratic principles by citizens (women, men and youth) in target municipalities.
Output 1 score and performance description: A / Indicator 1: % of citizens with knowledge of how local government functions and its roles and responsibilities in delivering services (target population disaggregated by gender and youth). / Relevant Inception Phase Indicators: / The Management Unit team (including facilitators) are in place, and possess an appropriate mix of skills and experience. / The focal municipalities have been selected according to agreed criteria and following dialogue with Government and other partners. / An approach to measuring and reviewing political risk in the municipal areas has been defined and agreed with local partners. / The Management Committee and Advisory Committee have been established and have met at least once to validate decisions listed above.
Progress against expected results: / This Annual Review covers the Inception Phase of the DIALOGO (Democratic Governance Support) Programme. A one year contract was issued to a Managing Agent (a consortium led by DAI Europe) for this Inception Phase. Deliverables were defined in the Terms of Reference for the Inception Phase and progress against these was evaluated in an external Inception Review. A contract has subsequently been issued to the Managing Agent for the Implementation Phase. / A programme Management Unit (MU) was successfully established, municipalities selected and a Management Committee formed. Local facilitators have been engaged and a system of risk monitoring and reporting established. / The MU produced local engagement and advocacy strategies. These also include the Terms of Reference of the Local Engagement and Research and Advocacy Challenge Funds. These documents were informed by the Programme’s field research and Theory of Change. / To implement the core activities related to achieving this output, the MU designed a central/municipal management structure to lead the Local Engagement and Advocacy Strategies. / Baseline data to measure progress on this output were collected through a local mapping exercise carried out by CESC (a local CSO and part of the implementing consortium), and through MU field visits to the five target municipalities. The information collected during this process was also useful for the programme design, as well as updating the risks and assumptions in the Theory of Change and the logframe revision. / The data collected contain baseline information related to DIÁLOGO outputs and activities, such as current levels of citizen engagement, priority community issues, and entry points for the development of coalitions. DIÁLOGO estimates the level of public engagement with municipal institutions will increase from 15.5% to 25.5% during the Implementation Phase. / Recommendations: / The collected baseline data are not yet fully analysed and disaggregated for every municipality. It is important that this is done in order to understand and monitor the differences in citizen knowledge and engagement in each municipality and among the different groups of citizens (youth, women). / Impact Weighting (%): 15 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Private (non-state) media able to contribute to strengthened democratic process
Output 2 score and performance description: A / Indicator 1: Number of media partnerships established / Indicator 2: Measures to assess health of media environment in place (reach, regulation/law, financial flows, investment and advertisement etc.) / Indicator 3: Revenues of private (non-state) media increase in a) size and b) diversity / Relevant Inception Phase Indicators: / Management and approach of media and policy challenge grant funds have been agreed with DFID. / Strategy developed to strengthen independent media to cover municipal governance issues and to promote space for citizen’s voice.
Progress against expected results: / The Media Strategy and the Terms of Reference of the Media Challenge Fund have been finalised and agreed with DFID. These emphasise support to independent, locally-engaged and rooted media outlets and partnerships. / A strategic partnership with IREX was negotiated to support media outfits in the 5 target municipalities. IREX was part of the initial DAI consortium, but later in 2012 won a tender to implement a large USAID funded media support programme. This opens up new opportunities to maximize cooperation and impact; the USAID project focuses on the national media, but sharing, replication and exchange possibilities with municipal-level media supported by DIÁLOGO have been identified. The support that IREX will provide will focus on the organisational aspects of local media (business plans, financial management and sustainability). / Baseline data on media organisations to partner with in the 5 municipalities, including citizen perceptions of local media, were collected. This baseline survey negated the need for the annual media study that was initially foreseen. / Recommendations: / The MU need to define how the media support will be related to the work carried out by the municipal facilitators, local partner CSOs and municipal governments. The complementarity between various interventions will not be automatic, but will need to be engineered. Some monitoring will need to be done to guarantee that the DIÁLOGO component is not marginalised by IREX / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthened democratic decision-making processes in target municipalities
Output 3 score and performance description: B / Indicator 1: % of citizens demanding responses from municipal institutions on issues of concern in target areas, disaggregated by issue and gender/youth / Indicator 2: Degree to which citizens’ voice in target areas is heard between elections, disaggregated by gender and youth / Relevant Inception Phase Indicators: / Partner CSOs have been selected in focal municipalities. These organisations have been ‘contracted’ and trained. / An approach for identifying focal issues at the municipal level has been designed and agreed, and tested.
Progress against expected results: / Potential partner CSOs have been identified, but no further steps could be taken given that no formal engagements could be made beyond the inception contract period of one year. The municipal mappings carried out during the Inception Phase inform a specific approach to identifying focal issues for citizen engagement in each municipality. The mappings are complemented with information from the baseline survey and field visits. In late 2012, the programme started with the development of an implementation approach for each municipality built around concrete identified issues. Memoranda of Understanding between the programme and the municipal executive and legislative bodies were also introduced at that time and will be signed in the first quarter of the Implementation Phase. / Terms of Reference for a Citizen Engagement and an Advocacy Challenge Fund were formulated and approved. However, as a result of the Inception Review and work that the MU had undertaken to refine the Theory of Change, the emphasis on challenge funds has been diminished and new mechanisms of direct granting introduced. / Resources have been re-allocated in the Implementation Phase to provide broader support within each municipality: / The newly created position of Municipal Governance Advisor, as recommended in the Inception Review, is responsible for this support. / The role of the municipal partner NGO is strengthened for the Implementation Phase. / The Terms of Reference for the Municipal Facilitator have also been re-written to allow for greater focus on civic platforms at the neighbourhood and community level, in line with the programme’s Theory of Change. Recent training for the five facilitators reinforced this change. / In the first six months, a group of 15 Citizen Observers (3 in each municipality) with community engagement or development backgrounds were trained and hired to work on a part-time basis. These are women and young men who live in neighbourhoods within each of the five municipalities, and act as junior “citizen reporters” for external context monitoring. They also identify and report on concrete issues at the local level, such as crime, public transport costs, and the effects of recent flooding on local infrastructure. These reports feed into the programme learning process and are potentially powerful advocacy and communications tools. / Recommendations: / It is recommended to strengthen the programme’s presence in each municipality. A lot of the programme’s core business will hinge on the effectiveness of the municipal facilitators, but the task seems daunting for one single person. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Enhanced electoral processes in target municipalities
Output 4 score and performance description: B / Indicator 1: Voter registration undertaken to the satisfaction of national and international observers disaggregated by gender and first time voters / Indicator 2: % of women candidates who stand for election disaggregated by political party / Relevant Inception Phase Indicators: There were no indicators relating to this output.
Progress against expected results: / The programme is rolled out in the run-up to elections in the 5 target municipalities and initially civic education programmes were foreseen to generate interest and stimulate participation in the forthcoming (November 2013) municipal elections; voter registration and education were included in the Inception Phase Terms of Reference for the MU. Given the lack of evidence that sustains the assumption that civic education promotes electoral participation in Mozambique, the intervention strategy was revised. More creative and alternative interventions are also being prepared with experienced local partners. / The MU produced the first drafts of the programme’s Local Engagement and Advocacy strategies. These include the Terms of Reference of the Local Engagement and Research & Advocacy challenge funds. The Electoral Institute for Sustainable Democracy in Africa (EISA), the programme’s Mozambican expert partner for this component, provided input on these strategies as well as the Media Strategy and Terms of Reference and the programme’s workplanning process, Theory of Change development, and risk analysis. / Recommendations: / Engagement in the electoral process needs to be taken forth in full awareness of its political sensitivity. Well intentioned actions can easily be misinterpreted. Given the fact that the programme has not yet established its “credibility”, accusations of inappropriate behaviour or partisan agenda could have strong consequences. The MU is consulting within its consortium and with other experienced local organisations and research institutes to assess the potential impact or perception of activities in this component. / Clear communication with all parties and full transparency and predictability of interventions will be required. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 5: Communications and advocacy strategy for disseminating and sharing practical experience with municipalities, national research and policy institutions as well as other interested parties.
Output 5 score and performance description: A / Indicator 1: Number of briefings undertaken with key actors (e.g. ministries, parliamentarians, CSO’s, academia) / Indicator 2: Number of examples of good practice adopted in other municipalities as a result of dissemination and sharing of experience / Relevant Inception Phase Indicators: / A programme name to be used externally has been identified and an identity created. / An organisation has been contracted to provide independent evaluation throughout the programme life and has conducted the baseline study. / An approach to monitoring and evaluation, including the measurement of Value for Money, has been defined and agreed with DFID.
Progress against expected results: / The programme was named DIALOGO after an extensive consultation. It was introduced to each mayor and municipal government of the 5 target municipalities. The programme management also met with the Ministry of State Administration, the Study Office of the Presidency, and the National Parliament. The programme was launched in multi-stakeholder seminars where the findings of the municipal mappings were discussed. / The Baseline Study was undertaken by IDS and the results have led to the refinement of the Theory of Change and the programme logical framework. / At DFID’s request, a comprehensive monitoring, evaluation and learning strategy was developed. It is designed to support replication, exchange, and learning across municipalities and from municipalities to the national level. It includes not only activities that will allow for the regularly tracking of indicators for all five outputs, but also activities that will allow the programme to follow the changing political context in each municipality. The MU, in collaboration with the programme’s independent M&E team (IDS), has designed a Theory of Change based on the findings from the baseline study and local context assessments. This review culminated in a workshop in November 2012, which allowed for adjustments to DIÁLOGO'S Theory of Change and logframe, with the participation of Municipal Facilitators and Citizen Observers from each municipality to ground the discussion in specific local contexts. / A Communications and Outreach strategy was designed which details the approach for strategically engaging with stakeholders, partners and beneficiaries over the life of the programme. / Recommendations: / The strong emphasis on permanent learning in the programme is highly appropriate and useful. It is recommended though that the learning does not overly focus on informing the programme management, but that there are also processes that feed, inspire and inform the local actors. It is specifically recommended to promote horizontal learning between the municipalities and between the different actors involved. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / A new logframe was finalised at the end of the Inception phase, in December 2012. This new logframe was used as a reference for the Inception Review and will serve for the 2013/14 annual review. / The new logframe is a result of discussions with DFID, the analysis of the baseline survey, visits to municipalities and an ensuing revision of the programme’s Theory of Change. The new DFID Empowerment and Accountability indicator has been added. / 1.2 Overall Output Score and Description: / The overall output score is “A” considering that all agreed deliverables for the inception phase have been met. It needs to be noted though that expected results have been dynamic and that performance is measured against the changing expectation, rather than against the indicators fixed before the start of the programme. This was due to a post-tender decision to build-in a one-year inception phase, during which concrete deliverables had to be produced. / 1.3 Direct feedback from beneficiaries / Meetings took place with municipal governments. The programme was generally welcomed as a good initiative, but there was some wariness as to why such a programme was launched a year before local elections take place. Some people in local Frelimo leadership suspect this programme is a cover-up for foreign support to the opposition and one official from the opposition MDM party expressed fears that the programme supports the ruling party. / The programme was launched in each municipality in the presence of municipal governments and assemblies, media and civil society. The meaningful discussions of the baseline survey findings and municipal mappings reflect a widespread opinion that the potential of this programme is broadly acknowledged. For example, in a public meeting covered by national and local media, the president of the Municipal Assembly of Nampula remarked that the dialogue between citizens and the municipality supported by the UK was a “fundamental instrument” for social justice. / As noted above, the municipal government level is relatively new in Mozambique, and participatory governance projects have engaged more at the rural level than in municipalities. The coordinator of a multi-NGO governance forum commented that “the DIÁLOGO programme is an opportunity to translate our experience in governance and monitoring at district level in the rural areas into the municipal urban space.”
1.4 Summary of overall progress / A management structure has been put in place and essential steps have been taken to ensure optimal implementation: 5 municipalities were selected, municipal facilitators and citizen observers were recruited and trained and a comprehensive baseline survey on citizen knowledge of municipal affairs and citizen engagement was carried out resulting in important modifications of the programme’s Theory of Change and logframe. A monitoring, evaluation and learning strategy was developed as well as the ToR for two grant mechanisms. Progress against the Inception Phase deliverables was evaluated in the Inception Review, and found to be satisfactory. / The option to go for an inception year facilitated the creation of solid programme fundamentals and instruments, but it has delayed a firm rooting in local realities because no long-term engagements with potential partner organisations could be made, and a lightly staffed management unit had limited political and geographic reach and coverage as it was also responsible for the design, research, and writing of the programme’s M&E and deliverables. The inception year created a dynamic between programme management and DFID rather than programme and local partners/beneficiaries, but this should be able to change quickly when the programme is actually rolled out. / The recommended changes to the programme identified through the refinement of the Theory of Change and the externally conducted Inception Review have been accepted and incorporated in a new Implementation Plan and logical framework. The Implementation Contract is based on these revised documents.
1.5 Key challenges / The key challenge is to further adjust the ‘theory of action’ following the changes to the Theory of Change late 2012. The latter indicate that a competitive, supply driven “challenge fund” approach may not be the best implementation strategy in the short term. Relationships of trust need to be established between the programme and local actors and among local actors. The programme will need to trigger action through dialogue, training, mentoring and coaching. / The programme also still needs to take root in the respective municipal governance fabrics and, while contacts were initiated, strategic and iterative cooperation needs to be established with municipal support programmes (PDA, Pro-Maputo) and social accountability programmes (CIP, Concern, etc). / These issues were highlighted in the Inception Review and were accepted by the MU. Plans are being implemented to address them.
Annual Outcome Assessment / The character of the inception phase was very much focused on optimally preparing the implementation phase. Most of the work done was of a conceptual and managerial nature. So far no programmatic outputs were produced that have a direct relation with the programme outcome. Importantly though, a very thorough baseline survey was carried out and a strategy was developed to monitor and assess outcome level change.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / At the beginning of the Inception phase DFID allocated £1,564,874.46 of which £1,383,619.5 (or 88.4%) will be spent by the end of the phase. / Key cost drivers / During the Inception phase, a large focus was on collecting and analysing data in order to test programme assumptions and to improve on proposed implementation approaches and methods. For the past year the majority of the funds were used up on specialised local and international assistance and establishing operations and strategic partnerships. / Programme costs drivers include: / Poor infrastructure and high costs of operating outside the capital city: Mozambique has suffered from low investment in infrastructure (and poor basic infrastructure) and this, together with a state monopoly on internal air travel and the size of the country, drives up transport and accommodation costs. / Limited pool of local expertise to use, and of local organisations: Mozambique has the least educated adult population in the world (UN Human Development Index 2012). This is reflected in a scarcity of local experts in governance and decentralisation issues, particularly since municipal governments are recently created, with the first municipal officials elected in 1998. As a result fee rates are high for those individuals who do have the skills and knowledge in this area. / Also, the nature of this programme requires a significant level of Technical Assistance and a large number of local facilitators, in order to support engagement and communication between local communities, government and stakeholders. To carry out comprehensive, rigorous quantitative and qualitative data collection and analysis for the baseline study and for ongoing monitoring, the programme allocated significant resources to senior M&E expertise from the UK and within Mozambique. This has resulted in 52% of the programme assigned to fee rates. / 2.3 Is the project on-track against original timescale: Y / Generally, the programme is on-track to deliver on the logframe objectives.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The inception phase outputs (in particular the comprehensive baseline survey) produced evidence that challenged aspects of the original Theory of Change and its underlying assumptions. It turns out that accountability relations between municipal governments and civil society/citizens are far less developed than was anticipated. / Considerable time was invested to produce a new logframe that was in line with the reality check provided by on-the-ground experience and the baseline study. The effects of these changes on the project design are currently elaborated and integrated into the new implementation plan that forms the basis of the Implementation Phase Contract. Important operational changes are a reduced reliance on challenge funds in the short term and an increased investment in the municipal facilitation work done by CESC and municipal-level partner NGOs. / The baseline survey provides a broad set of data for the monitoring and evaluation of progress, along with the permanent reporting on changes in the local context by the citizen observers. The high investment in the production of verifiable evidence should allow DFID to assess progress with confidence and/or to timely adjust project design during the actual implementation phase. / 3.2 Where an evaluation is planned what progress has been made? / A mid-term evaluation is planned in 2015, with a final evaluation planned for 2017. The baseline study has already been undertaken to provide information against which progress will be evaluated in the target municipalities.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium. / 4.2 Assessment of the risk level / The programme has updated the initial risk analysis, and has identified specific risks to the work plan activities in each of the municipalities in which it will work. The risks have been graded as low, medium and high. / An approach to measuring and reviewing political risk in the municipal areas has been defined and agreed with local facilitators. Local facilitators have been trained and deployed, with an express eye towards local risk mitigation. “Quick win” activities are being undertaken in partner municipalities to test risk assumptions and risk mitigation approaches. / The Management Committee takes an overview of risk on a quarterly basis. Although the upcoming municipal elections provide a challenge to implementation at the municipal level, the risk is still judged to be medium.
Risk of funds not being used as intended / DAI is a credible and trusted organization with robust systems and internal controls over financial management and accountability of funds. As for grants to partner organisations DAI can rely on its own experience combined with lessons learned from MASC in particular. / Climate and Environment Risk / The Climate and Environmental risk is rated Low due to the nature of the programme.

5. Value for Money
5.1 Performance on VfM measures / Value for Money indicators have been defined and are integrated in the new logframe in order to ensure due follow-up. 8 indicators were developed covering efficiency, effectiveness, economy and equity. / 5.2 Commercial Improvement and Value for Money / The human resource input is a considerable part of the investment in this kind of programme. The fact that the management team and technical team composition was redesigned during the inception phase demonstrates a clear commitment to strive for maximum effectiveness of the investment. / The Inception Review in December 2012 looked at options for improving programme performance and VfM. This has led to adaptions to the technical approach and the budget (linked to revisions to the Theory of Change). For example, the original intention was to transfer responsibility to a local Team Leader during the programme, however DFID Mozambique have pushed that this happen at the outset, resulting in significantly lower costs (£430 per day as opposed to £725 per day) while also serving programme needs for improved local knowledge now that the approach and systems are established. / DAI has been receptive to DFID requests for them to reduce certain fee rates, both when the inception contract was being negotiated, and more recently in respect to some new roles. They have reduced the new national Team Leader fee rates by £120 per day. In terms of the VfM consideration of “Effectiveness”, the National Team Leader profile was designed to increase the effectiveness of the programme, particularly in the current political context. / As a result of these changes DFID has achieved a saving of approximately £287,000 on this contract amendment for the Implementation Phase, primarily through challenging fee rates and removing costly consultancy inputs and costs. / The DIÁLOGO MU will conduct cost-benefit analyses of its activities, and based on the evidence and data available, propose modifying resource allocations across activities, challenge funds, personnel, equipment, and travel over the course of the programme as the context and requirements of the programme change to ensure efficiency and effectiveness as well as economy. In this vein, the MU decreased expenses by approximately £30,000 by deferring purchase of a second vehicle, ultimately determining that this was not needed and could be re-allocated to other budget lines. The MU is also saving DFID over £20,000 annually by sharing a modest office (rent, security, utilities, maintenance) with DAI’s country office. / DFID Mozambique will agree a suite of supplier Key Performance Indicators (KPIs) in the second quarter of 2013, against which DAI will be regularly monitored. The broad areas these will cover have been defined in the contract. DFID Mozambique has agreed with DAI that we will consider linking part of their payment to strong performance against these KPIs after the first year of this contract. Payment for the new Implementation Phase contract is a fixed amount explicitly linked to programme deliverables and outputs (60% linked to deliverables / 40% linked to outputs). This will ensure that there is a strong incentive for DAI to continue delivering as expected, and to ensure costs will not escalate (as they will need to meet any shortfall). / 5.3 Role of project partners / The selection of consortium partners seeks to optimise the response capacity to the ambitious and diverse objectives of the programme. The consortium composition is challenging, but clearly results-oriented and well-experienced in Mozambique. / The MU is also seeking to optimise VfM through collaboration with other programmes. DIÁLOGO could not only draw on the grant management experience gained by MASC and the many grants programmes operational in Mozambique, but also on operational manuals, CSO databases and training materials on CSO engagement. Besides with MASC, there have been exchanges with other programmes that promote the demand side of local governance (e.g. CIP, Concern) in order to maximize benefit from existing experiences. / The programme has also initiated collaboration with municipal capacity development (supply side) programmes such as PDA and Pro-Maputo. These programmes can potentially facilitate further collaboration with the municipal governments. For example, PDA’s Director stated that “We really need a programme like DIALOGO in involving the citizens to create the spaces of dialogue. We sense the lack of participation from citizens where we are working.” A UN-HABITAT official similarly stated, “DIALOGO can complement what we are doing in order to create a space to discuss urban issues.” / 5.4 Does the project still represent Value for Money: Y / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable.

7. Conclusions and actions
The programme produced practically all outputs that were agreed for the Inception Phase. These have been arbitrarily allocated to different outputs for the sake of this review. In some cases (for example the annual media study) the programme and DFID agreed not to carry them out. An Inception Review provided further suggestions for improving the implementation strategy (or ‘theory of action’). These suggestions have been accepted and incorporated in the revised implementation plan. Some of these changes, such to the staffing of the MU, have already been made. / The programme management needs to get the capacity to think and act more politically, and be able to use multiple formal and informal sources to keep a finger on the pulse in all 5 municipalities and on national policy processes. The team also needs to get more technical capacity on municipal governance than has been the case so far. / The programme has the necessary instruments in place and the Inception Phase created a much more realistic perception of what can be done by the programme. With the inception recommendations adopted on top of what was created before the programme is well equipped and well resourced for implementation.

8. Review Process
An Inception Report produced by DAI and an independent review of the inception phase was used as input to this AR.