Type of Review: Annual Review

Project Title: Tanzania Climate Change Institutional Strengthening Programme

Date started:	April 2011	Date review undertaken: July 2012

Introduction and Context

What support is the UK providing?
The UK is providing £2 million over 4 years from April 2011 – March 2015 to fund: i) a climate change programme advisor and ii) a flexible technical assistance fund, to strengthen the capacity of Tanzanian institutions to lead/engage successfully on climate change issues.

What are the expected results?
The key outcome is for Tanzania to access at least $300 million of climate finance by 2015 and for it to be used effectively to support climate resilient and low carbon development. / The key changes which are expected to result from UK support are: / Tanzania has a comprehensive National Climate Change Strategy. / Tanzania has a strong policy and institutional framework to plan, budget and deliver for effective use of climate finance at a national level. / Establishment and implementation of an effective national level policy and financing framework with climate change mainstreamed into key sector policies and annual budgeting processes. / Ministry of Finance and key sector Ministries are more engaged and active on the climate change agenda. / Climate change plans developed in key sector ministries and for key sector investments / Performance based climate financing piloted in at least 5 villages / districts by 2015, to enable them to effectively plan and budget for climate change. / Increased number of people who are better able to cope with the adverse effects of climate change.

What is the context in which UK support is provided?
Tanzania has a population of 40 million, which is expect to rise to 75 million by 2030 and 110 million by 2050. Despite consistent economic growth, Tanzania remains a poor country with 80% of the population living on less than £20 a month. The Tanzanian economy is based on climate sensitive sectors e.g. agriculture, hydro-electricity, forestry and tourism. Extreme climate events are already causing major socio-economic impacts and reduced economic growth, with the 2005/6 droughts reducing economic growth by at least 1%. The economic costs of climate change are predicted to rise to 1-2% of GDP by 2030 and current trends indicate that climate variability will undermine the achievement of the MDGs in Tanzania. / Despite the existence of a National Action Platform for Adaptation (NAPA) – the cornerstone of Tanzania’s response to climate change, the country has an adaptation deficit. The NAPA has limited support, in part because it is not sufficiently robust and secondly because of the limited national ownership stemming from poor institutional governance. / Tanzania is falling behind other countries in the region in addressing the challenges of climate change, this is limiting the country’s ability to access potential climate financing, which is needed to take action. / UK support is provided in order to address two capacity gaps: / Institutional strengthening / Access to climate financing

## Section A: Detailed Output Scoring

Output 1: Comprehensive climate change strategy in place including adaptation and low carbon development and being effectively delivered at sector and district level with sufficient budget allocation.
Output 1 score and performance description: / Tanzania is falling behind other countries in the region in addressing climate change. This is in part due to not having the right capacity and institutional arrangements to enable access to significant levels of international climate finance. / To counter this, this output supports the development and implementation of a National Climate Change Strategy (NCCS) for Tanzania and the development of a national climate fund to support the implementation of the strategy. The existence of a robust strategy is a critical factor in a) enabling Tanzania to access international climate finance b) enabling the setting up of a national climate financing mechanism, through which donors would support the implementation of the strategy and c) improve mainstreaming of climate change across Tanzania’s development plans. The first draft of the strategy was released in September 2011. / The UK and other DPs expressed strong concerns over the quality of the document and the level of transparency during its development. There has been a delay in the launch of the NCCS – reportedly due to delays in stakeholder comments on the first draft – but we are confident that a final draft will be launched by September 2012. Zanzibar is in the process of developing a parallel but complementary national strategy, which will be delivered by November 2012 under the UN Development Assistance Framework (UNDAF), which the UK is supporting. DFID is the lead donor in delivering results on climate change in Tanzania. This is complements work led by other donors, including; Norway on REDD and forestry, USAID on water, Germany and the EU on renewable energy. / The development of a national climate financing mechanism is still in the scoping phase and will be a key focus for this programme over the next 6 months. The Government of Tanzania welcomed the DPs support to develop a national financing mechanism, which will improved donor harmonisation and strengthen Tanzania’s ability to access international climate finance. / A: Outputs met expectations although some concerns over the quality of the national climate change strategy and the delay in its launch. / Economics of Climate Change Studies for Tanzania and Zanzibar delivered. / National Climate Change Strategy (NCCS) Workshop hosted in Windhoek, Namibia / Draft National Climate Change Strategy released September 2011, final strategy expected by September 2012. / TNRF delivered two workshops and help multiple stakeholder consultations on integrating climate adaptation into district level dry lands planning. / Scoping paper on National Climate Financing Mechanism (NCFM) at terms of reference stage, with product delivery set for November 2012. / First workshop on the development of a National Climate Financing Mechanism (NCFM) will take place with the Government of Tanzania and Development Partners (DPs) in August 2012. The meeting will have an initial discussion on needs and preferences to inform the development of a scoping paper. A further meeting will take place in November / December 2012 to agree a preferred option.
Progress against expected results / Indicator 1: National Climate Change Strategy, including Zanzibar is established and funded / Milestone stone 1: Strategy Finalised and Action Plans agreed by 2012 / Progress: On track to meet Milestone 1; some concern over the quality and the delayed release of the strategy. It is understood that the delay in launch was caused by late contributions by key stakeholders. / To ensure a comprehensive NCCS, in 2011/2012 DFID supported two important studies; Economics of Climate Change for Tanzania and subsequently for Zanzibar. The Government of Tanzania and civil society were fully engaged and consulted. This provided the basis for the development of the NCCS and carried the additional benefit of engaging non climate ministries i.e. Planning Commission in the climate agenda. / The GoT Tanzania released the first draft of the NCCS in September 2011 covering low carbon, adaptation and resilience on both the mainland (Tanzania) and Zanzibar (Unguja and Pemba). In November 2011, DFID and the World Bank supported a cross-government learning event on the development of national strategy in Windhoek, Namibia. The event was attended by the Government of Tanzania, including parliamentarians, the Governments of Zambia, Mexico, Namibia and South Africa as well as other DPs and representative of civil society. This improved the transparency and consultation in the development of the NCCS. As of July 2012, the final stakeholder consultations are being completed and the GoT has indicated that the NCCS will be released by September 2012. / Compared to other countries in the region e.g. Ethiopia and Rwanda, the quality of the NCCs is a concern. This is indicative of the relative lack of capacity in the GoT to address climate change when benchmarked across other EAT countries and illustrates the critical need for sustained effort to support capacity development and institutional strengthening. DFID’s climate change support plays a key role in this. / Zanzibar will develop a separate but related climate change strategy, which acknowledges that Zanzibar faces a number of unique climate challenges. The process for developing a climate change strategy for Zanzibar commenced in May 2012, with a predicted launch date of November 2012. It will be informed by the Economics of Climate Change for Zanzibar study. / In parallel to the development of the NCCS, DFID supported Tanzania Natural Resource Forum (TNRF) to integrate climate change adaptation into drylands development planning. This will strengthen the capacity of district-level authorities and civil society actors in 3 districts, Monduli, Ngorongoro and Longido, bringing together informal and formal land-use planning to support improved resilience to climate change. As a result of the May 2012 TNRF workshop, Masai tribes and district planners in the Ngorongoro district are working towards a more integrated land-use planning tool, which better supports the Masai’s ability to sustain their livelihoods under climate variability. / DFID’s climate change advisor played a strategic role in developing the evidence base for the NCCS. As the Chair of the Development Partner Group-Environment (DPG-E) sub-group on climate change, the Advisor played a critical role of both supporting the government deliver its strategy and ensuring the buy in and support of the donor group. DFID’s Climate Advisor has play an important role in supporting the government as well as playing an interfacing role between the government and other DPs. / Indicator 2: Transparent national climate change financing mechanism established / Milestone 1: Options paper on the financing mechanism with Ministry of Financial Affairs (MoFEA) and agreement on the preferred option by 2012. / Progress: On track to meet Milestone 1. An options paper for a national climate financing mechanism will be delivered by independent consultants in November 2012. A workshop will be held at the end of 2012 with the Government of Tanzania and other DPs to agree a preferred option. The workshop and scoping paper will feed into the UN Development Assistance Programme (UNDAF) / This indicator aims to develop a national climate financing mechanism, which will pool donor funding in support of the Government of Tanzania’s National Climate Change Strategy. It will strengthen the institutional arrangements around climate financing in Tanzania, which is critical to improving Tanzania’s access to international climate funding. / As chair of the development partners’ climate change group, DFID’s climate change advisor has played an instrumental role in facilitating dialogue between DPs and the GoT (Vice Presidents Office, the Planning Commission and the Ministry of Finance) and other DPs on the issue of a national financing mechanism. The outcomes of which are a) general agreement to work towards a national climate financing mechanism for Tanzania b) the development of a programme of work - including through the UNDAF to achieve this goal. The Climate Advisor has also helped leverage additional funding for capacity building, in particular from the UN and the World Bank. / Recommendations: / That DFID Tanzania strengthens its working relationship with UNDP to deliver the UNDAF, which will be instrumental in leveraging additional financial flows into Tanzania. / Impact Weighting (%): 40% / Revised since last Annual Review? N/A / Risk: Low/Medium/High: Medium to High / Revised since last Annual Review? N/A

Output 2: GoT and development partner investments and expenditure are climate smart
Output 2 score and performance description: / The purpose of this output is to mainstream climate change across everything that DFID, other DPs and the Government of Tanzania does. A recent review of the programme’s log-frame suggested the ability to ensure all spending of other DPs and the Government of Tanzania was climate smart, was too ambitious. / However in terms of ensuring DFID spend is climate smart, good progress has been made. DFID has screened GBS (50% of DFID-Tanzania spend) and 17 business cases. In addition a strategic programme review was under taken. / Progress with other DPs and the GoT has been slower and more difficult to measure. / Good progress has been made in the development of sectoral plans for climate change, though there has been a delay in the launch of the green growth strategy for SAGCOT and there are some concerns over the quality of work being produced. / A: Outputs on average met expectations: the Green Growth Strategy for SAGCOT has been delayed due to a delay in contracting by the Government of Tanzania. / Methodology for climate screening DFID programmes developed and applied: May – June 2012. / Methodology for climate screening PRBS developed and applied April – June 2012, ahead of 2014 milestone. / SAGCOT Green Investment Framework to be delivered in September 2012 / Three economic sector climate action plans under initial stage of development – ahead of 2015 milestone.
Progress against expected results / Indicator 1: Proportion of DFID (and development partner) spend that is climate smart / Milestone 1: Methodology of climate screening PRBS is developed by 2012. / Progress: Milestone met and exceeded. Methodology for screening Government Budget Support (GBS) was developed and implemented in May / June 2012. In addition the methodology for climate screening Tanzania’s development strategies (MKUKUTA II, 5 Year Development Plan and Long-Term Prosperity Plan) was developed and implemented in April / May 2012. Methodology for climate screening DFID-Tanzania’s portfolio was developed and implemented in May 2012 as part of DFID-Tanzania’s Strategic Programme Review (SPR) refresh. / Between 2011 and 2012 17 new business cases underwent a rigorous climate and environment assessment and as a result all 17 are now “climate smart.” / In May 2012 DFID-Tanzania climate screened GBS, this included a full screening of the GoT development strategies. The GoT and other DPs were fully consulted. The results of the climate screening were presented to GBS HOPs on 29 June 2012. / It is not possible to measure the proportion of other DP spend which is climate smart. This indicator will be revised following this review. / Indicator 2: Proportion of GoT budget that is climate smart. / Milestone 1: Methodology agreed with the GoT to screen Poverty Reduction Budget Support (PRBS) and Government of Tanzania (GoT) Budget by 2012. / Milestone 2: Screening undertaken by 2014. / Progress: Milestone achieved and exceeded. In May 2012, a methodology was agreed with the GoT to screen PRBS and GoT budget. In June 2012, the screening took place (well ahead of 2014 deadline). / DFID Tanzania is the second DFID country office (after Rwanda) to undertake a climate screening of General Budget Support (approximately 50% of DFID-Tanzania’s overall spend). The methodology developed by independent consultations was agreed with the Government of Tanzania through a series of meetings in April and May. / The screening was undertaken in three stages: 1. Screening of Tanzania’s development strategy (MUKUKUTA II, 5 Year Development Plan). 2. Screening of Tanzania’s Budget. 3. Screening of DFID’s General Budget Support. / The findings were presented to the GoT and to the General Budget Support Heads of Co-operation in June 2012. / The findings indicate that the GoT invest approximately 0.3% of the national budget on climate mitigation and adaptation. The study undertook an initial screening of individual projects in Tanzania’s 5 Year Development Plan (5YDP) using a simplified climate screening system. This reveals that around three quarters (75%) of the plans / projects would be potentially at risks of current climate variability and future climate change and around one third (32%) are considered to be at high risk. The 5 YDP would therefore benefit from formal climate screening, though it is highlighted that UNDP is advancing a climate screening of development plans in Tanzania, and there is on-going Technical Assistance from World Bank/DFID in this area, which should help mainstream and progress this screening / The screening illustrates that Tanzania is following a traditional model of industrial development, with extensive use of fossil resources (including coal as well as gas) and heavy industry (cement, iron and steel, petro-chemical and fertiliser production). As a result, the analysis shows a strong increase over previous industry CO2 emissions by 2015/2016, with a fivefold increase in emissions from these sectors over current emissions, and with future projections consistent with the 5YDP more than double previous projections from MKUTUTA II. / The exercise has illustrated two key issues which were received seriously by the GoT: 1. That Tanzania’s development vision is not following a ‘green growth’ pathway, which could potentially put it at a disadvantage in comparison to other countries in the region (Rwanda, Ethiopia, Kenya) who will be more competitively placed to access climate financing due to their ‘green growth vision’. 2. That there is a significant need and opportunity to support the GoT to undertake internal screening of the government’s budget and expenditure to ensure investments are resilient to climate change. / As a result of this exercise three things will now happen. 1. In depth screening of Tanzania’s development strategies by UNDP, supported by DFID and the World Bank. 2. Policy dialogue on what a green growth development pathway would look like for Tanzania and what needs to happen to achieve this. 3. Internal GoT screening: This recommendation is being taken forward by the GBS team in DFID-Tanzania and is likely to form part of the Public Expenditure Systems review. It will also be taken forward by DFID, the World Bank and UNDP to develop a screening methodology and provide capacity support to the GoT. As of July 2012, both elements were in the concept stage and were being discussed with the GoT and other DPs. / In August 2012, ODI will undertake a Public Expenditure Review of climate change in Tanzania. This will provide a methodology and baseline. The review will be delivered under ODI’s Accountable Grant with DFID-London. / Indicator 3: Climate Change plans developed in key sector ministries and for key sector investments such as SAGCOT. / Milestone 1: SAGCOT Green Growth Strategy by 2011. / Progress: Milestone not met: SAGCOT Green Growth Strategy was not delivered in 2011 due to a delay by the consultants; Eco-Agriculture and a shift in scope of the work. The Green Growth Strategy has now been superseded by the Green Growth Investment Framework, which will be delivered in September 2012. DFID and other donors (Norway and World Bank) as well as the SAGCOT Centre have ongoing concerns around the quality of work provided by Eco-Agriculture – responsible for producing the Green Growth Investment Framework. Concerns have been raised formally and an upward trend is being noticed. However, expectation management over the relevance of the final product is underway and a no-cost extension to their contract has been agreed from July until September 2012. / DFID and the World Bank have supported the development of the Strategic Environmental Assessment (SEA) of SAGCOT, which will deliver its results in September 2012. It will be important to ensure coherence between the SEA and the Green Growth Investment Framework and decide how the two can most effectively be taken forward post September 2012. More work will be needed to ensure that the GGIF is not a standalone document, but is integrated into the decision making framework for SAGCOT as a whole - including the Catalytic Fund. / Milestone 2: By 2015, 3 economic sectors have climate change strategies and action plans. / Progress: Milestone on track to be exceeded: Good progress towards the 2015 milestone. As of July 2012, the Ministry of Water, Agriculture and Local Authorities (under PMO) are in the initial phases of developing sectoral climate action plans. These will be finalised by 2013. / As of July 2012, the GoT is finalising the National Climate Change Strategy. In March 2012, DFID and the World Bank undertook a joint meeting to understand the capacity needs of sectoral Ministries for implementing the NCCS (once finalised). As a result of the Mission, the Ministry of Water, Ministry of Agriculture and PMO-RALG requested support from donors to develop Sectoral Climate Action Plans. Support will commence in August 2012 and Sectoral Climate Action Plans will be developed for release in 2012-2013. / Recommendations: / That DFID undertakes a critical review of the work of Eco-Agriculture and maintains regular pressure to ensure the delivery of a quality product / DFID works with the World Bank and others to ensure consistency between the GGIF and the SAGCOT Strategic Environmental Assessment / DFID works with other donors and the SAGCOT centre to ensure the recommendations of the SAGCOT Strategy Environmental Assessment and Green Growth Investment Framework are not stand alone documents, but are mainstreamed into investment decisions. / DFID maintains strong working level relationship with economic sectoral Ministries to support the development of climate action plans, and reaches out to those not taking a more proactive role – in particular the Ministry of Energy. / Impact Weighting (%): 30% / Revised since last Annual Review? N/A / Risk: Low/Medium/High: Medium / Revised since last Annual Review? N/A

Output 3: Improved aid effectiveness through a comprehensive framework for development partner support in Tanzania on climate change
Output 3 score and performance description: / The aim of this output is to strengthen donor coordination on climate change in Tanzania. DANIDA and DFID led the development of the Joint Assistance Framework for Tanzania on Climate Change in 2011 to help frame donor support and engagement on climate change. / Good progress has been made. However, the recent review of the programmes log-frame has suggested a change in this output and indicators; it is difficult to assess the performance of the programme against indicators which are largely out of DFID’s control i.e. how other DPs allocate their funding centrally. / A+ Outputs moderately exceeded expectations / On track to deliver 2013 milestone of 25% climate change funding in support of DP framework. / Over 4 joint DP programmes on climate change (2012 milestone was 3).
Progress against expected results / Indicator 1: Increased proportion of development partner spend in line with Development Partners Climate Change framework (and National CC strategy) / Milestone 1: By 2013 25% of climate change funds in support of the DP framework / Progress: On track to meet Milestone 1 by 2013. 14 DP’s have agreed to harmonize development funding around the Joint Assistance Strategy for Tanzania; clear evidence of increased donor harmonisation on climate change in Tanzania. As of July 2012, the NCCS had not been launched. It is therefore not possible to measure proportion of DP spend in line with the strategy. / Indicator 2: Increased proportion of joint DP programmes on climate change / Milestone: 3 joint DP programmes on climate change by 2012. / Progress: Milestone has been met and exceeded. As of July 2012 over four joint DP programme exist on climate change, against a baseline of 0 in 2010/2011 / In excess of four joint DP programmes now exist on climate change. A new monitoring framework has been put in place to enable this going forward. Joint programmes include: 1. DFID and DANIDA: Climate Window of Accountability Tanzania. 2. DFID, World Bank and Norway: SAGCOT Green Growth Investment Framework. 3. DFID and World Bank: Development of Sectoral Climate Action Plans. 4: DFID and UN (through the UNDAF) Institutional Strengthening for Climate Change. / Recommendations: / That DFID continues to chair the DPG-E sub-group on climate change, and increases outreach to ensure improved collaboration across DPs on climate change and climate relevant programmes – including energy, agriculture and water. / Impact Weighting (%): 25% / Revised since last Annual Review? N/A / Risk: Low/Medium/High: Low to medium / Revised since last Annual Review? N/A

Output 4: Establish an effective M&E framework for climate change in Tanzania
Output 4 score and performance description: / The aim of this output is to ensure that DFID Tanzania is effectively monitoring and evaluating its impact on building resilience to and mitigating climate change. An extensive exercise was undertaken by ITAD in May / June 2012 which flagged two issues: 1. Need for the TCCISP log-frame to be significantly updated and 2. That the objective of building resilience to climate change is being delivered by DFID Tanzania’s broad portfolio (i.e. education, health etc) rather than the climate portfolio. DFID Tanzania should therefore re-consider its results framework. / A+ Output moderately exceeded. / M&E climate framework developed, / DFID climate portfolio log-frames updated to align with International Climate Fund Key Performance Indicators and indicators developed for DFID portfolio for use at an appropriate time.
Progress against expected results / Indicator 1: M&E framework in place for all climate change interventions and monitoring climate change as a cross cutting issue in the DFID operational plan (£600m), with work plan for implementation / Milestone 1: Establish M&E framework with baseline data – identify data sources and needs. / Progress: Milestone 1 met and exceeded. As of July 2012, DFID Tanzania was one of the only DFID country offices to have undertaken a full M&E assessment on climate change / covering the climate portfolio and other programmes with specific relevance to climate change (e.g. Cotton, Water, TMEA etc). / There are multiple outcomes from the assessment. These are: 1. Revised M&E / log frames for the climate portfolio. 2. Suggested revisions to log frames for climate relevant programmes. 3. Suggested M&E framework to measure the impact of DFID's operational plan on climate change. However, due to the timing of the assessment a number of the recommendations won’t be taken through to implementation until 2013 (i.e. next update of the OP). The final outcomes from the assessment, including a work plan for implementation will be delivered on July 16 2012. / HMG in Tanzania has a UK Framework for Climate Change which will have a full M&E Framework attached by August 2012. / The M&E exercise has raised the need for DFID to reassess which ICF key performance indicator it is reporting against. Currently this is KPI1 – building resilience. However, the consultants advised that the length of the theory of change was too long and that KPI 13 – institutional capacity building – was a better fit. This could have implications for DFID Tanzania’s results framework. / Indicator 2: Independent evaluation undertaken and results shared / Milestone 1. Scope of evaluation identified and key questions as part of M&E framework (longitudinal analysis) / Progress: Milestone 1 met: ITAD undertook an independent evaluation of the M&E frameworks of the climate portfolio and DFID Tanzania’s broad portfolio. The evaluation raised key questions with regards to DFID Tanzania’s results framework, which will be taken forward over the next 6 months (to December 2012) / Recommendations: / That the log-frame for TCCISP is revised and updated to simplify and bring them into line with the ICF KPIs. / DFID Tanzania standardizes climate indicators to capability to monitor progress towards building resilience to climate change. / Those non climate specific programmes integrate M&E indicators for climate change at the most appropriate opportunity. / Impact Weighting (%): 5% / Revised since last Annual Review? N/A / Risk: Low/Medium/High: Low / Revised since last Annual Review? N/A

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / No. / A recommendation of this annual review is to update the log-frame. / Overall Output Score and Description: / A: Met expectations. / In 2011-2012, the programme on average met expectations, delivering well against its objectives and 2012 milestones. Despite this, there is a mixed picture across a number of the outputs (e.g. output 3), with some indicators being moderately exceeded and others being off track. Where the indicators are off track i.e. release of the SAGCOT Green Growth Investment Framework, DFID is working with other donors to maintain significant pressure on delivery agents to ensure the delivery of a high quality product under a revised time-scale. The delay in delivery will not impact the overall programme time-scale. / A number of lessons have been learned from the first phases of the programme, the key of which is the need for increased engagement with the Government of Tanzania and increased levels of capacity building and technical support. The first year of the programme has illustrated that the capacity gap is larger than originally assessed. This raises the question of the potential of the programme to deliver increased results and value for money. It can do so, but is likely to require an increased level of investment from DFID Tanzania to match levels of support now being provided by other DPs. / Direct feedback from beneficiaries / The GoT and the GoZ have expressed clear appreciation of DFID support for the Economics of Climate Change. In both instances the Governments expressed gratitude for DFID support with providing the information on which to base national climate change strategies. / The Planning Commission and MoFEA have proactively engaged and fed back to DFID on the issue of climate financing and internal screening, requesting additional and on-going engagement with us in taking this work forward.
Summary of overall progress / Strong progress has been made, though two deliverables were off track as of July 2012; 1. Launch of the National Climate Change Strategy 2. Delivery of the Green Growth Investment Framework. Neither will impact the programmes overall time-scale and both will be delivered by September 2012. / Key successes of the programme as of July 2012 are: / Screening of GBS and Tanzania’s development strategies. The Government of Tanzania recognising the need for internal climate screening and to address the issue of green growth to ensure competitiveness going forward. / Hosting of National Climate Change Strategy Workshop in Namibia, resulting in a more transparent process for the development of Tanzania’s strategy.
1.5 Key challenges / The pace of change within the Government of Tanzania continues to be a key challenge in the delivery. This is in part due to institutional weaknesses and information blockages in the GoT, which this programme is aiming to address. / A drawn out decision by UNDP on the co-funding arrangement on the delivery of the UNDAF has meant that the World Bank and DFID have had to undertake work outside of the UNDAF in order to deliver results in 2011/2012. An MoU with UNDP for the delivery of the UNDAF is currently being delivered which will mitigate this challenge in year 2. / Having in place the right delivery agent / consultants to produce high quality pieces of work – this was a particularly challenge with the SAGCOT Green Growth Investment Framework, where Eco-Agriculture are not delivering to the standard we would expect. This will be taken account of in future consultancy sifts. / Funding levels. The TCCISP requires an extension to support the delivery of all outputs to a high level.
Annual Outcome Assessment / The intended outcome of the programme is for Tanzania to access climate financing and use it effectively to support climate change resilience and low carbon sustainable growth. / The programme is on track to deliver the outcome. The building blocks phases in year 1; evidence generation, technical capacity building, and the development of relationship are all critical factors to leveraging additional climate finance. / As a result of this programme, the Government of Tanzania is more informed on the potential levels of climate finance available to them, and the need for institutional reform in order to access them. This is a significant step forward from 2010/2011. The Economics of Climate Change study; supported by DFID has been instrumental in bringing about this shift. / Going forward, DFID and other DPs will need to work with the GoT to quicken the pace of institutional strengthening to ensure that Tanzania does not miss out – by comparison to other countries in the region – on available climate finance.

2. Costs and timescale
Is the project on-track against financial forecasts? / Yes / Key cost drivers / Technical Assistance: Consultancy fee rates and expenses. / Consultancy contracts are in line with DFID guidance on VfM: economy flights are taken – in May 2012 Hartwell consultants were asked to absorb the cost of upgrading to Premium Economy, despite the flight cost being within the consultancy budget. / In May 2012, negotiated down ITAD consultancy day rates by £50. / All consultants are closely measured for their efficiency and quality of work. / Is the project on-track against original timescale / Yes, although there have been two delays in delivery in this reporting period: 1. Launch of the National Climate Change Strategy and 2. Delivery of the SAGCOT Green Growth Strategy. Neither of these will impact the overall time-scale of the programme. / 2012 milestones have been met and the programme is on track to meet its 2013 milestones. The July 2012 Monitoring and Evaluation Assessment flagged the need for DFID to maintain pressure on the GoT and DPs to ensure delivery of 2013 milestones.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The programme itself has generated increased evidence i.e. Economics of Climate Change in Zanzibar of the need for sustained capacity building and technical assistance on climate change in Tanzania. / 3.2 Where an evaluation is planned what progress has been made? / A VfM evaluation of the programme is currently being undertaken (July 2012).

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium / 4.2 Assessment of the risk level / Accurate
Risk of funds not being used as intended / Year 1 deliverables were achieved though procurement of consultancy services through a management agent, or directly with the consultant / organisation. This allowed DFID to play a strong scrutiny role on how the funds were being used. / Going forward, DFID will be spending through the World Bank and UNDP. This will increase the risk of funds not being used as intended. However, M&E measures and break clauses in the funding agreements will increase DFID’s ability to manage the use of funds and ensure delivery of expected results against these. / 4.4 Climate and Environment Risk / As a climate specific programme, TCCISP does not carry any significant climate risks other than travel and document printing, which are being managed through effective mitigation measures e.g. reducing air travel where possible, limiting printing and using environmentally sound printing techniques.

5. Value for Money
5.1 Performance on VfM measures / Overall the programme continues to deliver value for money. Over the £2 Million £570,000 has been spent in year 1 and £387,400 is committed. / There have been two trigger points for the programme during this reporting period. / Delay in launch of the National Climate Change Strategy / Delay in delivery of the SAGCOT Green Growth Strategy / Neither of these has resulted in increased costs to the programme. / The timing of the launch of the NCCS was not within the control of DFID, and we expect the GoT to release the strategy in 2012, which will meet the programmes milestone. / The delivery of the SAGCOT Green Growth Strategy has been an on going concern for DFID and Norway (two predominant funders). Significant pressure has been placed on Eco-Agriculture by DFID and Norway as well as the SAGCOT Centre. Payments have been with-held until the delivery of a quality product. The final report is expected in September 2012. Due to the delay in the overall SAGCOT programme getting off the ground, the delay in the green growth strategy will not negatively impact its usefulness. / In July 2012, ITAD will put all DFID-Tanzania climate programme’s through a VfM matrix. The results of which will be taken into account in improving – where possible – VfM of the programme. / Least cost delivery mechanisms / Performance: Good. Five out of seven contracts awarded in this reporting period were awarded to Harewell Resource centre. These awards were made through a competitive tender process, which Harewell was successful in given their competitive management costs, ability to procure high quality consultants and proven track record of delivery. Overall they have managed the contracts well and their costs are competitive compared to other managing agents. Contracting through Hartwell is efficient; short turn-around times from ToR to consultant start date is effective; guarantee of a high quality consultant and is cost-effective / economic; contracting through Hartwell reduces transaction costs for DFID. However, there have been two instances with Hartwell during the SACGOT SEA where DFID has had to push back on invoices as they have not adhered to consultancy guidelines and ToRs, these were on a) class of flight and b) receipting for taxi expenses. / The total value of the contracts awarded through Harwell was £335,000. They have delivered all contracts within budget and provided time-sheets for consultants work. Working through Harwell has reduced programme management costs by reducing the amount of DFID programme management staff time required to manage the contracts by approximately 20%. / The outstanding two contracts were procured directly with Paul Watkiss Associates and IDLS partners. Because these were ‘small’ contracts (only amounted to £16,960), direct contracting offered improved value for money by comparison to procuring through a management agent. / There have been two instances in this reporting period where costs were outside of vfm measures: / A contract with SUZA (through Harewell) the consultant took a flight via Nairobi instead of direct flight to Dar es Salaam and charged us for accommodation in Nairobi. DFID picked Harewell up on this, as they had missed it as the total cost of the flight remained within the budget limits. DFID-Tanzania requested Harewell to ensure more effective due diligence on costs and strongly reminded them that the budget agreed in the contract was the upper limit of expenditure, but that least cost options should always be chosen. / A consultant was contracted through Harewell for the SAGCOT SEA. DFID-Tanzania scrutinised the invoice for the consultants time and identified taxi expenditure that had not been receipted for and was over the cost that we would expect for similar journeys. The un-receipted taxi fares were not paid and the consultant was given the names of taxi’s who provided receipts and offered a fair journey price. / This level of expectation and due diligence will be set out at the point of contract with the PEAK to avoid any confusion around vfm. / Maximising resources under the technical assistance fund by leveraging additional finance: Performance: Moderate. / DFID’s Climate Advisor effectively worked with the World Bank and UN to lever additional funding for institutional capacity building, development of national climate change strategy as well as the scoping and development of national climate financing mechanism. The total leverage costs to date is US$1,880,000 broken down as: / Support to ACT: DFIDT contributes US$ 200,000 and Norwegians $80,000 / Support by World Bank for REA, National Climate Change Strategy whereby DFID contributed US$500,000 while World Bank Contribution is US$ 1,800,000 / Future leverages: Going forward, DFID-Tanzania support will leverage funding from Finland and the UN to support the implementation of the National Climate Change Strategy. / Exploiting existing arrangements to minimise start up times. / Performance: Good. Eco-Agriculture funded through pre-existing ACT Accountable Grant of GBP £360,000 which has also been co-financed by DANIDA as well as TNRF Accountable Grant of £125,000 for Mainstreaming CC in development planning in drylands. Utilising the existing funding arrangement ensured efficiency in start-up time as a new programme did not need to be designed, has been economical by reducing transaction costs, and has been effective as the programme is on track to deliver in September 2012. / Reducing transaction costs in a pooled funding arrangement for development partners. / Performance: Good. Capacity building and technical assistance delivered through pooled funds through a) World Bank EFO and b) UNDAF. AMCEM funding delivered through cost-share with UNDP. Pooled funds through the EFO are an effective means of reducing transaction costs for delivering a number of relatively small programmes. It enables greater efficiency by achieving donor coordination. / Piloting performance based payment for delivery of climate finance. / Performance: Good. All consultancy contracts are performance based payment. This is an extremely effective means of driving quality and timeliness of work and ensures efficiency by the consultants themselves as payment for time is dependent on delivery of product. Performance based payment for consultancy is the most economic mechanism as it avoids payment being made for poor quality work, or work which is not delivered on time. / Achieving significant returns from its impact on climate change resilience, the more sustainable use of natural resources, and Tanzania’s access to international climate finance. / Performance against this vfm measure is too early to assess, but as per earlier results sections, the project is on track to meet its targets. / Commercial Improvement and Value for Money / Competition is used to drive value for money in the provision of technical assistance. Technical assistance on climate is a competitive market, which allows us to drive costs down. / In the Economics of Climate Change contract we were able to negotiate a 2.5% discount on the total contract value having savings of £3,098 / As mentioned in the 5.1 section above savings from the 2 accountable grants of totalling to £82,571 / Saved $400 on flight costs for one of the consultants who wanted to take his preferred airline when a cheaper option was available / A saving of approximately £100 was achieved on taxi reimbursements where the consultant did not provide receipts and instead charged according to the budget ceiling. DFID-Tanzania refused to reimburse unless receipt was obtained or reasonable charges were sought. / Value for money is always built into the terms of reference e.g. economy class flights, using consultants already in country etc and is used as a key filter for awarding contracts. / Negotiations are always entered into to drive down consultancy day rates e.g. ITAD reduced their day rates by £50 during the negotiation with DFID-Tanzania whereby we saved a total of £2,550 on the total fees. Contracts are always performance based payments to ensure value for money in the product delivered. / In addition, negotiations through the Accountable Grants under this programme have resulted in reduced costs. Key examples are: / TNRF: “Mainstreaming climate change in development planning in drylands”. The original budget was £360,000 but we negotiated it downwards to £297,429 making a savings of £62,571. This saving was made on reducing ‘overhead / management costs’. / ACT: The original budget was for USD$ 300,000 and we were able to reduce the overhead costs by $20,000 bringing the total budget to $280,000 of which DFID-Tanzania contributed $200,000 and Norwegian contributed $80,000. / DFID will shortly sign an MoU with UNDP for the delivery of the institutional strengthening component of the UNDAF. An assessment of UNDPs procurement capacity will be undertaken prior to the signing to ensure systems are in place to deliver vfm. A break-clause will be built in to the contract at 12 months to allow a VfM assessment. A performance incentive will be built in at 24 months for additional funding if the programme is delivering to or above expected outputs. / 5.3 Role of project partners / The total programme project costs are £2 Million of which £ 570,000 has been spent and £387,400 are committed. The costs have not changed over the year however we have been able to attract more development partners into funding various initiatives. / We have clearly been able to reduce the overhead costs by the partners as well as consultancy costs as mentioned in 5.1 and 5.2. We have also assessed the partner’s procurement procedures to ensure that value for money is obtained such as ensuring 3 quotes for procurement and also cutting down on consultancy and overhead costs. / Hartwell International are adhering to consultancy guidelines, but could improve vfm through improved invoicing i.e. sending time-sheets through at time of invoice and clearing stating vfm ToR to their consultancy team. / 5.4 Does the project still represent Value for Money : / There is no evidence to suggest that the programme does not reflect value for money. It is anticipated that vfm will increase in year 2. / In year 1, the programme was implemented through multiple delivery partners. This was accounted for in the original business case, so there has been no change in value for money. However, experience from year 1 has illustrated that vfm could be improved by reducing the number of delivery partners. / As a result, year 2 will see a streamlining of delivery partners to work predominantly through the UN Development Assistance Framework and the World Bank. It is anticipated that this will significant improve vfm of the programme in future years. / 5.5. If not, what action will you take? / As per 5.4 the number of delivery partners of the programme will be streamlined. / 5.6. Lessons learned / Harewell: we have learned that using the management agent helps reduce administration burden on DFID. A key lesson is for vfm measures to be set out clearly in the original contracting and for Harewell to communicate these to the consultants. Where this does not happen, rigorous follow up is required to ensure value for money is achieved i.e. economy or least cost airlines are taken (referring to the example in 5.1 above). This lesson will be taken forward during the transition to PEAKS. / Multiple delivery mechanisms: In this reporting period a number of delivery agents were used. Managing these was time intensive for the Climate Advisor and Programme Manager. It is therefore proposed that the number of delivery agents is reduced for year 2 with the World Bank and the UN being the main delivery channels going forward. / When contracting through a direct delivery partner, it is important to scrutinise the partner’s budget to ensure that costs especially related to overhead running costs have been justified and not just given as a % of the total budget for the project. A great deal of savings can be achieved if bulk procurement is done as well as ensuring 3 quotes and market surveys. / The value for money measures set out in the original business case are not deemed appropriate. As a result of this review, a new value for money framework will be developed, building on the vfm screening by ITAD, which will bring the framework in line with the 3Es.

6. Conditionality
6.1 Update on specific conditions / There are no specific conditions for the programme.

7. Conclusions and actions
Conclusions: / The programme is on track to meet its milestones and is delivering well against stated objectives. / The climate agenda is moving forward at rapid pace in Tanzania and DFID has the opportunity to leverage significant change through increased levels of funding. / The climate portfolio is not directly contributing to climate resilience – the theory of change chain is too long. However, DFID-Tanzania’s broader portfolio e.g. water, health, education, agriculture etc is having a significant impact on building climate resilience. These results need to be better captured through M&E. / Actions: / Discussion on an extension to the programme in order to maximise the UKs ability to leverage change and deliver results as well as maintain its position – as the only DP with a specific advisor on climate change – as the lead donor on climate change in Tanzania. Whilst the programme is leveraging in significant amounts of additional support from other DPs, there remains a significant funding gap. DFID is currently the lead donor on climate change in Tanzania and is well placed – technically and influence – to drive forward an ambitious agenda in Tanzania and deliver significant poverty alleviation results. However, this position and level of impact is likely to be diminished if DFID is unable to increase our level of support. / Significant update of the TCCISP programme log-frame. This will not change the Impact, Outcome or type of UK intervention. It will improve the UK’s ability to monitor and evaluate impacts and to report on results against the ICF KPIs. This action is based on recommendations from: M&E Assessment (ITAD – June 2012), lessons learned from undertaking this first annual review and, need to better align the programme with ICF KPI’s to improve efficiency of reporting. / DFID-Tanzania to consider overall results framework with advice from DFID-London on the use and methodology of ICF KPIs.

8. Review Process
In July 2012, the programme will be put through a VfM Matrix. Recommendations from this exercise will be taken into account in the delivery of the programme going forward. / The log-frame will be updated by September 2012. / The next annual review will be completed in by July 2013.