Annual Review – post April 2018

Title: Policy Development Facility Phase II (PDF II)
Programme Value £ (full life): £18.5m		Review Date: 11/10/2018
Programme Code: 203922	Start Date: 01/04/2015	End Date: 31/03/2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017/18	2018/19
Programme Score	A / (Pre-Contracting)	A / (Inception Phase)	A / (First full year of implementation	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203922/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203922/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Policy Development Facility Phase II (PDF II) is the successor to DFID Nigeria’s Policy Development Facility (PDF) programme, which succeeded the Policy and Knowledge Programme (PAK). PDF II started 1st April 2015 and is set to end 31 March 2020. PDF II is comparable in most respects to PDF I but has a more robust approach to knowledge management designed during the Inception Phase.

PDF II’s objective is to provide targeted assistance over a five-year period to help Nigeria’s ‘champions of change’ implement economic and social policies that lead to poverty reduction, enabling the UK Government support reform through:
- Backing key economic and public-sector reformers in Nigeria with technical support.
- Conducting research and studies that can be used to influence and shape Nigeria’s economic reform agenda.
- Initiating explorative studies for potential complementary DFID programming.

The Impact PDF II seeks is that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform.

The impact and outcome of this programme (PDF II) are fully aligned with DFID Nigeria’s business plan. It will help leverage better use of Nigeria’s resources for its national development, unleashing its growth potential. The programme’s approach reflects a principle in the business plan that better governance and growth are inter-dependent. The PDF programme also aligns well with the new Africa Strategy to address long term issues that matter most for Africa’s prosperity. The programme supports policy makers who can make an impact on inclusive growth, trade, and economic partnerships (via research and technical support to the Office of the Vice President (OVP), the Ministry of Budget and Planning, the Chief Economic Adviser to the President, the Finance Minister and more). The programme also supports climate change and natural resource management via technical advice to the Ministry of Environment and supports stability within Nigeria via support on DFID Nigeria’s North-East interventions.

Context:

In 2016, Nigeria experienced the worst recession in two decades as oil prices collapsed from over $114 per barrel in June of 2014 to a low of $30 per barrel in early 2016. This had severe knock-on impacts for jobs, with unemployment rates rising to 18.8 percent by the end of 2017. While the economy began to rebound in mid-2017, Nigeria’s recovery has been driven to some extent by improvements in local oil production and global prices as oil contributes over 70 percent to government revenues and is also responsible for close to 90 percent of foreign exchange earnings. In essence, crude oil is the lubricant that keeps Nigerian’s economic engine humming whether as a source of government spending and its multiplier impacts or as a source of necessary foreign exchange for businesses that need to import key inputs into their production processes.

Unfortunately, the economic rebound which started in 2017 is yet to be sufficient or inclusive enough to support job creation or poverty alleviation. The projected 1.9 percent growth by the IMF for 2018 (and 2.3 percent for 2019) falls short of population growth, implying that poverty levels may actually rise in the near term. In addition, fiscal challenges imply that the government cannot make the necessary capital investments to drive long term growth. For example, the 2018 budget plans for a deficit of 23 percent of revenue underpinned by an assumption of improved revenue performance. Ironically, current levels of borrowing by the federal government are almost at the same levels of interest payments which implies that the government is borrowing just to cover its interest payments. Without a strong growing economy, this debt strategy is unsustainable with interest payments now representing 72 percent of Federal Government revenue and projected to reach 82 percent by 2023[1]. As a result of the aforementioned, the risks to Nigeria’s fragile economic recovery are clear: First, it remains highly dependent on the performance of the oil sector. A major reversal of the oil price would result in a rapid reversal of recent gains. Second, the large deficits and the accumulation of debt are not sustainable – revenue mobilisation is imperative but not likely prior to the election.
[1] 2018 IMF Article IV Staff Report

In the midst of the recession, the government responded with its overarching policy response- The Economic Recovery and Growth Plan (ERGP). The Plan is for the years 2017-2020 and is to build on a previously drafted Strategic Implementation plan, National Industrial Revolution Plan, and Nigeria Integrated Infrastructure Master Plan. The ERGP has the broad objectives of restoring growth, investing in the Nigerian people, and building a globally competitive economy. Unfortunately, an implementation plan setting out an appropriate and coherent set of policies that will deliver on the goals set out in the ERGP remains wanting and critical.

The UK’s Policy Development Facility (PDF II) has continued to step up in mobilising technical assistance to support President Buhari’s economic policy agenda amid challenging economic prospects for the country. The programme has continued to remain responsive having laid the foundation of support and policy influence in the first year, and is repositioning itself on the back of a recently completed political economy analysis of the President’s cabinet. The programme has also held the fort on DFID Nigeria’s infrastructure interventions, keeping up momentum and ensuring previous gains are not lost with any DFID programming gaps. This will be even more critical as Nigeria heads into the election season.

The UK Government’s ability to be responsive and provide support helps the UK to stand-out as a donor partner of choice and provides important political capital to the UK’s work in Nigeria. PDF continues to be a highly visible programme which gives the UK government the opportunity to influence evidence-based policy decision making by the Nigerian government. In addition, the work that PDF has done in building an evidence base on policy has been complemented by UK Government influencing through DFID advisers along with support from the British High Commission. Yet, the current economic challenges following the recent recession in the country and the policy responses of government demonstrate the limits of providing technical assistance to influence policy outcomes.

As the programme has been recognised as the go-to programme for technical assistance by members of the Nigerian government, this has meant a higher than anticipated number of projects under the administration since its inception in 2015. Unlike under PDF I, where the administration pursued a smaller number of large, potentially high impact reforms projects such as the setup of the Nigerian Sovereign Investment Authority (NSIA) and YouWiN! requests to DFID under PDF II have been for assistance on a higher number of smaller sized projects. This may also be reflective of Nigeria’s current context (recession and aftermath) and the consequent budgetary challenges. In response, PDF II continues to seize opportunities possible whist ensuring that it provides assistance that contributes to pro-poor outcomes.

Programmatically, the major part of this year has focused on opportunities for consolidating support in areas of success. The adoption of core technical assistance teams to ensure that key reforms in the power sector were continued, and ensuing that past gains are maintained towards more efficient outcomes has also been critical. This has however put significant burden on PDF II’s finances and necessitated measures to manage the depleted resources pending a contract amendment. Despite these challenges, through this programme review, there is evidence that the support the programme has provided remains relevant in the policy space and continues to be valued by beneficiaries.

Summary supporting narrative for the overall score in this review (1/2 page)

PDF II actively sought and seized opportunities within government’s priorities, which are beginning to show positive outcomes. The current administration came into office in 2015 and prioritised growth and development of the private sector (especially medium, small and micro- enterprises) as a major lever to achieve its broader economic development priorities. To execute this, the President directed the launch of the Presidential Enabling Business Environment (PEBEC) secretariat in mid-2016 to develop and drive a reform programme that would change the business landscape. PDF’s engagement with the EBES started in mid-2017 in recognition that work by the PEBEC could ultimately impact jobs and decrease poverty levels. PDF commissioned work to take stock of current reforms, launch a process to articulate the end state vision, design a 24month implementation roadmap, build capacity within relevant agencies and support a reporting process. The impact of the work commissioned was that reforms were taken across multiple agencies which resulted in Nigeria moving up by 24 points from 169th position to 145 in the World Bank’s Ease of Doing Business 2018 report.

PDF’s package of support to the Office of the Auditor General of the Federation (OAuGF) has strengthened the ability of the OAuGF to conduct its statutory responsibilities with improved technical efficiency and professionalism, thus, supporting institution building. PDF’s support was a result of an MoU signed by Prime Minister Cameron and President Buhari to fight corruption in Nigeria at the 2016 Anticorruption summit. The summit, a first of its kind, brought together world leaders, business and civil society to agree on a package of practical steps to expose corruption and drive out the culture of corruption wherever it exists. The package of support involved in house technical support on audit methodologies and programme management; legal support for the drafting of an audit bill which would enshrine the independence of the Office of the Auditor General in Nigerian law; support on the drafting of a five-year strategic plan for the OAuGF, as well as technical support to deepen the working relationship between the OAuGF and the National Assembly (NASS). This support to the OAuGF has led to the government taking a more critical look at its own operations. For the first time in the history of Nigeria, the OAuGF has issued a qualified audit[2] to the Federal Government. According to the Auditor General;
[2] https://www.proshareng.com/news/NIGERIA%20ECONOMY/OAuGF-2016-Audited-Annual-Report-Submitted--Issues-Qualified-Report-/40935

Deficiencies were noted in the process for consolidating the balances of Ministries, Departments and Agencies into one economic entity. Furthermore, the consolidation boundary for the Federal Governments’ Financial Statements is not adequately defined, and the justification for the exclusion of several significant balances was uncertain.

In addition, there were reflections on the impairment of a fair representation of the assets and revenues of several government agencies due to the exemptions given in the adoption of the of International Public Sector Accounting Standards (IPSAS).

Other outcomes from PDF support are that Auditor General’s office has been able to conduct more periodic audits of government agencies as the programme supported capacity building to the OAuGF in conjunction with the National Audit Office. Also, the OAuGF currently has a better working relationship with the Public Accounts Committees of the NASS through technical assistance provided by PDF. PDF II further supported the OAuGF with a study tour to the UK by members of the NASS and key staff of the OAuGF. The result was an agreement on a time table for the passage of the Audit Bill. PDF II subsequently worked with other DFID programmes (The Partnership to Engage, Reform and Learn (PERL) as well as the Policy and Legal Advocacy Centre (PLAC)) to facilitate engagement and procedures for passing the Bill in the Senate. The law providing for the Supreme Audit Institution’s independence has now been passed by the Senate and House of Assembly. The bill now awaits transmission to the executive for presidential assent which may happen over the next few months.

As a result of PDF II’s support to the Nigerian Government’s Efficiency Unit, significant savings have been delivered from cuts to inefficiencies observed in Federal Ministries Departments and Agencies’ (MDAs) operations. PDF’s engagement with the Efficiency Unit began in 2016, supporting with four Embedded Advisors (EAs) over the period (one long term adviser and three short term advisers at various periods). The EAs focused on cutting costs to generate savings across various government activities and improving government procurement processes to enhance value for money. While strategies were developed depending on the nature of the expenditure, the unit focused on the top five expenditure items; travel, welfare, training, maintenance and stationaries/consumer consumables. The outcome of this initial strategic review helped to establish strategies for cost-containment across MDAs and resulted in the Unit saving the Nigerian Government over £500 million. In addition, more efficiency gains are in the pipeline as Unit is developing an on-line price register where government agencies can compare costs across multiple suppliers to control recurrent expenditure. There has also been the introduction of an expense card scheme for purchase of small items to reduce the use of cash as cash use is susceptible to abuse and possible fraud. The successes registered has prompted requests at the subnational level on lessons learned. The Unit now offers these lessons to other states and agencies.

PDFII’s support, in conjunction with other DFID programmes has also helped raise the profile of the Ministry of Environment (MoE). PDF’s work with the MoE began with an EA provided to the then Minister (Amina Mohammed) in 2016. The EA worked on the development of a strategy and work plan to govern the Ministry’s work. When the minister was appointed Deputy Secretary General to the UN, work continued on Green Bonds, specifically on communications and other activities in the Ministry. More recent EA work on the Green Bonds focused on providing guidance on technical matters on the bond issuance, the development of an engagement framework around the bonds; the development of a prospectus, and the set-up of accounts and areas of authority across the offices of the Debt Management Organisation (DMO), Office of the Accountant General of the Federation and MoE. As a result, the government raised £25 million in December 2017 as a first tranche of its Green Bonds Initiative. The ministry hopes to be able to raise £100 million by the end of the year. Such results has raised the profile of the MoE and in return, its capital allowance has increased significantly (from roughly £3.5 million at the start of the administration in 2015 to £21 million in the 2018 budget).

PDF II has also supported reforms in the Mining Sector, which has made a significant contribution towards Nigeria’s drive to diversify its economy. PDF’s engagement began in 2016 when the Ministry of Mines and Steel Development reached out to DFID for support on policy development and driving sector reforms. The EA’s support helped produce a roadmap for growth and development of the industry and sector reforms which focused on management and administration of mineral titles, establishing new revenue generation initiatives, capturing partnerships with relevant stakeholders, setting up 30 mineral processing and buying centres nationwide, and more. These reforms have led to an increase in government revenues from the sector from roughly £2.4 million in 2015 to £8.8 million in 2017. The EA also had the mandate to develop the capacity of existing human resources within the ministry which has also improved.

While the Npower programme is a short-term palliative measure with limited prospects for sustainability, it gives an important signal on the government’s commitment to job creation. In addition, the programme has been quite helpful, enabling some Nigerians find meaningful work during the recent economic recession. The Npower programme is a two-year programme that aims to provide a series of empowerment or skills competency programmes for graduates and non-graduates. Through the 2016 round, 200,000 public and private sector positions were filled, where the government provided stipends to enable participants transition into the private sector at the end of the programme. The 2018 round has created an extra 300,000 positions. In addition, the Npower programme extension for non-graduates also began implementation to help applicants build skills in painting, decoration, carpentry and other areas. Thus, with PDF’s support, the programme has met its target to create 500,000 jobs for youth between the ages of 18 and 35. PDF’s support to the Nigerian government on the Npower programme began in 2015 with support on a Youth Employment Summit, a follow up tracer study and commissioning research to produce a strategic framework for job creation and an implementation plan. More recently, PDF’s support has centred on technical assistance which also aided the design of regional innovation hubs. Following the report on innovation hubs, plans are underway to set up seven innovation hubs across the country. The success of the Npower programme would depend on the ability of applicants to transition beyond the two-year government supported program to more self-sustaining ventures or other forms of permanent employment.

It is worth noting that the challenges posed by a fast depleting Managed Fund were handled delicately by PDF II to ensure that impact on existing projects and DFID’s relationship with the Nigerian government has been minimised. While communicating the difficult messages regarding the programme’s financial position earlier in the year, PDF II continued to manage relationships to ensure that EAs continue to feel valued and avoid disruptions to projects EAs are working on.

This review therefore assesses PDF II as having achieved an ‘A’ reflecting the good progress made. Despite significant challenges, the programme has continued to responsively shape technical assistance to targeted parts of President Buhari’s government. The programme has achieved its key output indicators and is on track to achieve its outcomes by the end of the programme.

Recommendations for the year ahead (1/2 page)

PDF’s recent Political Economy Analysis (PEA) revealed that some technical reforms are more immune to electoral politics. e.g. the enabling business environment reforms. This is an area that PDF has been supporting and is ideally placed to continue support with the possibility of minimal disruptions from the elections season. Similarly, the work to support the modernisation of the Public Accounts Committee should continue to be done in a way that avoids discontent politically about take up of the PAC reports. Another area would be bringing skills to bear on the mechanics of how to implement social protection programmes in conjunction with other DFID Programmes in post (such as the Child Development Grant Programme). The programme should explore other areas beyond the aforementioned areas, where PDF is already providing support. The key criteria for choosing such interventions is that they should improve the productivity of what will be done regardless of who wins the election.

PDF has worked with various agencies which have supported job creation in the country in one form or another. For example, the governments’ Npower programme has supported job creation and skills acquisition for both university and non-university graduates. Beyond the 200,000 jobs created in 2016, the programme has on-boarded another 300,000 applicants. There are also projects with the intent to create jobs being executed by the Ministry of Mines and Steel, and the Ministry of Agriculture. Next steps beyond highlighting successes across agencies (which the programme has done) would be to conduct further research to ascertain just how many jobs the programme has been able to support disaggregated by gender.

In addition, PDF has demonstrated effectiveness across various interventions such as support to the Efficiency Unit which has created a savings of over £500 million, work with the MoE on the origination of Green Bonds worth over £20 million, and other interventions. Value for Money case studies highlighting attribution to the programme should be drawn up on such interventions by the next annual review.

As the uncertainty of election outcomes beyond the 2019 presidential elections heightens, it is likely that requests for technical assistance and requests for studies which inform policy making may slow. This period will be instrumental for the programme to take a step back and reprioritize its areas of engagement to champions of change within the new administration. It will be critical to review the roster of embedded advisor on a case by case basis. Also beyond the current annual review, the programme should look to revise its logical framework to ensure that milestones set are realistic.

A log frame revision may also be necessary following a recommendation in the 2017 Annual Review regarding how projects are aggregated. PDF II reviewed its portfolio and found that while Output 1 (mostly EAs) may lend itself to aggregation by work area to some degree, Output 2 (research studies, events etc.) was less amenable. Hence, a new methodology for counting Output 1 projects was brought in (without changes to the log frame). The new method enables PDF II to look at clusters of support provided in reform areas in a more strategic manner. However, this change mid-way through the programme means that some metrics produced for assessment (financial and otherwise) of the programme, may not be directly comparable to previous years or PDF I. PDF should conduct further research to finalize and report back to DFID as soon as possible what may and may not be comparable under Output 1.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Relevant and high quality PDF II organisational support delivered to beneficiaries
Output number per LF		1	Output Score	A
Impact weighting (%):		60%	Impact weighting % revised since last AR?	No (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of projects assessed as executed satisfactorily (as planned) or better during implementation	53	As of the time of this review, PDF II had 54* projects assessed as satisfactory at implementation/Completion stage.
1.2. Beneficiary, user perceptions of relevance and quality of PDF II funded organisational support	Relevance…………………90% / Quality……………………..80%	Beneficiary feedback has been positive with projects scoring on average 93% on relevance and 90% on quality, above the log frame thresholds.
1.3. Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs……….10	76

*In the year under review, 3 projects under Output 1 (an Intergovernmental Relations Officer, technical support on the National Asset Decision Support System and infrastructure screening) were assessed as unsatisfactory during implementation. Though they technically met the beneficiaries’ approval, they were assessed by PDF II as not having met the desired objectives/standards, and so have not been included in the count for Indicator 1.1.

Provide supporting narrative for the score

At the time of this review, in line with the new project count methodology[3], under Output 1, PDF II has a total of 71 projects. These projects have focused on issues such as economic reforms and improving tax compliance in Nigeria, supporting cost cutting measures across the government via the Efficiency Unit, the Power Sector Recovery Plan, issuing Green Bonds, etc. Of the 71 projects, four projects are in pipeline, 34 are ongoing projects and 33 are completed/closed/resigned projects (of which ten projects inherited from PDF I were completed and archived during the Inception Phase of PDF II). No new projects commenced within the last year (from April 2018). Seven dropped projects (under the various new major groupings) do not register in the count.
[3] On the back of the last Annual Review, the AR team had recommended that the projects be grouped according to thematic areas and not solely according to the number of projects contracted.

PDF continues to seek opportunities to position itself to offer relevant support to those identified as potential ‘Champions of Change’ within President Buhari’s cabinet. Support has been provided across multiple areas in the OVP (such as on job creation, social safety nets, ease of doing business etc). In addition, support has been provided to the ministries of Work Power and Housing to support on-going reforms on the Power Sector Recovery Programme, the Ministry of Trade and Industry, Ministry of Mines and Steel Development and others. At the onset of the new administration, A PEA was conducted which helped shape the programme’s initial support to the administration. More recently, the programme has leverage on a further PEA carried out in July 2018 which focused on individuals within the cabinet, the balance of influence and potential policy opportunities. The findings of the PEA have fed into internal DFID efforts to identify areas of promise on the development agenda, and recommendations into areas that may be prioritised in this pre-election season to ensure consolidation of reforms.

Technical Assistance has been provided to the following Federal Ministries, Departments and Agencies (MDAs) as set-out in Table 2 below (some projects have closed).

Table 2: Overview of areas of technical assistance:
Federal Ministry, Department & Agency	Areas of Technical Assistance
State House (Office of the Vice President – OVP & Chief of Staff – CoS)	Economic Advisory Council
	Economic Advisory Board
	Job Creation & Youth Employment
	Policy and Delivery Unit
	Internally Displaced Persons (IDPs)
	Communication, Digital & New Media
	Advisory Power Team Cross-sectional Support
	Nigeria Asset Decision Support System (NADSS)
	Rural Electrification Agency & Power Sector Recovery Plan
	Energising Education & Regulation Programme Implementation Support
	Industry Trade & Investment (EBES)
Ministry of Industry, Trade and Investment (MITI)	Special Advisers on Investment & Strategic Communications
	Direct Investor Summit 2018 & Sector Summaries
Ministry of Foreign Affairs (MFA)	Senior Adviser on Trade & Investment issues
	Technical Assistance on Economic Diplomacy Initiative
Ministry of Finance (MoF)	Chief of Staff, Support to Efficiency Unit, Economic Reforms
	Technical Assistance on Improving Tax Compliance in Nigeria
	Special Assistant on Key MSMEs financing Initiatives
	PPP Unit Coordinator & Project Adviser
Ministry of Planning & Budget (MBP)	Monitoring & Evaluation, Media, Policy & Planning Advisers
	Humanitarian Coordination Group
Ministry of Health (MoH)	Universal Health Coverage Agenda: One PHC Per Ward & Rapid Results Initiative
Ministry of Environment (MoE)	Special Adviser & Support to the Implementation of the UNEP report on Ogoni Clean up
	Communications Adviser
	Climate Finance Advisor (Green Bonds)
Ministry of Agriculture & Rural Development (FMARD)	Project Management Advisor
	Studies on Addressing Agricultural Finance Constraints, Assessing Capacity needs at FMARD, & Youth Unemployment in Agriculture
	Support to Transforming Nigeria’s Livestock Industry
Ministry of Solid Minerals (MSM)	Delivery Unit /Technical Adviser
Nigeria Extractive Industries Transparency Initiative (NEITI)	Policy, Planning & Strategy
Nigeria Sovereign Investment Authority (NSIA)	Technical, Communications, & Health Investment Advisor
	Technical Assistance & Investment Decision support for the Nigeria Infrastructure fund
Office of the Auditor General for the Federation (OAuGF)	National Audit Office Partnership
	Technical Advisor & Project Management of the OAuGF Reform Initiatives
Central Bank of Nigeria (CBN)	Technical Support on Energy (Power) matters
Federal Ministry of Power, Works, and Housing (MoPWH)	Chief of Staff & Project Management Unit Support
	Policy, Roads, Urban Development & Housing, Energising Education, & Emergency Generation
	Performance Monitoring & Communications
Nigeria Office for Trade Negotiations (NOTN)	Technical Assistance
	Training on Trade Policy
National Assembly (NASS)	Technical Support to the Chairman, House of Representatives Public Accounts Committee (PAC)

Over the life of PDF II, the 71 “projects” translates to 116 Embedded Advisers (with contracts ranging from three months, to a year) provided under Output 1 towards supporting Champions of Change. The feedback from beneficiaries and the count on “number of instances where PDF has supported data and analysis which has directly influenced any of the five stages of policy formulation” continues to support the evidence that the programmes approach remains important to influencing policy that can lead to poverty reduction.

The impact of PDF’s embedded advisors also reflects the wide package of support to the Nigerian government under the programme. Government collaboration with the private sector has improved via PDF II’s EAs’ monthly macroeconomic and comparative reports which feed into support rendered by the Economic Advisory Council (EAC) to the OVP. The reports support in discussions with the private sector at the presidential Quarterly Business Forum and the Diplomats Business Breakfast Meeting (a general meeting for business stakeholders and the diplomatic community hosted by the Nigerian government). With this approach, private sector is carried along in the economic formulation and execution of government policies.

PDF II’s EA provided technical assistance to operationalise the Development Bank of Nigeria and to enable the DBN and Pension Finance Institutions deploy best practice in providing loans to MSMEs (e.g., cash-based lending). So far, N619 million has been disbursed to over 300 MSMEs across the country. An additional N1.5 billion has also been made available for further disbursement, which is currently on going. These will ultimately have impact on growth of MSMEs, job creation and poverty reduction.

Nigeria Sovereign Wealth Fund and the Presidential Infrastructure Development Fund: The President has approved the establishment of a Presidential Infrastructure Development Fund (PIDF) to be managed by the Nigeria Sovereign Investment Authority (NSIA). Funds are to be invested specifically in critical road and power projects across the country. This initiative aims to eliminate the risks to project funding, cost variation and completion that have plagued the development of the nation’s critical infrastructure assets such as the Second Niger Bridge, Lagos to Ibadan Expressway, East-West Road (Akwa Ibom to Cross River), Abuja to Kano Road and the Mambilla Hydroelectric Power project. The Presidential approval led to the authorisation by the National Economic Council (NEC) to transfer $650 million dollars as seed funding for PIDF. The EA supported in the development of the strategic plan that saw to the establishment of the fund.

Technology Innovation in the North East: PDF II’s EA initiated the North-East “Makeathon”; a process to crowd source ideas around humanitarian solutions. This is related to the first set of priority challenges earlier identified through consultations with NGOs and affected persons in the region. The NE Makeathon (which precedes the launching of the North-East Hub) is a programme to crowd source and support innovative ideas to develop effective and scalable solutions to the humanitarian challenges faced by the IDPs and Host Communities in the North East. Thus far the developers of 25 ideas have been shortlisted to attend a co-creation boot camp for mentorship, team partnership and refinement of their ideas with field-testing. These ideas will then be further shortlisted for a final demo day presentation to select the top ideas to be sponsored and incubated in the North-East Hub.

Lessons identified this year, and recommendations for the year ahead linked to this output

PDF implementing infrastructure projects in addition to its broader array of support to the Nigerian government created significant delivery challenges which the programme overcame. As the NIAF II programme came to a close, PDF stepped into the infrastructure space to ensure that DFID Nigeria did not lose any gains from its previous programme as delays in the commercial process to the sequel programme (United Kingdom Nigeria Infrastructure Advisory Facility- UKNIAF) meant that the UKNIAF programme would not begin promptly. While the PDF business case was written to be able to accommodate such requests, in reality, the on-boarding of the infrastructure programme created significant challenges to delivery. In response, the programme had to recruit in house expertise to ensure synergy and delivery.

As the onboarding of the NIAF advisors drew down on PDF’s managed fund, the DFID programme team applied for a contract amendment which took time to be approved. To ensure that the programme was able to keep its promise of support to various agencies across the Nigerian government, EAs had to be engaged on three-monthly contracts. Without this alternative being in place, there could have been a significant reputational risk as some EAs would have had contracts whilst others would not. It took support from across the office and the implementing partner to ensure that beneficiaries were comfortable with the approach taken in light of delays to the commercial process.

Delivering and Sustaining Reforms: The bureaucratic bottlenecks are a major factor that affects the ease of doing business in Nigeria. This led to the setting up of the Presidential Committee on Ease of Doing Business (PEBEC) which is supported by PDF. The programme has embedded two advisors- The Senior Special Assistant to the President on Industry, Trade & Investment who heads the Enabling Business Secretariat and a supporting technical assistant. These EAs worked with key reform MDAs to develop the PEBEC National Action Plans which they also monitor. Additionally, in 2017, at the PEBEC’s request, PDF II commissioned a report to consolidate existing reforms, chart a way forward for reform priorities and ensure reform measures create tangible impacts for small businesses in Nigeria. Following the implementation of PEBEC’s National Action Points which cut across 13 MDAs relevant to shaping the business environment, Nigeria moved 24 places up to 145th position in 2018 from 169th in 2017. The use of extra-ministerial authority, deriving from the Presidency, was key to this success. PEBEC played the much-needed coordination role across selected MDAs, which is achieving desired results. Whilst it is unlikely that Nigerian will make any big gains in the 2019 rankings as no new laws were passed, PDF should continue to support this process. In addition, PDF should do more with agencies likely to be immune from the election cycle such as the NoTN and the NSIA while recognising possible delivery risks.

As the election season approaches and the uncertainty of election outcomes beyond the 2019 presidential elections heightens, it is likely that requests for technical assistance and requests for studies which inform policy making may slow. This period will be instrumental for the programme to take a step back and reprioritize its areas of engagement to champions of change within the new administration. It would be critical to review the roster of embedded advisor on a case by case basis. Also beyond the current annual review, the programme should look to revise its logical framework to ensure that milestones set are realistic.

Output Title	Relevant and high quality PDF II policy research, explorative studies and consultation products delivered to beneficiaries
Output number per LF		2	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of projects assessed as executed satisfactorily (as planned) or better during implementation	36	As of the time of this review, 38** projects assessed as satisfactory at implementation/Completion stage.
2.2. Beneficiary, user perceptions of relevance and quality of PDF II-supported policy studies and events	Relevance………………… 90% / Quality………………..…… 80%	Beneficiary feedback has been positive with projects scoring on average 93% on relevance and 85% on quality, above the log frame thresholds.
2.3. Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs….. 7	8

**In the year under review no projects under Output 2 were assessed as unsatisfactory. For further information on projects, please see Annex 1.

Provide supporting narrative for the score

Since the inception of the programme, PDF II has taken on a total of 74 projects under Output 2. Of these, 6 are in pipeline, 63 are closed (completed) projects, and 5 are ongoing. To manage the financial constraints on the programme which occurred during the year, most pipeline projects under Output 2 were put on hold or dropped, hence the Trade Policy Workstream therefore took centre stage for this output.

Exploring Other Opportunities Beyond Reports: Unlocking the Potential of Franchising in Nigeria and The Diaspora study.

Following the completion of the study on franchising before its last annual review and subsequent discussions with stakeholders to support the dissemination of the research, it was obvious that the legislative and regulatory framework guiding the Franchise Industry in Nigeria has been largely inadequate. In the past year, PDF has continued to support the development of franchising in Nigeria. A group of private sector businesses in collaboration with the Franchise Business Development Services (FBDS) developed a Franchise agenda for Nigeria. PDF II has continued to work with the group to implement aspects of the agenda by identifying and reaching out to key private sector actors identified to be invited as trustees of the association. Registration of the association is currently in process.

Diaspora Study

Following the delivery of the PDF II funded study on diaspora remittances, further work with the private sector led to the design of a Nigeria Middle Class study aimed at providing similar information on potential investment opportunities and interests of Nigeria’s middle class. In addition, the private sector identified crowd funding as a potential tool for diaspora investment which is untapped due to the Nigeria Securities and Exchange Commission’s (SEC) embargo pending issuance of regulations. The regulations had been expected for two years with no sign of movement. PDF II flagged this with the OVP which raised the profile of the issue at the Economic Management Team (EMT) and it is now being taken forward as part of a suite of reforms. PDF II has continued to push this agenda, and will look into possibility of working directly with SEC before and after the relaxing of regulations by the SEC.

Trade Policy Support: The political economy of trade policy remains challenging with certain groups dominating the policy discourse and many other local voices unrepresented. Rather than traditional institutional support, PDF II explored how it might strengthen the role of relatively weak exporter groups to feed into policy formulation as well as consider how it could work to reflect a broader group of manufacturers and businesses into policy discussions (including SMEs and the informal sector). PDF II designed a workstream through which the balance of its efforts is focused on the building blocks of long-term trade policy by strengthening alternative (or under-represented) voices that can feed into the policy processes. The work stream is now in its second year of operation. In the past year, PDF II Trade Work Stream deepened its relevance and impact through the strategic relationships it has built with high level champions of change and creating a platform for underrepresented voices to engage more in policy discourse. Two areas are highlighted below:

  1. The PDF II Trade Work Stream commissioned a study to map experiences of exporters of non-oil commodities in Nigeria. The aim of the study was to analyse and document the exporters’ experience on sequence, processes and costs for exporting products from Nigeria and thus, to bridge the knowledge gap in exporting by drawing up a clear sequential procedural map with costs and approximate durations for processing. This provided valuable evidence necessary to drive the reform efforts on ease of doing business. Feedback received from Ease of Doing Business Secretariat (EBES) confirmed that findings from the Exporter Experience study were used as inputs into the next round of reforms to be embarked upon in its National Action Plan III. These include:
- The automation of the NXP form (a form for export processes).
- Consolidating all reforms achieved thus far via the National Action Plans e.g. extension of the Executive Order on single joint examination to cover export cargo.
- Focus on regulatory agencies particularly as it concerns export activities.

In February 2018, with support from PDF II a non-oil export Community of Practice (CoP) was established for the purpose of advocacy, learning, capacity building, and development of Nigeria’s non-oil exporters’ participation in policy and exports. Some members of the group have come together to form a cooperative to facilitate members’ access to finance. The CoP was identified by EBES as a viable platform to monitor implementation of reform efforts by the CoP using the PEBEC report app to enable users report non-compliance of MDAs. PDF II continues to monitor developments in this area.

  1. As part of its support to trade facilitation and upon the request of the Managing Director of the Nigerian Ports Authority (NPA), PDF II commissioned a study to look at ports reforms and how to increase efficiency and block revenue leakages. There are early indications which suggest that some of the recommendations of the study were taken forward by NPA in various areas including:
- Inter-agency committee on the review of the ports concession agreements, which includes the Bureau for Public Enterprises.
- Submission made to Federal Ministry of Transportation have catalysed plans for the reactivation of rail system in Lagos Ports Complex and construction of new rail lines linking Tin Can Island Container Parks to assist in the quick and massive evacuation of cargo

A tracer study is on-going to assess the extent to which recommendations are being implemented and associated outcomes.

39.3	The third exporter dialogue (ED3) which addressed trade across borders provided enlightenment on the processes involved in trade policy negotiations, with a detailed review of the African Continental Free Trade Agreement (AfCFTA) and implications of signing for Nigeria. The non-oil export CoP gave their full endorsement for Nigeria to sign the AfCFTA agreement in a communique issued from the dialogue. It is hoped that through communiques and a radio program developed to highlight constraints and topical issues on exporting, the group will have a wider reach as it continues to advocate and address topical issues for reform in the sector.

Lessons identified this year, and recommendations for the year ahead linked to this output

The President requiring further stakeholder consultation on the AfCFTA should be seen by the programme as a challenge for further research and advocacy to support openness and a trade policy strategy. Openness, trade and competitiveness can sometimes be emotional subjects in Nigeria as most Nigerians hold an infant industry perspective; that Nigerian industries are at a nascent stage without the qualities to be internationally competitive. It was no surprise that after subsequent engagement with various stakeholders by the NoTN on the AfCFTA, the President redirected the head of the NoTN to have further engagements with local stakeholders. Subsequently, when the head of the NoTN conducted these consultations across various zones of the country, it was evident that while Nigerians were concerned about their livelihoods being affected by foreign competition, they were also for signing the agreement. This also underscores the need for constant communication with stakeholders on issues as unnecessary anxiety could ultimately torpedo an initiative which may ultimately benefit stakeholders.

Alignment with champions of change at high levels of the government of Nigeria ultimately ensures that outcomes will be achieved. The programme found a powerful ally within the Nigerian government interested in poverty alleviation in the OVP. The Office has taken on recommendations from findings on the diaspora and the exporter experience studies to nudge other agencies into action.

Gradually the CoP is evolving its role of galvanising disaggregated voices in the non-oil export sector. Members of the CoP represent every activity in the value chain as they have been drawn from the private sector, Business Membership Organisations and associations thereby bringing all the voices together as one community. The ability to leverage the pool of resources available in the CoP, the network of organisations and the unique value that a CoP offers to its members is what is needed to drive results.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The intended outcome of PDF 2 is that Nigeria’s ‘champions of change’ use increased capacity and evidence to enable them to pursue vital economic and social reform. The diagram below illustrates PDF II’s theory of Change.

While this review still considers the theory of change set-out in the PDF II business case (see above) to still be valid, some risks to delivery which were anticipated by DFID in the drafting of the ToC heightened during the year. These were generally around the realities of politics and struggles between arms of government. One key assumption related to the ToC is that; “The National Assembly is supportive of evidence-based policy priorities identified with PDF II support and approved budgets which are adequate for implementation”. In reality, there was the recognition that the passage of the budget has been late as in recent years as the Nigerian government has constantly struggled to meet its revenue projections. This was the case again over the last year. Despite the heightened risk, PDF has supported key achievements over the last year such as savings by the Efficiency Unit and better audits by the OAuGF. In addition, to translate outputs to outcomes, another assumption is that PDF II relies on sufficient capacity within MDAs (supported by other DFID programmes) to implement policies. As some DFID programmes closed, PDF leveraged on traditional partners to support its work (advocacy from other DFID Advisers along with support from the British High Commission). Thus, PDF has continued to operate in ways which leverages the full-suite of UK government influencing to ensure it has the most possible effect.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The Outcome indicator milestone for Indicator 1.3 and 2.3 is that the number of instances when beneficiaries can demonstrate that PDF II support directly influenced any of the 5 stages of policy formulation should be at least ten and seven instances respectively. As of this annual review, there have been 76 instances identified for output 1.3 and 8 for output 2.3. The number of instances range from EAs work at the OVP who coordinate the sub-national reforms around the ease of doing business, developing a Humanitarian Response Plan for the North East of Nigeria in collaboration with the UN, to developing a concept note on a call to action around gender issues and gender-based violence in emergencies. In addition, an assessment of delivery by beneficiaries (the average score based on beneficiary feedback is 93.5% on relevance, and 87.5% on Quality) implies that PDF II has been able to continue to deliver a high level of support that has been relevant to the success of beneficiaries’ reform agenda.

Explain major changes to the logframe in the past year (1/2 page)

No changes were made to the logframe.

Describe any planned changes to the logframe as a result of this review (1/2 page)

Following a recommendation in the 2017 annual review regarding how projects are counted, PDF II reviewed its portfolio and found that while Output 1 (mostly EAs) may lend itself to aggregation by work area to some degree, Output 2 (research studies, events etc.) was less amenable. While the new methodology for counting Output 1 projects was adopted, there have been no changes to the log frame. The new method enables PDF II to look at clusters of support provided in reform areas in a more strategic manner. However, this definitional change mid-way through the programme means that some metrics produced for assessment (financial and otherwise) of the programme, may not be directly comparable to previous years or PDF I. As the programme assesses comparability of output classifications over years and broader administrative implications of this change, it is clear that with a lower count of projects, relevant log frame milestones will need to be amended in the coming year.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The Value for Money (VfM) of PDF can be considered from the perspective of a portfolio of development interventions. As a portfolio, while not all interventions are expected to be successful, the overall portfolio should be able to demonstrate sufficient results to justify the overall cost of the programme. When a policy maker within the Nigerian government requests support on policy formulation, DFID responds by evaluating the political economy around the request in conjunction with the following questions: Is implementation possible? Can providing a solution help meet DFID’s objectives, can we provide a critical contribution? Can HMG influence for a better outcome? If the responses are positive, DIFD will provide support which is in cases where necessary, complemented with HMG lobbying for change. On the back of the interventions, the Outcome the programme seeks to achieve is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform. While vital “economic and social reform” may reflect a broad scope of operations, the reality is that the programme must be strategically selective on interventions to implement as it is limited by annual budgetary allocations. Therefore, there are instances where the programme would decline a request for support, and or revise the terms of reference associated with some support to achieve the desired outputs, or in some instances, cease support.

The following cases highlight instances where the programme had to be selective in its support: In 2016, PDF was approached by the Nigerian government to support the design of a follow-on programme to the largely successful Youwin! programme titled the “Entrepreneurial Investment Programme”. After discussions with DFID and the proposed beneficiaries, the DFID and the programme were not convinced that the approach and design was the right follow-on to YouWin! As a result, the programme did not support the programme. In another instance, a state government had requested support to develop some of its cottage industries. PDF was initially hesitant because the programme does not traditionally support projects at the sub-national level. Nevertheless, the programme engaged in discussions with the beneficiaries to explore possible opportunities. During discussions, it was realized that the programme would not be replicable across various states. The programme at that instance needed to decide between the state level intervention and another project; unlocking domestic investment via franchising. The programme decided to support a franchising project due to the potential to have a broader impact.

Re-pivoting an intervention: PDF’s support on the humanitarian response in the OVP was to provide M&E support to the North-East Humanitarian efforts. During PDF’s M&E processes, the programme picked up that the EA’s skill set were not well matched to the role. After several conversations with the EA, beneficiary and DFID, it was obvious that his skills and experience were better suited to Disaster Risk Management (DRR) for which there was also a need. His ToR was revised for this role to enable him focus on DRR, and reporting arrangements were also revised to better support him. The EA has since improved in his technical and administrative delivery and the project is running much better.

Withdrawing Support on an Intervention: An EA was contracted in the OVP primarily to support the operationalisation of the Nigeria Asset Decision Support System (NADSS) and secondarily to play a coordinating role amongst MDAs and MSMEs. During the course of his engagement, he delivered on MSMES development but failed to do so on NADSS. After various interventions by PDF II including developing an action plan to operationalise NADSS with milestones to help him stay on track; and consultations with DFID and the Deputy Chief of Staff (DcoS) in the OVP, PDF II suggested that his ToR be revised to 50% of whole time equivalent so that the EA could focus solely on MSME development while another consultant was engaged to work on NADSS. This was a viable solution to which DCoS was open, but the EA declined the 50% WTE offer. In addition, PDF declined extension of a contract to a consultant at the OAuGF as he was not delivering.

Whilst not all the results are monetizable, some are systemic and qualitative which are worth highlighting. Two instances highlight quantifiable results of the PDF approach in VfM (effectiveness) terms; PDF’s support to the Efficiency Unit and the Ministry of Environment. Also, the programme’s support to the OAuGF highlights a result while not quantifiable, is just as important.

The current fiscal challenges faced by the Nigerian government reflect the need for the government to be able to do more with less as the government’s budget is heavily skewed towards recurrent expenditure with not enough fiscal space for investments to support long term growth. This is why the savings delivered by PDF EAs become even more important. With a cost thus far of roughly £126,496, the EAs have been able to support the government save over £500 million from its top 5 expenditure items. Thus, for every pound the UK Government spent on technical assistance in this instance, Nigeria has been able to save £3,953 in excess expenditures.

Also, PDF’s support to the MoE assisted in raising over £20 million in Green Bonds with support to the ministry costing DFID £224,252 over the period. The EA supporting the ministry has helped develop a Green bond prospectus, set-up accounts and areas of authority across three key agencies/ministries- the DMO, the MoE and the Ministry of Finance. Under this instance, for every pound the UK Government spends on technical assistance, Nigeria is able to raise an extra £89 to support budgetary expenditures.

Finally, PDF’s EAs have supported the Nigerian government in enhancing transparency and accountability across government agencies. The OAuGF, leveraging on two EAs and other institutional support (from the NAO) has been able to enhance its audit procedures and has flagged a significant process gaps in the consolidation of government accounts. As a result, the OAuGF has issued a qualified audit to the Federal Government of Nigeria (the first in Nigeria’s history) highlighting the need for more standardized procedures in government financial accounting. The results listed above highlight the significant value of over £500 million which the programme could support with a budget of £18.5 million, thus, justifying the programme spend despite some interventions not materialising as anticipated.

Efficiency: DFID’s definition of efficiency is focused on the relationship between inputs and outputs (i.e., technical efficiency): How well do we or our agents convert inputs into outputs? (DFID, 2011, p.4). To ensure that there is a maximum likelihood of delivery to standards required by beneficiaries, project ToRs are carefully designed to document agreed deliverables and required skill sets. In addition, technical expertise is vetted to ensure it can deliver to the ToR outputs by reviewing consultants’ CVs and where required, interviewing prospective candidates. Where the beneficiary identifies a preferred candidate, and PDF II has concerns with delivery, this is flagged with the beneficiary and a recruitment recommendation made based on the requirements set out on the ToR. In addition, beneficiary feedback is obtained at various intervals to ensure contractors are delivering agreed outputs and contractor payments are tied to confirmation that outputs are delivered in line with the agreed ToR.

Economy: DFID’s guidelines[4] on economy asks the following question: Are we or our agents buying inputs of the appropriate quality at the right price? (inputs include things such as staff, consultants, raw materials and capital that are used to produce outputs) (DFID, 2011, p.4). Also, The PDFII business case states that at every annual review DFID will consider the economy, efficiency and effectiveness of the program across key areas such as:
[4] DFID. (2011). DFID’s Approach to Value for Money (VFM). Department for International Development, United Kingdom
- Average cost of embedded advisers (and benchmarked with other DFID programmes)
- Average daily cost of expertise brought in for policy studies and research (also benchmarked).

PDF continues to adhere to the strict cap in place for embedded advisers at £6,250 monthly. In addition, project activities and associated budgets for studies are carefully designed and negotiated to ensure value for money in the delivery approach. Below are the monthly ranges for cost of expertise for Output 1 (primarily embedded advisers fee) and daily ranges for cost of expertise brought in for Output 2 (policy studies and research) with average fees declining over a three-year period, showing the programme’s commitment to savings.

Table 3:

Description	Monthly Fee Rate (£)			Daily Fee Rate (£)
Period	2016	2017	2018	2016	2017	2018
Minimum	2,759	1,379	357	34	60	53
Mean	5,360	5,509	4,675	428	400	391
Maximum	6,250	6,250	6,250	870	985	1,200

In addition, the strict cap on rates has led to a reduction in average daily fee rates and a significant positive impact on economy during the transition of Embedded Advisers from the NIAF 2 and GEMS 3 programmes. Savings to DFID of about £20,000 per month were generated.

Table 4 shows the personnel cost per project for comparison between PDF I and PDF II based on a relatively conservative estimate of growth in the number of projects expected over the remainder of PDF II. Significant savings are the results of economies of scale relative to PDF I – over £2,000 per project, including the infrastructure portfolio. Table 5 shows that if the cost of the infrastructure portfolio is excluded this amendment delivers even more savings – about £3,150 (26%).

Table 4: Comparison of Cost Per Project under PDF I and PDF II
Description	Personnel Costs (£)	Total No of Projects	Avg. cost per project
PDF II (5-year projection)	2,293,716	231	9,930
PDF (5 years)	1,258,691	105	11,988
Variance	1,035,025	126	-2,058
Percentage Change	82%	120%	-17%

Table 5: Comparison of Cost Per Project under PDF I and PDF II (excluding infrastructure projects)
Description	Personnel Costs (£)	Total No of Projects	Avg. cost per project
PDF II (5-year projection less / Infrastructure)	1,705,816	193	8,838
PDF I (5 years)	1,258,691	105	11,988
Variance / Increase (£)	447,125	88	-3,149
Variance (%)	36%	84%	-26%

Despite challenges faced during budget negotiations with individual consultants and international consultancy firms, PDF II has largely been successful in maintaining the caps, while ensuring effective delivery of technical support to beneficiaries. A good illustration of this is the technical support to the Transmission Company of Nigeria implemented by Em-One Energy Solutions. PDF was able to strategically negotiate the initial budget downward from £943,914 to £628,801, a 33% reduction.

The average cost of committed funds per project as of August 2018 under output 1 and 2 are £139,763 and £48,831 respectively. This reflects an increase in the average cost of committed funds per project under output 1[5] and a decrease under output 2 from the previous year recorded at £78,248 and £52,287 respectively.
[5] As a result of a change in the methodology of project grouping and count means averages over the previous period will no longer be directly comparable.

In summary, the contracting process by the programme ensures that VFM is always a priority.
Before a contractor is hired, the terms of reference are designed to ensure that the project aligns to the necessary outputs and outcomes to ensure the project is ultimately relevant to the beneficiary. During the design of a project, opportunities to show considerations on gender and exclusion may not be clear cut but the programme ensures that due consideration is given to the impact of the project on women or girls, and how the project activities and outputs are proposing to harness opportunities, and mitigate risks on women, girls or excluded groups. The caps on embedded advisors ensures that the programme strives to obtain the highest quality technical expertise within limits of the pay scale agreed with DFID. Finally, contractor payments are tied to confirmation that outputs are delivered in line with the agreed ToR. The ToRs also ensure that considerations are made for how projects may impact on gender, equity as well as the environment.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

Based on results mentioned above and feedback from Beneficiaries, there is little doubt that the support provided by PDF to beneficiaries is appreciated and has provided them with capability to deliver impact during their term in office. Beneficiaries on average scored PDF II support 93.5% on Relevance and 87.4% on Quality, above log frame targets. The UK Government’s ability to be responsive and provide this type of support helps the UK to stand-out as a donor partner of choice and provides important political capital to the UK’s work in Nigeria. The programme has also made significant strides towards its milestone targets at the outcome level. Outcome Indicator 1.1 requires that the programme demonstrate 17 instances when beneficiaries can demonstrate that PDF II’s support directly influenced any of the 5 stages of policy formulation. As of this annual review, the programme has validated 18 instances under Outcome 1 and 4 instances under Output 2, already surpassing milestone targets set for 2020. Thus, the program meets necessary VFM considerations and should continue.

The PDF programme also aligns well with the new Africa Strategy to address long term issues that matter most for Africa’s prosperity. The programme supports policy makers who can make an impact on inclusive growth, trade, and economic partnerships (via research and technical support to the OVP, the Ministry of Budget and Planning, the Chief Economic Adviser to the President, the Finance Minister and more). The programme also supports climate change and natural resource management via technical advice to the MoE and supports stability within Nigeria via support on DFID’s North-East interventions.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: The overall risk remains Moderate for PDF II which continues to reflect the substantial uncertainty about the political environment for reforms, challenges to delivery and reputational risks. Thus, the major risks identified are classified as either external context or delivery risks or reputational risks (other risks identified are listed in the risk register attached). The past year has seen improvement on risk monitoring across the portfolio with the programme regularly collating and managing programme risks in line with DFID’s guidance. The section below highlights the main risks areas from the PDF II risk register and maps these against DFID Nigeria’s risk appetite.

External Context: A risk that there is insufficient political and managerial leadership, including capacity to drive through the wider organisational reforms in the Ministries, Departments and Agencies (MDA's) needed to support evidence-based policy implementation. This has been tested robustly under current administration. While embedded advisers confirm that their principals are pro-reform, the civil service poses significant constraints to implementation due to capacity issues and resistance to change.
Gross risk: Major

Mitigation: PDF II continues to raise awareness among EAs on the importance of identifying key Senior Civil Servants besides their principals who will act as enablers for their reform initiatives. EAs are encouraged to work with civil servants and ensure capacity building through transfer of skills and institutionalisation of reforms. Where possible, PDF provides organisational support to facilitate the change process and backstopping support/advice to EAs.
Net risk: Moderate

External Context: Whilst the operating context remains broadly positive, there is a risk that the newly elected government does not appoint its cabinet, or settle in and work efficiently (policy direction setting, policy formulation and implementation) in a timely way following the upcoming 2019 elections. Cabinet appointments took 7 months in 2015
Gross risk: Major

Mitigation: PDF II began identifying opportunities to support the administration in 2015 even in the absence of a cabinet. In advance, a PEA was conducted to identify key champions and an assessment on areas of government priority. These were used to sense check the balance of PDF II support to government. At mid-term (September 2017), government priorities were re-assessed, and the assessment has fed into programming decisions. A PEA was conducted at the end of June 2018. Findings are also being incorporated into programming to ensure that PDF positions itself well to consolidate successes and to seize opportunities following the coming elections, especially as the programme is in its final 18 months of implementation.
Net risk: Moderate

External Context: The National Assembly is not supportive of evidence-based policy priorities identified with PDF II support and does not approve budgets which are adequate for implementation. The NASS has been broadly supportive of policies in the executive's priority. However, progress has been slower than anticipated (e.g. the passage of the Audit Bill has taken almost an entire political cycle). The budget is rarely passed by the NASS on time and this also puts projects in priority areas at risk of not being executed.

Gross risk: Severe

Mitigation: PDF II work with embedded Advisers to look for solutions that are not dependent on government funding, and that make efficient use of the available systems/resources and private sector partnerships. Where specific projects are affected, PDF continues to strategize and support beneficiaries (the Executive) to engage with NASS to achieve resolution.

Net risk: Major

Delivery: Late passage of annual budgets by NASS (2017 & 2018) with attendant impact on appropriation, release and performance poses a general risk to government projects supported by PDF, which require funding from the federal budget. e.g. the Energising Education Projects may not receive budget allocation in 2018 or allocations are being stalled due to NASS on-going queries and allegation of non-compliance with provisions of Power Purchase Agreements (PPA) about the project.

Gross risk: Major

Mitigation: Focus on project preparation while waiting on funding. Early engagement with necessary procurement officers to ensure early allocation and early release of funds. PDF II also encourages consultants to look for innovative solutions and alternative sources of funding (e.g. private sector or other government institutions) where possible. e.g. The EA supporting the Chairman of PAC House of Representative approached NCC to provide hardware, and National Finance Council to provide software needed to achieve a paperless system for the PACs. On the energising education project, the senior infrastructure adviser continues to engage the National Assembly, while the communications team is working to create public awareness on the scope and objectives of the project. In addition, while the budget (for a calendar year) may not be passed in timely manner, there is the provision to spend approved amounts through June of the next calendar year.

Net risk: Moderate.

Delivery: There is significant risk to the Power Sector Recovery Programme (PSRP) if the requisite policy support and political will on the part of Government is lacking. There is also a technical capacity gap within the MDAs to implement various components of the PSRP. In addition, there are liquidity issues in the Nigerian Electricity Supply Industry (NESI) because of the inefficiencies of the Distribution Companies (DISCOs) in revenue collection, subsequent remittance to Bulk Trader (NBET) and the Generation Companies (GENCOS).

Gross risk: Major

Mitigation: This is being addressed through monthly Power Sector Operators meeting to deepen engagement with the relevant stakeholders in the industry such as DISCO, GENCOS, Gas Companies (GASCOs), relevant MDAs and the media to align their interests with the vision and policies of the Minister as it relates to PSRP implementation. The risk was flagged with GoN and government earmarked ₦701bn payment assurance intervention to support the Nigerian Electricity Supply Industry (NESI). Steps are also being taken to include funds in the budget to take care of further shortfalls as envisaged by the team.

Net risk: Major

Reputational: As the elections approach, there is the risk that DFID embedded advisors may engage in election activities and deviate from DFID guidelines on providing apolitical technical support to beneficiaries within the Nigerian government.

Gross Risk: Major

Mitigation: The programme has developed a code of conduct manual especially designed for the election season. It spells out the obligations and responsibilities of the embedded advisors.

Net risk: Moderate

Reputational: There is also the risk that some DFID embedded advisors may receive counterpart funding without DFID’s approval.

Mitigation: PDF’s contract spells out that an Embedded Advisor would need to contact PDF before taking on any additional projects.

Net risk: Moderate

Update on partnership principles

The programme does not use the Partnership Principles as formal conditionality in programming as no UK aid money goes directly to the Government of Nigeria. However, greater resources will be directed to those institutions that demonstrate greater commitment to the partnership principles. For instance, institutions committed to improving poverty reduction may be highly considered when determining the level of technical assistance that the programme provides. This will be used alongside political economy analysis of where job creation and poverty alleviation is likely to be championed within the Nigerian government.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The programme remains compliant with the terms of the contract. In the third implementing year of the programme cycle, the £13.2m managed fund earmarked for programme projects was fast depleting. This was primarily due to the on-boarding of another DFID programme’s technical advisers – NIAF. The contract amendment process began at the beginning of the first quarter of financial year 2018/19 to mitigate the risk of running out of funds before the planned project end date. Unfortunately, due to changes and modification of DFID internal procurement processes; PDF II was constrained by low funds for the most part of the year under review. DFID’s programme team together with PDF II in managing the potential reputational risk for DFID devised a strategy of quarterly contracts renewals for embedded advisers versus six-monthly or annual contracts while a considerable number of output 2 projects were placed on hold. At the end of this review the contract amendment has been finalised specifically on 1st October 2018. This contract has been signed based on the new terms and conditions.

The contract amendment has increased the total contract value by £2.6m; an overall increase from £15.7m to £18.3m. Timely completion of the contract amendment means PDF II can now re-activate output 2 projects in pipeline and the programme will be poised to respond to beneficiaries in April 2019, once the federal elections are concluded.

Financial performance of the programme during the period under review has been satisfactory in line with DFID’s measurement of financial performance; i.e. meeting forecasted spend and timely submission of monthly invoices. The programme has consistently submitted monthly invoices on or before the 15th of the following month as required. A key challenge from last annual review was the untimely invoice and report submission of EAs, upon which a 10% withholding fees was introduced to PDF II contractors for invoices turned in later than three months. A further significant improvement of PDFII’s financial management was recorded in this reporting year because of lessons learned from the previous year. The programme has achieved an average of 1% variance from September 2017 to August 2018 of forecast vs spend budget. PDF II has demonstrated a better understanding of financial management and prepared adequate mitigative measures for potential risks in ensuring they meet their obligation as stated in the contract regarding expectations on financial performance.

Month	Sep-17	Oct-17	Nov-17	Dec-17	Jan-18	Feb-18	Mar-18	Apr-18	May-18	Jun-18	Jul-18	Aug-18
% Variance	0%	0%	39%	4%	24%	3%	0%	-1%	0%	4%	1%	-4%

The delay in contract amendment has slightly shifted PDF II’s strong trajectory of hitting approved budget against its ODA target for this FY from 90% to 85%.

An independent programme audit has just been concluded which was assessed as unqualified and did not flag concerns of significant issue. This provides confidence of adequate robustness of financial and programme management to deliver on objectives. Progress on recommendations shared would be monitored closely. The Service Provider’s last annual audited statements (AAS) for the period ended December 2017 is being finalised and to be shared with DFID when completed. We do not anticipate any key issues or concerns.

Date of last narrative financial report(s)	Oct 2018
Date of last audited annual statement (s)	Oct 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

During the review period, the Annual Review team met with various beneficiaries and embedded advisors who work on the programme. For instance, there were meetings with the Chief of Staff to the Vice President, the Chief Executive of the Rural Electrification programme, beneficiaries within the Ministry of Finance (who oversee the Efficiency Unit) and more. Conversations with the beneficiaries highlighted the relevance of PDF’s support and the recognition that PDF’s technical assistance has helped their ability to deliver on key policy issues.

Evidence (1/2 page)

The evidence gathered on PDF’s support on the stages of policy formulation highlight the importance of the programme. Total number of instances counting PDF’s support on the stages of policy formulation cited in this year alone is 76 for Output 1, and 8 for Output 2. In addition, the realities of politics have heightened some of the risks envisioned during the conception of the programme. For example, the assumption that the National Assembly would approve budgets which are adequate for implementation has come into question over the last year. Nevertheless, in some sense this assumption holds that while budgetary allocation may by low, there is still some support from the NASS. Also, the lack of other DFID programmes (NIAF and GEMS) have also heightened some risks envisaged on PDF’s ability to deliver (which was to be in conjunction with the programmes).

Learning (1/2 page)

From the inception of PDF II, a monitoring and learning system was set up as part of the KM system. The monitoring and learning system which complements formal reports from EAs and consultants has continued to enable PDF II to not only capture key learning and evidence but also ensure that EAs work more collaboratively and learn from each other. The following monitoring arrangements are being used:

- Interim and exit interviews: These interviews have continued to reveal process learning as well as shedding more light on achievements, lessons risks and mitigation measures. For each EA two interim interviews are held in the course of a year and exit interviews are held at the end of their assignment.
- Annual reviews and beneficiary feedback: A sample of PDF II’s Output 1 projects are reviewed annually to assess the extent to which outcomes have been achieved and if beneficiaries still find the support relevant. These are held at one-year mark for EAs whose projects are extended for another year.
- PDF’s assessment of projects across relevance and quality domains: PDF II internally assesses all projects across outputs 1 and 2 across the relevance and quality domains. The beneficiaries are also required to carry out a similar assessment for each EA.
- Anecdote Circles: two anecdote circles were held in November 2017 and April 2018, which brought EAs together to share experiences on ‘the working pace of government’ and ‘the availability of government resources’ in November, and ‘sustainability of PDF II’s on-going reforms’ in April.
- Semi-formal event: These are held at the end of every calendar year to encourage networking and learning on broader/over-arching issues. The last one focused on the implementation of ERGP
- Technical back stopping event: Technical backstopping sessions are used to provide insights and new evidence to EAs to enhance their work. These are held twice every year. The last one which held in July 2018 looked at the use of extra-ministerial authority in pursuing reforms.

Over the next year, case studies around major policies that have been introduced with support from PDF 2 should be carried out with an attempt to monetise the attribution to the programme where possible and credible.

Progress on recommendations from previous reviews (1/2 page)

The programme implemented all recommendations from the last annual review. Please see the annex attached.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g. on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided