Type of Review: Project Completion Review

Project Title: Universal Elementary Education
(Sarva Shiksha Abhiyan)

Date started: 11/03/2008	Date review undertaken: 7-28 March 2013
## Introduction and Context
What support did the UK provide?
DFID supported the Government of India’s flagship elementary education programme, Sarva Shiksha Abhiyan, to provide universal access to good quality education for children from 6 to 14 years. Between 2010/11 and 2012/13 DFID provided £140 million in financial aid, along with £6 million in technical co-operation to help strengthen India’s national learning assessment system and evaluate pilot initiatives to improve the quality of education. / Table 1 below summarises the funding support DFID has provided to SSA over the period 2003 to 2013. The table is also instructive in that it shows how DFID support has evolved over time to place more emphasis on technical cooperation and latterly greater funding of innovation and operational research – reflecting a growing appreciation of where, how and why DFID support can work best and the need to disseminate this more widely[1]. / Total budget: £509 million over a period of 10 years from 2003 to 2013 (£495 million Financial Assistance (FA) and £14 million Technical Cooperation (TC)). / Phase / Period Total Budget FA TC Of which Innovation Expenditure / Phase – I: 2003-2006 £210 million £210 million 0 0 / Phase – II: 2007-2010 £150 million £145 million £4 million £0.5 million / Phase - II Extension: 2011-2013 £149 million £140 million £8 million £1.5 million / Table 1
[1] The availability of funds to support innovation greatly increased DFID India’s scope for engagement and influence. This contrasts with findings relating to DFID education programmes in East Africa as highlighted by the recent ICAI evaluation report on DFID’s health and education programmes in Bihar.

What were the expected results?
SSA, which was launched by the Government of India’s in 2002 aimed to: / provide 8 years of elementary school education for all of satisfactory quality; / bridge education gaps between boys and girls and different social categories; and / make sure all children stay in school. / The Government of India implemented SSA in partnership with state governments, using / government systems. Around 85% of SSA resources are targeted on India’s 12 poorest states. There are norms that determine the activities that SSA supports, which DFID and other development partners (the World Bank and European Union) have agreed. / What changed as a result of our support? / More children stay at school than otherwise has been the case and achieve better learning outcomes. Key purpose level targets over the programme period were: / 1. Retention rate at primary level increases from 75% to 80%. / 2. Improvement in learning levels at Grade 3, 5 and 8 (i.e. age 9, 11, 14). / While DFID programme funding has now ended, SSA itself will continue and it is therefore not expected that all targets should have been met at the time of compiling DFID’s own PCR. Nevertheless, achievements are impressive. The 17th Joint Review Mission of SSA, reporting in January 2013, presented these achievements as follows, drawing on ‘District Information System for Education’ (DISE) official data: / Targets exceeded / Figure 1 / Targets Met (or nearly met) / Figure 2 / Targets, where significant further progress still needs to be made / Figure 3 / What were the planned outputs attributable to UK support? / DFID provided around 2% of total SSA funding; and attributes 2% of the overall programme results. For the three years of support, the project achieved the following: / (i) Increase in percentage of children who stay in school until Grade 5 from 78% to 82%. / (ii) Increase gross intake to the last grade of primary (Grade 8) by 10,500 (from 350,000 to 360,500). / (iii) Directly supported 60,000 in elementary education / (iv) Increase in the percentage of children who after 2 years primary schooling have sufficient reading fluency and comprehension to 'read to learn' from 25.7% to 27.5%. / (v) Built 6,000 new classrooms / (vi) Trained 90,000 teachers / How will we determine whether the expected results have been achieved? / We monitored SSA results using Government of India’s data systems, including District Information System for Education (DISE), complemented by independent data reviews commissioned by DFID. We took part in twice yearly monitoring with the Government of India through Joint Review Missions and carried out internal annual reviews and regular progress analysis.

What was the context in which UK support was provided?
What need did we try to address? / When this third phase of the programme was initiated, good progress was evident with increasing access to schooling across India, and India being on track to achieve universal primary education (MDG 2) (for enrolment but not completion) and gender equality in primary education (MDG 3). However, 8.1 million children continued to be out of school, mostly children from disadvantaged groups. Major challenges remained with ensuring children stay at school (current retention rate is 74%) and receive quality education that ensured they are learning well: research showed that only about half of India’s ten year-olds could read a simple paragraph. Critically there was no national learning assessment that was comparable overtime – hence no meaningful learning benchmark. / What did we do to tackle this problem? / DFID’s support was aimed at tackling the challenges of expanding upper primary schooling (11-14 years) and improving the quality of education. In addition to financial aid, DFID’s technical assistance’s objective was to strengthen the implementation of SSA overall – for instance, by bringing experience from other countries’ education systems and advising on teaching methods. In particular, DFID’s technical support was used to help India to expand and strengthen its student assessment system; in particular introducing new techniques that enable comparison of results over time so there is better information available on what children learn in school and how government schools are performing. This is essential for improving the performance and accountability of the elementary education system. / DFID India saw SSA as a potent vehicle primarily to support national progress on Indian achievement of MDG 2 and 3. However, DFID India wished to move beyond a focus on school attendance and support meaningful learning. Thus DFID’s support took a ‘finance plus approach’ focusing technical support on three key areas (i) learning outcome measurement as a pre-requisite for informed performance improvement (ii) teachers as drivers of change, and (iii) evidence and innovation to promote debate and demonstrable impact through small scale catalytic innovation. / Theory of change for DFID’s technical assistance support to SSA:

## Section A: Detailed Output Scoring

Output 1: All Children in School
Output 1: final score and performance description: A+ / SSA has been hugely successful in the transformation it has achieved in bringing children into school. This needs to be appreciated in the context of: the access it has created; the increases in actual enrolment that have been achieved; the major decrease in numbers of out-of-school children; the improving levels of retention in school that have occurred; and the substantially increased transition rates from primary to upper primary schools – and hence the increasing numbers of children that are now completing a full 8-year cycle of elementary education. / Quantifiable evidence against each of these parameters is presented below. / Final results: / DFID selected three logframe indicators for Output 1, as follows: numbers of out-of-school children; transition rates from primary to upper primary schools; and student attendance. Changes against a 2010 baseline, and in relation to the target set, are shown below:
Output 1: DFID Logframe Indicator 1.1 / Out of School Children / 2010 Baseline Target Achieved / All 8.1 million All 5.1 million All 3.2 million / Boys 4.1 million Boys n/a Boys n/a / Girls 4.0 million Girls n/a Girls n/a / SC 2.3 million SC n/a SC n/a / ST 1.0 million ST n/a ST n/a / Muslims 1.9 million Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural 7.0 million Rural n/a Rural n/a / Urban 1.1 million Urban n/a Urban n/a / Data Source: AWP&B 2012-13

Output 1: DFID Logframe Indicator 1.2 / Transition from Primary to Upper Primary / 2010 Baseline Target Achieved / All 83% All 83% All 87% / Boys 83% Boys n/a Boys 86% / Girls 83% Girls n/a Girls 87% / SC n/a SC n/a SC n/a / ST n/a ST n/a ST n/a / Muslims n/a Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural n/a Rural n/a Rural n/a / Comment: Latest Data Source = DISE 2011-12, which may not fairly reflect the end of project situation
Output 1: DFID Logframe Indicator 1.3 / Student Attendance / 2010 Baseline Target Achieved / All 74% All 80% All n/a / Boys n/a Boys n/a Boys n/a / Girls n/a Girls n/a Girls n/a / SC n/a SC n/a SC n/a / ST n/a ST n/a ST n/a / Muslims n/a Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural n/a Rural n/a Rural n/a / Comment: no more recent data on student attendance, since the date of the baseline, have become available
However, the robust evidence base for reaching conclusions about achievement of Output 1 is far broader. What can also be taken into account is: increased access; increased enrolment; changes in gross enrolment ration at primary and upper primary levels; and reduced dropout and increased retention. Data against these parameters are presented below:
Increased Access: With regard to extension of access, the achievements of SSA are staggering. According to official data, the 30 May 2012 position was as follows: / 176,131 new primary schools have been completed or construction is in progress (91.3% of target). / 102,831 new upper primary schools have been completed or construction is in progress (96.1% of target). / 1,277,411 new classrooms have been completed or construction is in progress (96.8% of target). / Consequently, based on an average classroom size of 3.7 classrooms in India, and assuming a ratio of 1 classroom per 40 students, it is calculated that access has been extended to accommodate over an additional 100 million children[2].

Figure 5		Increased Enrolment: Figure 5 shows the clear upward trends to be observed in primary and upper primary enrolment. According to DISE data for 2011-12, 199 million children are enrolled in elementary education and enrolment trends. The trend in upper primary school enrolment is stronger. There has been some stagnation at primary level since 2007-08, though this is possibly to a decline in the child population and the reduction in the number of over-age and under-age children attending primary schools. / Figures 6 and 7 clearly demonstrate the significant increase in Gross Enrolment Ratio, nationwide, at primary and upper primary levels – comparing the two periods 2005-06 and 2011-12.
Figure 6		Figure 7
Reduced Dropout and Increased Retention: The comparative data presented in Figure 8 show substantial improvement in annual dropout rates, between the two periods 2004-05 and 2011-12. The overall percentage dropout has reduced from 10.6% to 6.5%. Figure 8 presents dropout data year by year and by Grade. The substantially higher ‘dropout’ rate for Grade 5 is, in fact, essentially a transition issue as the figure mainly depicts the number of children who complete their schooling at the end of the primary cycle, rather than progress to upper primary school.
Figure 8	Figure 9
In respect of the transition rates captured in logframe indicator 1.2 above, Figure 10 shows graphically the changes that SSA is bringing about: a direct result of the intervention of building large numbers of upper primary schools, to reduce the ratio of primary to upper primary schools and thus creating upper primary school access.	Figure 10
Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[2] Smawfield, David (2013) Civil Works and Infrastructure: Sarva Shiksha Abhiyan. New Delhi: DFID.

Output 2: Bridging Gender and Social Gaps
Output 2: final score and performance description: A+ / SSA has been hugely successful in bridging gender and social gaps. Among targets exceeded is what has been achieved in terms of girls’ enrolment as a percentage of total enrolment at both primary and upper primary levels. The grade V national achievement survey also recorded no significant differences between the achievement of girls and boys. Among targets met is the number of children with special needs enrolled in school. Very significant progress has been made in bridging other social gaps and in the provision of relevant inputs such as girls’ toilets and the number of schools with female teachers. / PROBE, a respected independent review of ten years of SSA, concludes: / Stark social disparities in school enrolment have virtually disappeared at the primary level, whether it is the gap between boys and girls, or that between children of different communities. Enrolment rates among SC children (94%) and Muslim children (95%) are as high as the sample for all children (95%).[3]
Final results: / DFID selected three logframe indicators for Output 2, as follows: percentage of schools with girls toilets; completion rates for both primary and upper primary level schooling; and numbers of children with special needs enrolled. Changes against a 2010 baseline, and in relation to the targets set, are shown below:
Output 2: DFID Logframe Indicator 2.1 / Percentage of Schools with Girls Toilets / 2010 Baseline Target Achieved / 58% 70% 69% / Comment: Latest Data Source = DISE 2011-12, which may not fairly reflect the end of project situation
Output 2: DFID Logframe Indicator 2.2a / Completion Rates for Primary / 2010 Baseline Target Achieved / All 96% All All n/a / Boys n/a Boys n/a Boys n/a / Girls n/a Girls n/a Girls n/a / SC n/a SC n/a SC n/a / ST n/a ST n/a ST n/a / Muslims n/a Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural n/a Rural n/a Rural n/a / Comment: no more recent data on primary level completion rates, since the date of the baseline, have become available
Output 2: DFID Logframe Indicator 2.2b / Completion Rates for Upper Primary / 2010 Baseline Target Achieved / All 96% All All n/a / Boys n/a Boys n/a Boys n/a / Girls n/a Girls n/a Girls n/a / SC n/a SC n/a SC n/a / ST n/a ST n/a ST n/a / Muslims n/a Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural n/a Rural n/a Rural n/a / Comment: no more recent data on upper primary level completion rates, since the date of the baseline, have become available
Output 2: DFID Logframe Indicator 2.3 / Number of Children With Special Needs Enrolled / 2010 Baseline Target Achieved / 2.5 million 2.65 million 2.87 million / Data Source: AWP&B 2012-13
However, the evidence base for reaching conclusions about achievement of Output 2 is far broader. What can also be taken into account is: reduced social gaps; annual dropout rates for different social categories; progress made not only enrolling children with special needs, but also identifying them in the first instance; and progress made against other equity focused indicators such as percentage of schools with female teachers, girls as a percentage of enrolment at primary and upper primary levels, and percentage of schools with an access ramp for wheelchair users. / Data against these parameters are presented below:
Reduced Social Gaps: The proportion of children from educationally disadvantaged communities such as SC, ST and Muslims enrolling in schools has been steadily increasing.
Figure 11	Figure 11 focusing specifically on dropout patterns is instructive in that it not only shows that girls’ dropout is invariably lower than overall dropout in all categories, but that different social groups do not dropout at rates that deviate very significantly for the school population as a whole – and that other backward classes in fact fare significantly better. Indeed, statistics also show that the proportion of children from socially disadvantaged groups such as scheduled castes, scheduled tribes and other backward classes enrolled in government primary schools is now greater than their share of the population.
A significant exception, however, is the share in enrolment of Muslim children, which remains short, at upper primary levels, of the population proportion of Muslim children. One theory for the strong representation of disadvantaged groups is that government schools cater more to poor and marginalised groups and that forward caste groups do not access government schools to the same extent[4]. While not captured in the data there is also growing concern about the state of provision educational provision to schedule tribes –where: language, nutrition and the challenges of operating in remote and often Naxalite guerrilla operations combine.
Successes Identifying and Enrolling Children with Special Needs: The data presented in Figure 12 show the increasing success that SSA has had in both: (a) identifying children with special needs; and then (b) bringing these children into the education system. Not only have the children been brought into the system but, after successful special pre-integration programmes, many have been mainstreamed into regular schools. / Strong Progress Made in relation to Equity focused Input Indicators: Strong progress has also been made in relation to a number of equity related input indicators, as the three examples in Figure 13 show.	Figure 12
Figure 13

Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[3] Anuradha De, Reetika Khera, Meera Samson and A. K. Shiva Kumar (2011) Probe Revisted: A Report on Elementary Education in India. New Delhi: Oxford University Press.
[4] Technical Support Group (2012) Inclusion and Exclusion of Students in the School and in the Classroom in Primary and Upper Primary Schools: A qualitative study commissioned by Sarva Shiksha Abhiyan, MHRD, Government of India. Principle Investigators: Vimla Ramachadran and Taramani Naorem, p. 29.

Output 3: Education of Satisfactory Quality
Output 3: final score and performance description: A+ / Numerically, SSA has substantially increased the percentage of trained teachers; substantially improved the condition of classrooms; substantially reduced the size of large classes; substantially reduced the number of single teacher schools; and substantially increased the availability of computers. These are all important proxy indicators of enhanced educational quality. DFID’s further distinctive contributions are (i) the way it has helped to forward, support, and influence the policy debate around the importance of learning outcomes – the ‘acid test’ of educational quality – together with building capacity in this regard; and (ii) in the successful way it has supported research and innovation with a quality focus – initiatives that have produced solid results and new knowledge that have fed back into both the Indian system and more widely. / DFID’s main focus in the current phase of SSA has centred around: / Building capacity at both central and state levels in modern learning assessment techniques and impact evaluation – in particular focus on approaches that enable comparison over time. / Contributing to the policy debate / Supporting national policy development / Promoting innovation / All of this has been to raise awareness of the importance of learning outcomes; and help place learning outcomes far more centrally and prominently in policy debate. Additionally, DFID has then gone on to make a significant contribution to building capacity in this important technical area. / Thus, DFID’s value addition and contribution to quality is captured not just in a percentage attribution of big numbers, but also in other ways. Furthermore, over and above DFID’s learning outcomes focus, its contribution has also: / helped to increase the rigour with which SSA is supervised; / helped to improve the technical quality of programme management and design and strengthened monitoring evaluation arrangements; / directly supported technical improvements in Indian education, particularly in relation to learning assessment, pedagogy, teacher development, curriculum development, materials development, research, monitoring and evaluation; / provided policy advice which is sensitive to and understanding of India’s machinery of government in education; / given, together with other development partners, greater credibility to GoI programmes; / shared international experience, know-how and best practices; / helped to boost the confidence and capacity of implementation staff at central and state levels.
Figure 14	Figure 14 captures illustratively the kinds of way in which DFID has helped to influence SSA and its strategic direction. More recent JRM Reports, dating from the 14th JRM report onwards, show a marked change of emphasis in relation to learning outcomes. A 14th JRM recommendation, proposed by DFID, led to the constitution and report of a Committee ‘to review class V draft NAS report and develop strategic plan for the achievement surveys in the country and its communication plan’. The Committee’s Report (the ‘Panchapakesan Report’) was tabled in July 2012. / The reactivation of a ‘National Resource Group’ for curriculum planning, pedagogy and evaluation methodologies was a specific recommendation of the 16th JRM.
The most recent, 17th, JRM adopted a ‘number one’ key recommendation that: / With immediate effect, shift programme emphasis to learning outcomes. This should find reflection in future AWP&Bs. In consultation with relevant stakeholders, adopt a revised format for future JRM Aide Memoires that addresses ‘Learning Outcomes’ specifically. / DFID staff were involved in tabling this recommendation to the JRM.
Final results: / DFID selected three logframe indicators for Output 3, as follows: percentage of teachers receiving in-service training; teacher attendance; and availability of teaching and learning materials. In respect of these indicators, changes against a 2010 baseline, and in relation to the targets set, are shown below:
Output 3: DFID Logframe Indicator 3.1 / Percentage of Teachers Receiving In-service Training / 2010 Baseline Target Achieved / 78% 85% 83% / Data Source: AWP&B 2012-13
Output 3: DFID Logframe Indicator 3.2 / Teacher Attendance / 2010 Baseline Target Achieved / 85% 90% n/a / Comment: no further data on teacher attendance, since the date of the baseline, have become available
Output 3: DFID Logframe Indicator 3.3 / Availability of Teaching and Learning Materials / 2010 Baseline Target Achieved / 99% 100% 95.7% / Data Source: State Report Cards 2011-12, which may not fairly reflect the end of project situation.
A number of further indicators provide a proxy basis for drawing even stronger conclusions as to the impact SSA has had in raising the quality of education. This is especially when changes over time in relation to such indicators can be demonstrated. As alluded to above, and what the table below shows, among these indicators are the following. Against each indicator, what is also explained is the link/assumption that is made concerning how quality is effected: / Indicator: Assumed impact on ‘Education Quality’ / Percentage of trained teachers All other things being equal, trained teachers perform more effectively in the classroom than untrained teachers. / Percentage of classrooms in good condition The condition, i.e. quality, of the physical learning environment impacts on the quality of education that is provided. / Class size Very large class sizes impact adversely on educational quality, particularly with younger and pre literate groups. It is more difficult for teachers to provide individual support and attention to individual students; and more difficult to organise practical activities and group work, etc. The physical environment is also less ‘child friendly’ from the perspective of students. / Percentage of single teacher schools It is far more difficult for a single teacher to take simultaneous responsibility for student learning across five grade levels. The learning environment is much more vulnerable as everything depends on the attendance, commitment, and quality of that one teacher. / Availability of computers Computers can enrich the curriculum and opportunities for learning in many ways. The development of computer literacy is itself now considered an essential life skill by many. / Availability of textbooks and other learning materials Quality textbooks and other learning materials help teachers to teach more effectively and students to learn more effectively on an independent basis at their own pace. / Retention rates These can be equated to ‘voting with one’s feet’. If education is perceived as becoming more worthwhile, and teaching is more interesting and relevant (i.e. ‘better quality’) children are more likely to stay in the system. / SSA can be demonstrated to have had a very significant impact against all of these parameters. As Figure 15 helps to show, SSA has strong performance to demonstrate:
The overall trend for the percentage of trained teachers over the most recent seven-year period is a positive one, though there has been some tailing off of momentum in the most recent four-year period. The percentage of classrooms in good condition has risen steadily over the most recent seven-year period Teacher pupil ratios have declined steadily (a positive trend) over the most recent six-year period. / The percentage of single teacher schools has fallen steadily (a positive trend) over the most recent six-year period. The percentage of upper primary schools with computers between 2008-09 and 2011-12 has risen significantly. The indicator illustrates only one aspect of teaching and learning martials provision overall, but it manifests the only trend in the six data sets presented here not to show a positive pattern – reinforcing the evidence presented under ‘Results’ above: that this is a target area where more progress needs to be made under the remainder of the SSA programme.
Figure 15
With regard to improving levels of ‘Retention’ as a proxy indicator of educational ‘quality’, as data presented in Figure 9 under ‘Output 1’ above show, SSA has achieved marked positive trends: ‘retention’ correlates inversely with ‘school dropout’.
Strengthened National Assessment: / DFID’s technical co-operation in SSA was expressly conceived to strengthen the capacity of National and State levels in learning assessment systems and conducting programme evaluations. This component of the programme has demonstrated strong results, including what has been referred to above. It has directly helped to develop India’s institutional capacity (NCERT) to lead a national assessment programme (grades iii, v and viii) and programme evaluations, providing a much-needed platform for quality monitoring, diagnostic analysis, remedial action, better resource targeting and improved school accountability. DFID’s advice has also enabled the first Indian engagement with international learning assessment - OECD’s Programme for International Student Assessment (PISA). / The growing recognition of and capacity to undertake rigorous diagnostic learning assessment is a transformational achievement in itself. Part of the credit for this should go to the DFID funded technical cooperation fund (TCF). Working with MHRD and staff of the National Centre for Education Research and Training (NCERT) capacity to administer and analyse learning assessments has been greatly strengthened. In particular, the TCF has enabled the adoption of Item Response Theory (IRT): the international standard approach for learning assessment that enables the results to be compared over time. TCF staff have worked alongside NCERT colleagues in the administration of a ‘Baseline Achievement Survey’ (BAS) and a ‘Mid-line Achievement Survey’ (MAS). The latter, which involved over 84,000 students in 7,000 schools, gives some indication of the scale of logistical challenge. Together, both surveys represent a significant step forward in the objective measurement of learner achievement in India. The National Achievement surveys are scheduled on a three year cycle. The grade V NAS is the first use of IRT and as establishes a baseline for learning. While DFID has not used NAS for detailed project monitoring (DFID opted for the less scientifically robust but annually produced ASER ‘snapshot data’) it has used NAS outcomes in detailed policy discussion. Encouragingly, findings from NAS are now appearing in high level government discussions. Most recently in the education ministers response to a question on learning outcomes in the national parliament[5]. / The TCF and senior DFID adviser have also played an instrumental role in supporting the ‘Panchapakesan Committee’, which was set up to advise on a national achievement strategy for India. Overall, while it cannot be denied that learning levels in India are disappointingly low, the technical foundations are in place to undertake diagnostic learning assessments of sufficient diagnostic power to identify learning bottlenecks and inform appropriate remedial actions. / Additional to the above, DFID technical assistance has contributed directly in increasing the capacity of almost 100 faculty members from the National Institute of Education, Regional Institute of Education, State Council for Educational Research and Training, and SSA State Project Offices. This has included workshops and training; and exposure to best practices, including providing opportunities to participate in international conferences. All of this activity has been focused on two main technical strands: capacity building for, and the subsequent delivery of, National Achievement Surveys; and programme evaluation of quality initiatives. / The aide memoire of the 16th Joint Review Mission (JRM) of SSA specifically mentions the contribution of the NAS Review and Strategic Planning Committee and its helpful recommendations on making National Achievement Survey a continuous, rolling programme as a ‘Health Check’ of the education system that extends beyond monitoring and increase emphasis on systems diagnosis. / Among significant documentary outputs of the technical assistance, contributing to knowledge, are the following examples: / Children’s Learning Acceleration Programme for Sustainability (CLAPS), Andhra Pradesh: Programme Evaluation Study. 2011. / Multi-Lingual Education in Orissa: Programme Evaluation Study. 2011. / Programme Evaluation Report: Aadhar Quality Initiative Himachal Pradesh. / Programme Evaluation Report of Activity Based Learning, Tamil Nadu. 2011 / The SSA Technical Cooperation Fund also supported the execution and subsequent report by the National Council of Educational Research and Training of the (2012), National Achievement Survey for Class V. This was the first substantive report of its kind. The technical support group also assisted in producing a user friendly summary version – What do they know ? A summary of India’s National Achievement Survey, Class V, Cycle 3, 2010/11 / Promotion of Innovation and Evidence Generation: / Since 2010, and in addition to its programmatic support to SSA, DFID India has made a notable effort to promote innovation and made important contributions to evidence generation. / Gyan Shala: is an innovative programme delivering quality schooling to children living in some of India’s most deprived slums. Working in collaboration, the DFID India education team and the FCO/DFID funded South Asia Research Hub (SARH) put in place a research programme that firstly established the efficacy, equity and value for money of Gyan Shala (as a precursor for UK Aid investment). This found Gyan Shala as effective – reaching the most disadvantaged and delivering better learning outcomes, achieving higher levels of teacher and student attendance at substantially lower cost than government and low fee private school counterparts. This evidence justified DFID investment of close to a million pounds (September 2011- March 2013) to enable: / Gyan Shala to scale up to cover an additional 28,000 children in Gujarat and Bihar, with increased focus on Muslim girls in Bihar Sharif; / Strengthen knowledge on PPP approaches and their broader feasibility in response to urban schooling provision / DFID engagement in Gyan Shala has gone beyond a focus on deliverables to a focus on learning. Findings from the SARH studies are informing broader DFID debate on engagement with private education and the role of PPPs. A paper[6] co-authored by DFID India’s senior adviser has appeared in the leading international journal on education and development and was cited at an All Party Parliamentary Group on Global Education for All debate on donor support to low cost private schools, 5 December 2012. The APPG's notes are available at http://bit.ly/ZiGykt. / STIR: ‘Schools & Teachers Innovating for Results’ (STIR) (August 2012 to March 2013; budget £284,345) is specifically designed as a lessons learning project, It focuses on unleashing the potential of frontline professionals to deliver substantive and sustainable improvement. STIR applies business practices in innovation search, selection, brokering and convening to identify, incubate, scale and trial promising ‘micro-innovations’ – small-scale, low cost practices in classrooms or in the way schools are run In pursuing this quest STIR have focused in on the teacher and principal as critical innovators and change agents. / DFID provided seed funding to STIR. The project has subsequently been successful in linking with substantive scale up partners such as the Azim Premji Foundation, Bharti Foundation, Teach for India, Pearson, Pratham; and the national education ministry – all of whom have signed up to ‘trial’ these innovations in new contexts. STIR has also secured the services of JPAL and the Education Endowment Foundation to evaluate whether the innovation transplant delivered impact. In addition to local news coverage, the STIR programme to promote innovation has received international coverage in: The New York Times (http://www.nytimes.com/2013/03/04/world/asia/04iht-educside04.html?pagewanted=all&_r=0); The International Herald Tribune; and the Economist. / In Madhya Pradesh - School Quality Assurance Framework / DFID is providing accountable grant funding of £213,000 to the Madhya Pradesh government and UK charity ‘ARK’ for the development of a simple school focused (Quality Assurance) observation framework. This will provide actionable advice for school management, and also from which data can be aggregated to give an overall picture of the standard of school provision to system administrators. DFID has confined its funding to developing the framework and piloting its implementation. Most recently, DFID has received political commitment that the State government is keen and prepared to fund this initiative to take it to scale. More widely, this is a growing area of interest – the work of Ofsted was one of the highlights of the recent visit to UK of the Indian Minister of Education. / Support of Quality Research, with Research Outputs feeding back into the System: / Under SSA, DFID India has directly supported a number of research and knowledge dissemination activities. These include: / Sponsorship of a high-level Indian delegation (Government, Private Sector and NGO) to participate in a GPE international workshop on early grade reading. / Four regional workshops and the publication and dissemination of associated proceedings on teacher management and education. / A detailed study on caste based exclusion and workshops on how to build inclusive classrooms for all. / Funding Indian teacher participation in workshops on English language. / DFID India education staff also provide intellectual support and ensure centrally DFID programmes engage with and support the SSA programme. This includes representation on the advisory board of the ‘Young Lives’ research programme and providing technical advice on the Civil Society Challenge Fund and Girls Education Challenge Fund. The most recently published work in these areas includes work on school accountability and governance – through score cards (with CfBT). This has shown dramatic results, as reported in: / Community-based accountability for school improvement: A case study from rural India. http://www.cfbt.com/evidenceforeducation/PDF/CfBT%20%20Rural%20India%20%20web.pdf / ‘Young Lives’ work in Andhra Pradesh has also produced some very important work, particularly on low fee private schools, and most recently relative teacher performance: / Renu Singh and Sudipa Sarkar Young (2013) Teaching Quality Counts: How Student Outcomes Relate to Quality of Teaching in Private and Public Schools in India. Lives Working Paper 91. http://www.younglives.org.uk/publications/WP/teaching-quality-counts / In 2009, the DFID India Office hosted DFID India’s entire education cadre for a professional development, immersion, visit to the Activity Based Learning programme in Tamil Nadu. Subsequently, the programme has been visited by Ethiopian and Ghanaian official delegations. This is a demonstrative example of how DFID India contributes to broader debate and capacity development in an international context.
Impact Weighting (%): 50 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[5] GOVERNMENT OF INDIA MINISTRY OF HUMAN RESOURCE DEVELOPMENT RAJYA SABHA QUESTION NO 2115: ANSWERED ON 15.03.2013
[6] Bangay, Colin and Latham, Michael (2013). Are we asking the right questions? Moving beyond the state vs non-state providers debate: Reflections and a Case Study from India. International Journal of Educational Development, 33, 3, 244-252.

## Section B: Results and Value for Money.

1. Achievement and Results
1.1 Has the logframe been changed since the last review? No / 1.2 Final Output score and description: A+ / SSA has brought about significant change in respect of provision of access, increase in enrolment, reduced dropout, and increased transition rates. It has also brought about equally significant change in respect of bridging gender and social gaps. For the vast majority of indicators set against these parameters, trends are strong and positive and look likely to continue. SSA has also made marked progress against a set of indicators that are proxy indicators of improved educational quality. / The most significant area of remaining concern is to do with learning outcomes themselves. While the evidence is weak, it raises cause for on-going concern. There are of course mitigating factors: it is not easy to raise quality in a system that is expanding so quickly and which is also taking in significant numbers of first generation learners. DFID’s distinctive contributions include (i) the way it has helped to make learning outcomes a recent strong area of policy focus, and the technical support it has provided to strengthen national assessment testing and move its activities forward; (ii) the ‘quality’ related innovation it has introduced and supported; and (ii) the outcomes of supported research activity that are feeding back positively into the system.
Direct feedback from beneficiaries / One of the series of five research studies commissioned by DFID in late 2012 examined the ‘Emergence and Evolution of Sarva Shiksha Abhiyan’[7]. The study was informed, in part, by a series of 26 interviews conducted with a cross-section of key project beneficiaries. Among the study’s findings were the following: / Although the aid monies [contributed by donors] remained a small proportion of total budgetary expenditure on education, the non-monetary the influence of donors on SSA went much beyond what this might otherwise imply. Stakeholders point to their appreciation of the systems of procurement, management, accountability and planning that donors have helped to put in place, the value they have added to dialogue between central government and states, and the external endorsement they have helped to provide. [Page vi] / Stakeholders believe (Interviews 18, 19) that the increased influence of TC resources (via DFID) has usefully broadened the debate about potential policy responses to problems of education quality in SSA. [Page 33] / The donor partners . . . helped the central government define the rules for the whole programme management . . . . GoI appreciated the fact that the tools developed . . . helped in ensuring that the allocated money was spent according to plan. There has been no significant corruption scandal in SSA for its first eight years (Interviews 17 and 18).[8] [Pages 45-46] / The Aide Memoire of the 17th Joint Review Mission of SSA has also placed on record appreciation of the contribution that DFID has made to SSA.
1.4 Overall Outcome score and description: A+ / The overall outcome has moderately exceeded expectation. SSA has made a major contribution toward: Millennium Development Goal 2 – Achieving Universal Primary Education; and Millennium Development Goal 3 – Promote Gender Equality. It has significantly increased the number of 6-14 year old children, especially from special focus groups, enrolled, regularly attending and completing elementary education and demonstrating basic learning levels. / Impact and Sustainability / What has been demonstrated above is that SSA has delivered very substantially against its expected outputs and outcome. There is no reason to doubt the consistency of the logic articulated in the project logical framework document. Therefore, it is reasonable to assume that these corresponding successful outputs and outcome will lead to desired impact. / However, the full impact of the programme may not be visible for a number of years. This is not only because some impact data that could demonstrate any ‘knock on effect’ have still to emerge through the system. For example, key census data only becomes available every ten years. It is also to do with the legacy SSA will leave for other programmes and other parts of the system to build on. What will be important to continue to measure over time is what impact the cohort of children passing through SSA have on secondary educational expansion and achievement; and, even further down the line, the ways in which the tertiary education sector is ultimately impacted, or indeed the productive capacity of the economy as a result of increased human capital. / Two of the research studies specially commissioned by DFID have demonstrated how a considerable part of the essence of SSA can be traced back to earlier programmes and how the influence of DPEP and the Andhra Pradesh Primary Education Project (APPEP), both supported by DFID, retain their significance in informing the programme (significant examples being community involvement in the management of schools, community involvement in construction and the concept of a child-friendly learning environment). Impact of this kind was of course still to materialise at the time these initiatives ended. SSA’s eventual legacy is likely to be even more important in consequence of the huge size of the programme compared to its antecedents. / DFID selected two logframe indicators for Impact, as follows: Youth Literacy Rate and Secondary Level Gross Enrolment Ratio. In respect of these indicators, changes against a 2010 baseline, and in relation to the targets set, are shown below:
Impact: DFID Logframe Indicator 1 / Youth Literacy Rate / 2010 Baseline Target Achieved / All 82% All 90% All n/a / Boys 88% Boys n/a Boys n/a / Girls 74% Girls n/a Girls n/a / SC n/a SC n/a SC n/a / ST n/a ST n/a ST n/a / Muslims n/a Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural n/a Rural n/a Rural n/a / Urban n/a Urban n/a Urban n/a / Comment: Baseline data for youth literacy remain the most recent data available.
Impact: DFID Logframe Indicator 2 / Secondary Level Gross Enrolment Ratio / 2010 Baseline Target Achieved / All 58% All 62% All 65% / Boys 63% Boys n/a Boys 69% / Girls 53% Girls n/a Girls 61% / SC 43% SC n/a SC 71% / ST n/a ST n/a ST 53% / Muslims n/a Muslims n/a Muslims n/a / Disabled n/a Disabled n/a Disabled n/a / Rural 51% Rural n/a Rural n/a / Urban n/a Urban n/a Urban n/a / Source: Statistics of Schools Education (SSE - 2010-11). These data may not fairly reflect the end of project position.
According to DFID’s own calculations, based on UNESCO statistics, the Government of India was expected to spend Rs 314,265.49 crores on education in 2012/13, of which 49.2 per cent of the total (i.e. Rs 154,618.6211crores) was for elementary education. This can be compared to a Rs 214,735.63 expenditure figure on education for 2009/10: representing a 46.3% per cent increase over a three-year period. DFID’s own estimated contribution for 2012/13 was Rs 291.7 crores (£36.5 million). Thus DFID’s contribution has approximated to 0.19% of government annual expenditure on elementary education. The fact that DFID’s own financial contribution is such a small part of government expenditure and government has been able to increase its own expenditure on education over the project time period makes it manifest that SSA is fully financially sustainable beyond DFID’s exit. The World Bank and the EC will continue to support SSA, but their financial contributions, too, are extremely modest when set against total expenditure by the government. Over time, it is DFID’s technical support rather than simply its budgetary support that has come to be increasingly valued. However, the latter was somewhat dependent on the former in that it was the financial support that bought DFID a seat of influence within the programme.
[7] Colclough and De, 2013, op. cit.
[8] There has been one major allegation in 2010 regarding diversion of DFID funds for SSAII. However, the inquiry report of DFID Audit Department have explained it and stated that “the risk to UK funds has been adequately managed by DFID making payment only on the basis of valid externally-audited expenditure”. www.dfid.gov.uk/Documents/.../India-SSA-Inquiry-Final-Report.pdf

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / DFID’s contribution to the current phase of SSA has been £149 million over a period of 2 years (2011-12 and 2012-13), through non-budgetary financial aid (£140 m) and technical cooperation (£9 m). DFID’s contribution was reimbursed on an annual basis on receipt of detailed financial management returns from the Government of India along with an audited expenditure statement. Payment was released only against the financial forecasts and agreed capped annual ceiling. / 2.2 Key cost drivers / The government of India (GOI) is the key cost driver of SSA. GOI releases funds based upon the approved Annual Work Plan and Budget (AWPB) of the states. AWPBs are submitted by states and reviewed by a national committee. SSA is a partnership between National and State governments and development partners (DPs): The World Bank, European Union and, until 31 March 2013, DFID. Around 90% of the programme is funded from India’s own resources, with the balance being provided by the donor partners. Donor partner support to SSA is provided through a sector wide approach (SWAp). / The technical cooperation fund under SSA has provided technical support for planning, implementation, management and evaluation and capacity building. The main technical support agency (TSA), Cambridge Education, was selected by international competitive tender under OJEU processes. TSA activities and expenditure were monitored against pre-agreed milestone deliverables. The TSA submitted monthly progress reports and claims, which were checked and matched against the agreed deliverables before the process of payment. / 2.3 Was the project completed within the expected timescale: Yes / DFID support ended on 31st March 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / There has been no change in evidence over time that calls into question any previously reported findings. Where there has been a change in evidence is in a sense that SSA itself has helped to make education management information systems even stronger. For example, the SSA management culture of putting all-important documents pertaining to SSA in the public domain through on state and national websites (see: www.ssa.nic.in) is exemplary. The data that are emerging from these systems are now even more robust. Importantly, the last three years of data extend very significantly the time-series data that are available to draw important conclusions about data patterns and trends. SSA has also built its capacity to present and analyse data in this way and this was especially evident in, and commented upon by, the 17th JRM. / In respect of emerging data on learning outcomes, DFID has made a very significant contribution to building capacity in this area – and again thus strengthening the evidence base upon which to form future policy and practice. / The evidence base for this PCR has comprised: / Official data; / Official documents, including 17 Joint Review Mission Aide Memoires (wherein DFID was a participant in the JRM missions); / Five independent research studies on aspects of SSA, especially commissioned by DFID to inform the PCR, focusing on: / The Emergence and Evolution of the Programme / Civil Works and Infrastructure / Assessing Learning Outcomes: Policies and Progress / Equity, Effectiveness and Efficiency of Teaching Services / The Role of the Private Sector and Public Private Partnerships / 3.2 Set out what plans are in place for an evaluation. / The PCR constitutes the terminal review of performance. This has been supported by five separate studies detailed elsewhere in this report and through secondary review of available information sources. / A future retrospective study may yield even greater insights to SSA impact and DFID’s own contribution within it – in the same way that SSA itself has helped to reveal the full contribution of DFID supported projects and programmes that preceded SSA and provided important foundations on which to build. It is expressly recommended that DFID considers conducting such a study ten years from now.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended: Moderate / All financial contributions from Development Partners (DP) are in the form of reimbursement against the total SSA expenditure (both GOI and states) in the previous financial year. DPs jointly monitor SSA’s financial management systems based on the review of GOI’s Financial Management Reports (FMRs), Audit Reports, JRM documentation, IPAI reports on concurrent reviews, manual and GOI’s external website. / DPs review status of the progress and issues related to programme planning, implementation, monitoring and evaluation, including financial management/procurement capacity of states and districts and agree on actions to support the weaker states. / The GOI provides six-monthly financial management reports (FMRs) to DPs in December and June. Eligible expenditure for reimbursement by DPs is calculated based on June FMR covering expenditures in the preceding GOI Financial year (April to March). / DPs examine the FMRs and seek clarification from GOI as necessary. Any disparities between the expenditure statements and audited statements are disqualified from the calculation of eligible expenditure for reimbursement. The World Bank submits a consolidated recommendation of the weaknesses and other observations of the FMR along with the eligible reimbursement by DPs. / 4.3 Climate and Environment Impact: Low / The climate and environmental issues in the SSA are judged to be low. The main area of environment risk is associated with civil works. Several guidelines have been prepared to ensure better construction management, better learning environment, child friendly elements of schools, and health and hygiene on the school premises. However, it is a future challenge for SSA to do more to promote green technologies in school fabrication and to pursue related research that can help to identify even better technical solutions.

5. Value for Money
5.1 Performance on VfM measures / The indicators under the Effectiveness parameter of the 3Es (Economy, Efficiency and Effectiveness) of VfM in education have shown a positive trend in the last four years of SSA implementation (2007/08 to 2011/12): / DFID itself commissioned an independent Value-for-Money analysis of its programme[9]. This verified spending on primary education was a sound investment: with an internal rate of return of approximately 13% to primary education[10]. It also predicted a positive rate of return for every child completing grade 8 for the next 10 years. The analysis concluded that DFID technical cooperation offers “excellent returns” estimating a value gain of £1.48 for every DFID pound spent. / Effectiveness Increase in elementary (grades 1 to 8) enrolment from 185 million to 199 million / Increase in gross completion rate at primary level from 90.2% to 101.9% (2010-11 latest data) (target: 95%) / Increase in the transition rate (primary to upper primary) from 81% to 87.1% (target 85%) / Increase in retention at elementary from: / 38 to 55% in states with elementary stage from grades 1 to 8 (target: 45%) / 56 to 81% in states with elementary stage from grades 1 to 7 (target: 70%) / In addition, the elementary education system in India has grown by close to two-thirds, from 750,000 schools to over 1.40 million schools in just seven years, with one million new classrooms built and close to one million new teachers recruited. This is an unprecedented pace of growth - approximately 6,000 new schools every month (50,000 schools constructed in 2009-10). Innovative methodologies for getting children into school have also been promoted. / Over a million teachers were recruited in the year 2011-12 (1.23 million). Social gaps in terms of enrolment across different social categories are reducing. / The March 2012 Independent Commission for Aid Impact (ICAI) Report concluded that the contribution DFID makes through technical assistance in India, transferring skills and knowledge, is where it adds most value[11]. The Report also observed that: / We agree with DFID India’s partners, as well as third party experts, who note that DFID’s added value is not primarily a result of the size of its financial contributions. Rather, it is the knowledge and expertise that DFID is able to provide, both through its staff and the technical assistance it hires, that then catalyses positive change in service delivery.[12] / This is consistent with direct feedback from beneficiaries reported in Section 1.3 above. / Specifically, DFID technical assistance has provided value for money through: / quality-related capacity building; / the policy and global knowledge generated; / the embedded research and evaluation undertaken; and / the partner relationships it has helped to develop. / The promotion of innovation / 5.2 Commercial Improvement and Value for Money / DFID directly managed the Technical Assistance funds. The Technical Support Agency (TSA) was selected through OJEU competition and an output based contracting arrangement was renegotiated in the year 2011 for better VfM. Specific and measurable milestones with target dates were agreed with TSA and monitored on a monthly basis. All other low value suppliers/contracts (up to £25,000) were engaged either through nomination or bidding processes for managing short-term studies and other related supplementary activities; e.g. The SSA Fiduciary Risk Assessment contract; design and dissemination of the proceeding of the conference on In-Service development of Elementary Teachers etc. A DFID team visited the Gyanshala project headquarters and reviewed their procurement and financial management procedures. A DFID procurement specialist also participated in the January 2013 JRM, with a procurement monitoring brief. A proper inventory has been maintained for all the items procured from DFID funds. / Procurement under Financial Aid is managed by respective state implementation agencies adhering to the standard GOI procurement standards. Some good practices are in place to facilitate commercial improvement and VfM: Most states have introduced e-procurement system and all procurement plans are uploaded on their official SSA website; Electronic accounting software (TALLY) is used in most states for financial management; Procurement and Financial Management specialists on behalf of the DPs review the procurement plans and ensure that all procurement practices are in compliance with the standard practices set out in the Financial Management and Procurement manual prepared by the GOI with input from DPs. The Ministry of Human Resource Development at the national level has developed online software to monitor progress of procurement contracts in excess of Rupees 1 million. / 5.3 Role of project partners / SSA is a partnership between National and State governments and three donor partners (DPs): The World Bank, European Union and UK’s DFID. Around 90% of the programme is funded from India’s own resources, with the balance being provided by the donor partners. Donor partner support to SSA is provided through a sector wide approach (SWAp). DPs participate in the Joint Review Missions and review status of the progress and issues. DPs actively contribute on activities related to programme planning, implementation, monitoring and evaluation, including financial management/procurement capacity of states and districts and agree on actions to support the weaker states. DFID is the sole provider for technical assistance to government of India’s SSA programme, on behalf of the DPs. / SSA has been approached by the donor partners very much in the spirit of the Paris Declaration on Aid Effectiveness and can be considered an exemplar in this regard. Donor cooperation has created synergy and complementarity and there has been much cross-fertilisation of ideas and mutual and reciprocal learning. / 5.4 Did the project represent Value for Money? Yes / DFID’s financial contribution has added value to SSA by: / increasing the rigour with which SSA is supervised; / improving the technical quality of GOI programme management and design and strengthening monitoring and evaluation arrangements; / historically supporting technical improvements in Indian education, particularly pedagogy, teacher development, curriculum development, materials development, research, monitoring and evaluation; / providing policy advice which is sensitive to and understanding of India’s machinery of government in education; / being a ‘mature voice of reason and balance’ among the DPs and strengthening partnership processes; / with other DPs, giving greater credibility to GOI programmes we have supported; / sharing international experience; and helping to boost the confidence and capacity of the GOI and State staff responsible for programme implementation.
[9] Kingdon, G. and Atherton P. (2010). Breakeven Analysis of DFID India Technical Cooperation Fund. EDRM no: 2746099.
[10] Rate of Return is a measure of the relationship between the costs of education during the period of study to the predicted lifetime financial gains from education thereafter.
[11] ICAI (2012) op. cit., page 1.
[12] Ibid., page 17.

6. Conditionality
6.1 Update on specific conditions / There are no conditions.

7. Conclusions
Evidence has been presented to demonstrate that, overall, SSA is a very successful programme that has had a transformational effect in respect of many key indicators associated with access, retention, equity, and quality. DFID can also take very considerable satisfaction from the contribution it has made to this success story. / Such a conclusion has also been reached separately by independent sources. / With regard to SSA as a whole, the findings of a 2010 Planning Commission Evaluation of SSA[13] are fully consistent with the evidence, and interpretation of it, presented here: / significant progress in the attainment of accessibility targets . . . a rapid rise in the overall enrolment of children . . . The enrolment ratio of girls improved significantly . . . The share of socially disadvantaged groups in school enrolment was . . . higher than their share in the population. . . . An impressive increase was also observed in the enrolment of differently abled children. (pages iv-vi) / This kind of momentum has continued and been consolidated in the period 2010-13. / With regard to DFID’s contribution in particular, Professor Geeta Kingdon concluded: / There has been a positive and robust return on DFID’s investment in Sarva Shiksha Abhiyan[14]. / Kingdon has also taken the position that: / It is not in the quantum of aid that is given, but more in the catalytic nature of it[15]. / This again resonates with evidence presented consistently throughout this report that the impact of DFID’s financial support should be seen not only in terms of headline numbers, but in the satisfaction it can take from the ways its technical competence and expertise have influenced the policy agenda, including promoting innovation, and its direct technical support has built capacity to measure and monitor future learning outcomes. There remain, of course, huge challenges, none more so than those associated with raising learning outcomes; though, it should also be acknowledged that these challenges are not unique to DFID India. / Two recent DFID research studies, specially commissioned to inform the PCR,[16] have shown how SSA is a programme that has built on and consolidated earlier investments by DFID in primary and elementary education: in the form of the Andhra Pradesh Primary Education Project (1984-93), the Mahila Samakhya Project, and subsequently the District Primary Education Programme (1994-2000). Moreover, the research studies highlighted how the full impact these earlier projects have had is only now apparent and was certainly not a form of impact that was manifest at the time of contemporary impact assessments. / DFID’s direct support to elementary education has now come to an end after a period of 29 years, as it turns it priority to supporting the secondary education sector in the form of Rashtrya Madhyamik Shiksha Abhiyan (RMSA). In the way that APPEP and DPEP provided the foundations for SSA to build on, SSA already leaves a legacy and strong basis on which to build for DFID’s forward support to RMSA: this is in terms of policy reform and also the ‘groundswell’ of increased demand for secondary education in direct consequence of the successes of SSA. It is also to do with the fact that much of the programme ‘know-how’ developed by SSA in terms of approaches to project finance, planning, procurement, data capture and programme monitoring have been adopted by RMSA itself.
[13] Programme Evaluation Organisation (PEO), Planning Commission (2010). Evaluation Report on Sarva Shiksha Abhiyan, PEO Report No. 203. New Delhi: Government of India.
[14] G. Kingdon IDC 2011 Ev 11
[15] G Kingdon. IDC 2011 Ev 12
[16] Colclough, Christopher and De, Anurada (2013) The Emergence and Evolution of Sarva Shiksha Abhiyan. A New Approach to Elementary Education Provision in India. New Delhi: DFID; and Smawfield, op. cit.

8. Review Process
An independent international consultant with a long history of involvement in education in India, including DPEP and SSA, was contracted to undertake the PCR. The consultant was designated to lead the donor partners in the, January 2013, Seventeenth JRM, in part with a view to the experience informing PCR findings. / The review has also comprised desk-based study and analysis of official data and documents. As noted in more detail above, in Section 3.1, it was also informed by five independent research studies on aspects of SSA, specially commissioned by DFID to feed into the PCR process.