Type of Review: Annual Review

Project Title: World Bank Trust Fund – International Comparison Programme – 2011 Round

Date started:	August 2010	Date review undertaken: May 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID will provide a contribution of £4 million over a 6 year period from August 2010 to July 2016 in support of the International Comparison Program (ICP) which is a worldwide statistical initiative. / The programme is required to estimate Purchasing Power Parities (PPPs) to be used as currency converters to enable comparison of the size of economies around the world. The indicator for the Millennium Development Goal (MDG) on poverty reduction explicitly uses PPP data to set a poverty line of $1.25 per person per day measured in constant purchasing power parities. / DFID support will help ICP produce internationally comparable price and volume measures for gross domestic product (GDP) and its component expenditures. The measures are based on purchasing power parities (PPPs). To calculate the PPPs, the ICP conducts surveys every six years to collect price and expenditure data for the goods and services that comprise GDP including consumer goods and services, government services and capital goods. / The GDP volumes facilitate comparisons of the economic size of countries and, when put on a per capita basis, the economic welfare of their populations. They can also be used to compare the overall productivity and investment potential of countries.

What are the expected results?
The intended impact of this project is that data informs policies of donor agencies, government and civil society institutions. / The intended outcome of the project is timely and reliable statistical data on purchasing power parities for GDP and its main sub-aggregates for all major countries and regions are compiled and published. / The outputs attributable to DFIDs support are: / New methodological preparation developed for various components of the program / Accurate and timely collection of price survey data / Improvements in statistical capacity in IDA countries / This round of the ICP support is leveraging on the successful implementation of the 2005 round and its scope is being further extended. It will be designed to enhance the robustness of PPP estimates through greater adherence to the System of National Accounts (SNA), the improvement of price survey methodologies, and to perform additional methodological research.

What is the context in which UK support is provided?
There is a clear need for countries to have good quality statistics. They are essential not only to inform policy, but also to enhance the credibility of policies by enabling citizens to hold governments to account. Particularly crucial for the international community is reliable data on MDG indicators. These play a key role in: / holding the international community to account; / encouraging sustained public support and funding for development; / ensuring effective allocation of aid, and; / comparing progress across countries. / The results framework of the Global Statistics Partnership (GSP) team’s operational plan identifies areas of our work that contribute to delivering the following Structural Reform Plan pillars and DFID strategic priorities: / Improve quality and availability of statistics to enable more transparent results reporting. / Improve the quality and comparability of MDG data to inform policies, and to allow robust monitoring of MDG progress. / The international system provides more coordinated and effective support to statistics. / Increase the quality and availability of gender specific and sex disaggregated data to inform policies, and to measure the progress of DFIDs efforts to improve the lives of girls and women. / DFIDs support for the ICP will contribute towards delivering these priorities.

## Section A: Detailed Output Scoring

Output 1: New methodological preparation developed for various components of the program.
Output 1 score and performance description: / A. Outputs met expectation
Progress against expected results: / Indicator 1: Number of components that have methodological improvements approved by TAG (technical advisory groups) / The target was 14 and was to be achieved by October 2011. / Progress against the expected result up to May 2013 has been as follows: / As of May 2013, 13 components have had methodological improvements approved / discussed by the ICP Technical Advisory Group (TAG). The TAG adopted an improved PPP extrapolation approach, and discussed the findings of a sub-national PPP study in Philippines. Using PPPs for poverty is now part of a larger discussion on the World Bank poverty and prosperity goals. / Recommendations: / No action required. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Accurate and timely collection of price survey data.
Output 2 score and performance description: / A. Outputs met expectation
Progress against expected results: / Indicator 1: Number of countries collecting price data relating to main price survey on household goods and services. / The target was to be achieved by December 2011 and was as follows: / Approximately 160 countries (all countries except for small Caribbean Island states) / Progress against the expected results up to May 2013 has been as follows: / 155 countries submitted price data for their main household consumption survey, excluding small Caribbean Island States and Pacific Island States. All major participating countries have submitted data. We are still awaiting data from the remaining Caribbean islands, Iran (we received partial data from them), and Cuba by the end of June 2013. / Indicator 2: Number of countries collecting price data relating to other price surveys: / Targets/milestones were as follows: / surveys for education, health , equipment and construction) to be done by December 2011, for approx. 160 countries (all countries except for small Caribbean Island states) / survey for compensation of government employees to be done by December 2012, for approx. 160 countries (all countries except for small Caribbean Island states) / Progress against the expected results up to May 2013 has been as follows: / a) As of May 2013, 118 countries submitted data for education, 185 countries for health, 132 countries for equipment, and 96 countries for construction. The 47 countries from Eurostat-OECD program implement a different private education and construction method than ICP regions and have completed their surveys for education and construction. Pacific Islands conduct only the main household consumption survey (incl. health) and have no plans to conduct surveys for education, equipment or construction. / b) As of May 2013, 154 countries submitted data on compensation of government employees. The Pacific islands have no plans to collect data for this survey. / Indicator 3: Number of countries transmitting major aggregates and basic headings expenditure to the Global Office in a timely fashion / April 2013 milestone = 175 countries transmitting final major aggregates / Progress is as follows: / As of May 2013, 141 countries have submitted detailed expenditure data. Caribbean islands have not submitted their data yet. Pacific islands have no plans to submit expenditure data. / May 2013 milestone = 175 countries transmitting final basic headings expenditure / Progress is as follows: / By May 2013, 155 countries have submitted basic heading expenditure data. We are expecting the remaining countries to submit this data by the end of June 2013. / Recommendations: / The target for indictor 2.1 and 2.2 can now be confirmed as 157. Up until now the logframe had said “Approx. 160”. / Risk rating revised to Low (see below) / Impact Weighting (%): 60% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? Y / This risk has been moved from Medium to Low to reflect the good progress being made with regards to the number of countries collecting price data relating to the various surveys.

Output 3: Improvements in statistical capacity in IDA countries.
Output 3 score and performance description: / B. Outputs moderately did not meet expectation
Progress against expected results: / Indicator 1: Percentage of IDA Borrowers (with a population of 1 million or more) whose World Bank Statistical capacity indicator has increased / September 2012 milestone was 70% / Progress is as follows: / Comparing 2012 with 2011, 38% of IDA countries with a population more than 1 million have increased their statistical capacity indicator score. The target was 70%. It should be noted however that the many of the factors which influence the score are outside the scope of this program / Recommendations: / Risk rating revised to Medium (see below) / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y / In the last annual review this risk was Low. However, given that many of the factors which influence the score are outside the scope of this program then it is more appropriate to give this a Medium risk rating.

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / No, the logframe has not been updated since the last review which was in August 2012. / 1.2 Overall Output Score and Description: / A. Outputs met expectation / 1.3 Direct feedback from beneficiaries / The main beneficiaries of the volume and price measures generated by the ICP are international organisations and regional agencies. There is a growing demand for PPPs from a variety of users at the national level including government agencies, research institutes, private firms and public enterprises. Countries on low Gross National Income will also benefit as PPP data collation and analysis targets the poor and will help to identify and compare the spending power in the 175 participating countries. An independent, external evaluation of ICP will be conducted in year 5 of the program and is expected to commence when the results are published in December 2013.
1.4 Summary of overall progress / The project is progressing well and remains on schedule and on budget. Program activities are being implemented according to the initial timetable with no noticeable delays. The final results of the program are expected to be released by the end of 2013.
1.5 Key challenges / The main challenges will continue to be that: / National Statistics offices are committed to carrying out data collection and have the capacity to do so. / Better data quality and availability does not engender a political backlash in certain country contexts. / Regional agencies have the capacity to provide guidance and coordinate data collection and data validation / The international community remain interested in regional and global results
1.6 Annual Outcome Assessment / The outcome of the program is to produce timely and reliable statistical data on purchasing power parities for GDP and its main sub-aggregates for all major countries and regions. Given the progress to date we expect to achieve the project outcome. / 1.7 Gender / The ICP project does not have a specific focus on gender, nor does it produce sex-disaggregated or age-disaggregated data. / The main output that the project produces (purchasing power parities) is a public good however, and by definition public goods like national statistics do not discriminate toward groups of users but should be available to everyone for all manner of uses. The intended impact goal of better informed policies is also supposed to benefit everyone.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / The key cost drivers related to the delivery of the ICP programme continue to be Staff/Consultant costs, including workshops, and grants to support technical assistance missions in regional programmes. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The need for timely and reliable statistical data on purchasing power parities for country and regional GDPs, which inform policies of donor agencies and government, is still the rational behind the design of this project. Therefore no modifications to the design or theory of change are recommended for this project. / 3.2 Where an evaluation is planned what progress has been made? / An independent, external evaluation of ICP will be conducted in year 5 of the program and is expected to commence when the results are published in December 2013. It will review data quality and other aspects of the program and will make recommendations for financing it on an ongoing basis. As was the case for the 2005 round, it is anticipated that this review will be carried out by the United nations Statistics Commission Friends of the Chair working group. The evaluation would use the responses of Countries, Regional Implementing Agencies, and the Global Office to the ICP Quality Assurance Framework checklists.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The ICP report to donors dated April 2013 highlighted the following categories of risk currently linked with the programme delivery: / Data Quality Risks – an assessment by the Global Office of revised National Annual Averages for Household Consumption showed noticeable improvement in country data quality. However, the data for some regions requires inter-country validation which regional coordinators are addressing this with their countries and through a series of workshops. There is also a risk in quality due to some inconsistencies in ICP price data. To aid this validation process, the Global Office provides operational material and guidelines on validating price data, as well as technical support in data validation to regions where needed. / Another quality risk observed is ICP prices exhibiting inconsistencies with movement of time series of ancillary data (such as CPI) from 2005 and 2011, where some countries exhibit systematic data problems including systematically higher/lower prices across all the basic headings. In light of this, the Global Office has drafted a note on conducting high-level ICP missions to the countries exhibiting these inconsistencies. / Timeline risk – there is risk that some African countries will not implement their Special Surveys on time. The Global Office is working with the African Development Bank to design an emergency plan to ensure such ICP activities are completed within the internationally set timetable. / Production of Medadata – this is a crucial requirement for this round of the ICP. The Global Office have prepared a series of questionnaires to ensure that the 2011 round will produce better metadata than the 2005 round. The Global Office and Regional Coordinators continue to pressure countries to submit these metadata questionnaires.
Risk of funds not being used as intended / There are no indications that misuse of funds is a major risk or concern. DFID funding will be covered by a formal arrangement with the World Bank in the form of a multi donor trust fund. Under this established mechanism, DFID’s contribution is administered in accordance with the World Banks standard policies and procedures, including its framework to prevent and combat fraud and corruption. / 4.4 Climate and Environment Risk / The environmental risks are negligible since this is a project to improve statistical reporting. ICP is a worldwide initiative that compares the size of economies around the world and the information gathered will be useful in a wide range of policy development and decision making. Any environmental and carbon footprints that arise during the conduct of the work will be minimised by the project.

5. Value for Money
5.1 Performance on VfM measures / Preparation of the ICP project documents preceded the introduction and new requirements of the Business Case template, so, although VFM measures were identified from the outset, no indicators or trigger points were established to monitor and measure VFM performance. / However, DFID’s financial support for this program will result in many benefits including improvement in the quality of the data produced, improvement in the methodology used and a greater number of countries being included in the program. / The 2011 Round introduced improvements in ICP methodologies, a Quality Assurance Framework, a software tool to facilitate data collection, validation, and analysis, and a Global Core list of items that can be used for data collection in subsequent years and rounds. These improvements and innovations will reduce the cost of the program in future years. The program will also lead to improved price collection capacity in poor countries which reduces the costs of future ICP rounds and contributes to the sustainability of the program. / 5.2 Commercial Improvement and Value for Money / A strong governance structure is in place for the management and Implementation of the ICP which informs value for money. This comprises of an ICP Executive Board, a Global Office led by a Global manager appointed through an international, transparent and competitive selection process, a Technical Advisory Group and Regional Implemental agencies. The World Bank hosts the Global Office. The framework defines the role of each governance body and their mandate to coordinate international regional and national efforts to produce PPPs. / The World bank continues to mange any Procurement activities under this project in accordance with their internal standard guidelines and procedures covering expenditures allocated to goods and services. / 5.3 Role of project partners / No specific indicators have been developed to measure the World Banks performance in the delivery of value for money. The Bank, however, have already introduced processes (see 5.1 above) to the programme that bring cost-effective savings. The bank are also focused on making the ICP sustainable which includes efforts to ensure greater access to ICP data through their recently approved Data Access and Archiving Policy. The bank continues to explore new more cost-effective technologies which improve data collection in the future. / 5.4 Does the project still represent Value for Money : Y / Yes, we are satisfied that the project is delivering results and representing value for money / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Despite experiencing some delays, the project is progressing well and remains on schedule and on budget. Results are generally being achieved as planned. There are no changes required to the milestones, targets or indicators in the logframe. The project risks (as noted in section 4.2) are being successfully managed by the World Bank ICP team and the overall risk of the project is low.

8. Review Process
The review process was conducted by Kenny Bambrick (Statistics advisor in the Global Statistics Partnership team) in May 2013. / Consultation during this process was conducted with the following people: / Robert Morrison, Deputy Programme Manager, Global Statistics Partnerships Team / Michel Mouyelo-Katoula (World Bank) / Nada Hamadeh (World Bank) / Alexander Hamilton (Statistics Advisor, DFID Sudan) / This Annual Review was informed by: / Annual Review of ICP activities produced by World Bank and sent to DFID in March 2013 (QUEST number 3967457). / Regular discussions with relevant World Bank staff throughout the last 12 months. Progress was also discussed at the annual meeting in Washington in December 2012. / Terms of Reference (Quest number: 4000992)