Type of Review: Annual Review

Project Title: Humanitarian Support to UNICEF Nutrition Surveillance

Date started:	April 1 2012	Date review undertaken: March 22, 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Log frame / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £2 million (47% of the budget) to UNICEF to support the timely availability of quality nutrition data, and the development of a national nutrition surveillance system in Ethiopia. / The overall cost of the programme is £4.2 million. The remaining funds are provided by UNICEF, Canadian International Development Agency (CIDA), USAID and the Netherlands government. / Originally intended to be completed within 2 years, the programme was recently extended for a 3rd year – within the original budget - due to lengthy delays in start-up resulting from slow government approvals. This review falls after 2 years of the projects 3 year life.

What are the expected results?
The goal of the project is to improve targeting, coverage and quality of the humanitarian response. The primary outcome is to improve timely availability and quality of nutrition data using nutrition surveillance approach linked to agro-economic baseline data and early warning. / Resources are focused on improving data quality and the rapid flow of information from sub district/district levels for analysis and use. / The main outputs of the programme include: / Timely availability of nutrition indicators from existing programme data systems. Existing sources includethe Community Based Nutrition (CBN) programme, Therapeutic Feeding Program (TFP), Emergency Outreach Strategy (EOS) and Child Health Days (CHD); / Timely availability of quality bi-annual nutrition survey indicators; / Increased knowledge and guidance of nutrition data collection and interpretation in pastoral areas.

What is the context in which UK support is provided?
Ethiopia has high rates of malnutrition, even by Sub Saharan African Standards[1]. The country’s large (and rapidly growing) population means that high malnutrition rates translate intohighnumbers of malnourished children. / Around 11 million children are currently under-5 in Ethiopia[2]. According to the 2011 Ethiopia Demographic Health Survey (EDHC)[3] of these children an estimated: / 4,884,000 are stunted - reflecting the cumulative effect of chronic malnutrition. / 1,067,000 are wasted - reflecting an acute or recent nutritional deficit. / 3,157,000 are underweight – reflecting children with a double burden of malnutrition who are wasted and stunted. / There have been encouraging reductions in all three indicators among children in Ethiopia. However, the high baseline ensures that all three indicators remain at very high levels. The estimates (children 6-59 months) of the national prevalence for stunting was 44.4%, wasting was 9.7% and 38% underweight[4]. / The causes of malnutrition in Ethiopia are myriad and complex. The three layers of determinants affecting nutritional status – notably dietary intake, care practices and environmental health factors - are illustrated in Figure 2. / Figure 2 UNICEF Conceptual Framework of Malnutrition / Although many of the underlying causes of malnutrition are structural and chronic, they often manifest themselves in widespread prevalence of acute malnutrition that surpasses emergency thresholds and requires a humanitarian response. This is particularly the case following a shock such as a drought, resulting in even less satisfactory dietary intake, or floods resulting in displacement and poor sanitation conditions. / Humanitarian financing needs in Ethiopia are some £200 - £400 million annually. TheUKis the second largest bilateral humanitarian donor to Ethiopia (After the USA), contributing some £30 million annually in relief assistance. Timely and quality nutrition information is required to determine the scale, nature and location of humanitarian needs. Moreover, available funding is rarely sufficient to meet all the requirements, and rigorous prioritisation is required to ensure that the assistance available reaches those most in need. This also requires the availability of timely and quality nutrition information. / Challenges to obtaining the right nutrition information at the right time to inform the humanitarian response include barriers to inter-sectoral information sharing (for example between health and water and sanitation departments and agencies), myriad and not necessarily coordinated sources of nutrition information, limited coverage of nutritional surveys and delays in publication, lack of a central system for analysis and presentation of all available nutrition information, and varying capacity in government structures to collect and utilise nutrition information. / Moreover, this project is being implemented in a politically sensitive context: The Government of Ethiopia is often reluctant to acknowledge the full scale and severity of humanitarian needs overall and within certain parts of the country, and occasionally prevents the undertaking of responsive nutrition surveys or the release of the “results” or data. With this in mind, this nutrition surveillance project has ambitious objectives in terms of increasing the quality and availability – and in places independence - of nutrition information to inform the humanitarian response, and also to embed nutrition surveillance as a regular facet and responsibility of government structures rather than responsive to shocks and external to government.
[1] Malnutrition is defined as an abnormal physiological condition caused by deficiencies, excesses or imbalances in energy, protein and/or nutrients. Under nutrition is when the body contains lower than normal amounts of one or more nutrients i.e. deficiencies in macronutrients and/or micronutrients (DFID 2011 The neglected crisis of under nutrition). Malnutrition is the concept most commonly used in Ethiopia.
[2] Population Projection (2010) according to the Ethiopia Census 2007. Central Statistics Agency.
[3] Ethiopian Demographic Health Survey 2011, Federal Ministry of Health, Ethiopia.
[4] Ethiopia Demographic and Health Survey 2010. Preliminary Report, Addis Ababa

## Section A: Detailed Output Scoring

Output 1: Timely availability of nutrition indicators from existing TFP, CBN and EOS/CHD data systems to feed into early warning system
Output 1 score and performance description: B - Outputs moderately did not meet expectation / In summary: Of the 3 existing nutrition programme data systems that should have provided information to the early warning system, only the TFP did so in full accordance with the targets of reporting content and timeliness. The CBN and CHD programmes marginally missed these targets (for various reasons outlined below). And their utility for early warning was limited by coverage. A third indicator – the roll out of new technology for a central database – simply did not happen due to lack of Government buy-in. / Notwithstanding the sub-optimal output score based on the 3 indicators, it should be noted that the most critical achievement – timely availability of quality reporting from the TFP programme – contributed substantially towards the Goal of influencing the humanitarian response. The timely availability of TFP data – particularly rising admission rates - from feeding centres in the Southern Nations Region in mid-2012 was essential to alerting agencies and advocating to Government the need for a scaled up response, prompting additional funding from donors and pre-positioning of supplies. Thus the output score may not fully reflect the contribution towards the Goal. / In detail: The performance of the 3 data systems are addressed her in more detail: / Therapeutic Feeding Programme (TFP): The quality and consistency of TFP reporting was high throughout the reporting period: The reporting rate (number of centres providing reporting in a given month) was maintained at an average of 87 per cent. The timeliness of data availability was consistently within 3-4 weeks of data collection. The content was also inclusive of all required elements, critically including new admissions that allows trend monitoring from month to month (as opposed to e.g. death rates that indicate the effectiveness of the programme). Considering there are currently 11,050 TFP sites across approximately 600 districts, this is a significant achievement. During the reporting period, the Government of Ethiopia also incorporated TFP into its Integrated Community Case Management (ICCM) Strategy. This will lead to further expansion of TFP centres and thus the availability of data, allowing for trend comparison and monitoring at a national level. / The Community Based Nutrition (CBN) Programme: The CBNcollects growth monitoring data. The CBN demonstrated a reasonable degree of timelinessin making the data available within 4-6 weeks of data collection throughout the reporting period. However, the utility of the information is limited due to the coverage of the programme, which reached a combined average of 40-45% for the four regions of SNNPR, Amhara, Tigray and Oromia. Over 80% coverage (as with the TFP) would be required in order for the data to be sufficiently representative for inclusion in Early Warning reports. SNNPR alone reached a participation rate of 78% which could represent a basis for inclusion in future, while other regions have some way to go. / The Enhance Outreach Strategy (EOS): The EOS screens children for malnutrition using Mid-Upper Arm Circumference (MUAC). Coverage is good at over 90 per cent with high levels of community acceptability. Timeliness of reporting averages 4-6 weeks from data collection. However, being based on campaign-style Community Health Days (CHDs), the approach and timing is inconsistent, limiting the utility of the data for early warning due to limited or no comparability between rounds or seasons. Government has sought to transition the sporadic CHD approach to collecting MUAC data to routine work under theestablished Health Extension Program (HEP). This was successfully completed by mid-2012 in Tigray and later in 2012 in Amhara, Oromia and SNNPR. It has not been completed in Afar, B. Gumuz, Gambella and Somali Regions. The ongoing transition meant that in the first half of 2012, only 46 districts produced MUAC data, but this increased to 681 by the end of 2012. In 2013, coverage should be back on track in the 4 regions that have completed the transition, but more time and capacity will be required in the other regions. / On the final indicator of availability of new technology for the national database, UNICEF discussed the potential use of cell phone based data collection systems with FMOH. There is currently no government buy in to this element of the programme. It appears unlikely that progress will be made under this indicator within the life-cycle of the project.
Progress against expected milestones: / Baseline (2010) Milestone 2 (18 months from start of project) Target (24 months from start of project / Plan Achieved Plan Achieved / Indicator 1: / Five agreed indicators on CBN (1. Coverage, 2. Underweight and 3. Severe underweight) and TFP (1. Reporting Rate; 2. New admissions) consistently reported Poor reporting rate > 90% of districts reporting all five agreed indicators Fully 100% of districts reporting all five agreed indicators TFP 87% / CBN/CHD largely achieved though coverage undermined utility. / Indicator 2: / Number of weeks from collection to availability of data Delay up to 8 weeks Reducing delays to 4 weeks TFP/CBN – fully / CHD – partially Reducing delays to 4 weeks TFP– Achieved (3-4 weeks) / CBN/CHD – partly achieved (4-6 weeks) / Indicator 3: Availability of new technology - database None None None NA No progress, despite discussion. / Recommendations: / UNICEF will seek to consolidate the success and essential contribution of the TFP data system reporting to early warning through continuing support to further scale up at national level, including through the substantial planned new programme of DFID support. / Transition of MUAC data collection from CHD to HEP should be consolidated in the 4 agrarian regions and supported in the DRS regions. / In future, DFID and partners should give more critical thought to the ambition of timeframes of targets within logframes that require structural or systemic change within Government systems, and ensure sufficient Government buy in and agency technical expertise is dedicated at the outset of the project. / Impact Weighting: (50%) / Revised since last Annual Review?: Yes / Risk: Low / Revised since last Annual Review?: No

Output 2: Timely availability and quality of bi-annual nutrition survey indicators / Score and performance description: B Outputs moderately did not meet expectation / In summary, 2 rounds of nutrition surveys were completed under the reporting period. While the first was subject to some delays and omissions (16 of 22 surveys completed), the second was almost perfectly executed, fully achieving the first target. All survey reports were endorsed within the second target deadline of 2 weeks. / A third target that was recently added under this output – the development of e-learning modules on nutrition data analysis for government capacity building – has not yet been achieved. Without this new target, the output score would have been A. / Moreover, as with the TFP data under output 1, data from the nutrition surveys was critical in contributing to the Goal of influencing the humanitarian response. This was particularly the case in the Southern Nations and Somali Regions, where timely surveys provided evidence of a rapidly deteriorating situation that required increased assistance. Thus – once again – the output scoring belies the significant successes of the programme in achieving the goal. / There are also indications that Government is belatedly beginning to internalise and prioritise the system of 6 monthly nutrition surveys. / In detail: The first round of surveys was delayed and fragmented; 16 out of the planned 22 surveys were implemented across 4 of the 6 participating regions (SNNPR, Amhara, Afar and Oromia, but not Somali or Tigray regions). Where the planned surveys did not take place, reasons varied from a lack of access, capacity or agreement from authorities. In instances where surveys were delayed, reasons ranged from problems in planning surveys including the timeliness of trainings and data collection. / In a few instances, the timing of payments from UNICEF to Regional authorities was delayed due to unforeseen glitches in UNICEF’s transition to a new global financial system, ‘VISION’. UNICEF Ethiopia has since taken several measures for managing the risks involved in the introduction of VISION. Notably: / UNICEF has established a ‘VISION Hub’ to support the management of programme transactions, with a team of specialists to trouble shoot problems encountered with the financial system. / UNICEF is hiring three new staff who will be dedicated to programme transactions, including a VISION specialist and a HACT (Harmonised Approach to CASH Transfers) specialist. / The second round of surveys, implemented in October/November 2012 was the most successful to date, with 22 district surveys carried out in 5 of the 6 participating regions (Oromia, SNNPR, Tigray, Amhara and Somali, but not Afar region). Regional governments in Tigray and Amhara requested the addition of one district each, bringing the total number of districts to be surveyed to 25. Afar region was not able to implement surveys in the 3 districts during the second round due to the UNICEF internal financial system issues mentioned above. Therefore in terms of districts covered, plan versus performance is 100% (while in terms of regions would constitute 88%). / All survey reports in the reporting period were endorsed within two weeks of submission to government (at regional and Federal level), fully meeting the second target. (However, there were delays between data collection and the production of the report at regional level due to limited capacity to undertake the data analysis and writing). This regular endorsement in comparison to previous frequent blocking of surveys may indicate that Government is beginning to internalise the six monthly system of surveys as routine, rather than reactive to crises and therefore politically sensitive. There is demand for survey information not only from agencies, but from government as well. / The process of undertaking regular surveys has in itself increased the technical capacity of government staff on nutrition data collection, analysis and reporting. A series of trainings were carried out specifically for nutrition survey and analysis, for trainers at the Federal level, and in Oromia, SNNPR, Somali and Amhara regions. To capitalise on the capacity development benefits of the surveys, it was proposed in the last annual review to develop a series of e-learning modules on nutrition data analysis. This was added to the logframe, but has not yet been completed. A consultant has been contracted to carry out this work within the reporting period. Completion of the modules is expected within 2013. / Progress against expected milestones: / Baseline (2010) Milestone 2 (18 months from start of project) Target (24 months from start of project / Plan Achieved Plan Achieved / Indicator 1: Number of surveys implemented on seasonal calendar Delay in approval 50% surveys conducted based on seasonal calendar (April-May and October-November) Achieved: 72% of surveys were completed in round 1 of 2012. 100% of surveys conducted based on seasonal calendar Achieved: 100 % of planned 22 surveys were completed in second round 2012. / Indicator 2:Number of survey reports endorsed within two weeks of release of reports Delay in endorsement 100% of survey reports endorsed within two weeks of release of reports Achieved 100% of survey reports endorsed within two weeks Achieved / Indicator 3: E-learning training modules developed for improved capacity development NA NA NA 100% of modules developed for use by nutrition staff Not yet achieved / Completion of the modules is expected within 2013. / Recommendations: / The performance of the second round of surveys in 2012 should be consolidated and improved on during the extension period in 2013. UNICEF should address internal financial delays and begin planning with regions early. / UNICEF should prioritise the development of the e-learning modules on nutrition data analysis for completion by August/Sep 2013. / As with output 1, DFID and partners should give due thought to the ambition of timelines for targets that require systemic change with Government systems and ensure that sufficient political buy in and agency capacity is dedicated to achievement. / Impact Weighting: (40%) / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 3: Increased knowledge and guidance on nutrition data collection and interpretation in pastoral areas
Output 3 score and performance description: B Outputs moderately did not meet expectation / In summary: This output essentially entails the undertaking of operational research and production of best practice notes on nutrition in pastoralist areas. Under the original project timeframe, these should have been completed within the reporting period. But with the one-year no cost extension now in place, they should be completed by end 2013. While progress has been slow, this output is on track. / In detail: In 2012, a consulting firm was contracted to carry out a study entitled “Improving Nutrition Monitoring in Pastoralist Areas of Afar and Somali”. A steering committee for the study was established consisting of government, UN and NGO members of the Multi-Agency Nutrition Task Force (MANTF). An initial meeting between the steering committee and the consulting firm concluded the study should cover all pastoralist communities, including those in Oromia and SNNPR. Field work commenced in late January 2013 and has been completed in Afar, SNNPR and Oromia, while for Somali Region it started in April. The final report of the assessment is expected by June 2013. / The study is meant to look at past and current systems of nutrition monitoring, identify lessons learned, and make recommendations for improving current methodologies. A critical component of this study will be an investigation into the movements of pastoralist communities. The information from this study should not only benefit nutrition monitoring, but other sectors as well.
Progress against expected results: / Baseline (2010) Milestone 1 (18 months from start of project) Target (24 months from start of project) / Plan Achieved Plan Achieved / Indicator 1: Operational research conducted on nutrition in pastoral areas Operational research conducted in pastoral areas NA NA Completion by end of project Note yet achieved. On track to deliver by June 2013. / Indicator 2: Best practice note(s) produced No best practice document available NA NA Completion by end of project Completion is dependent on above study completion. On track to deliver by end of project. / Recommendations: / UNICEFshould expedite the implementation of the study before end June 2013 and complete the best practice documents before the end of November 2013. / Impact Weighting: (10%) / Revised since last Annual Review?:No / Risk: High / Revised since last Annual Review?:No

## Section B: Results and Value for Money
1. Progress and results

1.1 Has the log frame been updated since last review? No / 1.2 Overall Output Score and Description: Outputs moderately did not met expectation / The overall output score is based on the 3 individual output scores, all of which achieved a B. / This scoring, classifying the project as poor performing, belies the critical success of the programme in making timely nutrition information available to influence the humanitarian response. In particular the regular TFP data showing increasing trends in admittances to feeding programmes, combined with the nutrition surveys that provided solid technical data on the locality and severity of the humanitarian situation, were instrumental in influencing and prioritising the humanitarian response in 2012. As a result of the availability of this information, levels of assistance were increased and a worse humanitarian situation was undoubtedly mitigated. The importance of this contribution of the programme should not be under-estimated. / However, where the programme falls down is the failure to fully internalise nutrition data systems within Government’s own systems in the timeframes set out in the logframe. While there has been limited progress in this regard, and further progress is likely in the last year, full achievement of an integrated nutrition surveillance system is clearly subject to a set of processes and commitments that are at least partly outside the control of this programme. The programme score is therefore, to an extent, a victim of some overambitious timeframes in the logframe target setting process. / 1.3 Direct feedback from beneficiaries / The direct beneficiaries of this programme are Government and the international humanitarian community, who are able to make use of the improved timeliness and availability of nutrition data for decision making regarding humanitarian response. / Throughout late 2011 and 2012, a period of drought and acute humanitarian need in Ethiopia, donors, humanitarian agencies and government made extensive use of the information provided under this programme. Monitoring of TFP data was instrumental to identifying the locality and extent of humanitarian need. Higher than normal peaks in admissions of severe acute malnutrition were recognized in April and May 2011 enabling donors to increase commitments and agencies to scale up response, to some extent, even before the broader Horn of Africa Emergency was declared in July. / The nutrition surveys of 2012 were similarly critical. In Humanitarian Country Team Meetings, reference was often made to the “UNICEF or DFID funded nutrition surveys” as a critical information source on the severity of the situation and need for response in certain areas. / The ongoing research on nutrition surveillance in pastoralist areas which is looking at improving “routine nutrition monitoring in pastoralist areas’’ is highly anticipated by local government and NGO partners who are responding to nutrition emergencies in these areas. / We will collate and incorporate more specific feedback of beneficiaries in project completion review (PCR) due by February 2014.
1.4 Summary of overall progress / The project has clearly and significantly contributed to the purpose of improving the timeliness and availability of high quality nutrition data that has been essential in influencing the humanitarian response. / Reporting rates remain high with an average of 87 per cent of TFP units reporting. / Nutrition information is now generated from over 11,000 sites in 600 districts. / The turnaround time for release of information has reduced to approximately four weeks from data collection. / 6 monthly surveys are now being implemented with increased coverage and regularity. / There are indications that the demand for nutrition information from government as well as agencies is increasing. / The capacity of government to undertake their own data collection and management may also be increasing. / The extension of one year to the project will allow some of the outstanding targets to be met, such as the production of e-learning resources and research on nutrition in pastoralist areas. However, given the high ambition of the expected speed of internalisation of nutrition surveillance systems into government systems, this programme will not likely exceed its ambitious targets.
Key challenges / There are several limiting factors to full achievement of the programme outputs, some of which are outside the direct influence of the programme: / The information from the CBN programme is improving both in terms of timeliness and coverage for SNNPR, but in all other regions (Amhara, Tigray and Oromia) is lagging behind. It would take a substantial prioritisation of the CBN programme by government and donors to achieve the approximately 80% coverage required for the growth monitoring data collected under the programme to be of use to the early warning system. While expansion of CBN would be beneficial to this programme in terms of data, it is not certain – and in fact doubted by many experts - that growth monitoring is an effective means of improving nutrition outcomes. / Similarly, the transition of MUAC data collection from the campaign based Community Health Days to the more regular Health Extension Programme has much wider and more significant considerations than just within this programme: Increased regularity of MUAC data would be beneficial, but the transition to Health Extension Worker duties will take time, particularly in the developing region states where capacity and logistics are more challenging. There is also a danger of overloading the health extension worker critical tasks. / The various factors that delay or prevent the undertaking of regular six monthly assessments will persist. Political sensitivities appear to be reducing with the routine approach, but could resurface in any given area. Conflict or flooding may also prevent access. And critically, competing and overbearing priorities on local authorities may delay the planning and participation in surveys. / The challenges posed by the transition of UNICEF to a new internal financial management system now appear to be resolved or mitigated.
1.6 Annual Outcome Assessment / The outcome of the project is: timely available and quality nutrition reporting linked to agro economic baseline data and the early warning system. / TFP data is now routinely reported at district level via the weekly Early Warning Reports and monthly through the regional Disaster Prevention and Preparedness Bureau (DPPB) and federal Disaster Risk Management and Food Security Secretariat (DRMFSS) reports, all of which are widely disseminated to stakeholders.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / No. The project is behind the agreed financial forecast schedule. This problem was initially attributed to lack of government approval of the methodology for nutrition surveillance and surveys later on coupled with other programming constraints as mentioned under section 1.5. To ensure the achievement of the expected results and Value for Money DFID has already approved a no cost extension until November 2013. / 2.2 Key cost drivers / The key cost drivers of this project are costs applied for undertaking the bi-annual nutrition surveys,an activity that takes majority of the funds of the project. This is mainly driven by costs for employing enumerators and hiring vehicles. Second to this is the cost of specialist human resources, specifically within theEmergency Nutrition Coordination Unit (ENCU) and regional UNICEF staff who are responsible for coordinating the bi-annual surveys, and collecting and processing the routine nutrition information. / Information obtained from UNICEF shows that the basic costs of implementing the surveys have not changed significantly since the start of the bi-annual nutrition surveys in Nov 2011. The cost of enumerators’ daily subsistence allowance (DSAs) has remained at ETB 165/day in compliance with the agreed rates between UNICEF and Government under the Programme Implementation Manual (except for Afar where it is ETB 200/day). The average cost of renting a vehicle also remained between ETB 2000-2,300/day (including fuel and driver costs). / Is the project on-track against original timescale: / No. The project is behind the originally agreed schedule of implementation. The delay was initially attributed to lack of government approval of the methodology for nutrition surveillance. To ensure the achievement of the expected results and Value for Money DFID has already approved a no cost extension until November 2013.

3. Evidence and Evaluation
Assess any changes in evidence and implications for the project / There are no specific changes in evidence since the last annual review that should alter the implementation of the remainder of the project. / However, it is worth recording in this review that new data from the five-yearly Demographic Health Survey (DHS) undertaken in 2010 was release during the period under review. This indicates that – from a very low base - Ethiopia continues to demonstrate positive reductions in under nutrition prevalence; however population size and rapid population growth mean that this still translates into extremely high numbers of malnourished children. / Themain observations arising from this new DHS data is regarding the continued relevance of the project in the Ethiopian context. Specifically, with a continued high burden of malnutrition there is a continued need for regular nutrition monitoring and data, that is also complementary to the five-yearly DHS data at the national level. / A graph showing the latest EDHS nutrition data is shown below. / 3.2 Where an evaluation is planned what progress has been made?No evaluation planned

4. Risk
Output Risk Rating: / Medium / 4.2 Assessment of the risk level / Appropriate
Risk of funds not being used as intended / The overall risk rating for this programme is medium. The risk of unintended use of resources is limited due to UNICEF’s overall financial management of the project, which involves discrete payments for specific tasks through partners. Recently, the UK National Audit Office (NAO) reviewed the project’s financial and accounting procedures and gave a clean and positive audit report. / 4.4 Climate and Environment Risk / n/a

5. Value for Money
5.1 Performance on VfM measures / Due to limitations in the availability of data, thisVfM assessment focuses on economy and effectiveness. / The two major cost drivers of implementing the Bi-annual nutrition surveys are the cost of enumerators and the cost of renting vehicles. Seen against these two the average costs of implementing the surveys have not changed significantly since the start of the bi-annual nutrition surveys in Nov 2011. The cost of enumerators’ DSAs has remained at ETB 165/day while that of renting vehicle maintained between ETB 2000-2,300/day (including fuel and driver costs). / SNNPR Oromia Amhara Somali Afar Tigray / Average Vehilce cost per distrct (ETB) 128,800 172,000 87,400 160,000 177,000 138,000 / Avergae DSA cost (ETB) 60,810 110,638 90,200 90,100 112,000 107,000 / Average cost per district (ETB) 195,000 348,000 184,400 283,000 321,000 278,000 / If the overall thrust of the project to embed nutrition survey and surveillance systems fully within government structures were achieved, these costs to the project would likely be reduced as government would meet them through routine departmental and local administrative expenditure. This review demonstrates that there is some way to go in terms of political prioritisation, capacity building and coordination for nutrition surveillance within Government structures before Government are likely to internally and effectively dedicate resources to carry out the surveys that are currently produced by this project. / Comparing the cost of implementing this project through UNICEF with other alternatives has proved to be difficult. Nutrition surveys conducted in Ethiopia by NGOs are ad-hoc, and conducted usually in response to an emergency or sharp deterioration, providing a one-off ‘’snapshot’’ of the situation. In contrast the Bi-annual surveys under this programme are implemented in the same districts over time allowing for an analysis of trends and comparison between similar points in different years. / According to the information acquired from UNICEF, a standalone, NGO-led nutrition survey costs around ETB 270,000-350,000 per district. When compared with the bi-annual survey implemented via UNICEF (circa ETB 270,000) the cost is comparable or more expensive, while the benefits of trend monitoring or annual comparisons are limited or non-existent. / The effectiveness of the project is measured against the milestones set for this period and shows that the targets have largely been achieved. The outcome of this project is timely availability and quality of nutrition report linked to agro-economic baseline data and early warning data. / There are two outcome level targets set for this review period: The first target is that nutrition reportsare available within 2 - 4 weeks of data collection in 90% of targeteddistricts. The timeliness of TFP data availability was consistently within 3-4 weeks of data collection. This target has been met. The CBN and CHD were reported within 4-6 weeks of data collection throughout the reporting period, which shows that this target has been partially achieved. / The second target is more than 85% of districts reporting on all agreed nutrition indicators. Of the 3 existing nutrition programme data systems that should have provided information to the early warning system, only the TFP did so in full accordance with the targets of reporting while the CBN and CHD programmes marginally missed these targets. The TFP reporting rate was maintained at an average of 87 per cent. / In terms of benefits, nutrition data-particularly that provided by the Bi-annual surveys and TFP monitoring under this project- do have a multiplier effect in terms of leveraging wider humanitarian expenditure, which totals £200 - £400 million annually in humanitarian response. Explicitly, the nutrition data has been shown to help ensure that these larger resources are targeted to where it is needed most. This was the case in SNNPR during 2010/11 when the results of nutritional surveys combined with TFP datafound higher than average levels of global acute malnutrition (GAM) and admittances to therapeutic feeding programmes. The highest was in Sidama Zone. The GAM rate found in May 2012 was 16%, above emergency thresholds (15%) and double what it was in Nov/Dec 2011, indicating a deteriorating situation. Specifically, the data achieved through this project was instrumental in identifying early the onset of the 2011 drought indicating which areas were most affected and facilitating improved emergency coordination of partners, supplies and resources to affected areas. The increased assistance based on availability of data likely mitigatedwhat would otherwise have been a far worse humanitarian situation. / A more in in-depth VfM analysis will be addressed in the project completion report for this programme planned in December 2013. / 5.2 Commercial Improvement and Value for Money / Over the last year responsibility for implementation of the Bi-annual Surveys under this project has been gradually shifting to the Government of Ethiopia, although significant initiative, technical and financial support is still required from UNICEF to ensure that surveys happen on time and to sufficient quality. Implementing the project through Government systems has meant low (and in many cases lower) comparative costs of undertaking the activities than compared to the most prevalent alternative model of individual NGO-led surveys (see VFM section above). In other words, although there has not been a commercial improvement during this reporting period, the costs of conducting bi-annual surveys have remained almost similar to the year before. / 5.3 Role of project partners / Government at all levels and NGOs are integral to the success of this project. This project has been successful in improving relationships among the key stakeholders working on nutrition. The agreement to go ahead with nutritional surveys in sensitive areas is an indicator of this. Even with the identification of high levels of malnutrition, as evidenced in one district of SNNPR (second round) and one district in Somali region (third round), government has released the information and acted upon it by providing supportthemselves and by asking NGO partners to assist. This can likely be attributed to a sense of ownership of the system by the government. / DFID provided support under this project for the Emergency Nutrition Coordination Unit (ENCU), both for Federal and Regional staff. ENCU members are responsible for collecting TFP data from RHBs, assuring the quality and reporting the findings. They are also responsible for coordinating bi-annual surveys, carrying out analysis and reporting, and coordinating emergency nutrition response. DFID plays a key role in lobbying for greater access for UN and NGOS for nutritional surveys. / Does the project still represent Value for Money / Yes. This judgement is based on three premises: / First, the unit cost of the key cost drivers hasn’t changed during the reporting period. / Second, the costs of conducting nutrition surveys through Government systems are equal to or less expensive than the alternative mechanism of NGO-led studies, while also incurring benefits of monitoring trends and comparing nutrition status over time. / Third, the outcome level targets for this project have largely been achieved. / Having made this judgment, we recognise that output 3 will need to deliver within the project timeframe. / 5.5. If not, what action will you take? / DFID will closely follow-up and push for the delivery of output 3. DFID and UNICEF discussed as to when output 3 will be delivered and agreed that this will be delivered by June/July 2013. Please refer to Quest # 3948987

6. Conditionality
6.1 Update on specific conditions. / n/a

7. Conclusions and actions
The improved availability of nutrition data provided through this project was invaluable in informing the humanitarian response during the critical period from late 2011 through 2012 in Ethiopia. However, the overall poor output scoring reflects ambitious targets in terms of timing for systemic change within government systems. / This review provides an opportunity to inform the start up of DFID Ethiopia’s planned and much larger new nutrition programme. In recognition of the importance of continued improvements in nutritional surveillance and the longer timeframe required to embed improvements and systems, DFID will make further investments in Ethiopia’s nutrition surveillance system through UNICEF. / Actions include: / Programme management: / The performance of the second round of surveys in 2012 should be consolidated and improved on during the extension period in 2013. UNICEF should address internal financial delays and begin planning with regions early. / UNICEF should prioritise the development of the e-learning modules on nutrition data analysis for completion by August/Sep 2013. / UNICEF will seek to consolidate the success and essential contribution of the TFP data system reporting to early warning through continuing support to further scale up at national level, including through the substantial planned new programme of DFID support. / Transition of MUAC data collection from CHD to HEP should be consolidated in the 4 agrarian regions and supported in the DRS regions. / UNICEFshould expedite the implementation of the study before end June 2013 and complete the best practice documents before the end of November 2013. / Internal learning: / In future, DFID and partners should give more critical thought to the ambition of timeframes of targets within logframes that require structural or systemic change within Government systems, and ensure sufficient Government buy in and agency technical expertise is dedicated at the outset of the project. / In preparation for the Project Completion Review: / Collect direct beneficiary feedback, particularly on the utility of the availability of nutrition data from government and agencies. / Consultation with DFID-E Economist on how to tackle the VFM section in the PCR.

8. Review Process
The review process was carried out in a participatory manner. DFID’s Nutrition and humanitarian advisers, Deputy program manager and program officer consulted relevant staffs from UNICEF in the compilation of progress report, comments and suggestions. Review meetings and frequent e-mail communications were also part of the review process that helped to collect and clarify information explained in this report.