Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Ethiopian Investment Advisory Facility
Programme Value: £35 million		Review Date: May 2016
Programme Code: / 204635	Start Date: June 2015	End Date: June 2020

Summary of Programme Performance
Year	2016
Programme Score	B
Risk Rating	Moderate

Summary of progress and lessons learnt since last review

This is the first review of the EIAF programme. The programme is still in start-up phase with the focus of the last year being on the procurement of the main implementing partner. DFID Ethiopia had anticipated this to be the case, even so progress is slightly behind the expected timeframes. This has not had any cost implications and will not have any impact on the results that the programme can deliver. Delivery of technical advice to Government has been limited to one workshop, which was highly relevant and valued by the participants.

Summary of recommendations for the next year

- The EIAF programme should be extended by one year on DFID systems to allow five years of full implementation. This is due to inconsistencies between the original business case time frame and the contract and is not due to any specific delay. This will not be associated with any additional financing. A submission should be made to the DFID Head of Office for a decision on this.
- DFID Ethiopia should work with DFID’s Procurement and Commercial Department on learning lessons from this procurement process for future adaptive programmes.
- The log frame should be updated to ensure baseline data is as accurate and up to date as possible.

A. Introduction and Context

DevTracker Link to Business Case:	Commercial process not yet concluded therefore still commercially sensitive.
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4805277.xlsx

What support is the UK providing?
The Ethiopian Investment Advisory Facility (EIAF) is a £35 million programme being delivered over five years to help the Government of Ethiopia strengthen the effectiveness of its public investment spending. Once fully operational it will deliver flexible, demand-led technical assistance to government ministries and agencies who are involved in planning and implementing public investment activities. It focuses on three key sectors critical to Ethiopia’s growth plans: energy, trade logistics and urban development. In addition, a fourth pillar is focused on cross-cutting issues relevant to capital expenditure, for example the development of a public-private partnership framework or capacity building on public investment management.
The £35 million programme comprises three elements: £30 million to the main facility, which will deliver the majority of technical assistance and an additional £5 million which is split between a grant window managed by DFID to fund activities complementary to the facility and an independent technical review and monitoring panel.
Why is UK support required?
Ethiopia’s economy has experienced impressive growth and poverty reduction since 2004, driven by growth in the agriculture and services sectors. However, there has been disappointing progress in structural change and export performance, which risks the sustainability of the current growth path. The Government of Ethiopia has actively pursued a ‘development state’ model with a strong pro-growth and pro-poor focus and a highly interventionist industrial policy. A major pillar of the Government of Ethiopia’s growth strategy has been a massive public investment programme, often implemented by large State Owned Enterprises (SoEs).
Within the government’s public investment programme the areas of i) trade logistics, ii) energy, and iii) urban development are critical to supporting Ethiopia’s transition to a more export orientated and manufacturing led growth path. Limited capacity within the GoE can sometimes mean the effectiveness and efficiency of the public investment programme is not maximised.
By providing technical assistance to the Government of Ethiopia the UK aims to help improve the returns to public investment. By focusing support on areas that have been identified as critical to supporting growth, this can contribute to outward orientated, manufacturing-led inclusive growth in Ethiopia.
What are the expected results?
The overall outcome expected from this programme is “strengthened effectiveness of growth-enhancing public investment in Ethiopia”. This will be achieved through improving capacity within the Ethiopian public sector to plan, appraise and implement public investment projects, as well as the provision of high quality technical inputs which can be used for decision-making.
The specific results that will be achieved within each sector will depend on the type of assistance that is being delivered. These are captured in the programme results framework and as the programme matures it will be possible to aggregate these within sectors. Our initial expectation of how the programme will contribute to each of the focus sectors is as follows: a reduction in the number of firms who cite electricity as a constraint to doing business; an improvement in the overall trade logistics system (as measured by the logistics performance index); and more efficient cities (indicator to be determined).

B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
As programme activities have been very limited to date, it is not possible to make an evidence-based assessment of whether the outcome is likely to be achieved. However, there is no reason why our expectations regarding the outcome should change since the assumptions in the theory of change remain valid.

Overall output score and description
Significant progress has been made since the EIAF programme officially started one year ago. However, based on the performance of the outputs against log frame targets it has scored a B overall i.e. it moderately did not meet expectations. This is not as a result of poor performance of any supplier, but a reflection of how long procurement processes can take for contracts of significant value (in this case £30 million):
- The business case was approved at the end of March 2015, at which point DFID initiated the procurement process.
- DFID conducted early market engagement, including a supplier event on 14th April 2015 in London.
- The Invitation to Tender was issued on 4th August and bids received by 14th September 2015.
- All bids were fully evaluated and moderated by November and, after a slight unforeseen delay, the standstill letters were issued in January 2016.
- Post-tender clarifications with the preferred supplier began in February 2016 and are now complete.

DFID had anticipated that the procurement process would take a significant period of time and therefore the indicators in the log frame are mainly process orientated. However, it has taken a couple of months longer than anticipated, which is why expectations on the process indicators have not been fully met. When the log frame was revised in February DFID thought that the contract would be signed shortly after, giving time for inception phase deliverables. This proved optimistic.

Despite the main implementing partner not yet being in place, significant preparatory work has been carried out in EIAF’s focal sectors. Relationships with key Government stakeholders have been being built and demand for support is strong. Project proposals have been discussed and developed with the Government of Ethiopia for high priority projects in the trade logistics and cross-cutting pillars, which will start as soon as possible after the contract with the implementing partner is signed. This sends strong signals that this is an important programme for Government and therefore has huge potential for achieving transformational results. In addition, complementary pieces of work in the urbanisation and energy pillars, funded through the grant window, have begun or have already taken place.

Key lessons

The key lessons learned to date are related to the procurement process. Procurement of contracts for delivering adaptive programmes is still relatively novel in DFID, however as the popularity of this type of programme increases so too will the demand for suitable contracts. Advisers in DFID Ethiopia worked very closely with DFID’s Procurement and Commercial Department throughout the process to ensure the contract meets the needs of the programme. The process has generated lots of lessons, both positive and areas for improvement, that would be useful for future procurement processes. A key lesson is that the post tender clarification stage can take a significant length of time. DFID demonstrated optimism bias in this area during the log frame review in February 2016. Other lessons include the relevance of the standard commercial pro formas and benefits of conducting a joint value for money evaluation. DFID Ethiopia should work with Procurement and Commercial Department to record and learn the lessons from this procurement process.

Has the log frame been updated since the last review?
This is the first review. However, the log frame has been updated since the business case was approved in April 2015. In February 2016 the log frame was revised to refine and clarify some of the language and capture some of the important preparatory work that had happened.

C: DETAILED OUTPUT SCORING

Output Title	Trade Logistics sector benefits from high quality technical inputs and strengthened capacity
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1) Share of completed projects scoring 4 or above (out of 5) on individual project performance score	Methodology for scoring projects agreed between DFID and PMU. One well developed project proposal negotiated with GoE counterparts (but not yet approved by Project Steering Committee) that demonstrates a good grasp of sectoral priorities.	The methodology for scoring projects has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score B) / One well-developed project proposal agreed. (Score A)
1.2) Degree to which TA leads to capacity building within GoE clients	Methodology for assessing capacity building agreed between DFID and the PMU PMU's inception report to include a qualitative baselining of capacity within the sector.	The methodology for assessing capacity has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score: B)
1.3) Relevance and quality of TA provided, as reported by GoE	Methodology for scoring agreed between DFID and project management unit.	As above (Score: B)

Key Points

DFID has been discussing the EIAF programme with key counterparts within the Government of Ethiopia since the pre-design stage. On the basis of these discussions DFID has been working closely with GoE on the preparation of a major project in the trade logistics sector which is in a position to start as soon as the contract with the implementing partner has been signed.

Output Title	Energy sector benefits from high quality technical inputs and strengthened capacity.
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1) Share of completed projects scoring 4 or above (out of 5) on individual project performance score	Methodology for scoring projects agreed between DFID and PMU. One well developed project proposal negotiated with GoE counterparts (but not yet approved by Project Steering Committee) that demonstrates a good grasp of sectoral priorities.	The methodology for scoring projects has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score B) / One small project in the energy sector has been delivered (Score: A+)
2.2) Degree to which TA leads to capacity building within GoE clients	Methodology for assessing capacity building agreed between DFID and the PMU PMU's inception report to include a qualitative baselining of capacity within the sector.	The methodology for assessing capacity has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score: B)
2.3) Relevance and quality of TA provided, as reported by GoE	Methodology for scoring agreed between DFID and project management unit.	As above. (Score: B)

Key Points

The first project approved under the EIAF grant window was a workshop on private investment in the power sector in Ethiopia, which arose from discussions between the Economic Adviser to the Ethiopian Prime Minister and Sir Paul Collier of the Blavatnik School of Government at Oxford University. The workshop brought together ten key Ethiopian policy makers with a small group of experts in the field: Sir Paul Collier, Professor Colin Mayer from the Said Business School at Oxford University, Professor Anton Eberhard from the University of Cape Town and Michel Wormser, former VP of MIGA, and one private sector participant. The written feedback from the Ethiopian side in mid-October was as follows: “Those who attended the workshop expressed strong satisfaction and requested the presentations for further reference”.

Output Title	Urban Development sector benefits from high quality technical inputs and strengthened capacity.
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1) Share of completed projects scoring 4 or above (out of 5) on individual project performance score	Methodology for scoring projects agreed between DFID and PMU. One well developed project proposal negotiated with GoE counterparts (but not yet approved by Project Steering Committee) that demonstrates a good grasp of sectoral priorities.	The methodology for scoring projects has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score: B) / One project under the grant window has been agreed. (Score A)
3.2) Degree to which TA leads to capacity building within GoE clients	Methodology for assessing capacity building agreed between DFID and the PMU PMU's inception report to include a qualitative baselining of capacity within the sector.	The methodology for assessing capacity has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score: B)
3.3) Relevance and quality of TA provided, as reported by GoE	Methodology for scoring agreed between DFID and project management unit.	As above. (Score: B)

Key Points

Following the launch of the “Ethiopia Urbanisation Review” by the World Bank, the Government of Ethiopia requested the review team to do some follow-up work on urban land and housing. DFID is financing this work through the EIAF grant window. The specific objectives of the project are to inform policy decisions on how to address the growing demand for urban land and housing in the context of rapid urbanization. The key outputs will be one comprehensive report for each pillar, supported by background papers, short policy notes, presentations and other materials as needed. DFID and the World Bank signed an agreement in March 2016. The World Bank has just signed a contract with a supplier to carry out work on the land cadastre, which will begin soon.

Output Title	Cross-cutting issues related to the effectiveness of public investment benefit from high quality TA and strengthened capacity
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1) Share of completed projects scoring 4 or above (out of 5) on individual project performance score	Methodology for scoring projects agreed between DFID and PMU. One well developed project proposal negotiated with GoE counterparts (but not yet approved by Project Steering Committee) that demonstrates a good grasp of sectoral priorities.	The methodology for scoring projects has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score: B) / One project proposal is well developed with another in the pipeline. (Score: A+)
4.2) Degree to which TA leads to capacity building within GoE clients	Methodology for assessing capacity building agreed between DFID and the PMU PMU's inception report to include a qualitative baselining of capacity within the sector.	The methodology for assessing capacity has not been agreed – this is planned for the inception phase, which has not yet started. However, a proposed monitoring system was included as part of the preferred supplier’s technical bid which will be the basis for the methodology. (Score: B)
4.3) Relevance and quality of TA provided, as reported by GoE	Methodology for scoring agreed between DFID and project management unit.	As above (Score: B)

Key Points

The Government has approached DFID to urgently provide transaction advice on a major oil pipeline linking Ethiopia to Djibouti. Due to the urgency and importance of this work DFID has been working with the Ministry of Finance to develop the project proposal which will start as soon as possible once the contract with the main EIAF supplier is signed.

In addition, the GoE has asked DFID (working with other donors) to support it in the establishment of a Public Private Partnership (PPP) unit within the Ministry of Finance.

Output Title	Effective, efficient and responsive programme management of facility
Output number per LF		5	Output Score	B
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
5.1) Status of PMU	PMU has established an office in Addis and formed relationships with GoE counterparts in central government and relevant sectors	Some PMU staff already based in Addis. Some key relationships established but not in a uniform way across sectors. (Score B)
5.2) Time taken from receiving a written request from Government and having advisers in place	PMU and DFID have agreed targets for turn-around of proposals	No formal agreement / (Score C)
5.3) % of total budget spent on administration of facility	DFID and PMU have agreed what can be categorised as admin vs programme spend / DFID and PMU agree trajectory of admin costs over programme lifetime	No formal agreement but proposal contained in commercial proposal / (Score B)
5.4) Frequency and quality of reporting from PMU	Set of sectoral mappings have been commissioned / Reporting format and cycle agreed between DFID and PMU	Sector mappings will begin as soon as contract is signed. / Not formally agreed but contained in technical proposal. / (Score B)

As with outputs 1 – 4 achievements under this output are restricted due to the fact that the contract has not yet been signed and therefore activity has not officially started. However as key members of the project leadership team are based in Addis, and are active in the EIAF sectors in other ways, relationships with Government stakeholders have already been made, which will be leveraged by EIAF. In addition, as the supplier already has an office in Addis the time it will take to set up the PMU will be minimised.

Although the PMU systems and procedures will formally be agreed under the inception phase, the preferred supplier’s technical proposal contains the foundation of many of these.

Recommendations

The business case for EIAF states that achieving the project outcome will require a sufficient start-up phase, long-term engagement and activities spanning several years. For these reasons the business case put forward the case for a five year programme, forecasting spend from 2015/16 to 2019/20. The terms of reference for both the main implementing partner and the TRAMP stipulate the contracts will be for 5 years. However the total programme length on DFID systems is five years, which does not account for significant procurement lead time. This inconsistency is partly due to optimism bias in the design stage (which forecast spend in 2015/16) and partly an oversight of not aligning the different timelines. It is recommended that the programme be extended on the DFID systems to ensure consistency with the period of the contracts. A submission should be made to the DFID Ethiopia Head of Office for a decision on this.

As set out in the business case, the log frame will evolve as the programme mature. The log frame should have a light touch update immediately to ensure that baseline data is as accurate and up to date as possible.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
To date the programme has disbursed a total of £372,700, approximately 1% of the total programme budget.
- £22,700 was spent on the power sector workshop (see output 2), which covered travel and expenses for 8 team members, who provided their time pro bono.
- £350,000 out of a total allocation of £705,000 was disbursed to the World Bank in March 2016 for a series of studies related to Urban Development (see output 3). The World Bank has just signed a contract with a supplier and the first payment of approximately £11,000 is about to be disbursed.

The contract for the implementation of the main programme facility will be signed by mid-June. The total value is £30 million. DFID expects that front line delivery of technical advice will account for 82% of the contract value and management and administrative costs will account for 18%. This is within the normal range for this type of project as strong programme management and administration is required for the programme to operate in a flexible and responsive way and to be continually learning. For example, administrative overheads of the Nigeria Infrastructure Advisory Facility (NIAF) have trended down to 15.7% after ten years of implementation. A decline in admin fees over time is also expected for EIAF and this will be monitored throughout the life of the contract.

VFM performance compared to the original VFM proposition in the business case
The business case did not present specific VFM indicators. It instead recommended an approach to measuring VFM using indicators tailored to specific projects. Only one project has been completed – the power sector workshop. Ten key policymakers attended resulting in a cost per government participant of £2,270, which is assessed to be good value for money given the caliber of presenters. Although it is difficult to directly link the workshop with tangible outcomes, it did take place at an opportune time, while Government is in the early stages of setting policy for private participation in the energy sector.

The broader basis presented in the business case of why this programme is likely to be good value for money remains relevant. There is potential for large benefits from improving the effectiveness of public investment spending as the Government continues to invest heavily in public investment. The assumptions in the theory of change remain valid and therefore it is expected that benefits will be realised.

Assessment of whether the programme continues to represent value for money
Overall the information presented in this review suggests that the programme represents value for money. Although progress on mobilisation of the programme activities has been slightly slower than anticipated at the design stage, this has not been associated with any financial cost – only 1% of programme resources have been expended.

DFID is confident that the best value for money possible was secured from the procurement process. Following an extensive early market engagement exercise the tender elicited a strong response and 7 credible international firms submitted bids. The technical content of the winning bid was extremely strong and fully met the requirements set out in the Business Case and ToRs. The commercial proposal demonstrated good value for money through competitive fee rates, cost avoidances and economies of scale.

Quality of financial management
No financial reports or audits have been required yet due to the early stage in the project cycle.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK

Overall risk rating: Moderate

Overview of programme risk
The overall risk environment has not changed significantly since the business case was approved, however the probability and triggers of a small number of specific risks have changed. These changes have been reflected in the updated risk register. None of the risks identified in the risk register are high probability, high impact and only one (an excessive focus on capital spending and insufficient spending on operation and maintenance) is high probability, medium impact. This being mitigated through capacity building within the programme.

The key risks to the success of the programme are:
- Issues related to the macroeconomic and broader economic policy making environment. Deterioration in the policy environment could undermine gains made by EIAF and reduce the likelihood of the outcome being met.
- The sectors that EIAF will be supporting expose the programme to environmental and social, as well as reputational, risks. EIAF could inadvertently support a project which somehow has links to negative social or environmental impacts. The programme has taken steps to mitigate this through its risk assessment and approval processes but it is impossible to entirely eliminate.

A key operational risk will be balancing the speed and flexibility that is integral to the programme design, with governance arrangements that secure genuine government ownership. Too little oversight from government risks disengagement and lack of demand, whereas too much risks slowing down approval processes. This will be a delicate balance which may require regular adjustment of the governance arrangement to get right.

The preferred supplier has designed a risk assessment, monitoring and mitigation strategy which will become operational once full programme implementation begins.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The mobilisation of the main contract under this programme has taken longer than expected. This has primarily been due to the complexity and innovative nature of the contract. This has not resulted in any additional costs and will not have any adverse impacts on the potential benefits of the programme.

Asset monitoring and control
This programme does not currently have any assets.

G: CONDITIONALITY

There is no specific conditionality attached to this programme. Commitment to the Partnership Principles does not play a specific role in the management or monitoring of this programme, therefore a programme level Partnerships Principles Assessment (PPA) has not been undertaken. Our assessment is that this assessment remains valid and there are no plans to undertake a PPA in the next year.

H: MONITORING & EVALUATION

Evidence and evaluation
There has been no significant change in the evidence base since the approval of the business case and therefore the theory of change remains valid.

The DFID Ethiopia team has recently developed a monitoring, evaluation and learning (MEL) strategy for EIAF. This builds on the information in the business case and sets out priorities for MEL of the EIAF programme. The terms of reference for a supplier to deliver the function of Technical Review and Monitoring Panel (TRAMP) have been shared in draft form with suppliers under a ‘Prior Information Notice’. The full Pre-Qualification Questionnaire and Invitation to Tender will issue in mid-June. If the planned timeline is adhered to the contract should be in place by December 2016, however there is a risk that this could slip and there would be no external technical review and monitoring function in place before the next annual review.

Monitoring progress throughout the review period
Apart from seeking feedback from Government on the energy sector workshop no monitoring activities have taken place.