Type of Review: Annual Review

Project Title: Support for Electoral Reform in Pakistan (SERP)
Date started:	April 2012	Date review undertaken: January 2013
## Introduction and Context
What support is the UK providing?
DFID is providing £5.4 million for IFES to implement the Support for Electoral Reform Programme (SERP) from April 2012 to December 2014 in Pakistan. UKAid funding amounts to approximately 40% of the $20.4 million project, which is jointly funded with the Canadian International Development Agency (CIDA) and the European Union (EU). This support will help to build capacity of the Election Commission of Pakistan and the delivery of its Five Year Strategic Plan in order to deliver credible federal, provincial and (dependent on timings) local elections. With monitoring and evaluating costs, the total cost of the DFID support is £5.68 million. In addition, the Conflict Pool has confirmed it will provide £1.2 million to IFES to support training of election officials.

What are the expected results?
The ultimate impact is a stable, inclusive and tolerant democratic state in Pakistan that is accountable and responsive to all of its citizens. The outcome is a more credible inclusive electoral process focusing on the conduct of the next general elections and the next local government elections. This outcome will be assessed by considering international and domestic observer reports on the elections alongside voter turnout. The project will contribute to registered voter turnout increasing from 44% (35 million in the 2008 elections) to 50%, with 40% turnout of registered women voters (the actual number of voters this represents will depend on the size of the final voter list). / Outputs include: / Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections – IFES is assisting with drafting updated legislation including a proposal for a Unified Electoral Law. / Strengthened institutional capacity of the ECP to manage the electoral process –IFES is providing technical assistance to the ECP to implement their Strategic Plan; / Increased professionalism and competence of election officials –IFES is assisting the ECP with its short-term and long-term training needs; / Improved and accurate electoral rolls that can be updated and challenged for any inaccuracies –IFES is offering ongoing technical assistance that builds on previous support work; / Enhanced capacity of ECP to conduct electoral operations – IFES is assisting with updates and improvements to electoral systems and procedures, and the procurement of ballot boxes. / Strengthened ECP capacity in the conduct of voter/civic education – IFES is assisting with the preparation and implementation of the ECP Voter Education Plan 2012-13. / Increased civil society organisation (CSO) capacity for the conduct of voter/civic education ­­– IFES is preparing guidance and materials for civil society and will support manage sub-grants. / The result will be a more capable and independent ECP that is focused on delivering to citizens. This will increase public and civil society (including political parties) confidence in the ECP making acceptance of the results more likely. This will in turn support a more peaceful political transition and a more legitimate, accountable and democratic government. Evidence shows that more accountable and responsive states are better at meeting the needs of their citizens and more likely to deliver stability than are autocracies or transitional democracies[1]. Moreover, democracies generally have higher economic growth rates than autocracies[2] and faster growth generally means faster reduction in absolute poverty.[3] Effective governance is a key factor underlying economic growth[4] and poverty reduction.
[1] Sen, A (2009) Development as Freedom, Oxford University Press.
[2] Low income democracies have average growth rates 30% higher than low income autocracies. See Halperin H, Siegle J and Weinstein M (2010) The Democracy Advantage: How democracies promote prosperity and peace.
[3] World Bank (2005) Economic growth in the 1990s – learning from a decade of reform. Washington DC
[4] Kaufmaan D. and Kraat, A. (2002) Growth Without Governance, World Bank Policy Research Working Paper No 2928.

What is the context in which UK support is provided?
Pakistan is not assessed by the Freedom House Freedom In the World index as an “electoral democracy”[5] and elections have not consistently consolidated democracy. While the 2008 elections ushered in a return to civilian rule, the election process remains vulnerable to exclusion of certain groups, manipulation, and military interference[6]. As a result, democracy and the participation of citizens have remained weak. Without credible, inclusive opportunities for citizens to hold the state to account, the state has been less able to allocate resources in ways which meet the development needs of its citizens, especially women and other marginalised groups[7]. In addition, the lack of opportunities for genuine political participation has reduced confidence in the political systems and increased the appeal of militancy[8]. / Pakistan is due to hold federal and provincial elections by May/June 2013. These elections are an important opportunity: the first time in Pakistan’s history that a civilian government has completed its full term and transferred power through elections, to another democratically elected government. / Fully imbedding democratic institutions and effective governance happens over multiple election cycles. Pakistani voters remain sceptical that on Election Day their vote will count[9]. Common forms of electoral fraud as reported by domestic and international observers include: / the unauthorised transfer and re-posting of district administration/election officers; / pressuring candidates to change their political allegiance; / disqualifying candidates only days before polling; / intimidating voters[10]; / intimidating the media; / kidnapping of candidates, proposers and seconders by the police; / the theft of ballot boxes; / the unlawful use of nazims and local government councillors[11] in support of political parties and candidates; and / denying parties permission to hold public rallies. / In some of the recent by-elections, women have been prevented from voting and been almost entirely absent from the voting process[12]. There are estimates that the voter lists exclude 10 million women[13]. That alone would disenfranchise approximately 12% of the estimated voting-age population. / At the same time, the conditions that enabled the 2008 transition from military to civilian rule remain in place including a proactive judiciary, an active civil society and growing media autonomy and youth engagement. Perception studies show that the public still value democracy[14] and want elections to be held on time[15]. Moreover, there have been a number of impressive democratic achievements since 2008 that increase prospects for a credible election. This includes the 18th Constitutional Amendment, which devolved power from the President to the Prime Minister and from the National Assembly to the Provincial Assemblies and reformed the appointment procedure for the Election Commission of Pakistan; and the 20th Amendment setting out the process for agreement on a Caretaker government. The challenge for donors will be in supporting these positive dynamics, and helping the election process draw upon them, supporting Pakistan’s move towards democracy on its own terms.
[5] See Freedom House Index Freedom in the World 2011
[6] See ELECTIONS IN PAKISTAN THE ROLE OF THE UK AND THE INTERNATIONAL COMMUNITY 2000-2008 Mohammad Waseem, Lahore University of Management Sciences (LUMS) Lahore Fauzia Yazdani, Consulting Researchers, Islamabad
[7] Gazdar, H. (2007). Class, Caste or Race: Veils over Social Oppression in Pakistan
[8] As noted in the 2011 Pakistan Country Governance Analysis
[9] Only 15% of voters thought the 2008 election would be fair (Gallup Pakistan survey November 2007)
[10] Observed in 10% of the constituencies monitored by the Free and Fair Election Network (FAFEN) in 2008
[11] In up to one-third of constituencies observed by FAFEN in 2008
[12] See FAFEN 25 November 2011 report on Kohistan by-elections. Female voters were prevented from voting reportedly due to an informal agreement among political parties.
[13] See FAFEN reports
[14] An April 2011 Gallup Pakistan National Public Opinion Poll  showed that 61% of respondents said that the solution to Pakistan’s social, economic and security issues lay in democracy.
[15] 56% Pakistanis believe that Electoral System should change but elections should be on time. .Gallup Poll January 2013.

## Section A: Detailed Output Scoring

Output 1.1: Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections
Output 1 score and performance description: A – outputs met expectation
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. Degree to which legal framework meets international standards 5 (standards met in adopted legal framework) Baseline+1 +1 in draft unified law pending approval Baseline+5 B / 2. Number of adopted laws or amendments designed to improve credibility of elections that were drafted with IFES assistance 0 +2 +3 amendments designed and submitted to parliament by ECP 6 (one new unified law adopted and 5 acts repealed) A+ / 3. Number of recommendations that are relevant to the legal framework and consistent with international standards made by civil society organisations that are incorporated into the legal framework 2 adopted; 74 proposed +1 adopted +2 approved by the ECP and Cabinet, pending adoption by Parliament. / +1 proposed (75 total proposed) Baseline + 3 adopted A+ / IFES has made substantial contributions to proposed reforms associated with the legal framework for elections in Pakistan that are in line with international standards, improve the credibility of elections and reflect the concerns of civil society. / Overall the contribution of IFES in terms of identifying, advocating for and drafting legislation is widely recognised, not least by the ECP, and it is clear that IFES is regularly used as a technical advisor and resource for guidance on international standards, comparative examples and legal issues in Pakistan, as well as for extensive legal drafting. While this has clearly enabled the ECP to move forward more swiftly and effectively on crucial legislative reforms, longer-term sustainability and ECP capacity will depend on gradually shifting the burden of drafting to the ECP through continued capacity building. / The assessment of the project’s contributions to reform of the legislative framework for elections is partially undermined in the output scoring by the fact that in all cases the associated legislation has not yet been approved by Parliament. While the enactment of the laws is the ultimate goal, it is important to take into account the achievements in securing the approval of the ECP and in preparing for future change, as well as the severely limited influence IFES could have over any subsequent steps in the parliamentary approval process. / Indicator 1.1: Degree to which legal framework meets international standards: / Most of IFES’ work on the legal framework has taken place in the context of efforts to introduce a Unified Electoral Law, which IFES has been supporting since 2009. The Unified Electoral Law brings together five different electoral laws, the consequential amendments resulting from the 18th Constitutional Amendment, recommendations from the National Assembly Standing Committee on Law, Justice and Parliamentary Affairs and other amendments agreed on by the ECP with IFES technical assistance. Amendments that IFES has assisted the Election Commission of Pakistan (ECP) in identifying as priorities before the general elections have also been included. The draft Unified Electoral Law is now before the ECP for approval, after which it will go to the Special Committee of the Senate and the Standing Committee of the National Assembly. / In terms of international standards, IFES has advocated for the draft Unified Electoral Law to meet international standards. (Pakistan is a signatory to the International Convention on Civil and Political Rights (ICCPR) and the Convention on the Elimination of all forms of Discrimination Against Women (CEDAW), both of which lay out standards and commitments that are relevant to elections). IFES report that the draft law is in line with international election standards however, there may be changes made before it is passed. Looking ahead, IFES has flagged as priority areas for attention in future are clarity in election dispute mechanisms, presence of legal provisions on election observers and provisions on accreditation requirements for domestic election observers. / Despite IFES’ work under this indicator, the draft law is still with the ECP for approval and so there has been no change to the legal framework. For this reason, this indicator has been scored a B (while noting that this is beyond IFES’s control). The project could explore whether there are opportunities for joint activity with Democracy Reporting International (DRI) through its parliamentary programme that could assist with securing approval of the relevant legislation. / While waiting for the approval of the draft Unified Electoral Law, IFES is also working on a draft of Unified Election Rules and a list of priority rules to be adopted before the general elections. IFES has also worked closely with the ECP in the drafting of Codes of Conduct for Political Parties and Candidates (finalised), Media, Polling Personnel, Observers and Security Personnel, including collaboration with the implementers of other related projects – notably UNDP/UNWOMEN – to improve the associated consultation processes. / IFES also helped the ECP to respond to the Supreme Court Judgment No 87. of June 2012 by providing in‑depth analysis of the judgment and highlighting options for immediate implementation in by-elections of some elements that would not require legal amendments. However, neither this nor IFES’s support for drafting and stakeholders consultations on codes of conduct are currently captured under output indicators. / Indicator 1.2: Number of adopted laws or amendments designed to improve credibility of elections that were drafted with IFES assistance. / The ECP, with IFES assistance, has drafted a Bill with three amendments designed to improve the credibility of elections. The ECP and the Federal Cabinet have approved the Bill. It is now pending adoption by Parliament. The amendments are: / Introduction of photographs of voters in the electoral rolls / Collection of gender-disaggregated data of voter turnout at each polling station / Empowerment of the Commission to declare the poll void if it is proven that women were restrained from exercising their right to vote. / In addition to these amendments, the draft Unified Electoral Law also includes 28 amendments drafted by the ECP with IFES assistance and 53 consequential amendments resulting from the 18th Constitutional Amendment, drafted by IFES. / As this indicator reflects IFES’ role in drafting laws and amendments rather than efforts to secure their approval, and as ECP approval has been secured for the main three amendments attributed to the indicator, it has been scored A+. However, while we expect that the introduction of photographs and gender disaggregation of voter turnout will be implemented, the issue of whether a poll should be declared void if women are prevented from voting is more controversial and unlikely to be implemented for this election. / Indicator 1.3: Number of recommendations that are relevant to the legal framework and consistent with international standards made by civil society organisations that are incorporated into the legal framework. / In 2011, IFES assisted the Free and Fair Elections Network (FAFEN – also funded by DFID and whose work provides the “demand” to the IFES/ECP “supply”) to prepare a package of laws based on civil society input, which provided a baseline for this indicator. The package consisted of 74 proposed reforms, two of which were adopted before April 2012 and therefore form the baseline for the project. The two additional reforms that have since been included in the proposed legislation are: / Gender disaggregation of voter turnout / Empowering the Election Commission to declare a poll void if it can be proven that women were prevented from exercising their right to vote / In 2012 IFES also worked closely with Democracy Reporting International (DRI) to feed recommendations from additional stakeholder consultations including those from a Senate Special Committee on Elections public hearing into the legislative reform process and a set of IFES-driven recommendations for priority changes to implement before the election. / Another useful source of recommendations is the European Union Election Observation Mission (EU EOM) of 2008, which put forward 83 recommendations. An EU EOM is planned for the 2013 and as the methodology and assessment framework will be consistent with that used in 2008 it can offer a useful baseline to assess progress. EU EOM mission findings are already referenced at outcome level but could be explored as an option to feed into these indicators at output level. / The changes to the legal framework that were drafted with technical assistance from IFES have been accepted by the ECP and are therefore counted as additions under this indicator. This indicator is therefore scored A+. However, as mentioned under 1.2 above, the issue of whether a poll should be declared void if women are prevented from voting is unlikely to be implemented for this election. / The review team also note that indicators 1.2 and 1.3 report on two of the same amendments. For the purposes of this review it has been agreed that this is not duplication because the indicators look at two different types of contribution – for 1.2. at the drafting process and for 1.3 at the responsiveness to civil society. However, for future reviews the indicators should be updated to ensure that they clearly measure different contributions. / A note on IFES’ coordination role / IFES has played a major role in bringing together the election stakeholders for coordination purposes, for example as facilitator and host of the Election Support Group, which meets monthly bringing together donors and implementers. The ESG could be further strengthened by making it more participatory and consultative. It appears that IFES recognises the importance of this forum and is acting accordingly, for example by enabling groups such as FAFEN to present on key aspects of their activities. IFES also meets regularly with other key project implementers including DRI and NDI, and between the organisations there are clearly identified roles, as well as encouraging indications of integrated activity including reciprocal contribution at each other’s events. / This role is not adequately reflected in any of the current outputs. It could be included in future under output 1 as a reflection of increased interaction with stakeholders to ensure broad public support for reform but would require an additional specific indicator to reflect the nature of the work. / Recommendations: / EITHER update indicators 1.1-1.3 to reflect drafting and ECP approval of legislation rather than Parliamentary approval and enactment OR ensure that the programme’s strategy for securing approval is clearly documented and feasible. Formal approval of legislation could be considered for an additional outcome level indicator. Explore options for referencing EU EOM at output indicator level. / Review indicators 1.1., 1.2 and 1.3 to ensure they do not report on the same activities – for example indicator 1.3 could be revised to reflect promotion of ECP engagement with civil society on the legislative framework. / Include an additional indicator to reflect IFES’ role in coordinating stakeholder meetings. / EITHER include an additional indicator for drafting of Codes of Conduct and responding to Supreme Court requests OR clarify which of the current indicators they will be reported under. / Explore post-election options for increasing in-house ECP capacity for drafting and legal analysis with IFES mentoring. / Continue to advocate for approval of the Unified Electoral Law and follow-up regulations. Explore options for closer collaboration with the DRI parliamentary programme to do so. / Consider how EU EOM mission findings could feed into output level indicators. / Increase the impact weighting given the proportion of IFES time spent on this output. / Impact Weighting (%): 15%+10%=25%[16] / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[16] Impact Weighting of output 3.2 (10%) moved to output 1.1

Output 2.1: Strengthened institutional capacity of the ECP to manage the electoral process
Output 2.1 score and performance description: B – outputs moderately did not meet expectation
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. Number of IFES-supported objectives of the ECP’s Strategic Plan achieved 35 objectives Baseline+5 +2 objectives completely achieved. 60% of the objectives achieved overall. Baseline+25 B / The status of progress against the ECP Strategic Plan (2010-2014) as of December 2012 was as follows: / 37 objectives achieved / 77 objectives underway / 13 objectives not started because of the implementation timeline or timing of upcoming general election / 2 objectives no longer applicable / ECP estimates that it has completed 60% of the plan / The current indicator reflects only the number of fully completed objectives which therefore fails to take into account partial progress on objectives and generates a score of B. In this context, an approximation of what percentage of the plan is complete may be a more appropriate indicator. Completion of 60% of the plan within 2 (of 3) years would suggest that implementation is broadly on track. / In addition to a broad measure of progress against planning, IFES may be able to identify specific objectives that are most relevant to the management of future elections and should be given priority in assessing progress under the Plan. / The Strategic Plan was developed with support from IFES under a previous project and forms the foundation for SERP planning. As such a broad range of project activities contribute in some form to the Plan’s objectives and the indicator may be more appropriate at outcome level. This would also be consistent with the fact that ECP initiatives and activity independent of IFES support also contribute to completion of objectives under the Plan. The Plan is consistently referred to by the ECP in conversations as their baseline planning document and is therefore likely to remain a lynchpin for SERP programming. While IFES makes a strong contribution to achievement of the Plan, as the project is not directly responsible for implementation of the Plan (which falls to the ECP) and is also one of several organisations providing support to ECP in implementing aspects of the Plan (notably UNDP/UNWOMEN) this indicator would be more appropriate at outcome level. / Recommendations: / Output 2.1. to be removed from the logframe. The associated indicator (2.1.1.) to be raised to outcome level and adapted to take into account partially- as well as fully-achieved objectives. Impact weighting to be distributed across other outputs. Consider using the 2013 EU EOM reporting as a source for cross-verification of reporting against Strategic Plan achievements. / IFES to identify priority objectives within the Strategic Plan to be assessed individually in addition to the overall performance against the Plan. / Explore post-election options for investment in planning processes that will ensure a smooth transition from the current Strategic Plan to a successor plan in 2014, including a possible Strategic Plan refresh. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2.2: Increased professionalism and competence of election officials
Output 2.2 score and performance description: A – outputs met expectation
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. Degree to which job skills, electoral knowledge, and electoral event trainings for temporary election staff supported by IFES result in increased job knowledge of participants = Average of 70% of PrOs and 30% of ROs performed Election Day duties correctly during the 2008 election N/A N/A Average of 75% of PrOs and 40% of ROs performed their Election Day duties correctly during Pakistan’s General Election N/A / 2. Degree to which job skills, electoral knowledge, and electoral event trainings for permanent ECP staff supported by IFES result in increased job knowledge of participants. 0 80 permanent employees have undergone skills training with an average 15% increase in knowledge 124 employees trained: / 42 underwent core skills training with an average 9% increase in knowledge. / 82 were trained as Lead and Master Trainers and not scored for increase in knowledge. 300 permanent employees have undergone skills training with an average 15% increase in knowledge. A / The training contributions of IFES have both short-term (indicator 2.2.1) and long-term (indicator 2.2.2) horizons. / Indicator 2.2.1: Degree to which job skills, electoral knowledge, and electoral event trainings for temporary election staff supported by IFES result in increased job knowledge of participants / Under indicator 2.2.1, IFES focuses on preparing temporary election staff to perform effectively in election contexts. While the main indicator focuses officials’ performance during the General Elections anticipated for 2013 and are therefore not reported on at this stage, IFES preparations have already included preparation for training of District Returning Officers (DRO) and Returning Officers (RO), and piloting of different systems of cascade training during three by-elections in order to assess the most effective method for ensuring high quality training for all polling officials for the General Elections; preparation – in collaboration with the United Nations Development Programme (UNDP/UNWOMEN) – of a comprehensive training plan approved by the ECP, and which the ECP regularly refers to; and training of a core of Lead and Master Trainers (reflected under indicator 2.2.2.). / IFES and UNDP/UNWOMEN have worked closely throughout the process of preparing for training of polling officials, and have established a clear division of labour based on Pakistan’s administrative Divisions, which is clearly understood by all ECP officials. The decision for IFES and UNDP/UNWOMEN to be directly involved in the roll-out training was made following the by-election pilots and in conjunction with the ECP in order to ensure high quality training and performance of officials. The DROs and ROs in particular have a substantial role to play in the election process including review of nominations papers, management of the voting process and polling officials, and front-line management of any complaints or incidents, and need to be fully equipped to deal with these processes. While the review team would strongly encourage a shift toward more direct implementation led by the ECP’s training institute – the Federal Election Academy (FEA) – in future, it recognises that limitations in terms of FEA capacity and resources make this unfeasible for the current elections. / Based on current status of preparations and the decision to retain direct IFES (and UNDP/UNWOMEN) involvement in training, as well as the experience gained by the ECP since 2008, it is realistic to anticipate that the target for this indicator will be met. / Indicator 2.2.2: Degree to which job skills, electoral knowledge, and electoral event trainings for permanent ECP staff supported by IFES result in increased job knowledge of participants: / Under indicator 2.2.2., IFES focuses on the core capacity needs of the ECP. IFES worked with the ECP to develop the ECP-Federal Election Academy (FEA) Training plan for 2012-13, which has been approved by the ECP. In line with the plan, specific achievements under this activity are as follows: / BRIDGE Workshop on Pre-Election Activities for ECP mid-level management – 25 participants. Average increase in knowledge as measured by pre-and post-training surveys (carried out at the end of the training sessions) was 16%. / BRIDGE Workshop on Political Finance for ECP’s senior management officers – 17 participants. Average increase in knowledge was 3%. Poor uptake is attributed to the complexity of the material, particularly given the limited prior exposure to the theme in Pakistan, and a mismatch between the training materials (which focused on theoretical examples) and the post-training questionnaire (which focused on the Pakistan case). IFES is planning follow-up training that would be more closely tailored to the needs and circumstances of the ECP. / Training of Lead and Master Trainers (see indicator 2.2.1 above) – 48 new participants, 34 participants receiving “refresher” training. Knowledge gained was not tested by questionnaire but was clearly demonstrated as the Trainers carried out follow-up trainings for polling personnel for by-elections. / While the use of post-training questionnaires administered immediately after training is a useful measure of attention paid during training, a better indication of knowledge retained would be secured either from questionnaires administered after a few weeks or months or from indicators that reflect the ways in which knowledge is being put into practice. In the case of training Trainers, in particular, IFES should ensure that there is a more formal indication of the effectiveness of the training. If questionnaires on knowledge gained do not accurately reflect the quality of participants’ training skills, records of follow-up trainings run by those trainers or feedback from participants in future trainings may be more useful. Staff retention can also provide a useful indication of whether the investment has been effective, although external factors can also affect staff movement. / The project’s investment in training of core staff with a longer-term capacity building perspective has been hampered in some cases by the more urgent short-term needs and focus of the ECP. Initially the ECP gave priority to the preparation of electoral rolls in early 2012 and more recently the ECP has put on hold any training not directly associated with preparation for general elections in 2013, including postponement of a BRIDGE Voter Education training planned for December 2012. / Feedback from the project team and others suggests that progress on building the capacity the FEA to manage its training programmes independently has been somewhat disappointing in this period, but also that the major obstacles, including the failure to put in place four key staff members, are not within the immediate control of the project. Among the most significant challenges are high management turnover and shifting ECP priorities as they respond to emerging obstacles, which has in some cases led to decisions to postpone internal capacity building workshops. / Recommendations: / Pre elections ensure knowledge gained through training of lead and master trainers can be measured and that Political Finance training and testing is set at an appropriate level. / Explore post-election options for: / increasing the involvement of ECP personnel –in particular the FEA– in provision of training for both temporary polling officials and permanent staff; / bolstering the core capacity of the FEA in conjunction with the ECP including ensuring that permanent staff are recruited and supported to take responsibility for meeting the ECP’s training needs, and that adequate budgets are agreed and provided; / establishing concrete, agreed long-term training plans with the ECP and FEA in order to reduce the impact of last-minute changes and to ensure that plans are fully in line with ECP priorities; / Shifting the balance of donor- support to training and the FEA in order to reduce dependence on donor support in future; and / Exploring options for increasing effectiveness of ECP/FEA training approaches including mentoring and specialisation of trainers. / Update the indicators for this output to reflect not only training provision but also the mechanisms through which it is provided as this is a major contribution of IFES. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2.3: Improved and accurate electoral rolls that can be updated and challenged for any inaccuracies
Output 2.3 score and performance description: B – outputs moderately did not meet expectation
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. Number of parties, domestic observer groups and citizens with confidence in the electoral rolls 0 political parties and observer organisations, 51% of citizens 53% of citizens 46.2% of citizens 20 organisations (16 political parties in the ECP consultative group and 4 observer organisations of which at least 1 is a women’s group); 65% of citizens B / IFES’ recent survey results found that 12.8% of citizens believe the voter list is accurate to a great extent and 33.4% believe it is accurate to some extent. It is likely that the decrease in confidence has been influenced by the recent Supreme Court order for the ECP to re-verify the electoral rolls in Karachi, and the political parties questioning the accuracy of the rolls in the media. / The ECP has responded in Karachi by organising a door-to-door re-validation exercise, which may have a positive (or negative) influence on public confidence in the electoral rolls. / Given the sensitivity of confidence in electoral rolls to changes in political environment, the target for December 2014 seems ambitious and moreover is ultimately not within IFES’ control, not least as IFES is not directly responsible for convincing political parties, observer organisations and the public of its quality and is explicitly discouraged from engaging with political parties outside the formal consultative frameworks in which it supports the ECP. While public confidence in the electoral rolls is clearly a crucial factor in the likely success of elections, it is also important to recognise that technical analysis of the quality of the electoral rolls clearly indicates major improvements in their accuracy between 2008 and 2013, with approximately 40m names removed and re-verified during the 2011 update process and a much closer link with the civil register (NADRA). / Recommendations: / This indicator may be more appropriate at outcome level given the limited influence IFES has over it. Depending on the level of engagement they expect to have on electoral rolls over the lifetime of the project, IFES may consider developing (an) alternative indicator(s) that reflect their specific contributions – for example related to the take-up of IFES recommendations on the Electoral Rolls Format on Election Day and on the "Anonymisation” of Electoral Rolls placed in the public domain (both currently reflected under Output 2.4), or an objective assessment of the quality of the Electoral Rolls through an audit process. / The issue of underrepresentation of women on the electoral roll has emerged as a concern in 2012, related in part to the under-registration of women in the civil register, which is a formal pre-requisite for registration as voters. IFES can play an important role in keeping the issue on the agenda for ECP and assisting them in tackling this challenge, ideally in collaboration with other organisations working on related issues such as Aurat Foundation and FAFEN. / Reduce the impact weighting given the proportion of IFES time spent on this output. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 2.4: Enhanced capacity of the ECP to conduct electoral operations
Output 2.4 score and performance description: A+ – output moderately exceeded expectation
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. Number of electoral operations systems and procedures amended and strengthened with IFES assistance 0 +2 +3 7 A+ / 2. Number of ballot boxes procured for elections through SERP 0 Order placed Order placed after a competitive tendering process 41,000 ballot boxes used for general and other elections A / IFES’ guidance to the ECP on electoral operations systems and procedures is a major factor in the project’s efforts to build sustainability and therefore a crucial indicator of project success. IFES has focused on presenting options for –and supporting the introduction of– systems and procedures that will not only change the way the ECP runs elections in 2013 but that also implement those changes in a way that is easy to sustain for future elections. Standard Operating Procedures, forms and templates, and accompanying training materials and handbooks all help to ensure that the ECP will follow the agreed changes in future. / The ECP has made clear that it values the contribution of IFES to systems and procedure design, and regularly seeks IFES input as part of the design process. The way in which this is done, however, is usually through a request for a concept note, which increases the dependence on detailed paperwork and potentially reduces the diversity of options explored. This can also mean that IFES carries out extensive work that does not always immediately translate into a decision and follow-up implementation but that may be revisited or adjusted for implementation in future. / Indicator 2.4.1: Number of electoral operations systems and procedures amended and strengthened with IFES assistance / The following electoral operations systems and procedures have been developed and approved by the ECP with technical assistance and input from IFES: / A procedure for the inclusion of new National Identity Card holders’ data in the electoral rolls after field verification; / Procedures for door-to-door re-verification of electoral rolls in Karachi Division on the order of the Supreme Court; and / A format for including photos in the electoral roll with space for obtaining thumb impression, which will be used in polling stations. / Contributions to ongoing decision-making include: / A concept paper on “Anonymisation” of Electoral Rolls in the Public Domain / An electoral roll format for polling stations with sample data developed for a concept outlining” Electoral roll design at polling stations” advocating sorting of electoral rolls based on voters’ names instead of household number and also changing the current process so only one electoral roll is required per polling station. / Concept paper illustrating viable options for sorting of electoral rolls in polling stations, highlighting the pros and cons of each proposed option. / Concept paper for monitoring committees to help establish and train monitoring teams to monitor the upcoming General Elections [already piloted in by-elections]. / Concept paper on ballot paper integrity. [Shared by the ECP with the Printing Corporation of Pakistan and Security Printing Press]. / Support for the conduct of a GIS pilot. / Indicator 2.4.2: Number of ballot boxes procured for elections through SERP. [Note there is no opportunity for exceeding expectations on this indicator.] / The procurement of ballot boxes under the project was added in October 2012 on the understanding that this was a core need of the ECP in order to implement elections effectively after the supreme court verdict to reduce the average radius of polling stations, and one that the Government of Pakistan was unable to meet in the timeframe required. Procurement is underway. The vendor has been selected and production is in progress. Expected delivery time is late February 2013. / Recommendations: / Consider updating indicator 2.4.1 to reflect partial progress (e.g. submission of concept notes) as well as adopted procedures. / Consider how the risk of flooding/natural disaster would be managed by the ECP in the event that they occur around election time. / Explore post-election options for adapting ECP approach to designing and modifying systems, possibly through increasing in-house ECP capacity for drafting concept notes with IFES mentoring. / Continue to advocate for approval of key systems and procedures within the ECP. Ensure there is a close link between design/approval and supported implementation. Explore mentoring options to increase uptake. / Work with the ECP to identify specific systems and procedures to target for reform in the post-election period. / If possible, work with the ECP on forward planning and budgeting to avoid situations in which external resources are required for core election costs. / Consider increasing the impact weighting given the contribution this work makes to sustainability. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3.1: Strengthened ECP capacity in the conduct of voter/civic education
Output 3.1 score and performance description: A+ – output moderately exceeded expectation
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. ECP successfully implements its voter/civic education plan 0 = first time for establishment of plan Adoption and beginning implementation of voter education plan Adoption of the voter education plan and 5 major implementation steps taken 6 components of the voter education plan implemented, 2 components of the civic education plan implemented A+ / Under this output, IFES provided technical and material support in the development of the first ever Voter Education Plan (VEP) 2012-13, which was approved in September 2012 by the ECP. The plan includes the following components: / District-centred national voter outreach supported by provincial governments / Participation of Government ministries/departments / Private sector engagement with civil society and others / Institutional strengthening of ECP through training and capacity building / Media campaign through electronic and print media / Voter education material development / Steps taken so far by the ECP with direct support provided by IFES include: / A briefing on the VE plan 2012-13 for media in October 2012. / National Voters’ Day (NVD) on 17 October – intended to become an annual event. Participation is estimated at well over 7000 (although the vast majority were male) across 114 events nationwide (1 national event in Islamabad, 4 in the Provincial capitals, 109 in the Districts). IFES, UNDP/UNWOMEN and ECP developed voter education materials for NVD. IFES provided 100,000 pamphlets, 6,000 posters, 266 banners. In preparation for the event, IFES and the ECP disseminated 1,100 VE CDs (with materials for re-printing) to 213 civil society organisations and to the ECP for distribution to government, autonomous bodies, semi-government, private sector organisations and media, and have seen immediate results with confirmed use of materials by banks on ATM displays, by the Pakistani Post and Motor and Highway police on banners and by the Benazir Bhutto Medical University among others. / IFES with UN Women arranged provincial launches of the VE Plan in Balochistan and Sindh to provide orientation to the participants and get feedback to refine the ECP’s VE strategies. / While these steps in themselves demonstrate considerable progress, the most significant achievement in this area has been the consistent buy-in across the whole ECP structure for voter education. Voter Education was emphasised in meetings with the ECP, and there is widespread awareness of ongoing activities. There was also regular mention by ECP officials of the need to increase women’s participation and to target women with voter education activities, although the specific approaches were not always clear. This is an area in which both IFES and UNDP/UNWOMEN have active projects with the ECP and while the two organisations have established clear boundaries in terms of their responsibilities and engagement, are working well together on joint initiatives such as design of materials, and have briefed the ECP on their plans, the ECP still expressed some confusion about the specific limitations of IFES’ role in terms of their contributions to ECP activities and training of ECP officials. / Recommendations: / Consider adjusting indicator 3.1.1. to reflect priority aspects of the voter/civic education plan. / Continue working with the ECP to increase outreach to women as part of its voter education plans. / Work with the ECP to explore how their voter education initiatives could contribute to public confidence in the ECP and its systems, including confidence in the electoral rolls. / Explore post-election options for sustaining ECP interest in civic/voter education beyond the General Elections. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3.2: Increased Civil Society Organisation (CSO) capacity for the conduct of voter/civic education
Output 3.2 score and performance description: N/A
Progress against expected results: / Indicator Baseline Milestone 1 Dec 2012 Achieved Target Dec 2014 Score / 1. Degree to which the understanding of target citizens of the electoral/voting process is enhanced 0 N/A N/A 62% of the target population of CSO campaigns N/A / Preparatory work toward this output is underway and includes: / A Voter Education Activists Handbook - 500 copies of the first draft have been distributed for feedback and comments through provincial voter education plan launching events. / Circulation of a request for proposals for civic/voter education projects that focus on persons with disabilities and for innovative projects for support of VEP 2012-13. / IFES facilitation of three Voter Education Group meetings (June, July, September 2012). IFES and Democracy Reporting International’s (DRI) support to ECP to revive the Civil Society Consultative Forum (October 2012) to engage CSOs working on voter education. / Recommendations: / Consider adjusting or adding to indicator 3.2.1 to reflect contribution to improving CSO capacity more directly rather than the effectiveness of voter education, which is dependent on a much broader range of factors. / Consider adding an indicator under civic/voter education that reflects IFES’ coordination/facilitation contributions. / Ensure that IFES contributions are consistent with, build on, and draw on lessons learned from other ongoing initiatives to promote maximum sustainability. / Impact Weighting (%): 10%-10%=0%[17] / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[17] Impact Weighting of output 3.2 treated as zero and moved to output 1.1

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes. Since the start of the project, indicator 2.4.4. has been added to the logframe to reflect a new activity – purchase of ballot boxes for the ECP. / 1.2 Overall Output Score and Description: A – outputs met expectations / Output Score Weighting / 1.1 Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections A 15% / 2.1 Strengthened institutional capacity of the ECP to manage the electoral process B 15% / 2.2 Increased professionalism and competence of election officials A 15% / 2.3 Improved and accurate electoral rolls that can be updated and challenged for any inaccuracies B 15% / 2.4 Enhanced capacity of ECP to conduct electoral operations A+ 15% / 3.1. Strengthened ECP capacity in the conduct of voter/civic education A+ 15% / 3.2. Increased CSO capacity for the conduct of voter/civic education N/A 10% / Overall Score A / 1.3 Direct feedback from beneficiaries / The Election Commission of Pakistan is the primary beneficiary for SERP, although the program will indirectly benefit the Pakistan people as well. Extensive meetings were held with ECP during the course of review to gather feedback on their satisfaction with IFES’ performance over the past year. It was found that on the whole ECP is appreciative of the support IFES has been providing but there are areas where the support can be further strengthened. IFES support was highlighted as especially helpful in areas of legislative reforms, training and capacity building, as well as logistical support such as the procurement of transparent ballot boxes. / Provincial Election Commissioners and their Directors were broadly aware of IFES activities including the IFES-UNDP/UNWOMEN training plans for the upcoming elections and some voter education efforts, and had in several cases been the beneficiaries of training themselves. They had limited knowledge of the details of IFES work with the ECP centrally, however. IFES may benefit from investing more time in communicating details of its activities and approach at the provincial level, and also from encouraging greater provincial level involvement in its central activities. / It was found that the ECP-IFES relationship could be further improved through agreement on detailed work plans for the post-election phase. Joint ownership of work plans would allow increased information sharing and would be in the interests of both programme efficiency and also the key DFID principles of transparency and accountability. However, while SERP should support the ECP’s priorities, ultimately IFES are responsible for the delivery of SERP and, IFES have to remain able to take final decisions on its direction within the mandate of SERP and oversight of a steering committee if established.
1.4 Summary of overall progress / Since the publication of their first-ever Five Year Strategic Plan, the ECP has demonstrably changed the way they perceive their role, expanding their focus beyond the technical conduct of elections. Since the beginning of the SERP project, the ECP has taken a much more active role in voter education, spearheading the inaugural National Voter’s Day, and involving all its district offices in district-centred voter outreach. They have also clearly acknowledged the importance of providing training for polling officials, which they have demonstrated by approving trainings ahead of all by-elections since April 2012. In developing the Codes of Conduct, the ECP held stakeholder consultations to involve political parties, observers, and media in the electoral process in a transparent, productive manner. / Overall the project is broadly on track and making progress. With IFES support, preparation for elections are well underway and the ECP is well placed to manage a significantly more effective, transparent and inclusive election than previously: / A unified law has been drafted that reflects international standards, recommendations of civil society and the legislation needs of the ECP. Accompanying regulations are being drafted and updated, and Codes of Conduct are being developed – these are key components to provide a sound basis for credible elections and, where required, their formal approval by Parliament should be encouraged as quickly as possible. / The capacity of ECP to manage General Elections in 2013 is being increased through training of Lead and Master Trainers who will roll-out election-specific training for core election staff including DROs, ROs and polling officials. Plans are clearly defined and feasible, and preparations are on track. There has also been some progress on longer-term capacity building for permanent ECP staff. / Key systems and procedures for the election process are being developed with IFES support, although not all have yet been approved for use in 2013. The electoral rolls for 2013 are considerably more accurate than those used in 2008 and the project is helping ECP to design procedures for their use for public display and on Election Day. / The ECP has a coherent Voter Education Plan for 2012-13 and has made headway in the first steps of implementation including preparation and dissemination of materials, consultations with civil society, and designation of 17th October as the first annual “National Voters Day”.
1.5 Key challenges / Timing of elections: When the project was launched, the timing of general elections seemed uncertain due to political developments. While most stakeholders now anticipate elections on schedule in May/June 2013 there is still considerable political uncertainty. Timing of local elections is not yet confirmed. This uncertainty poses programming challenges for IFES, which must have the flexibility to respond at short notice without losing sight of longer-term objectives. / Short-term vs. Long-term needs: Imminent elections for most of the project life have meant that the ECP focus has been almost exclusively on short-term preparations for elections. In some instances this has prevented IFES from making headway on longer-term initiatives such as finalization of legislation, including unified law, reform of electoral system and reserved seats for women, the pilot on electronic voting machines, preparing for local elections, media outreach and restructuring of the ECP, including the formation of new units and wings. / While the current focus on election preparations is both inevitable and appropriate, once the elections are over, it will be important for the project to build on its achievements in its first year by expanding on its efforts to promote a greater degree of institutional sustainability. In the meantime IFES has worked hard to strengthen sustainability by promoting a durable and comprehensive legal framework and accompanying regulatory framework; and by emphasising systemic and procedural changes at the operational level with back-up Standard Operating Procedures and support to ensure that implementation becomes the norm rather than a one-off. The effectiveness of this approach can only really be gauged in terms of how ECP sustains processes once IFES’ involvement is reduced. / The post-election window is a clear opportunity for a shift in focus toward longer-term needs. Thinking about how to tackle the post-election period should begin well before elections in order to begin laying foundations and building support for key initiatives both within the ECP and more broadly. The findings of election observation missions including the EU election observation mission can offer a valuable starting point. Their relevance is already reflected as a key source for the project’s outcome indicators. / Need for results vs. need for sustainable reform: Donors want both results that can be directly attributable to the implementer and sustainable institutional reform. These do not always mean the same thing. For example, if IFES prioritised delivering results, they would focus on outputs they could deliver alone. But this would not build the ECP’s capacity and not have sustainable impact. SERP will need to continue striking a balance between these two needs and to ensure that the project has a credible plan for moving toward increased ECP “self-sufficiency”. / Relationship with ECP: As mentioned in section 1.3 above, while ECP is broadly satisfied with IFES working and outputs, several areas for improvement were pointed out during our meetings. IFES and the ECP could aim to be more strategic in the post-election phase of the project. It would be worthwhile for donors to join quarterly progress meetings with ECP to review progress and adjust the work plan accordingly so that the needs of the key beneficiary are properly responded to. While ECP ownership of plans is crucial, ultimately the programme needs to balance the need to be responsive to ECP priorities and short-term requests, against overarching electoral reform needs (as identified within the ECP Strategic Plan, SERP logframe and work plan) of benefit to Pakistani citizens.. / Relationship with UNDP/UNWOMEN and other projects: While it was encouraging to note that IFES and UNDP/UNWOMEN are working in a well-coordinated manner, it will be vital for them to continue to share information on their progress and to plan ahead together to avoid any overlap or confusion. All contributing donors, along with IFES and UNDP/UNWOMEN could hold joint quarterly progress reviews to ensure both programmes are working towards compatible objectives. / Underrepresentation of Women: The project design documents openly acknowledge the major challenges associated with the underrepresentation of women in all aspects of the electoral process – ranging from the gender bias in ECP staffing to the under-registration of women as voters to the low levels of participation of women on Election Day. While ECP has already demonstrated its awareness of this issue, the SERP project consistently makes efforts to draw attention to this imbalance and has been effective in particular in securing representation of women as trainers and in increasing the attention paid to women as part of ECP’s approach to voter education. Both attitudes and concrete obstacles to women’s engagement continue to pose a massive challenge to inclusive participation in Pakistan – above all in the form of women’s participation on Election Day.
1.6 Annual Outcome Assessment / The project’s outcomes focus on ECP performance during the General Elections anticipated for May/June 2013. For indicators 1 and 2 there is some limited (positive) reporting available from the National Democratic Institute (NDI) pre-election mission but otherwise none of these outcomes can feasibly be reported on before the General Elections. There is, however, a strong correlation between achievements at output level and progress toward achieving the project’s outcomes that gives a good indication that the project is on track in terms of outcomes. The evidence is particularly strong for indicator 1 and 3, while indicator 2 is more vulnerable to external influences – notably the volatile political environment: / Outcome Indicator 1: Number of international and domestic observer missions that report that the legal framework provides a sound basis for credible elections; / Key legislation is drafted and ready for approval. IFES have responded to the risk that the Unified Electoral Law not be passed before the upcoming General Elections by working with ECP to prepare a summary of priority legislative amendments that can be processed before that Election. Final findings will, however, depend on securing Parliamentary approval. / Outcome Indicator 2: Number of international observer and domestic observer missions, political parties and citizens reporting confidence in the capacity of the ECP / The capacity of ECP is being increased through training, updating of systems and procedures, support for internal organisation and improvements in IT infrastructure such as GIS. IFES has provided useful support to the ECP in handling a series of key processes including the recent re-validation of the electoral roll for Karachi which had threatened to undermine public confidence in the electoral rolls and in the ECP more broadly. But confidence in the ECP will depend not only on its technical abilities and preparedness but on the public’s perception of the ECP’s ability to hold credible elections. / Outcome Indicator 3: Percentage of registered voters participating in the elections is increased. / Maintenance of accurate electoral rolls; a comprehensive ECP Voter Education Plan and support for implementation; production of a voter’s handbook and sub-grants for civil society engagement in voter education; and increased transparency in ECP activity should all help to increase confidence in the electoral system as well as knowledge of election procedures, in turn leading to an increase in voter turnout. The recent IRI survey showed that 75% of respondents said they would vote. In by-elections 2012-13, the turnout has ranged between 25% and 47% as reported by FAFEN. / IFES currently references the EU Exploratory Mission report as a source for assessing progress toward achieving a legal framework that meets international standards at outcome level, as well as perceptions of ECP capacity to provide a sound basis for credible elections. As Exploratory Mission reports are not usually published, it would be helpful to identify an additional or alternative source if possible. / Recommendations: / Raise indicator 2.1.1: Number of IFES-supported objectives of the ECP’s Strategic Plan achieved to outcome level and adapt it to take into account partially- as well as fully-achieved objectives (see output 2.1). / Raise indicator 2.3.1: Number of parties, domestic observer groups and citizens with confidence in the electoral rolls to outcome level (see output 2.3). / Consider developing an additional outcome indicator that reflects the project’s longer-term capacity-building work with the ECP. / Reach out to Provincial Election Commissioners to ensure they are fully informed of, and involved in, the IFES programme and planned activities. / Establish quarterly donor-IFES-ECP meetings as a form of Project Steering Committee. / Work with the ECP to define and agree on work plans for the post-election phase that pay greater attention to long-term reform needs and sustainability. / Maintain emphasis on close coordination with UNDP/UNWOMEN and explore areas in which greater coordination could strengthen sustainability.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / SERP’s forecast for FY 2012-13 is £1.7 m (including 0.4m for ballot boxes). £1.39 m has already been disbursed and the programme activities are on track to spend the disbursements by the end of financial year. The remaining £0.31 m will be disbursed in February 2013 after the delivery of ballot boxes. / 2.2 Key cost drivers / The largest proportion of the costs is for local field staff (19% in overall budget, and 21% in first year’s spend from DFID funding) and consultants (11% in overall budget, and 4% in first year’s spend from DFID funding), with staffing and associated costs absorbing over 50% of the first year spend, all of which is consistent with a technical assistance programme with an extensive outreach and training component. . Funds for special events (9% in overall budget, and 4.5% in first year’s spend from DFID funding) and related commodity purchases (9% in overall budget, and 1% in first year’s spend from DFID funding) are also used for program activities including trainings (both delivering the training directly to recipients and developing training materials for use by stakeholders, across the ECP, and others such as election observers, political parties, media). The programme administration costs which include the management fee and overheads are charged at a fixed rate of 12%. A small amount (2.5% of the total budget) is to procure IT commodities. In October 2012, the programme was granted a cost-extension of £400,000 to procure ballot boxes for ECP. / 2.3 Is the project on-track against original timescale: Y / The programme is well on track against most activities for the reporting period and overall output ratings reflect that. In some areas such as internal reorganization of ECP and recruitment policy, no real progress was made. This is mainly because internal reforms are not a priority for ECP in the pre-elections period.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Increased DFID Emphasis on Institution- Building: Over the past year DFID has responded to the recognised need to tackle the root causes of poverty with an increasing emphasis on what Prime Minister David Cameron has referred to as: “the golden thread of conditions that enable open economies and open societies to thrive: the rule of law, the absence of conflict and corruption, and the presence of property rights and strong institutions.” [Wall Street Journal 1 November 2012]. The SERP project is fully in line with this response, placing the need for a stronger, more responsive Election Commission of Pakistan – a crucial democratic institution – at the centre of its contribution to development in Pakistan. / ICAI review of DFID support to UNDP on Elections: In April 2012, the Independent Commission for Aid Impact (ICAI), the organisation responsible for the scrutiny of UK aid, published a report on the UK’s support for elections through the United Nations Development Programme (UNDP). The review looks at the effectiveness of DFID funding for electoral support through UNDP, rather than UNDP’s own performance.[18] / The ICAI report concludes that DFID’s choice of UNDP as the primary channel for electoral assistance is credible and that its work through UNDP has contributed to the successful conduct of elections, but also that DFID should make efforts to seek alternative or additional delivery partners to complement its work with UNDP. Among the recommendations the report also makes are: / DFID should place greater emphasis on ensuring value for money in electoral assistance by encouraging more realistic budget processes and advocating appropriate electoral systems and technologies. / DFID should strengthen governance arrangements. They should separate political dialogue from technical oversight and make more use of third party monitoring. Risk management arrangements should be fully integrated into the design of assistance through UNDP. / DFID should ensure that electoral support is anchored in a strategy for democratic development. This should include how the election assistance relates to governance objectives beyond the time frame of that election. / This programme already adopts the approach recommended by ICAI. The selection of IFES as primary implementing partner reflected the working realities on the ground in Pakistan – and in particular IFES’ long-standing relationship with the Election Commission of Pakistan. DFID Pakistan works with IFES to ensure that its programming not only avoids any overlaps with UNDP’s work with the ECP but also seeks synergies and opportunities for collaboration. DFID also strongly encourages collaboration between its two main election-related projects – SERP and STAEP[19] – and with other political governance projects including NDI’s work with political parties and DRI’s advocacy work with civil society. Under this project, IFES continues to act as facilitator/secretariat for the Election Support Group, which meets monthly and actively promotes sharing of both plans and experiences. / 3.2 Where an evaluation is planned what progress has been made? / DFID plans to conduct a joint impact evaluation for its election portfolio following the General Elections anticipated for 2013. The evaluation will look at all the activities of SERP and STAEP and will evaluate how both projects contributed to, among other things, the overall turnout and public confidence in general elections. The results of the evaluation will be fed into subsequent reviews and, depending on timing, used to inform programme activity around local elections.
[18] http://icai.independent.gov.uk/2012/04/25/icai-evaluation-of-dfids-electoral-support-through-undp/
[19] Supporting Transparency, Accountability and Electoral Processes in Pakistan (STAEP) is a three-year project supporting the work of the main citizen election observer network in Pakistan - the Free and Fair Elections Network (FAFEN).

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / A number of risks associated with the project were identified at the inception stage. In this reporting period these risks have either not materialised or have been managed. Due to the inherent political nature of any election-related project, the dynamic political situation presents an ongoing challenge. Despite recent protests – which in part centred on the role of ECP – and a recent Supreme Court judgement on a number of electoral matters, preparation for elections still appear on track with no major disruption to ECP’s or the SERP project’s activities. / However, the threat of increasing tensions in the run-up to elections either through violence or civic disturbance will be a constant challenge that will be monitored closely. This could disrupt or delay the election timetable but may also strain IFES’ working relationship with ECP. Building and maintaining a broad consensus around adherence to the timetable will be necessary for timely and credible elections. / The major risk posed by calling of early elections now seems unlikely and it appears the election will be held as per schedule in May/June 2013. However violence or security issues in the run up to elections are still a possible threat, though increasingly less likely to be significant enough to cause a delay in elections. Similarly the working relationship among donors, implementing partners and ECP continues to improve and appears to be on a positive tangent, bringing dividends in terms of the achievement of various outputs.
Risk of funds not being used as intended / The programme has a low-medium risk of fraud and corruption. With reduced uncertainty on timing of elections, improved partnerships with ECP and UNDP and track record of first year, the residual risk of delivery has significantly been mitigated. / The accountable grant modality used for this project and the regular oversight it requires helps ensure that the risks of corruption are relatively low. IFES’ corporate policy relating to the procurement of goods and services is tailored upon the regulations of the United States Government (USG), and take into account international donor’s policies, rules, and regulations governing a specific grant agreement. IFES’ procurement principles conform to the parameters of the procurement guidelines as outlined in Blue Book Section D and HMG’s procurement policies. / IFES has delegated procurement actions under $5,000 USD (approximately £3,210) or the local currency equivalent (LCE) to field procurement officers within the implementing program team. All procurement actions over this amount are processed by headquarters in the US. / Consistent with the principles of Value for Money (VfM), IFES procurement activities adhere to the following principles: / 1. Full and open competition / 2. Fair and reasonable prices / 3. Fair and objective evaluation of offers / 4. Responsible suppliers / 5. Documentation / As per the standard accountable grant requirement, SERP has an annual external audit requirement. The external audit for first reporting period (calendar year 2012) will be made available in April 2013. This is an additional safeguard to check the risk of fraud and corruption. / CIDA conducted the pre-grant due diligence of IFES in November 2011, which confirmed that IFES has robust systems and in-house capacity to implement a multi-donors national scale electoral assistance programme in Pakistan. / In terms of project implementation decisions about appropriate spending, IFES has direct responsibility for all spending decisions and maintains strict policies about the more vulnerable areas of spending on their activities such as travel allowances, per diems, reimbursable event expenses and provision of accommodation for attendees that are in line with donor requirements. There have been some cases over the past year in which ECP internal policies have not been fully in line with IFES policies for implementation of similar activities. IFES has consistently sought donor approval for any exceptions and has demonstrated a good understanding of how to identify and avoid inappropriate expenses. / Climate and Environment Risk / Addressing climate and environment issues through the programme: The SERP project does not address climate change and environmental issues directly. / Risks to disruption of programme activities: Though there has been a recent history of flooding in Pakistan, it is not expected that this will present a risk as the elections should be held during the “dry” season. Other natural disasters cannot be discounted – it would be useful to have a clearer indication of how these will be managed in the event that they occur around election time. / Mitigation of environmental impact of programme activities: Most SERP project activities have low environmental impact associated with maintaining central office facilities, limited office supplies and coordination of events. Additional –but still low– impact is associated with maintaining the presence of trainers at provincial level and periodic staff field visits for participation in activities and for monitoring purposes. DFID management of the SERP programme has very low environmental impact associated with limited office supplies and periodic short field visits for monitoring purposes.

5. Value for Money (VfM)
There are differing approaches to assess the “value” of election-related projects. From a long-run approach it can be argued that elections may lead to greater democracy and stability thereby providing the space for economic growth and reduction in poverty levels. While attempts have been made to conduct economic appraisals of such projects, the evidence base is thin, relies on quantifying intangible benefits and rests on assumptions and data which cannot be readily applied from one situation to another. Furthermore, there is the question of attribution: to what extent can we reliably say a DFID-funded elections project has contributed to long-term inclusive economic growth? / From the outset, DFID approach to elections in Pakistan attempts to address the supply and demand side constraints particular to Pakistan. By addressing these constraints in a holistic manner and taking into account the work of other donors in this area, DFID seeks to maximise the value of its project’s outputs. In the case of SERP, DFID is working to strengthen the “supply-side” of the equation. Strengthening local capacity and sustaining that capacity can produce wider benefits by enhancing the ability of local institutions and civil-society networks to contribute to better governance processes/practices. / Within this context this VfM assessment will present a qualitative summary of the SERP project. It must be noted that DFID Pakistan’s support for elections not only addresses the “supply side” (i.e. institutional capacity and credibility), but also the “demand side” (i.e. through STAEP, which aims to strengthen civil society’s capacity to monitor electoral and governance processes; and Aawaz, which aims to increase the engagement of marginalised groups). Therefore the data which is produced will be unique and not necessarily comparable. Nevertheless, this will build and add to the existing evidence base. / While beyond the remit of this Annual Review, it is recommended that the Project Completion Review be designed to include the necessary tools and mechanisms to gauge the impact of the project – in particular qualitative assessments of “intangible benefits”, while also considering how appropriate it is to consider economic appraisals in this particular field. / 5.1 Performance on VfM measures / Economy / We consider an assessment of “economy” in terms of the inputs and costs associated with the project. / Selection of IFES was based on an independent Election Assessment that concluded it was best placed to support ECP. IFES was already working in situ with the ECP (since 2002) and was the only organisation that had been working with ECP since the 2008 election. Exploiting this existing relationship therefore lowered DFID-P’s transaction costs - e.g. IFES’ previous work with ECP on devising their Strategic Plan provided a foundation for the SERP programme. / The Voter Education component and associated design and provision of voter education materials have also produced significant multiplier effects: these materials have been used by other organisations, companies and government departments for voter education purposes at no extra cost to the programme. / Economy can also be considered in terms of whether DFID funds are “additional” or “substitutional” - i.e. whether DFID is displacing funds that could be provided locally or from other donors and therefore DFID’s resources could be used elsewhere. Under this criterion we cannot ignore the existence of UNDP/UNWOMEN’s elections project with its overlapping scope and activities. The questions that arise from this situation are: / whether the project’s objectives could be achieved solely by the UNDP/UNWOMEN project; and / whether economies of scale are lost by the two projects effectively “competing” with each other / In terms of the first question, at the start of the project implementation an active decision was made based on experience and evidence from the previous election that UNDP/UNWOMEN would not be able to achieve all of DFID Pakistan’s objectives and would not present value for money[20]. Furthermore, the absence of UNDP/UNWOMEN in electoral work in Pakistan since the 2008 election had the potential to raise transaction costs as they would be required to build new systems, processes and relationships with ECP. In terms of the second question, it is noted that IFES and UNDP/UNWOMEN have resolved to coordinate their respective agendas thereby reducing duplication of efforts. It is not immediately apparently that there are any significant cost-saving implications from this coordination (e.g. savings in bulk procurement etc.). / The question of “additionality” has specific relevance to Output 2 and the procurement of ballot boxes. In the absence of government or other donor funding this was identified as a specific need that would contribute to achieving DFID-P’s objectives within the SERP project. However, the procurement of ballot boxes is technically not a capacity issue but essentially a cost and planning issue. The review team recognizes that there was very little window for planning as the need emerged from a Supreme Court order to increase the number of polling station with elections coming closer, and as the ECP does not control their own budget. When viewed as such, it is natural to ask whether lack of funds is a genuine resource issue or an issue of willingness i.e. funds could have been sourced from the Federal Government given the right planning and articulation of why the ballot boxes were required. For the upcoming general elections the ECP has demanded from the Ministry of Finance a sum of Rs 5.9 billion and the approval is awaited. This expenditure is in addition to the operational cost for running normal business of the ECP. / Efficiency / Efficiency can be viewed as how well outputs are being achieved at the budgeted costs. In the narrow definition, we consider efficiency in terms of converting inputs (costs) to outputs. This definition by itself only indicates how well (or poorly) an indicator is being achieved and therefore other factors need to be taken into account to give a broader measure of “efficiency”. As costs were not disaggregated to activity level, the unit cost method is inappropriate. Therefore it is necessary to describe efficiency aspects in qualitative terms. / At the time of SERP design, delivering through UNDP was not assessed to deliver the best value for money compared to IFES (as set out in the Business Case). Since then, UNDP has begun delivering a programme of support to the ECP meaning that a major factor in determining the efficiency of SERP rests on the relationship between IFES and UNDP/UNWOMEN. If UNDP/UNWOMEN is doing the same activities as IFES (with comparable outputs/outcomes) then in efficiency terms DFID funds could be used elsewhere to address the wider issue of strengthening ECP capacity. As noted before, IFES and UNDP/UNWOMEN have resolved to coordinate their respective agendas thereby reducing duplication of efforts. In particular, the training component for polling staff has been divided geographically and there has been coordination over content for voter education handbooks and other training materials. / A donor/implementing partner coordination mechanism in the form of the Election Support Group (ESG), supported by project specific coordination mechanisms and meetings is also useful to identify and resolve potential conflicts and overlaps. As both IFES and UNDP/UNWOMEN have acknowledged, their leadership has sought to create a good working relationship creating the space for both teams to operate effectively. That is not to say this situation is ideal – an area in which this presents a problem is in IFES’ relationship with the ECP, which on the part of the ECP manifests itself in confusion over who does what in some areas. While IFES (and UNDP/UNWOMEN) attempt to communicate clearly with the ECP, repeated clarification of roles and the ECP calling on both parties to advise them on the same issue is not an efficient use of time. / Another dimension of efficiency in this project is the extent to which IFES performs functions that the ECP could reasonably be expected to do e.g. drafting legislation or direct provision of trainers/training. In the short-term this does not present a problem: limited capacity within the ECP has been the driving force of this project and the ECP has stated that IFES add value and quality through their activities with the ECP. Over the longer term, due thought will need to be given as to how capacity is expanded and sustained within the ECP so that IFES’ activities are increasingly being done by the ECP. / The project has benefited from the decision by three major donors – DFID, CIDA and the EU – to combine their efforts in a coordinated, jointly funded project with streamlined reporting in one format, against one logframe and according to one timetable; with all donor coordination meetings carried out with all three donors present; and with remarkable coherence in messages received from its donors by IFES. All this has made a significant contribution to the efficiency of the project in terms of the reduced project administration burden IFES has faced as a result. / Effectiveness / We describe effectiveness in terms of converting outputs to higher level outcomes. This is mainly assessed through beneficiary feedback, and judgements on whether key areas such as capacity and sustainability are being strengthened. / From the outset, the ECP was clear that IFES’ work was of value and importance to them and is contributing to ECP outputs and achievements. In specific areas such as training they also emphasised its contribution to raising the quality of their work. Nevertheless, a key theme in this measure is to what extent the presence of UNDP/UNWOMEN has affected IFES’ relationship with the ECP. In terms of advising the ECP coordination between IFES and UNDP seems crucial –as coordination issues could hamper progress towards the project’s outcomes. The senior management teams of both organisations have worked hard to coordinate activities. However, there was tacit acknowledgement that this does not necessarily extend to the lower levels which has implications for both teams to work effectively in the field. / As section 1.6 indicates, the project’s activities suggest that progress is being made to achieve the desired outcomes. However, a critical element of effectiveness is the concept of sustainability in reforms and capacity. Successes under this include reforms and implementation of systems that will be hard to reverse: / Legal Framework / Management of Electoral Rolls / Rules and Regulations relating to Electoral Finance / Voter Education – 17th October established as annual “National Voters Day” / There are questions around longer term sustainability, which are addressed under section 5.4 below. / In terms of effectiveness, DFID-CIDA-EU donor coordination has played a crucial role in terms of the project’s responsiveness to both opportunities and challenges faced in ensuring effectiveness in a fast-changing context and will be even more relevant as discussions into post-election plans and the sustainability of the project evolve. The flexibility that the project has to respond to environmental and political changes is supported by the excellent coordination mechanisms among the project donors and by the efforts that they made initially to ensure that they were all fully on board during the conceptualisation, design and initiation of the project. The involvement of the EU as a donor for both IFES and UNDP/UNWOMEN has also increased the pressure on both projects to coordinate effectively. / Recommendations: / IFES should continue to work with UNDP/UNWOMEN to ensure clearly defined lines of responsibility and coordination that not only avoid duplication or overlap but also look for synergies and opportunities to benefit from the comparative advantages of both organisations. / IFES should continue to invest in its relationship with ECP to increase clarity over its role and contributions. / IFES should continue to work with the ECP to promote a shift in key functions and leadership of initiatives from IFES to permanent ECP staff and to place greater emphasis on ECP capacity. / Project plans for the future – and in particular for the post-election period – should place greater emphasis on the sustainability of reforms. / 5.2 Commercial Improvement and Value for Money / The review team and project team are broadly satisfied with IFES’ approach. / Recommendation / IFES could look at ways for the financial information can be shared with ECP to increase the transparency and accountability to the beneficiary. / 5.3 Role of project partners / The project is implemented directly by IFES and no sub-grants have yet been approved. IFES commitment to the Economy component of VfM in particular is clear from its inclusion of VfM analysis in its quarterly reporting that demonstrates clearly it is meeting DFID requirements. / The initial project design included the expectation of some form of cost-share from ECP to cover training costs. This has not been forthcoming and at times the confusion around issues like logistics of training undermines the utility of such trainings. It may be helpful for IFES and its donors to clarify the levels of authority IFES can exercise over this type of decision and what mechanism they should set in motion if a decision requires donor input. / It was noted that these discussions also require more formal and regular meetings of donors with ECP where such issues should be discussed and then reflected in minutes and work plans so as to avoid any confusion at operational levels. / Recommendation / IFES and its donors should clarify the levels of authority IFES can exercise over decisions about allowable expenses, ECP cost-share contributions and other spending queries that emerge, and to define a mechanism they should set in motion if a decision requires donor input. / The project would benefit from greater donor engagement with the ECP to discuss emerging issues and seek formal recognition through minutes and work plans so as to avoid any confusion at operational levels. Additional regular discussion with UNDP/UNWOMEN would help to ensure that messages received by ECP are as clear as possible. / 5.4 Does the project still represent Value for Money : Yes / We believe in the pre-election period this project represents Value for Money. On a broader level a key consideration will be that of post-election planning, which will need to take account of longer-term sustainability issues and how ECP is incentivised to achieve them. While the ECP have expressed desire to lead the agenda, a lack of longer-term planning restricts the ability of the ECP to function effectively. This includes the ability to assess the level and type of resources required to hold elections and also what is required between elections such as research and training priorities – some of IFES’ activities should help to resolve these issues. / Recommendations / Aim to build ECP in-house capacity to perform functions in terms of drafting laws, rules and regulations, assessing training needs and holding training sessions. / Seek ways to move forward the recruitment of key staff e.g. for the Federal Elections Academy. / Look at options for achieving structural change through identifying a broad-based coalition for change and securing middle-management buy-in. / Look at how to assist the ECP in asserting its role in terms of enforcing codes of conduct, electoral fraud, complaints etc. Co-ordinate with UNDP/UNWOMEN in this process. / This is not an exhaustive list, but if there is not some identifiable movement away from IFES performing functions of the ECP, or a credible plan for the ECP to journey towards “self-sufficiency” then there may be a case to re-shape or scale back the project in the post-election period. / 5.5 If not, what action will you take? N/A
[20] Intervention Summary

6. Conditionality
6.1 Update on specific conditions - Not applicable

7. Conclusions and actions
Current Performance: Overall the review team was broadly satisfied with the performance and achievements of SERP over the past year. While not all indicators show strong progress, the team recognised that in a challenging and politically charged working environment IFES has demonstrated a strong work ethic and the flexibility to adapt to unexpected events, sound technical knowledge and overall positive management of the working relationship with the ECP and other organisations working on elections. Preparations for the elections are well underway, the ECP is in a much stronger position than it was even a year ago, and IFES has made significant contributions to that strengthening. / Over the coming 6 months it is expected that the focus will fall squarely on election preparations. IFES is well placed to contribute in the key areas of training of election officials (in particular temporary polling staff) and voter education, as well as to continue supporting ECP in pushing for priority legal and regulatory amendments and preparing for aspects of the process such as electoral dispute management. / In order to ensure that output scoring gives a more accurate reflection of project achievements in future, a series of specific changes to the logframe have been recommended that will ensure that some indicators (1.1-1.3, 2.1.1, 2.4.1, 3.1.1.) provide a more nuanced reflection of the achievements of the project, indicators are added to cover work not currently reflected (e.g. Codes of Conduct under output 1) and some indicators are raised to outcome level (2.1.1, 2.3.1, 3.2.1). / Priorities for the future: Offset against this broad satisfaction with current performance are the team’s concerns about the longer-term sustainability of the project. The past year has demonstrated that project plans are often undermined by the short-term priorities of the ECP. While many of these have in themselves been valuable initiatives, they have shifted focus away from the longer-term aspirations of the project. There are also some concerns that IFES is implementing tasks that would ordinarily fall under the responsibility of ECP staff members. / In this context the future success of the project will depend on defining and agreeing on post-election plans and priorities with the ECP that include an emphasis on in-house capacity and confidence, longer-term strategic planning, increased ECP staff involvement and matched financial commitments over time in areas such as training and promoting and nurturing initiative and innovation within the ECP. / Another concern is that the contributions of the project are at times stopped short by the failure to convert drafts into legislation, and also by the seeking of legal approval for regulations and codes of conduct that should fall within the remit of the ECP. While acknowledging that its influence is limited, IFES should nevertheless consider how to address this challenge as part of its programming. The issue of underrepresentation of women on the electoral rolls and as voters is another advocacy issue that should continue to be given high priority by IFES going forward. / Relationships and donor coordination: Finally, the review recognises the sensitivity of the working relationships associated with the project and recommends not only that IFES engage the ECP intensively in the development of its post-election work plan but also that IFES make efforts to share clear information about its remit as widely as possible within the ECP structures, including to Provincial level. The review recommends quarterly donor-IFES-ECP meetings, possibly in the form of a Project Steering Committee, as well as if possible a more formalised relationship between ECP and IFES and/or ECP and DFID with regard to this project. It also recommends regular donor-IFES-UNDP/UNWOMEN coordination meetings in order to ensure that all donors are fully informed about the coordination arrangements IFES and UNDP/UNWOMEN establish – efforts for which they are both commended. Finally it also recommends sustained coordination among donors funding related election support projects.

8. Review Process
The Review was conducted by Ms Helen Barnes (Governance Adviser, Bangladesh), Mr Ilyas Malek (Economic Adviser, Pakistan) and Mr Omar Mukhtar-Khan (Governance Adviser, Pakistan). Evidence was collected through a desk review of project documentation and relevant election-related analysis, followed by meetings with IFES, ECP (including PECs for Sindh, Balochistan and KPK), UNDP, CIDA, EU, AusAID, FAFEN, DRI, NDI and other election stakeholders.