Annual Review

Title: DFID-ESRC Joint Research Fund on Raising Learning Outcomes (RLO)
Programme Value £ (full life): £15m		Review Date: August 2018
Programme Code: 204324	Start Date: 10 Jan 2014	End Date: 30 March 2022

Summary of Programme Performance
Year	2014	2015	2016	2017	2018
Programme Score	A+	A+	A+	A	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204324/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204324/documents

TO NOTE: This Annual Review has been moved forward from November 2018 to August 2018 to better align with ESRC’s Annual Reporting structure. Looking ahead, the annual review will now be completed annually in July/August. As a result, the current reporting period has been reduced from 12 months to 8 months and therefore consideration for this should be made.

A. Summary and Overview (1-2 pages)

Description of programme: Raising Learning Outcomes (RLO)

- A £20 million joint programme between DFID and ESRC to fund a portfolio of research on critical policy areas that are currently constraining education systems in developing countries, including translating resources into improved education outcomes. DFID is contributing £15 million and ESRC is adding £5 million.
- The aim of the research is to provide policymakers and practitioners with concrete recommendations on how to improve learning outcomes and an understanding of how these will translate to their specific context and institutions.
- To date, 31 grants have been awarded by ESRC for the RLO programme, through three annual research calls, each with a core thematic focus.
- Call 1 (2014): Effective Teaching, 11 awards. The four small scale/pilot projects were completed in 2016. The five medium grants are active and on schedule to complete within the next year. The one large grant is active and on schedule to complete in March 2019. One grant was terminated.
- Call 1 scale up: Two of the Call 1 grant holders applied successfully for further funding; these grants are on track.
- Call 2 (2016): Challenging Contexts, 8 awards. All active and on schedule.
- Call 3 (2017): Accountability, 10 awards commissioned and now active.
- Call 4 (2018): Follow on Fund for existing grant holders. Funding not allocated through the three main calls is being made available to grant holders for additional activities. Initial awards through this call are due to be made by early 2019.
DFID-ESRC are also funding two ambitious additional functions as part of the RLO programme:
- The Impact Initiative for International Research which is increasing the uptake and impact of funded research from these programmes. It is co-funded with the ESRC-DFID Joint Fund for Poverty Alleviation Research and is a collaboration between the Institute of Development Studies (IDS) and the University of Cambridge’s Research for Equitable Access and Learning (REAL) Centre,
- The Programme Research Lead (PRL) is maximising the scientific value of the programme by identifying, evidencing and promoting opportunities for research collaboration and synergy across the portfolio of projects.
- The programme is focused on efforts to raise learning outcomes for all, including attention to issues relating to gender and disability. The research is being carried out in low and middle income countries but there are no geographical constraints.
- ESRC manage the programme and lead on communication with grant holders. DFID work very closely with ESRC, especially on strategic issues. This partnership produces well-managed rigorous research. This year, ESRC have appointed a new programme manager for RLO and the Impact Initiative, Emily Hancock. Laura Savage continues to be the SRO for DFID.

Summary supporting narrative for the overall score in this review (1/2 page)

The RLO programme is on track, successfully commissioning policy-relevant, rigorous research. This research has exceeded expectations in terms of being multidisciplinary and using mixed methods, with links to Southern institutions and Southern research leads as well as non-academic stakeholders as partners. Both the PRL and the Impact Initiative passed their break point as they are adding value to the programme. Most grant holders are engaging with these two additional functions, which support the grants with identifying cross-programme academic themes and with achieving greater policy impact. In interviews conducted for this Annual Review, and regular DFID monitoring, grant holders report positive feedback on the programme. Grant holders are beginning to share findings and methodological innovations with each other, which contributes towards DFID’s objective of encouraging a ‘cohort’ of academics producing rigorous, policy-relevant research on how to improve learning outcomes at-scale. Strong examples of impact and policy influence are also starting to emerge, though most research is still ongoing. Due to the success of the programme, both the ESRC and DFID are pursuing the extension of the partnership and programme.

Recommendations for the year ahead (1/2 page)

Evaluation: ESRC and DFID should (i) Draw lessons from ESRC’s evaluation of impact and support functions across ESRC-supported programmes in early 2019 to improve the Impact Initiative and Programme Research Lead functions on the RLO programme. (ii) Design the programme-wide evaluation by June 2019 with a view to commissioning a team to draw some initial insights early enough to inform early stages of Phase II.

Research: (i) ESRC and DFID should finalise the design of the internal programme funding call, ensuring underspend in the programme is distributed in support of programme goals. The first round of decisions should be achieved before the January 2019 grant holder workshop. (ii) Funders should review the extent of explicit gender analysis within grants and work with the Impact Initiative and PRL to identify ways to encourage more.

Cross-cutting functions: ESRC and DFID should continue to closely monitor work of the Impact Initiative and Programme Research Lead, to ensure recommendations from their mid-point reviews are followed through. Logistics for the January 2019 grant holder conference should be completed before November 2018 to support high participation rates, particularly from Southern researchers.

Impact: The Impact Initiative have started to collect impact case stories from grant holders. ESRC and DFID should support this effort through facilitating linkages with other DFID-funded research programmes (including RISE – the Research on Improving Systems of Education programme) for a ‘impact story writing event’ in March 2019.

## B: DETAILED OUTPUT SCORING

Output Title	A portfolio of high quality, policy-relevant research on what works to deliver learning outcomes through effective, equitable education systems in low income countries is delivered.
Output number per LF		1	Output Score	A
Impact weighting (%):		40 %	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number and quality profile of research grants awarded funding through independent assessment of scientific quality and policy relevance.	March 2021: At least 27 research grants awarded which meet scheme scientific quality and policy relevance requirements	Milestone exceeded. 31 research grants have been awarded to date.
1.2 Number of research grants operating in line with contract terms and conditions, measured by compliance with grant annual progress reporting and ResearchFish validation requirements	March 2019: At least 24 of 27 (90%) research grants will have submitted annual progress reports and completed ResearchFish validation as required.	On track. 16 out of 16 (100%) live research grants submitted an annual progress report. 20 out of 20 (100%) live and completed grants submitted their ResearchFish validation as required.
1.3 Number of research grants completed to approved timescales, measured by end of award reports received.	March 2020: At least 15 of 16 (90%) research grants expected to have submitted end of award reports in approved timescales	On track. 4 out of 4 (100%) of completed research grants have submitted end of award reports.
1.4 Number of scheme-funded journal articles, books, or book chapters reported as published or accepted for publication.	March 2020: At least 73 journal articles, books or book chapters reported by RLO research grants	On track. 34 journal articles, books or book chapters reported by March 2018.

Provide supporting narrative for the score

  1. In addition to the 21 research grants that were reported previously, this year ten Call 3 grants were awarded, making 31 in total awarded to date. Grants were awarded in line with ESRC’s rigorous peer review and assessment processes, which ensure only funding of the highest quality research is commissioned. DFID and ESRC work closely together to nominate expert panel members to ensure a focus on methodological rigour, thematic fit and adherence to RLO requirements (research on ‘at-scale’ interventions, policy relevance and equity). Due to the Hardman grant (Call 1) being terminated[1] (this leaves 30 grants in total.
    [1] Hardman grant terminated due to the retirement of the Principal Investigator – see 16/17 Annual Report for further details.

  1. All live grants completed their progress report submissions as required (6 Call 1; 8 Call 2; 2 Call 1 Follow on Fund). The four Call 1 completed grants have submitted the end of award reporting within approved timescales. ESRC monitor grants through a mechanism called ‘ResearchFish’- a platform for funders to receive comprehensive reporting from grant holders on activities and progress towards impact. In short, the projects are on track, and managed well.

  1. ESRC and DFID are satisfied that this 30-grant cohort constitutes the portfolio of quality, policy-relevant research that we aimed to generate through this programme. The third call was the final open research call under this programme. The three calls were organised around a central framework for understanding education systems: elements, context and dynamics. Each challenged the academic community to ask new questions (for example of education in urban slums) and to use innovative mixed methods and country partnerships. Annual grant holder meetings are proving useful fora to identify commonalities and strengthen policy implications.

  1. To date 34 journal articles, books or book chapters have been reported by the RLO grant holders as published or accepted for publication. Eleven of these are new outputs reported this year, comprising of 5 journal articles, 1 edited book and 5 book chapters. To note, grant holders also reported additional publications including 3 policy briefing reports, 1 technical report, 2 conference abstracts and 1 thesis, which are not counted in the above figures. Outputs to date are relatively high, benchmarked with other similar programmes across RED, for this stage in the programme.
Lessons and Recommendations

Recommendation: ESRC and DFID should finalise the design of the internal programme funding call, ensuring underspend in the programme is distributed in support of programme goals. The first round of decisions should be achieved before the January 2019 grant holder workshop. DFID and ESRC have discussed how to spend the remaining £2 million, which was not used by calls 1-3. This would not be sufficient funding to run a fourth call of similar size, and so funders have agreed to run an internal programme funding call. This will offer current grant holders an opportunity to bid for funding to improve current grants, including extension of their research (if new directions have been identified), activities to improve impact, capacity-building of junior and Southern researchers, and cross-grant collaboration on publications. The call will be open regularly for 6 month periods every year (with regular assessments by an expert panel)[2] for the next 3 years, with the first grants awarded in 2019. Discussions to inform a potential future RLO programme are ongoing and will feed into any other potential use of remaining unallocated funds.
[2] As per review panels for previous calls, this expert panel will consist of respected academics, policy makers and practitioners who work to improve student learning outcomes in developing countries.

Recommendation: ESRC and DFID should (i) Draw lessons from ESRC’s evaluation of impact and support functions across ESRC-supported programmes in early 2019 to improve the Impact Initiative and Programme Research Lead functions on the RLO programme. (ii) Design the programme-wide evaluation by June 2019 with a view to commissioning a team to draw some initial insights early enough to inform early stages of Phase II.

Lesson: DFID is currently undertaking a review of its Open Access Policy, using RLO as a case study. Feedback will be used to inform how to support grant holders to ensure their research is Open Access. Guidance to applicants in recent years encourages the costs of open access to be included in research proposals. There have been no requests for open access funding on the RLO programme in the reporting year.

Output Title	Research funded through the programme draws on diverse disciplines and methodologies, appropriately addresses core cross-cutting issues, and actively involves non-academic stakeholders.
Output number per LF		2	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of research grants which involve more than one academic discipline, as defined by RCUK	March 2021: At least 14 of 27 (50%) research grants are classified to more than one academic discipline at proposal stage.	Milestone exceeded. 19 of the 30 (63%) contracted grants reported more than one discipline at the proposal stage.
2.2 Number of research grants that include a mixture of quantitative and qualitative methodological research designs and/or methods.	March 2021: At least 14 of 27 (50%) research grants are classified as mixing quantitative and qualitative approaches at proposal stage.	Milestone exceeded 23 of the 30 (77%) contracted grants are classified as mixing quantitative and qualitative approaches at proposal stage.
2.3 Number of research grants that report undertaking gender analysis or disaggregating by gender or other structural inequalities	March 2019: At least 17 of 24 (70%) research grants reporting to date report they will undertake gender analysis or disaggregate data by gender or other structural inequalities.	Milestone exceeded. 14 of the 16 (87.5%) live grants required to submit a progress report reported the incorporation of gender analysis.
2.4: Number of research grants involving non-academic organisations as co-Is, project partners or advisory board members.	March 2021: At least 23 of 27 (85%) research grants include non-academic stakeholders as co-Is, project partners or advisory board members in their proposals.	Milestone exceeded. 26 of the 30 (87%) contracted grants include non-academic stakeholders as Co-Is, project partners or advisory board members.

Briefly describe the output and provide supporting narrative for the score

2.1 Of the 30 awarded and completed grants, 19 (63%) are classified to more than one academic discipline at the proposal stage and of the 16 live grants proving progress reports this year, 12 (75%) indicated their projects were multidisciplinary, reaffirming that this milestone has been exceeded.
Discipline	No. of times Primary Discipline	No. of times Additional Discipline	Total
Area and Development Studies	6	4	10
Economics	5	1	6
Education	14	12	26
Development Studies	2	0	2
Linguistics	1	1	2
Psychology	2	1	3
Management and Business Studies	0	1	1

An interesting example of how different academic disciplines are working together is Pauline Rose’s grant (Call 1) which looks into the learning outcomes for children facing multiple disadvantages in both India and Pakistan. The team is from various disciplinary backgrounds, including Economics, Psychology, Education and Sociology. Converging these different perspectives through regular meetings enables a more comprehensive analysis of the data. Common themes have been identified and used to shape strategies to support children from disadvantaged backgrounds. Similarly, publications have been approached in this way too, in order to address research questions and approaches that will engage within and across disciplines.

2.2 Of the 16 live grants required to submit progress reports, 10 (62.5%) stated that their research grant includes a mixture of quantitative and qualitative research methods, reaffirming that this milestone has been exceeded.
A good example of a research grant which includes a mixture of quantitative and qualitative research methods is Vanessa Kind’s grant (Call 1) which considers how pedagogy for STEM subjects in Ethiopia can be transformed from using one-way lecturing and closed teacher questions, to dialogical discourse and argumentation. The data collected was a mixture of quantitative examination results and conceptual knowledge tests, alongside qualitative interviews and lesson videos. By using varied forms of data collection, the comparison helped determine the impact of this intervention. The research thus far has revealed a gap between the intended curriculum for physics learning and the actual curriculum attained by teacher candidates in Ethiopian teacher education for primary schools. This outcome has subsequently generated a wide network of institutions and individuals in Ethiopia who want to improve the overall quality of STEM teaching.

2.3 Although 14 out of 16 grant holders reported that their projects incorporated gender analysis, only 5 out of 16 (31.25%) grant holders reported that they were undertaking explicit gender analysis. Review of proposal summaries of the Call 3 grants indicates that at least 5 of the 10 (50%) projects funded will undertake gender analysis or disaggregate data by gender or other structural inequalities.

Ianthi Maria Tsimpli’s grant (Call 2) on multilingual education in India is a good example of how gender is considered and analysed. Gender is taken as an independent variable that is included in the quantitative analysis of numeracy, literacy and cognition, as well as the language history and geographical localities. This perspective enables gender inequalities to be visible beyond the structural inequalities arising from children living in either urban slums or remote rural areas.

Lessons and recommendations

Lesson: ESRC and DFID completed a thorough mid-term review of the PRL in April 2018. This concluded that the PRL does play a valuable role across the programme, and that it should continue beyond its midpoint review. However the PRL team were given clear recommendations to complete (and in some cases discontinue) a range of specified actions, as well as be more creative, reflective and ambitious, in order to fully meet the objectives set out in their Terms of Reference.

Recommendation: ESRC and DFID should continue to closely monitor the Programme Research Lead (PRL), to support the effective identification and communication of cross cutting themes. DFID should play a particular role in ensuring that the PRL book consolidating findings from across the grants speaks to issues of policy relevance.

Recommendation: In order to incentivise explicit gender analysis, DFID and ESRC should consider how to use the Programme Research Lead function or next grant holders workshop to share best practice and tools on gender analysis.

Output Title	Programme funding is accessible to Southern researchers, and supports individual and institutional capacity to design, conduct and disseminate high quality social science research on learning outcomes and education systems.
Output number per LF		3	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1: Proportion of proposals and number of research awards funded which include PIs or Co-Is based at Southern Institutions.	March 2021: At least 40% of proposals and 12 of 27 (45%) research grants awarded involve Southern PIs and Co-Is.	Milestone exceeded. 56% of proposals and 16 of 30 (53%) research grants awarded involve Southern PIs or Co-Is
3.2: Proportion of research funding awarded that is allocated to Southern institutions	March 2021: At least 35% of research funding awarded is allocated to Southern institutions.	Milestone exceeded. 41% of funding awarded is going to Southern institutions.
3.3: Number of grants reporting undertaking capacity building activities benefiting Southern researchers, by type of activity.	March 2019: At least 5 of 17 (30%) research grants reporting to date report undertaking capacity building activities benefiting Southern researchers.	Milestone exceeded. 17 of the 20 live and completed grants (85%) reported capacity building activities benefitting Southern researchers.

3.1 The proportion of proposals with either a Southern Principal or Co-investigator has increased. In total, 16 of the 30 RLO research grants (53%) involve Southern principal investigators and/or co-investigators.
		All proposals
		Southern PIs	Southern PIs/Co-Is
Call 1 (n=89)	No.	25	40
	Percentage	28%	45%
Call 2 (n=53)	No.	17	33
	Percentage	32%	62%
Follow on Fund (n=4)	No	0	2
	Percentage	0%	50%
Call 3 (n = 63)	No.	26	42
	Percentage	41%	67%
RLO programme total (n=209)	Percentage	32.54%	55.98%

3.2 Of the £14,280,721.44 funding awarded, a total of £5,867,086.49 (41.1%) has been allocated to Southern institutions. One grant holder commented that

‘It is really brilliant that we can allocate up to 50% of our grant to Southern partners and meet their costs, otherwise they would not be able to take part in the research…..but ESRC could do more in making it more explicit that Southern partners should be involved in the research programme: not only leading academics but also wider stakeholders linked to the programme. For example, community facilitator, peer tutors…. This helps with both engagement and training’.

Another grant holder suggested offering translators as a way of being more inclusive to non-Anglophone Southern partners. Another described the current disadvantage of being a non UK grant holder, in terms of being harder to feel a sense of cohort and learn from other grants. The PRL-supported conferences in Uganda and South Africa in September will go some way to mitigating this in the sub-Saharan region.

3.3 17 of the 20 live and completed grants (85%) reported capacity building activities benefitting Southern researchers. Of the 16 live grants to submit annual progress reports, 15 of 16 (94%) reported undertaking capacity building activities benefitting Southern researchers. The activities reported included geographical information systems training, and participating in workshops that highlight the importance of impact evaluations , which helps to develop the skills needed to understand randomised evaluations as well as other dissemination activities including co-authorship of publications.
- Extensive training in working with human subjects,
  A specific example of a project which has benefitted Southern Researchers is Tristan McCowan’s grant (Call 1) where local capacity-building has been built into their research design from the start by recruiting emerging researchers in Kenya, Ghana and Botswana to work as their in-country Research Officers. The Research Officers are thus gaining substantial skills throughout the project, as they are responsible for conducting most of the data collection during the quantitative phase of the study and are also assisting the in-country Team Leads with data collection and analysis during the qualitative component. In order to support their development throughout the project, training workshops have been organised, one at the beginning of each of three main phases of the study. Although the in-country Team Leads are academics with extensive research experience, none has worked previously on a predominantly quantitative study, so the project is providing them with valuable training in quantitative research design and data collection.

- Conducting interviews,
- Completing summary sheets and field notes.

Capacity building activities are self-reported by grant holders and vary in type and what they achieve. Understanding which activities are the most impactful in terms of capacity building could be a useful dimension of the RLO evaluation.

3.4 Ongoing efforts to support the participation and prominence of Southern researchers are promising, and will be reported on fully in the next Annual Review. Southern researchers were supported to attend the January 2017 grant holders workshop, and this is an even more explicit focus for January 2018. The PRL are working with research teams to produce articles and book chapters and are particularly encouraging junior researchers as well as Southern researchers to contribute. The upcoming RLO panel at the What Works for Africa’s Poorest Children conference (Uganda, September 2018) and RLO symposium in South Africa will provide opportunities for Southern researchers, especially from sub-Saharan Africa, to present and engage with the programme. The latter is an unusual event, specifically designed to forge connections between regionally based academics to encourage sharing of findings and methods, building a community of practice

Lessons and recommendations

1. Lesson: Last year’s Annual Review recommended better link-up between the RLO grants and GCRF/DFID events. Education was not a focus of any of the GCRF events in Kenya and Delhi, this year (an indication of the wider lack of focus on/resources to education research, and thus value of this programme). DFID’s East Africa Research Hub team have been notified of the PRL and ESRC-DFID Southern Researchers involvement at the What Works for Africa’s Poorest Children conference in Uganda in September.

2. Recommendation: DFID and ESRC should encourage The Impact Initiative and PRL to plan the 2019 grant holder conference in advance as possible to support as many Southern researchers to attend as possible and ensure there are sessions that will be particularly relevant to them.

Output Title	Research findings are accessibly communicated and synthesised for broad audiences including potential policy and practice research users with an interest in raising learning outcomes in education systems in low income countries
Output number per LF		4	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1: Number of conference/working papers produced and workshops/ lectures conducted by scheme-funded research grants.	March 2018: At least 19 conference/ working papers or seminar/lectures reported.	Met. 19 conference abstracts and working papers have been reported by grant holders to date.
4.2: Number of outputs targeting non-academic audiences reported by research grants, by type.	March 2019: At least 20 non-academic outputs reported	Milestone exceeded. 82 non-academic outputs have been reported. The definition of ‘outputs targeting non-academic audiences’ will be tightened next year to include hard outputs only. Blogs and press releases will be reported but not counted towards this milestone.
4.3: Number of outputs produced at programme level which make learning from more than one RLO grant accessible to potential research users, by type	March 2018: At least 3 outputs produced at programme level which combine learning from more than one RLO grant for research user audiences.	Milestone met. 7 programme level outputs have been produced that make learning from more than one RLO grant accessible to potential users.
4.4: Number of research grants taking part in events and activities organised at a programme level which are designed to facilitate knowledge exchange with potential research users	March 2019: Researchers from at least 11 RLO grants have taken part in programme-level activities designed to facilitate knowledge exchange opportunities with potential research users.	Milestone exceeded. 24 RLO grants have taken part in programme-level activities designed to facilitate knowledge exchange opportunities with potential researcher users.

Provide supporting narrative for the score

4.1 A satisfactory number of grant holders are already presenting findings at the appropriate conferences. To date 16 conference abstracts and 3 working papers have been reported by grant holders. This includes five grant holders who presented papers this year at the major international education conference, Comparative and International Education Society (CIES), as part of a well-received PRL-organised RLO session. The 30 grant holders reported a further 87 talks or presentations this year, 118 instances of participating in a workshop, and 31 instances of participating in a formal working group or expert panel.
4.2 With many Call 1 grants now mature or nearing end, and Call 2 grants established, the variety of non-academic outputs is increasing. Across the 30 grants this year, 33 were referenced in a press release or response to media enquiry, 5 were represented in an online or magazine publication, 33 included on a website or blog, 3 in a technical report, and 8 on a TV/radio/podcast broadcast.
.
Ulrike Zeshan’s grant (Call 1) included a project launch event for "Peer to Peer Deaf Multiliteracies" in New Delhi, India. The event included presentations and a screening of the pilot project's documentary movie "Deaf literacy from the grassroots", a short documentary film about the research project. The film shows both the research process, with its main actors such as the research team on the ground and the learners, and the research outcomes, with interviews of the lead academics. The film was produced by a team of deaf filmmakers. The event was attended by 150 participants from a mix of different backgrounds, from different parts of India as well as Uganda, Ghana, and the UK.

Nicola Ansell’s team (Call 2) organised village meetings (“pitsos”) in their two case study villages in rural Lesotho. At these meetings they presented the research findings, sought the perspectives of community members, and discussed messages for policy makers.

4.3 The Impact Initiative is providing a sound platform for improving the impact of these grants, through training for grant holders in ‘pitching’ (to Ministers, or the press) and producing impact stories that pull together findings from different grants. As of July 2018 the Impact Initiative have produced 8 products that make learning from more than one RLO grant accessible to potential users; 3 in the last reporting year and 5 previously. The 3 new outputs reported this year are:

ESRC-DFID research for policy and practice: Quality teaching
This collection of ESRC-DFID-funded research explores the process of teaching, and the factors that make good quality teaching. Drawing on evidence across three continents, this collection highlights: innovative teacher training and recruitment approaches that are improving learning outcomes in Honduras; a classroom observation tool that has improved teaching in Uganda; how Professional Learning Communities can improve teaching quality in China; and the way that transforming teaching quality through active learning is having an impact in Ethiopia.

ESRC-DFID research for policy and practice: disability and education
This is a collection of findings from four RLO projects: Ulrike Zeshan (Call 1); Paul Lynch (Call 1); Parul Bakhsh (Call 1); and Pauline Rose (Call 1). Together they provide new evidence of what governments should consider to ensure children with disabilities benefit from quality education without discrimination or exclusion. As a group of case studies this research contains excellent, globally relevant and contextually grounded evidence of how the education sector can plan and design policies with a lasting impact for children with disabilities.

Putting children first – event, booklet, blogs
The above booklet was prepared for the international conference “Putting Children first: Identifying solutions and taking actions to tackle poverty and inequality in Africa”, which took place in Addis Ababa, Ethiopia in October 2017. The booklet highlights research evidence on children and young people in Africa both from Joint Fund for Poverty Alleviation Research and 10 RLO grants, covering 9 African countries.

4.4 Grant holders value the additional support provided by the Impact Initiative and PRL. 15 grant holders have been represented in Impact Initiative organised events, at which there were opportunities to engage with potential research users. One grant holder stated that she was ‘impressed with the initiative of the programme to increase the impact in this way’; others have commented on the invaluable learning and feedback on how to make their work relevant to a wide audience. Such events include:

Global Disability Summit Workshop in Cambridge in April 2018. This Impact Initiative-hosted workshop provided the opportunity for researchers to engage with donors and NGOs to inform the framing of the Inclusive Education Initiative that was announced by DFID’s Secretary of State at the 2018 Global Disability Summit. Their collaboration at the workshop also resulted in the development of the Statement of Action on Inclusive Education which emphasised the importance of better evidence and data to inform policy and practice. The Statement in turn influenced this focus in the Summit’s Charter for Change and was signed by over 30 international organisations including DFID.

The Comparative International Education Society (CIES) conference – This is the major international education conference annually, and attracts a wide academic and policy audience. The PRL organised a double-session involving five grant holders. The lead up to the conference was particularly useful, involving three conference calls on which the researchers identified interesting findings that cut across their different research projects. This led to an innovative presentation technique in which the grant holders plus the DFID SRO engaged in ‘compered conversation’ with the CIES audience, responding to carefully constructed questions on cross-cutting themes. Feedback from the audience was that this was a welcome alternative to presentations, but the main gain of the session was the engagement with the RLO core themes by this sub-set of grant holders.

“Putting Children First: Identifying Solution and Taking Action to Tackle Poverty and Inequality in Africa”: A three-day international conference which took place in Addis Ababa, Ethiopia in October 2017. Two RLO grant holders (Paul Lynch and Pauline Rose) attended. The conference engaged policy makers, practitioners and researchers in identifying solutions for fighting child poverty and inequality in Africa, and aimed to inspire action towards change. The conference offered a platform for bridging divides across sectors.

Day 2 of the ESRC-DFID RLO Grantholders Workshop 2018: This 2 day workshop was organised by the Impact initiative and PRL. Delegates representing 22 grants attended the event. Discussions were facilitated on the challenges involved in effective research communication; and by providing practical support sessions on the best strategies for engaging non-academic audiences and identifying the needs and priorities of (potential) non-academic users of the ESRC-DFID research with respect to equity and inclusivity.

Lessons identified this year, and recommendations for the year ahead linked to this output

This year DFID and ESRC carried out very thorough Mid-Point Reviews for both the PRL and Impact Initiative. Both were found to be valuable to the outcomes of the programme, but were given significant steer by DFID and ESRC to ensure they are as effective as possible for the remainder of the contract.

PRL Mid-Point Review: Feedback was collated from grant holders, DFID and ESRC. This was discussed along with a report from PRL themselves, which made up the midpoint review in March 2018. It was decided the contract should continue until the end date of March 2019, on condition the PRL took action on recommendations. This included continuing their work to build a feeling of ‘cohort’ among grant holders. For example the PRL had organised a successful grant holder workshop in February 2018, CIES panel in March 2018 and looking ahead to a RLO South Africa symposium, BAICE conference and conference in Kampala, all in September. The mid-point review also praised the work on methods and innovations, such as the planned SAGE special issue that will draw out innovative methods used by grant holders. The online methods repository for grant holders is found useful by grant holders, albeit at an early stage. However, clear recommendations were given to stop activities that did not speak to the outcomes of the programme, for example a Seminar Series which was not successfully promoting communication or synthesis of findings. DFID and ESRC are holding monthly calls with the PRL to check that activities are sufficiently ambitious and on track. Funders concluded that the PRL needed to be more ambitious in their work on identifying synergies across grants for PRL publication, and publishing to increase the conceptual contribution of the programme. Recent feedback from a grant holder described the PRL as ‘a good initiative, which is imaginative and provides fantastic opportunities which promote equal relationships with Southern partners’.

The Impact Initiative midpoint review: An independent Mid Term Review of the Impact Initiative was commissioned by DFID and ESRC in 2017. The report found that the Impact Initiative needed to be more demand driven than supply driven and respond to opportunistic policy windows. It needed a clearer strategy, better communication with PRL and more momentum especially with impact stories. Since the findings of the review, the Impact Initiative’s workplan has been revamped; they are making the most of windows of opportunity; there is more momentum with products and better communication with the PRL. Reporting by the Initiative following the midterm review has demonstrated the significant positive impact of the changes made through the MTR process. Although the MTR is complete, ESRC and DFID will continue to promote, support and expect a learning-focused and adaptive response by the Initiative.

Recommendations:

The Impact Initiative have started to collect impact case stories from grant holders. ESRC and DFID should support this effort through facilitating linkages with other DFID-funded research programmes (including RISE – the Research on Improving Systems of Education programme) for a ‘impact story writing event’ in March 2019.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

Below is the Theory of Change from the Business Case. A more detailed theory of change has been developed by ESRC and DFID and is used in internal monitoring of the programme, particularly when updating logframe indicators.

There have been no major changes to the Theory of Change this year and as outlined above outputs are either being met or largely succeeded. Outcomes and impact will be discussed below.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Now all grants have been commissioned, with some starting to end this year, more attention will be placed on ensuring the outputs lead to expected outcomes and impacts.

The three main programme outcomes, as stated in the current Logframe are:
1. A community of practice will be established and supported to produce high-quality, policy-relevant evidence on how learning outcomes can be raised within education systems in low income countries.
2. Evidence generated through the programme will add to and inform the body of research knowledge relevant to how education systems can raise learning outcomes in developing countries.
3. Evidence generated through the programme will contribute to debates amongst policymakers and practitioners on education systems and how they can deliver learning at scale.

Outcome 1: One grant holder described the programme as ‘flexible, rigorous and speaks to policy’. The programme has provided opportunities above and beyond a ‘traditional’ grant-making research programme in which academics apply for a grant and, if successful, run their project and report back on their funding. RLO offers additional opportunities to network, to engage with a core conceptual framework around education systems, to share learning about research challenges, approaches and tools, as well as to publish and co-publish with other grant holders. As discussed earlier, how the community of practice can be strengthened globally will be a focus going forward.

Outcome 2: Identifying and synthesising themes and placing this within the wider body of research is a priority for the PRL but this function will need to be closely monitored to ensure it is on track. The CIES panel in 2018 was a positive example of grant holders coming together to present on common themes. Currently only 12% of outputs are reported as cited. We expect programme outputs, and citation of these outputs, to increase exponentially as the programme progresses.

Outcome 3: Currently 26% of outputs are reported as cited in non-academic publications. The workshop hosted by the Impact Initiative ahead of the Global Disability summit in July 2018 is a clear example of starting on the right track for Outcome 3. This workshop, which built on a thread of RLO research identified across 5 grants, led to an evidenced based Statement of Action on Inclusive Education, being signed by 31 donor agencies, international NGOs, research organisations and global education networks. This was then shared with 700 global policy makers and practitioners at the event. The Impact Initiative’s contract will be extended to March 2020 to provide targeted support to promote the uptake of research through mapping pathways to impact and engaging policy and programme makers.

The 2018 DFID Education Policy; Get Children Learning and the 2018 World Development Report, Learning to Realise Education’s Promise, both call for the continued need to be producing rigorous research to tackle the global learning crisis. Therefore ‘what works to raise learning outcomes?’ continues to be a question relevant to the current political climate and global education agenda. For example, the recent collection of ESRC-DFID-funded research exploring the process of teaching, and the factors that make good quality teaching, is an input to the DFID Education Policy Team as they work up a delivery plan for the policy promise to increase focus on improved teaching.

Impact Case Studies

## LOCAL LANGUAGE EDUCATION IMPROVES LITERACY IN UGANDA
In Northern Uganda where 80% of children aged 7-8 years are unable to read, teaching and provision of educational resources in local languages has greatly improved learning in rural, under-resourced classrooms. A Randomized Control Trial by The University of Illinois in collaboration with Ugandan private enterprise partner, Mango Tree, showed that, with just one year of engagement with the programme, pupils continued to benefit from learning gains three years later − amongst the largest ever gains achieved for randomised education interventions. The research guided literacy initiatives and teacher training programmes in Uganda via the DFID-funded education programme Strengthening Education Systems for Improved Learning (SESIL). Study findings also led to the inclusion of a local language development component in a USAID White Paper on approaches to improving literacy instruction in Uganda.

Outcomes and impacts are expected to build as the programme progresses.

UNIQUE DATA INFORMS PAKISTAN’S SUPPORT TO EDUCATION FOR CHILDREN WITH DISABILITIES
High quality data on education of children with disabilities is scarce and presents significant obstacles to developing disability sensitive policies. To fill this gap, researchers at the University of Cambridge and partners in India and Pakistan pioneered combining questions from the Washington Group for Disability Statistics in assessing children’s learning. Finding that many children with disabilities are in mainstream schools, the research identifies the types of support teachers need, to adopt effective teaching practices for diverse classrooms. “The research has been influential in training Punjab Special Education Departments to use child functioning survey tools, enabling better assessment of disability prevalence in schools supported by BRAC Pakistan, in Sindh province. This is vital for improving support for children with disabilities.” - Ed Davis, Team Leader for DFID Pakistan’s Education Policy Team.

Both ESRC and DFID seek efficiency in programme management, and have been reflecting this year on options to develop a new, strategic partnership between DFID and ESRC that covers several programmes at once, and allows the partnership to respond to new areas of joint strategic interest in a flexible manner. As the development of this model is likely to take time, in the meantime ESRC and the DFID Education team have been working towards a renewal of the Raising Learning Outcomes programme, within the context of other education and development related initiatives. The recently appointed Global Challenges Research Fund (GCRF) Leader is involved in informing these discussions.

In thinking about the future strategic direction of the partnership, ESRC and DFID have reflected on the strengths of the programme and will summarise these in forthcoming internal documents that seek funding approval. Next year’s annual review, and the design of the programme evaluation this year, will pick up on these.

Explain major changes to the logframe in the past year (1/2 page)

ESRC and DFID undertook a revision process of the logframe in February 2018, including benchmarking it against the two other ESRC-DFID log frames. It was deemed to be sufficiently ambitious, which validates the successes of where targets have been exceeded. However, it would be good to better understand why the programme is excelling. An evaluation into the programme will help with this. Changes were not recorded as part of the ‘change frame’ on the log frame but will be going forward.

Describe any planned changes to the logframe as a result of this review (1/2 page)
The impact and outcome statements remain relevant. Changes will need to be made to some of the outputs to reflect that there are no further research calls to new grantees. This will affect indicators 1.1, 2.1, 2.2, 2.3, 2.4, 3.1 and 3.2 However, a target could be added to reflect the commissioning of the Follow on Fund opportunity for existing grants. An indicator could also capture the funders’ ambition to raise the profile of the RLO programme.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

In the Business Case, the value for money indicators to be identified and tracked are:

1. Number of publications in peer reviewed publications
2. Engagement with policymakers from outset of project
3. Dissemination activities with policymakers
4. Number of awardees implementing their pathway to impact
5. Identifiable influence on policymaking
6. Leverage of ESRC funds as a percentage of total programme costs.
7. Monitoring ESRC administration and staff costs.

This programme is on track with the majority of the above indicators. Progress against the fifth, identifiable influence on policy making, is starting to happen but will need to be tracked closely over the next year.

Economy
- ESRC has excellent structures and processes for administering research calls. This includes significant scrutiny of project level costs. After the commissioning panel, a review of costs is undertaken by ESRC to ensure that costs are reasonable with suggestions or recommendations provided if not.
- At the award contract stage all costs are subject to detailed scrutiny by the ESRC Secretariat. Any unjustified or excessive costs may be removed from the budget if further justification is not provided by the host research organization, or is not satisfactory.
- Projects are barred from exceeding their awarded budget. On average, projects are completed for just under the full budget cost (97%).
- Grants are contracted with RCUK standard T&Cs which include financial management and reporting requirements.
- Grants are only held by institutions which have passed RCUK Due Diligence processes, which include checks on financial management and capacities
- The overall scheme budget profile and payments are maintained and managed by the Professional Support Unit Finance Team with input from the ESRC Programme Secretariat. DFID payments are made in arrears. ESRC provides necessary information in good time so that adjustments can be made promptly and variance across the year has been good.
- All forecasts and profiling continue to be extremely accurate, with good financial management shown and detailed information provided to DFID.
- DFID and ESRC have a good relationship, where cost transparency is shared and interrogated on a quarterly basis.
- Grant holders report ESRC processes as easy, user friendly, straightforward and very responsive.

Efficiency
- The number of scheme-funded journal articles, books, or book chapters reported as published or accepted for publication is on track (34 publications).
- As discussed earlier, the contract for the Programme Research Lead and the Impact Initiative both had break clauses at 13 months and 24 months respectively. Following a formal review meeting with members of DFID and ESRC commissioning teams and incorporating feedback from grant holders, it was agreed that both functions should continue beyond the breakpoints, provided required actions take place. This process was viewed positively by both functions, who have adapted their work plan to meet requirements and are now performing more efficiently.
- The Open Access review, which is currently taking place in DFID using RLO as a case study, identified over 60% of RLO publications as Open Access.
- The Impact initiative has put all publications on Open docs, bringing total downloads to 51,651. ESRC and DFID will support DFID’s Open Access review and will action feedback from the review to increase the number of Open Access publications.
- Both the PRL and the Impact Initiative are increasingly targeting their efforts to make the most of opportunities and events, to increase value for money of programmes. For example CIES, the Disability Summit, Works for Africa’s Poorest Children? Conference in Uganda.
- The log frame indicators were reviewed with wider RED programmes and viewed to be sufficiently ambitious.
.
Effectiveness
- The two cross cutting functions are supporting ways the outputs can better lead to desired outcomes.
- ESRC and DFID are closely monitoring the performance and work plans of the PRL to ensure their outputs represent value for money
- There has been learning and sharing across RED, especially in relation to the Impact Initiative and how it can be supported as well as benchmarking indicators between programmes.
- All ESRC grant holders produce detailed “Pathways to Impact” and report annually on progress influencing policy and practice.
- Several grantees have collaborated closely with the Impact Initiative to create high quality policy relevant products to communicate their impact.
- There is a strong research uptake strategy. There are plans to carry out an evaluation of the Impact Initiative to assess the extent to which it is having an impact on grant holder behaviour.
- Over the last 6 months, there has been regular strategic engagement between ESRC and DFID, to discuss the Theory of Change and explore what a potential RLO Phase 2 could look like.

Equity
- 14 of 16 (87%) grant holders reported the incorporation of gender analysis within their projects. However, ways in which gender can be better explored as a cross cutting theme in the programme will be a recommendation this year.
- In 2017/18 9 additional journal articles and book chapters were produced on education and disability under RLO.
- ESRC-DFID funded researchers were key to creating The Statement of Action on Inclusive Education, signed by 31 donor agencies, international NGOs, research organisations and global education networks and launched at the Global Disability Summit.
- The Impact Initiative produced a collection of RLO research titled: Research for Policy and Practice: Disability and Education. This is aimed at a wide audience, including policy makers.
- 56% of proposals and 16 of 30 (53%) research grants awarded involve Southern PIs or Co-Is
- 17 of the 20 live and completed grants (85%) reported capacity building activities benefitting Southern researchers.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The original VfM proposition in the business case still holds and the programme continues to represent value for money. ESRC have well established systems and value for money is one of the key criteria on which research proposals are assessed. There is a strong focus on impact demonstrated through the “Pathways to Impact” process and representation of users alongside academics on the funding panel, both of the programme functions have been reviewed, refined and closely monitored to ensure value for money. ESRC are interested in continuing the partnership with DFID and considering leveraging additional funds to increase the amount of funds available for researching learning outcomes.

RED guidance on VfM recommends developing VfM benchmarking indicators where possible and ESRC have already drawn on benchmark indicators for outputs per grant from the DFID-ESRC Joint Fund for Poverty Alleviation programme to set targets within the RLO logframe (e.g. number of peer reviewed journal articles per grant). However, going forward DFID will share the RED guidance on VfM with ESRC so this can provide a shared focus.

The focus for value for money this year has been ensuring the programme level functions of the Programme Research Lead (PRL) and Impact Initiative are delivering. Both these elements represent novel methods of delivery intended to maximise the effectiveness of the grants beyond their individual scope. These functions are therefore critical to the overall impact of the programme so both DFID and ESRC have continued to invest significant resources in the iterative learning and adaption process required to deliver these functions. Both functions have been deemed to be able to meet DFID and ESRC’s expectations and the Impact Initiative is going through the process to extend its contract to 2020. DFID and ESRC are closely monitoring key deliverables from both functions over the next year to ensure they stay on track and value for money is met.

The PRL role is intended to deliver three programme-level aims: support and provide evidence of RLO’s scientific, conceptual and methodological contributions; maximise scientific quality and best practice between RLO grants across calls and around cross-cutting themes; and implement and strengthen cohort-building opportunities and activities within RLO. DFID and ESRC have been supporting PRL to steer away from the publication and promotion of individual research efforts in favour of more strategic activities that support research synthesis and learning between grants. There has been positive uptake amongst grant holders to explore the methodological synergies between grants and make the most of the unique multidisciplinary and mixed methods aspect of the programme.

Since the findings of the review, the Impact Initiative’s workplan has been revamped. The team are making the most of windows of opportunity. There is more momentum with products and better communication with the PRL. As a result, ESRC and DFID have decided to offer an extension to the function until 2020.

E: RISK (½ to 1 page)

Overview of programme risk (Moderate) and mitigation

Overall, risk has remained consistent across the programme. Although there are a number of challenges around the programme, given the high-quality of the grants and continued work to shape the PRL and Impact Initiative function, the overall risk rating should remain at moderate.

The ESRC report on risks annually to DFID and maintains and updates a full corporate risk register.
Through peer review and expert advice the ESRC only gives grants to institutions recognised as bona-fide research institutions and provided those institutions and award holders are willing to adhere to ESRC terms and conditions. Normally, ESRC Research grants are only given to UK institutions. As reported previously, non-UK or other unrecognised institutions funded under this scheme are required to gain full UKRI funding assurance before contracts will be issued and funding can commence. In order to ensure compliance, ESRC also operates a number of sanctions against institutions or individuals that fail to comply with the terms and conditions of their grants. The ESRC risk assessment strategy recognises this research funding environment.
The ESRC risk register covers programme management, research commissioning, award management and programme impact risks. It sets out their overall likelihood and potential severity, identifies mitigation measures in place, provides a current rating of how likely we consider they are to occur, and describes the current issues underlying that assessment. This approach is harmonised across ESRC-DFID programmes. In summary:
One risk has a current risk rating of “Amber”: (medium)
- Strategic support functions such as the Impact Initiative (formerly EPD) and Programme Research Lead (PRL) do not provide the strategic input required to support successful delivery of the programme.
- As detailed above and in the risk register, both functions have a revised focus on their objectives, however they will continue to be closely monitored and regularly reviewed to ensure they continue to deliver.

Four risks have current risk ratings of “Amber/Green”: (moderate)
1. DFID and ESRC disagree on key components of the scheme
2. Staff changes in ESRC and/or DFID lead to ineffective or delayed delivery through reduced capacity or loss of expertise
3. The quality of applications received from Southern lead organisations is poor, leading to a low proportion of applications being funded
4. Cash limits expressed in sterling cause problems for lead institutions due to currency fluctuations

All remaining risks have current risk ratings of “Green”. (low)

- A further will be added as a result of discussions toward this Annual Review:
  - Limited ESRC capacity means ESRC-DFID partnership cannot take full advantage of all programme opportunities.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

ESRC continue to provide DFID with excellent financial management, with up to date financial forecasts provided every quarter with detailed explanation. ESRC have been very responsive to DFID’s financial reporting and invoicing requirements, providing detailed breakdowns of funds before every disbursement in order to comply with DFID financial procedures. Overall, spending is on track.

Delivery chain mapping (first tier) was completed in January 2018 by ESRC. The Education Research Team are currently looking into how to better ensure best practice with regard to safeguarding is followed as part of the implementation and monitoring process of research programmes.

Date of last narrative financial report(s)	June 2018
Date of last audited annual statement (s)	February 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The programme uses existing ESRC mechanisms to monitor and evaluate funded research. Funded projects are required in their contracts to produce an annual progress report using a template developed specifically for ESRC/DFID collaborative programmes. This reporting year the only major amendment to the annual report was a small set of questions about the Programme Research Lead (PRL) function. These reports allow grants to report on activities, both completed and planned, and to raise any issues in grant management, which were then followed up by ESRC and have also been flagged in this report.

ResearchFish
Grant holders are also required to upload award publications and other outputs on the ResearchFish system as their research progresses and for up to five years after the grant’s end date. After grants end, grant holders also have to submit on ResearchFish a Key Findings section (3 months after the end of their award) and a Narrative Impact report (12 months after the end date). Data uploaded has to be validated by lead researchers/ research organisations each year. Following the submission period and validation of the data, all information is made publically available on Gateway to Research. Following completion and validation by the Principal Investigator, all reports are migrated to ‘Gateway to Research’ to ensure public access to this information. ESRC sends a list of outputs annually for DFID to upload onto R4D. The formal ResearchFish submission period for this year was between 5 February and 15 March 2018. Sanctions apply to any UKRI funded researchers who do not make a submission each year during the Submission Period. All RLO awards have been compliant meaning no sanctions have been applied. Relevant outputs have been shared with both cross-cutting functions to support their engagement with grant holders.

Cross-Cutting Functions
The Impact Initiative and PRL join quarterly calls with ESRC and DFID to provide updates. In addition, the PRL submit monthly workplans to ESRC and DFID. The PRL are in the process of authoring an book on key themes emerging across RLO grants. DFID will be involved in the drafting process, starting with a workshop at the end of August 2018 and offering periodic feedback going forward.

Events:
Both ESRC and DFID attended the two day RLO grant holder workshop in London in Feburary 2018, which was hosted by PRL and the Impact Initiative and attended by representatives from 22 grants. This was a successful event with largely very positive feedback from grant holders. According to the PRL report, 21 of 24 respondents indicated that ‘learning about their colleagues’ research approaches and methods was important or very important to the RLO programme’. The Impact Initiative also received positive feedback for the policy and skills focussed dimension to their sessions.

“The Impact Initiative helped us to frame research and research findings within our networks in a way that was more understandable and accessible for the audiences we were working which include government officials, ministers, advocates, members of civil society, fellow NGOs, and the UN agencies”.

“Bringing grant holders together with the Impact Initiative team in those events, people are seeing opportunities they wouldn’t have seen, exchanging ideas about how to influence, who is doing what, learning from each other, getting new ideas…. We thought that until you have results [you have] nothing to say on impact but when you see projects more advanced we can see what they are doing, mixture of projects is useful, they give ideas of how to start.

ESRC and DFID also attended three events of the PRL Seminar Series in early 2018. This process confirmed concerns that this activity did not speak directly to the PRL’s objectives and as a result it was recommended in the Mid Term Review that the seminar series was dropped or significantly altered. The PRL have since amended the seminar series to be a quarterly workshop with a number of grant holders, which supports cohort building and shared learning.

DFID attended the Impact Initiative hosted Disability workshop in April as well as the summit in July, where the initiative had a stall, showcasing how evidence underpins the commitments made on education at the Summit. DFID will attend the conference in Uganda, where Southern RLO researchers will be presenting and ESRC will attend the event in South Africa for sub-Saharan grant holders. Both events are in September 2018. Feedback from both will support the planning of the 2019 grantholders workshop.

This Annual Review was developed closely with ESRC, building on their recent Annual Report (the timing of which each year follows the ResearchFish submissions, and hence the decision to align our Annual Review with this process). DFID have also reached out to grant holders across all three calls and in USA, UK, and South Africa as part of this Annual Review. DFID have also discussed reflections and recommendations across other DFID teams that partner with ESRC, to ensure the process is aligned across ESRC-DFID partnership programmes.

Evidence (1/2 page)

A budget line for evaluation is included in the RLO programme. Planning of this activity will draw actively on lessons from other programmes, including the 2011 Joint Fund scheme evaluation and the Impact Evaluation of the Joint Fund. A smaller-scale evaluation is also planned, of the Impact Initiative function and PRL. This evaluation aims to draw out lessons learned to inform the development of similar functions within and beyond the ESRC-DFID partnership, as well as for ESRC-DFID phase 2.

87% of grants are collecting data disaggregated by gender. Over half of the grants focus directly on disadvantaged groups such as children with disabilities, minority groups and children in rural areas or conflict areas. Therefore each of these grants will produce evidence, which speaks to the ‘Leave no one Behind’ agenda. For example there have been 9 RLO journal articles on children with disabilities this year alone. The PRL and Impact Initiative will also continue to draw together findings to ensure evidence on equity is synthesised and policy relevant.

Learning (1/2 page)

ESRC and DFID keep in regular contact over the management of RLO. This helps to anticipate and address issues easily as well as share lessons and know how where necessary. It also supports creating a united partnership for the grant holders and the functions.

ESRC discusses the three ESRC/DFID programmes regularly to compare and share good practice and learning. The progress report requests to grant holders are amended annually to reflect learning from the programmes and to better suit the needs of end users (Impact Initiative, PRL, ESRC and DFID teams). ESRC also discuss within wider ESRC to gather information from others, for example on managing investments and working with media. DFID teams working on the 3 ESRC-DFID programmes are in regular communication, which helps to ensure the RLO programme is following current DFID recommendations.

The external Mid Point Review commissioned by ESRC and DFID provided invaluable learning for how to progress strategically with the Impact Initiative, as stated in discussion above. The PRL Midpoint review was internal, given the smaller and shorter scope of contract. Both reviews yielded useful lessons and recommendations which have resulted in activity change.

DFIDs Open Access Review will support ESRC and DFID with recommendations on how to better support grant holders to ensure outputs are always Open Access and follow DFIDs Open Access Policy.

For grant holders, the key opportunities from learning from each other in 2018 were the January grant holder workshop, CIES 2018 and the online methods repository. Grant holders, who have worked more closely with The Impact Initiative to develop their impact stories and policy briefs have also gained from that expertise (as stated earlier).

As mentioned above, the PRL Seminar series did not support learning amongst grant holders to date, but the amended versions should provide this learning opportunity. Grant holders said they would like even more opportunities to engage across projects, either in workshops or virtually, so they can be up to date on what other programmes are doing and also continue to be signposted to those that may be working on something similar either conceptually or methodologically. The multidisciplinary and mixed methods identity of the programme is viewed as a real strength and a learning opportunity. One grant holder suggested that more could be done to try to bridge understanding of methods and suggested a session ‘to discuss the norms of rigour in each discipline’.

This year, ESRC will plan and commission an evaluation of impact support functions across different programmes, including the Impact Initiative and PRL on this programme. This will feed into wider DFID and ESRC future programme design as well as a potential RLO Phase 2. ESRC and DFID will also start to plan for a programme wide evaluation. This could start to explore the policy uptake of the RLO research. DFID will aim to better link researchers with DFID advisors in country. PRL will continue to be monitored monthly and both ESRC and DFID will try to find a way of collating outputs so they can be systematically shared.

Progress on recommendations from previous reviews (1/2 page)

Recommendation	Action by	Timing	Review
DFID and ESRC to review status of unallocated funds to decide how they can be most appropriately and strategically reallocated by November 2017. This will draw on analysis from across the DFID-ESRC partnership, analysis of the existing RLO portfolio and gaps within that, as well as other learning from the calls to date.	ESRC and DFID	Ongoing	Decisions for the follow on fund have been agreed with ESRC-DFID and grant holders. However, these funds have not yet been commissioned, partly due to change over of staff in ESRC. The unallocated funds will be available to all current grant holders, with funding (30K- 100K) linked to four possible areas: Impact enhancement, research augmentation, capacity building and cross-grant synthesis. This has been positively received by all 19 grant holders who responded to the expression of interest survey. Commissioning will take place in Autumn of 2018. No grant has been disadvantaged by the delay. The fund will be open for 6 monthly tranches over the next 3 years to maximise grant holder participation as they are all at different stages of implementation.
DFID and ESRC to have a high level discussion, including a senior RED representative, on the future of the partnership as annual research calls come to an end by December 2017. This should incorporate emerging opportunities around GCRF funding and changes expected with the formation of UKRI.	ESRC and DFID	Ongoing	DFID and ESRC are having regular, ongoing discussion regarding the future strategic direction of the partnership. Discussions have taken place to explore options to develop a new, single business case model that encompasses multiple strands of activity and allows the partnership to respond to new areas of joint strategic interest in a flexible manner. As the development of this model is likely to take time, in the meantime ESRC and the DFID Education team have been working towards a renewal of the Raising Learning Outcomes programme, within the context of other education and development related initiatives. The recently appointed GCRF Education Challenge Leader is involved in informing these discussions as well as a group of expert researchers and users. The commissioning of Call 1 Phase 2 will aim to take place in March 2019.
DFID to arrange an internal meeting on ESRC partnership with Education, Growth and Governance Conflict and Social Development research teams to discuss future plans and opportunities for the partnership as a whole.	DFID	Spring /summer 2018	See above. / Following discussion, it seems that the next phase of the ESRC partnership will be initially education led as other teams’ programmes have had longer partnerships and therefore likely to come to an end sooner.
ESRC and DFID to review opportunities to maximise proportion of open access research outputs produced under this programme, including from researchers based at institutions not in receipt of RCUK open access block grants. ESRC and DFID to pursue this issue through the RCUK-DFID forum before considering alternative options to support open access at programme			Guidance to applicants in recent years encourages the costs of open access to be included in research proposals. Non-UK organisations should therefore have provision for open access. There have been no requests for open access funding on the RLO programme in the reporting year. The programme will continue to be mindful of the need for open access in any future calls. DFID is supporting a review of our Open Access policy and using the RLO programme as one of eight case studies. Feedback from this will be incorporated into RLO Phase 2 commissioning going forward.

Annex: List of all ESRC DFID RLO Grants

Call	Grant Ref	Stream/ Thematic Focus	Project Title	Project Webpage	Country/Countries of Focus	PI name
Call 1	ES/M005240/1	Medium	Transforming the Pedagogy of STEM Subjects	https://www.dur.ac.uk/research/directory/view/?mode=project&id=780	Ethiopia	Vanessa Kind
Call 1	ES/M005496/1	Medium	Pedagogies for Critical Thinking: Innovation and Outcomes in African Higher Education	https://iris.ucl.ac.uk/iris/browse/researchActivity/14351	Kenya; Ghana; Botswana	Tristan McCowan
Call 1	ES/M005453/1	Medium	Improving curriculum and teaching methods to influence policy and increase the quality of ECDE provision for children with disabilities in Malawi.	http://www.birmingham.ac.uk/schools/education/research/victar/research/early-childhood-services-for-children-with-disabilities-in-Malawi.aspx	Malawi	Paul Lynch
Call 1	ES/M005186/1	Small	Literacy development with deaf communities using sign language, peer tuition, and learner-generated online content: sustainable educational innovation	http://www.research.lancs.ac.uk/portal/en/projects/literacy-development-with-deaf-communities-using-sign-language-peer-tuition-and-learnergenerated-online-content-sustainable-educational-innovation(091d7aa1-e376-4228-b8a8-21347f9646a6).html	India; Ghana; Uganda	Ulrike Zeshan
Call 1	ES/M005445/1	Medium	Learning outcomes and teacher effectiveness for children facing multiple disadvantages, including those with disabilities: India and Pakistan		India; Pakistan	Pauline Rose
Call 1	ES/M004740/1	Small	Toward the Development of a Rigorous and Practical Classroom Observation Tool: The Uganda secondary school project	http://www.theimpactinitiative.net/project/toward-development-rigorous-and-practical-classroom-observation-tool-uganda-secondary-school	Uganda	Edward Seidman
Call 1	ES/M005011/1	Small	Constructing a Global Framework for Analysis of Social Exclusion From and Within Learning Systems		Afghanistan; India; Dafur; Sierra Leone; Morocco; Tunisia	Parul Bakhshi
Call 1	ES/M004732/1	Small	Promoting Children's Learning Outcomes in Conflict-Affected Countries: Generating, Communicating, and Incorporating Evidence for Impact	http://steinhardt.nyu.edu/research/projects/promoting-childrens-learning-outcomes-in-conflict-affected-countries	Democratic Republic of Congo; Bukavu; South Kivu	John Aber
Call 1	ES/M004864/1	Medium	Examining Effective Teaching in Rural Honduran Secondary Schools		Honduras	Erin Murphy-Graham
Call 1	ES/M004996/2	Large	The Literacy Laboratory Project (LLP) under the Northern Uganda Literacy Program	http://www.psc.isr.umich.edu/research/project-detail/36479	Uganda	Rebecca THORNTON
Call 2	ES/N010094/1	Remote Rural; Urban Slums	Inclusive higher education learning outcomes for rural and township youth: developing a multi-dimensional capabilities-based higher education index	https://www.ufs.ac.za/crhed/centre-for-research-on-higher-education-and-development-home/research-projects/esrc-dfid-'miratho'-project	South Africa	Melanie Walker
Call 2	ES/N010205/1	Remote Rural	Facilitating Innovative Growth of Low Cost Private Schools: Experimental Evidence from Pakistan	http://pedl.cepr.org/content/facilitating-innovative-growth-low-cost-private-schools-experimental-evidence-pakistan-1	Pakistan	Asim Khwaja
Call 2	ES/N010221/1	Remote Rural	Investing in our Future: The Early Childhood Intervention and Parental Involvement in Bangladesh	http://monash.edu/research/explore/en/persons/asadul-islam(6e0ad770-703d-4dc1-a8f3-7e0c20d0a156)/projects.html	Bangladesh	Asadul Islam
Call 2	ES/N01023X/1	Remote Rural	Succeeding Against the Odds: Understanding resilience and exceptionalism in high-functioning township and rural primary schools in South Africa		South Africa	Servaas van der Berg
Call 2	ES/N010345/1	Remote Rural; Urban Slums	Multilingualism and Multiliteracy: Raising learning outcomes in challenging contexts in primary schools across India	http://www.reading.ac.uk/research/theme-prosperity-resilience/rd-education.aspx	India	Ianthi Maria Tsimpli
Call 2	ES/N01037X/1	Remote Rural	Education systems, aspiration and learning in remote rural settings	https://www.brunel.ac.uk/research/Projects/Education-aspiration	India; Laos; Lesotho	Nicola Ansell
Call 2	ES/N010388/1	Remote Rural	Improving school governance and learning outcomes at scale: A randomized evaluation of the Madhya Pradesh School Quality Assessment program		India	Karthik Muralidharan
Call 2	ES/N010515/1	Urban Slums	AFLA - Assessment for Learning in Africa: Improving Pedagogy and Assessment for Numeracy in Foundation Years.	http://oucea.education.ox.ac.uk/research/recent-research-projects/assessment-for-learning-in-africa-afla/	South Africa; Tanzania	Therese N. Hopfenbeck
Follow on Funding	ES/P008607/1	N/A	Promoting Children's Learning Outcomes in Conflict-Affected Countries: Evidence for Action in Niger		Niger	John Aber
Follow on Funding	ES/P008623/1	N/A	Peer to Peer Deaf Multiliteracies: research into a sustainable approach to education of Deaf children and young adults in the Global South		India; Ghana; Uganda; Nepal; Rwanda	Ulrike Zeshan
Call 3	ES/P005594/1	Accountability	Technology, Monitoring and Teacher Support in Niger	Niger	Jenny Carson Aker	Tufts University
Call 3	ES/P005675/1	Accountability	Accountability for gender equality in education: Critical perspectives on an indicator framework for the SDGs	Malawi and South Africa	Elaine Unterhalter	Elaine Unterhalter
Call 3	ES/P005888/1	Accountability	Accountability, capacity and trust to improve learning outcomes in South Africa; a systems approach	South Africa	Melanie Ehren	Dr. Melanie Ehren
Call 3	ES/P005349/1	Accountability	Can schools' accountability for learning be strengthened from the grassroots? Investigating the potential for community-school partnerships in India	India	Ricardo Sabates	Dr Ricardo Sabates
Call 3	ES/P005551/1	Accountability	Improving Learning: Developing Measures of Accountability and Evaluating their Association with Students' Gains in Achievement in Nepal	Nepal	Dirgha Ghimire	Dirgha Ghimire
Call 3	ES/P005802/1	Accountability	Making the elementary schooling system in India work for disadvantaged learners: a cross-scalar comparative study of accountability relations	India	Caroline Dyer	University of Leeds
Call 3	ES/P005810/1	Accountability	Disadvantage and Participation Accountability Processes: Theory and Evidence from School Development and Management Committees in Karnataka, India	India	Sayantan Ghosal	University of Glasgow
Call 3	ES/P006043/1	Accountability	Partnership Schools for Liberia: Impact on Accountability Mechanisms and Education Outcomes	Liberia	Justin Sandefur	Innovations for Poverty Action
Call 3	ES/P005799/1	Accountability	STRENGTHENING SCHOOLS ACCOUNTABILITY MECHANISMS THROUGH PARTICIPATION: ADDRESSING EDUCATION QUALITY AND EQUITY IN AFGHANISTAN AND PAKISTAN	Afghanistan and Pakistan	Jean-Francois Trani	Washington University in St Louis
Call 3	ES/P005489/1	Accountability	Organizational Perspectives on Accountability and Learning (OPAL): School Management Models and the Social Impact of Schooling in Mumbai and Kathmand	India	Robin Shields	Dr Robin Shields