Annual Review Template

Type of Review: Annual Review

Project Title: Transparency and Accountability Interventions

Date started: 1 May 2012	Date review undertaken: June 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Introduction and Context

What support is the UK providing?

DFID provided £100,000 to the Transparency and Accountability Initiative (T/AI) as an Accountable Grant to manage an 11 month research design exercise for a new research programme to be co-funded by DFID, the Bill and Melinda Gates Foundation (BMGF) and the William and Flora Hewlett Foundation (Hewlett). The business case is available on Quest (2537083). / BMGF had already funded the scoping work which helped to inform the design phase. UK support was required to take this collaboration to the next stage and produce a detailed and costed research proposal, enabling all three organisations to make a final decision regarding investment in the full research. / Since T/AI already received core funding from DFID there was no extra administrative cost involved. The full £100,000 was passed to the research consortium which won the bid to design the programme and, if approved by the three funding donors, implement the research programme. There was a high response to the Request for Proposals with 27 high calibre submissions received. A consortium led by Harvard Kennedy School and the Results for Development Institute was selected as the preferred bidder based on the following criteria: relevant expertise and experience; applicable project management skills and the ability to address broad research questions. Under the Accountable Grant T/AI and Harvard were responsible for designing the full research proposal.

What are the expected results?
The expected result was a detailed design of a rigorous, multi-year research programme to provide robust quantitative and qualitative evidence on the impact of transparency and accountability interventions on human development outcomes. The design was expected to measure specifically the impact on health outcomes. This will be a unique addition to the existing evidence base of what works in development and provide a global public good. This in turn can inform of DFID and other development actors’ policies, programmes and partnerships globally. In particular this research has the potential to influence the decisions of major funders in these sectors (including the Gates and Hewlett foundations) about whether to invest in transparency and accountability interventions, and how to scale up, target or refine work in these areas. This should result in greater benefits from future development programmes, and therefore better human development outcomes for the beneficiaries.

What is the context in which UK support is provided?
The proposed research was designed to explore a growing operational field of development, in which the UK has significant new investments. There is increasing interest in transparency and accountability (T/A) interventions to promote greater openness on the part of governments, companies and other institutions so that the public can hold them to account. Examples of T/A interventions include citizen report cards, scorecards, social audits, civil society budget analysis, and public expenditure tracking surveys. Evidence on the extent to which these transparency and accountability interventions lead to better human development outcomes is lacking. As DFID scales up its work in the area of empowerment and accountability, it is important to ensure our aid investments are effective, deliver good value for money for taxpayers, and that we can take strategic decisions based on robust and credible evidence. / There are clear conceptual and empirical gaps in the existing global knowledge base on the impact of T/A interventions. A mix of qualitative and quantitative evidence and theory suggest these interventions may positively affect outcomes but the evidence is patchy and based on different interventions in different contexts, assessed with different criteria, and not generalisable. Some research argues that the positive impacts have been over-stated. Research that will yield generalisable and policy significant findings focused on T/A interventions that have likelihood of being replicable and scalable across a wide range of contexts is needed. / To generate more robust evidence requires a large study of T/A interventions replicated across contexts, including rigorous experimental impact evaluation methods. This requires a large investment and therefore major donor support. Both the Bill and Melinda Gates Foundation (BMGF) and The William and Flora Hewlett Foundation (Hewlett) have collaborated with DFID under the T/AI umbrella since April 2011 to prepare this research initiative, and are ready to commit multi-million dollar investments to a multi-year research programme. DFID’s involvement has led to increased commitment to the research by the leadership of those foundations. DFID’s familiarity with T/A initiatives and research procurement has added significant technical and commercial rigour to the process to date. UK investment in the design phase is therefore required to i) help leverage significant donor funding and ii) increase the quality, VFM and policy relevance of the research.

Section A: Detailed Output Scoring

Output 1: Design of a multi-year, multi-site Transparency and Accountability Evaluation Project
Output 1 score and performance description: A / The design of the research programme, including consultations with stakeholders is the sole output for the Accountable Grant. It has been scored an A – the output met expectation / T/AI, Harvard Kennedy School (HKS) and Results for Development (R4D) have met the Terms of Reference set out in the DFID contract (see Quest No 3581240). / T/AI provided an effective coordination role. This included among other things - chairing monthly meetings with the funding partners, organising and facilitating two one day workshops with the research team and funding partners, coordinating funding partner comments on draft research designs and budgets, providing technical assistance to different parties, commissioning two rounds of peer review comments on the preliminary and draft research design, commissioning a value for money review of the final research budget / Harvard and Results for Development have delivered a credible research design which meets the criteria set out in the contract (see Quest 3735325 for the final design). The design has been subject to two rounds of anonymous external peer review (see synthesis of reviewer’s comments on Quest Nos 3728117 and 3689052). With some qualifications has been endorsed by Chief Head of Profession for Governance, Social Development and Conflict and the Head of Profession Health (see Quest Nos 3728153 and 3728155). The budget was subject to 3rd party independent review (see Quest No 3732390) which raised a number of issues which have been addressed by the research team. Additional fieldwork to Indonesia was paid for by HKS and the team also went to India, a country discarded from the initial sample, and was paid for by the Hewlett Foundation. / There has been some slippage on delivery dates and there was only one field visit rather than two made in preparing the proposal but these were discussed and agreed with the funding partners .The second visit was made in February 2013 to Tanzania. The prime goal of this visit was to provide both sides-the research team and potential implementing partners-with an opportunity to gauge the likelihood of a successful partnership.
Progress against expected results: / Recommendations: / Impact Weighting (%): 80 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2 The development of outreach products and consultation activities that contribute to stakeholder engagement and policy uptake of its future research
Output 2 score and performance description: A / T/AI, Harvard Kennedy School and Results for Development have met the Terms of Reference set out in the DFID contract (see Quest No 3581240). / T/AI provided an effective coordination role. This included among other things – supporting the research consortium as it carried out one-on-one interviews with a broad range of stakeholders, organizing a workshop with academics to provide inputs to the draft research design, organizing a case clinic in which the research consortium consulted more than 50 colleagues (funders, researchers, and civil society organizations) from around the world. T/AI also invited the researchers to present their initial findings to a group of leading thinkers and practitioners in the field in March 2013. T/AI, in collaboration with the research team, identified inputs and outputs produced during the planning phase that could be of interest to key target audiences in the field through a series of blog posts and think pieces. T/AI commissioned design templates to facilitate dissemination and branding and will post the results to its networks and website. / Harvard and Results for Development have interviewed a broad range of stakeholders to produce the research design (see proposal).The team has also prepared presentations shared in the events organized by T/AI. They have also produced: / a series of 3 blog posts focusing on take-aways from the review of T/A evaluations conducted by the T4D team. These blog posts will be built from a larger paper on this subject being written by Archon Fung and Stephen Kosack for publication in summer 2013; / a series of at least 3 blog posts focusing on take-aways from CSO interviews conducted by the T4D team. / one “think piece” on the process of selecting CSO partners for T/A-focused impact evaluations
. / Progress against expected results: / Recommendations: / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review ?N

Output 3: [insert output]
Output 3 score and performance description:
Progress against expected results: / Recommendations: / Impact Weighting (%): / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

Output 4: [insert output]
Output 4 score and performance description:
Progress against expected results: / Recommendations: / Impact Weighting (%): / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

If the project involves more than 4 Outputs please copy the box above and paste below.

Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / Not applicable. There was no logframe for this accountable grant since it focussed on delivery of a single output – the research design – in a four month period. Performance was based on delivery against the contract. / 1.2 Overall Output Score and Description: / The design of the research programme is the sole output for the Accountable Grant. It has been scored an A – the outcome met expectation. / 1.3 Direct feedback from beneficiaries / Not applicable since this is a research design
1.4 Summary of overall progress / The outcome met expectation. The research design and process has been of sufficient quality to achieve a commitment from the funding donors to invest £5.2m in a new five year research programme. / This will be a unique addition to the existing evidence base of what works in development and provide a global public good. This in turn can inform DFID and other development actors’ policies, programmes and partnerships globally. In particular this research has the potential to influence the decisions of major funders in these sectors (including the Gates and Hewlett foundations) about whether to invest in transparency and accountability interventions, and how to scale up, target or refine work in these areas. This should result in greater benefits from future development programmes, and therefore better human development outcomes for the beneficiaries.
1.5 Key challenges / Brokering and overseeing the procurement of a research programme at this scale was challenging for T/AI. These challenges were largely overcome, and a strong research programme has materialised. Without T/AI, it is unlikely that momentum would have been maintained. T/AI has learnt from the experience and would only repeat a similar role if the following conditions are in place: / Very strong interest and commitment among multiple stakeholders to tackle large and tough research questions about real world problems in the field and generate rigorous, credible evidence / Strategic relevance of the question for the broader field; / Appropriate levels of funding available. / Viable management approach is available that is consistent with T/AI’s bandwidth, processes and systems. / T/AI has shared these insights with its eight members – all leading funders in the field - during its recent strategy development process.
1.6 Annual Outcome Assessment / The overall outcome score is A as the outcome has met the expectation.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / The main cost drivers were the time spent by the researchers in designing the programme and the cost of one field visit to Tanzania which was used to scope implementing partners. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Not applicable given the short timeframe and nature of the accountable grant. / 3.2 Where an evaluation is planned what progress has been made? / Not applicable. The research programme which this accountable grant was used to design will be evaluated in several stages of the five year programme (see Quest 3735325).

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level
Risk of funds not being used as intended / Low – we have had a breakdown of costs and have been checking invoices to ensure the funds have been used appropriately and as intended / 4.4 Climate and Environment Risk / The only impact on the climate and environment was the travel associated with a single field visit to Tanzania by the research team and the two donor research meetings in Boston. For the second Boston meeting DFID joined by VC to avoid the cost and environmental damage of a return flight.

5. Value for Money
5.1 Performance on VfM measures / The output has been delivered on time and within the agreed budget over the 11 month period. / 5.2 Commercial Improvement and Value for Money / The research design team was selected as preferred bidder following a global competitive process in which DFID, Hewlett and Gates were directly involved. / 5.3 Role of project partners / T/AI and the research design team delivered the agreed outputs and within the agreed budget. The three funding partners – DFID, Gates and Hewlet – have agreed to fund the multiyear research programme which was the expected outcome. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
T/AI provided an effective coordination role. This included among other things - chairing monthly meetings with the funding partners, organising and facilitating two one day workshops with the research team and funding partners, coordinating funding partner comments on draft research designs and budgets, commissioning two rounds of peer review comments on the preliminary and draft research design, commissioning a value for money review of the final research budget. / Harvard and Results for Development have delivered a credible research design which meets the criteria set out in the contract (see Quest 3735325 for the final design).

8. Review Process
Desk review by Senior Responsible Officer and Project Officer in GCSD Team with site visits to TAI offices in London and a meeting with Harvard and Results for Development in Boston. / The design has been subject to two rounds of anonymous external peer review (see synthesis of reviewer’s comments on Quest Nos 3728117 and 3689052). With some qualifications has been endorsed by Chief Head of Profession for Governance, Social Development and Conflict and the Head of Profession Health (see Quest Nos 3728153 and 3728155). The budget was subject to 3rd party independent review (see Quest No 3732390) which raised a number of issues which have been addressed by the research team