Business Case
## Title: United Kingdom International Search and Rescue (UK ISAR) Deployment Support Programme for Emergency Response Operations Overseas (2012 - 2015). (203423)

Strategic Case
A. Context and need for a DFID intervention / 1. There has been no diminution in humanitarian disasters in poorer countries, quite the contrary. In 2010 alone, 263 million people were affected by disasters, 110 million more than in 2004, the year which included those affected by the Asian Tsunami. [1] As global climate changes, urbanisation increases and other population and resource pressures mount, so does the frequency and severity of disasters, the vulnerability of disaster-prone populations and the impact of disasters upon them. / 2. Humanitarian actors, bilateral and multilateral, are rightly seeking to ensure that response mechanisms are as up to date, complementary and effective as possible in order to react appropriately to an increasingly disaster-prone world. / 3. The international framework for search and rescue activities, including policies and operational guidelines, is organised through the International Search and Rescue Advisory Group (INSARAG), a global network of more than 80 countries (including the UK) and organisations under the UN umbrella addressing urban search and rescue. This was endorsed by the UN General Assembly Resolution (GAR 57/150) “Strengthening the effectiveness and coordination of international urban search and rescue assistance” in 2002. As a strong humanitarian actor, the UK is well placed to sponsor a high value search and rescue capability by supplying rapidly deployed world-class search and rescue teams, and helping maintain international standards, expertise and coordination. In recent years, the UK has deployed the UK International Search and Rescue (UK ISAR) Team to natural disasters in Japan, New Zealand and Haiti. / 4. The 2010 independent Humanitarian Emergency Response Review (the “HERR”)[2] recommended that: DFID should continue to exert an active role in overseas humanitarian response, including selected search and rescue missions, and to maximise its influence in the UN and wider international humanitarian system. International search and rescue is an integral and highly visible part of this; and one in which the UK has a particularly strong capability. / 5. Though not a substantial area of DFID policy, UK search and rescue deployments nonetheless generate high profile positive publicity, being highly visible and often dramatic. The search and rescue teams wear the DFID “UK Aid” logo on their uniforms and may give press interviews. There is anecdotal evidence that the high profile rescues of individuals and associated personal interest stories also help generate significant public support for UK humanitarian agencies through, for instance, DEC appeals. Generous UK public contributions complement UK funding for humanitarian action and encourage a common purpose in helping the victims of disaster and may as a side effect increase public familiarity with DFID’s work. / 6. Search and rescue deployments promote good inter-departmental relations and co-operation between DFID, the FCO, the Department for Communities and Local Government (DCLG) and the Cabinet Office, all of which are involved in the UK’s search and rescue deployments. The MoD and UK armed forces are also frequently involved, through the use of military aircraft when most appropriate. These resources are sourced under pre agreed terms of the DFID-MoD Memorandum of Understanding which regulates the use of UK military assets in humanitarian response. / 7. Continued support for UK ISAR and its role in INSARAG represents a strong strategic fit with DFID support for the United Nations Disaster Assessment and Coordination (UNDAC), whose rapidly deployed teams have a primary role in assisting the affected state in coordinating international search and rescue teams provided by different nations. UNDAC teams are frequently staffed and sometimes led by UK UNDAC members, and represent the only place in the UN system which bridges disaster management functions (such as immediate search and rescue) with the broader humanitarian work which will follow on. / 8. Finally, situations of sudden onset natural disasters can provide valuable opportunities for political dialogue in unlikely circumstances. High profile UK ISAR teams have been welcomed into otherwise restricted contexts such as Bam (Iran), northern Pakistan and Algeria demonstrating international unity in the humanitarian endeavour of saving lives and reducing human suffering. / 9. UK fire services (coordinated by Fire AID since 2012) donate high quality fire and rescue equipment to developing countries. But due to concern about terrorism and misuse of ‘trojan’ vehicles it is now riskier for UK fire services to provide redundant equipment overseas. To help address this problem, DFID will support Fire AID in its efforts to match the availability of high quality, second-hand fire fighting and crash extrication equipment donated by UK fire services, with well-researched needs in destination countries working in partnership with local people. These donations will be accompanied by top-quality training for trainers and will form part of a sustainable local fire prevention, injury reduction and road safety strategy.
B. Impact and Outcome that we expect to achieve / 10. The expected impact and outcome are: / Impact: To save lives, alleviate suffering and maintain dignity in the immediate aftermath of sudden onset natural disasters. / Outcome: Rapid, well-coordinated and appropriately assessed international search and rescue responses saving as many lives as technically possible in the limited timeframes associated with rapid onset natural disasters. / Through: Rapid deployment of expert UK ISAR teams direct to disaster sites to; / Immediately assess and start search and rescue of survivors and to transfer them to appropriate medical care; / Deployment with specialised equipment from the UK, often not available locally, to locate survivors under rubble or water and enable the whole rescue effort to concentrate on where living survivors might be found; / Inclusion of middle ranking and senior UK Fire and Rescue officers in UK ISAR teams, who contribute enormously to local and international search and rescue control and co-ordination on-site. / Results Chain: / 11. The nature of sudden onset disasters makes specific impact and outcome of search and rescue interventions hard to predict or quantify. In crude numerical terms, lives saved by foreign search and rescue teams are always few in comparison to local efforts and, in the very early stages, the efforts of the affected population themselves. However, the technical expertise of UK ISAR teams enables survivors to be located and rescued in situations where local teams may not have the right technical capacity, and/or may not be able to prioritise over multiple other critical demands in other affected areas (where there may be a higher chance of a successful rescue in the timeframe). It is hard to put a price on a single human life, but the benefit of UK ISAR deployments also extends to other lives saved through freeing up local/other capacity to undertake potentially easier rescues at the same time. / 12. The UK ISAR teams, with their high professionalism and expertise, have consistently saved lives, albeit few in total numbers. In rare circumstances, for consular reasons, UK ISAR have also recovered bodies of UK nationals killed in disasters where their teams are deployed, although recovery of bodies is not a priority area for UK ISAR teams. / 13. Fire AID will target communities with greatest need, providing equipment, training and community support to improve their ability to respond to fire and road risk. Fire AID members already work in countries of key interest to DFID, such as Nepal, Bangladesh, Kenya and Kyrgyzstan. Members work closely with local fire and rescue services to gauge needs for both equipment and training in emergency response. / Inputs / Activities / Outputs / Outcome / Impact / Inputs / Process / Outputs / Outcome / Impact / 1. Operational competence of all UKISAR personnel achieved through appropriate training. / 2. UKISAR equipment maintained at a constant state of readiness. / 3. UKISAR makes an effective contribution to the / development of INSARAG methodologies to improve urban search and rescue assistance. / 4. All UKISAR personnel /canines are prepared to deploy overseas for up to 14 days. / 5. Effective management and administration in place to support operations. / 6. Fire AID better able to track availability of UK equipment for donation and match to applications for assistance from target countries / To save lives, alleviate suffering and maintain dignity. / UK will provide £434,681 over 3 years, to support UKISAR preparedness activities. / UK will provide £85,000 over 2 years to support Fire Aid activities. / MOU for UKISAR services established with CFOA National Resilience. / Interdepartmental MOU between CFOA and DFID/DCLG and CO. / AG arranged with Fire Aid. / UKISAR fully prepared to provide rapid, well-coordinated and appropriately assessed international search and rescue responses saving as many lives as technically possible in the limited timeframes associated with rapid onset natural disasters. (UNGAR 57/150) / Fire AID network strengthened and better prepared to build fire and rescue capacity in target countries.
[1] World Disasters Report, IFRC, 2010
[2] Humanitarian and Emergency Response Review (HERR), 2010.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / 14. For UKISAR There are three feasible options: / Option 1: UK Search and Rescue capacity continues to be provided through UK ISAR. / Option 2: Providing a UK search and rescue capacity through another mechanism. / Option3: “Do Nothing”. Ending DFID/UK support for international search and rescue. / 15. DFID’s decision to fund Fire AID was approved later (May 2013) and was considered on the basis of its “fit “ with the existing UKISAR project and the risks of “doing nothing”.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Strong / 2 Strong / 3 Strong / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C. No Risk. Continued support to the UK ISAR mechanism carries negligible risk/impact in environmental terms. Only international flights and local transport. C. No opportunity. Continued support to the UK ISAR mechanism carries no new opportunities over existing combined use of single flights for the entire deployment and local transport resources. . / 2 C. Medium Risk. Using another mechanism, Such as NGOs, carries the slight risk/impact that lack of coordination/agreement may lead to additional flights being used. Otherwise there would be no additional environmental risk if transport arrangements remain similar to Option1. C. No opportunity. If fully coordinated and / deployed as one team, this option / would offer no additional / opportunities over the arrangements / in place for Option1. / 3 C. No Risk. Ending DFID/UK support for international search and rescue carries negligible risk in environmental terms. C. No opportunity. Ending DFID/UK support would offer only the advantage of not requiring any air travel or logistics support, but then no search and rescue service could be provided. / On the environmental guidelines for vehicle/equipment disposals – Fire AID individual partners have these in place. Fire AID and EASST are planning to agree uniform guidelines for all projects at the next Fire AID meeting in July 2013.
C. What are the costs and benefits of each feasible option? / 16. Option 1: Continued support through for UK ISAR / This will enable DFID to maintain search and rescue capability at a level which has proved equitable and effective over the last ten years of international experience, and which maintains a sustainable 24/7 UK readiness to respond to unforeseen disaster events. There will be some modest cost increases based on additional operational requirements and ensuring that previously underestimated budget lines are set at correct levels. The pool of personnel available will increase from 200 to 240 people, reflecting the increase from 13 to 15 in number of participating Fire and Rescue Services, this will help to spread the burden / benefits more widely across the service, with only minimal cost implications for the project (the cost of additional vaccinations). The HERR[3] found that the present level of DFID financial commitment to search and rescue activities is at about the correct level in view of a) its efficacy in distant disasters and the capacity of the wider relief effort; and b) assuming the Department of Communities and Local Government (DCLG) and the UK Fire and Rescue Services are content to provide this international service at present levels. Any increase might be difficult to balance with their core duty to provide search and rescue within the UK and the EU. Conversely, a decrease would weaken UK ISAR capacity, and impair international search and rescue capability, at a time when the increasing frequency of high impact-disasters makes maintaining such capacity increasingly prudent. An additional benefit of support to UKISAR is the contribution it makes to the capability of the fire and rescue services to respond to major events in the UK. / 17. Option 2: Providing a UK search and rescue capacity through another mechanism. / It would be possible to provide an alternative international search and rescue capacity through coordinating the efforts of five or six UK NGOs. This option is not recommended for reasons which include; the transactional costs of managing a set of five or six separate administrative arrangements with five or six points of contact, rather than through a UK ISAR single point of contact. Similarly, more efforts would be needed by DFID staff to establish and maintain a system of command and control and a sense of coordination during deployment. NGOs are likely to be more mutually independent and some may deploy under their own resources to contexts which DFID does not feel are the most appropriate. This could potentially cause a number of tensions and complications between DFID and the NGOs and between NGOs which are competing against each other for public funding and media profile. The independent NGOs may present less of a unified UK media profile as they may need to maintain their own identity within a UK deployment. This can potentially lead to more confusing media reporting of UK efforts than one associated with one UK response though its fire and rescue services Use of NGO’s, would also mean that UK fire and rescue services would lose the additional training and readiness benefits that UKISAR support provides to the strengthening of UK domestic capabilities. / 18. Option3: “Do Nothing”. Ending DFID/UK support for international search and rescue. / Ending DFID/UK support for international search and rescue altogether would a) weaken the UK’s humanitarian response capability; and b) the wider international search and rescue network, in which the UK is a leading participant in terms of ability, expertise and professionalism. A small number of additional lives lost and unnecessary human suffering would be expected outcomes, with an associated loss of political opportunity for dialogue and demonstrating unity through responding to adversity in a humanitarian spirit. The ending of DFID/UK support for international search and rescue could become challenging for media handling in future sudden onset disasters where other nations are providing highly visible response, especially if needs outweigh a reduced international capacity to respond. It may also generate public criticism of DFID’s overall humanitarian approach. / 19. For the Fire Aid component the decision to fund was taken in the context of how it complemented the existing UKISAR project, in the terms of the benefits it would bring to the fire and rescue services sector, and the risks of “doing nothing”. The benefits are that it will support preparedness for fire and other risks, vital both for preventing and responding to disasters and conflict. Basic fire & rescue equipment and training are vital components of any country’s ability to respond to disasters and therefore recover quickly. But these are often lacking in many countries at most risk. Fire AID assistance will work with local government agencies, communities and fire & rescue services to provide needed equipment accompanied by training for trainers and assistance with emergency response strategies. This would form part of a sustainable local initiative, involving civil society and local policy makers to make maximum impact. / 20. The “do nothing” option would mean that there would continue to be a risk that donations of fire and rescue aid would be ad hoc, uncoordinated and not always accompanied by training or measures to ensure equipment is used properly and effectively (for example, equipment may not be stored properly, local rescue workers may not be trained for new equipment, and there may be no provision for spare parts). Fire AID will create a system where donations are made ethically and sustainably; they will work with police and emergency services in destination countries to match donations of road crash response equipment with areas of greatest need; and work with local road safety partner organizations and government agencies to make donations part of a sustainable injury reduction and public safety strategy.
D. What measures can be used to assess Value for Money for the intervention? / 21. UK ISAR can be assessed in terms of DFID’s three components of humanitarian value for money; cost, quality and speed. More specifically, UK ISAR can be assessed on: / - The speed at which UK ISAR teams deploy from Britain to the disaster zone and become fully operational in the affected area. / - The 24/7 availability of an optimum number of trained and experienced search and rescue experts to comprise ideally sized functional UK ISAR teams of 60-70 persons. / - The quality of UK ISAR liaison and coordination with INSARAG, other search and rescue teams, state and UN coordination mechanisms / - The quality of procedures undertaken in the transfer of survivors rescued by UK ISAR for follow up medical care. / - The quality of internal UK ISAR coordination and command and control in training and deployments, and in functional operational relationships with DFID CHASE. / - The cost of search and rescue preparedness set against the above benefits. / 22. As noted above, it is not appropriate to attempt an overall count of live rescues per response or ratio of rescues per affected population number as a measure of value. Because of the wide variety of possible conditions within an affected area, it is also not appropriate to compare the tally of live rescues between different international search and rescue teams deployed to the same disaster. / 23. The Fire AID component can also be assessed in terms of cost, quality and speed: / - the speed with which donations of UK fire and rescue equipment can be matched to target country needs; / - the speed and effectiveness of rescues and response times improved; / - the quality of equipment and training provided; / - improvements in the quality and sustainability of the Fire AID network; / - the quality of results monitoring improved, in terms of results of each donation, extent local capacity strengthened and effects on casualties; / - The costs set against the above benefits.
E. Summary Value for Money Statement for the preferred option / 24. Support for UK ISAR (Option 1) will maintain DFID support at a modest but effective level, consistent with making a key contribution to international disaster response while maintaining appropriate fire, search and rescue cover within the UK and the EU. / 25. Value for money will be achieved by providing an additional level of international capacity to an existing UK service and, as needs demand, having that capability ready to rapidly deploy a high quality search and rescue team to a disaster zone to support and supplement a local and international response. / 26. Further added value is provided in the field by the provision of highly competent specialist services which complement local efforts by locating and extracting survivors in particularly challenging circumstances - often beyond immediate local technical capacities. / 27. DFID will continue to measure and improve services provided by regular discussion and scrutiny with Fire and Rescue Service partners to ensure that training and equipment is cost effective and offers good value for money. / 28. In line with the HERR recommendations, DFID will ensure that UKISAR capability is deployed appropriately and only in places where UK search and rescue teams can have an effective impact. DFID will also support the development of complementary UK niche skills, such as surgical and medical expertise which can be deployed alongside the immediate lifesaving capability provided by UKISAR. / 29. The modest support to Fire Aid will complement the UKISAR project by helping to build fire and rescue capacity in target countries and through strengthening support to UK fire services, local authorities and other agencies seeking to provide equipment and training to those countries.
[3] Humanitarian and Emergency Response Review (HERR). DFID, 2010

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / 30. Indirect – A Memorandum of Understanding (MOU) will be agreed between DFID and the Chief Fire Officers Association (CFOA) (UK registered charity: 1074071), through its subsidiary, the CFOA Centre for National Resilience Ltd (CNR), who will manage the project on behalf of the 15 concerned UK Fire and Rescue services. / 31. The MOU between DFID and CFOA will form one of the supporting annexes to the interdepartmental MOU - “UK Fire and Rescue Sector support to HMG for Emergency Response Operations Overseas” - which has been also signed between the CFOA and three Government departments – DFID, the Department for Communities and Local Government (DCLG) and the Cabinet Office. It sets out the framework for the provision of emergency response capabilities to the UK Government when required. / 32. Indirect – An Accountable Grant will be agreed with the UK registered charity EASST (the Eastern Alliance for Safe and Sustainable Transport) who provide organisational and administrative support to Fire AID.
B. How does the intervention design use competition to drive commercial advantage for DFID? / Not applicable.
C. How do we expect the market place will respond to this opportunity? / Not applicable.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Not applicable.
E. What is the intended Procurement Process to support contract award? / Not applicable.
F. How will contract & supplier performance be managed through the life of the intervention? / Not applicable.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / 33. DFID’s funding arrangement with the UK fire and rescue services will be through the Chief Fire Officers Association (CFOA), a UK registered charity (number: 1074071), and will be managed through an MOU with its Centre for National Resilience (CNR) Ltd, part of the CFOA group. This arrangement will be governed by an inter-departmental Memorandum of Understanding (MOU) concerning UK Fire and Rescue Sector support to HMG for Emergency Response Operations Overseas agreed by DFID, Cabinet Office, the Department for Communities and Local Government (DCLG) and the Chief Fire Officers Association (CFOA). / 34. The MOU with CNR will cover the costs of: / procuring specialist equipment / the training, coordination, readiness and release mechanisms of the 15 concerned UK Search and Rescue services. / 35. The 15 concerned UK Fire and Rescue Services hold and maintain specialist equipment and replace such items expended on each rescue mission. They also engage in regular training and in maintaining their relationship with INSARAG and compliance with international standards. All UK Fire and Rescue services comply with UK Local Government Legislation and DCLG guidance concerning procurement procedures, and use interoperable equipment which teams from all 15 services are trained on and fully conversant with. / 36. The technical expertise of the 15 concerned services is the most appropriate to be used for the procurement of the necessary specialist search and rescue equipment. Oversight for the coordination of purchase, ensuring synergy with training and interoperability between the 15 services is provided by the UK ISAR management team. All procurement is undertaken according to standard UK Local Government guidelines and legislation, and in respect of Department of Communities and Local Government parameters. / 37. To monitor the effectiveness of the services provided by UK ISAR, DFID will meet regularly with senior UKISAR managers to discuss results. DFID will also continue to solicit feedback from its field teams of humanitarian advisers deployed to sudden onset emergencies and from coordination bodies such as UNDAC and the concerned government departments of affected states. / 38. For the Fire AID component, an Accountable Grant (AG) will be arranged with the UK registered charity EASST (the Eastern Alliance for Safe and Sustainable Transport) registration number 1133552, who provide organisational and administrative support to Fire AID. / 39. The AG will cover the costs for : / - Developing and extend the Fire AID network to make best use of expert volunteers and trainers; / - Developing a website to give recognition to UK donations and encourage wider membership; / - Developing a database (linked to the website) to track good quality, redundant UK equipment available for donation to fire & rescue services in DFID target countries. / 40. Fire AID is a group of UK organizations and services with a mutual interest in providing ethical, sustainable donations of fire & rescue equipment to developing countries. Fire AID was established in 2012, though its members have been operating for many years – successfully donating equipment, training and expertise to over 30 countries. / 41. The Eastern Alliance for Safe and Sustainable Transport (EASST) provides organisational and administrative support to Fire AID, convening regular meetings to share information and coordinate donations. Members operate an Ethical Donations Policy to ensure scarce resources are used effectively. / 42. DFID officials will meet regularly with Fire AID and EASST to monitor the effectiveness of the programme and to discuss results.
B. Value for money through procurement / 43. The UK Fire and Rescue Service will apply to this project its rigorous standard procedures in procurement and international technical expertise in ensuring the most appropriate specialist equipment and best value for money. The interoperability of the 15 services, overseen by the CFOA, will ensure that a minimum of duplication of equipment is achieved, and that there is no redundancy in any potential team composition-equipment combination which might be required at a particular time for a particular event. / 44. Equipment costs charged to DFID will be minimised by utilising existing fire and rescue service equipment wherever possible, this includes command support equipment, base of operations equipment, medical and personal protective equipment. DFID will contribute to the maintenance and replacement of this equipment, as well as meeting some standing charges. For equipment used on deployment, DFID and UKISAR have agreed criteria for when equipment replacement costs will be reimbursed or not. / 45. The provision of medical equipment is essential to support safe systems of work for the UK ISAR team. Recent years have seen the previously problematic supply of medical equipment and consumables, including drugs, dramatically improved as a result of links developed with the Event Medicine Company (EMC) which now provides the equipment, drugs, medical supplies and logistics to stock and maintain the cache. Current arrangements require EMC to provide c £70,000 worth of equipment in accordance with agreed scales, which ensures that UK ISAR is guaranteed a level of medical equipment and supplies sufficient to provide injured personnel with the best possible care whilst in theatre and further ensures compliance with INSARAG requirements. / 46. The CFOA operates as a registered charity and a company limited by guarantee. Three wholly owned subsidiary companies sit within the CFOA Group and report to the CFOA Board. The subsidiary responsible for managing this project is CFOA National Resilience Ltd (CNR). The objective of CNR is to enhance UK fire and rescue response to local, regional, national and international incidents by being the provider of choice for fire and rescue national resilience. CNR aims to enhance preparedness and resilience by maintaining and improving the capability of fire and rescue service assets. CNR also provides an assurance function to the UK Fire and Rescue service and the UK Government on the efficacy of national resilience capabilities. CNR has unique access to, and use of, the CFOA membership providing experience and expertise. / 47. Administrative and financial management was identified as an area of relative weakness in the previous DFID supported UKISAR project. This was due to under resourcing of staff time to compile financial and other reports. Under this new project, these functions will no longer be provided by the individual fire and rescue services, who are already stretched, but centrally by CFOA through CNR. Although additional costs will be incurred these are justified due to the scale of the workload and the need for accurate and timely reporting. / 48. For the Fire AID component, value for money will be achieved by developing a system where donations are made ethically and sustainably. Fire AID members operate an Ethical Donations Policy to ensure scarce resources are used effectively. Fire AID is innovative, by matching needs with redundant, good quality equipment that would otherwise be scrapped or disposed of with no public benefit. It makes use of teams of expert volunteers from a variety of backgrounds, linking them to local development projects.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / 49. The UK ISAR and Fire AID budget for three years FY 2012/13 to FY2014/15 is profiled as follows: / Financial Year UKISAR £ Fire AID £ Total / 2012/13 124,650* - 124,650 / 2013/14 153,403 50,040 203,443 / 2014/15 156,628 35,000 191,628 / Total 434,681 85,040 519,721 / * The budget for FY2012/13 does not include £31,978 operational costs during the period Apr – Oct 2012, which were charged to the previous project. (200519) / 50. The main costs associated with the project lies in maintaining equipment and training levels. The equipment required for training and for maintaining an effective readiness and 24/7 deployable capacity has to be stored, maintained and replaced (if necessary). The above budget covers the cost of maintaining equipment and training levels. This project does not cover deployment costs, which are met from DFID programme funds for each specific response. Neither does the cost include salary and related costs of the UK Fire and Rescue Service personnel, which are met by their individual services. Also not included are the costs of equipment needed for training and for maintaining effective readiness and 24/7 deployable capacity, which has to be stored, practised on and regularly replaced. / 51. The detailed budget is presented below. It is judged to be sufficient based on previous experience and forward expectations agreed in discussion with representatives of the UK Fire and Rescue Service. DFID CHASE will monitor expenditure through regular dialogue, and financial reporting against the agreed budget with the UK Fire and Rescue Service. / Budget Area 12-13 13-14 14-15 / 1. Command/Management training: / Commander courses; / Regional INSARAG courses; 4000 4000 4000 / 2. UK ISAR Medical Team training – field medicine and procedures 9500 7500 7500 / 3. Command Support Team training 2000 2000 2000 / 4. Logistics training 1000 1000 1000 / 5. Canine training and assessment 2000 2000 2000 / 6 Internal operational assurance (exercises): / - one large scale and two smaller scale training and assessment exercises per year. 27000 27000 30000 / 7 International observers exercises/incidents 2000 2000 2000 / 8 Medical equipment replacement/maintenance and contribution to leasing contract. 11500 11500 11500 / 9 Command support equipment replacement/maintenance and standing charges. 2000 2000 2000 / 10 Logistics and Base of Operations equipment / Maintenance/ replacement and testing 2000 2000 2000 / 11 Vaccinations – to ensure 240 search/rescue personnel and 12 medical personnel remain fully vaccinated. 38000 38000 38000 / 12 Medical Support Team / Personal Protective Equipment 2000 2000 2000 / 13 Canine welfare costs and deployment equipment. 1000 1000 1000 / 14 Management and administration costs 10000 10000 10000 / 15 National management meetings (contribution) – 6 per year 1200 1200 1200 / 16 INSARAG: / Annual Team Leaders meeting; / Participate in 3 technical Working groups (7 meetings) 8000 7000 7000 / 17 INSARAG External Classification and Reclassification (IEC and IER) support / - 4 events per year 4500 4500 4500 / 18 Asset Refresh of equipment requiring replacing or updating (including tents, generators, storage, command equipment, medical equipment ) 18000 18000 18000 / Total £145,700.00 £142,700.00 £145,700.00 / Contingency £10,927.50 £10,702.50 £10,927.50 / Total £156,628.00* £153,403.00 £156,628.00 / * The budget for FY2012/13 does not include £31,978 operational costs during the period Apr – Oct 2012, which were charged to the previous project. (200519)
B. How will it be funded: capital/programme/admin? / 52. Funds will be available from the CHASE Programme budget: P0144, through Project Component number: 203423-101
C. How will funds be paid out? / 53. An MOU has been arranged with the CFOA Centre for National Resilience (CNR) detailing funding requirements. CNR is part of the CFOA group. CFOA is a registered charity and not for profit organisation. CNR will manage the project on behalf of the 15 concerned Fire and Rescue Services. Funds will be paid out in arrears upon receipt of appropriate invoicing in line with the arrangements specified in the MOU. / 54. For the Fire AID component, an Accountable Grant (AG) will be arranged with the UK registered charity EASST (the Eastern Alliance for Safe and Sustainable Transport) who provide organisational and administrative support to Fire AID. Funds will be paid out quarterly in arrears upon receipt of appropriate invoicing in line with the arrangements specified in the AG.
D. What is the assessment of financial risk and fraud? / 55. Very minimal. The project is subject to double controls, by both DFID and the UK Fire and Rescue Service, and fully accountable under UK Government guidelines, procedures and legislation. / 56. Fire AID has shared its Anti-bribery and Corruption policy with DFID.
E. How will expenditure be monitored, reported, and accounted for? / 57. By standard DFID monitoring, reporting and accounting systems, supplemented by those of the CHASE Humanitarian Emergency Operations Support Service, the UK Fire and Rescue Service (consolidated and reported on to DFID by CNR), and for the Fire AID component EASST will provide financial reporting in line with the requirements specified in the AG.

Management Case

A. What are the Management Arrangements for implementing the intervention? / 58. DFID CHASE Humanitarian Response Group will have a permanent official at grade A2 overseeing the project, assisted by DFID officials at grades B1 and B2 and by Crown Agents contracted experts in the CHASE Humanitarian Emergency Operations Support Service. Regular project monitoring meetings will be held between DFID and CNR/UKISAR managers to report on progress, with an annual report provided by CNR to DFID, which will feed into a formal DFID Annual Report. A final report will be provided at the end of the project which will inform DFID’s Project Completion Report. Specific reporting will be completed around each response. Financial management of the project will be provided by CNR who will be responsible for compiling financial reporting for the 15 concerned Fire and Rescue Services. The Fire and Rescue Service focal point (Senior Manager) will implement procurement procedures which fall under Department for Communities and Local Government guidance. EASST will manage the Fire AID component and report to DFID.
B. What are the risks and how these will be managed? / 59. Low. The risks of this tested arrangement not being able maintain equipment, training and readiness to deploy a specialist team are currently low. This facility and capacity has been managed without difficulty for more than ten years. / 60. The Fire AID component is also seen as low risk – the database and website development proposed should be within their capabilities. / 61. However, it is possible risks may increase. During the current Comprehensive Spending Review most Fire and Rescue Services are reducing staffing levels, and instigating savings across all levels of service delivery. This may prevent staff attendance at training and development events, and logistical and maintenance support might be reduced. To mitigate risks, budget lines where FRSs contributions may not be forthcoming, such as inoculations, have been fully costed with the additional costs being met by DFID if required. But in view of these funding pressures, risks should continue to be monitored on a regular basis throughout the project, and if necessary reassessed.
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / 51. Progress will be monitored through standard DFID reporting mechanisms, supplemented by regular meetings between DFID and representatives of the UK Fire and Rescue Service. CNR will submit an Annual Report to DFID. Fire AID / EASST will produce an Annual Report summarising activities and results. Progress will be monitored, measured and evaluated against the following areas: / - The speed at which UK ISAR teams deploy from Britain to the disaster zone and become fully operational in the affected area will be measured by standard DFID and UK ISAR mechanisms, OCHA/UNDAC reporting and through operational dialogue. / - The 24/7 availability of an optimum number of trained and experienced search and rescue experts to comprise ideally sized functional UK ISAR teams will be measured through standard UK ISAR reporting and dialogue with DFID. / - The quality of UKISAR preparedness and readiness arrangements, including provision of technical and specialist training appropriate to international standards, and quality and availability of equipment maintained at a constant state of readiness in line with INSARAG guidelines, will both be monitored through DFID and UK ISAR reporting mechanisms / - The quality of UK ISAR liaison and coordination with other search and rescue teams, state and UN coordination mechanisms will be measured by reporting from DFID humanitarian advisers deployed to the field and through reporting from OCHA/UNDAC and other stakeholders including host governments. / - The quality of procedures undertaken in the transfer of survivors rescued by UK ISAR for follow up medical care will be measured by reporting from UK ISAR reports, from DFID humanitarian advisors in the field, from OCHA/UNDAC reports and feedback from other stakeholders, including providers of medical services. / - The quality of internal UK ISAR coordination and command and control in training and deployments, and in functional operational relationships with DFID CHASE will be measured from relationships with CHASE, DFID humanitarian advisers in the field and other stakeholders (including in the 15 concerned Fire and Rescue services where appropriate). / - The cost of search and rescue preparedness set against the above benefits will be measured from financial reporting provided by UK ISAR against the MoU with DFID. / - The effectiveness of the Fire AID database and website in tracking the availability of equipment for donation and matching to target country needs; / - The quality of Fire AID equipment and training provided, leading to improvements in local capacity in target countries, and the speed and effectiveness of rescues and response times improved; / - Improvements in the quality and sustainability of the Fire AID network;
Lograme / Quest No of logframe for this intervention: 3750358