Type of Review: Annual Review

Project Title: UK Post Conflict Development Programme for Northern Uganda

Date started:	2010	Date review undertaken: April 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet willcalculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meetexpectation C

## Introduction and Context

What support is the UK providing?
The UK’s Northern Uganda Post-Conflict Development Programme (PCDP) provides £100 million from 2010 to 2015 to support recovery in Northern Uganda. / This programme was designed to build on the emerging peace in greater northern Uganda following the Juba Peace Talk’s Cessation of Hostility Agreement between the Lord’s Resistance Army (LRA) and the Government of Uganda (GoU). PCDP aims to generate growth, development and opportunities and promote peace building in a region emerging from a period of conflict and neglect.

What are the expected results?
The goal/impact of the UK PCDP is to build a peaceful, vibrant northern Uganda, with increased opportunities for the people of the north and reduced poverty for all of Uganda. / The purpose/outcome of UK PCDP is to create economic, social and political opportunities that improve the lives of people affected by conflict. / The logical framework of the programme identifies key results expected by 2015 from the activities of the key components of the programme under four main outputs: / Local government capacity for equitable service delivery and management is strengthened (£31.95m). This output envisages that 4,000 houses are built and all the 21 sub-counties of Gulu and Lira districts meet minimum governance conditions. / The most vulnerable conflict-affected communities are rebuilt and empowered (£27.22m). This output envisages that 10,000 extremely vulnerable people are resettled and their livelihoods supported in Acholi and Lango sub-regions, access to income-earning opportunities and better economic services of 77,000 moderately food insecure households in Karamoja are improved, and 360,000 treatments are provided by private-not-for-profit (PNFPs) health facilities in Acholi and Lango sub-regions. / The private sector is revitalised and accessible employment opportunities are created (£34m). Under this output it is envisaged that an analysis of the north’s comparative advantage, current and potential markets as well as barriers to economic growth is undertaken and disseminated; 100,000 youth in northern Uganda are trained in literacy and vocational/technical skills for productive employment, and 1000 business enterprises supported to pursue investment opportunities with 5000 jobs created. / Government, civil society and communities can engage actively in peace building and reconciliation (£6.8m). This output envisages that transitional justice policy is adopted and implementation plan agreed and national reconciliation bill is passed and that the interventions under PCDP remain conflict sensitive.

What is the context in which UK support is provided?
Context / The conflict in northern Uganda lasted 23 years and prevented the people of northern Uganda from enjoying the benefits of national stability and economic growth seen elsewhere in the country. Instead, over two million people were in camps for internally displaced persons from 1991-2011 and 22,000 children were abducted (an estimated 2,000 of whom have never returned) during the period of protracted armed conflict. / The protracted conflicts in greater northern Uganda not only led to loss of lives and displacement of over 2 million people, they also resulted in the destruction of livelihoods, infrastructure and property, and disruption of economic activities. The result was increased poverty in the region. For significant periods the affected population were unable to farm their land and access basic social services and had to rely on humanitarian assistance. Between 2006 and 2009 the total cost of the humanitarian response in Uganda was £497m, of which DFID contributed £60m. / As a result of the conflict, poverty levels in the north stood at 22% above the national average in 2009. The consequences of the conflict further intensified perceptions that the north was marginalised by the GoU. / However, following the signing of the Cessation of Hostility Agreement between GoU and LRA in 2006, the situation in northern Uganda transformed from that of armed conflict to relative peace. There was a strong case for a concerted recovery process for northern Uganda in order to minimise the risk of the resumption of conflict. GoU developed the Peace Recovery and Development Plan (PRDP) to consolidate peace and security, lay the foundations for recovery and development, reduce poverty, and tackle the root causes of the protracted conflicts in northern Uganda. / Programme delivery / This programme is complex, with 15 sub-projects under one programme umbrella, with delivery through multiple channels. These included the Office the Prime Minister (OPM) which led the Government’s response to post conflict recovery in the north through PRDP. The OPM not only managed the economic recovery analysis, youth development and private sector grants scheme components of the PCDP, OPM also chaired the PCDP Steering Committee meetings, which brought together all implementing partners on a quarterly basis. / Within the first two years of the programme the following results have been achieved: / 77,360 households provided with livelihood and economic opportunities in Karamoja; / 3500 extremely vulnerable individuals returned and reintegrated into communities; / 351 business provided with grants and 2004 jobs created; / 16,894 youth across the north trained in literacy and vocational skills; / 75 houses for teachers and health workers constructed, 1127 houses under construction and new contract awarded for 116 additional houses; / Gulu and Lira local government capacity substantially strengthened, leading to improved performance of both districts according to Ministry of Local Government assessments; / Progress in the first two years of the PCDP was mixed. It made some important contributions to recovery in Northern Uganda, for example through the UNHCR resettlement programme and the Karamoja livelihoods programme. It is also making important progress in strengthening local government capacity in Gulu and Lira districts and in supporting health service delivery in Acholi and Lango sub-regions. Progress has been slow and results disappointing for longer term development programmes such as NUSAF2, the grants scheme and youth training projects. / However, programme delivery was significantly impacted by a corruption scandal in Office of the Prime Minister (OPM) in July 2012. Following allegations of fraud in OPM, DFID suspended aid to OPM and commissioned a forensic audit of all UK aid provided through OPM. In October 2012 Uganda’s Auditor General released a Special Audit of OPM which identified serious fraud, as well as at Ministry of Finance (MoFPED) and the Bank of Uganda (BoU). The report caused DFID to extend its suspension to all financial aid provided to Government (including Budget Support), and the suspension of budget support by the nine other Joint Budget Support donors. DFID’s forensic audit was concluded in March 2013 and found that £1.3 million of UK aid provided to OPM had been misused. The GoU has now repaid this money, and is in the process of returning additional unspent UK aid funds sitting in GoU accounts. / The suspension of all aid to OPM has had serious implications for PCDP’s youth development programme and grants scheme programme funded through PCDP. It has also meant that DFID has not proceeded with a proposed PRDP Budget Support grant as envisaged during the initial programme design.

## Section A: Detailed Output Scoring
Output 1:Local government capacity for equitable service delivery and management is strengthened.
Output 1 score and performance description: / B - Outputs moderately did not meet expectation / Overall Risk: Medium / Impact Weighting: 25% / Indicator1.1. Number of houses for health workers and school teachers constructed / Output Indicator 1.1 Baseline 2009 Milestone 2012 Achieved / Number of houses for health workers and teachers constructed by NUSAF2 (DFID attributable) Planned 0 1,000 75 (completed) / 1127 (under construction) / 116 (contracts awarded) / Source: / World Bank NUSAF2 annual reviews / Progress against expected results (See Annex 1 for detail): / DFID provides a £24m ($35m) grant to the World Bank (WB) NUSAF2 programme to cover the building of 4000 houses for teachers and health workers. Of this sum, £21m ($30,450,000) is allocated to building of houses, £2.2m ($3.5m) is to cover overhead costs of the project and £.8m ($1.25m) for Inspectorate of Government (IG) to improve transparency, accountability and anti-corruption (TAAC) of NUSAF2 as a whole. / The purpose of the DFID’s support to NUSAF2 is to increase access to basic social services in the education and health sectors by building houses for teachers and health workers in order to attract and retain public sector staff in the north, which has experienced on-going problems in attracting staff. Lack of housing for teachers and health workers was identified as one of the priority constraints to improved service delivery in the education and health sector in the north at programme design. Anecdotally, teachers report the impact of these houses on their performance. Each house is equipped with solar panels, enabling teachers to do lesson planning, mark students’ homework, charge their phones and be in touch with district officials. However, the mid-term review of NUSAF, which is due to take place in June, will thoroughly assess the impact of these houses on the delivery of health and education services. / All projects under NUSAF2 are identified and implemented by communities – an innovative model for a large scale project. As a result, a key strength of NUSAF2 is its strong engagement of communities in sub-project implementation – however the focus on community participation has meant that the process of building teachers and health workers’ houses has been slow. / The December 2012 target for NUSAF2 was 1000 teachers and health workers houses constructed. To date only 75 of the 1,000 houses has been built with a further 1127 under construction and are expected to be completed within six months. This target, therefore, is significantly off track. / The slower-than expected pace of construction is partly attributable to the rigorous accounting arrangements put in place by the World Bank. Communities and districts must account for 80% of previous funds received before subsequent disbursements are made. Project accounts are also subject to six-monthly procurement audits by the Bank. Until districts receive a clean bill of health from these audits, they do not receive any further funds, causing delays to the construction process. This rigorous accountability mechanism was introduced to guard against the corruption problems which plagued NUSAF1 and resulted in the first project being terminated early. / In the course of this review, DFID also identified an anomaly between the targets set in the original 2010 PCDP logframe and those agreed between DFID and the World Bank in the 2011 Financing Agreement for NUSAF2. The 2010 logframe sets a target of 4,000 houses built, however in the financing agreement the World Bank committed to building 1696 houses through DFID grants by end of 2014, but the PCDP logframe states that the World Bank will build 4,000 houses by 2014. This discrepancy is due to a misunderstanding about what is meant by one “house.” Health-workers and school teachers’ houses are constructed as part of a duplex – one unit has two houses. DFID had understood that around 2,000 duplexes (1696) would be built, whereas the Bank committed to building 1,000 duplexes. This anomaly urgently needs to be corrected in the log-frame. / At project design stage, the Bank had anticipated that each semi-detached house would cost £11,436. However the average costs is £9,838. The reduction is costs is because of exchange rate which has seen the US dollar make gains against the Ugandan shillings. / A Mid-Term Review (MTR) of NUSAF2 was to take place in February 2012, but the GoU requested a postponement to June 2013. The MTR will assess whether the building of teachers and health workers houses is having the desired impact on the quality of health and education provision for the people of Northern Uganda. An interim review of the programme was conducted in February 2013 which concluded the following: / Housing / In response to concerns on the quality and pace of implementation of NUSAF2 infrastructure investments during the 2011 review, the NUSAF2 directorate in 2012 hired engineering assistants in all the PRDP districts covered by NUSAF2 for improved supervision and monitoring of infrastructure being built. The engineering assistants have carried out field appraisals, verified cost estimates and have also closely monitored contractors to minimise fraud and raised certificates for payments and sub-project completion. This improved the quality and pace of project implementation over 2012. / Inspectorate of Government (IG) / The IG is fully committed to implementing the TAAC component that seeks to improve efficiency, effectiveness, accountability and transparency in the use of project resources through its regional offices. Some key achievements include: / Creating an IGG-civil society partnership which will result in training 1,500 communities on social accountability and community monitoring to ensure effective use of funds at the grassroots (sub-project) levels. / Development of a new remote SMS corruption reporting and monitoring system which will equip community trainers with mobile handsets to monitor training activities as well as the status of the Project. The purpose of the SMS system is to improve accountability at lower levels and transparency of procurement as communities are encouraged to do procurement themselves. / The Auditor General audited NUSAF2 TAAC Financial statements for the financial year ending 30th June 2012 and issued an unqualified opinion on TAAC. / Following the February interim review, NUSAF2 directorate developed an action plan to ensure timely disbursements of funds and consistent project implementation. However, this has not been implemented because the NUSAF2 Task Team Leader refused to allocate additional resources to this exercise. DFID will need to communicate with the Nairobi-based World Bank NUSAF2 Task Team Leader in order to address the operations funds constraints to ensure continued programme implementation. / Recommendations: / DFID Post Conflict Recovery Adviser, the MDG team and WB NUSAF2 Task Team Leader to agree new regular monitoring of progress with revised timeline for delivery. / Log-frame targets need to be amended to reflect that the original target was 2,000 semi-detached houses, not 2,000 duplexes. The 2013 milestone also needs to be revised. Responsibility: Recovery Adviser by July 31st 2013. / NUSAF2 Mid-Term Review should assess the impact of houses for teachers and health workers on service delivery. Responsibility: MDG team leader. / Impact Weighting and Score: C– output substantially did not meet expectation. Only 75 are completed, 1127 houses are under construction, and new contracts awarded for building 116 more houses. The IG component of programme registered some positive developments and interesting innovations which need to be monitored more closely. / Revised since last Annual Review? No / Risk: Medium / Indicator 1.2: Number of sub-counties in target districts meeting minimum governance conditions / Output Indicator 1.2 Baseline 2009 Milestone 2012 Achieved / Number of sub-counties in target districts meeting minimum governance conditions Planned 4 12 15 / Source: / MoLG Annual Assessment Process of Local and Lower Local Governments / Progress against expected results (See Annex 2 for details): / Progress against expected results (See Annex 2 for detail): / The overall aim of this pilot project is to build the capacity of the Gulu and Lira district Local Governments and Lower Local Governments (sub-counties) to improve service delivery. This programme was being delivered through the Uganda Local Government Association (ULGA). / The Annual Review of the programme was conducted in June 2012. The Annual Review judged that the programme had a positive impact on the performance of both local governments. Key outcomes of the programme included: / The technical support provided to the Gulu district Chairman, significantly enhanced his capacity to engage with both his constituents and the local government administration. The district Chairman was assessed as the best performer in the country (as was his district) according to the Local Government Councils Score Card Report of 2011/12. The report attributes the performance of the Chairman to the technical support that he received through the DFID programme. / The establishment and effective use of a district resource pool (DRP). The DRP is made up of staff from the district who mentor officers at lower local government. This led to improved performance of the local governments of Gulu and Lira districts, with an increased number of Lower Local Governments meeting minimum governance conditions in Gulu and Lira districts according to the Ministry of 2011/12 Local Government assessments. / The staff incentive scheme, which rates and rewards high performing staff each year improved time keeping and attendance by local government staff. / Staff savings and credit cooperative organisations (SACCOS) in both Gulu and Lira districts have been established, improving access to credit for local government staff. / The project log frame has seven milestones. The programme has exceeded four of its milestone targets, met one milestone, moderately did not meet one milestone and was off-track on one milestone. The one milestone against which the programme was off track related to the number of people visiting the citizens’ advice bureau. The reason was that the construction of the centre was completed later than planned and it took time to fully set up the resource centre for use. When assessed against the indicator in the PCDP log frame eight lower local governments in Gulu district and seven lower local government in Lira district met minimum governance conditions, thus exceeding the set target for the year by three. / The project was due to end in December 2012 and DFID was considering a 6-month no-cost extension. However, in the course of the 2012 review the project accounts held by ULGA were also audited and the findings received a qualified opinion. The areas of concern listed included inadequately supported expenditure, diversion of funds, budget overruns and un-cleared advances. This means that ULGA has weak internal financial and oversight controls. As a result of the audit findings, DFID decided not to extend its contract with ULGA. / However, we intend to build on the achievements of the ULGA projects and potentially scale up some of the capacity building activities to more districts in the north, and will be undertaking a scoping study to look into the options for this in the next few months. This could include a re-engagement of ULGA if the association is seen as the most effective partner and can demonstrate that it has improved its financial management and controls. In the interim DFID will provide contracts for the Technical Assistants to the Chairpersons of Gulu and Lira districts. / Recommendations: / DFID to conduct a scoping study on the potential scale up of the programme since local governments’ capacity remains an area of great need across northern Uganda. Responsibility: Recovery Adviser and Governance Adviser. / DFID to provide 12-months contracts to the Technical assistants to the District Chairs of Gulu and Lira districts while scoping study is underway to ensure continuity of the programme (while scoping study is underway) and in view of positive assessments of the technical support offered under this programme. Responsibility: NU project officer. / Impact Weighting and Score:A+ – moderately exceeded expectation. / Revised since last Annual Review? Yes, the log frame was revised to reflect the current number of sub-counties in Gulu and Lira districts. At the design of the PCDP, Gulu and Lira districts both had 38 sub-counties. However, in the course of the implementation of the PCDP, Amuru and Nwoya districts were created out of Gulu district and Otuke and Alebtong districts were created out of Lira district. The net effect of the creation of more districts from the original Gulu and Lira districts was the reduction in the number of sub-counties in both districts. / Risk: Medium / Indicator 1.3: / Output Indicator 1.3 Baseline 2009 Milestone 2012 Achieved / Percentage of sub-counties with operational community-level project M&E tracking systems Planned 0 30% 100% (485/485) / Source: / World Bank NUSAF2 annual reviews / Progress against expected results (See Annex 1 for detail): / DFID contributes £2.2m ($3.5m) towards NUSAF2 administrative costs on delivery, of which M&E is a component. According to the NUSAF2 update received during this review period, all sub counties (485/485) have operational community-level project M&E tracking systems though not all share the same level of efficiency. The system (which is managed by Community Development Officers and NUSAF2 officers in the districts) tracks and analyses sub-project processes, outputs and intermediate outcomes at sub-project levels at the sub-county levels. While all community level tracking systems have been set up, only 75% of funded sub-projects have submitted their tracking reports to NUSAF2 directorate. / During the World Bank support mission in February, NUSAF2 technical team was tasked with strengthening all the tracking systems in order to increase the reporting rate from 75% to 85% by June 2013. Districts are being encouraged to allocate a percentage of their NUSAF2 operations funds to sub-project monitoring and tracking reports collation. However, a number of districts are arguing that NUSAF2 has not allocated sufficient NUSAF2 operations funds to them. / Recommendations: / Recovery Adviser and MDG team leader to set up a teleconference before end of May with the World Bank’s NUSAF2 Task Team Leader to resolve outstanding issue of operations funds. / Recovery Adviser to follow up regularly with the World Bank NUSAF2 Task Team Leader and NUSAF2 directorate on maintaining and strengthening the performance of the M&E tracking system. / Impact Weighting and Score:A+ – Moderately exceeded expectation. While the milestone for this year was substantially exceeded, the tracking system needs further strengthening for all sub-projects at both sub-county and district levels. / Risk: Medium / Revised since last Annual Review? N / Indicator 1.4: Percentage of respondents assessing that local government is responsive to community needs / Output Indicator 1.4 Baseline 2011 Milestone 2012 Achieved / Percentage of respondents assessing that local government is responsive to community needs Planned Acholi: 44% [M: 23%, F: 21%]; Lango: 44% (M: 22%, F: 22%]; West Nile: No data available; Karamoja: No data available. Acholi: 50%; Lango: 50% / West Nile (baseline): 53% [M: 26%, F:27%]; Karamoja (baseline): 47% [M: 29%, F:18%] Acholi: 55% [M: 28%; F:27%]; Lango: 53% [M:24%; F:29%]; / Source: / Advisory Consortium on Conflict Sensitivity / Progress against expected results (See Annex Seven): / This indicator is monitored by the Advisory Consortium on Conflict Sensitivity (ACCS) which conducts an annual peace and conflict impact (PCI) survey across northern Uganda. The indicator provides an assessment of people’s perception of improvements in local government responsiveness. The 2012 survey covered 3,982 respondents (1,963 male and 2,019 female). / According to the perception survey report of 2012, there is marked improvement in people’s perception of local government responsiveness to community needs - 11.6% in Acholi sub-region and 9.3% in Lango sub-region. Findings from the perception survey show that optimism around local government responsiveness to community needs centre around the participatory processes in local government planning structures and feedback mechanisms. The findings further indicate that these processes were particularly strong around PRDP infrastructure investments in schools and health facilities. DFID’s theory of change here is particularly hinged on NUSAF2 which takes a strong community engagement approach in the implementation of its sub-projects. / Notwithstanding the marked improvements noted in Acholi and Lango sub-regions in local governments’ responsiveness to community needs, in focus group discussions people referred to the fact that local governments still faced challenges of inadequate funding from central government and leakages of funds through corruption. / Recommendations: / It is difficult to attribute improvements in this perception indicator solely to DFID’s funding. This indicator should be moved to outcome level. Responsibility: Recovery Adviser. / With the finalisation of the 2012 PCI report, ACCS to expedite dissemination of key findings to key stakeholders. / The findings of the PCI report should be looked at together with the findings of the conflict analysis. This will be important for identifying critical practical challenges and policy dilemmas involved in supporting effective transitions from recovery to long term development in northern Uganda within the next two years. Responsibility: Recovery Adviser / Impact Weighting and Score: A – Outputs met expectation. / Revised since last Annual Review? No / Risk: Low

Output 2: The most vulnerable conflict-affected communities are rebuilt and empowered
Output 2 score and performance description: / B - Outputs moderately did not meet expectation / Overall Risk: Medium / Impact Weighting: 25%
Performance against specific indicators: / Indicator 2.1: Number of Especially Vulnerable Individuals (EVIs) and Persons with Special Needs (PSNs) lacking access to social services, shelter and livelihoods in areas to which they return, resettle or reintegrate / 2.1: Number of EVIs and PSNs lacking access to social services shelter and livelihoods in areas to which they return, resettle or reintegrate Baseline 2009 Milestone 2011 Achieved (2011) / 10,190 (total); 3,748 (M), 6,442 (F) 0 (all EVIs and PSNs resettled and provided with basic services) 0 (all EVIs and PSNs resettled and provided with basic services) / Source: UNHCR performance reports / Progress against expected results: / UNHCR’s resettlement and reintegration programme, which was fully funded by DFID, ended in December 2011. By that time all EVIs and PSNs previously living in camps had been successfully resettled and provided with shelter and livelihoods support. The final number of resettled EVIs/PSNs was 3,500. This was lower than the original estimate of 10,190 as many of the PSNs and EVIs had voluntarily moved out of the IDP camps prior to UNHCR starting this project. / Recommendations: N/A – this project ended in December 2011. / Impact Weighting and score: A – outputs met expectation / Revised since last Annual Review? No / Risk: Medium / Indicator 2.2: Number of labour hours worked on food/cash for work projects in Karamoja (attributable to DFID) / 2.2: Number of labour hours worked on food/cash for work projects in Karamoja Baseline 2009 Milestone 2012 Achieved / 0 28 million 23.9m / Source: WFP/NUSAF2 annual reviews / Progress against expected results (See Annex 2 for detail): / The purpose of the three year £14m World Food Programme (WFP) NUSAF2 livelihood Karamoja programme was to improve the access of 77,000 moderately food insecure households to income-earning opportunities and better socio-economic services. This programme was implemented by WFP and its 11 implementing partners across Karamoja. The June 2012 evaluation noted the following achievements of the programme: / WFP introduced, within a short space of time, a dramatic shift in the type of programming used in Karamoja at a very large scale providing livelihood and economic opportunities to 76,360 households – this reflected the move from free food distribution to other forms of programming: public works programmes (PWPs) and household income support programmes (HISP) / Roads and dams were the primary assets created by the public works component. Assets created provided employment opportunities, however the evaluation noted that the PWP programme reflected a series of disconnected projects rather than being based on and informing a local-level livelihoods strategy. / WFP’s operational capacity, significant credibility and relationships, and wide reach in the region enabled a rapid programme start up. The programme showed WFP’s ability to operate in a complex and challenging environment. There was a real sense of demand for the programme at both local government and community levels. / The programme was judged innovative with good quality targeting and an appropriate balance between food and cash. / Coordination between WFP, implementing partners and the local districts improved with time, although required further strengthening. / Notwithstanding the achievements, both food and cash transfers experienced delays, which undermined trust in the programme. It was also noted that WFP had few dedicated programme staff in Karamoja, and that the technical capacity of both WFP and their implementing partners required further strengthening. Also, the programme lacked attention to pastoralist livelihoods, the dominant form of livelihoods in Karamoja. / When assessed against the PCDP log frame the programme does not meet the cumulative target for the second year. However, the evaluation found that the original milestone was overly ambitious. When assessed against the targets WFP submitted at the beginning of year 2, the programme did meet expectations. Funding from PCDP for this programme ends this financial year. From next year, the programme will be rolled into the broader DFID ICF programme in Karamoja. / Recommendations: / Within the new Karamoja ICF programme, DFID needs to continue to engage with WFP to highlight the following issues: / the need for sharper focus, greater analytical and technical capacity, and increased attention to quality for their programming in Karamoja; / need for maintenance and/or sustainability measures for most of the assets created; / attention to pastoralist livelihoods / Responsibility: Climate Change Adviser / Impact Weighting and Score: B – Outputs moderately did not meet expectation. / Revised since last Annual Review? No / Risk: Medium / Indicator 2.3: Conditional food transfers received by NUSAF2 participating households in Karamoja (metric tonnes attributable to DFID) / 2.3: Conditional food transfers received by NUSAF2 participating households in Karamoja (metric tonnes, attributable to DFID) Baseline 2009 Milestone 2012 Achieved / 0 13,468 9,878 / Source: WFP/NUSAF2 annual reviews / Progress against expected results (See Annex 2 for detail): / This indicator is taken from the WFP livelihoods Karamoja programme (see 2.2). / When assessed against the PCDP log frame the programme does not meet the cumulative target for the second year. However, as with indicator 2.2, the evaluation found this milestone to be overly ambitious. When assessed against the targets WFP submitted at the beginning of year 2, the programme did meet expectations. WFP’s target for year 2 was 7,949 metric tonnes of food distributed, they exceeded this target and achieved 8,394 metric tonnes. However, since the targets are calculated cumulatively, the overall score is still a ‘B’. / Impact Weighting and Score: B– Outputs moderately did not meet expectation. / Revised since last Annual Review? No / Risk: Medium / Indicator 2.4: Number of additional consultations and treatments in PNFP health centres in Acholi region / 2.4: Number of additional consultations and treatments in PNFP health centres in Acholi region Baseline 2009 Milestone 2012 Achieved / 0 50,000 Not achieved. / The milestone is being revised. The final design of the programme focuses on Acholi as well as Lango sub-regions and on total consultations and treatments in 31 PNFP facilities. Therefore, during the annual review it was agreed to revise this indicator to “Number of consultations and treatments in 31 PNFP health centres in Acholi and Lango regions”, target and milestones numbers will be updated by July 31st 2013. / Source: NU Health reports / Progress against expected results (See Annex 4 for detail): / DFID contracted Health Partners International (HPI) and Montrose (referred to as NU Health) to design and manage a programme to incentivise improvements in health results through a results based financing (RBF) mechanism in northern Uganda. The purpose of this programme is threefold: / to improve the availability of essential medicines in PNFP facilities; / to improve the quality and quantity of services/consultations and treatments provided by PNFP facilities. / to test a new aid instrument (RBF)/a new way of financing private-not-for-profit (PNFP) health facilities; / The inception phase of this programme started in October 2011. During the inception phase (between October 2011 to July 2012), the NU Health team, in consultation with DFID, PNFPs, Ministry of Health and others, finalised the RBF design. Implementation started in July 2012 by DFID’s Innovative Aid Instrument Adviser. / In addition to NU Health, DFID has also hired the services of Liverpool Associates in Tropical Health, which is a part of the Liverpool School of Tropical Medicine, to carry out an independent impact evaluation of this programme. / To capture lessons, the PNFP facilities have been divided into a ‘treatment group,’ which comprises 21 PNFPs receiving financing through RBF mechanism, and a ‘control group’ which comprises 10 PNFPs receiving financing through the traditional ‘input based financing’ (IBF) mechanism. Payments to PNFP facilities in the treatment group are being made on a quarterly basis to reward improvements to the quality and quantity of maternal and child related health care. The first annual review of this programme was done in November 2012. It noted the following achievements and challenges: / A contextually sensitive and technically sound Results Based Financing (RBF) design has been developed and implementation initiated; / The programme design has separated the roles and responsibilities of purchaser (the NU health), provider (health facilities), the verifier (the District Health Teams) – this has improved accountability; / All 31 PNFP facilities are receiving essential medicines. Overall progress of the programme appears good, although it is too early to draw any conclusions on the success of the programme. Initial responses from PNFP facilities look promising, with clear attempts by the facilities to improve results. The Government of Uganda is very interested in the pilot, and is considering ways to expand the pilot beyond the private sector in the future. / There are some behavioural changes at PNFPs with some actively considering new ways to attract patients, including dissemination of information and reduction of user fees for key services; / The NU Health team has managed to secure buy-in from the District Health Teams into the concept of results based financing and has trained them in verification; / The Impact Evaluation design looks technically sound and the baseline survey has been completed. However, it primarily focuses on impact. It will be useful to find a way to the assess process of developing this programme in order to understand the strengths and weakness of the new aid instrument (RBF). Because this is a pilot programme, DFID is interested in learning how the aid modality is changing behaviours and processes. / The double layers of management and budgeting by HPI and Montrose make it difficult to isolate intervention cost from the support and management costs. The HPI/Montrose’s Milestones/Benchmarks could be revised to clearly distinguish between these costs which will help in undertaking the value-for-money analysis. Procurement Group (PrG) is currently re-negotiating the milestone and overall costs of the programme and this process is expected to be concluded by end of July 31st 2013. / The log-frame of the NU Health programme needs to be revised to reflect the final design. Also, the PCDP log frame indicators against which the NU Health programme is to deliver are not aligned. / Recommendations: / PCDP log frame indicators against which Northern Uganda Health is measured need to be reviewed and revised in order to bring them into line with current NU Health programme objectives and ensure consistency throughout the PCDP programme by July 31st 2013. Responsibility: Health Adviser / A quality indicator such as “the average quality score achieved by the RBFPNFPs improves by X%” should be added to the PCDP log frame so that the programme measures both quality and quantity. The baseline will be finalised at the end of July 31st 2013. Responsibility: Health Adviser / Impact Weighting and Score: B – Output moderately did not meet expectation. The overall Annual l Review for this project assessed the project as on track and gave it a scoring of an A+. The review highlighted positive progress. The programme design is sound with a lot of upfront work done with in-depth engagement across DFID and other stakeholders and a growing demand for the programme in both PNFP and public health facilities. However the project did not meet the milestone in this PCDP log frame. / Revised since last Annual Review? No / Risk: Medium

Output 3: The private sector is revitalised and accessible employment opportunities are created
Output 3 score and performance description: / B – Moderately did not meet expectation / Impact weighting: 25%
Performance against specific indicators: / Indicator 3.1: Number of applications for small grant scheme received and approved / 3.1 Number of applications for small grant scheme received and approved Baseline 2009 Milestone 2012 Achieved / 0 1200 (received) / 800 (approved) 363 (received) / 273 (approved) / PSFU management records / Progress against expected results (see Annex 5 for detail): / The purpose of this grants scheme programme is to support the creation of new businesses and jobs and the expansion of existing small and medium scale enterprises through grants and business advisory services. Grant support is given to business enterprises to enable them pursue the right investment opportunities in a region recovering from conflict. While managed by OPM, the programme was being implemented by Private Sector Foundation Uganda (PSFU), a non-government institution. The budget for the programme is £13m. The Annual Review was conducted in October 2012 by a DFID Economist from London. / In terms of the programme performance against its log frame, the scheme did not deliver the anticipated results. The start-up of the grants scheme was slow because of PSFU’s limited outreach to the various sub-regions in the north and the scheme’s pre-financing methodology that limited access to a few business enterprises (this issue was rectified only after the annual review in 2011). The Annual Review also found that PSFU is not able to perform the role of financial outreach institution - PSFU lacks the necessary expertise to evaluate grant proposals effectively, handle asset transfers or monitor grants’ effectiveness. Thus, PSFU’s ability to make a long-lasting contribution to financial sector deepening was judged as questionable thus the management of the scheme will be transferred to a new service provider. / The Annual Review noted the following progress and challenges: / Figures showed that in the months preceding the period of Annual Review (October) the rate of grant approval had increased by 65% due to improved outreach and upfront payment of grants rather than the pre-financing reimbursement method, which had previously required all businesses to make a 40% up-front contribution towards total costs in order to access grants under the scheme. This approach had limited the number of beneficiaries who could access grants under the scheme either due to lack of finance or the inability of a business enterprise to access credit to implement activities. / As a result of the 2011 Annual Review recommendation, a new approach was developed for accessing grants under the scheme. In the new approach, PSFU would make upfront payments of grants and a business enterprise made a percentage contribution depending on the nature and size of the business. This approach promoted flexibility in beneficiaries’ contributions as it made it easier for businesses to access the grants under the scheme. Adjustments in eligibility criteria resulted in the programme gaining considerable momentum since April 2012 in terms of increasing the number of applications. The number of approved applications increased in six months (April to October 2012) from 124 to 351. / The scheme had been careful in assessing and supporting activities in sub-regions most affected by conflict (that is, Acholi and Lango sub-regions). This was important given the political sensitivity across northern Uganda that more support needed to go to business enterprises in areas most affected by conflict. / The Annual Review noted that disbursement delays of funds from OPM to PSFU affected project implementation and further found that PSFU was not systematically checking how money was being used or whether equipment/services which were purchased were being used for the intended tasks. The result was that there were mixed reports from beneficiaries about the effectiveness of PSFU. / PSFU did not have a clear methodology on how to count direct jobs, nor were jobs disaggregated by gender/sector or as skilled/ unskilled in the log frame. / The Annual Review also pointed out that there were risks that the provision of the grants could crowd out the private sector. While PSFU was tasked to look at business viability as a key criterion for providing grants to enterprises, PSFU work was also to be complemented by the deeper analytical study through the Economic Recovery Analysis, which was delayed due to poor performance of the original implementer. DFID contracted Oxford Economics to finalise the Economic Recovery Analysis. It will be published by August 2013. / Funds to PSFU via OPM were suspended following OPM corruption scandal, which resulted in DFID commissioning a forensic audit of UK aid provided to OPM. The audit found only minor irregularities with PSFU. Since the suspension and freezing of UK aid, PSFU have accumulated over £3m of contractual obligations and liabilities for grants approved (resulting from client agreements, commitments on goods and services consumed, project running costs and staff salaries) prior to the financial aid freeze taking effect. DFID is planning to re-route support to PSFU from OPM to a direct Accountable Grant to allow PSFU to meet liabilities. Once these liabilities are met, the management of the grant scheme will be passed onto the new service provider (KPMG) as part of a new, wider Financial Services programme DFID Uganda is implementing. KPMG will need to review the suspended grants scheme model in order to assess whether or not it is a good model for generating new businesses and jobs and then make the necessary changes to refine the model. / Recommendations: / DFID should ensure KPMG works with PSFU to handle the large backlog of existing grant applications. This would mean using PSFU’s networks, presence and reputation in the north, but with the assurances of an experienced financial service provider to ensure technical competence in the area of financial deepening. Responsibility: Economic Adviser. / KPMG to do a fast track assessment of current model of the grants scheme in terms of whether or not it is a good model for generating businesses and creating jobs, revise and refine the model including the possibility of identifying a financial institution for providing grants to businesses in the north, and review PSFU’s function within the revised model. Responsibility: Economic Adviser. / Impact Weighting and Score: C – outputs substantially did not meet expectation. / Revised since last Annual Review? No / Risk: Medium / Indicator 3.2: Jobs created (number of new job opportunities) / 3.2 Jobs created (number of new job opportunities) Baseline 2009 Milestone 2012 Achieved / 0 2500 2004 direct / (52, 299 indirect jobs) / PSFU management records / Progress against expected results (see Annex 5 for detail): / This indicator is part of the PSFU logframe. / According to the Annual Review, as of September 2012, 2004 direct jobs were created by the grants scheme and 56,299 indirect jobs created which was calculated by looking at the MoUs between businesses and out growers and the number of people employed in the distribution and transportation of products/goods. However, the understanding of the indicator above was that it referred to direct jobs created. All the same, the Annual Review is clear that PSFU does not have a clear methodology for counting jobs nor are the data disaggregated by gender/sector/skilled vs unskilled, making the value of this indicator questionable. / Recommendations: / KPMG as the new management agent of the grants scheme to develop a clear and robust methodology for counting direct and indirect jobs created under the scheme. Responsibility: Economic Adviser. / Impact Weighting and Score: B – Outputs moderately did not meet expectation / Revised since last Annual Review? Yes. The 2011 Annual Review suggested adding ‘jobs created’ as an indicator to replace ‘investment leverage.’ The log frame was revised to reflect direct jobs created. / Risk: Medium / Indicator 3.3: Number of youth trained by DFID-funded programmes in targeted vocational and micro-enterprise skills / 3.3 Number of youth trained by DFID-funded programmes in targeted vocational and micro-enterprise skills Baseline 2009 Milestone 2012 Achieved / 0 30,000 (≥10,000F) 11,460 (3,896F) / NUYDC management records / Progress against expected results (see Annex 6 for detail): / The purpose of this programme is to train 100,000 youth across northern Uganda by 2015 through literacy, vocational skills and apprenticeship programmes with the aim of helping them find employment. Through this programme DFID, working together with the Government of Uganda, aimed to support the Northern Uganda Youth Development Centre (NUYDC) to become a centre of excellence and best practice in high quality vocational training. The original vision was for NUYDC to become the ‘hub’ for a wider network of Vocational Training Institutions (VTIs). The budget for the programme is £12m. The review of this programme was carried out by DFID’s Social Development Adviser from London who was accompanied by DFID Uganda’s Social Development Adviser. / The findings of the Annual Review indicated that publicity around the training courses at NUYDC and through the VTIs network deliberately targeted marginalised and conflict-affected youth, in line with their mandate. NUYDC made active efforts to recruit girls and women, in order to meet the target of 30% female students. However, despite encouraging girls to apply for training, no consideration was given to the specific constraints or opportunities for girls and women in terms of their being able to access and benefit from relevant training courses. While the ratio of young women enrolled increased, they were channelled to traditional and relatively low-value vocations. Furthermore, while there was an on-site counsellor at NUYDC, other VTIs provided only one or two short sessions on life skills and/or conflict resolution – although these issues were meant to be systematically addressed according to the programme principles and conception. Also, while the training curricula included health talks, there was no systematic effort to provide reproductive health information and/or family planning support. Hidden costs, such as for uniforms, might have been a disincentive for the poorest young people to access or persist in training. / The implicit theory of change underlying the NUYDC saw youth unemployment being defined as the problem and being driven fundamentally by a deficit of job-relevant skills. The war in the north was seen as a major disruption to young people gaining basic education and job-relevant skills and this has resulted in a dearth of skilled workers to meet the labour demand needs of a resurgent regional economy. By providing youth with basic and technical skills in traditional occupations, the NUYDC saw itself as aspiring to create new jobs for youth. The reality in the north, however, is much more complex, with youth under-employment, not unemployment, being the predominant problem, whilst the resurgence of the regional economy has not taken place as quickly as originally anticipated. The drivers of youth underemployment include a lack of labour demand, job-search constraints, low levels of firm start-ups, poor infrastructure and certain social constraints on labour supply, which all lie beyond the current scope of the NUYDC interventions. / In terms of assessment against the PCDP log frame, the centre remained significantly off-track to reach the target of 100,000 youth with relevant skills training and the centre continues to present technical, institutional and post-project sustainability concerns. The Annual Review also found that NUYDC was providing minimal support to its graduates to secure employment or exploit opportunities for enterprise. / NUYDC was managed and overseen by OPM. All funds were frozen when funds in OPM accounts were frozen. NUYDC was audited as part of the forensic audit. The findings showed that NUYDC’s accountabilities exhibited poor financial recording and documentation, price inflation, and often did not add up or contained unusual transactions. / DFID’s support for NUYDC has been stopped on the basis of the management and financial issues noted above. DFID funds are being reprogrammed so that youth development programme in north will be delivered through VSO and Youth Business International through its partnership with Enterprise Uganda. The GoU, through the Minister for Northern Uganda, has agreed to take on full responsibility for NUYDC. / Recommendations: / The theory of change and activities that characterised the work of Northern Uganda Youth Development Centre (NUYDC) were narrowly conceived and failed to address wider constraints to transitioning young people into productive employment (self-employment and paid employment). Moving forward, a future youth development programme needs a good theory of change around how to help young people into employment by going beyond simple vocational skills training to address wider economic, social and psychological barriers. Responsibility: Social Development Adviser. / Indicator to be revised in light of reprogramming through new delivery channels (Youth Business International/Enterprise Uganda and VSO) for the programme. Responsibility: Social Development Adviser. / The Economic Recovery Analysis (which is an analytical study of the north’s comparative advantage, current and potential markets and barriers to its economic growth) findings need to be linked up with reprogrammed youth training in northern Uganda. The economic recovery analysis is due to be completed in June 2013. Responsibility: Economic Adviser. / Impact Weighting and Score: B – output moderately did not meet expectation. In terms of the set target for the year under review, the programme substantially did not meet the set milestone. At the same time, it must be acknowledged that the programme started from a very low base of inadequate and poor infrastructure and very limited staffing. Given the low base from which the youth development programme started, the score given recognises that a lot of progress was made over the last one year in fully setting up the centre (both in terms of infrastructure and human resource) to the operational level of a vocational training institution, contractor and manager of grants for forty two Vocational Training Institutes (VTIs). Also, the programme trained twice as many youth as in 2011. / Revised since last Annual Review? No / Risk: Medium / Indicator 3.4: Percentage of respondents perceiving they have access to increased economic opportunity / 3.4Percentage of respondents perceiving they have access to increased economic opportunity Baseline 2011 Milestone 2012 Achieved / Acholi: 32% [M: 16%, F:16%]; / Lango: 27% [M: 13%, F:14%]; / West Nile: No data available; / Karamoja: No data available. Acholi 42% / Lango 37% / West Nile (baseline): 24% [M:14%, 10%]; / Karamoja (baseline): 19% [M:14%, F:5%] Acholi: 45% [M:24%, F:21%]; / Lango: 41% [21%, 20%]; / ACCS annual PCI reports / Progress against expected results (see Annex 7 for detail): / This indicator is monitored by the Advisory Consortium on Conflict Sensitivity. For background information on the consortium see comment under indicator 1.4 above. / During 2011, baseline data was gathered for Acholi and Lango sub-regions. / Recommendations: see for indicator 1.4 above. / Impact Weighting and Score: A – Outputs met expectation. / Risk: Medium / The purpose of this indicator is to show whether investments under PRDP to which PCDP contribute are expanding economic opportunities for people across the north. The indicator also assesses whether or not long-term patterns of social exclusion in the economic sphere are being addressed as a result of the interventions under the PRDP/PCDP. / According to the 2012 PCI report, people perceive there to be strong potential and expanding opportunities in agricultural sector across northern Uganda due to availability of land and favourable livestock and crop husbandry conditions. However, according to focus group discussions conducted people noted that access to economic opportunities were impeded by lack of money to save and failure to access credit, laziness/alcohol drinking, and lack of qualification/employable skills together with discrimination in formal and informal employment. In Karamoja sub-region, there is also the additional constraint of high transaction costs associated with poor infrastructural development. This indicator is important because DFID is a major bilateral donor to Northern Uganda with interventions in key areas of education, health, local government, youth development, livelihoods and private businesses, and peace building. / Revised since last Annual Review? No

Output 4: Government, civil society and communities can engage actively in peacebuilding and reconciliation
Output 4 score and performance description: / A – outputs met expectation / Impact weighting: 25%
Performance against specific indicators: / Indicator 4.1: Number of PRDP interventions and systems modified to take better account of conflict analysis / 4.1 Number of PRDP interventions and systems modified to take better account of conflict analysis Baseline 2009 Milestone 2012 Achieved / 0 5 5 / Through ACCS participation in the technical working group, PRDP M&E framework adopted the PCI indicators; conflict sensitive training offered to NUYDC; and Lira, Gulu, and Amuru DLGs led to improved conflict sensitive plan ning. / ACCS annual PCI report / Progress against expected results (see Annex 7 for detail): / This result is monitored by the ACCS. The purpose of the consortium is to strengthen the ability of key stakeholders in the DFID Post Conflict Development Programme for Northern Uganda to effectively address the drivers of conflict and contribute to building peace through their interventions. The mandate of the consortium is to make PCDP conflict sensitive and in so doing make PRDP achieve peace building aims. In fulfilling this mandate, the consortium carries out an annual perception survey on peace and conflict impact of PCDP/PRDP across the northern Uganda, and conducts research, public dialogues and radio programmes on a number of thematic issues. The programme budget is £2.8m. The Annual review of the programme was done by an independent consultant contracted by DFID Uganda. / According to the Annual review, the programme achieved momentum in 2012 after a relatively slow progress in 2011. Outcome achievements made include the following: / The consortium made substantial attempts to engage more effectively with PCDP/PRDP stakeholders during 2012 with some success, particularly at district levels. The consortium’s conflict sensitivity assessments of PCDP partners led to the development of capacity building assessment tool. This tool can be used to assess new programmes partners for their conflict sensitivity. / The consortium’s engagements with Local Governments in the north have resulted in increased responsiveness and engagement by district local governments of Nwoya, Amuru, Gulu, Zombo and Lira on land and natural resource conflicts through research, training in conflict-sensitive approaches, community and stakeholder dialogues, and radio programmes. The responsiveness of the Local Governments have helped reduce tensions and initiated some meetings and dialogues among communities in these districts in relation to some conflicts. In view of this outcome, the Annual Review notes that the influence of the consortium was stronger at the local levels than at the national level. / During 2011 the consortiums had limited engagements with OPM, but in 2012 concerted efforts were made by the consortium to improve contact and interactions. These attempts begun to bear fruit through OPM’s acceptance of the consortium’s products at the PCDP steering committee and PRDP technical working group meetings and OPM’s willingness to share information with the consortium until the corruption scandal in OPM constrained further meaningful engagement. / The inclusion of International Alert’s peace and conflict impact (PCI) indicators into the PRDP2 M&E framework is an important achievement which has the potential to make government more accountable to the people. However, due to the corruption scandal the future of PRDP2 remains uncertain. / The consortium provided training on conflict sensitive approaches for local government staff, as well as staff from PSFU and NUYDC. The Annual Review judged that the training and mentoring support led to greater consideration of conflict drivers and risks in planning processes and service delivery and have helped improve effective working relationships and tensions within district local government teams. / The conflict analysis conducted by the ACCS was credible and comprehensive, which has the potential to fill a significant analytical gap at the national and sub-regional level in terms of government, civil society and development partner discourse and understanding of conflict drivers across the greater northern Uganda. However, the finalisation of the conflict analysis is significantly delayed. / However, while the consortium tried to cover a lot of issues through field research, community dialogues, and radio programmes during 2012 this coverage in itself also undermined the consortium’s ability to focus and do in-depth work on the relevant issues. / Against its project log frame the programme achieved three of its targets and partially achieved seven. Partial achievements are due to the incomplete nature of the products of the consortium especially the conflict analysis report and the peace and conflict impact reports at the time of the review. Against the PCDP log frame, the programme achieved its milestones of conducting a survey of community perceptions across all the PRDP sub-regions and also influenced interventions. Also, output indicator 4.1 needs to be reviewed in light of the aid suspension to GoU that has affected delivery of PRDP. / The Annual Review makes an observation that the overall performance of the consortium needs to be seen against the assumptions of continual delivery of the PRDP/PCDP which has now been impacted by the OPM corruption scandal and the consequent suspension of financial aid to GoU in November 2012. During the latter half of 2012 the OPM corruption scandal affected the consortium’s dialogue and work with the OPM and with other PCDP partners whose activities/programmes were suspended. / Recommendations: / In line with the recommendations of the larger review, ACCS will review their workplan and priorities for the next two years. They have agreed to focus on fewer issues, which they will work on collectively to ensure greater impact. The consortium will finalise their logframe and work plan by 30th June, 2013. Responsibility: Recovery Adviser. / The consortium needs to urgently finalise and publish its conflict analysis by 30th June 2013. Responsibility: Recovery Adviser. / Key findings from the perception survey report to be further considered in light of the conflict analysis. Common key issues emerging from both to be prioritised. Responsibility: Recovery Adviser. / 4. In view of OPM corruption scandal that has affected the normal implementation of PRDP, this indicator needs to be reviewed. Since this indicator is also the same as the ACCS outcome indicator, ACCS log frame to be reviewed and aligned accordingly by 30th June, 2013. Responsibility: Recovery Adviser. / Impact Weighting and Score: A – Outputs met expectation. Even though this specific target was met, the ACCS failed to deliver on a number of other outputs on time, including the PCI and conflict analysis reports, which were subject to significant delays. In addition, a number of relevant activities were not sufficiently coordinated. / Revised since last Annual Review? No / Risk: Medium / Indicator 4.2: Progress of parliamentary legislation on reconciliation / 4.2 Progress of parliamentary legislation on reconciliation Baseline 2009 Milestone 2012 Achieved / No legislation proposed Parliamentary debate on National Reconciliation Bill Draft transitional justice policy shared with JLOS and being discussed by the Parliamentary Committee on defence and internal affairs. However, the draft bill has not yet reached the stage of parliamentary debate. / Parliamentary records/Greater Northern Parliamentary Forum / Progress against expected results (see Annex 8 for detail): / This indicator is drawn from the Rights, Justice and Peace (RJP) component of the Democratic Governance Facility (DGF), which is a multi-donor basket fund. The purpose of this £2 million programme is to support civil society organisations to engage in dialogue, at local and national levels, on peace building and transitional justice as well as to work with Government of Uganda on the development of policy and legislation. The programme was reviewed by two DFID Uganda programme officers. / According to the Annual Review, the programme made some significant progress over the last year through support given to civil society organisations and government agencies or institutions. Achievements made include the following: / Refugee Law Project (RLP) presented the draft of the National Reconciliation Bill to the Parliamentary Committee on Defence and Internal Affairs. The committee is examining the draft and considering ways of bringing the bill to the floor of the Parliament. This step represents a significant progress given that prior to 2012 there was no mention of this bill within Parliament. / Civil society organisations supported by the DGF held regional consultations on transitional justice in Soroti, Kasese, Gulu and Lira. These consultations raised awareness in different regions on the national transitional justice processes. Civil society organisations in Kasese and Soroti initiated regional transitional justice platforms. / As part of their transitional justice and peace building efforts a) RLP provided psycho-social support to conflict victims and carried out a mapping of categories of violations in order to inform transitional justice healing processes; b) Centre for Women in Governance (CEWIGO) organised the National Peace Exposition in Lira in November and December 2012 that highlighted the role of women in peace building and security. Several policy makers, civil society organisations, local governments and other key actors attended the occasion. / When assessed against the DGF’s own log frame, it is too soon to score the performance of this project as their first targets were set for December 2013. Preliminary findings during this review period show that out of ten indicators, DGF met one target under output 1, exceeded two targets under output 2 and achieved its target under output 3. Data for five indicators will only become available by December 2013. / When assessed against the PCDP log frame the programme has made progress and partially achieved the set target. The draft national reconciliation bill was submitted to the parliamentary committee on defence and internal affairs. However, this is a sensitive area and clearly factors beyond the remit of the programme can significantly influence delivery. / Recommendations: / Indicator 4.2 needs to be revised and aligned with the DGF component 2 log frame in order to link directly DGF support to interventions with set results. The proposed new indicators are: Number of Women and Men reached by legal aid service provision offered by DGF; Level of satisfaction of war affected communities with both formal and informal transitional justice processes. / Impact Weighting and Score: B – Outputs moderately did not meet expectation. Milestone not achieved but substantial progress made towards peace building and reconciliation despite late start of programme. / Revised since last Annual Review: No / Risk: Medium / Indicator 4.3: Proportion of respondents perceiving a decrease in levels of competition and grievance between PRDP regions and between north and south / 4.3 Proportion of respondents perceiving a decrease in levels of competition and grievance between PRDP regions and between north and south Baseline 2011 Baseline 2012 Achieved / No data available Acholi: 34% [M:18%; F: 16%]; / Lango: 40%% [M: 21%, F:19%]; / West Nile: 34%% [M:19%, F:15%]'; / Karamoja: 30% [M: 20%, F:10%] Achieved. As recommended by the 2011 AR, the target for 2012 was the establishment of baseline data, which was achieved. / ACCS PCI annual reports / Progress against expected results (see Annex 7 for detail): / This indicator is monitored by ACCS. The purpose of this indicator is to show that development interventions under the PRDP are having an impact in terms of promoting national harmony. This indicator is important because of the north-south divide and sub-regional tensions and grievances that were often key drivers of previous armed conflicts in Uganda. The assumption is that DFID’sPCDP interventions in key areas of education, health, local government, youth development, livelihoods and private businesses, and peace building are contributing to improved perceptions of peace and harmony in the north and nationally. / Last year no data was available for this indicator. In accordance with the 2011 Annual Review, the data for 2012 will form the baseline for this indicator. / According to the peace and conflict indicators survey report, across the PRDP regions, 34.2% of all respondents reported that there was a decrease in competition and grievance between their region and other PRDP regions. / In terms of drivers of competition and grievances between PRDP regions focus group discussions’ respondents referred to levels of business activities, coverage and/or proximity to a main tarmac road, better health care facilities, and the presence of many schools. These indicators were also seen as very much affected by effects of war and displacement (especially in Acholi, Lango and Teso sub-regions), corruption, unfair resource allocations and bad leadership. In Lango sub-region there was particularly strong feeling that Acholi sub-region was preferred to them, with Gulu district being singled out as the biggest beneficiary of the recovery efforts in the North. This sub-regional tension is important to take note of because it previously led to the overthrow of Obote’s government in 1985 through a military coup that was in turn overthrown by the National Resistance Movement (NRM) in 1986. / People in Karamoja perceived themselves to be particularly disadvantaged, especially as a result of remoteness and hardships associated with the terrain and climate. Also, the sub-region saw itself as significantly lacking adequate infrastructure / Impact Weighting and Score: A – Output met expectation. The first set of data available in 2012 is a baseline for the indicator. However, the results from the first survey are encouraging. Indicator remains relevant because perceptions of people are important for national peace building initiatives and efforts. / Revised since last Annual Review? No / Risk: Medium

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y/N / Yes. However, not all indicators could be updated as some data were not available. / Outcome Indicators: / The programme outcome statement is: Increased economic, social and political opportunities that improve the lives of people affected by conflict in northern Uganda / The three outcome indicators are: / Proportion of U5s with fever receiving malaria treatment within 24 hours (PRDP districts). Source: HMIS / MoH Annual Health Sector Performance Report / Number of trained young people retained in formal employment for six months or more (attributable to DFID). Source: Youth development programme annual tracking surveys / Level of satisfaction among targeted population with quality of basic socio-economic services[disaggregation by gender to be requested from NUSAF2 data]. Source: NUSAF2 / Community Score Cards - 6 monthly survey / These indicators could not be updated during the Annual Review. Several reasons account for this fact: / The health outcome indicator 1 is a higher level indicator beyond the health intervention under the PNFPs, which is more restricted to central northern Uganda, covering Acholi and Lango sub-regions. Besides, the way the Ministry of Health disaggregates its data makes it impossible to measure health data for PRDP districts as a whole. Furthermore, OPM could not provide the relevant data for PRDP districts on health. / NUYDC was unable to put in place a tracking system to measure outcome indicator 2. / For outcome indicator 3, NUSAF 2 community score card study is not complete and the findings are not yet available. Study expected to be completed by June 2013. / Outcome indicators 1 and 2 will be revised to measurable indicators that can be delivered through the Northern Uganda Health programme and the reprogrammed youth development programme which will be delivered by VSO and Youth Business International. Outcome indicator 3 will be maintained as it is also one of the World Bank Key Results Indicator (KRI) under NUSAF2. / Output Indicators: / Output indicator 1.2: log frame indicator for work with local governments was revised to reflect the drop in the number of sub-counties in Gulu and Lira districts from 38 to 21. / Output indicators 1.4, 3.4, and 4.3: Milestone targets for Acholi and Lango sub-regions now set for the remaining years of the programme. Baseline data for West Nile and Karamoja sub-regions only became available this year. / Output Indicator 3.2: 2011 Annual review suggested ‘jobs created’ as an indicator to replace ‘investment leverage’. The log frame was revised accordingly. / 1.2 Overall Output Score and Description: / B – Outputs moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / A number of direct beneficiaries from various components of the PCDP were interviewed as part of the annual review process. / On the ULGA project, representatives from lower tier local governments said: ‘We are benefiting greatly from the program, especially the district resource pools, the Technical Assistance to the Chairperson and the Savings and Credit Co-operative Initiative’; ‘The TA role has helped coordinate the activities of the district given that the clerk to council is very busy’; ‘Mentoring of LLGs through the DRP is a good thing.” / At district level the work of ACCS is well known and has been positively received by those that they have interacted with them. A number of the Consortium’s information products – in particular the radio programmes - have generated significant debates and interests at both community levels and with decision makers. Training provided on conflict sensitive approaches (CSA) has been well received particularly by Local Government partners. / There were mixed reports from beneficiaries about the effectiveness of PSFU. In some instances the feedback was excellent, whilst others pointed to long delays taking on average four months from submission to approval while some beneficiaries waited for more than a year and often with no information. This is in part due to PSFU’s thorough approach to assessing applications against the checklist. / Direct feedback from current beneficiaries at NUYDC and five of the VTIs suggested that trainees on a number of courses have already been able to secure temporary work on the basis of the skills they are learning. This is most true to motorcycle mechanics, masonry/block-laying and electrical installation. Former graduates suggest that their employment prospects and willingness to start their own businesses were generally boosted by the exposure to local businesses during the training. / 1.4 Summary of overall progress / The overall progress of the PCDP has been disappointing and progress has been very mixed, with better progress in humanitarian, recovery and livelihoods initiatives (such as the UNHCR and WFP programmes) than in longer term development programmes (NUSAF, PSFU and NUYDC) which have all suffered from problems with poor design, slow progress and delays in funds disbursements. Some of the smaller, experimental initiatives, such as the ULGA programme, have yielded interesting results which may warrant scale up. / Of all the four PCDP outputs, outputs 1, 2 and 3 did not meet expectation while outputs 4 did meet expectation. The reasons why some components did not meet expectation include the following: / poor programme design and overly ambitious milestones(PSFU, NUYDC, WFP); / slow start up and implementation (ACCS, NUSAF2, DGF); / the impact of the OPM corruption scandal and subsequent aid suspension (PSFU, NUYDC and, to an extent, ACCS). / The context in northern Uganda is changing significantly from post-conflict recovery to long term development as people have moved from internally displaced people’ camps to their villages. However, northern Uganda is still largely marginalised and poor, with poverty rates almost twice the national average, and remains a priority for development assistance. Going forward, the nature of programmes and delivery channels will need to adjust to this transition from recovery to development.
1.5 Key challenges / Initially, PCDP was designed to deliver results quickly and at scale within emergency and recovery contexts in northern Uganda. However, the fast changing contexts in northern Uganda from emergency to recovery and development means that the six remaining components of PCDP need to be re-oriented. / The corruption scandal within the Office of the Prime Minister (OPM) of 2012 disrupted the implementation of the grants scheme and youth development programme that were managed by OPM. These programmes will be re-oriented and implemented outside of the Government of Uganda systems. The corruption scandal and the forensic audit process which followed has highlighted the need for greater vigilance in the management of any financial aid to the GoU. / On several fronts, implementation of programme components was slower than expected or had late start up. NUSAF2, the youth development programme and grant scheme, DGF and northern Uganda health components of the programme exhibited slower pace of implementation than initially envisaged. The PNFP and DGF components of the programme only became fully operational in 2012. The youth development and grant scheme components of the programme that were being managed by OPM also experienced delayed funds disbursements. For NUSAF2, the WB’s processes were also very slow, partly due to the robust processes for ensuring accountability (learning from the lessons of NUSAF1, which suffered a significant corruption scandal). These processes, though burdensome, are necessary to give the WB and us assurance that our funds are not being misused. / Another issue is the relevance of the current log-frame and targets. A number of developments since 2010 (e.g. experience of implementing the WFP NUSAF2 project in Karamoja, design of the PNFP project to build in a results-based financing pilot) have meant that the log-frame is now out of date and needs to be reviewed. / Perhaps the most significant challenge to effective delivery of the results expected from PCDP is the design of the programme. One summary logframe covers 22 different projects. While each project should ultimately contribute to recovery in northern Uganda, monitoring each project against the overarching log frame has proved to be a significant task and co-ordination and complementarity between each project has been challenging. A clear lesson for the future is to have tighter monitoring, closer engagement with fewer projects which can be clearly linked to one robust theory of change.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / The programme was on track against this year financial forecast until the OPM corruption scandal which led to freezing of DFID funds for the grants scheme and youth development programme and the termination of the technical support to OPM. However the suspension of financial aid to Government of Uganda means PCDP will significantly under-spend for the financial year 2013/2014 as the youth training is reprogrammed, the grants scheme is rolled into the upcoming financial services programme, and proposed PRDP budget support for northern Uganda will not go ahead. Programme spend and balance stand as follows: / Spend: £53,351,306 / Committed: £37,164,242 / Unprogrammed: £10m to be returned to the centre. / See annex at the end of this Annual Review report for programme spend from 2009 to 2012 and the forecasts for the remaining components of the programme for the next two years. / 2.2 Key cost drivers / The major costs drivers are consultant fees, management fees, training, staff costs, office administration overheads, travel expenses, programme evaluation costs, conferences, and research costs. / 2.3 Is the project on-track against original timescale: No / Results are mixed. As noted elsewhere, a number of PCDP components had slow start up and implementation: ACCS, youth development programme, grants scheme, economic recovery analysis, advisory consortium on conflict sensitivity, and NUSAF2. Two components of the programme had late start up: health work with PNFPs and peace building and reconciliation work through DGF. Four components of the programme started on time: resettlement and reintegration of EVIs/PSNs with UNHCR, Karamoja livelihoods programme, capacity building of the Local Governments of Gulu and Lira districts, and technical support by PWC to OPM. Of the various components of the programme, the grants scheme and youth development programme have been off track in terms of set targets. The reasons for this are: a) slow start up of programmes; b) weak institutional capacity of NUYDC and PSFU to effectively implement their components of the programme, c) delayed disbursement of funds from OPM to NUYDC and PSFU which affected implementation of programmes. / With the review of the targets for a number of the components of the programme and the reprogramming of the youth development programme within the next financial year 2013/2014, the programme will be able to meet its objectives by programme completion date.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Evidence here relates to changes in conditions in northern Uganda and PCDP delivery models. / Evidence on conditions in the North: While according to UBOS National Household Surveys, poverty in northern Uganda has dropped from 60.7% in 2005/6 to 46.2% in 2009/10 the region continues to remain marginalised and is still the poorest part of Uganda as compared with the national poverty average of 24.5% (Year 2009/10). At the same time, the living environment in northern Uganda has changed from emergency to recovery and long term development as people moved from internally displaced peoples’ camps to their villages. Because northern Uganda is still marginalised and poor, programme interventions still remain relevant but different in that the region needs more long term development interventions than humanitarian interventions. The context and evidence of need that originally informed the development of the PCDP programme has not changed even though people’s living environments in which programme interventions are being delivered have evolved. / Evidence on delivery models: In terms of what works and what does not work, evidence has come to light that there is high fiduciary risk in delivering components of the programme through GoU systems. OPM corruption scandal exposed serious fraud within GoU systems. Also, question has arisen in regard to the credibility of technical assistance given by PWC consultants to PS OPM and PSFU’s technical capacity to effectively deliver the grants scheme for financial services deepening. / 3.2 Where an evaluation is planned what progress has been made? / A formative evaluation of the WFP Karamoja livelihoods programme was undertaken last year. According to the evaluation, despite challenges in operational capacity and delays in food and cash distribution, WFP introduced a dramatic shift from free food distribution in Karamoja to income-generating activities for 76,360 food insecure households. The evaluation findings also highlighted that public works programmes reflected more of a series of disconnected projects rather than being based on and informing a local-level livelihoods strategy. / A fully independent impact evaluation of the PNFP component of the programme is being carried out by the Liverpool Associates of Tropical Health (LATH). While the quality of outputs thus far is high, the EvD focal point on Payment By Results (PBR) has recommended that DFID Uganda encourage LATH to find ways to further explore the process of change in the intervention. This could be situated around the Theory of Change. Furthermore, the EvD focal point further recommended that the examination of the Theory of Change should include analysis of identified risks and unintended consequences. It is additionally recommended that DFID regional evaluation capacity building lead work together with DFID Uganda and the EvD PBR focal point to a) explore possibilities for capturing process lessons through an exploration of the theory of change; b) ensure additional technical questions raised during this process are incorporated. / In the financial year 2013/14 WB plans to undertake an impact evaluation of NUSAF2; it also plans to take a separate impact evaluation of its transparency, accountability and anti-corruption component of NUSAF2. / In addition, the programme team is considering together with the Regional Evaluation Adviser an impact evaluation of the ACCS and DGF sub-components of the programme.

4. Risk
4.1 Output Risk Rating: Medium / PCDP contains a set of risk categories against which the overall programme risk is determined and scored. An assessment of the main programme risks is contained in the table below. Also, there is detailed PCDP risk matrix which is monitored and updated every six months for the various components of the programme (See Annex Nine). / 4.2 Assessment of the risk level / Risk Status and mitigating action Rating / The absence of final peace agreement between LRA and the GoU and the likely return of the LRA in Uganda DFID has been monitoring the attitudes of both LRA and GoU through the Advisory Consortium on Conflict Sensitivity (ACCS), news media and regular LRA updates from the US government. LRA have not returned to northern Uganda. Low / Conflict emerges in northern Uganda ACCS conducted periodic conflict analysis of the various sub-regions and have been monitoring prevalence of conflicts across the region and providing early warning. While inter-communal conflict exists, as well as tensions over land and natural resources, the evidence suggests that a resumption of widespread conflict is high unlikely. Low / The uncertain status of peace, security and stability in South Sudan/DRC and Kenya leading to unstable northern Uganda. The region is relatively stable. Kenyan elections went peacefully and new political leadership sworn in. However, military coup in CentralAfricaRepublic has led to a halt in the Uganda People Defence Forces’ hunt for LRA leader and led to a rise in the tension between Government of Sudan and GoU with some medium risk that the Republic of South Sudan could be drawn into escalating tension between the governments of Uganda and Sudan. Low/Medium / Lack of political will within central government to support local government institutions For most of 2012 DFID engaged with central government through the PRDP Technical Working Group (PRDPTWG) and key local governments in northern Uganda to sustain political will for the recovery of the north. When misappropriation of donor funds meant to support recovery of northern Uganda came to light the matter raised questions about the political will of central government to fully support the recovery of the north. Also, as a result of donor funds misappropriation, DFID suspended all financial aid to GoU. Medium / Supplementary resources from GoU are inadequate and OPM does not use DFID funds for intended purposes DFID together with other Development Partners sought clarity onPRDP ‘additionality’ through PRDPTWG, which OPM provided but has been discredited by the corruption scandal. / When allegations of corruption within OPM emerged, DFID informed Counter Fraud Unitand commissioned a forensic audit of DFID funds within OPM. Subsequently, as a result of the findings of the Special Audit of OPM by Office of the Auditor General, DFID suspended financial aid to GoU. / Currently, DFID is considering new funding modalities for programme components that were being implemented through OPM. High / Failure of youth development programme to secure employment creates tensions and resentment The programme showed limited success in securing employment for trainees. Coupled with the suspension of financial aid to GoU, DFID is reviewing and redesigning the programme to improve livelihoods and train youth in skills relevant to labour market demands, including self-employment. Medium / Private investors do not respond to grants scheme due to fear of socio-economic tension and instability / Private investments does not create the intended socio-economic outcome / Grants scheme is politicised In the year under review, DFID engaged with PSFU to improve outreach across the region and to carry out due diligence on beneficiaries to avoid conflict of interests and undue influence by politicians on the programme. However, with aid suspension coupled with PSFU’s limited capacity for effective programme implementation, the programme has been suspended. The grants scheme will be passed on to a new service provider in 2013/14 to ensure greater technical competence in the area of financial deepening. Medium / Medium / Medium / Uganda Investment Authority (UIA) economic recovery analysis is inaccurate and misguides economic recovery When the quality of the first phase of the economic recovery analysis was unsatisfactory, DFID engaged OPM to terminate contract with UIA in 2012. The second phase of the work has been contracted to Oxford Economics through competitive bid. Work is progressing well. Medium / Building of houses for teachers and health workers causes health and environmental damage World Bank conducts a regular procurement audit of NUSAF2 sub-projects (during which time project implementation is halted) to ensure that proper procurement processes are followed. While regular audit process slows down project implementation, it minimises misuse of funds and ensures that good quality houses are built by professional contractors who follow national guidelines on building teachers and health workers. Low
Risk of funds not being used as intended / See above. DFID Uganda suspended funding to OPM and froze all outstanding balances in project accounts following allegations of corruption in August 2012 (Budget Support and all direct financial aid to other parts of government were also suspended in November 2012). The forensic audit which was subsequently carried out revealed that £1.3m of a total £9.5m disbursed to OPM since 2010 (£7.6 for PCDP) had been used for activities that were ineligible under the scope of DFID’s MoU with OPM. This money has been returned to DFID by GoU. / DFID will not return to a direct financial aid arrangement with OPM under this programme. However, in order to minimise the impact of this change on our direct beneficiaries, DFID is currently exploring ways of delivering the small business grant scheme and youth training components outside of GoU systems, by working with VSO and KPMG as the new service provider for the Financial Services programme. / Under NUSAF2 (World Bank), funds are transmitted to district bank accounts, and a limited proportion of the implementation budget is allocated to OPM. A review of third party funding to the GoU was undertaken in December, which found that the WB’s systems for managing the fiduciary risk associated with this system were robust, and that the risk of funds not being used for intended purposes was low. / Corruption in Uganda is judged to be widespread and not limited to the public sector. DFID needs to increase its vigilance in the monitoring of all programmes. All requests for payment are being scrutinised prior to any funds being disbursed; routine processes are being redoubled, including costs being compared with the original budget and work plan. In addition, DFID Uganda will carry out due diligence assessments of all new implementing partners of the components of the PCDP. Frequent field visits and solicitation of direct feedback from beneficiaries will also be important to guard against misappropriation of funds in future. / 4.4 Climate and Environment Risk / Interventions under NUSAF2, WFP Karamoja livelihoods and the grants scheme carry some environmental risks: / NUSAF2: Under this programme DFID funds the building of teachers’ and health workers’ houses. Construction of new housing can lead to poor sanitation if there are insufficient toilet facilities for the workers; land uptake; loss of vegetation; risk of soil erosion and runoff; management concerns over construction debris and poor restoration of material extraction sites; and risks associated with transportation of construction materials. / WFPKaramoja livelihoods programme: Through public works, improvements of public utilities such as community roads and dams have potential to cause soil erosion and loss of vegetation. Improved roads can also lead to increased vehicle speeds and higher concentrations of suspended soil particles and other pollutants associated with vehicular use while the construction of dams carried the risk of siltation. / PSFU Grants Scheme: A lot of the beneficiaries of the grants scheme are involved in the agricultural sector. The associated risks include: expansion of agricultural production to fragile ecosystems including wetlands and forest lands that then disturb ecosystems’ integrity through loss of vegetation cover; increased instances of slash and burn practices which reduce soil fertility and biodiversity; and concerns over the safe handling, usage and storage of agro-chemicals. Construction of agro-processing facilities also carry associated risks such as: noise from the equipment; vibration; waste management from livestock; pollution of water sources from agro-processing waste; and solid waste management concerns. Besides, poor management of the agro-processing facilities could result in environmental nuisances and public health hazards including an increase in pests as a result of poor storage; and increased use of non-biodegradable packaging materials. / DFID’s role in the environmental management of these components of the PCDP has been one of entering constructive dialogue with World Bank, WFP and Private Sector Foundation Uganda on the environmental impacts of interventions that they manage and the importance of environmental management and compliance with existing procedures. This matter is frequently raised during the visits of WB’s NUSAF2 mission and reflected in the Aide Memoire. WB’s and WFP’s environmental management procedures are sufficiently rigorous to ensure that the environmental risks of programmes that they manage are sufficiently mitigated and managed in accordance with Ugandan environmental legislation and construction standards. PSFU environmental procedures were less systematic and less rigorous. The inconsistency of PSFU in this respect has been due to its lack of capacity to provide oversight and ensure systematically environmental assessment for all grants applications. This issue grants scheme applicants working in adherence with national environmental requirements will be carried forward once the management of the grants scheme is passed on to KPMG as the new service provider of the Financial Services programme.

5. Value for Money
5.1 Performance on VfM measures / The original programme memorandum made the assumption that the total investment of £100m would deliver economic benefits worth 2.5 times the cost of the programme, based on the following assumptions: / Improvements to health and education outcomes due to construction of health workers and schoolteachers houses / Improvements to governance conditions (reduced leakage through corruption) / Jobs created through private sector grant scheme / Increased employability and opportunities for young people / Social support provided to the extremely vulnerable / Without revisiting the detailed cost benefit analysis it is clear that some of these assumptions have changed, whilst others remain valid. / On A – improvements to health and education – this assumption still stands, but will be thoroughly assessed as part of the World Bank’s June 2012 Mid Term review of the NUSAF2 project. The review will test the assumption that increasing the number of houses for health workers and school teachers really does result in improved health and education outcomes. On work with PNFPs the programme team together with PrG are re-negotiating the overall cost of the component which should increase its VfM. / On B – improved governance conditions - the recent OPM corruption scandal has thrown into sharp relief the endemic nature of corruption in the public sector, and the ability of corruption to undermine wider development efforts. In the original programme memorandum, it was envisaged that DFID would contribute to building capacity both of local government (through the ULGA programme) and of central government (through contributions to PRDP2 sector budget support and provision of technical assistance through PWC). Following a revision to the programme in June 2011, it was decided that sector budget support to PRDP2 would not be provided until 2013/14. The ULGA project also received a qualified opinion on its recent audit and DFID is exploring options for taking forward its work with local government. / In hindsight, it can be seen that the approach taken in this case was too risky and that insufficient controls were in place to guard against corruption. As such OPM officials were able to misappropriate around £1.3m of the £9.5m provided to OPM, of which £7.6m was for PCDP, between 2010 and 2012. In light of the scandal DFID will not go ahead with the plans to provide sector budget support to PRDP2. / However, there is quantitative and qualitative evidence that the technical assistance DFID supported at local level (through ULGA) did make a significant impact in improving governance, government performance and management of finances (in the case of local government). The Technical Assistance given through ULGA, at just over £400,000 for three years, provided hands on support to lower district governments in financial management, for example through the Output Based Budget Tool. This tool has led to timely budgeting and development of local government plans, procurement plans and activities. / On C – jobs created - the original assumption in the programme memorandum was that the grant scheme would create 9,800 jobs over five years. In this review, PSFU has to date approved grants leading to the creation of a total of 2004 jobs. Given PSFU expenditure to date is around 25% of the original allocation, this assumption is arguably still valid and as such this component still represents value for money in line with the criteria in the original programme memorandum. In addition, we envisage that over the next two years VSO youth training programme will provide the pathway for 11,000 young women and men (50% female) to find decent jobs (including through self-employment) at a cost of £7.6m. Also through youth entrepreneurship programme through Youth Business International we envisage creating and/or expanding 5000 youth and family-owned enterprises, of which 1,000 enterprises would create an additional job at a cost of £2.5m over two years. Furthermore, the plan with KPMG over the next two years is that KPMG would carry out a rapid assessment of the grants scheme model in order to determine if it is a good model for creating businesses and jobs and then revise and refine the model appropriately, including the decision whether or not PSFU can play a role within the revised model. / On D – increased opportunities for young people. The assumption in the PCDP revised submission to SoS in 2011 was that 100,000 young people would receive vocational training at a cost of £12.5m, roughly £125 per student. Expenditure by NUYDC to date amounts to £2.5m, whilst 16,894 young people have received training. Notably, training through VTIs was on track on costs while it was moderately above originally envisaged costs for NUYDC. Overall, the cost of delivering training to each student over the last two years was £148. The high cost of delivering training was particularly driven by the more labour and resource-intensive nature of the training provided (residential courses, lasting between 1 – 2 years) at NUYDC. However, value for money for the more intensive residential courses offered by NUYDC vis-à-vis the shorter term courses offered by the other VTIs is difficult to determine without statistically significant data on employment patterns among graduates as NUYDC was unable to develop a graduate tracking system. The reprogramming and future delivery of the youth development programme through VSO and YBI/Enterprise Uganda will make it possible for us to determine value for money for the programme within the next two years through the graduates tracking systems that will be developed. / E – social support to the most vulnerable - this assumption, which relates to the work undertaken by UNHCR to resettle extremely vulnerable individuals and persons with special needs from IDP camps back into their communities and improving access to income-generating opportunities to moderately insecure households in Karamoja, remains unchanged. / 5.2 Commercial Improvement and Value for Money / Overall, in 2012 DFID disbursed PCDP funds on the basis of approved and detailed costed work plans with clear results indicators and targets. Regular monitoring trips were also carried out to ensure that programme components continue to deliver the envisage results at set costs. / Early in 2012 all PCDP implementing partners attended the DFID financial management workshop with a view to improving financial management and oversight and improving value for money. / DFID has followed open competition principles in all procurement processes within the PCDP. All contract opportunities under the WFPKaramoja livelihoods programme, WB NUSAF2 programme and youth development programmes were advertised, following which submitted bids were evaluated and contracts issued on competitive basis. WFP and WB used their own procurement procedures while NUYDC used GoU procurement procedures. / Under the grants scheme, all applicants submitted at least three invoices from different service providers for the kinds of equipment and/or services that they wanted grants support. PSFU then chose the service provider that they then asked to supply some particular equipment or service to support some business enterprise. Through regular meetings with DFID PSFU informed us that they made their choice of service providers basing on costs and quality of equipment that a supplier could offer. However, we did not independently verify this fact. / In the first half of 2012, the contract with the Uganda Investment Authority for the economic recovery analysis of the north, while being delivered through approved work plans and budget, was terminated because the product delivered was not of high quality and did not offer good value for money. / During the second half of 2012, amidst OPM corruption scandal and in the absence of functional Steering Committee OPM released some DFID funds to NUYDC and PSFU without seeking approval of DFID. The DFID Uganda commissioned forensic audit revealed that OPM oversight controls of DFID funds were deficient. The findings of the forensic audit showed that there was no evidence of deliberate and large scale misappropriation of funds by PSFU but that NUYDC’s accountability for DFID funds did add not up or contained questionable transactions. As well as repaying the £1.3 million misappropriated funds, the GoU has agreed to refund all unspent balances of UK aid on OPM accounts, with £2.2m expected to be returned in August 2013. / It is worth noting that during the course of 2012 the contract with HPI/Montrose to implement the PNFP programme increased from £6.5m to £10.5m. The reason cited for the increase was the unexpectedly complex nature of the programme (which was amended to include a control group, in order to allow a robust impact evaluation of results based financing to take place) as well as the lower than expected capacity of the PNFPs in Northern Uganda. Together with the Procurement Group programme team is making efforts now to reduce the value of this contract whilst retaining the expected results. / 5.3 Role of project partners / PCDP is a complex programme involving several partners. / DFID Uganda: Is responsible for overall management of the programme and for reporting on outputs and impact, but specific components of programme delivery are outsourced to the GoU, NGOs and technical assistance providers. The responsibility to manage fiduciary risk sits with DFID Uganda. / Office of the Prime Minister (OPM): Managed disbursements of funds according to approved work plans and budgets to youth development and the business grant scheme components of the programme. OPM NUSAF2 directorate also implements the World Bank NUSAF2 programme following WB procurement processes and contracting procedures. However, the findings of the DFID commissioned forensic audit show that OPM oversight controls over PCDP funds were deficient. The forensic audit also questioned the value added by channelling DFID funding for PSFU and NUYDC through OPM. While the forensic audit report showed that PSFU did not misuse DFID funds, it revealed that NUYDC exhibited poor financial records and documentation, price inflations and its accountabilities often did not add up or contained questionable transactions. Financial aid to OPM has been suspended. / Private Sector Foundation Uganda (PSFU): PSFU conducted outreach activities and also received, assessed, approved and provided funds for approved applications for the grant scheme. Applications were required to include quotes from three different suppliers. PSFU also monitored implementation of agreed activities under the grants scheme. The findings of the forensic show that with PSFU there was no evidence of deliberate and large scale misappropriation of funds by PSFU. However, it is clear that PSFU did not do enough in terms of monitoring to ensure assets bought with grant funds were functional and being used for the originally envisaged purpose. In addition, whilst PSFU has done an adequate job of outreach and publicity for the grant scheme, it lacks the commercial expertise and knowledge of the market to make strategic decisions about investments. For this reason management of the grant scheme will be rolled into the upcoming Financial Services Programme. / Northern Uganda Youth Development Centre (NUYDC): previously responsible for implementation of the youth development plan. Awarded contracts to network of 42 training institutions through a competitive bidding process. However, as the forensic audit revealed, NUYDC had poor financial reporting and documentation, price inflation and offered poor accountabilities for funds used. NUYDC was previously supported by a team of advisers from Maxwell Stamp; this contract has now elapsed. Following the annual review the decision was taken not to renew the contract with Maxwell Stamp, but to source advisory and support services from VSO, who provide better value for money through the use of experienced volunteers. / PriceWaterhouseCoopers (PWC): Provided technical support to PS OPM in order to strengthen PRDP and PCDP coordination. PWC technical assistance to PS OPM ended with the suspension of financial aid to GoU. / World Food Programme (WFP): responsible for delivering the NUSAF2 programme in Karamoja. Used a range of implementing partners to deliver the programme, including national and international NGOs. Previous DFID Internal Audit questioned the high overhead cost of the programme – this issue is being addressed in the continuation of the programme being funded through the ICF. / Uganda Local Government Association (ULGA): Provided good technical support to the district resource pools of Gulu and Lira districts. While ULGA showed strong technical competency, their internal financial management systems were found to be weak in the review of third party financial aid. A subsequent audit of project accounts within ULGA received qualified opinion. As a result DFID has opted to fund the TA to Gulu and Lira districts directly, rather than renewing our partnership with ULGA. / World Bank (WB): responsible for construction of health workers and schoolteachers’ houses. WB uses its own procurement processes and contracting procedures for NUSAF2 project implementation, to guard against financial impropriety. / Advisory Consortium on Conflict-Sensitivity (ACCS): DFID disburses funds in advance to the consortium after a thorough scrutiny of its budget lines and agreed work plans. DFID needs to continue to monitor the Consortium closely to ensure the use of funds is in line with the objectives set out in the ACCS log-frame. / Democratic Governance Facility (DGF):DGF uses partner agreements and calls for proposal to choose implementing partners for various programmes. DGF also conducts robust financial and management checks before beginning effective engagement with civil society organisations and GoU agencies. DGF disburses funds according to agreed work plans and budgets. / Health Partners International/Montrose: implements the results-based financing pilot involving 31 PNFPs in Acholi and Lango sub-regions. Management costs have escalated since the programme was designed, and now represent almost 40% of project costs. This is largely due to the experimental nature of the project, which involves separate arrangements for an “intervention” and a “control” group, as well as the cost of seconding 10 health officials to the district health teams. The milestones and pricing for this contract are currently being reviewed with a view to securing better value for money for DFID. / 5.4 Does the project still represent Value for Money : Y/N / Performance on VfM measures, as set out in Section 5.1 above, is mixed. / On jobs created and support for the most vulnerable, the project provided livelihood and economic opportunities through public works programme to 77,360 moderately food insecure households in Karamoja through WFP livelihoods programme and supported the return of 3500 extremely vulnerable individuals into communities in the north. On youth, 16,894 youth were trained at the costs moderately higher than originally envisaged. This was particularly so because of the more labour and resource-intensive nature of the training provided (residential courses, lasting between 1 – 2 years) at NUYDC. Value for money for the more intensive residential courses offered by NUYDC vis-à-vis the shorter term courses offered by the other VTIs is difficult to determine without statistically significant data on employment patterns among graduates as NUYDC was unable to develop a graduate tracking system / On improved health and education outcomes, although the outputs from the World Bank NUSAF2 component will likely meet set targets, more work needs to be done to ensure that the original assumptions in the programme memorandum about additional housing for health workers and teachers resulting in improved health and education outcomes are still valid. / On governance and corruption, the assumption that channelling resources through GoU systems will enhance governance and reduce leakage through corruption is flawed. However, the investments DFID made through the TA provided to local government through ULGA did have a significant impact on improving government’s ability to deliver programmes and services and represent good value for money. Although these improvements are difficult to reflect in quantitative VfM measures, we believe the provision of TA did represent good value for money. / 5.5 If not, what action will you take? / We are now looking critically at all the components of the PCDP – in particular those previously delivered through OPM – with two aims. The first aim is to improve development outcomes and the value for money of the programme as a whole and the second related aim is to simplify and streamline programme management arrangements in order to reduce transaction costs for DFID Uganda and to improve the effectiveness of DFID’s oversight over the various components of the programme. This will involve looking anew at the theory of change behind the various components and assessing whether original assumptions (e.g. that channelling funds through GoU systems will help to improve those systems) are still valid, as well as assessing how to streamline and simplify delivery channels. / The recent OPM corruption scandal will necessitate reprogramming to ensure delivery of the private sector grant scheme and youth development plan outside of GoU channels. We believe that moving the management of the grant scheme into the Financial Services Programme, under the management of KPMG, will ensure that grants are more targeted to the growth needs of the north, and that all applications are assessed through a more commercial lens. Similarly, contracting VSO to take on management of the youth development plan represents better value for money than under the previous arrangement, not only on account of leakage through NUYDC due to corruption, but also the fact that the previous technical assistance being provided through Maxwell Stamp amounted to just under £400,000 a year for 2 full time and one part time advisers, whilst VSO is providing volunteers at a cost of around £20,000 per year. / We will also press the World Bank to undertake analysis to confirm that the health workers and teachers’ houses are having an impact on health and education outcomes. / In addition, we will continue to find ways to reduce the implementation costs of the PNFP programme, working closely with Procurement Group. / Due diligence assessments will be carried out on all new implementing partners that will carry forward the components of PCDP.

6. Conditionality
6.1 Update on specific conditions / PCDP conditionality is restricted to GoU compliance with Development Partnership Arrangement (DPA) commitments to poverty reduction, protection of human rights and improved financial management and accountability. This conditionality is attached to the delivery of components of the programme through the GoU systems. / These conditions have remained the same and over the last year, GoU exhibited poor financial management and accountability as evidenced by the findings of Auditor General’s Special Audit of the OPM and of the DFID’s commissioned forensic audit of the DFID funds within OPM which showed that DFID funds were misused. GoU noncompliance with improved financial management and accountability led to DFID Uganda and nine other donors to suspend budget support and/orall financial aid to GoU, which decision led to the suspension of the youth development and grants scheme programmes that were being implemented through OPM. Currently, these programmes are being re-programmed to be implemented outside of GoU institutions.

7. Conclusions and actions
Since the 2011 Annual Review various components of the PCDP made modest progress, except for components being managed by OPM, which were critical to the overall delivery of the programme. / The outcome of PCDP could not be assessed because relevant data are not accessible. When the programme was originally conceived it was anticipated that the data for outcome indicators would be available and accessible on an annual basis with the start of programme implementation. Moving forward, the outcome indicators urgently need to be revised and replaced with alternative indicators from relevant component of the programme. / The 2012 OPM corruption scandal posed a significant risk, both fiduciary and political, to PCDP implementation during the review period. Political risks associated with OPM corruption scandal will need to be monitored in the next financial year. / With two years left, components of the programme that will continue include: NUSAF2, Northern Uganda health programme with PNFPs, youth development programme, DGF, ACCS, and the strengthening the capacity of local governments in the north. The following actions are recommended for simplifying the management and improving the performance of PCDP implementation: / Simplification and restructuring of DFID’s support to northern Uganda. The context in northern Uganda has changed significantly since this programme was designed. The region has moved from post conflict recovery towards development. While DFID needs to retain a clear focus on northern Uganda, programme design, delivery and monitoring will be more effectively undertaken through the structure of DFID Uganda’s three teams – Governance, Growth and the MDGs. This should simplify our approach to northern Uganda, rationalise our engagement and clearly link programme objectives to team priorities. This approach should also strengthen ownership of programmes by the lead advisers in each of the three teams. Responsibility: Senior Management Team. / Log frames. PCDP log frame indicators and milestones impact indicator dates need to be reviewed in order to align them with the years when relevant data become available. Log frame Indicators relating to PNFPs, NUSAF2, youth development programme, grants scheme programme, and DGF need to be revised and aligned to the specific results that the programme components can deliver. Also, the individual log frames of all the different components of the PCDP needs to be aligned with the PCDP log frame. The logframe will be revised by July 31st 2013 Responsibility: Recovery Adviser / Theory of Change. Theories of change of the six remaining components of the PCDP need to be reviewed by 31st July 2013 in light of the changed context of northern Uganda from emergency to recovery to long term development and programme adapted accordingly. Responsibility: lead advisers. / Financial Management. Where possible, DFID Uganda to amend signed MoUs to include quarterly financial and narrative reporting. Also, DFID needs to scrutinise financial and narrative reports from implementing partners to ensure that funds are spent on approved work plans and that accountabilities are consistent with agreed work plans. Responsibility: programme officer. / Monitoring. During monitoring visits DFID programme staff should interact more with beneficiaries to ensure DFID visibility (more so for reprogrammed components) while avoiding getting involved in day to day management of programmes. Increased interactions with beneficiaries might help identify risks in time. Also, component leads should update the office on progress on regular basis. Responsibility: lead advisers and programme officers. / Grants Scheme and Financial Services Programme. Since the service provider of the financial services programme is to carry forward the grants scheme programme, it is important that the grants scheme and financial services programme are carefully sequenced. This is because the same beneficiaries of the grants scheme are likely to be the key players for the financial services programme. Responsibility: DFID economist. / Work with Local Governments. DFID to consider scaling up the programme as the capacity of local governments across northern Uganda is lower than that of their counterparts in the rest of the country. The low capacity of local governments is affecting the quality of service delivery in the north. Responsibility: Governance adviser and Recovery adviser. / Conflict Sensitivity work. The consortium work to be refocused in light of the peace and conflict indicators and conflict analysis reports. Prioritised work should include work on land because the land question is likely to affect the grants scheme and financial services programme as well as the effectiveness of youth development programme in northern Uganda. Responsibility: Recovery adviser

8. Review Process
Every component of the PCDP was reviewed separately and in detail given that the 2012 Annual Review took place midway into the programme implementation. Different teams led the AR of different components of the PCDP. As a result, the AR of the programme lasted over six months. / As the Annual Review was taking place, OPM corruption scandal broke out and this led to suspension of financial aid to Government of Uganda. This suspension affected especially components of the PCDP programme that were being implemented through OPM. Currently, DFID Uganda is reprogramming these programmes so that they may continue to deliver their intended results. Some of the recommendations in the Annual Review incorporate these later developments associated with misappropriation of donor funds within the Office of the Prime Minister.

## Annex on PCDP Spend from 2009-2012

	2009/10	2010/11	2011/12	2012/13	2013/14	2014/15	2015/16	Total	Total allocation	Previous allocation (June 2011)	Change
Output 1 - Local Government Capacity
NUSAF2	£4,000,000	£15,000,000	£0	£0	£5,000,000	£0	£0	£24,000,000	£24,000,000	£24,000,000	£0
ULGA	£0	£140,091	£174,677	£102,655	£50,000	£50,000	£0	£517,423	£1,034,846	£450,000	£584,846
PRDP 2 Budget support	£0	£0	£0	£0	£0	£0	£0	£0	£0	£7,500,000	-£7,500,000
Sub-total									£24,517,423	£31,530,000	-£7,012,577

Output 2 - Support to Vulnerable Communities
UNHCR	£3,720,000	£2,000,000	£0	£0	£0	£0	£0	£5,720,000	£5,720,000	£5,720,000	£0
WFP	£0	£6,000,000	£6,000,000	£2,000,000	£0	£0	£0	£14,000,000	£14,000,000	£12,000,000	£2,000,000
PNFPs	£0	£0	£193,252	£2,237,182	£3,453,560	£3,896,837	£0	£9,780,831	£9,780,831	£7,500,000	£2,280,831
Nodding syndrome	£0	£0	£0	£60,000	£0	£0	£0	£60,000	£60,000	£0	£60,000
Sub-total									£29,560,831	£27,220,000	£2,340,831

Output 3 - Private Sector Revitalised
PSFU grant scheme*	£0	£2,000,000	£2,500,000	£2,000,000	£1,400,000	£0	£0	£7,900,000	£7,900,000	£16,000,000	-£8,100,000
Youth programme	£0	£1,702,727	£408,433	£670,682	£5,025,441	£5,518,388	£0	£13,325,671	£13,325,671	£16,000,000	-£2,674,329
Economic Recovery Analysis*	£0	£1,000,000	£500,000	£202,917	£100,000			£1,802,917	£1,802,917	£2,000,000	-£197,083
Sub-total									£23,028,588	£34,000,000	-£10,971,413

Output 4 - Peace & Reconciliation
ACCS	£0	£265,754	£565,194	£608,441	£700,000	£784,052	£0	£2,923,441	£2,923,441	£2,000,000	£923,441
DGF	£0	£0	£600,000	£500,000	£2,600,000	£2,735,000	£2,150,000	£8,585,000	£8,585,000	£3,850,000	£4,735,000
Sub-total									£11,508,441	£5,850,000	£5,658,441

Advisory Support, Research and Evaluation	£0	£90,861	£459,552	£474,583	£100,000	£100,000	£159,721	£1,384,717	£1,384,717	£1,029,000	£355,717
Total								£90,000,000		£100,000,000	£10,000,001

*On ERA, UIA received a total of £445,000 for the first phase of the ERA report. £202,000 was returned to OPM at the end of the project (and subsequently to DFID, in the April 2013 repayment), and the remainder of the £1.5m was paid to NUYDC.
*On PSFU, funds for 2013/14 are to meet outstanding liabilities only